P092786 | Human Capital Technical Assistance (SIDEM APL #1) | Europe and Central Asia | Slovak Republic |  | Non-FCS | Human Development | Education | IBRD | IPF | 2005 | 2009 | 2010 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/979721474492349058/text/000020051-20140620073647.txt | http://documents.worldbank.org/curated/en/979721474492349058/pdf/000020051-20140620073647.pdf | The following lessons can be put forward: Designing a Project that depends on the permanence and commitment of a handful of high level individuals is a high risk proposition. More work up front, and where that is not possible, early on in implementation, to build support for the Project at the technical level would have resulted in greater ownership and deeper commitment, even under circumstances when original Project advocates were replaced. Technical assistance projects are inherently difficult to assess, making it particularly important that objectives be unambiguously stated and that M&E systems be carefully and expertly designed and implemented. This was not a part of HCTA preparation, making it difficult to show achievement of objectives during and at the end of implementation. The amount of the loan for the HCTA project was probably adequate for the actual tasks, but not enough to catch and hold the interest of Ministers once the original Project champions had moved on. Also, the fact that the Project was not incremental to regular ministry budgets further reduced interest. If it had been possible to decentralize the project steering committee to a lower level (perhaps to department heads), the given amount of money might have been enough to galvanize attention and build lasting commitment.In a country and region with increased funding options, the traditional Bank project model did not work well. Traditional Bank investment projects carry many processing requirements and transaction costs. In regions like Eastern Europe, new funding sources (EU) with fewer strings attached are becoming available, and this means that ministries can turn to other sources to fund their technical assistance needs. Under such circumstances motivation to seek or implement conventional Bank projects becomes less pressing. Building a regional IBRD program of technical assistance around the strong proposal of a single country (and planning to expand to other countries through a horizontal APL) proved to be nonviable, as commitment in the original country waned and no other countries submitted proposals. A more appropriate model would have been for the vanguard country and program to be seen as a pilot for the regional concept, with expansion following the pilot's success and lessons learned.
P092836 | Institutional Strengthening - ANSES II TA | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2006 | 2013 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/582111474665556320/text/000020051-20140626105723.txt | http://documents.worldbank.org/curated/en/582111474665556320/pdf/000020051-20140626105723.pdf | The four main lessons learned from the implementation of the Argentina ANSES II are:1. The desire for flexibility should not come at the cost of ensuring key conditions for project success. Given the difficult and ever changing circumstances facing member countries, there is a need for the Bank to be flexible regarding project design and implementation. In the case of ANSES II, Bank management granted a partial waiver on the condition for effectiveness regarding the creation of the Steering Committee. While the waiver may have been viewed as necessary to expedite loan effectiveness, its impact on overall project implementation (particularly regarding Component 2) could have been confronted and addressed prior to effectiveness. 2. Analysis of political and bureaucratic factors can ensure better project outcomes. Ex ante political economic analyses are critical to effective project design and successful project implementation. The tensions and differences of view between the two implementing bodies (ANSES and the SSS) were well known and ultimately proved problematic for project implementation. The project would have therefore benefited from a deeper analysis of the political factors complicating inter-agency coordination. 3. Adjustments to project indicators and targets should be formalized in the context of mid-term reviews and/or restructurings. It is inevitable that performance indicators may need to respond to changes in program activities and circumstances. The Bank revised several indicators and targets in response to changes in project activities arising from strategy and technological changes at ANSES. The lack of formalizing these changes undermined project monitoring and assessment relative to the RF specified in the PAD. 4. Effective coordination mechanisms are needed to facilitate cooperation when institutional responsibilities overlap and service delivery is segmented. Political buy-in and ownership is critical to any reform effort. Such buy-in becomes even more important when there are multiple agencies involved in and critical to project implementation. The lack of coordination and collaboration by the key agencies involved in project implementation therefore impeded satisfactory project implementation. Efforts need to be redoubled at the design stage and prior to project effectiveness to ensure that broad-based support is in place, including through the inclusion of an inter-agency steering committee as originally proposed.
P092837 | UGANDA TRANSPORT SECTOR DEVELOPMENT PROJECT | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2010 | 2016 | 2018 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/497451512576968297/text/ICRR-Disclosable-P092837-12-06-2017-1512576945345.txt | http://documents.worldbank.org/curated/en/497451512576968297/pdf/ICRR-Disclosable-P092837-12-06-2017-1512576945345.pdf | Of the nine lessons listed in the ICR from the experience of implementing this project,the following seven lessons are themost important,with some adaptation of language.(1) New transport agencies should only be established whentheres sound understanding of the financial, legal and political implications of such initiatives. There needs to besufficient capacity in place to ensure the necessary stakeholder buy in, financial clearance from the appropriate financialministryandsuitable legislation. Envisioning establishment offour new agencies for covering road safety,metropolitan transport, multi-sector transport regulation and district urban and community access roads as done in the case of thisproject was unrealistic particularly given the project time lines and the absorptive capacity of the Ministry of Works andTransport to implement such initiatives.(2). Reform initiatives and capacity buildingare as important asphysical investment components in transport sector projects. In the case of this project, although project activitiesaimed atsector reforms, the focus of the project was more on physical construction progress once contracts had been awardedand not so much on the softer components of the projected. This contributed to the undermining of these aspects of projectactivities.(3) Whencapacity of the implementing agency is low, it would be prudent to focus on fewerbut more focused activities. In the case of this project, there were simply too many activities, particularlygiventhe capacity of the implementing agencies.(4) In complex projects, a thorough assessment of all aspectsrelating to the implementing agencys capacity including safeguards is essential, with credible measures to address theidentified weakness. In large infrastructure projects, the Bank needs to ensure that sufficient contract capacity is inplace before implementation commences and that qualifiedenvironmental safeguards staff are assigned to the project, or ifthis is not likely, that alternative arrangements are madefor greater implementation oversight.(5). When thescope of a project is expanded substantially, a thorough review of safeguards implementation of the new components needs to beundertaken. In some cases, the revised project should not necessarily be given the same environmental classification asthe parent project. In this project, the circumstances associated with the added road were much more complex than the ones in theoriginal project and an environmental category A recognizing potentially significant adverse impacts, should have beendesignated.(6) Failure to put in place robust community engagement processes can weaken the Banks ability toanticipate potential social impacts and respond appropriately when problems arise during implementation. In this project,no grievance redress mechanism was in place or partnerships with Non Governmental Organizations (NGOs) that could assist inunderstanding and resolving sensitive local issues.(7). The World Bank staff skills and capacity need to match therisk and complexity of the anticipated operations. In the case of this project, the Bank over-reliedon newly hiredsafeguard staff who had received limited support from others in the region and from headquarters. Until after the Inspection Panelcompliantwas received, there was no deployment of staff with the right skills to address systemic social risks or to engagethe communities.
P092898 | Performance Results and Accountability Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2008 | 2013 | 2014 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/965541474897591461/text/000020051-20140626114439.txt | http://documents.worldbank.org/curated/en/965541474897591461/pdf/000020051-20140626114439.pdf | The main lessons that can be drawn from the experience of this project are:Learning from experience needs to be enhanced, as several of the problems that affected project performance were not new or unforeseeable when the project was designed.Complexity and excessive ambition should be easy to detect at project entry. There must be a stronger focus on avoiding costly mistakes by applying a more rigorous screening during preparation.A rigorous assessment of political economy risks is needed for any support to ambitious civil service reform programs. The result chain linking government performance and service delivery must be thoroughly understood, particularly as far as decentralization is concerned.Regional management decisions should consider that poor performance could be linked to a conscious decision to tackle difficult issues. Failure in this regard should not be measured simply in terms of pace of disbursement, and be better coordinated with development partners.
P092944 | Second Poverty Reduction Strategy Credit | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2006 | 2007 | 2009 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/557261474635355472/text/000020051-20140619090207.txt | http://documents.worldbank.org/curated/en/557261474635355472/pdf/000020051-20140619090207.pdf | The ICR contains good lessons from the experience with DPLs in Rwanda, three of which stand out.General budget support can be much more effective than individual projects in promoting better resource allocation among and within sectors as well as in promoting appropriate sector strategies and policy reform.Continuous dialogue and continuity in Bank teams are essential for success.Coordination and harmonization with other donors and their policies is greatly enhanced by joint analytical work.
P092965 | Information and Communications Infrastructure Development Project | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2006 | 2013 | 2015 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/931581468190185393/text/ICRR14634-P092965-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/931581468190185393/pdf/ICRR14634-P092965-Box393183B-PUBLIC.pdf | The experience of this project highlights four key factors that contribute to the successful implementation of private sector participation in the ICT sector: (i) Credible stakeholder consultation prior to appraisal to gauge interest from potential operators and to design a practical approach to providing access in rural areas; (ii) World Bank's up front contribution of $5 million as ready seed money for the Universal Service Obligation Fund, and the capital subsidies in an already proven output-based aid approach helped attract the private sector;(iii) The time it takes to introduce E-Government should not be underestimated. In the case of Mongolia, identification of target services and beneficiary agencies should have been done up front to avoid delays or eventual cancellations; (iv) Standard bidding documents readily understood by potential private sector partners help speed up procurement - these were not available for public private partnerships in e-Government, causing delays.
P092986 | GH-Economic Management Cap. Bldg. Proj. | Western and Central Africa | Ghana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2006 | 2013 | 2014 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/348871475070873449/text/000020051-20140626122426.txt | http://documents.worldbank.org/curated/en/348871475070873449/pdf/Ghana-Economic-Management-Capacity-Building-Project.pdf | The lessons drawn in the ICR are generally appropriate. Among them:Â· Synergy among the parts of the project helps improve outcomes;Â· A project predicated on low capacity needs to avoid overtaxing that capacity with excessive complexity;Â· Quality assurance is an ongoing activity, not one-off task;Â· Project ownership needs to be broadly-based;In addition, experience in capacity building might suggest that:Capacity development may -- and often does -- take longer than expected;Self assessments among implementing agencies can help improve results;Strict adherence to pre-determined goals may be counter-productive to the acquisition of capacity.
P092990 | BR - Road Transport Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2006 | 2013 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/755551475113944880/text/000180307-20141203050048.txt | http://documents.worldbank.org/curated/en/755551475113944880/pdf/000180307-20141203050048.pdf | The ICR draws the following lessons from the experience of preparing and implementing this project.(1) It is always important to take into account country context while designing innovative projects. The results of this project demonstrate that innovative projects need to be tried in mature economies.(2) "Crisis" conditions can provide a strong incentive for adopting new paradigms, but care needs to be taken that the client may not have sustained interest once the crisis subsides. The rather poor state of the road infrastructure situation in Brazil provided strong incentives for the government and the central ministries to adopt new measures- such as the performance based contracts.(3) A clear articulation of project development objective is necessary to design the proper choice of M&E indicators, and thereby gauge how much of the achievement of the project development objective could be attributed to the project.
P092999 | Bor Regional Development Project | Europe and Central Asia | Serbia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2007 | 2015 | 2017 | ICRR | >=10 million & <25 million | Highly Unsatisfactory | Highly Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/264421471039043736/text/ICRR0020092-REVISED-PUBLIC-Final-ICRR-P092999.txt | http://documents.worldbank.org/curated/en/264421471039043736/pdf/ICRR0020092-REVISED-PUBLIC-Final-ICRR-P092999.pdf | 1. The formulation and achievement of the development objectives suffer when no sound economic analysis of the issues,accompanied by in-depth consultations, is undertaken at the concept stage (or before). In this case, an opportunity to providesupport tothe Government in relation to the revival of the Bor region and to the restructuring of the SOE was lost. Theassumption of similarity to coal mine closures proved erroneous, and the option of restructuring and modernizing the SOE (afterprivatization was cancelled) which actually occurred was not fully considered.2.A complex structure of components that do not complement or support each other and require very different expertise andimplementation speed,carries a high risk of implementation failure. This project attempted to combine an environmentalemergency operation, technical assistance to address weak government capacity, and a series of activities aimed at private sectordevelopment.3. Multiagency projects in a situation of low Government capacity, limitedcoordination,and insufficient Governmentownership are likely to be unsuccessful.4.Implementation capacity, including the requisite level of technical expertise, is critical and the lack of it may jeopardize theentire project.5. When circumstances change during project implementation in such a way that the projectbecomes irrelevant,speedy action can save undue further expenditure of Bank and Borrower resources.
P093050 | Registration Project | Europe and Central Asia | Russian Federation | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2006 | 2016 | 2017 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/731821485212790080/text/ICRR-Disclosable-P093050-01-23-2017-1485212779602.txt | http://documents.worldbank.org/curated/en/731821485212790080/pdf/ICRR-Disclosable-P093050-01-23-2017-1485212779602.pdf | The ICR draws the following main lessons from implementing this project with some adjustment of language.1.Political engagement coming from the highest levels of government, backed by resources, and holding managers responsible cancontribute greatly to the success of a project. In the case of this project, government leadership was supportive,putting a lot of responsibility on managers and providing the necessary resources to reach targets.2. Slowdisbursement is not necessarily a sign of poor performance where external factors such as a substantial institutionalreorganization is undertaken with benefits for longer-term institutional development.In this case, the restructuring andthe creation of a unified agency, while initially disruptive,led to a more sustainable framework for the longerterm.3. In the development of immovable property registration systems,substantive andsustainedcollaboration between borrower specialists, the World Bank and FAO can be very useful for assembling and adaptingglobal learning, particularly since such projects involve tailoring complex computerized management systems to local realities onthe ground.In this case, the fruitful collaboration between the specialists from Rosreestr, the World Bank and the FAOproved particularly useful foradaptinginternational experience.
P093096 | SOCIAL INCLUSION PROJECT | Europe and Central Asia | Romania | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2006 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/325771468179353555/text/ICRR14761-P093096-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/325771468179353555/pdf/ICRR14761-P093096-Box393191B-PUBLIC.pdf | Lessons drawn from the ICR:A rigorous assessment of organizational and institutional capacities is critical at preparation and prior to implementation. This allows designers to properly calibrate project objectives, activities, and responsibilities, and establish realistic implementation schedulesCoordination mechanisms need to be considered when multiple agencies are involved in project implementation. This may be particularly important for social inclusion programs, which tend to operate in a context of fragmented approaches, across sectors, and include a range of different interventions, diverse actors and differing institutional arrangements. Capturing how activities ultimately contribute to social inclusion is essential in the design of social inclusion projects. Construction and rehabilitation of facilities and training of providers â€“ often the core of social inclusion action â€“ are of course key to providing services. Yet, they do not represent the full measure of social inclusion and empowerment. Results frameworks would need to capture and measure what was built, but also how assets contribute to and translated into enhanced inclusion and well-being.
P093132 | LK Dam Safety and Water Resources Planning (DSWRPP) | South Asia | Sri Lanka | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2008 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/305801548996963070/text/Sri-Lanka-LK-Dam-Safety-Water-Resources-Planning.txt | http://documents.worldbank.org/curated/en/305801548996963070/pdf/Sri-Lanka-LK-Dam-Safety-Water-Resources-Planning.pdf | The ICR (pages 24-25) draws six lessons from the experience of implementing this project. Some of the lessons were focused onthe details of issues facing Sri Lankawithout broad relevance to Bank operations in general. IEGconsidered that twomost important lessons with relevance beyond this project(with some modification of language) wereas follows:(1) The projectdesign chosenat appraisal needs to be tailored to the projectsobjectives. Despite strong government ownership and commitment, this project fell short in not establishing the NationalCenter for Dam Safety. The shortfall ofthis important objectivereflected thedifficulty of supporting policy andinstitutional reforms through a conventional investment project design.(2)This project demonstrated theimportance of critical importance of capacity building ofimplementing agencies, if implementing agencies are to beusedfor facilitating project implementation.In this project, followingaCabinet decision inSeptember 2007,implementing agencies were to limit international consultancies and give preference to local consultants orimplementing agencies. Theability of the local implementing agencies to take the lead in implementing the project during theAF phase reflected the strong capacity developed by local implementing agencies during the initial phase of theproject.The IEG draws the following lesson from the experience of implementing this project.(1) Toachieve critical institutionaldevelopment such as establishingaNational Center for Dam Safety in the context of aproject or programthe achievementneeds to be an agreedpriorcondition for the project orprogram. In this project the establishment of the National Center for Dam Safety was neither anagreedprioraction nor a formallyagreed objective to be achieved during project implementation.The choice ofproject or program design will determine the scope for achieving an agreedprior action or an agreed projectobjective.
P093133 | Programmatic Broad-Based Growth Development Support Loan | Latin America and Caribbean | El Salvador | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2005 | 2006 | 2009 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/330411474632270944/text/000020051-20140619074328.txt | http://documents.worldbank.org/curated/en/330411474632270944/pdf/000020051-20140619074328.pdf | The ICR contains several lessons, notably the importance of strong country ownership of reform.
P093165 | Market led Smallholder Development in the Zambezi Valley | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2006 | 2014 | 2015 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/469461475116018756/text/000012394-20150309080254.txt | http://documents.worldbank.org/curated/en/469461475116018756/pdf/000012394-20150309080254.pdf | The following lessons are taken from the ICR with some adaptation of language: It is important that the design of projects for implementation under decentralized arrangements, using country systems, critically examine the existing capacity at all levels at the outset of project design so that risk mitigation or remedial measures can be put in place. Long-term approaches, using for example, flexible lending instruments such as adjustable program loans, may help to build strong decentralization capacity at various levels of government and ensure consistent and continued support for the project over a longer period of time. In this case, the life-span of a single project proved to be too short for reaching this goal.Continued government follow-up, facilitating appropriate linkages with service providers and agribusiness value chain players, will likely be necessary for the sustainability of community empowerment. Clear targeting and beneficiary selection criteria can enhance project impact. In this case, the lack of such criteria led to a far larger number of beneficiaries than planned, which likely signified that project resources were spread too thinly.
P093165 | Market led Smallholder Development in the Zambezi Valley | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2006 | 2014 | 2016 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/154361467987858426/text/104190-PPAR-P093165-P098040-SecM2016-0129-Box394878B-OUO-9.txt | http://documents.worldbank.org/curated/en/154361467987858426/pdf/104190-PPAR-P093165-P098040-SecM2016-0129-Box394878B-OUO-9.pdf | 10. Lessons Â· Rural institutions can play a key service delivery role in the absence of strong state capacity, but sustained support is needed to ensure their good governance and capacity to provide services to the poor. In the absence of this support, there is a risk that such institutions may favor some participants over others, may neglect attention to gender and other vulnerable groups, and may lack the capacity to deliver sustained services after project close. The quality of sensitization and training, grounded in local culture, is key to enabling equitable and sustained service delivery. In the case of the Market-Led Smallholder Development Project in the Zambezi Valley, IEG found that the poor quality of facilitation services undermined the ability of the rural smallholders to benefit more from the productive investments made by the project and to engage in productive activities after project close. Â· Social accountability tools are important elements of a project intended to be implemented through village-level organizations. M&E systems that include social accountability assessments, including village-level scorecards, can help the project team (client counterpart and the Bank), identify and address underperforming areas, the underprovision of services, the relative strength of rural organizations, and other related behavioral issues that may be undermining efficacy. Â· A market-based approach to developing the smallholder sector requires an upfront analysis of skills, knowledge, and capacity in order to engage in various value chain activities, such as marketing. In Mozambique, owing in part to the nascent nature of the country's market-led economy, skills in areas such as efficient marketing were rare in many of the district-level administrations. Â· Simple technologies work best in poor rural communities. The introduction of complex technology into poor farming areas is risky and unlikely to succeed because the maintenance of complex systems is almost always unaffordable for poor smallholder farmers. Â· Behavior and incentives, both individual and at the policy level, should be placed at the heart of programs geared toward supporting sustainable land management. In the case of this project, land tenure security and land rights are central to farmers' decision to engage in sustainable land, soil, and water management practices, and yet the project tended to focus more on the technical fixes.
P093201 | Promotion of a Wind Power Market | Middle East and North Africa | Jordan | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2008 | 2015 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/562421483116828941/text/ICRR-Disclosable-P093201-12-30-2016-1483116821654.txt | http://documents.worldbank.org/curated/en/562421483116828941/pdf/ICRR-Disclosable-P093201-12-30-2016-1483116821654.pdf | The ICR provides the following key lessons: A full-scale Environmental Social ImpactAseessment should be part of preparing the tender for a pioneering wind power project, if capacity is to be procured competitively.Wind power projects can involve a range of environmental impacts, including ecological, resettlement, etc., the significance ofeach of which depends upon local conditions, and it is difficult to anticipate in the absence of other comparable projects in thesame region. Hence, for first-of-a-kind projects, efforts need tp be made to resolve all safeguard issues prior to starting acompetitive bidding process. An approach based on financing the incremental cost of renewable energyprojects can work provided the legal, regulatory and policy basis for the operation is in place prior to project approval. Findingdonors or governments to finance incremental costs is often necessary to promote environmentally or socially additional projectswherever market prices do not reflect the full social benefit of the projects. For such projects, relatively small amounts offinancing from donors/governments can be effective in closing financing gap, allowing a larger amount of private sector financingto be leveraged. However, the provision of an appropriate enabling legal and regulatory framework should not be part of theproject; otherwise delays on account of unforeseen challenges can tie up financing commitments for an extended period,significantly raising the cost of the projectand possibly increasing the cost of the original incremental cost subsidyenvisaged.
P093245 | PRSO 2 | Europe and Central Asia | Georgia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2008 | 2011 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/338571474632724024/text/000020051-20140620075810.txt | http://documents.worldbank.org/curated/en/338571474632724024/pdf/000020051-20140620075810.pdf | IEG broadly concurs with the lessons outlined in the ICR. In particular, the lessons about the importance of strong Government ownership of the reform program, good donor coordination, and the focus by the government on results are unexceptionable. Using the flexibility available under the programmatic lending to adapt the programs to the actual implementation experience is also sound advice for the Bank TTLs.
P093294 | Nepal Economic Reform TA (NERTA) | South Asia | Nepal | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2005 | 2010 | 2011 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/625591474577774472/text/000020051-20140624164653.txt | http://documents.worldbank.org/curated/en/625591474577774472/pdf/000020051-20140624164653.pdf | Even in demand-based projects, a clear results framework is needed. New proposals must be framed within this overall results framework, ensuring a link between objectives and the associated indicators with the desired outcomes.In demand-driven projects of such short duration, the approval process needs to be rapid, particularly in proposals that have been pre-identified. Broader ownership of TA activities is needed if objectives are to be realized; the Nepal experience shows that reform ownership by a few senior officials is insufficient.
P093384 | Mainstreaming Market-Based Instruments for Environmental Management Project | Latin America and Caribbean | Costa Rica | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2006 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/473251468189542347/text/ICRR14684-P093384-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/473251468189542347/pdf/ICRR14684-P093384-Box393183B-PUBLIC.pdf | While some of the lessons drawn by the ICR are generic and most are not new, the following should be highlighted: 1. Project design and implementation need to take into account country-specific complexities and pay particular attention to project readiness prior to and during appraisal. The ICR adds (para 64, pg. 15) that "where project effectiveness is delayed, the validity of assumptions made at appraisal needs to be reviewed and corrective action taken as early as possible." This did not occur in the present project. 2. To ensure that a project's M&E framework serves its purpose as a project management and results assessment tool, project implementing agencies need to adequately understand its purpose and possess the capacity to ensure its appropriate implementation. This was a critical weakness of the present project. 3. Payment for Environmental Services (PES) projects have proven effective in promoting afforestation/ reforestation as well as forest conservation, while providing a number of environmental services such as watershed protection to downstream users. However, such programs can also create perverse incentives that projects like the present one have sought to avoid. In Costa Rica, for example, given the high value of certain products such as pineapples, areas previously participating in the PES program are being converted into agricultural lands for the production of cash crops. In addition, if PES programs are mainly financed through government subsidies (and/or co-financed by external grants), the incentive for a symbiotic relationship between upstream providers and downstream beneficiaries of the environmental service is removed. Thus, it is important that a monetary value be attached to biodiversity conservation as part of the PES system so that the financial incentive for not converting the land to -- or back -- to alternative uses is higher. 4. Given the conditional cash transfer nature of PES, using this instrument to support vulnerable and disadvantaged communities, such as indigenous populations, can both help to expand its territorial coverage and improve the livelihoods of these beneficiaries.
P093459 | Second Poverty Reduction Support Credit | Europe and Central Asia | Armenia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2006 | 2007 | 2010 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/175111474488975473/text/Armenia-Poverty-Reduction-Support-Credit-PRSC.txt | http://documents.worldbank.org/curated/en/175111474488975473/pdf/Armenia-Poverty-Reduction-Support-Credit-PRSC.pdf | IEG broadly concurs with the lessons outlined in the ICR but would like to highlight the following two lessons in particular:First, a sound PRSP, prepared in a participatory manner and owned by the government is a critical input for a successful PRSC program. However, it should not be treated as a straightjacket and the PRSCs should not shy away from supporting difficult actions that go beyond the PRSP but are critical to sustained growth. Such an approach should, however, only be used in cases where; (i) there is robust analytical basis for supporting the proposed reforms; and (ii) there are important constituencies within the government and outside who are keen to use the leverage of the PRSC to change the status quo.Second, the weak results framework and inadequate M&E still remain an important constraint to realizing the full potential of the PRSCs. Assuring a pragmatic design up front and a systematic follow through during the implementation should continue to be the priority agenda for the task teams.
P093460 | PRSC3 | Europe and Central Asia | Armenia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2008 | 2010 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/175111474488975473/text/Armenia-Poverty-Reduction-Support-Credit-PRSC.txt | http://documents.worldbank.org/curated/en/175111474488975473/pdf/Armenia-Poverty-Reduction-Support-Credit-PRSC.pdf | IEG broadly concurs with the lessons outlined in the ICR but would like to highlight the following two lessons in particular:First, a sound PRSP, prepared in a participatory manner and owned by the government is a critical input for a successful PRSC program. However, it should not be treated as a straightjacket and the PRSCs should not shy away from supporting difficult actions that go beyond the PRSP but are critical to sustained growth. Such an approach should, however, only be used in cases where; (i) there is robust analytical basis for supporting the proposed reforms; and (ii) there are important constituencies within the government and outside who are keen to use the leverage of the PRSC to change the status quo.Second, the weak results framework and inadequate M&E still remain an important constraint to realizing the full potential of the PRSCs. Assuring a pragmatic design up front and a systematic follow through during the implementation should continue to be the priority agenda for the task teams.
P093461 | Sustainable Tourism Development Project (Montenegro) | Europe and Central Asia | Montenegro | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2007 | 2010 | 2011 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/667751474570033690/text/000020051-20140624184739.txt | http://documents.worldbank.org/curated/en/667751474570033690/pdf/000020051-20140624184739.pdf | When designing projects with broader social or environmental mandates or safeguards that may go beyond the more narrow commercial or economic interests of the client, it is not enough to obtain written commitments from the borrower without linking progress toward their achievement to continued financial disbursements. This connection between achieving tangible results and receiving continued project support must be made at an early enough stage in project implementation when the Bank still retains sufficient leverage with the client to influence or persuade them to undertake meaningful corrective actions and comply with their contractual obligations.
P093470 | EG-MORTGAGE FINANCE | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2007 | 2012 | 2012 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/718711474939000736/text/000020051-20140625111656.txt | http://documents.worldbank.org/curated/en/718711474939000736/pdf/000020051-20140625111656.pdf | IEG concurs with the ICR that the project demonstrates the importance of the following factors to the success of the operation: prior analytical work; strong policy dialogue with the authorities; prompt response to clientâ€™s needs and the changing environment; provision of technical assistance; conducive legal and regulatory framework; innovative and creative approaches; consultations with the different stake-holders; close coordination with IFC; effective cooperation with development partners; and overall flexibility in implementation of the reforms. Another lesson is the importance of the synergy generated by the Bank's engagement on a country's financial sector through multiple approaches. The success of the Egypt Mortgage Finance project owes much to the 2002 FSAP, which identified the challenges in the financial sector and provided policy recommendations to address them, as well as to the series of Financial Sector DPLs supporting the financial sector reform program (2004?2012), which helped in strengthening the legal and institutional framework of the financial sector for the mortgage market.
P093470 | EG-MORTGAGE FINANCE | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2007 | 2012 | 2015 | PPAR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/209291468187798051/text/97439-PPAR-P093470-Box391497B-OUO-9-SecM2015-0226.txt | http://documents.worldbank.org/curated/en/209291468187798051/pdf/97439-PPAR-P093470-Box391497B-OUO-9-SecM2015-0226.pdf | 8. Lessons 8.1 Housing finance is not an island. This project is a stark reminder that housing finance is embedded in the broader financial markets, economy, and political situation of a country. The social upheavals since the global financial crises of 2008 battered the financial system. With rising inflation and falling investor confidence, financial depth (M2/GDP ratio) fell sharply, as did capital markets activities. Housing finance which seemed poised in 2005 for a major spurt in growth and innovations was put on hold. However, a recovery may have begun in 2015. 8.2 Housing markets shape housing finance. Housing finance is also an integral part of the overall housing markets. Satisfactory outcomes of housing finance initiatives, such as responsiveness, wider access or improved affordability, depend on many elements of housing-market policies other than finance, including property rights and registration records, provision of infrastructure, the availability and ownership of land, regulations of land use and the building industry, rent control and housing subsidies. This project shows that constraints in the housing markets can severely impede effort to broaden and revitalize housing finance\. a. First, a large proportion of housing units, including more than half of those in greater Cairo, is located in informal settlements, without proper registration and documentation. Resolving these legal uncertainties has been shown to spur owners to undertake upgrade investments efforts that could be supported with properly designed housing finance instruments increasing the overall demand for housing finance. However with unclear legal status, these housing units are not eligible for credit from regulated financial institutions and therefore lessened the need to refinance their mortgage portfolios' with EMRC. b. Second, a large percentage of new housing units (in government-sponsored satellite cities mostly located in deserts surrounding major urban centers) is left unoccupied. Although these properties are by and large legal and properly documented, the demand is limited due to the distance from jobs and employment opportunities. Housing finance may help enhance affordability, but it cannot overcome more fundamental issues of the housing system. c. Third, millions of formal and fully documented residential units, including 42% of those in Cairo, are subject to rent control. Property owners hope to see a better day but are now unable to sell or recover the investment cost. Other than those occupied by owners, most of the units are left vacant or in disrepair. d. Thus, the volume of home purchases and investment in the sector (e.g., for rental property) is determined by housing policy and broader social objectives of the Government. For the time being, these various constraints have significantly restricted the scope of housing finance. Today, the mortgage markets are less than half of one percent of GDP. 8.3 Housing finance is not the exclusive domain of formal financial institutions. In designing the project, it is important to have a good understanding of the various formal and informal market players that affect and would be affected by the intervention. In Egypt, formal financial institutions account for a small share of the market. Self-finance plays a large role and so do informal lenders extending personal loans to home buyers. Critically, builders and developers offer extended payment plans, including installment plans of five to eight years, and provide more housing loans to homebuyers than banks and mortgage finance companies combined, accounting for more than two-thirds of the market.20 8.4 Developers are usually well positioned to manage credit risk. Builders/developers, especially those operating on a large scale, may possess significant competitive advantages in providing housing loans but they also raise concerns. The case of Egypt provides an illustration. First, developers are well positioned to assess the credit risk of buyers/borrowers. The marketing and construction of housing units allow developers to get to know and often work closely with homebuyers. Second, developers typically keep the title of a property for the first five years of the installment plan and thereafter transfer the title but retain the property as collateral. The risk of foreclosure and litigation faced by developers is much lower than that of banks or finance companies. With the skills and experience that they have accumulated, many of the developers in Egypt have also set up formal mortgage finance affiliates. However, unlike banks and finance companies, developers are not subject to official oversight or established prudential rules. Homebuyers interviewed by IEG cited cases where developers failed to deliver the contracted homes and absconded with the funds collected from homebuyers. In a reversal of typical risk-bearing roles, until developers release property titles to the buyers, the borrowers of the home loans (homebuyers) face a credit risk, while the lenders of the home loans (developers) face little or none of it. 8.5 A checklist for reviewing a mortgage liquidity facility. Many countries have shown interest in following Egypt's example and adopting the mortgage liquidity facility. But this model is not always appropriate. Among the circumstances to consider are\. a. Readiness of bond markets. A mortgage liquidity facility that seeks to fund itself through capital markets needs liquid and active bond markets, with reliable benchmark instruments to establish a yield curve with 15 to 20-year maturities. If 20 According to estimates of a mortgage market participant. No data is available for the size of the overall housing finance market. such markets are not in place, the mortgage liquidity facility would not be able to perform its most critical role of being central issuer of bonds at competitive rates. b. Local inflation. Even if the bond markets are functional, high and persistent inflation may render the mortgage liquidity facility impotent. As in Egypt's case, the EMRC has not been able to raise funds at competitive rates. Banks can mobilize deposits at much lower rates. c. The presence of non-bank mortgage finance companies. Without access to cheap sources of funds in the form of bank deposits, non-bank financial firms are more likely to draw on the services of the mortgage liquidity facility. d. Size of the mortgage market. To compete with banks, the mortgage liquidity facility needs a large scale of operations and frequent appearance in the bond markets to reduce the cost of operations. (The issuance cost of bonds â€“ in percentage terms â€“ is high when the volume is small.) If the size of the mortgage markets is miniscule, as it is in Egypt, the mortgage liquidity facility will not be competitive. e. The viability of adjustable rate mortgage. If mortgages are predominantly of fixed rates, the case for adopting a mortgage liquidity facility is stronger. Lending large sums on extended terms is not suited for short-term funding like bank deposits. The appeal of a mortgage liquidity facility is its ability to raise term funds on fixed rate at low cost. However, where adjustable rate mortgages are viable, supported by laws and consumer acceptance, the case for a mortgage liquidity facility is much weaker. Banks can rely on short-term deposits to fund ARM without incurring undue interest rate risk. (The liquidity risk remains, however, and needs to be mitigated.)
P093478 | Orissa Rural Livelihoods Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2015 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/256891471616435803/text/ICRR-Disclosable-P093478-08-19-2016-1471616426589.txt | http://documents.worldbank.org/curated/en/256891471616435803/pdf/ICRR-Disclosable-P093478-08-19-2016-1471616426589.pdf | The following lessons are drawn from the ICR but with selectivity and adaptation of language. Inrural livelihoods projects targeted at the poorest, participatory targeting is the essential first step for the identification ofthe target group, but this needs to be supported by a focus subsequently on those identified beneficiaries through all of theimplemented project components, through the mobilization process, through incentives and through ensuring leadership positions forthe poor. In this case, the project aimed to work with the entire village. This included older and newer self-help groupsand the poor and vulnerable but also the better off population. This breadth of accomodationhelped the poor and vulnerable tofeel, and to be seen to be, a part of the wider community. Rural livelihoods projects need to build on a producergroup base; this can be accomplished with a combined extension model including demonstrations, farmer field schools, and dedicatedresource persons, all working with producer groups to spread and scale up innovations and interventions. However, in thiscase, there was a need to considerably advance the work towards integration with the private sector and market players and tobetter link farmers to technical support systems sensitive to the poorer producers needs. Also, in this case, it was notclear how the poorest, with littleland access and little surplus production, could be reached by a value chainapproach. A state support system for a rural livelihoods project calls for dedicated staff architecture, theidentification of champions, attention to political traction, systematic and sustained partnerships, and convergence with existingstate government institutions to ensure continued scaling up. In this case the project supported well-trained anddedicated professionals at all levels but could have been more systematic in involving experienced local partners such as NGOs forinnovation and capacity building, particularly in the social area of entitlements. The complexity andcontext-specificity of livelihoods and community-based projects means that the design must incorporate flexibility and leave spacefor lower-level decision-making; to achieve this, performance based approaches to management and strong monitoringand evaluation are required. In this case, the incorporation of situational analysis data from the project databases wasimportant.
P093491 | AR APL2 Urban Flood Prevention and Drainage | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2006 | 2015 | 2016 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/445181468003619309/text/ICRR-Disclosable-P093491-06-15-2016-1466036304139.txt | http://documents.worldbank.org/curated/en/445181468003619309/pdf/ICRR-Disclosable-P093491-06-15-2016-1466036304139.pdf | The ICR provided a number of useful lessons, presented here with some adaptation:Replicating Best Practiceis not always smart context matters.Replication should be based on strategic analysis of the existing environment, as in many cases the context shifts,particularly in countries where political instability isprevalent. The subject project adopted the same design as theprevious Project and considered the new regulatory framework with some adjustments, without undertaking various scenario analysisto better pin down the differences of the participating provinces.With a new fiscal regulatory framework in place, theadded changes in legislators and contextwere significant and led to years of delay ineffectiveness.Strategic assessment of proposed resettlement procedures is highly critical, given thecomplexity of resettlement.While self-construction of resettlement housing by beneficiaries issuccessful, it cannot be replicated without fully considering the context. It is found to be feasible when beneficiaries havesufficient time to devote to construction; and when the timeline for construction of works is not dependent on completion ofresettlement. The Project was unable to replicate its predecessors approach inself-construction, given that theinvoluntarily resettled persons on average had neither the time nor the inclination to complete construction within the stricttimeline of the Project intervention.
P093568 | Export Finance Intermediation Loan 3 (EFIL 3) | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2005 | 2010 | 2010 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/827531474397451062/text/000020051-20140620081559.txt | http://documents.worldbank.org/curated/en/827531474397451062/pdf/000020051-20140620081559.pdf | It may be important to simplify procedures and minimize transaction costs further as an incentive to encourage more small exporters.
P093610 | eGhana | Western and Central Africa | Ghana | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2007 | 2015 | 2016 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/634111467992519072/text/ICRR14845-P093610-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/634111467992519072/pdf/ICRR14845-P093610-Box394823B-PUBLIC.pdf | The ICR draws the following lessons from the experience of preparing and implementing this project.It is important to undertake activities associated with improving the enabling environment that could have impact beyond the Project Development Objective. In the case of this project, to address the need for improved quality of ICT service and lower prices of internet services, the Information Technology Enabled Services (ITES) industry secretariat, in collaboration with the Bank, also negotiated with the Ghana Telecom to develop service level agreements. This in turn contributed to lowering the prices of internet services.Although Public Private Partnership (PPP) can be challenging to implement, they can be very useful in providing incentives for the contractor to deliver good value. In the case of this project, the structuring of the contract which linked compensation to contractor-based performance contributed to the outcomes. Financing by multiple development partners can be challenging when different partners have different reporting requirements. It would be useful to consider alternatives such as allowing for a consolidated report that satisfies all donors.
P093610 | eGhana | Western and Central Africa | Ghana | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2007 | 2015 | 2017 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/160891483464903876/text/108359-PPAR-P157755-PUBLIC.txt | http://documents.worldbank.org/curated/en/160891483464903876/pdf/108359-PPAR-P157755-PUBLIC.pdf | 7. Lessons 7.1 Following are the major lessons learnt from this project\. â€¢ It is important to include those activities in the project, upfront, which can directly and most effectively contribute to the achievement of project objectives. In the case of this Project, establishing BPO centers and Business Incubation activities could have directly contributed to the PDO of growth and employment, but these were not included in the project design at appraisal. They were included after the mid-term review of the project in 2010, and since these started late, they could not be completed by project end and therefore could not contribute to the PDO. â€¢ Financing by multiple development partners can be challenging when different partners have different reporting requirements. It would be useful to consider alternatives such as allowing for a consolidated report that satisfies all donors. â€¢ Implementing IFMIS under a partnership between the Ministry of Finance and a ministry incharge of establishing government wide-area network, with the former taking the lead on taking all decisions on PFM functionality and the latter leading and managing the IT infrastructure, produces effective results. A successful implementation of IFMIS requires a combination of both skills, and in this particular project, complete ownership of, and partnership between, both ministries, with an overall lead by the Ministry of Finance, ensured success. â€¢ With projects involving creation of large infrastructure, there must be a commitment taken from the government to provide necessary funding and institutional support for their operation and maintenance. In the absence of this, the sustainability of project investments can be put to high risk. In the case of this Project, a country WAN was created on which the eServices and GIFMIS operate, but the government did not make adequate budget provisions for its operation and maintenance. This has put on risk GovNet, which can collapse in a period of 2-3 years if the funding is not provided. â€¢ The Project design must include activities to address the binding constraints to development objectives and indicators to measure them. In the case of this Project, eServices like birth registration, marriage registration, police verification, company registration were started but they are being used by less than 10 % of targeted citizens for lack of internet and broadband penetration and awareness among citizens.
P093622 | Agricultural Services & Producer Organizations Project 2 | Western and Central Africa | Senegal | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2006 | 2011 | 2014 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/237291475114851929/text/000020051-20140626111252.txt | http://documents.worldbank.org/curated/en/237291475114851929/pdf/000020051-20140626111252.pdf | The ICR offers a number of lessons of which the following are the most important (with some reformulation of language):Institutional reforms in the agricultural sector requires long-term and high level involvement by the Bank and other donors. Since such reforms are generally politically sensitive, frequent political dialogue is required at the highest level, over the course of an Adaptable Program Loan. Such efforts should be supported not only by the technical department but also at the level of the country director. Collaboration with other donors is also important. Producer organizations are a crucial part of agricultural services provision and they should be supported and involved for successful reform of the sector. Producer organizations should be supported if they are to become partners with government in formulating agricultural policy and implementing agricultural programs at the national, regional, and local levels. The effectiveness of the agricultural extension and research system depends to a large extent on the strength of producer organizations.Evaluating the impact of agricultural services projects is a complex and methodologically challenging task but can be overcome by hiring universities to carry out the work. In many countries, the capacity to do such studies is very limited or nonexistent. Partnerships between local specialized universities and external universities with strong evaluation capabilities might be the best solution. These partnerships should be active from the very beginning of the project to ensure that baseline studies are undertaken on time. Project design should clearly spell out institutional implementation arrangements including amounts and sources for budgets. The project experience showed that lack of clear mandates for the implementing agencies may create competition between the agencies. Also the design lacked a financial plan to implement national coverage of extension agency's services, and it was not clear how the rising costs would be shared among government, and the users of services.
P093640 | Haiti Community Driven Development (CDD) Project / PRODEP | Latin America and Caribbean | Haiti | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2006 | 2013 | 2015 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/201321475112821461/text/000012394-20150108151314.txt | http://documents.worldbank.org/curated/en/201321475112821461/pdf/000012394-20150108151314.pdf | Several lessons reported in the ICR -- that draw on the experience in Northeast Brazil and that were used to inform the design of the Haiti pilot and PRODEP project - are very relevant for the design and implementation of CDD projects. These lessons are: 1. High quality technical assistance should be accessible to rural communities to enable them to identify, prepare and implement their own subprojects. Technical assistance should be targeted to weaker municipalities to improve their ability to plan, manage and maintain their subproject investments.2. An intensive, widely disseminated and carefully designed communication and information campaign is essential to ensure transparency and adequate knowledge of a CDD program's objectives and contents by all potential beneficiaries, as well as to hedge the risk of elite capture.3. Participation of Community â€“based organizations in the financing of subprojects generates a sense of ownership as well as a willingness to share responsibility for the future cooperation and maintenance of project investments. Participation in the selection, execution and supervision of subprojects ensures that investments respond to perceived needs, generate cost savings, increase accountability at the local level and ensure proper O based on objective criteria; foster transparency; and minimize political interference in project resource allocation.5. Sustained commitment by the Government and the Bank is critical to achieving lasting results under CDD, as the approach requires time to achieve even a modest behavioral change, bring it to maturity and eventually mainstream it.
P093699 | AO-Market Oriented Smallholder Agriculture Project | Eastern and Southern Africa | Angola | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/725431484338258035/text/ICRR-Disclosable-P093699-01-13-2017-1484338247813.txt | http://documents.worldbank.org/curated/en/725431484338258035/pdf/ICRR-Disclosable-P093699-01-13-2017-1484338247813.pdf | The ICR included five Lessons. The following are emphasized with some adaptation oflanguage: Arranging training sessions to favor womens participation is importanttoensure that women play an equal role in farmers organizations and influence project investmentdecisions. The projects experience demonstrated that women had limited influence on the choice of sub-projects.Womens participation in farmers organizations was alsolower than that of men and women usually had a secondaryrole, with only a few occupying leadership positions. More women could be encouraged to get training as Farmers Field Schoolfacilitators and become community leaders, for example by arranging training sessions to favor womensparticipation. Procurement, Financial Management, and ME teams need to be involved in the earlystages of project design to avoid implementation delays. Duringimplementation, the project had difficulty findinglocal qualified professionals to effectively undertake the fiduciary and ME functions. The lack of qualified financialmanagement andprocurement staff was in part responsible for the delayed start of project implementation. While hiring waspossible within a reasonable period, the selected consultants were not familiar with World Bankprocedures. The following Lesson is emphasized by IEG: It is critical toaddress constraints on the input side of the agricultural production chainin order to achieve improvements inyields. The project experience demonstrated the importance of addressing any limitations on the input side of agriculturalproduction chain, in particular variable inputs, such asseeds and fertilizers. Without the availability of seeds andfertilizers efforts to increase yields will not achieve the desired results; and itwould be highly unlikely that theintervention areas will experience any meaningful improvements in production.
P093719 | MA-Modernization of Irrigated Agriculture in the Oum Er Rbia Basin | Middle East and North Africa | Morocco | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2010 | 2018 | 2019 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/988241538145632575/text/Morocco-MA-Modern-of-Irrig-Agric-in-OER-Basin.txt | http://documents.worldbank.org/curated/en/988241538145632575/pdf/Morocco-MA-Modern-of-Irrig-Agric-in-OER-Basin.pdf | The ICR (pages 26-27) draws six lessons from the experience of implementing this project. Of these, the threemost important are;(1) Careful consideration of the land tenure situation may be required atappraisal for irrigation sector activities. In this project, activities pertaining to on-farm irrigation investments weresubject to delays during implementation, in view of the process associated withestablishing landownershiprights.(2) A relatively long implementation period may be required for large scaleirrigation sector activities.This project was designed from the beginning as a seven-year operation. Even withthisrelatively lengthytime frame, the project closing date had to be extended further in view of the delays duringimplementation.(3) Tailored procedures may berequired for targeting smallfarmers. Under this project, a 100 percentsubsidy was provided for drip irrigation by the national AgriculturalDevelopment Fund (FDA).The subsidy was initially designed in the form of reimbursement, but the limited financial capacity offarmers caused the Ministry of Agriculture to allow the irrigation company to be directly reimbursedby the FDA once theirrigation system was in place.IEG draws the followinglesson from thisproject.(1)A realistic assessment of the project timelines is required forarobusttheory of change. The original PDOs in this project were unrealistic in terms of the project timeframe.This undermined the theory of change and the relevance of the results framework. This issue was appropriately addressed at theLevel 1 restructuring.
P093720 | Himachal Pradesh Mid-Himalayan Watershed Development Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2006 | 2020 | 2018 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/957951521102541772/text/India-IN-Mid-Himalayan-HP-Watersheds.txt | http://documents.worldbank.org/curated/en/957951521102541772/pdf/India-IN-Mid-Himalayan-HP-Watersheds.pdf | The ICR identifies several key lessons of which two are especially important with useful implications beyond thisproject.Local Capacity Building. There is value in developing local capacity and then linking theprojects activities to local ownership and assumption of responsibility for many of the activities, such as cost sharing forthe building of infrastructure. The ICR (paragraph 97) concluded that local ownership and responsibility provide a key explanationfor the positive results achieved during implementationWatershed Development.Comprehensive treatment of selected catchments and application of productive practices have created improved incomestreams, thus making the watershed development project relevant for transforming theproductive potentialof rain-fedagriculture.Other lessons, based on this Review, include the following:Importance of a Robust ResultsFramework. The absence of a robust results framework (an explicit theory of change) and suitable indicators at theprojects initiation demonstrated the value of having an ME specialist involved in a projects design and theimplementation of ME programs.Secondary Benefits from Investments in Agricultural Production.Investments aimed at increasing agricultural production, including those related to crop diversification, can produce manyindirect benefits, such as improved nutrition, a healthier diet, as well as improved access to schools and health care when aproject improves or builds roads, foot bridges, and foot paths for more efficient marketing of agricultural products.
P093765 | GAS SECTOR DEVELOPMENT PROJECT | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2006 | 2022 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099625512222218340/text/P093765-658212f2-346d-4331-9f7d-246963378e41.txt | https://documents.worldbank.org/curated/en/099625512222218340/pdf/P093765-658212f2-346d-4331-9f7d-246963378e41.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. It would be useful to consider gas storage as an integral part of the Banks options, whenconsidering support to a country to ensure energy security. Given that gas demand patterns from end-users typicallycoincide with gas supply profiles, a buffer capacity would aid in ensuring reliable gas services. This is particularly so incountries like Turkiye which import significant amounts of natural gas.2. Adequate analysis of the related risksand appropriate mitigation measures are particularly needed in ambitious, Bank-financed projects. This project, which wasthe first of its kind financed by the Bankidentified fiduciary risks as substantial. It did not however make an assessment ofthe geological risks. This eventually led to the infeasibility of two caverns envisioned in the originaldesign.3. The overall theory of change needs to be consistent with the activities financed under theproject.In this project, a PDO indicator (storage operates as a separate business unit to ensureindependence and open access), was not attributable to any project interventions. The design implicitly assumed that Bankinterventions elsewhere would produce this intended outcome. The key lesson is that such a presumption needs to be formalized, andthis link needs to be explicitly recognized as acceptable practice for evaluation purposes.
P093767 | TRADE AND TRANSPORT INTEGRATION | Europe and Central Asia | Croatia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2007 | 2016 | 2017 | ICRR | >=100 million | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/844971498746816938/text/Croatia-TRADE-TRANS-INTEG.txt | http://documents.worldbank.org/curated/en/844971498746816938/pdf/Croatia-TRADE-TRANS-INTEG.pdf | Two lessons were selected from a longer list in the ICR, with some adaptation of thelanguage: Projects that depend on regional cooperationare challenging and special attentionneeds to begiven to facilitating a dialogue among thevarious stakeholders and sustaining that dialogue throughimplementation. The project development objective and the associated design should payparticular attention to the causative linkages to attribution and avoid claiming impacts that are beyond the scope of theproject.
P093775 | GEF Romania Integrated Nutrient Pollution Control Project | Europe and Central Asia | Romania | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2008 | 2024 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099092024163510261/text/P093775-904bc989-6a02-418c-a434-8430795e4547.txt | https://documents.worldbank.org/curated/en/099092024163510261/pdf/P093775-904bc989-6a02-418c-a434-8430795e4547.pdf | The ICR (p. 36-37) included several lessons learned, which were adapted by IEG: Using standardizedtemplates for investments in manure management or similar agricultural practices can ensure adequate quality. In thisproject, the original project used a standard template to control the design and technical specifications of the manure platforms.The AF changed the approach to a customized design to fit the needs and geography of each individual commune which resulted in poorquality designs and a lot of pressure on the PMU to support the communes in the preparation of technical designs, procurementdocuments, and to verify disbursement linked construction. Including performance indicators and reportingrequirements can stimulate beneficiaries to engage strongly in project activities. In this project, beneficiaries andcommunes officials, were not sufficiently incentivized to engage with farmers after the platforms were built resulting in anunderutilization of the platforms. To address this issue, the PMU imposed contractual performance indicators on all beneficiariesand established an online reporting tool to periodically submit reports to the PMU. The combination of raisingawareness as well as implementing an incentive system can positively impact farmers resistance to implement sustainablefarming practices. This project raised awareness through a Knowledge Transfer Network that allowed for building capacityand exchanging information and best practices among farmers and local communities. Also, payments to farmers incentivizedcompliance with sustainable farming practices. However, this was not sufficient and more direct involvement by e.g. a SocialDevelopment Specialist would have been needed to move from awareness to adoption of SLM practices at a higherlevel.
P093787 | Bahia State Integrated Project: Rural Poverty | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2006 | 2014 | 2016 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/779251468188363012/text/ICRR14916-ICRR-PUBLIC-P093787-Box396265B.txt | http://documents.worldbank.org/curated/en/779251468188363012/pdf/ICRR14916-ICRR-PUBLIC-P093787-Box396265B.pdf | The ICR suggested that five lessons emerged from the project. However some such as the suggestion to focus more on growth poles than broad CDD programs, and to weigh the costs and benefits of other programs with similar objectives were not only making the similar points but were also part of basic appraisal methodology rather than lessons from this project. Three lessons in the ICR had substantive points to make. With some editing they were as follows::(a) Natural resource management in CDD projects in rural areas can move beyond the traditional focus on safeguards compliance. Utilizing simple, "climate-smart technologies" such projects could incorporate water conservation and drought resistance strategies that would have long term pay-offs for poor producers. (b) Monitoring and evaluation require intensive focus from the project preparation stage to closing and beyond. While this is an old lesson this project again showed the folly of not establishing a sound M&E system based on a logical results framework which includes clear results chains. Well documented results from successive projects can contribute to an overall body of data/knowledge on addressing rural poverty through policy and projects.(c) Rapid preparation of scaling up of Bank-supported completed projects needs to be balanced by the need to step back to consider improvements in the project's design. If scaling up is the only objective a follow-on project may not address the changing needs of the client and the poor. Nor might the follow-on project address the weaknesses in its predecessor such as the absence of a focus on marketing in Produzir II , or be aligned with a changing economic or social context. An additional lesson. This project showed the potential for leveraging complementary funds from other sources within the country in order to substantially extend the project's impact and benefits. The success in this project indicates possibilities in the future in Brazil and other middle income countries.
P093806 | Niger Basin Water Resources Development and Sustainable Ecosystems Management Project | Western and Central Africa | Western and Central Africa |  |  | Sustainable Development | Water | IDA | IPF | 2008 | 2020 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/914521538145693780/text/Western-Africa-3A-Niger-Basin-Water-Resources.txt | http://documents.worldbank.org/curated/en/914521538145693780/pdf/Western-Africa-3A-Niger-Basin-Water-Resources.pdf | The ICR (p. 34-37) includes several lessons learned. This Review considered that the following specific lessonswere particularly important with general application to similarprojects. Conducting an in-depth risk assessment, which also includes externally driven risks and setting up a contingencybudget for unforeseeable costs, is critical for successful project implementation. In this project the coupdtats in Guinea, Niger, and Mali and an Ebola outbreak were not identified as potential risks, resulting insignificant implementation delays and a five-year project extension. Setting realisticobjectives is critical for building a track record of success and buy-in by member states for a newly set up implementationauthority. The original objectives of this project (some aspects of legal reforms as well as some of the infrastructureactivities) were overly ambitious, resulting in delays and tensions between the NBA and its member states. Allowing the NBA toachieve less ambitious objectives first before transitioning to a more challenging phase might have beenbeneficial. Including project activities that boost the local economy, build capacity,and improve the environment are beneficial for the sustainability of project outcomes. In this project activitiesrelated to traditional fishery, watershed restoration and agroforestry, and small-scale irrigation built managerial,organizational, and technical capacity within local communities to ensure sustainability, and had a positive impact on incomelevels and the environment.
P093812 | TRANSPORT SECTOR SUPPORT PROJECT | Europe and Central Asia | Romania | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2007 | 2010 | 2011 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/125411475091574163/text/000020051-20140624163505.txt | http://documents.worldbank.org/curated/en/125411475091574163/pdf/000020051-20140624163505.pdf | Inter-dependency of projects raises the risks, thus requiring especial attention at the highest management levels should issues occur. An early restructuring in this project coupled with frank discussions with government about the effects of the budget ceiling would have been appropriate.A clear and consistent government mandate for sector institutions is critical for success in project implementation. This would comprise a satisfactory financing framework; agreement between the ministries of transport and finance on the medium term sector budgets; a clear division of responsibilities between the line transport ministry and the implementing agencies; and stability in the management of those entities.When contemplating the design and launch of performance-based maintenance pilots it is important to take into account the capacity of the local road agency, the capacity and experience of the contractors, and the size of the pilot. The project can be customized in accordance with the degree of complexity of design, the local procurement rules, and staff available to oversee the implementation.
P093826 | Senegal River Basin Multi-purpose Water Resources Development Project | Western and Central Africa | Western and Central Africa |  |  | Sustainable Development | Water | IDA | IPF | 2006 | 2013 | 2015 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/774031467997915272/text/ICRR14636-P093826-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/774031467997915272/pdf/ICRR14636-P093826-Box393183B-PUBLIC.pdf | This review supports the three lessons identified in the ICR: (i) Trans-boundary projects dealing with river basins can have a role in disease control. The Bank should consider the advantages of a multi-sector project and/or a regional project when dealing with issues that are closely related and/or are trans-boundary. There were clear advantages to treating malaria across the four countries since the population is constantly moving in this area. This is applicable for most of the sub-sectors covered by the project.(ii) Support for a regional organization generally transcends the political instability that affects the individual national governments and may have positive development impacts. Close collaboration between the project executing agencies and the beneficiaries can mitigate the negative effects of national civil strife on project implementation. The implementation arrangement of channeling funds to the regional organization also had the advantage of keeping implementation moving forward despite military coups in three of the four riparian countries.(iii) Ensure that all aspects of the value chain are supported when local institutions are weak. Additional support following delivery of assets is needed for better outcomes and sustainability of value chains. To maximize development impacts, the program will typically need to go beyond delivery and provide follow-up support to recipients.
P093882 | Shandong Flue Gas Desulfurization | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2008 | 2012 | 2015 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/552451467998241330/text/ICRR14621-P093882-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/552451467998241330/pdf/ICRR14621-P093882-Box393183B-PUBLIC.pdf | Four of the ICR lessons have been modified and rewritten by IEG:Strong project management units are needed to support finance bureaus in supervising multiple sub-projects. This includes implementation arrangements with clear and transparent financial management systems, complemented with Bank team fiduciary supervision plans tailored to the assessed risk.Competency and Commitment should be assessed as part of selecting the project implementation unit. The project exemplifies the consequences of having the implications of a weak project management unit and the negative impacts from absence of up-front procedural agreements. As such, it endorses selection of the project management unit and up-front agreements critical for effectiveness.Project supporting mandatory targets should carefully time project support with the targetsâ€™ timeline. The PDO was timely and relevant at the time of identification and preparation, but the ability of the project to make an impact was continuously reduced as developments in the province quickly outpaced the preparation of the project. A strategic situation analysis emerges as critical for similar initiatives. Such analysis, would help the Bank to decipher lessons from the ground to better position itself. The Bank needs to be more proactive and clearer on initiating project restructuring. Client orientation and responsiveness are hallmarks of good project management. Global experience indicates that restructuring is not always easy, particularly when the client loses interest in obtaining the funds that the project was intended to supply. Clearer guidance on how to handle restructuring would help task teams to be forthcoming and attain earlier resolution of flaws in project design.
P093906 | Third Jiangxi Highway Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2006 | 2011 | 2013 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/539891474855020679/text/000020051-20140625060236.txt | http://documents.worldbank.org/curated/en/539891474855020679/pdf/000020051-20140625060236.pdf | The following lessons have been taken from the ICR with some adaptation:Implementation of rural roads components requires close cooperation between provincial and local government authorities. The problems experienced with the Ganzhou municipality in the design and implementation of the LRIP component suggests that the provincial highway agency did not have enough authority to ensure that the local government would comply with the requirements of the project, especially as regards to procurement. Highway projects can, during implementation, generate important social benefits, through well designed and implemented social policies. Employment is a prime benefit for the population in the area during the construction of a highway or other civil works. Substantial additional benefits can also occur such as improved health from the HIV/AIDS focused intervention with construction workers and residents. Achieving such additional benefits requires well designed and implemented social policies.
P093936 | Governance Technical Assistance Grant | Latin America and Caribbean | Haiti | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2005 | 2010 | 2010 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/870001475093951060/text/000020051-20140620084019.txt | http://documents.worldbank.org/curated/en/870001475093951060/pdf/000020051-20140620084019.pdf | IEG supports the lessons provided in the ICR. In addition, more work is called for on the possible need for a distinctive type of PFM support for fragile states. While progress has clearly taken place and the EGTAG results mainly achieved, the broader desired outcome of improved resource management leading to improved development results remains elusive. PEMFAR gives ample evidence that while Haiti made good progress in adopting many formal PFM arrangements, there were major shortcomings on functionality. Though budget quality has improved, budget execution is still weak; though controls have been tightened on resources within the formal PFM system, informal patronage systems are still the route for significant resources; though a personnel database has expanded coverage, there are weak checks to validate the data. More thinking is needed on how to break out of these constraints. Consideration could be given to approaches that have worked in other fragile states, including targeted incentives such as dual control arrangements, resource sharing agreements between central and sub-national authorities, enhanced discretion granted to subnational actors in the allocation and spending of resources, and accountability for results, and greater attention to leadership, coalition building and change management. The goal would be to gradually move political contests over what resources should become public from the opaque, informal and off-budget world to legitimate PFM and HR processes.
P093963 | Guiyang Transport Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2008 | 2014 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/429181475116904364/text/000020051-20150113010519.txt | http://documents.worldbank.org/curated/en/429181475116904364/pdf/000020051-20150113010519.pdf | The following important lessons are noted from the ICR : 1. Ensure interlink between project components to maximize the project impact. The project had investment on the urban road infrastructure, rural road infrastructure and transport services (bus terminals), which would help provide the improved infrastructure to the transport users. However, the locations of bus terminals were not well-selected and the bus service provision was not covered by the project. As a result, the rural infrastructure provided by the project could not ensure that the rural residents could have better transport services to enable them to have improved access to the social and economic services. Future engagement should pay more attention to the internal synergy of the project activities so as to maximize the benefit to the project beneficiaries. 2. Strong coordination at implementation. The implementation of Batch-I of 10 rural roads and 10 bus terminals under the rural transport component experienced substantial delays, a key factor contributing to the delay was the slow land acquisition and resettlement activities for Batch-I as a result of the limited capacity of Tongyuan Company. The strong coordination with the local government (county and township) led to the successful implementation of Batch-II activities. Such strong coordination should be ensured for any projects if land acquisition is required. In addition, civil works should commence only after the land acquisition and resettlement activities are fully (or at least substantially) completed.
P093987 | Health Sector Support & Multisectoral AIDS Project | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2006 | 2015 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/300811469051170452/text/ICRR-Disclosable-P093987-07-20-2016-1469051164832.txt | http://documents.worldbank.org/curated/en/300811469051170452/pdf/ICRR-Disclosable-P093987-07-20-2016-1469051164832.pdf | Lessons drawn from the ICR (pp. 43-44):Establishing an enabling environment for program achievement may beeasier than sustaining it. Projects are most effective when political leadership provides an enabling environment forprogram achievement and program achievement provides a justification for continued political commitment. Burkina Faso succeeded incombining several reinforcing elements for the enabling environment: political and strategic orientation; institutionalarrangements (harmonized procedures, participatory decision making including all stakeholders); fiduciary and administrativemodalities (pooled funding, decentralization); and programmatic decisions and results (community-based services). Sustaininga contribution to these mutually reinforcing relationships is particularly difficult for external funding agencies,as overtime: (a) changing leadership within these agencies requires constant consensus building; (b) perceptions of the utility ofinvesting time in sector coordination and harmonization differ; and (c) pressures to link individual agency financing with specificresults can become critical. Despite Burkina Fasos continued support for the strategic orientations above, there has been agradual attrition of support from the partners for certain key elements (and for pooled funding in particular). Such evolvingpriorities may have potential implications for the expansion of the RBF initiative currently being financed by theBank.Government ownership and leadership is a core requirement for successful institutional arrangements.Establishing the institutional framework for program implementation is an essential step during the preparation phase. Projectimplementation arrangements may also compensate for a lack of sectoral reform. Because key country reform elements (such asdecentralization, human and financial resource management, procurement, and so on) advance slowly, projects often provide a meansto achieve the reforms. Many of the projects initiatives were in advance of the countrys generalpolitico-administrative agenda and enabled the sector to demonstrate both the potential strengths and weaknesses of the proposedreforms. This was the case, for example, in the successful effort to decentralize management in the health sector.
P093988 | BD Dhaka Water Supply and Sanitation Project | South Asia | Bangladesh | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2009 | 2016 | 2017 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/615091488989952690/text/ICRR-Disclosable-P093988-03-08-2017-1488990826548.txt | http://documents.worldbank.org/curated/en/615091488989952690/pdf/ICRR-Disclosable-P093988-03-08-2017-1488990826548.pdf | Lessons drawn from the ICR, adapted by IEG: Longer-term maintenance arrangements and funding need to be includedin the project design to support sustainability of services. In the case of this project, the omission of theseinstitutional measures poses a significant risk to the continued functioning of infrastructure investments supported by theproject. Provision of services to low income communities in slum areas requires extensive understanding of existingconditions, legal aspects, and suitable technologies. In the case of this project, although a phased approach wasappropriate given the complexity of the activities, the lack of proper attention to the aforementioned issues led to significantshortfalls in implementation.
P093991 | Education Sector Investment Program II | Western and Central Africa | Mali | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2007 | 2011 | 2013 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/977811474592015065/text/000020051-20140625070807.txt | http://documents.worldbank.org/curated/en/977811474592015065/pdf/000020051-20140625070807.pdf | The main lessons that are learned from the ICR and this project are:Before functions can be effectively decentralized from the Ministry, a structure needs to be in place to monitor local and school level activities, as well as clear delineation of each partyâ€™s role/responsibilities. In this project budgets and school construction were decentralized before local-level reform of financial management and procurement systems and teacher management procedures. A SWAp requires careful project design based on sound analysis of the fiduciary and monitoring and evaluation to avoid overloading local capacity. In the case of this project, there was not sufficient analysis of the institutional capacity and discussion of harmonizing schedules. Differing fiduciary reporting schedules led to delays in the delivery of audits and annual work programs.
P094007 | Morocco - Second Rural Roads Project | Middle East and North Africa | Morocco | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2006 | 2017 | 2018 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/508571521841925640/text/Morocco-MA-Rural-Roads-II.txt | http://documents.worldbank.org/curated/en/508571521841925640/pdf/Morocco-MA-Rural-Roads-II.pdf | The main lessons adapted from the ICR are:Aparticipatory and decentralized approachisimportant for rural road development and sustainability, but implementation is best done gradually. Theachievements of NPRR-2 managed by the Directorate of Roadsprovided a platformfor initiatives by the regions andprovinces for decentralized rural roads programs based onthe active participation of localcommunities.Routine maintenance based on international experience is bestundertaken throughcommunity-based organizations (such as associations, cooperatives, and microenterprises). There has been notable successin Latin America. To test this concept in Morocco, the World Bank is preparing a pilot projectto be funded by a JapaneseSocial Fund grantgrant of US$3 millionto beimplemented by a regional government (followingdecentralization).Follow-up projects in Morocco (and roads elsewhere) could focusmore onrural roads that improve access in areas with agricultural potential.As NPRR-2was aimed primarily atlinking poor and isolated inhabitants in rural areas to social and administrative services and markets, priority was given to thepoorest and most remote regions, and not necessarily the ones with the most potential economic opportunities. Road transportremains a key area of intervention in Morocco to improve the productive capacity and market integration of farmers, and to developand diversify into value-added agriculture production. Addressing transport constraints will furtherenhancethefunctioning of the markets to benefit the poorest people.Implementing a nationalinvestment program requires the establishment up-front of a dedicated and properly staffed unit at the central level prior to itslaunch. At thecommencement of the NPRR-2, the DR was confrontedwith coordination and reporting issuesthat were only effectively addressed after the establishment of a PMU staffed with qualified engineers. This PMU provedespecially important given that the Programcomprised somany small subprojects dispersed over a large geographicalarea.Early deterioration of rural roads can be prevented by reducing the number of roaddesign issues. Problems included overdesign as wellas shortcomings in the detailed designs of rural roads.Mitigation was achieved mainly through the preparation and use of appropriate technical guidelines for rural road construction,with the support of the World Bank and other development partners. These guidelines, included in the Manual for Rural Roads Designand Appraisal, define a selection of road pavement structures and construction techniques (including the possibility of using localor reprocessed materials) to be used for the program and other projects in Morocco.Programmaticapproaches have both advantages and disadvantages. The programmatic approach adopted by the GoM for the NRRP-2enabled the leveraging of most of the development partnerssharing a common objective. However,World Bank financingamounted to a relatively small share of the total cost of the NRRP-2 (around 12 percent). Moreover, the fact that indicators weremeasured at program-level hindered their attributability to individual financiers. The contribution of the World Bank support tothe results of the overall government program (including in terms of outputs such as the kilometers of roads rehabilitated orupgraded) was thus not clearly visible. The programmatic approach meant that the Bank became de facto responsible forsupervising safeguards for the entire program, a mandate not necessarily commensurate with the level of resources allocated to thisendevour.
P094018 | Second Trade and Transport Facilitation Project | Europe and Central Asia | Bulgaria | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2007 | 2014 | 2015 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/839611467998243451/text/ICRR14710-P094018-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/839611467998243451/pdf/ICRR14710-P094018-Box393183B-PUBLIC.pdf | The key lesson emerging from the information provided by the ICR is the following:Institutional and capacity building through improved procedures, cooperation, and information exchange is as equally important as physical improvements to the infrastructure, in particular for trade and transport facilitation projects.The following lesson is formulated by IEG:A beneficiary survey is important in projects where service improvement is the main objective.
P094042 | BASIC EDUCATION, Phase I | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2007 | 2011 | 2013 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/426851475091919258/text/000020051-20140625065207.txt | http://documents.worldbank.org/curated/en/426851475091919258/pdf/000020051-20140625065207.pdf | The ICR contained several lessons:Education projects require time to achieve results and should not be planned with too short a time frame. The 18 month plan for this project was unrealistic and extensions could not make up for the lack of realistic planning needed for deep and sustainable reforms. To better support institutional reform and capacity building in centrally planned economies, Bank staff need to understand the nature of the public administration, procurement, and financial management systems and the working environment and culture. Bank staff also need to better support the learning curve of a new agency when implementing a Bank-financed project. It would be prudent to provide training on procurement and fiduciary matters in countries that are not familiar with Bank processes, prior to project implementation.
P094044 | Second East-West Highway Improvement | Europe and Central Asia | Georgia | IBRD | FCS | Infrastructure | Transport | IDA | IPF | 2008 | 2012 | 2014 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/226631474565607828/text/000020051-20140626001948.txt | http://documents.worldbank.org/curated/en/226631474565607828/pdf/000020051-20140626001948.pdf | The ICR has identified a number of lessons, of which the most important are listed below with some adaptation of language:Despite political pressure in highly visible projects, due diligence should be performed to ensure quality of project preparation and implementation. Political economy plays a critical and direct role in highly visible projects. Special attention should be paid to ensuring that project schedules are realistic and that due diligence is present in all aspects of preparation and implementation in order to minimize the risks of cost and time overruns and poor quality of outputs due to political pressure for speedy project implementation. A corridor and framework approach should be applied in preparation and implementation of the same type of road projects. In this way, a corridor approach will be followed in subsequent projects â€” and thus, the same framework will be applied throughout the entire road corridor. This approach is especially valuable when resources are limited and projects need to be done on a one-by-one basis. Safeguard-related frameworks developed under one project could also provide a sound basis for an upcoming project, and can be regularly updated and improved.The Project should allocate sufficient time and budget for the pre-construction activities, including preparation and review of designs. An ambitious timeline and a tight budget for the preparation of designs for a complex project could be major reasons for the poor quality of those designs. Traffic safety should be enforced by the employer and supervision consultants on all construction works in Georgia. There is a traffic safety provision in the Bills of Quantity â€” the employer and supervision consultant should take advantage of that provision. When it has been determined that the contractor has not been compliant with safety requirements, payment should be refused until such time as the contractor has undertaken a remedial action to adequately provide for the safety of construction workers and road users.
P094055 | VN-Local Development Investment (LDIFP) | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2010 | 2016 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/711331499352868279/text/ICRR-Disclosable-P094055-07-06-2017-1499352853299.txt | http://documents.worldbank.org/curated/en/711331499352868279/pdf/ICRR-Disclosable-P094055-07-06-2017-1499352853299.pdf | Most lessons presented in the ICR (pp 37-38) were either conclusions or findings rather than lessons.The following lessonswere selected from the ICR with some redrafting such they became generallyapplicable: The enabling policy necessary for a projects success needs to be part of theprojects design and legally established prior to project effectiveness. Inthis project the lack of a conducive Government policy and appropriate legislation allowing private sector equity participation inmunicipal development projects prevented the implementation of this important element in this project. Thechoice of beneficiaries or participants in a project will be most effective and efficient if the choice is based on clear andtransparent criteria. For example, in this project an open-ended system for qualifying potential borrowers (instead of arestricted list of borrowers) was appropriate in the context of a wholesale Financial Intermediary operation where it was difficultto determine ex ante where the demand for credit would comefrom.Lesson suggested by IEG: Theachievement of a project investment cannot be assessed unless it has a clear and measurable objective. This is anold lesson but it was learned again in this project because the PDO was not clear and difficult to measurable. This createddifficulties in the assessment of the projects efficacy and efficiency.
P094063 | National Program Support for Basic Education | East Asia and Pacific | Philippines | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2006 | 2013 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/860951474629316632/text/000020051-20140626113500.txt | http://documents.worldbank.org/curated/en/860951474629316632/pdf/000020051-20140626113500.pdf | The ICR (pp. 24-26) offers seven lessons on the project's preparation and implementation experience, four of which had a particularly strong relationship to the project's outcome: Institutionalization of reform requires a long-term commitment from the Government and the donor community as demonstrated by the Philippines Department of Education that needed eight years to move forward with decentralization, professional development, learning strategies, and organizational development.School-Based Management (SBM) is an effective tool to decentralize an education system and improve teaching outcomes, as demonstrated by its substantial impact throughout the Philippines.Public-private partnerships (PPP) can be key to ensure long-term availability of sufficient resources to support community schools. PPPs have increased the ability of community schools to raise funds from the private sector in the Philippines.A report-based disbursement system is more efficient than a Statement Of Expenses (SOE) system for a large education bureaucracy such as in the Philippines.
P094063 | National Program Support for Basic Education | East Asia and Pacific | Philippines | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2006 | 2013 | 2018 | PPAR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/764931528917588989/text/117900-PPAR-P163932-P163933-P094063-P106443-PUBLIC.txt | http://documents.worldbank.org/curated/en/764931528917588989/pdf/117900-PPAR-P163932-P163933-P094063-P106443-PUBLIC.pdf | 5. Common Lessons 5.1 Project and overall reform program achievements can be assessed and confirmed only through appropriate and relevant results frameworks. Careful consideration should be given to ensuring that a project's results framework is coherent, its objectives well defined, its theory of change well specified, and its indicators wellconceived to measure achievement of objectives. In this case, the lack of precision around the equity objective complicated assessment of achievement. Use of BESRA indicators may have been supplemented usefully with project-specific output and outcome indicators to flesh out the logic behind attribution. 5.2 Broadly defined interventions like SBM are conceptualized and implemented differently in different contexts, heightening the importance of country-specific analysis to explain the mechanisms at work in each intervention. In-depth evaluation of pilots to understand the level, degree, and types of autonomy and community participation achievable and realized, as well as the specific benefits to social efficiency and accountability and equity-related risks associated with various SBM designs, can illuminate important details and frame their generalizability. 5.3 The World Bank can play an important role in leveraging and implementing funds from development partners, but careful attention to implementation systems is warranted when these partnerships are conceived. In this case, challenges surrounding the harmonization of procurement and financial management systems led to inefficiencies and delays that jeopardized project efficiency. 5.4 A technical assistance project implemented in parallel with a major program supported by the World Bank can achieve important benefits. In this case, SPHERE provided resources to operationalize both NPSBE and BESRA and to fill identified gaps, achieving meaningful synergies.
P094084 | West Africa Agricultural Productivity Program (WAAPP) | Western and Central Africa | Western and Central Africa |  |  | Sustainable Development | Agriculture and Food | IDA | IPF | 2007 | 2014 | 2016 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/865891468197983112/text/ICRR14915-ICRR-PUBLIC-P094084-Box396265B.txt | http://documents.worldbank.org/curated/en/865891468197983112/pdf/ICRR14915-ICRR-PUBLIC-P094084-Box396265B.pdf | The following lessons are selected from those presented in the ICR (p.30-32), with some modification of language: While the rationale for regional integration in TGD is well known, integration does not occur automatically. Regional integration in agricultural TGD must be elicited purposefully by implementing proper instruments, guidelines, framework and mechanisms. To succeed, regional projects require a strong regional project coordination unit and strong and regular supervision and implementation support from the Bank. Both Bank staff and national project implementation teams must be committed to regional integration and remain vigilant in keeping the focus on that goal.While isolated technologies can make significant contributions to improving agricultural productivity, in some cases even larger impacts can be achieved by bundling several innovations into a single technology package. The case of composite flour is a good example of the advantages of linking innovations in plant varieties with organized farm production, coordinated processing, and product innovations. Public and private extension services and partnerships with producer organizations and the private sector are essential to implement action plans for technology dissemination successfully. In order to disseminate new technology widely and to ensure a high adoption rate of the new technologies, collaboration with grass roots organizations sand extension services are essential.
P094086 | Pakistan: Balochistan Education Support Project - BESP | South Asia | Pakistan | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2006 | 2015 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/800071467999728316/text/ICRR14746-P094086-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/800071467999728316/pdf/ICRR14746-P094086-Box393191B-PUBLIC.pdf | The ICR (p. 22-23) provides a number of lessons, which have been synthesized by IEG as the following:Empowerment of communities can lead to high levels of ownership and accountability. Communities raised non-salary recurrent funds in the absence of Government funding, ensured that female students enrolled and attended, and helped identify and attract teachers to their communities. Monitoring of community schools is needed for appropriate implementation.Adequate analysis during preparation is required to ensure sustainability of service delivery models. Community schools are only sustainable with Government fiscal contributions to salary and recurrent expenses, suggesting that Government ownership is needed up front. Private sector participation in low-cost education delivery was not a viable option in Balochistan, given the low propensity of households to pay. All of these factors were evident at design, but adequate preparatory analysis of these aspects was not undertaken.Increasing girls' enrollment in Pakistan requires specific attention. While the project optimized the conditions for girls to enroll, cultural barriers were not addressed. Girls' enrollment differences were observed between community schools and new private schools; however, this was not investigated by the implementing agency or the Bank.
P094097 | CO-3rd Prog. Labor Reform and Social Development Policy Loan | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2007 | 2007 | 2008 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/805651474660060405/text/000146597-20140618144925.txt | http://documents.worldbank.org/curated/en/805651474660060405/pdf/000146597-20140618144925.pdf | Joint Bank-GOC analytical work on training, health, and education issues helped establish a consensus that facilitated project progressProject focus on monitoring key outcomes permitted inclusion of a broader range of sectors than would otherwise have been possible
P094103 | AFCC2/RI-Regional Communications Infrastructure Project | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Digital | Digital Development | IDA | IPF | 2007 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/273281516400436503/text/ICRR-Disclosable-P094103-01-19-2018-1516400423191.txt | http://documents.worldbank.org/curated/en/273281516400436503/pdf/ICRR-Disclosable-P094103-01-19-2018-1516400423191.pdf | The ICR Review selected thefollowing main lessons from the ICR, with some modification of thelanguage.(1) Given the significant risks to incorporatingPPP arrangementsto large communicationinfrastructure projects in fragile countries (like Burundi and Madagascar),adequate technical assistance activities need tobe planned at appraisal. The experience of this project showed that project preparation did not properly anticipate thecomplexity of the operation, particularly in terms of engagement of the various stakeholders. In the case of Burundi, mitigationmeasures for addressing risks associated with PPP arrangements were not adequate and this in turn undermined the key principles ofPPP, like open access.(2) Proactivity of the supervision team can aid in implementing complex projects.In the case of this project, a willingness to adapt (such as through restructurings in case of the three countries and redesigningactivities in Madagascar following the political crisis in Madagascar)helped in realizing the PDOs.(3) Insituations where the Bank needs to provide significant support during implementation, Government ownership towards sector reform isparticularly important. In the case of this project, it is not clear if the supervision team focused adequately onsector reform. This contributed to the non-enforcement of activities pertaining to the enabling environment for development of theICT sector.
P094146 | Second Broad-Based Growth Development Policy Loan | Latin America and Caribbean | El Salvador | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2006 | 2007 | 2009 | ICRR | Less than 10 million |  | Satisfactory |  | Satisfactory |  | http://documents.worldbank.org/curated/en/120091474853692589/text/000020051-20140619073837.txt | http://documents.worldbank.org/curated/en/120091474853692589/pdf/000020051-20140619073837.pdf | The Note on Cancelled Operation contains numerous lessons, including:During project preparation, the Bank consultation process needs to be extended beyond the executive branch of government in order to engage with the country's legislative branch and other stakeholders.Information, education and communication strategies are key risk mitigation components in highly politicized environment.Project management in volatile political environments requires Bank staff to have skills in negotiation, conflict resolution, and alliance building.The changing socioeconomic environment in many Latin American countries requires the Bank to define a strategy to work with clients throughout the political and ideological spectrum, as well as the appropriate mix of lending and non-lending assistance.
P094152 | PE Irrigation Sub-Sector Supplemental Project | Latin America and Caribbean | Peru | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2005 | 2009 | 2012 | ICRR |  | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/594331474666503011/text/000020051-20140620084613.txt | http://documents.worldbank.org/curated/en/594331474666503011/pdf/000020051-20140620084613.pdf | While it is necessary that beneficiaries should contribute to irrigation infrastructure improvements great care should be taken in selection of the incentive structure. If qualification criteria for access to project financing are too onerous there is a risk that smaller and poorer farmers may be excluded. There is perhaps place for a sliding scale of farmer contribution related to socio-economic status. A competitive grant mechanism for selecting on-farm irrigation sub-projects has the risk of being slow and cumbersome, as shown by the project, especially when the demand for on-farm technology improvement is low.
P094167 | Privatization Social Support Project 2 | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2005 | 2010 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/861671474652813081/text/000020051-20140620085655.txt | http://documents.worldbank.org/curated/en/861671474652813081/pdf/000020051-20140620085655.pdf | Providing and institutional structure and working with firms and workers prior to lay-offs can improve the readiness of firms at the point of sale and ease any social, economic and political consequences of privatization. The project used the PSSP I structure which supported the Privatization Administration to work with firms that were on the list to be privatized and get them ready for privatization and the point of sale. The Labor Adjustment Group in the Privatization Administration worked with workers and provided them guidance on retiring or getting labor market counseling and training so as to help guarantee that firms would smoothly shed their labor force by the time of sale. In a project which is trying to affect people's behaviors (such as finding new employment) is essential to base project design on assessments of needs and incentives of the intended beneficiaries. Had project design more candidly factored in the sensitive but important findings from the impact studies of the first phase as well as assessed the incentives and needs of the affected SOE workers the project may have chosen to alter design details of the JLC and LRS to achieve the objectives more effectively and efficiently.When M&E plans are significantly altered during project implementation appropriate adjustments need to be made to the results framework early on to ensure that project performance can be rigorously assessed. Not until project closing did the ICR team try to compensate for this shortcoming and collect information about project outcomes, albeit only to a limited extent.
P094176 | Energy Community of South East Europe (APL #2) (Turkey) | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2005 | 2011 | 2014 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/983401474569034228/text/000020051-20140625065824.txt | http://documents.worldbank.org/curated/en/983401474569034228/pdf/000020051-20140625065824.pdf | The following three lessons are taken from the ICR with some adaptation of language:The projectâ€™s experience shows the importance of sustained political commitment and policy dialogue over time for effective electricity sector reform. In this regard, a long term instrument, such as the APL, was useful.Regional markets require strong national market operational capabilities and close attention to the design and operation of component national electricity markets.When, as in this case, reform implies unbundling, commercialization, and privatization, it is important that the system and market operator (here, TEIAS) has the capacity to react rapidly to an evolving operating environment in a pro-active and timely manner. There were indications during implementation that TEIAS capacity could be reinforced in these respects (particularly in terms of being able to attract and retain high quality staff).
P094183 | AFR RI Agricultural Productivity Program for Southern Africa (APPSA) | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Sustainable Development | Agriculture and Food | IDA | IPF | 2013 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/936571613497661475/text/Africa-Ag-Prod-Prog-for-Southern-Africa.txt | http://documents.worldbank.org/curated/en/936571613497661475/pdf/Africa-Ag-Prod-Prog-for-Southern-Africa.pdf | Based on APPSAs implementation experience and results, the ICR highlighted three core lessons (ICR, paras. 94-96, with someadded points shown below), which can enhance APPSAsustainability and also provide usefulinputs for enhancing othersimilar regional RD programs(i.e., EAPP, WAPP): (a) Strong partnershipswith the relevant CGIAR centers, a broad-basedprivate sector and producer organizations are essential to successfullyincrease technology generation and uptake (i.e.,dissemination and broad-based farmeradoption).The APPSA showed that collaboration with relevantCGIAR centers was highly beneficialin generating improved technologies through breeding and sharing of germplasm with various international research entities:International Maize and Wheat Improvement Center/CIMMYT; International Rice Research Institute/IRRI; International Crops ResearchInstitute for the Semi-Arid Tropics/ICRISAT; International Center for Tropical Agriculture/CIAT; and International Institute ofTropical Agriculture/IITA. With the successful development of pro-vitamin A orange maize by APPSA, formal partnerships andcollaboration with Harvest Plus, local milling and seed companies were instrumental in the expanded uptake of the pro-vitamin Aorange maize in Zambia and Malawi. This positive experience paves the way for promoting the uptake ofothercommodities supported by APPSA. (b) The potential impact of agricultural technology generation and dissemination of RDactivities is enhanced significantly when dissemination and delivery mechanisms are developed and considered early on/fromproject design stage. While the APPSA was successful in generating improved technologies, attention to dissemination to farmers wasintroduced mid-way, thereby limiting and delaying achievement of tangible production benefitsat the farmer level. Also, theProjectfocused dissemination on lead farmers, assuming that adoption would spill over quickly toother farmers, rather than taking a more direct approach to accelerate scaling up with followerfarmers, alsorecognizing that the adoption process take time (JIE, 2020). While lead farmers can and should play a key role, there canbesupporting actions to accelerate the dissemination activities through lead farmers and other complementaryprocesses.Accordingly, a key lesson is that RD type of projects/programs should include in the design phasedissemination component/activities through integrating program/project design with the national extension program/services, seedmultiplication, the expanded private sector, farmers groups and input providers. When there are many technologies on the shelf,more attention should be given to new technology generation (and to be reflected in the priorities of the annual researchagenda/work plan), and to including explicit dissemination mechanisms and activities, including adequate budgetaryallocations from public expenditures (which the Bank team alsoincluded as a topic of discussion duringimplementation).(c) Regional RD program/project can catalyze a strongculture of regionalcollaboration, facilitating applied research to efficiently address well identified shared problems with appropriate sharedsolutions.The ICR highlighted 2good examples of the importance of promoting this regional collaboration, which also canhelp expand and sustain APPSAfor the entire SADC region: (a) collaborative research to address the FAW outbreak and othercommon cross-border diseases affecting key commodities/staples (e.g., maize lethal necrosis disease) and nutrition deficiencyproblems, as addressed by the pro-vitamin A maize variety demonstrated the clear benefits of investment in regional RDprojects, and at the same time, to contribute to higher level food and nutrition security objectives in the region; (b) theregional ME framework developed through regional collaboration and led by CCARDESA is being used to improve the ME ofregional RD projects in the SADC region. Threeadditional lessons wereimplied by the ICR (paras. 65-69), but not includedas lessons, and merit inclusion.(a)the importance of deriving and strengthening the most appropriateand effective institutional arrangements and roles for guiding APPSAimplementation and making timely adjustments,while finding the right balance between developing and using country-level and regional arrangementsandmechanisms, and their linkages. The ICR recognized that the Projectexperienced various institutional coordinationchallenges during the early years;with the support of the findings of the MTR,Project Management progressively foundand used various institutional arrangements and mechanisms to promote improved and effective coordination at the regionalANDcountry levels (e.g., role and effectiveness of APPSA Regional Steering Committee, balanced with appropriate country-levelinstitutional coordination arrangements, mainly through the NARS/PIU at the country level, relevant working groups, and stronglinkages between the regional ME system and the decision-making entities and actors at the regional and country levels).Expanding the number of countries to participate in APPSA and meeting the challenges of sustainability of regional publicgoods will require close attention to sharpening and strengthening the most appropriate institutional arrangements foreffective, efficient and sustainable program coordination; (b) the strategicrole of promotinganexpanded role of the private sector, in different aspects of technology generation and dissemination (including as a keyactor in the subprojects supported by the Project), building on some of the emerging discussions with and initiatives by CCARDESAand the participating countries. The Project team shared some of these initiatives which merit follow up support by the Bank,especially in the on-going follow up support (for Angola and Lesotho), and in the event there is a follow up phase of APPSA for the3 countries, and possibly other countries who are members of SADCC; and(c) the value of completing a formalrestructuring of a Project in the event relevant findings ariseduring implementation (such as a mid-term review)and are also carried out as part of project implementation. In the case of this project, there were 2 strategic areaswhich wererecognized during the MTR which warranted a formal restructuring, for purposes of transparency andaccountability: making relevant adjustments to the RF and several outcome indicators, to reflect more realistic expectations;and strengthening various project actions to enhancevarious aspects of agricultural extension at the country level, andtherefore, to improvethe dissemination aspects of enhanced technologies regarding the projects PDO. At the sametime, it was recognized that the APPSA and Bank Project teams implementedthese adjustments during the remaining life of theproject.
P094193 | Post Tsunami Emergency Relief and Reconstruction Project | South Asia | Maldives | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2005 | 2010 | 2011 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/164231474491291107/text/000020051-20140624170143.txt | http://documents.worldbank.org/curated/en/164231474491291107/pdf/000020051-20140624170143.pdf | It is important to identify and monitor outcomes from the start even in Emergency Projects and to ensure funds and a framework to do this. Medium and small-scale contractors should be encouraged to support construction in such emergency contexts.
P094199 | Pelotas - Rio Grande do Sul Integrated Municipal Development Program (APL) | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2008 | 2014 | 2016 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/596351473921750436/text/ICRR14922-P094199-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/596351473921750436/pdf/ICRR14922-P094199-Box396299B-PUBLIC.pdf | The first three of the following lessons are drawn by IEG. The other two are taken from the ICR with some adaptation of language: Implementation difficulties are likely to arise when there is incongruence between the scope of objectives and the resources required to achieve them. In this case, the employment creation sub-objective, supported by Component 2, was too ambitious for the financial and technical inputs contemplated.If M&E is to be useful in an environment where the concept is new to the Borrower, and the Borrower has no expertise in quantitative monitoring, it is important that adequate training and capacity building should be provided during both the preparation and implementation stages and that a proper structure in terms of institutional arrangements and responsibilities be put in place. An under-budgeted M&E framework, without adequate means for establishing baselines and measuring progress in indicators is unlikely to function well. The quality of supervision is likely to be undermined when the financial resources made available for it do not match the particular demands of the project. In this case, these demands stemmed from having to deal with five small and medium-sized municipalities, none of which had any previous experience of working with the Bank.Implementation problems are also likely to arise from a mismatch between Borrower capacity and the complexity of a project spread over a wide range of small-scale activities and involving numerous entities in both the public and private sectors.The main reason why the implementing agency in Pelotas performed better than in most other municipalities supported by the project was the fact that the UGP was a robust, autonomous structure with its own staff linked directly to the Cabinet of the Prefecture.
P094205 | Sri Lanka Tsunami ERL | South Asia | Sri Lanka | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2005 | 2009 | 2011 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/328961474396436046/text/000146597-20140619165842.txt | http://documents.worldbank.org/curated/en/328961474396436046/pdf/000146597-20140619165842.pdf | Of the ICRs 13 lessons the most important six are presented:In disaster recovery homeowner-drive approach coupled with necessary technical assistance fosters ownership of the program among participants lending to strong results; however, the strategy needs to include special assistance to more vulnerable groups â€“ female-headed households and seniors â€“ in order to prevent disparities in construction completion. Homeowners under this approach had the incentive of constructing houses of their choice while adhering to specified safety guidelines set by the project. The approach also gave beneficiaries an opportunity to receive construction and supervision training increasing skills development within communities. This training will contribute to an increased likelihood that project outcomes will be maintained as more people have skills to construct and repair homes in the future. However, as was the experience of this project, female-headed households and those of seniors were disproportionately behind in construction.It is better to establish common standards and procedures for implementation in disaster recovery projects. Allowing varying approaches in implementation by different players in the same reconstruction program can contribute to inequity in the distribution of benefits among those affected by the disaster. The IDA-financed housing component utilized the homeowner-driven reconstruction model while at the same time a donor-driven model was also being used under the wider housing reconstruction program. The donor-driven model was financed by other bilateral donors and implemented primarily through NGOs. The latter model included the possibility of â€œtop-upsâ€ which involved homeowners receiving additional cash grants above the normal government housing grant. The distribution of â€œtop-upsâ€ was disproportionate between the South West and the North East, where the former received more. Greater consideration to the potential effects of using different approaches and increased communication between players with regard to distribution of beneficiaries throughout the project could prevent uneven results.Effective strategic communications, training and continuous social assessment and are critical components for project success and consolidation of gains. The lack of information dissemination under the housing component made it difficult in achieve commitment to implementation in some areas. Furthermore, poor dissemination of information created complications surrounding the reversal of the buffer zone policy and how this would affect households living in it. Training increased the capacity of homeowners and enabled communities to successfully reach target reconstruction and the skills developed by beneficiaries increased the pool of skilled labor contributing to the economy. In disaster recovery projects a comprehensive and institutionalized monitoring and evaluation system is critical for enabling informed decision making for policy and operations. While the project did involve reporting and monitoring through audits, surveys, and field visits among other mechanisms, the flow of information between the different levels of implementation was poor, and regular communication of this data to the central implementing agency, where policy decisions were being made, was not realized. This line of communication was further crippled by institutional reorganization midway through implementation. Without an effective grievance redress mechanism and associated documentation of grievances, the concerns of beneficiaries can go unattended and these eventually cause delays in implementation and disparities in outcomes. Grievance redress institutions related to land ownership and other housing complaints at the village, district and divisional level did not function at its full potential under the project. Grievances were also poorly documented. In the wake of such a large-scale disaster, the range of land ownership issues calls for consistent and strategic policy for assisting beneficiaries in dealing with related complications. In the case of this project, land demarcations were destroyed as well as titles, and in some cases landowners were forced to sell land (especially within the former buffer zone) and without an effective grievance mechanism or system for monitoring beneficiaries it is difficult to address these issues adequately, thus compromising project outcomes.Accountability is an important component of emergency reconstruction. This project highlights the importance that must be given to establishing sound and transparent M&E arrangements for inputs and outputs, as well as outcomes. Given that frequent reorganization of the implementing agencies frustrated sound M&E, the Bank partially addressed this failure by putting in place alternative and independent verification and reporting arrangements.
P094212 | Transitional Agriculture Reform Project | Europe and Central Asia | Serbia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2007 | 2013 | 2015 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/715691475113965984/text/000180307-20141203054441.txt | http://documents.worldbank.org/curated/en/715691475113965984/pdf/000180307-20141203054441.pdf | The Implementation Completion Report offers a number of lessons of which the following are the most important (with some reformulation of language):Â· The Bank needs a clearly agreed vision when negotiating a project. Attempting negotiations with a care taker government that does not have the mandate to push through deep rooted administrative reforms opposed by a number of stakeholders and lacking buy-in from the new administration is not likely to result in sustained reform implementation. Suspending preparation until more clarity as to policy direction could help the formulation of assistance with more buy in by policy makers.Â· In a dynamic political environment, where there are frequent changes in the government, a stable Bank leadership team is critical to maintaining project continuity and implementation performance in achieving project objectives. A frequent change of TTLs in these circumstances is likely to impact adversely on the management performance required for effective policy dialogue and project implementation that contribute to achievement of project objectives. Â· The Bank needs to better assess the risk of engaging in institutional capacity building in the agricultural sector in pre-accession countries given that perspectives of readiness towards a candidate State can change for reasons extraneous to the sector or the project. In the case of this project the delaying of the candidacy status from 2008 to 2012 had a significant impact on the borrowerâ€™s commitment to institutional structures in alignment with the EU requirement given that IPARD funding would remain unavailable. This Review finds the following additional lessons suggested by the experience of this project:Â· Partnering with other donor organizations, such as the EU. across a common objective can be highly beneficial, however the Bank should be prepared to accept a complementary role. This means that Bank interventions have to substantially agree with EU objectives and schedules and take an opportunistic approach to close gaps that EU support does not finance. Â· Having a realistic development objective is key for project success. All elements of project evaluation should be linked to the objectives- whether they are relevant, whether they are achieved and whether they are achieved efficiently. When a project has a very broad objective that is beyond the reasonable purview of the project, the causal chain between inputs, outputs and outcomes/impacts is lost and achieving the objectives fully becomes very difficult.Â· Setting up and implementing a proper M&E system to measure the achievement of a project is another key element for success. The M&E system should include all the related, measurable key outcome and intermediate indicators to adequately monitor and measure achievement of the objectives. The institutional arrangements as well as data collection/implementation methods and analysis should be clearly defined.
P094220 | Health Sector Reform Project | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2006 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/135141474940671441/text/000180307-20141203061623.txt | http://documents.worldbank.org/curated/en/135141474940671441/pdf/000180307-20141203061623.pdf | The following lessons are adapted from the ICR (pp. 22-23):Health sector reforms are costly, time-consuming, and politically sensitive, requiring a significant amount of political economy analysis. In this case, the impact of political processes on health financing reforms was apparently underestimated, resulting in a stalling of the Basic Benefits Package and mandatory health insurance. Without a long-term perspective, any momentum gained in these areas is now likely lost.Strong, effective political leadership is essential to ensuring progress on politically challenging reforms. In this case, there was no â€œchampionâ€ for the health insurance reform and its institutional base, the Health Insurance Agency. As a result, despite numerous policy papers, pieces of passed legislation, and related documents to support the reform, it has stagnated.Two additional lessons are offered by IEG:Pilot interventions are not likely to reveal many insights/lessons without well-designed M&E. This includes not only viable indicators, but also the assessment and strengthening of M&E capacity and the definition of systems, processes, and pilot evaluation designs tailored to accommodate learning and decision-making for adaptation/possible scale-up of models.One single operation is not sufficient to address systemic and long-standing issues in a sector. A longer time frame is required to create the conditions for institutional and structural change.
P094225 | Social Investment Fund III | Europe and Central Asia | Armenia | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2007 | 2015 | 2016 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/649861468008135486/text/ICRR-Disclosable-P094225-06-21-2016-1466547714069.txt | http://documents.worldbank.org/curated/en/649861468008135486/pdf/ICRR-Disclosable-P094225-06-21-2016-1466547714069.pdf | The ICR (pp. 28-29) provides valuable lessons, including the following: Poverty targeting iscritical for equitable and adequate allocation of project resources. In this project, targeting involved a two-stage process,geographical targeting at the regional level,and then identifying the neediest communities within each region throughcommunity mapping and profiling based on previously agreed criteria. This type of targeting was effective in selecting beneficiarycommunities. Enforcing operations and maintenance requirements and budgeting adequately for theserequirements isimportant for the long-term sustainability of infrastructure built in communities. For this project, a study conducted in 2012found that only 44% of sampled micro-projects had operation and maintenance cost planning and estimates for the yearbefore.
P094233 | Espirito Santo Biodiversity and Watershed Conservation and Restoration Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2009 | 2015 | 2017 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/402221488326277818/text/ICRR-Disclosable-P094233-02-28-2017-1488326272244.txt | http://documents.worldbank.org/curated/en/402221488326277818/pdf/ICRR-Disclosable-P094233-02-28-2017-1488326272244.pdf | The ICR draws the following main lessons from the experience of implementing this project.(1) Strong commitment fromthe Government and state agencies and stakeholders can be very useful. In the case of this project, the Government ofEspirito Santo revised the Payment for Environmental Services (PES) law and also replaced the initial program with a revisedone. This contributed to the implementation of the PES program in the latter years of the project.(2) While jointsupervision of GEF projects with other projects can bring in savings, they can also result in insufficient attention paid tokeyproject activities as happened in the case of this project.(3). Documentation of the expected and financial costsand benefits of degradation can be instrumental in securing Government commitment. In thecase of this project, theeconomic analysis prepared during appraisal was instrumental in convincing the Government of Espirito Santo and the Espirito SantoWater Utility Company (CESAN) to support this support and to continue supporting Reflorestar after the project.
P094278 | Health and Nutrition Support Project | Western and Central Africa | Mauritania | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2006 | 2011 | 2012 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/774691474489821459/text/000020051-20140625080928.txt | http://documents.worldbank.org/curated/en/774691474489821459/pdf/000020051-20140625080928.pdf | The ICR (page 22) appropriately notes that political stability in the country is important for smooth implementation and success of a project. The political instability that prevailed during this project led to frequent changes in key staff. Therefore, IEG would advise that the risks due to political instability should be carefully assessed, with adequate mitigation measures identified. Related to the lesson identified in the ICR (page 22), the M&E design should include indicators that are closely linked to project activities and adequately measure results relevant to the project objectives. This project's key indicators were primarily related to process and outputs, and thus hindered the ability to clearly assess outcomes.
P094288 | Reform Implementation Development Policy Loan (RIDPL) | Middle East and North Africa | Lebanon | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2008 | 2009 | 2010 | ICRR | >=100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/591691474944500584/text/000020051-20140620072354.txt | http://documents.worldbank.org/curated/en/591691474944500584/pdf/000020051-20140620072354.pdf | The central lesson of this operation is that political factors can easily derail an operation despite good technical inputs. The operation benefited from analyses and reports that provided the necessary knowledge of what needed to be done. However, the lack of political consensus undermined the leadership required to bring the reforms to fruition.
P094301 | 1st Business Productivity and Efficiency DPL | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2006 | 2006 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/812301474569050872/text/000020051-20140625074152.txt | http://documents.worldbank.org/curated/en/812301474569050872/pdf/000020051-20140625074152.pdf | IEG concurs with the ICR on the lessons learned emphasizing in particular the importance of government commitment to ensuring success of the program, attention to political economy of reform, and the importance of close collaboration with other partners active in the country. The lessons concerning importance of flexibility provided by the programmatic approach is also well taken although in this case, it appears that the Bank did not fully make use of that flexibility by resetting the program targets in light of the implementation experience.
P094301 | 1st Business Productivity and Efficiency DPL | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2006 | 2006 | 2018 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/385471500561415074/text/110740-PPAR-P094301-P095213-P105029-PUBLIC.txt | http://documents.worldbank.org/curated/en/385471500561415074/pdf/110740-PPAR-P094301-P095213-P105029-PUBLIC.pdf | 6. Lessons 6.1 The experience of this DPL program suggests, once again, that in-depth knowledge and government buy-in were essential in Colombia for designing reform programs with substance. In general, the prior actions of this program reflect well what the World Bank knew about Colombia. For example, in the financial sector, the reforms selected exemplify the World Bank's deep understanding of the problems that had to be solved to strengthen the financial system. The impact of the reforms is beginning to be felt even if the results indicators were inadequate for assessing properly the program's contribution. On the other hand, lack of political commitment to tackle the fundamental problems in Colombia's foreign trade sectorâ€”weak institutions and entrenched protectionismâ€”meant that the reform actions supported under this program addressed secondary issues. Consequently, the impact of the actions pursued was limited. 6.2 Staggering interventions by policy areas presented trade-offs between the breadth and depth of the program. While the approach appeared attractive by allowing the World Bank to tackle a larger number of issues while staying focused at each given moment, it also meant limited attention to some issues and one-off support in some areas. The design of the program could have paid more attention to assessing the implications of such trade-offs for achieving the program's objectives, especially the risks to development outcomes in the long run. The experience with this DPL program suggests that staggering interventions to cover more ground is likely to produce programs of modest relevance and shallow impact.
P094307 | SL-GEF Biodiversity Conservation Project | Western and Central Africa | Sierra Leone | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2010 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/564671476395269230/text/ICRR-Disclosable-P094307-10-13-2016-1476395259770.txt | http://documents.worldbank.org/curated/en/564671476395269230/pdf/ICRR-Disclosable-P094307-10-13-2016-1476395259770.pdf | The ICR included five lessons. The following are emphasized by IEG with some adaptation oflanguage: Inter-sectoral coordination is critical to expand conservation areas and respect boundaries of protected areas.Prior to the project intervention the Ministry of Mineral Resources did consult with Ministry of Agriculture,Forestry and Food Security (MAFFS) when issuing exploration licenses to the private sector. As a result of the project efforts tofoster and promote coordination between these ministries, licenses for mining firms around certain areas outside of a new ProtectedArea boundary were revoked. Building on this experience MAFFS decided to continue this coordination process among line ministriesand agencies, especially with the Ministry of Mineral Resources, the Ministry of Lands and Country Planning andtheEnvironmental Protection Agency. Consistent implementation support is key toachieve success in biodiversity conservation. Willingness and motivation of stakeholders were key issues to achievesuccess in biodiversity conservation. The Forestry Division/ National Protected Area Authority, Project Management Team and theWorld Bank worked together very closely during Project implementation, with joint project visits and several meetings withdifferent beneficiaries and authorities, speaking with one voice in the support of Projects objectives. Continued presenceof these partners raised trust and contributed to a much better relationship between traditional societies living around theProtected Areas and the Government.
P094311 | Integrated Sanitation& Sewerage Infrastructure Project | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2008 | 2016 | 2017 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/685761493305175273/text/ICRR-Disclosable-P094311-04-27-2017-1493305161265.txt | http://documents.worldbank.org/curated/en/685761493305175273/pdf/ICRR-Disclosable-P094311-04-27-2017-1493305161265.pdf | This Review finds the following lessons: Infrastructure projects may result in more positive outcomes ifsub-projects are given sufficient time to finish the works that have already started. The ISSIP 1 experience demonstratedthat had the project been given an extension, the works that started under Phase 2 as well as the capacity development activitiesthat were still ongoing, could have been finished. The Banks decision to close the project based on an overall portfolioreview did not consider the fact that many bottlenecks were resolved and the project started to disburse rapidly during the lastyear. Although the unfinished works were left to be completed through government funding, the availability of this funding was notcertain. Linked with the earlier lesson, follow-on projects need to be designed afterthe earlier project design is tested sufficiently, so that its lessons can bebrought into the next Project. Beforecompleting ISSIP I, ISSIP II project came into effect with similar design bottlenecks. Thus, two problematic projects were createdback to back without any opportunity for improvement.The ICR provided comprehensive lessons. Themost important follow with some modification of language: Complex project design jeopardizesproject outcomes. ISSIP 1 addressed rural sanitation as both a means to improved water quality and an objective in its ownright. Additionally, the project design included multiple innovations, and required high levels of coordination across governmentagencies and funding from multiple stakeholders. Institutional arrangements were weak involving two institutions without clearsplit of responsibility and ownership arrangements. A borrower unfamiliar with World Bank procedures working in a challengingsector is unlikely to be able to effectively carry out such a complex project. A simpler project design, and better institutionalarrangements adapted to the prevailing context would have had a greater likelihood ofsuccess. Technical assistance and policy reform are critical for sustainability ofinfrastructure projects and require stable funding. ISSIP 1 provides additional evidence that infrastructure cannot beleveraged effectively outside of a supportive policy framework and institutional environment. Although the PAD identified criticalcapacity and policy constraints, funding issues and delays in launching Components 2 and 3 pushed TA to the final years of theproject. Given the long time frame required for policy reform and capacity building, this TA would have been significantly moreeffective if it began well before construction started. Had the TA been funded through the IBRD loan or a global trust fund, thisdelay may have been avoided. Citizen engagement is a necessary step that needs to beintegrated in infrastructure projects. By engaging with communities earlier in the project, several problems could havebeen avoided, including the delays in land acquisition, villages blocking construction, and unwillingness to pay connection fees.Difficulties in identifying ownership, negotiating land prices, and navigating clearances from multiple ministries resulted in longdelays in land acquisition. Addressing land acquisition prior to effectiveness could have reduced the risk of implementationdelays. Until the JSDF-funded consultant began work, there was minimal outreach to communities impacted by the project. Morecommunity consultation could have helped build greater support for the project, which was initially opposed by somevillages. Effective procurement requires an understanding of contractor capacity, aswell as sufficient contract supervision. Many of the contractors eligible to bid on the sub-projects lacked the financialresources and technical ability to effectively carry out the complex technologies specified in the bidding documents. This resultedin multiple rounds of bidding, major cost overruns, and delays in beginning construction. Moreover, awarding two or three contractsto the same small contractors constrained their financial capacity to complete the respective contracts, which resulted insignificant delay in completion of their contracts. Prequalification introduced to exclude low-capacity contractors for Phase IIschemes resulted in bid prices significantly higher than the cost estimate, leading to rebidding, which significantly delayed theprocurement process. Also poor or lack of contract supervision during Phase I of the project, also caused delays as well as poorquality works in some cases.
P094315 | BR Municipal APL: Sao Luis Enhancing Municipal Governance and Quality of Life Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2009 | 2016 | 2017 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/451621485875621376/text/ICRR-Disclosable-P094315-01-31-2017-1485875611183.txt | http://documents.worldbank.org/curated/en/451621485875621376/pdf/ICRR-Disclosable-P094315-01-31-2017-1485875611183.pdf | The ICR provided comprehensive lessons. The most important follow with some modification oflanguage:Multiple, interrelated problems of urban poverty in Brazil require phased operations consistent with thelonger-term vision of states and municipalities. The level of difficulty and risk for integrated, multi-sector urbanoperations in fragile environments require a strong diagnosis, a programmatic approach with incremental implementation over alonger engagement period, focused objectives and a stable, institutional champion. Substantial capacity-buildingshould accompany infrastructure investments with a strategy for maintaining institutional and professional continuity andcommitment.Dependence fully on counterpart-financed interventions to support achievement of the PDO needs carefulconsideration, especially if the funds are sourced from public programs. The spread of targeted, sector-specific financingprograms in Brazil, many of them grant-based, is both an opportunity and a risk. Accessing these programs adds complexity throughprogram specific processing and approval criteria, schedules and financial intermediation arrangements. They also create a set ofautonomous project activities which are difficult to control within the project package. Client cost-sharing of owndevelopment should certainly be fostered, but the potential risks and benefits of fully counterpart-financed activities should beweighed. If they are needed, those activities should not be inter-linked with other activities, i.e. their existenceshouldnt be central to the success of the overall project.Ensuring a critical mass of quality engineeringdesigns ready for procurement at effectiveness should be standard practice to identify the correct scope and scale of works, andthe corresponding amount of resources and engagement period. Readiness to implement balanced with a flexible design canposition a project especially in an untried context for more rapid take-off, moderating expectations regarding whatcan be achieved, building momentum and demonstrating results. Similar MLP projects in Brazil suggest the option/benefits ofdividing works into well-defined/sequenced modules, adjustable depending on ambient conditions/timing.Urbanprojects which include resettlement need to analyze the political and economic pressures driving land use and allocation, the risksthese entail for the project and how they will be mitigated. The expropriating authority should take ownership of theresettlement process, collaborating with stakeholders to monitor/build commitment. The Bank should train the counterpart adequatelyto build capacity. The elements driving land allocation scarcity, poverty, competing uses, budgets, speculation need to be understood and reflected in project documents and design, including whether the correct/feasible approach is viainvoluntary or voluntary resettlement. Once land is expropriated the authority needs to ensure control over it, including byassigning social and/or public uses to prevent invasion or reoccupation. The Clients prior agreement and tangible commitmentto resettlement should be a condition of negotiations.The political risks to project implementation, can partiallybe mitigated through enforceable legal agreements and sustainable institutional structures. Risk mitigation needs tocarefully weigh design features for their potential to add to an operations political challenges. Legal agreements are alegitimate instrument only if enforceable. The project experience showed that even highly important issues such as dam safety maynot be addressed due to political issues/rivalries. Turnover in trained counterpart teams is unavoidable but the Bank can insist onvetting new candidates, and on the retention at minimum of fiduciary and ME specialists. An embedded international technicalagency could boost institutional capacity and continuity through such cycles.
P094321 | Project to Support a Rural Economic Development Program | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2006 | 2015 | 2016 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/143221473931322619/text/ICRR14935-P094321-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/143221473931322619/pdf/ICRR14935-P094321-Box396299B-PUBLIC.pdf | The ICR has five lessons, and most important three follow with some adaptation of language:To reduce political interference, transparent and competitive staff selection procedures and performance evaluations need to be included in the agreements for project implementation. Political instability and interference, with the resulting staff changes, affected project implementation. In anticipation of such challenges, it is critical to include mitigation measures, to the extent possible, during project preparation. In similar projects supported by the World Bank in Latin America, transparent and competitive staff selection procedures and performance evaluations are included in the agreements for project implementation.Improving womenâ€™s participation requires specific strategies, including differentiated support. Specific strategies should be considered to foster womenâ€™s participation, such as establishing a specific business line to support the types of businesses opportunities that traditionally attract a high level of interest among women. On the other hand, implementing dissemination events specifically directed at women is a good practice in demand-driven interventions as well as making targeted/customized gender sensitive training available for Rural Productive Organizations.Setting realistic outcome indicators aligned with â€œupgrades/improvementsâ€ supported through the project is critical for success. Over-ambitious targets and imperfect indicators can pose significant challenges to judging a projectâ€™s success. The increase in sales indicator (expressed in value terms) is a challenging indicator of competitiveness in demand-driven projects, as the exact size of the gains to be made by the project investments (in value terms) are difficult to know a priori and many exogenous factors may influence its increase. Overall, outcome indicators aligned to sustainable gains at the level of increased productivity, increased efficiencies, quality improvements, and reduction of post-harvest loses are very appropriate for projects that support improvements in agricultural enterprises.
P094335 | Conservation of Biodiversity and Sustainable Land Management in the Atlantic Forest of Eastern Paraguay | Latin America and Caribbean | Paraguay | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2010 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/702741498853631965/text/ICRR-Disclosable-P094335-06-30-2017-1498853620259.txt | http://documents.worldbank.org/curated/en/702741498853631965/pdf/ICRR-Disclosable-P094335-06-30-2017-1498853620259.pdf | The ICR identifiedfive lessons paragraphs 109-113. Those with some general applicability, with someediting,are summarized below Sustainable landscape management and restoration projects require long timeframes(as compared to 4 years in this project). The close participation of indigenous communities and their champion/leadershipis a necessary condition forsuccessful overall project outcomes In the context ofa weak institutionalframework, sophisticated economic incentive schemes will usuallynot function effectivelyThisReview suggests an additional lesson, namely Monitoring and evaluation is often a weakness that thwarts asatisfactory assessment of a projects results. This is an old lessonbut worth repeating because itwasrelevant to this project.
P094341 | Croatia Programmatic Adjustment Loan 2 (PAL2) | Europe and Central Asia | Croatia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2007 | 2009 | 2010 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/202431474397916347/text/000020051-20140620064745.txt | http://documents.worldbank.org/curated/en/202431474397916347/pdf/000020051-20140620064745.pdf | The ICR draws useful findings and lessons from PAL program. Salient among them are: policy based operations should be designed and implemented in a way that reinforces government ownership and broad political support; and government capacity should be strengthened throughout the process by collaboration with officials and providing them with technical assistance.
P094360 | India: National Vector Borne Disease Control & Polio Eradication Support Project | South Asia | India | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2009 | 2014 | 2015 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/253711474940341118/text/000020051-20150113011006.txt | http://documents.worldbank.org/curated/en/253711474940341118/pdf/000020051-20150113011006.pdf | Lessons drawn from the ICR, adapted by IEG:The introduction of innovations should be supported by a high level of available technical assistance and rigorous M&E to assess those innovations. In the case of this project, external technical assistance was financed by the project budget, but the need for qualified technical staff remained unmet. In addition, M&E capacity was inadequate to properly assess the outcomes.The inclusion of operations research in the M&E design can help to continually improve and update technical strategies during the project period. In the case of this project, incorporating drug resistance, insecticide resistance, and therapeutic efficacy monitoring led to changes in interventions.For a technically demanding project approach, project preparation should include an assessment of the availability of needed skills sets in the labor market. In the case of this project, the lack of availability of necessary technical skills greatly hampered project implementation.
P094365 | First Broad-Based Growth Development Policy Loan | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2006 | 2006 | 2010 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/101771475070656790/text/Guatemala-First-Broad-based-Growth-Development-Policy-Loan.txt | http://documents.worldbank.org/curated/en/101771475070656790/pdf/Guatemala-First-Broad-based-Growth-Development-Policy-Loan.pdf | DPLs are more likely to achieve their objectives when they support the governmentâ€™s reform program and the time frame for the actions they support takes into account the political barriers to reform and the capacity of the government to carry out the reforms. Trying to push for reforms beyond what is politically feasible may endanger the potential success of the program.Broadly designed DPLs are more likely to be more effective when complemented with technical support from Bank-financed projects, projects financed by other International Financial Institutions, government programs, or local institutions. This technical support for the DPLs reviewed made it easier to achieve their development objectives in a timely manner and on a yearly schedule coordinated with the national budget.When the government owns the reform agenda and its process, the Bank can design the program to accommodate risky environments as that ownership permits targeting other areas for reform when some part of the program proves intractable. As reforms in PPP became difficult, the DPL program gave more weight to reforms in the financial sector, which needed the reforms and the government supported it.
P094416 | ST LUCIA WATER SUPPLY INFRASTRUCTURE IMPROVEMENT | Latin America and Caribbean | St. Lucia | Blend | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2005 | 2009 | 2011 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/742691474750465464/text/000020051-20140620064915.txt | http://documents.worldbank.org/curated/en/742691474750465464/pdf/000020051-20140620064915.pdf | Considerable attention must be paid to political economy dimensions when designing water supply projects that include institutional reform and infrastructure improvements. In the case of St Lucia it was decided to have two projects because it was believed that improved infrastructure would increase the attractiveness of the utility to potential private sector operators. In practice, the government backtracked on its commitment to institutional reform and private sector participation once the infrastructure was complete. Additionally, agreeing to an accelerated implementation schedule was not very efficient as it increased costs.Decide on overall development priorities and structure project objectives accordingly. The history of the St Lucia project indicates that from a macroeconomic perspective it was believed that a stand-alone water supply operation would bolster economic growth as a basic input to the development and expansion of tourism. In the short-term this was the case as the success of the World Cricket Cup demonstrated. In the longer-term, however, economic growth from tourism may be jeopardized by falling standards of service provision as the utility is unable to finance routine operation and maintenance. Bundling utility reform together with infrastructure improvements in a single project may have been the better option. An alternative that was not considered was to split water supply provision and recognize that there are customers who fall into two quite different economic groups: (a) provide improved supplies to local commerce and domestic consumers and minimize costs; and (b) allow tourism investors to develop private desalinated water production plants for their own use.
P094476 | Community Development Fund | Eastern and Southern Africa | Sudan | IDA | FCS | Human Development | Social Protection & Jobs | RETF | IPF | 2006 | 2013 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/103601474940821044/text/000012394-20150109094856.txt | http://documents.worldbank.org/curated/en/103601474940821044/pdf/000012394-20150109094856.pdf | These lessons are adapted from the ICR, pp. 31-32:The role of field level mobilizers is essential for raising the commitment of communities in CDD projects, engaging them in project development, facilitating financial participation and maintaining operations and maintenance readiness beyond the completion of a sub-projectThe more straightforward channeling of funds from the central government to the ultimate user, the faster disbursements can become and the fewer opportunities for leakage - based on the government-local community transfer mechanism set up under the projectThis lesson arises from the ICRR and is offered by IEG:In some instances it may be difficult to draw up results frameworks and establish outcome indicators, in the absence of previous experience with community development initiatives. Still, targets should then be established as quickly as possible, once trends can be distinguished.
P094488 | Highway 2 | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2006 | 2015 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/272521474325652165/text/ICRR-Disclosable-P094488-09-19-2016-1474325637034.txt | http://documents.worldbank.org/curated/en/272521474325652165/pdf/ICRR-Disclosable-P094488-09-19-2016-1474325637034.pdf | The ICR draws the following main lessons from implementing the project..(1) The management of a largeroad investment project requires special attention. This projectenvisioned implementation in phases.Whileimplementing a large road investment in phases may aid in tackling other issues not foreseen on the original design,they can contribute tobringinguncertainties that require special attention. Further, having two additional financingsnearly doubled the efforts in terms of project preparation resources and Bank staff time.(2) Land acquisitionlegislation and implementation practices needs to be addressed in a timely fashion to avoid delays in projectimplementation.(3) It is necessary to have detailed design at preparation. In the case ofthis project,detailed design for only 22 km of roads (out of the originally planned 242 km of the highways) were ready atpreparation and detailed designfor the rest of the roads network were to be prepared. Thequality of engineeringdesigns and bid documents that were prepared at entry required additional or revised designs and this in turn contributedtounderestimation of project cost.
P094513 | India: Emergency Tsunami Reconstruction Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2005 | 2012 | 2013 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/980871474585857365/text/000020051-20140625194913.txt | http://documents.worldbank.org/curated/en/980871474585857365/pdf/000020051-20140625194913.pdf | The ICR offers a useful lesson of wide applicability: Frequent and early reviews of the implementation arrangements for emergency projects can assist implementation: Emergency projects are generally based on a limited amount of data, information and knowledge of local institutions. To maximize the effectiveness of resources provided soon after the disaster, frequent reviews of implementation arrangements are needed as more and more data become available over time. IEG also adds the below lessons: Government partnerships with NGOs to address emergency reconstruction can provide a valuable complement to the Bank project: The Government of India successfully coordinated emergency assistance from NGOs, which partly substituted for the use of the IDA Credit. NGOs not only assisted in the rural housing reconstruction component, but also supported the formation of self-help groups at the grassroots level throughout the tsunami-affected coastal area. Technical assistance for training may be required during emergency operations: Even emergency projects can benefit from thorough training in strategic planning and procurement followed by frequent supervision and appropriate and timely technical guidance. Community mobilization through consultation process is essential: In order to mitigate possible friction between those who receive project benefits and those who do not, the Bank and the Borrower should engage with potential beneficiaries (both direct and indirect) to raise awareness of project goals and expected outcomes during the project preparation or initial implementation phase. The Bankâ€™s comparative advantage lies in supporting sustainable emergency reconstruction initiatives and disaster management; other donors may have a comparative advantage in short term recovery assistance. In this project, such a shift in emphasis for the IDA Credit occurred at the restructuring; however, this took place too late to have a significant practical impact.
P094539 | OECS-Catastrophe Insurance | Latin America and Caribbean | OECS Countries |  |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2011 | 2012 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/549471474511683088/text/000020051-20140624203806.txt | http://documents.worldbank.org/curated/en/549471474511683088/pdf/000020051-20140624203806.pdf | The ICR offers a number of lessons of which lessons 2 to 5 are the most important (with some reformulation of language). IEG adds lesson 1:1. In designing a project supporting disaster insurance there needs to be clarity about the linkage between the objectives and how the project design will meet those objectives. If the objective is to reduce financial vulnerability then the design needs to address both means and scale. In this case, the project was supply-driven in the sense that the insurance solution was the modality on offer when the PDO seemed to invite a broader demand-driven approach.2. Risk pooling through disaster insurance can be effective In reducing individual country financial risk, However, reducing costs and sustaining financial strength, calls for an optimum balance between reserves and reinsurance.3. In the establishment of a catastrophe insurance facility, extensive communication with participants is important to ensure that the costs and benefits of its products are well understood.4. The use of parametric insurance ( insurance based on immediately measurable physical parameters) Is particularly important in catastrophe insurance to ensure rapid cash injection through quick payout. However, this injection of funds can only be effective for the impacted country if the country itself has, and can sustain, an effective post-disaster budget execution system.5. Even with a measure of insurance coverage, countries must continue to invest in risk reduction. Catastrophe insurance can only be a part of a broad risk management strategy. The cost of full financial protection would be prohibitive without proactive policy measures and physical investments to address the causes of risks and to mitigate vulnerabilities.
P094551 | Financial Sector Development Policy Loan II | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2008 | 2010 | 2011 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/968511474506504162/text/000020051-20140620085750.txt | http://documents.worldbank.org/curated/en/968511474506504162/pdf/000020051-20140620085750.pdf | The operation is a good example of the positive effects on results of strong government ownership of reforms combined with a strong enabling environment. The operation also shows that a financial sector reform program is a medium to long-term proposition. It needs to deal as a first priority with cleaning up the system (from e.g., NPLs, listing of non-trading stocks, poor corporate information) before it can expect much progress in financial deepening. For example, Egypt's credit penetration looks lower than it was before the reform as a result of the removal of non-performing loans and possibly to crowding out due to lending to the public sector. This suggests in turn that to achieve enhanced access to credit, the design of financial DPLs needs to incorporate a consistent fiscal program that contains excessive public sector borrowing. Furthermore, the failure of the IPO for the remaining stake in Bank of Alexandria, as a possible result of the fall in the stock market during the crisis, suggests that it may be a good idea to include privatization measures in a program that may be sensitive such market developments.The market-related risk associated to the bank of Alexandria IPO was not identified in the PAD.
P094551 | Financial Sector Development Policy Loan II | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2008 | 2010 | 2012 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/963891468325180297/text/700300PPAR0Box0IC0disclosed08080120.txt | http://documents.worldbank.org/curated/en/963891468325180297/pdf/700300PPAR0Box0IC0disclosed08080120.pdf | 4. Conclusions and Lessons Learned 1.78 A main finding of this evaluation is that the reforms supported by the Bank's operations strengthened the financial sectors of the four focus countries and helped them resist the impact of the financial crisis of 2008-2009. 1.79 In all countries the financial systems are still banking oriented but the banking sector is much stronger and generally in a better position to respond to the financing needs of the private sector. Yet, risks remain, as credit growth is often concentrated, credit risk management systems need further strengthening, and, in some cases, credit to state-owned enterprises is not entirely based on market criteria. Moreover, in most of the focus countries, growth in private sector credit has not reached the levels anticipated or desired. 1.80 In parallel with the specific conclusions reached in the PPARs of the individual operations, a number of lessons can be drawn from findings common to the four countries. Even though the measures supported by these operations were not necessarily representative of financial sector reform efforts around the world, lessons drawn from the comparison of experiences may be useful to the governments in question, in addition to expanding the knowledge base regarding the design of these types of operations as well as the approaches they took and the results achieved. (i) The quality of analytical work is crucial for the success of policy-based operations in the financial sector. 1.81 In three of the four countries, the policy content of the operations was closely based on the findings of recently completed FSAPs and further technical analysis conducted during preparation. In Guatemala, the high quality of the technical analysis in the 2000 FSAP and the FSAL preparation was crucial to engage the government's commitment to the reform agenda. This included interactions between the Bank and the Parliament. In Morocco, the 2002 FSAP recommendations were incorporated in the design of the Bank's operation. They were fully accepted by the authorities who endorsed the need for decisive action and committed to overhaul the regulatory framework and undertake a fundamental financial and operational restructuring of state-owned financial institutions. The high quality of the technical analysis (FSAP and Accounting and Auditing ROSC) provided the basis for the policy dialogue and technical discussions during the preparation and implementation of the operation, and underpinned the extensive and effective cooperation between the government and the Bank team during implementation. 1.82 The preparation of the programmatic operations in Egypt also built on the policy dialogue that had been conducted with the authorities over a long time and particularly in the context of the 2002 FSAP, the 2007 FSAP Update, and related analytical work. In addition to valuing the Bank's experience in designing development policy loans in the financial sector, the authorities placed special weight on the Bank's role in coordinating in a concerted and effective way the offers of technical and financial assistance of bilateral and multilateral donors. The division of labor among donors aimed at maximizing the financial and technical benefits for Egypt, although this may also create a challenging task in project monitoring and supervision (see below). In Pakistan, the BSRP was not prepared on the basis of a recent FSAP. The BSDP, however, picked up some of the recommendations of the FSAP carried out in early 2004, which took stock of the banking sector reforms that had been implemented so far. 1.83 In general, the analytical work undertaken by the Bank in the four countries has reflected a significant change in policy direction. Whereas in the 1980s, a main focus was placed on moving away from direct to indirect methods of monetary and credit control, the last two decades have seen a growing emphasis on micro prudential controls that seek to strengthen the soundness and safety of banks, insurance companies and other financial institutions. The Bank's analytical work has stressed the importance of maintaining reasonable macroeconomic and financial stability, entailing moderate inflation as well as small fiscal and external deficits. Less attention has been paid until relatively recently to macro prudential issues, perhaps because the banks and other financial institutions operating in these countries have not engaged in activities that created large systemic risks. Unlike banks in many European countries, there has been little reliance on wholesale funding and limited recourse to consumer and housing loans denominated in, or indexed to, foreign currencies. The authorities have applied higher capital adequacy requirements to reflect the higher credit risks facing banks in developing countries but have not considered a more extensive use of macro prudential controls. (ii) Effectiveness of implementation support is a key condition for results because financial sector reforms are easy to design but difficult to implement. 1.84 This was most evident in Guatemala, where high quality technical analysis and advice was provided as part of implementation support of the Bank's FSAL, not only through the supervision of the operation but also through the FTAL operation of technical assistance. This continued technical and policy dialogue with the authorities and their technical teams was important to maintain the authorities' ownership and commitment to the FSAL development objectives during the course of two administrations. The Bank extended technical assistance that has greatly helped strengthen the capacity of the Bank of Guatemala and the Superintendent of Banks to implement the reform actions supported by the FSAL. The high quality of TA under the FTAL was critical in setting up the deposit insurance and bank resolution agencies and in setting up the legal authority to carry out bank resolution, a system that responded successfully to the two problem banks in 2006 and 2007. Supervision missions of the FSAL, complemented by supervision of the FTAL operation, provided timely technical assistance and advisory services to the implementing agencies, including following the failure of the fourth largest bank during the second half of 2006. 1.85 This intense level of technical assistance efforts is often crucial for the success of policy-based operations, but the needed resources are not always available to Bank teams if, contrary to the case of Guatemala, there is no parallel technical assistance loan. Although grants for TA may be available from other development partners, the coordination with Bank operations can be too slow and complex when country problems must be met quickly to achieve the best results for the country. 1.86 In Egypt, by contrast, the effectiveness of operation implementation support suffered from the division of labor among several participating donors and an apparent failure to provide for joint supervision, implementation completion reports, and evaluation missions. The Bank played a key coordinating role in the division of labor during the preparation of the loan operations but failed to act as a clearing house for implementation support. As a result, crucial comprehensive reports on key aspects of the reform program, such as the effectiveness of the capacity building program in banking supervision and the solidity of the financial and operational restructuring of state-owned commercial banks, have not been compiled. Greater attention needs to be placed on the organization of effective project supervision when several financiers participate in complex operations. Multi-donor operations, as those in Egypt, face a challenging task of effective coordination and supervision, especially when there is a division of labor in the provision of technical assistance that is crucial for the successful implementation of the reform program. 1.87 Enhancing the quality of Monitoring and Evaluation (M&E) frameworks can play a key role in strengthening program implementation and improving outcomes as suggested by evidence from several evaluations conducted by IEG. This requires adequate design of M&E, with well-specified outcome (rather than output) indicators; adequate baselines and realistic targets; strong ownership and alignment with data collection capacity of client implementing agencies. But good M&E also requires a greater transparency of the reform program, through the regular publication of comprehensive data and assessments. Enhanced transparency conveys the continuing strong commitment of the authorities and inspires greater confidence that the reform is genuine and goes beyond mere cosmetic initiatives. Lessons learned are shared with a broader audience and do indeed generate greater demand for further reforms as well as for corrective adaptations when particular measures appear to be counter-productive and overly costly. Lack of transparency veils the whole reform program in excessive secrecy and risks undermining its credibility. 1.88 Egypt offers an example where information gaps do not facilitate monitoring and evaluation of the reform program. The CBE highlights in its annual reports the objectives and broad outlines of the capacity building program but contains little detailed information on the changes that have taken place or an evaluation of the impact of the new approach on bank solvency and efficiency. There is no indication of the success of the new approach in supervising the complex operations of modern banking groups and in redressing the regulatory forbearance that had long characterized its relations with the large state-owned banks. The same also applies to the financial and operational restructuring of the state-owned commercial banks. In Morocco there is regular publication of extensive economic and financial data, including a detailed annual report on banking supervision and bank performance. These permit a comprehensive assessment of the pace and achievements of the reform program. (iii) Multi-tranched financial sector adjustment operations are effective instruments to support major financial sector reforms. 1.89 The success of the Guatemala FSAL and the Morocco FSDPL shows that a multitranched adjustment operation can be very effective in cases of major financial sector reforms that involve the enactment of new basic legislation and its regulations, and the institutional strengthening of the agencies in charge of implementing the reforms, particularly agencies that carry out bank resolution. A multi-tranched adjustment operation can support the process of reform at different stages and respond to unforeseen challenges that could derail the reform process. By contrast, the stand-alone, single-tranched Banking Sector Development Policy Credit for Pakistan did not have a material impact on privatization of state-owned banks, which was concluded prior to this operation. The focus of the operation was on institutional building issues and further strengthening the State Bank of Pakistan, but sustained progress in such areas are difficult to achieve with a stand-alone, single-tranche operation, with no follow up and no associated technical assistance. Similarly to multitranched operations, programmatic loans are also potentially effective in supporting reform programs, but may require more focused efforts to obtain the best results from major reform processes. The slippages observed in the outcomes of the DPL-2 in Egypt, compared with the DPL-1, illustrate, although the two operations were not formally part of a programmatic series. (iv) A strengthened regulatory framework and banking supervision enhance credit risk management and help withstand shocks but do not eliminate the risk of overextension of credit and deterioration of the quality of bank portfolios. 1.90 Reflecting tighter supervision and the adoption of improved risk management practices, but also other factors, such as the limited development of their financial markets, the commercial banks in all four countries that received Bank assistance did not suffer large losses from the global financial crisis because they did not hold toxic assets and did not rely on wholesale funds to support their lending. They did not suffer from either maturity or currency mismatching, while neither bank leverage nor credit expansion were excessively high. Tighter prudential rules and the adoption of improved risk management practices contributed to this favorable outcome. 1.91 Pakistan offers perhaps the best illustration of the effectiveness of these reforms, as the banking system was able to withstand the impact of the global financial crisis as well as the various bouts of domestic turbulence both political and due to the 2010 flooding. The banking sector in Pakistan has not had any major issues following the global financial crisis, partially because the banks in Pakistan did not have significant foreign exposures and also banks were not active in trading or investing in derivatives and other off balance sheet type instruments. NPLs have increased since 2007 but the banks are well provisioned against the potential loss and are actively involved in resolving these loans. In Egypt too, the banking system seems to have withstood the political turbulence in 2011 relatively unscathed so far. 1.92 But Morocco illustrates a case were the banks expanded at a very rapid pace their financing of housing, among other sectors, and faced the risk of growing NPLs in the future resulting from the abrupt fall of sales of housing units targeted to nonresident buyers. Because the banks followed conservative lending policies and insisted on relatively low leverage levels by the property developers they financed, they were not, at least initially, impacted heavily from the collapse of housing sales. However, NPLs from property developers may increase in the future if the economic recovery in Europe is overly slow or if the sovereign debt crisis were to further intensify. The central bank took steps to ensure the resiliency of the banking system by raising the minimum CAR and the commercial banks responded by slowing down the rate of credit expansion, but these actions were taken somewhat late in the process. 1.93 In Pakistan too, the rapid expansion in consumer and SME credit in the period from 2000 to 2007 affected the quality of bank loan portfolios, partly owing to poor credit assessment standards and the absence of a credit bureau during this period. A credit bureau has been established recently and could help enhance the quality of consumer lending by improving the information available to lenders regarding the credit history of borrowers. Banks are well provisioned against NPLs but the absence of a satisfactory property registration mechanism creates uncertainty as to the ownership of property and thus the value of collateral held by banks. 1.94 The evidence reviewed by the PPAR in the four focus countries does not permit to draw insights on the desired sequence of reforms in the financial sectorâ€”a perennial quest of analysts and policymakers. Experience from the reviewed operations, as well as from other countries, suggests that reformers must implement change wherever they can and push for more extensive reforms as they go along. However, the one area where some progress is needed prior to the reform is in improving the regulatory frameworkâ€”otherwise liberalization, deregulation, privatization and restructuring are likely to fail if no attempt is made to strengthen prudential regulation. Strengthening the prudential and regulatory framework is a major challenge and is bound to take time. Moreover, it cannot be done while the system continues to be state-owned, undercapitalized, under-provided, overstaffed, and generally improperly managed. Thus, as also suggested by the experience of the four focus countries of the PPAR, structural reform and regulatory strengthening can only be done in parallel and require the strong and lasting commitment of the authorities and a willingness to learn from experience and adapt as needed. (v) Restructuring of state-owned banks without privatization requires strong safeguards to prevent retrogression into unsound practices. 1.95 In Pakistan, where financial and operational restructuring of state-owned banks was actively pursued with Bank support, transfer of bank ownership to the private sector was considered a key prerequisite for improved financial intermediation. The privatized banks were pushing ahead with institutional development plans to leverage their strengths and address their weaknesses and better position themselves as private sector banks. In Morocco, the restructuring and partial privatization of formerly specialized state-owned financial institutions was also implemented in a decisive and effective way. 1.96 In Egypt the reform program did not include the privatization of the two largest commercial banks nor the large insurance companies but many measures were taken to improve the management of these institutions, which one commentator resembled to an effective â€•privatization of managementâ€– rather than â€•privatization of ownershipâ€–. The reform program has privatized the smallest of the four state-owned commercial banks and has divested public bank shares in joint-venture banks. However, state-owned institutions still control close to 50 percent of banking assets and a higher market share of insurance business. 1.97 A dogmatic approach to the ownership question would not be justified, especially after the public rescue of so many leading private banks and insurance companies in highincome countries around the world during the 2008 global financial crisis. However, as in far too many countries state-owned banks have extended loans on non-commercial criteria to borrowers with strong political connections and have suffered from large and persistent NPLs from both state-owned enterprises and large private sector borrowers, strong safeguards would be required to ensure that their operational and financial reform is viable. In Egypt, the safeguards that have been created to prevent retrogression into unsound practices do not appear to be sufficiently strong since bank lending to SOEs on a long-term basis and thin margins has been resumed. Despite the impressive scope of the overall reform program, the objective of creating a resilient and competitive financial sector appears to call for stronger safeguards. (vi) Better access to credit for the private sector requires a broader set of reforms, including a favorable macroeconomic framework. 1.98 Bank financial restructuring, privatization, and strengthening of the prudential framework and supervision of banks can lay the groundwork for an increase in credit to the private sector on a sound basis but do not necessarily entail an increase in lending volumes in the short term. If anything, as a result of cleaning up the balance sheets of banks and writing down provisioned NPLs or NPLs settled by the government, the volume of outstanding bank credit to the private sector may decline. Depending on country circumstances, a broader array of reforms, especially in the legal area, may need to complement bank sector reform to help achieve a visible improvement of access to credit. 1.99 Key legal reforms include the establishment of an efficient bankruptcy legislation and insolvency regime; the establishment of a credit bureau to share borrower information; the creation of a modern collateral regime. However, these legal reforms are more difficult to implement and take longer to become effective. For example, it takes time to start a credit bureau up, get the data and get the banks to use it. But these reforms are important and should not be overlooked. And because they take time it is important that they be initiated early in the reform process. Other factors that may delay the impact of these legal reforms is that specific institutions may need to change the way they work in order to better serve potential clients. This again takes time, even when a distortion-free regulatory framework is in placeâ€”it takes, for example, time to set up a greater branch network to reach underserviced clients or to strengthen bank appraisal capabilities by assessing projects by cash flow. Bank restructuring and privatization contribute to these outcomes but their impact may not be strong enough if the legal reforms that facilitate access to credit are neglected. 1.100 In Egypt, the provision of credit to the private sector, and more especially to SMEs, continues to fall below relative to the needs for sustainable economic growth and employment creation. Partly as a result of writing down NPLs, partly reflecting tighter bank lending standards, and partly owing to the global financial crisis, and increased government borrowing from the banks as foreign holdings of bonds declined, the credit to the private sector in proportion to GDP declined from 54 percent in 2004 to 36 percent in 2009. Two fundamental shortcomings of the Egyptian legal framework that impede the rapid and sound expansion of credit facilities to SMEs include the absence of a modern bankruptcy law and insolvency regime; and the lack of an efficient registry of collateral security on movable assets. And while a credit bureau has been established, an attempt to develop an SME rating service did not succeed. These shortcomings were not addressed by the two Bank operations reviewed. 1.101 Another example is Pakistan, where growth in private sector credit has not reached the levels anticipated or desired. The Bank's operations were designed primarily to assist the privatization of the NCBs and to shift the structure of the market from one dominated by state-owned, loss-making, and inefficient banks to private, profitable, and well-managed banks. In addition the Bank' operations supported the strengthening of the Central bank and the removal of certain legal and structural distortions in the system. The reform should have facilitated increased lending to Pakistan's private sector and, indeed, banks expanded their lending portfolios post privatization in the years up to 2007. However, as a result of still weak risk management practices and economic shocks, they suffered some losses from NPLs, thus adopting more cautious lending approach. 1.102 In addition, a number of impediments stemming from the macroeconomic and fiscal situation have been present\. (i) inflation rates have been running in excess of 20 percent, resulting in very high interest rates; (ii) state borrowing from the banking system including T-Bills amounts to about 34 percent of bank assets, in effect beginning to crowd out the private sector; (iii) banks are in a position to generate very attractive margins from investing in T-Bills, with little incentive to pursue lending to the SME sector and consumers which is much more risky and carries a much higher administrative cost. Maintaining macroeconomic stability appears a necessary complement to bank sector reform in order to achieve viable growth in private sector access to credit. Similar trends have developed in Egypt, where bank lending to the private sector is being crowded out by growing bank holdings of government securities, as the budget deficit has steadily increased and foreign investor demand for government bonds has decreased since the onset of the global financial crisis.
P094650 | IQ-EMERGENCY WATER SUPPLY PROJECT | Middle East and North Africa | Iraq | IBRD | FCS | Sustainable Development | Water | IDA | IPF | 2008 | 2016 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/234151472846255278/text/Iraq-IQ-Emergency-Water-Supply.txt | http://documents.worldbank.org/curated/en/234151472846255278/pdf/Iraq-IQ-Emergency-Water-Supply.pdf | The following key lessons are drawn from the Lessons Learned section of the ICR (p.17-18). Realisticproject design: Project design should be realistic and appropriate to the institutional capacity of the client taking intoconsideration the qualifications and skills of the staff. In this project, most of MMWP staff being of engineering backgroundproved to be less efficient in monitoring and analyzing socio-economic issues. MMWP staff as well as contractors staffneeded more training on modern project management approaches including interaction with end users and clientsatisfaction. Close monitoring of contractor capacity: A cautious approach should be adopted beforeawarding multiple contracts to the same bidder, who should demonstrate theability to mobilize funding, equipment andpersonnel, and achieve timely implementation. In this project,two Works components were awarded to the same contractor.However, their scope was too large to managein parallel,thus resulting in the termination of Al-Nasr componentscontract. Adequate supervision of institutional aspects: Supervision should be more proactive towardsthe implementation of activities aimed at institutional development of the implementing agency. When necessary, adequate changesincluding restructuring of the project should have been considered at the mid-term reviewto ensure achievement of theinstitutional objectives.
P094692 | Kenya Coastal Development Proejct | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/115461524145271481/text/Kenya-KE-FMSCEDP-Coastal-CD-GEF-FISH.txt | http://documents.worldbank.org/curated/en/115461524145271481/pdf/Kenya-KE-FMSCEDP-Coastal-CD-GEF-FISH.pdf | The following three lessons come from the ICR with some adjustment of language:1.Private Sector engagement and financing through the private sectoror microfinancing organizations is an importantfactorin supporting SMEs and community subprojects. In this case, while the project trained over 200 SMEs andprovided them with business skills, the training hadmodest impact and most SMEs were not commercially viable by projectclosing. According to the ICR, an engagement strategy and involvement of microfinancing organizations and other private sectoractors could have better facilitated the SMEs with gaining access to markets and financial resources (ICR, para 42). This will beimportant in the follow-on project.2. Communication strategiescan beimportant inensuring collaboration, particularly when there aremultiple institutions and a broad and diverse stakeholder base.In this case, the project benefited from a communication strategy and tools (video, website) to create a project brand andidentity. This served as an incentive forstrong collaboration (ICR, para 67c). However, it needs to be sustained. In thiscase, the website was no longer active at the time of the ICRR.3. Early restructuringisimportant to address early roadblocks but needs to build on strong early ME. In this case, the early projectrestructuring was instrumentalin reversing severe qualityat entry limitations, weak borrower ownership, and inadequateinstitutional arrangements. However, the early restructuring was stillhandicapped by weak early ME and weakness inindicators.
P094694 | Eritrea HIV/AIDS/STI, TB, Malaria and Reproductive Health Project (HAMSET II) | Eastern and Southern Africa | Eritrea | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2005 | 2010 | 2012 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/796081474511605803/text/000020051-20140624193239.txt | http://documents.worldbank.org/curated/en/796081474511605803/pdf/000020051-20140624193239.pdf | An implementor-based approach can realize synergies more effectively than an approach defined by individual diseases. Integration of three vertical disease programs, together with reproductive health and human resource strengthening, by implementors -- but only where sufficient capacity exists -- allows for multiple integrated interventions and facilitates the search for synergies and efficiencies.Continuity of staff matters. By the time HAMSET II closed, most staff in the PMU had worked together on HAMSET projects for ten years, facilitating collaboration, trust, and efficiency.If a project chooses to rely on external surveys to evaluate performance, it must exercise some control over the mechanisms and timing of those surveys. In this case, the project relied on DHS data for a large share of endline data, but the 2010 DHS data were not available at closing. As a result, some data presented as endine data were from two years prior to closing.
P094704 | Ethiopia - Financial Sector Capacity Building Project | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2006 | 2012 | 2013 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/830171474509797451/text/000020051-20140625191742.txt | http://documents.worldbank.org/curated/en/830171474509797451/pdf/000020051-20140625191742.pdf | The following generic lessons were drawn from the ICR with some adaptation of language: Project design needs to be simple, with PDOs that are both relevant and achievable, and the M&E must incorporate well defined and measurable indicators. Furthermore, design should be based on a careful assessment of the governmentâ€™s ownership of proposed interventions, and should focus only on those that are likely to elicit sustained government commitment.During design, the Bank should accurately assess the local capacity of implementing agencies, and should include necessary improvements as conditions for effectiveness.Appropriate restructuring actions should be considered if major parts of a project are cancelled.Projects with technically complex components require a realistic time horizon to be implemented. In addition, IEG identified the following lesson related to development of the financial sector:. It is not realistic to expect to achieve modernization of the financial system through a single capacity building operation. This is even more the case when, as here, in-depth knowledge of financial sector constrains is limited due to a lack of relevant analytical work, and a track record of successful interventions specific to the countryâ€™s financial sector. Building up a modern financial sector requires continuous Bank engagement through knowledge services, country dialogue and a programmatic approach in lending operations.
P094715 | National Biodiversity Mainstreaming and Institutional Consolidation Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2008 | 2015 | 2016 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/213181473930504600/text/ICRR14940-P094715-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/213181473930504600/pdf/ICRR14940-P094715-Box396299B-PUBLIC.pdf | The ICR reports a number of lessons:Environmental mainstreaming requires a degree of complexity and inclusion to generate broad ownership.However, IEG would draw a distinction between including a wide range of stakeholders in a discussion, and using them all as direct implementers, which may or may not be required.The ICR states that it is important for a results framework to acknowledge achievements by individual agencies. However, IEG would note that this is not usual intended goal of a results framework, and that other mechanisms could be used for assigning institutional credit while a results framework could be used for assessing results.Establishing a fixed pool of funding for each implementing agency helps to promote cooperation and avoid inter-agency rivalry for funding, but allowing for some flexibility could help to drive resources to agencies with more capacity to implement outcomes. IEG would note that it is usual to assign resources based on which outputs are needed in order to achieve project objectives, rather than as a reward for successful implementation. IEG also finds that:Projects may not be effective in achieving specific objectives if they have a design that is relatively unfocused. If a project design describes a process to be followed rather than actual outputs, then there is a risk that the supported outputs may not have a coherent design.Projects that seek to have impact through support of sub-projects should be clear about the expected goals of those subprojects and should establish monitoring and evaluation systems to assess whether those goals were achieved. Progress on these goals should then be reported in the project's ICR.
P094715 | National Biodiversity Mainstreaming and Institutional Consolidation Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2008 | 2015 | 2021 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/764121611172158662/text/Brazil-National-Biodiversity-Mainstreaming-and-Institutional-Consolidation-Project-and-Sustainable-Cerrado-Initiative.txt | http://documents.worldbank.org/curated/en/764121611172158662/pdf/Brazil-National-Biodiversity-Mainstreaming-and-Institutional-Consolidation-Project-and-Sustainable-Cerrado-Initiative.pdf | Lessons 2.35 A critical element for the success of projects that seek to promote the mainstreaming of biodiversity across sectors, both public and private, is strong ownership and active participation by representatives of the various institutions involved throughout the project's life. This element was present for PROBIO 2 but was largely lacking in the case of GEF Cerrado, which was additionally complex because two levels of government were involved. 2.36 A firm up-front understanding of the underlying political, economic, and territorial contexts of the geographic area in which a project is seeking to establish new or expand existing protected areas is essential to properly gauge the possibilities of achieving such an objective. The most significant impediment to the creation of new protected areas in the Cerrado at the state level proved to be bureaucratic and political resistance to doing so. Neither of these constraints was identified as a risk at appraisal, even though it was well known that large parts of the Cerrado were already occupied by medium and large export-oriented commercial agriculture and ranching establishments. Project preparation would have benefited from a comprehensive stakeholder analysis, if not a full consultation, which would have allowed both the Brazilian government and the World Bank to better anticipate potential support for and opposition to the actions proposed. 2.37 Experience in Brazil (and elsewhere) has shown that government commitment to project objectives and design can shift significantly over time due to changes in administrations, both at the federal and state government levels. For GEF Cerrado, this risk was recognized at appraisal but assigned a low possibility of affecting project implementation. In retrospect, it should have been considered more seriously up front, especially given the project's unusually long gestation period. 2.38 Lessons from environment projects that use concessional financing, both successful and unsuccessful, can have policy implications that extend beyond the original project's intentions. Despite its considerable design shortcomings, implementation difficulties, and moderately unsatisfactory outcome, the GEF Cerrado Project directly contributed to evolving World Bank support for the biome. One of the main project outcomes was finalization of the Action Plan for the National Sustainable Cerrado Program, which aimed at preventing and controlling deforestation and fires in the biome and was largely implemented through nine later World Bankâ€“managed projects financed by trust funds from sources other than GEF.
P094755 | Yemen Health & Population | Middle East and North Africa | Yemen, Republic of | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2011 | 2018 | 2019 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/760501544638150572/text/Yemen-Republic-of-RY-Health-Population.txt | http://documents.worldbank.org/curated/en/760501544638150572/pdf/Yemen-Republic-of-RY-Health-Population.pdf | The ICR (pp. 33-34) offered several lessons, including the following lessons restated byIEG:In countries with fragility, conflict, and violence situations,a focus on outreachservices and human resources enhances the reach of service delivery to underprivilegedpopulations. The projecttripled the number of trained health personnelover what wasoriginally planned and developed a coordinated outreachmodel of service delivery to increase access and utilization of essential health services by targetedpopulations.Flexibility and alternative supervision arrangements in countries withfragility, conflict, and violence situations facilitate the Banks implementation support and oversight. Whenthe Bank did not have a physical presence in the country and could not organize field supervision missions, the Bank teamintensified both virtual meetings and electronic communications, and organized reverse missions in other countrieswhere government and United Nations(UN) partnerscould attend.Leveraging the capacitiesof UN agencies advances project implementation. The project initially used the support ofUNagencies forthe procurement of drugs and medical supplies. In view of the volatile country situationthat limited implementationcapabilities of the health sector, the Bank pursued the broadening of the role of UN agenciesalso toincludeimplementation support on the ground and distribution of medicines.
P094784 | EC Chimborazo Development Investment Project (PIDD) | Latin America and Caribbean | Ecuador | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2008 | 2014 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/465651468189545949/text/ICRR14740-REVISED-P094784-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/465651468189545949/pdf/ICRR14740-REVISED-P094784-Box393191B-PUBLIC.pdf | The ICR (page 25-26) draws the following main lessons from the project.(1) Leadership and ownership can be very important in project implementation. In the case of this project, the prefect understood the project's strategic context and envisaged the longer term potential for the province by working successfully with the Bank. The prefect could further aid in the execution of the project despite significant difficulties in Bank country relations during much of the project period.(2) The indirect benefits of an investment operation can be important. The project had a strong emphasis on local institutional capacity building and this aided in focusing on agricultural advancement rather than the constant struggle for water.(3) The permanent presence of an M&E specialist in the implementation unit can be helpful not only for the physical component of the project, but also for instilling the idea of M&E and institutionalizing its practices.
P094869 | Growth and Social Protection Technical Assistance Credit | Latin America and Caribbean | Dominica | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2007 | 2011 | 2012 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/252181474855039865/text/000020051-20140625061311.txt | http://documents.worldbank.org/curated/en/252181474855039865/pdf/000020051-20140625061311.pdf | The ICR listed a number of narrow/project specific lessons and general application lessons, including the following (i) reform programs need to be kept simple and well focused so as not to diffuse Bank and Government efforts too broadly.
P094897 | Second Broad Based Growth Development Policy Loan | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2007 | 2008 | 2010 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/101771475070656790/text/Guatemala-First-Broad-based-Growth-Development-Policy-Loan.txt | http://documents.worldbank.org/curated/en/101771475070656790/pdf/Guatemala-First-Broad-based-Growth-Development-Policy-Loan.pdf | DPLs are more likely to achieve their objectives when they support the governmentâ€™s reform program and the time frame for the actions they support takes into account the political barriers to reform and the capacity of the government to carry out the reforms. Trying to push for reforms beyond what is politically feasible may endanger the potential success of the program.Broadly designed DPLs are more likely to be more effective when complemented with technical support from Bank-financed projects, projects financed by other International Financial Institutions, government programs, or local institutions. This technical support for the DPLs reviewed made it easier to achieve their development objectives in a timely manner and on a yearly schedule coordinated with the national budget.When the government owns the reform agenda and its process, the Bank can design the program to accommodate risky environments as that ownership permits targeting other areas for reform when some part of the program proves intractable. As reforms in PPP became difficult, the DPL program gave more weight to reforms in the financial sector, which needed the reforms and the government supported it.
P094916 | WAPP APL 2 - OMVS Felou Hydroelectric Project | Western and Central Africa | Western and Central Africa |  |  | Infrastructure | Energy & Extractives | IDA | IPF | 2006 | 2015 | 2016 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/812301467057875468/text/ICRR-Disclosable-P094916-06-27-2016-1467057859843.txt | http://documents.worldbank.org/curated/en/812301467057875468/pdf/ICRR-Disclosable-P094916-06-27-2016-1467057859843.pdf | The ICR provides useful lessons that are well grounded in the projects implementation experience. These areparaphrased below:Careful consideration of any limitations in the capacity of theimplementingagencyand the inclusion in design of mitigating measures would help to avoid delays and other operationalinefficiencies.SOGEM was supported by an engineering consulting firm duringconstruction. Nevertheless, implementation was challenging and there was about a four-year delay in the completion of theproject. SOGEMs capacity issues were among the main contributing factors leading tothe slow implementationofthe project. A capacity building component focused on SOGEM could have strengthened the projects readiness forimplementation.Early preparation of bidding documents, especially of keycomponents of large projects,would help to avoid delays. It took a long time to award the design-buildcontractor of the Felou project under a two-stage bidding process. Bidding documentsshould be readybefore Boardapproval,especially when large projects are involved.Careful consideration of arrangements toaddress the potential build-up of accounts receivablecould help to avoidoperationalinefficiencies.There is arisk of irregularity in the payment bythe three national utilities, asthey are financially constrained.Arrangementsthat may helpto preventthe build-up of accountsreceivable may include mechanisms thatgive the system operator ability to cut supply in case of arrears and/or provide someleeway in tariff adjustments.Shortcomings in operation or maintenance of hydroelectric projects canhave very severe impacts, including in terms of safety issues, loss in generation or heavy rehabilitation costs.Typically, the project company takes the responsibility of performing OM activities. The track record ofhydroelectric projects where the OM responsibility has been taken by a company other than the project company, as also shownbythe experience with the Manantali project, points to the importance of putting in place arrangements that ensure theplants ability to generate electricity consistent with expectations atappraisal.Forcovenants to be meaningful,it is important that the implementingagency has the autonomy necessaryto comply with them.SOGEM was requiredto maintain a levelof accounts receivable of less than 90 days and to have net revenues to be at least 1.2 times the estimated maximum debt servicerequirements. However, SOGEM did not have the operational and financial independence necessary tocomply with theserequests.
P094917 | WAPP APL 1 (2nd Phase - COASTAL TRANSMISSION BACKBONE) | Western and Central Africa | Western and Central Africa |  |  | Infrastructure | Energy & Extractives | IDA | IPF | 2006 | 2016 | 2018 | ICRR | >=50 million & <100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/661191530232562167/text/Western-Africa-3A-WAPP-APL-1-CTB-Phase-2-Project.txt | http://documents.worldbank.org/curated/en/661191530232562167/pdf/Western-Africa-3A-WAPP-APL-1-CTB-Phase-2-Project.pdf | The ICR draws the following main lessons from the experience of implementing this project (with some modification of language)(ICR, pages 20-21).1. Risks associated withhaving two implementing agencies need to be considered at design.Although this project was implementedindependently by two implementing agencies, it was in essencean integratedendeavor that connected several countries. The experience of this project showed that establishing a single company to build,operate and maintain the facilities and thereby avoiding the disruptions that originate from piecemeal construction, maybemore effective in performing these types of projects.2 . The risks associated with participation in amulti-donor project need to be taken into account during preparation and the full range of the Banks instruments must be usedto address unanticipated investment needs during implementation. In this project, theBank contribution to the Beninproject componentwas restricted to financing the CEB control center and providing overall supervision of the transmissionline construction funded by other donors.An operationalresponse to addressing gaps in funding could have beenpivotal to proactively addressing implementation issues.3 . Government commitment needs to be secured throughinvolvement of a high-level steering committee for regional projects. Such a committee could help in coordination ofthedifferent players.4 . A lead funding agency needs to be designated at design. In this project,the West Africa Power Pool (WAPP) had not assigned the Bank as the lead coordinating agency and consequently the Bank was unable toproactively address issues associated with funding gaps that arose in the Benin project component.5 . Betterdesign of results indicators is required at preparation to monitor performance. One shortcoming of this project was thelack of indicators for monitoring the Banks contribution as distinct from the whole operation.
P094919 | WAPP: The First Phase of the Inter-Zonal Transmission Hub Project of the WAPP (APL3) Program | Western and Central Africa | Western and Central Africa |  |  | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2019 | 2020 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/844571592421969668/text/Western-Africa-3A-1st-Ph-Inter-Zonal-Transm-FY11.txt | http://documents.worldbank.org/curated/en/844571592421969668/pdf/Western-Africa-3A-1st-Ph-Inter-Zonal-Transm-FY11.pdf | The ICR derived severallessons from the projects implementation experience. The main ones are presented here,with some paraphrasing:Smooth and speedy project implementation requires the advance preparation of key technicalstudies and the launching of major procurement packages. The three-year extension of the projects closing date wasdue in large part to the late preparation of the detailed engineering studies and the ensuing change in scope of works and latefinalization of the bidding documents. Thus, it is essential to conclude all preparatory studies and use an advanced procurementapproach for large and capital-intensive infrastructure projects. In the particular case of this project, French versions of theprocurement documentation critically needed to be prepared in advance of project approval.Cross-effectivenessclauses among co-financiers could entail risk of delays. Requirements to comply with legal covenants andcross-conditionalitycan delay loan/credit effectiveness and start-up of implementation. For this project, 18 months ofdelay occurred before effectiveness because the other financiers experienced delays in obtaining approval fromtheirrespective authorities. Multi-donor project should be presented to the Board only when all have approved the arrangements. Also,the number of covenants needs to be restricted.Complex and multi-country/multi-donor projects require a jointprocurement strategy, a Joint Implementation Committee, and a common Owners Engineer to ensure adequate coordination andeffective implementation. These provisions would help ensure minimal disruption and successful projectimplementation in situations where thereare multiple contractors constructingdifferent sections of the transmissionline. It would also help avoid different owners engineers providing differing and potentially conflicting advice on thesame project. Joint implementation would also help ensure that all stakeholders are provided with the same level of information andinvolvement.Adequate safeguards supervision is critical in ensuring robustness in implementing environmental andsocial mitigation measures. Accidents thatoccurred might have been avoided if the following actions had been takenahead of time, instead of in reaction to the accidents after their occurrence: (i) certification of workers carrying outinstallations especially at heights; (ii) involvement of community organizations/NGOs in the implementation and/or monitoring ofsocial programs and public sensitization; and (c) securing all work sites with wooden barricades before starting any works. Albeitlate, these measures were put in place to greatly reduce the risk of fatal accidents from happeningagain.
P094919 | WAPP: The First Phase of the Inter-Zonal Transmission Hub Project of the WAPP (APL3) Program | Western and Central Africa | Western and Central Africa |  |  | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2019 | 2025 | PPAR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099458412022434923/text/SECBOS-a6a653d5-14c0-499d-b6cf-b545d1777b15.txt | https://documents.worldbank.org/curated/en/099458412022434923/pdf/SECBOS-a6a653d5-14c0-499d-b6cf-b545d1777b15.pdf | 4.1 Distribution networks need to be expanded beyond the immediate areas supported by donors under village electrification programs to gain the full benefits of large transmission projects on electricity access. This project electrified 25 villages along the BZ Transmission Line to support increased national electrification. Our assessment shows that the number of households reached averaged only 25 percent in the electrified villages, and unconnected households cited their distance from the village centers as the reason they are not electrified. With the potential for an increased power supply to Burkina Faso from Ghana and other WAPP countries as integrating member countriesâ€™ networks expand, Burkina Faso could rapidly expand access to electricity by addressing both demand-side constraints (for example, cost barriers, awareness of the potential benefits of access to electricity) and supply-side constraints (for example, technical standards) to expansion. 4.2 Implementing regional integration projects requires well-coordinated institutional and procurement arrangements among the recipient countries and the financing agencies. Drawing on previous experiences with transmission line projects, the project was designed for having one contract with a single ownerâ€™s engineer, establishing joint procurement processes, and setting up a high-level implementation coordinating committee. However, the financing agencies did not coordinate their conditions, which delayed effectiveness of the World Bank grant and credit by 18 months and contributed to a three-year delay in the project. Additionally, the donors did not have a formal agreement on a joint procurement strategy. Their informal understanding was that the project would use World Bank procedures and processes, but it was not implemented, and each donor followed its own rules, which delayed procurement of the main contracts and contributed to the projectâ€™s overall implementation delay.4.3 Project preparation readiness and, critically, completing engineering designs and bidding documents before project approval are essential for implementing large infrastructure projects quickly. Although the World Bank funding allowed for retroactive financing, the ownerâ€™s engineer, who was responsible for finalizing the engineering designs and bidding documents, was not engaged until 12 months after credit effectiveness, delaying the documentsâ€™ finalization. After the ownerâ€™s engineer was hired, design changes on the Ghanaian side of the transmission line and the Bolgatanga substation delayed the contracts procurement process for the transmission line even more. 4.4 The design and implementation of regional projects successfully require assurance that financing is available and a high-level commitment from national governments or supranational organizations. The World Bankâ€™s approval of funding for a sequence of projects supporting the development of the WAPP program provided assurances to the national governments of the ECOWAS that funding was available for the projects. The approval gave momentum to the preparation and implementation of the projects under the APL. Jointly developed strategic frameworks at the supranational level helped build commitment to the projects and programs.
P094967 | First Social Sectors Institutional Reform Development Policy Loan (SIR DPL1) | Europe and Central Asia | Bulgaria | IBRD | Non-FCS | Human Development | Education | IBRD | DPF | 2007 | 2008 | 2011 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/835901475100372628/text/Bulgaria-First-Social-Sectors-Institutional-Reform-Development-Policy-Loan-sir-Dpl1.txt | http://documents.worldbank.org/curated/en/835901475100372628/pdf/Bulgaria-First-Social-Sectors-Institutional-Reform-Development-Policy-Loan-sir-Dpl1.pdf | The lessons arising from the overall series are presented in the ICRR for SIRDPL III, project ID 115400.
P095003 | NG-RURAL ACCESS & MOBILITY PROJECT-Phase 2 | Western and Central Africa | Nigeria | Blend | FCS | Infrastructure | Transport | IDA | IPF | 2013 | 2021 | 2022 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099350012022120748/text/Nigeria000NG0RAMP0PHASE02.txt | http://documents.worldbank.org/curated/en/099350012022120748/pdf/Nigeria000NG0RAMP0PHASE02.pdf | This review has drawn three lessons based on information in the ICR.Lack of sufficient funds and institutionalarrangements for maintaining rural roads can adversely affect the rural populations sustained access to improved roadsbeyondproject closure. While the quality of civil works to rehabilitate the first stage roads was low, the projectactivities resulted in the improvement of the road conditions in the four states. However, local state authorities do not havesufficient funds nor are institutional arrangements in place to adequately maintain the roads. The State Road Maintenance Fundscould not be established. At the time of the Environmental and Social Safeguards Audit in March 2021, it was observed that someroads rehabilitated under the project had already started deteriorating and been in bad conditions because of lack ofmaintenance.The community-based road maintenance approach can be a viable solution for routine maintenance ofrural earth roads while positively impacting the social and economic well-being of women. Communities in the project areasdemonstrated interest in participating in routine maintenance of earth roads after their rehabilitation. This increased the localcommunities ownership of the road infrastructure and also provided an opportunity to women to contribute to the communitywhile economically benefitting from these activities in the form of direct and indirect income. A total of 2,445 people from thecommunities participated in road maintenance of which 726 were women (30 percent of the participants). However, the sustainedsuccess of this approach depends on the availability of local funds to maintain roads under this approach.A heavyprocurement load for investment activities can force the project implementation units with low capacity to focus more on civilworks and neglect technical activities for sector and institution reforms. The procurement processes of roadrehabilitation works that were to be implemented in two phases were complex for the SPIUs that did not have sufficient procurementcapacity. First, approximately 800 km of roads that were identified during project preparation as the first phase of roads were tobe rehabilitated, and lessons learned during the implementation of the first phase were expected to be used to improve theefficiency of the intervention in the second phase. Each SPIU had to procure and manage more than 100 contracts for roadrehabilitation during project implementation. Therefore, the SPIUs focused mostly on the implementation of road rehabilitation andriver crossings works, which had greater visibility and direct benefits to the population. This resulted in SPIUs paying lessattention to the technical assistance activities to reform the rural road sector, and most of these activities could not beimplemented.
P095012 | Tunisia: Sustainable Municipal Solid Waste Management Project | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2007 | 2014 | 2015 | ICRR | >=10 million & <25 million | Highly Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/391811468189543213/text/ICRR14729-P095012-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/391811468189543213/pdf/ICRR14729-P095012-Box393183B-PUBLIC.pdf | A number of lessons were selected from the ICR, with some adaptation of the language: In order to improve solid waste management at the municipal level, it is critical that lower government levels have sufficient autonomy and accountability.It is essential to develop a communication strategy with local communities to identify locations for new solid waste facilities. Under this project, opposition to opening of new landfills led to proliferation of illegal dump sites. It's important to develop solutions to integrate waste pickers into the solid waste management system. These will depend on recycling procedures, local circumstances, and waste pickersâ€™ traditional lifestyle, among other factors.The following lesson was identified by IEG: A close monitoring of carbon projects allows for the detection of poor performance to allow corrective actions.
P095028 | Uruguay Social Program Support Loan | Latin America and Caribbean | Uruguay | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2005 | 2006 | 2007 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/763351474898728136/text/000020051-20140617133451.txt | http://documents.worldbank.org/curated/en/763351474898728136/pdf/000020051-20140617133451.pdf | The ICR draws the following lessons:In middle-income countries with highly skilled government counterparts, it is critical to adopt a social participatory and consultative process in the preparation of operations.The institutional restrictions of a new administration must be taken into account when preparing an operation. In the SPDPL, the new government was able to work with the Bank in designing policy reforms and preparing the loan documents, and this helped to build ownership of the program.A single-tranche DPL can be an effective instrument for the Bank to provide continuity to reform efforts and lay the foundations for programmatic sector dialogue when a new administration takes office.
P095050 | Kenya - Natural Resource Management Project | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2007 | 2015 | 2016 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/207631468194954362/text/ICRR14893-P095050-Box394872B-PUBLIC.txt | http://documents.worldbank.org/curated/en/207631468194954362/pdf/ICRR14893-P095050-Box394872B-PUBLIC.pdf | Based partly on the ICR, the following are the three most important lessons: 1. A simple and limited project design that considers institutional capacity and promotes active stakeholder participation is especially appropriate for complex natural resource situations where there is potential for land rights conflict. Sufficient time, budgetary needs and staff capacity are critical factors during preparation to ensure that all the project elements are coordinated. In this case the Project design was too broad and ambitious to be implemented within the planned duration partly because it addressed multiple reforms across several implementing agencies that had insufficient capacity and staff retention.2. In-depth understanding of the political context and other historical evidence is critical in designing community-based natural resource management initiatives. In this case, there was insufficient appreciation at the design stage of the political and historical context of the land issue.3. Sustainable natural resource management actions should consider: (i) incentives for resource users to avoid free-rider behavior; (ii) secure rights to resources for local communities; (iii) strong environmental and socio-economic monitoring; and, (iv) effective coordination among stakeholders since changes in upstream watersheds affect downstream users and this can drive conflict.The ICR contains a number of other useful lessons, some more specific to Kenya.
P095081 | SD- Emergency Transport and Infrastructure Development Project - MDTF | Eastern and Southern Africa | South Sudan | IDA | Non-FCS | Infrastructure | Transport | RETF | IPF | 2006 | 2012 | 2015 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/168061475115705095/text/000020051-20150312115027.txt | http://documents.worldbank.org/curated/en/168061475115705095/pdf/000020051-20150312115027.pdf | 1. Regardless of the level of investments put in for rehabilitating the infrastructure, adequate amount of maintenance funding and the capacity of the responsible agencies to carry out timely and proper maintenance are key for the ensuring sustainability. Therefore, it is prudent to establish a stable and sustainable road maintenance financing scheme and build the necessary capacity of responsible agencies. 2. While engagement of World Food Program and UNOPS enabled good oversight and fast tracked civil works, it was important to put in a transition plan to shift the work from UN agencies to local contractors.3. The Bank's active involvement, from project identification, preparation, to implementation support is essential in a fragile or conflict affected country whose institutional capacity is weak.
P095091 | Mali-Fostering Agricultural Productivity | Western and Central Africa | Mali | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2010 | 2020 | 2020 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/305051590112396489/text/Mali-Mali-Agricultural-Productivity-GEF-SIP.txt | http://documents.worldbank.org/curated/en/305051590112396489/pdf/Mali-Mali-Agricultural-Productivity-GEF-SIP.pdf | The ICR included eight lessons. The following three are emphasized with some adaptation oflanguage: To ensure capturing early stage data, it is important to have the ME system fully designedand ready to implement once the project becomes effective.The project experience showed that relegating thesystems design to the projects implementation phase fails to capture early stage data, the system often becomesunder-resourced, and eventually becomes unhelpful as a management tool. For example, ensuring baseline information/studies areundertaken before project implementation begins. Projects implemented in challenging conditions like Mali need tobe more focused to ensure smooth implementation and achievement of outcomes. This includesbettertargeting at design stage, and strategic choice of value chains to accelerate the pace of implementation. Thecomplexity ofdemand-driven approaches need to be tempered by limiting the menu of options (type of support, commodities included, etc.), and byavoiding a geographical scattering of interventions. Successful Risk Management requires integratingsystemic risks (social, political and economic)in the design choices combined with the development ofadequateadaptation/mitigation measures. The projects risk analysis at design failed short of identifying any macro risks,yet the emerging crisis in 2012 posed multiple challenges to implementation. Innovations in terms of activities andimplementation arrangements have to be gradually introduced in riskier contexts and some contingency plans should bedeveloped for the main risks in order to avoid as much as possible disruptions to implementation and ad-hocdecision-making.
P095114 | Rampur Hydropower Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2008 | 2017 | 2016 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/423511473923659338/text/ICRR14936-P095114-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/423511473923659338/pdf/ICRR14936-P095114-Box396299B-PUBLIC.pdf | The ICR reviewer derived the first and the second lesson, while the third lesson is adopted from the 8 lessons provided by ICR.Lack of relevant output and outcome indicators for institutional strengthening makes it difficult to measure the efficacy of the project. In this project, output and outcome indicators for the second objective are simply about implementation of environmental and social safeguard except for one indicator about training outputs.Lack of M&E arrangements with partner organizations makes it difficult to monitor the progress of the project. In this project, SJVN and the Bank could not have enough information from the state authority on the progress of compensatory afforestation because there were no M&E arrangements with the state authority.Where significant resettlement and livelihood issues are anticipated, it is essential to build trust through early consultation, communication and interaction with the local community. In this project, acceptance from the local community was gained mainly due to the strong effort by SJVN to build a good relationship with the affected community from very early on.
P095115 | Post-Chernobyl Recovery Project | Europe and Central Asia | Belarus | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2006 | 2014 | 2015 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/544501474942692631/text/000012394-20150109151048.txt | http://documents.worldbank.org/curated/en/544501474942692631/pdf/000012394-20150109151048.pdf | Among the lessons noted in the ICR, the following are highlighted: 1. Energy efficiency delivers considerable macroeconomic benefits, especially in countries that depend on imported energy. The project showed that, despite shortcomings in sector policies (e.g. pricing reforms), improving efficiency in delivering and use of energy services is highly beneficial to both consumers and the country at large. The improvements in public buildings (schools, health clinics, etc) also helps local administrations' budgets.2. Participation of users and beneficiaries has multiple benefits. The Project encouraged participation of beneficiaries, especially school children and administrators; this increased their understanding of, and commitment to, the project and thus improved end results. This also motivated schools to include energy efficiency in the curriculum and promote broader understanding of the benefits of energy efficiency.
P095129 | Northern Delta Transport Development Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2008 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099060324144513555/text/P0951291c6b17803619cd610da80ea76aef.txt | http://documents.worldbank.org/curated/en/099060324144513555/pdf/P0951291c6b17803619cd610da80ea76aef.pdf | The ICR provided several lessons, of which three are presented here with some paraphrasing:Avoiding orminimizing delays requires the crucial collaboration among the project implementing agencies and managing entities. Theimplementing agencies (PMU-W and the managing entities) and those responsible for approving investments and later taking over theiroperation and management (VIWA and provincial authorities) needed to collaborate from implementation start-up in order to enhanceimplementation success and the sustainability of the project outcomes. However, most of the delays at an early stage of NDTDPimplementation were due to the lack of coordination and clear division of responsibilities between the PMU and VIWA, which led tothe lengthened internal approval process. Eventually, the strong commitment and guidance from the Ministry of Transport played akey role in establishing such strong collaboration by assigning clear roles and responsibilities to each agency and by providingresults-based management, frequent supervision, and guidance. This would help to promote the smooth transition to operating andmanaging the investments.Early budgeting and planning would help to ensure the timely and sufficientallocation of project funds, particularly counterpart funds for resettlement compensation. Resettlement compensation foraffected people is required for any infrastructure project in Vietnam, and in line with Government guidance on the use of ODAfunding, the counterpart funds should be used to cover this cost. The delayed allocation of counterpart funds for landacquisition and resettlement compensation is one of the key issues that contributed to delays in construction works in manyprojects of the same nature. The budgeting and fund allocation in Vietnam, on the other hand, follows a certain process that can becumbersome. Therefore, the early development and submission of the budget and implementation plan can help the implementationagencies be more proactive and effective in this process.Project success requires close monitoring and timelyadjustments during project implementation. The project had many components that faced long GoV approvals, GoV procurementprocesses, lack of counterpart funds for resettlement, landslides, and a pandemic. Success factors include close monitoringsupport, which was conducted every week and involved a meeting every fortnight, especially in the later stages, in addition to theusual missions. This helped resolve the issues and ensure successful completion of this project. There is a need for the Bank tofollow up very closely, coordinate with many agencies, collaborate and resolve issues with GoV leadership when needed, etc. For thelandslides, the COVID-19 pandemic, and double-digit inflation, the Bank had to be very responsive to make changes as requested bythe client.
P095155 | North-South Electricity Transmission Project | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2006 | 2012 | 2014 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/816131474504571765/text/000020051-20140625192813.txt | http://documents.worldbank.org/curated/en/816131474504571765/pdf/000020051-20140625192813.pdf | Even in situations where technical and management capacity of implementing agencies is apparently strong, the quality at entry process should ensure that all institutional aspects are adequately covered. In this project, capacity of the implementing agency was supplemented by a project management consultant with international experience, including the implementation of environmental safeguards.Technical assistance should be timed to be utilized and mainstreamed in a timely manner so that the gains are maximized and retained. In this project the Balancing Market can become fully functional only after sufficient electric power becomes available for trading.The following lessons are adapted from those in the ICR. Continuity in the composition of a Bank project team is an important factor in the smooth implementation of a complex project, allowing for a stable working relationship with the Borrower and implementing agency..Where multiple co-financiers/donors are involved, coordination between them and with the Bank is crucial for the timely implementation of a project
P095169 | Latin America: Multi-Country Capacity-Building for Compliance with the Cartagena Protocol on Biosafety | Latin America and Caribbean | Latin America and Caribbean |  |  | Sustainable Development | Agriculture and Food | GEF | IPF | 2008 | 2012 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/711481474945714274/text/000180307-20141203053029.txt | http://documents.worldbank.org/curated/en/711481474945714274/pdf/000180307-20141203053029.pdf | The following lessons are taken from the ICR with some reformulation of language:Multi-country collaborative capacity building operations on biosafety need to have explicit components on communications/public relations/knowledge exchange. The project did not have communications component but was jointly implemented by another GEF project that focused on communications. This was essential for the success of the project, as it enabled explanation and dissemination of project results to the public. A specific component on project management is also essential for such multi-country projects. The project experience shows that all project costs need to be explicitly captured by a separate project management component. Differences in country systems need to be carefully evaluated to see how streamlining of financial management approaches can be accomplished. There need to be sufficient funds for financial management implementation and supervision as different country systems makes it more challenging to carry out procurement and disbursements, leading to delays and higher costs. Continuous capacity building by the Bank should be carried out on financial management, preferably by a specialist from country offices. A full time financial management specialist also needs to be employed by the regional implementing agency. In kind contributions from counterparts are valid means of support but they can also be limiting factors for the financial fluidity of the project. Future operations should consider having only part of counter-part financing in kind, the rest being monetary contributions. Continuous and active engagement of environmental and agricultural sector institutions, as well as GEF focal points in each country is critical for project implementation and buy-in in the changing political economy of biosafety. Participation from both Ministries of Environment and Agriculture is essential both at the design and implementation periods, as this participation not only ensures continuous â€œownershipâ€ but also helps the project with adaptation to country contexts that evolve over time. Greater engagement and participation of GEF, including GEF country focal points, would improve coordination with other similar GEF initiatives.
P095171 | Integrated Health and Water Management Project (SWAP) | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2011 | 2018 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/431831528998310071/text/Brazil-BR-MST-Bahia-Health-and-Wtr-Mgt-SWAP.txt | http://documents.worldbank.org/curated/en/431831528998310071/pdf/Brazil-BR-MST-Bahia-Health-and-Wtr-Mgt-SWAP.pdf | The ICR (pp. 27-29) offered several useful lessons, including the following lessons restated byIEG: When projects finance government programs, the use of national database indicators facilitatesthe implementation of ME and prevents complexities arising from the introduction of additional non-essential indicators.The introduction of the Barema composite indicator generated little more information than what could have been provided by simpleindividual indicators, and made its monitoring unduly complex to the client (Section 9). A sectorwide approach provides a valuable instrument to promote results and multi-sectoral development. This was demonstrated by theoverall project experience in the water and health sectors, and in the examples noted in Section7. The deployment of water volunteer agents facilitates social mobilization andparticipatorymanagement of water resources in the community. The project trained more than 900 voluntary agents (Section 4, Objective 1)to work with local communities, promote awareness, and explain to the beneficiaries their rights and responsibilities with regardto the newly acquired water services, including their rights to complain about issues in water serviceprovision.
P095173 | MULTI DONOR FACILIT Y - PH MINDANAO RECONSTRUCTION & DEVELOPMENT | East Asia and Pacific | Philippines | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2006 | 2017 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/210661530232748183/text/Philippines-PH-Mindanao-Trust-Fund-Reconstr-Dev.txt | http://documents.worldbank.org/curated/en/210661530232748183/pdf/Philippines-PH-Mindanao-Trust-Fund-Reconstr-Dev.pdf | The following three lessons, based on lessons listed in the ICR and with some editing, were regarded by IEG as the mostimportant ones that emerged from this project,1. In a fragile, conflict and violence (FCV) context,the nature of project benefits and how they are distributed will determine their impact on social cohesion amid fracturedcommunities. For example, in this project livelihood interventions were extremely popular because the benefitsofthese interventions were more likely to have a direct impact on community members. Nevertheless, if the communityinfrastructure can be accessed by large numbers in a community as in this project it was a better option than the livelihoodssupport because it was delivered efficiently, sustainably, and benefited a greater number of people, thereby addressing inclusionand equity issues (ICR, pg. 32).2. A Multi-Donor Trust Fund proved to be an effective and flexiblemechanism to engage in Mindanao and ensure coordination of development efforts in conflict-affected areas. The TrustFund enabled six donors to fund activities and supporting the peace process in a flexible and adaptive mechanism. The trustfund management mechanisms in this case also enabled close donor engagement and coordination over the long-run (ICR, pg.32).3. A conflict-sensitive approach to supporting the planning for post-conflict development wellbefore the conflict ended worked well. For example, the Bank and the Trust Fund donors were able to support thepeace process by remaining engaged with a range of stakeholders and working with the BDA and MILF institutions. The gainsfrom this pre-planning provided a strong foundation to engage more deeply, continue to build trust and scale-up developmentinitiatives when a peace agreement was concluded (ICR, pg. 30-31).
P095203 | Second Export Develoment Project | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2007 | 2015 | 2016 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/199331468197373972/text/ICRR14903-ICRR-PUBLIC-P095203-Box396265B.txt | http://documents.worldbank.org/curated/en/199331468197373972/pdf/ICRR14903-ICRR-PUBLIC-P095203-Box396265B.pdf | IEG supports all lessons cited in the ICR. The ICR drew 5 lessons, and the three most important are: (i) Working through a sound financial institution with a proven implementation track-record is important for achieving results. In this case, the resources and skills for implementing the project were effective because of the choice of an experienced financial intermediary as an implementing partner.(ii) In a rapidly evolving context, implementation flexibility is crucial, since it isn't possible to predict all possible scenarios. In this case, the decision to restructure, to change the proportion of direct and wholesale lending, and to scale up disbursement were all crucial in delivering intended results. (iii) Lines of credit can be leveraged by close coordination with other Bank operations and those of other .partners. In this case, support from the Bank's Financial Sector Development Policy Loan and non-lending technical assistance, along with financing to UEB from other international financial institutions, was all important in leading to the successful outcomes.
P095205 | First Programmatic Development Policy Loan for Sustainable Environmental Management | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2009 | 2011 | 2015 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/341031475093078401/text/000012394-20150409075646.txt | http://documents.worldbank.org/curated/en/341031475093078401/pdf/000012394-20150409075646.pdf | Please see the detailed PPAR evaluation being done by IEG in parallel for more information.
P095205 | First Programmatic Development Policy Loan for Sustainable Environmental Management | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2009 | 2011 | 2015 | PPAR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/583611468006311410/text/898480PPAR0P0900brazil0sem0dpl0ppar.txt | http://documents.worldbank.org/curated/en/583611468006311410/pdf/898480PPAR0P0900brazil0sem0dpl0ppar.pdf | 6. Lessons 6.1 Certain aspects of the World Bank's policies and guidance on Development Policy Lending should be clarified. The lack of clarity with regard to certain aspects of the http\.//www.mma.gov.br/governanca-ambiental/portal-nacional-de-licenciamentoambiental/licenciamento-ambiental/compet%C3%AAncias-para-o-licenciamento See UNFCCC\. http\.//cdm.unfccc.int/Projects/pac/index.html See Ministry of Science, Technology and Innovation, Brazil, 2013\. http\.//www.mct.gov.br/upd_blob/0226/226578.pdf World Bank's OP 8.60 and associated guidance notes led to confusion on the part of the World Bank team, the Borrower, and civil society, as described at various points in this evaluation. The following questions governing the design, implementation and evaluation of DPLs should be clarified\. â€¢ According to the official interpretation, all lending is fungible, and the government can do whatever it wants with the money, so there is no connection between the DPL and the money that the government on-lent to BNDES. This is inconsistent with the common-sense view of the money being transferred to BNDES to complement their disbursements. There is a reputational risk to the Bank in such a case, particularly in relation to the potential environmental and social impacts of the financing. Such impacts are not covered by OP 8.60, which addresses only the potential impacts of policy reforms. â€¢ The requirements for monitoring and evaluation of potentially adverse social and environmental impacts of policies supported under DPLs are also not clear. While those impacts and mitigation mechanisms are supposed to be identified in the Program Document, the requirements on how to monitor them after the reforms are put in place and how to evaluate them in the ICR are not clear. 6.2 Particularly for DPLs focused on reforms in a sectorâ€”rather than on macroeconomic stabilityâ€”the impacts of the actions supported can often not be adequately perceived within the short timeframe of the loan, making monitoring and evaluation of outcomes difficult. The tight deadline for submitting an ICR after closure of an operation often does not allow for additional outcome evidence to be available and collected. It would be preferable to require that DPL operations wait for a reasonable period either before closing or before producing an ICRâ€”at least one yearâ€”in order to allow for adequate monitoring and evaluation. 6.3 Back-loading of reforms in a DPL programmatic series can increase the risk of later loans in the series being canceled without full realization of the objectives of the series. This appears to be the case with the SEM DPL. Back-loading refers to the practice of placing reforms that are more meaningful and have greater value-addedâ€”but are also often more difficultâ€”later in a DPL series. 79 In this regard, the SEM DPL does not appear to have benefitted from the lessons of the earlier Brazil environmental DPL, the 2004 Env PRL, which was planned as a three-loan programmatic series, but was also canceled after the first loan. 6.4 In future, when attempting to support reforms in state-owned banks like BNDES that finance both public and private-sector investments, it will be important to take a One World Bank Group approach. BNDES combines characteristics of the World Bank/IBRD and IFC\. it lends both for large public sector infrastructure projects, as For example, a back-loaded DPL series would typically have actions related to carrying out a study or drafting a law under loan/tranche 1, approving a law under loan/tranche 2, and implementing the loan under loan 3. For a law to have any impact, it has to be effectively implemented, but this is typically more difficult than drafting it. well as to the private sector. IFC was engaged in high-level discussions with BNDES on improving their environmental and social safeguardsâ€”including a visit to BNDES by IFC's then-Vice President for Business Advisory Servicesâ€”at the time the Bank began preparation of the SEM DPL. They were encouraging BNDES to adopt the Equator Principles, derived from IFC's Performance Standards, as other Brazilian banks have. By working together with the IFC, the World Bank could have helped ensure that BNDES adopted environmental and social standards that were considered as good practice internationally, and that were appropriate for both public and private investments. It also would have saved BNDES from having to re-invent the wheel by developing its own approach. This is consistent with IEG's often-repeated assertion that the IFC and the World Bank should work together more to increase development effectiveness. 6.5 The level of government targeted by DPL reforms should be consistent with the outcomes intended and the client country's institutional structure. Brazil has a federal system of government. Although many national-level laws and policies are approved by the central government, implementation depends in large part on lower levels of governmentâ€” particularly states and municipalities. That was the case with a number of the policy areas targeted by the SEM DPL, including improving the environmental licensing process, improving water quality, and implementing wastewater and solid waste investments. By limiting itself to federal-level implementing agencies, the SEM DPL had reduced scope to influence the achievement of objectives related to these policy areas.
P095210 | Niger Agro-Pastoral Export and Market Development Project | Western and Central Africa | Niger | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2018 | 2019 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/301081531939722478/text/Niger-NE-Agro-Pastoral-Export-Promotion-Proj.txt | http://documents.worldbank.org/curated/en/301081531939722478/pdf/Niger-NE-Agro-Pastoral-Export-Promotion-Proj.pdf | The ICR included four lessons. The following are emphasized with some adaptation of language: Productivealliances (PAs)need enough time toensure the development of sustainableand legallyenforceablecontractual relations. PAs develop joint business plans reflecting their interests and common vision to bringproducts to specific markets; these plans include the specification of the attendant investments to be made. The PA also specifiesthe marketing arrangements that partners must respect, including the quality and quantity of products to be produced and exchangedby each partner, the price level,the price determination criteria, andthe partnership specifies the financial andorganizational arrangements according to which it will operate. The development of all these arrangements need enough time to takehold and be respected by all parties. Physical investments need to be complemented by regulatory measuresthat create a more friendly business environment and facilitate trade flows. The project experience demonstratedthatan integrated approach to Value Chains (VC) management is required and that there isa need to intervene at allcritical links where difficulties arise. To this end, it is necessary to identify the key points on which actions are needed (e.g.,production of cowpea seeds, assembling, sorting/ sizing and conditioning of onions in marketing platforms, support to the fluidityof transport through the BEC procedure, or rehabilitation of rural tracks). In this context, efforts should be made to supportenterprises that can act as leaders to strengthen VCs moving forward. It is also important to define the properregulatory framework for each VC and strengthen professional organizations so that they can play their expectedrole.
P095211 | Community and Social Development Project | Eastern and Southern Africa | Burundi | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2013 | 2015 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/866341475115261104/text/000012394-20150108104840.txt | http://documents.worldbank.org/curated/en/866341475115261104/pdf/000012394-20150108104840.pdf | The following lessons are derived from the projectâ€™s experience, of which lessons 1 to 5 are taken from ICR (p. 18-19), and lesson 6 is from IEG: 1. A SIL operation on its own is not a sufficient vehicle to promote broad policy and institutional reforms needed for effective decentralization. The project contributed significantly to supporting the young decentralization process in Burundi. However, to generate the required policy momentum in a newly launched decentralization process, it would have been more effective to combine a SIL operation with other mechanisms to promote policy changes, such as DPLs. The decentralization process is still challenged by lack of coherence on fiscal decentralization, including the mechanism for fiscal transfers and local tax collection, and policy stagnation on devising clear roles and responsibilities for decentralized services such as health and education. The limited transfer of funds from the national to the local level, although required by law, severely constrains local government to carry out their new responsibilities. A CDD project, combined with a mechanism to support policy and institutional reforms could have better supported the development of a fully effective decentralization process.2. In a low capacity environment, CDD projects should use a gradual, transitional approach. CDD approaches have proven to be effective in low capacity, post-conflict environments. They transfer financial resources directly to communities to address their most important needs, rebuild social infrastructure, make government presence visible at the local level and contribute to peace building. However, sufficient time needs to be given to develop effective mechanisms at the community level and build the capacity of local authorities. Only in a second phase should responsibilities be transferred, including developing and implementing construction for social infrastructures. Otherwise, capacity building will be seen only as a pre-requisite to obtain funding for infrastructure subprojects, instead of as a key objective on its own to support sustainable local development.3. A comprehensive assessment of actual capacity among local officials in a fragile context is essential to avoid over-optimism and an unrealistic design at entry. The success of a CDD operation partially hangs on the capacity and ability of local officials to manage resources and provide technical inputs. Over estimating the ability of local officials does more harm (do no harm principle) and will ultimately waste time and resources at the start of a project while modifications are made to address capacity constraints.4. CDD projects need to be flexible during periods of elections in post-conflict settings. CDD projects are especially vulnerable to political interference and corruption during election periods, even more so in post-conflict countries. Bank and government teams need to take pro-active actions to avoid these potentially negative impacts on project performance, such as putting on hold selection of infrastructure projects at the community level during a significant period before elections, and foreseeing additional capacity building for newly elected officials at all levels following elections.5. Bank presence in-country, particularly in a post-conflict environment, is important. This lesson has been repeated in several recent Burundi ICRs, and no doubt from other countries. Complex operations, such as a large-scale CDD project, require closer guidance and mentoring by Bank staff than more straightforward projects or when working in a more stable context. In-country staff allows real-time technical support.6. A clear articulation of objectives and appropriate indicators for measuring their achievement are critical for monitoring implementation and ultimately assessing efficacy. Vague objectives and poorly articulated indicators put project teams at a disadvantage in terms of demonstrating the impact of the intervention on development outcomes and diminish their usefulness as a monitoring and management tool.
P095213 | Second Programmatic Business Product and Efficiency Development Policy Loan | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2007 | 2007 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/812301474569050872/text/000020051-20140625074152.txt | http://documents.worldbank.org/curated/en/812301474569050872/pdf/000020051-20140625074152.pdf | IEG concurs with the ICR on the lessons learned emphasizing in particular the importance of government commitment to ensuring success of the program, attention to political economy of reform, and the importance of close collaboration with other partners active in the country. The lessons concerning importance of flexibility provided by the programmatic approach is also well taken although in this case, it appears that the Bank did not fully make use of that flexibility by resetting the program targets in light of the implementation experience.
P095213 | Second Programmatic Business Product and Efficiency Development Policy Loan | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2007 | 2007 | 2018 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/385471500561415074/text/110740-PPAR-P094301-P095213-P105029-PUBLIC.txt | http://documents.worldbank.org/curated/en/385471500561415074/pdf/110740-PPAR-P094301-P095213-P105029-PUBLIC.pdf | 6. Lessons 6.1 The experience of this DPL program suggests, once again, that in-depth knowledge and government buy-in were essential in Colombia for designing reform programs with substance. In general, the prior actions of this program reflect well what the World Bank knew about Colombia. For example, in the financial sector, the reforms selected exemplify the World Bank's deep understanding of the problems that had to be solved to strengthen the financial system. The impact of the reforms is beginning to be felt even if the results indicators were inadequate for assessing properly the program's contribution. On the other hand, lack of political commitment to tackle the fundamental problems in Colombia's foreign trade sectorâ€”weak institutions and entrenched protectionismâ€”meant that the reform actions supported under this program addressed secondary issues. Consequently, the impact of the actions pursued was limited. 6.2 Staggering interventions by policy areas presented trade-offs between the breadth and depth of the program. While the approach appeared attractive by allowing the World Bank to tackle a larger number of issues while staying focused at each given moment, it also meant limited attention to some issues and one-off support in some areas. The design of the program could have paid more attention to assessing the implications of such trade-offs for achieving the program's objectives, especially the risks to development outcomes in the long run. The experience with this DPL program suggests that staggering interventions to cover more ground is likely to produce programs of modest relevance and shallow impact.
P095229 | ANGOLA EMERGENCY MULTI-SECTOR RECOVERY - PHASE 2 | Eastern and Southern Africa | Angola | IBRD | FCS | Infrastructure | Transport | IDA | IPF | 2007 | 2013 | 2016 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/545491468185967241/text/ICRR14872-P095229-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/545491468185967241/pdf/ICRR14872-P095229-Box394823B-PUBLIC.pdf | Two lessons are selected from the ICR, with some adaptation of the language:Emergency operations should have a simple design to facilitate prompt implementation and completion. In a post-conflict environment, emergency operations help address urgent and pressing needs, while often in an environment of widespread and systemic weaknesses in public agencies. Progress monitoring and mid- course project review are important tools to detect issues in project implementation and take corrective actions on time. Under this project, as there were several changes in the project team leadership and program coordinator, lack of the adequate M&E implementation and the mid--term review exacerbated the project implementation.
P095232 | Local Government Project (SLGP) | Eastern and Southern Africa | Eswatini | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2011 | 2019 | 2020 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/704831590112489205/text/Eswatini-SZ-Loc-Govt-SIL-FY11.txt | http://documents.worldbank.org/curated/en/704831590112489205/pdf/Eswatini-SZ-Loc-Govt-SIL-FY11.pdf | This review agrees with the lessons identified in the ICR, whichare summarized below:(i) ME efficacyrequires an improved data management: Foreffective monitoring and evaluation, itwasimportant tohavea central server with an archiving system thatcould provide a repository for all reports and documents for easyaccess by all stakeholders. This instrument generated the necessary support for the collection of PDO indicators, their regularupdate, interpretation andsharing with all key stakeholders. The lesson is that improved data management is important toensure the sustainability of achieved outcomes, as updated information and data on outcomes will allowgood maintenance andeventual scaling up.(ii) The mobilization of communitiesand their leadersis central tothesustainability of local government projects (para 85).The participation of communities in thesub-projectsimproved significantly during project implementation,but it was necessary to further improve communityresponsibility in the implementation, operation and maintenance of sub-projects.Sports fields were technically difficult todeliver andhave limited value in terms of actual numbers of community members using them. Similarly, the occupancy of marketstalls remained relatively low, although the significantly improved conditions for the limited number of traders (mostly female)who utilize them was appreciated.The lesson is that to get the beneficiaries support for sub-projects and achievea projects outcome, community mobilization is necessary and is only successful if sub-projects are of sound quality andcommunity mobilization is established at a high level (para)(iii) Close supervision focused on adherence toconstruction quality, building standards, and timeliness has to be the norm to ensure the satisfactory delivery of project results(para 86). The quality of implemented projects in rural areas is highly dependent on the experience of local contractorsand to the adequate supervision of contractors by the authorities. In this project, the overallquality of contractorperformancewas noted as acceptable from the functionality perspective; however there were variations at the detailedlevel.The lesson is that close supervision and standardized designs can mitigate some of the technical challengesfacing contractors, but the authorities need to guard against sites that are not suitable for standard designs, resulting inunsupervised changes on site and during construction.(para )(iv) There is a link betweenthe success of localGovernment projects and the national-level government system reforms (para 87). While decentralization triggered thelaunch of this project at the time, much of the longer-term sustainability of the project results were rooted in nationalgovernment system reforms. The changing macro-environment could not have been clearly foreseen, but the challenges and delaysencountered in the project design and effectiveness periods could have acted as early red flags. The lessonis thatthere could have been more explicit considerationof how to better ensure sustainability of capacity building interventions atthe local level. Implementation of this lesson might have been the compilation of training manuals into a handbook to serve asreference(v) Implementation readiness is essential to move rapidly toward project results. In thisproject, delays of project launch, and project extensions were caused by the lack of project implementation readiness at projectapproval. The lesson from the experience of this projectwas thatproject implementation readiness is essential tostart the project promptly and conclude it on time.
P095235 | PY Water & Sanitation Sector Modernization | Latin America and Caribbean | Paraguay | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2009 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/754861573849766440/text/Paraguay-PY-Water-Sanit-Sector-Modernization.txt | http://documents.worldbank.org/curated/en/754861573849766440/pdf/Paraguay-PY-Water-Sanit-Sector-Modernization.pdf | The ICR draws the following three lessons from the experience of implementing this project, with some adaptation oflanguage.(1) Framework projects should be accompanied by strong technical studies.While there areadvantages of adopting this approach (flexibility at implementation was expected to better selection of investments), lack oftechnical studies at design in this project, contributed to implementation delays. This along with other factors discussed in thetext contributed to the extension of the project closing dates.(2) Collaboration with local governance structurescould facilitate implementation of activities associated withimproving service deliveryin remote and culturally diverseareas. In this project, WSS activities in these areas was facilitated by the involvement ofmunicipalities and localcommunity leaders.(3) Funds need to be allocated at appraisal for resettlement expenses, if resettlement isforeseen at design.In this project, although resettlement was identified at appraisal, there was no allocationof funds for covering resettlement expenses.Eventually funds had to be diverted from other activities and this contributed tothe reduction in project scope and project delays.
P095240 | Power Sector Improvement and Recovery | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2007 | 2013 | 2015 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/410401475115030827/text/000012394-20150109131027.txt | http://documents.worldbank.org/curated/en/410401475115030827/pdf/000012394-20150109131027.pdf | A number of lessons were selected from a longer list identified by the ICR: 1. Fragile country situations with a mixed history of implementation would argue for modest development objectives that reflect the prevailing technical, economic, financial and implementation capacity constraints.2. Careful attention should be given to the results framework. In this project, for example, the data on the results indicators achieved at project closing were available but not regularly collected prior to the preparation of the ICR. This can leave the impression that there was a lack of focus on the impact and results of the project.3. When capacity building issues are identified as with MEM in this case, training and other remedial measures should be prioritized for fast track implementation soon after the preparation phase of the project, preferably prior to effectiveness in any case. Regional managers should assess the status of preparation of key capacity building components before authorizing appraisal.
P095250 | Health Services & Social Assistance | Europe and Central Asia | Moldova | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2007 | 2015 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/772831468189548593/text/ICRR14757-P095250-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/772831468189548593/pdf/ICRR14757-P095250-Box393191B-PUBLIC.pdf | The ICR (p. 26) identifies several lessons, including:A well designed Results Framework that includes measurable indicators with reliable baselines and realistic targets is critical for tracking progress towards the development objectives. In this project, the initial design did not allow for rigorous tracking and needed to be revised twice, with the final revision taking place only 16 months before project closing. This had a negative impact on the reliability and credibility of project results. Collaborating with different development partners is important for taking advantage of synergies and avoiding duplication of activities. In this project, the construction of the surgical block for the Republican Clinical Hospital was complemented by the European Union's Neighborhood Farm, and the equipment was provided by the Government of Japan. Also, the World Health Organization conducted several studies, including a study on extending health insurance coverage, which contributed to project implementation. A lesson added by IEG:This project demonstrated that strengthening primary care, conducting a political economy analysis, and extensive consultation with stakeholders prior to implementing hospital rationalization is critical for smoothing the political path for hospital reform.
P095251 | CG Rep. Agricultural Development and Rural Roads Rehabilitation Proj. | Western and Central Africa | Congo, Republic of | Blend | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2007 | 2017 | 2018 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/200031519310595486/text/Congo-Republic-of-CG-Agr-Rehab-SIL-FY07.txt | http://documents.worldbank.org/curated/en/200031519310595486/pdf/Congo-Republic-of-CG-Agr-Rehab-SIL-FY07.pdf | The lessons are drawn from the ICR, with some modification of language.(1) Involvement of all stakeholders,including private sector representatives, can aid project implementation. In this project, private actors identified theproblems encountered by producers and suppliers of inputs in accessing markets. The information provided by the private actors wasconveyed tothe Project Coordination Unit (PCU). This strategic partnership with private entities proved to be beneficial forimplementingactivities associated with constructingroads and market infrastructure.(2) Carefulconsideration of local conditions is required at project preparation for preventing implementation delays.In thisproject,delays with infrastructure work were due to climate risks, delivery of inputs during off season and shortcomings ofgroup producers (such as lack of knowledge of procedures and insufficient capacities). Mapping of stakeholders and betterprofilinglocal conditions duringpreparation would have helped in overcoming thedelays that occurred duringimplementation.(3) The link between actors along the entire value chain needs to be taken into account, whiledesigning productivity enhancing technologies aimed at improving agricultural yields.The focus of this project wasmainly on the agricultural upstream value chain (such as activities of agricultural extension services for improving agriculturalproductivity)and less so on downstream activities (after production activitiessuch as the logistics associatedwithbringing agricultural products to the final market and storage facilities). The experience of this project demonstratedthat the link between actors along the entire value chain needs to be consideredto ensure efficient matching of consumers andagricultural producers. buyers and sellers.This is especially required to provide theincentives to the producers toinvest over the longer term in productivity enhancing technologies that can improve yields, profitability and farm income.
P095275 | Central North Region Health Support Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2010 | 2017 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/375671498239629724/text/ICRR-Disclosable-P095275-06-23-2017-1498239616711.txt | http://documents.worldbank.org/curated/en/375671498239629724/pdf/ICRR-Disclosable-P095275-06-23-2017-1498239616711.pdf | The following are relevant lessons from project implementation, reported in the ICR andaugmented and reformulated by thisICRR: The combination of supply and demand side interventions, such as improving quality of healthcare services (infrastructure, equipment, medical skills, management, and incentives for retention), and increasing subsidizedhealth insurance among the poor and near poor, is an effective strategy to increase utilization of health services while improvingequity, thus contributing to achievement ofuniversal health coverage. However, the goal of financial protection may notbeachieved to the extent that the package of goods and services covered by insurance is not comprehensive. Near poorbeneficiaries of this project still experienced OOP health expenditures that exceeded 25% of their non-food consumption. This showsthat it is not enoughjust toincrease health insurance coverage. Focus must also be placed on thecomprehensiveness of the package andon the level of cost sharing and fees. A holisticapproach to addressing human resources for health shortages and retention issues typically occurring in isolated and remote areasispreferable toa one-dimensional strategy. This project combined training of local staff; improvements in quality ofteachingatamedical university and colleges, staff agreementson returning to workplaces, andperformance-based payments. As noted in Section 10, there may be tension between the qualityofa data collection instrument and the timely availability of data. This project showed that the use of VHLSSallowedthe project toobtain data by income level on some indicators, but at the expense of not having current data atthe end of the project life, asresults from national household surveys tend to be available with some delay.
P095314 | Fiscal Management and Public Sector Performance Technical Assistance Loan | Latin America and Caribbean | El Salvador | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2010 | 2017 | 2017 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/920841498850289215/text/ICRR-Disclosable-P095314-06-30-2017-1498850251206.txt | http://documents.worldbank.org/curated/en/920841498850289215/pdf/ICRR-Disclosable-P095314-06-30-2017-1498850251206.pdf | The following key lessons are drawn by IEG, building on lessons presented in the ICR: 1. Deeper assessment of the need, feasibility, viability, scoping and sequencing of PFM andIFMIS reforms will improve project design. In the case of this project, the project scope was kept too wide to coverdifferent aspects of revenue and expenditure management and transparency and accountability of the public sector. In case of theIFMIS, the initial design included several modules including public investment management and human resources management, which wasnot feasible to be implemented in the project time of 5 years. At the end of 2013, the government decided to implement IFMIS withproper sequencing, covering only the financial core budget, treasury and accounting modules in the firstphase. 2. Careful consideration of alternative technology options regardingIFMIS software can improve results. In the case of this project, the project chose to use a locally developed software.There was no careful consideration of alternative commercial-off-the-shelf software. It usually takes a longer time to developsoftware from scratch and one cannot be sure of its quality without testing and benchmarking by a third party. Thecommercial-off-the-shelf software is tested and patented and can often be more easily implemented with necessary adjustments tomeet requirements of countrys legal framework. There was no technical assessment of the two options before this decision touse locally developed software was taken, leading to uncertainties about the quality anddelays. 3. Donor Coordination and agreement reached on respectivestrengths and responsibilities for implementing reforms at the appraisal stage helps to achieve desired outcomes. In thecase of this project, the original project design was changed considerably at the time of first restructuring, with otherdevelopment partners picking up substantial proportion of funding for improving transparency and accountability. Governmentpreferred this funding as it came in the form of grants; however, if that information was available earlier, thegovernment togetherwith the Bank could have taken that decision earlier. Delays meant that the Banks inputs were notenough to reach the desired project outcomes, despite the ample available funding, much of which had to be cancelled in theend.
P095315 | Western Provinces Rural Water Supply, Sanitation and Hygiene Promotion Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2007 | 2013 | 2015 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/197741474941903770/text/000180307-20150108113230.txt | http://documents.worldbank.org/curated/en/197741474941903770/pdf/000180307-20150108113230.pdf | The ICR identified six lessons, summarized as follows:Significant co-financiers not honoring their funding commitment obligations for the life of a project has profound effects on project implementation and achievement of the PDO. DfID withdrew from the project using a standard and generic clause in the Memorandum of Understanding (MOU). In order to avoid future problems of this nature, MOUs should be strengthened to ensure that co-financiers honor their commitments for the life of projects and only cancel these commitments in well define, documented and transparent circumstances and with agreement of all parties involved in financing. For multi provincial projects, a Central government agency should be nominated to coordinate provincial activity. To avoid delays and prevent one province being held up by the inaction of another, as was the case with the restructuring of this project, a central agency like National Development and Reform Commission should be nominated as the responsible central agency to better coordinate project provinces. Alternatively, project design could be more flexible in the future to allow staged restructuring where one province is moving faster than another. Strategic partnerships and targeted TA add tremendous value. The strategic partnership established between the WB/UNICEF/Government of China/DfID added tremendous value and in the end the KASH TA program produced a best practice example of leverage and co-operation applied to help Government of China find solutions to a huge national challenge in the Rural Water Supply, Sanitation and Hygiene Promotion sector. The Bank should look for more opportunities to develop similar partnerships to enhance project outcomes. Standard physical and price contingence items for Bank lending in China need continual review and updating to better reflect reality. The underestimation of contingencies at appraisal resulted in significant cost variations. Strengthening the support provided by government departments to new community groups. A stronger and more permanent relationship between the WASH committees and the Town Water Supply Stations and County Water Resource Bureaus needs to be developed to support fledging community committees that have been assigned the Management, Operations and Maintenance responsibilities of water supply schemes, but have little or no experience with the operational and technical aspects of assets assigned. Strength of Programmatic approach to project design. Despite the implementation problems with this project, in future a programmatic approach to project design can be effective in addressing major national policy issues and challenges, particularly combined with a good technical assistance in China. Other lessons that might be considered: In addition to the lesson above on strengthening operational MOUs among partners, operations using programmatic approaches might also assess the risk of partners leaving an operation and outline mitigation measures. In the case of DfiDâ€™s departure, the decision to end its China program was carried out at political level which may have overridden any strengthened operational level agreements Another lesson to consider would be including incentives for the use of monitoring and evaluation systems among county and provincial entities. While the project developed robust M&E plans and was reported to have carried out extensive training, the results were mainly a monitoring system that reported routine outputs. Many data were not adequately captured that would have informed progress towards the PDO. This included water and sanitation related outcomes, and hygiene outputs. This might be strengthened in the future by committing adequate resources to assess appropriate collection methods including strengthening incentives for the use of existing systems within agencies and government, and considering the use of periodic surveys.Another lesson is the need to assess the optimal structures for Project Management Units. The ICR indicated that having the PPMO as a unit within an existing department was a driver in Shaanxiâ€™s ability to manage the restructuring process, whereas having the PPMO made up of seconded staff from multiple departments was a source of delays in Sichuan.
P095337 | Urban Infrastructure Project | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2008 | 2015 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/293231474479915720/text/ICRR-Disclosable-P095337-09-21-2016-1474485379544.txt | http://documents.worldbank.org/curated/en/293231474479915720/pdf/ICRR-Disclosable-P095337-09-21-2016-1474485379544.pdf | The ICR draws the following main lessons from implementing this project. Utility level ProjectImplementation Units (PIUs) can helpin building capacityat the local level. The Implementation arrangements ofthisproject included a central PIU and three regional PIUs. This arrangement whereby the central PIU was responsible forensuring consistency and oversight and the utility level PIUs were responsible for day-to-day management, proved useful in buildingcapacity at the local levelin all the cities. Ensuring project readiness to enable immediatestart can be critical in preventing implementation delays. This entails identifying activities in advance, having thefeasibility studies and project design completed by the time the project goes for Board approval.As in the case of thisproject, eligible utilities and municipalities were to be selected during the course of the project. In suchcases,project preparation could entail through sensitization workshops,standard templates, communicationwithmunicipalities and advance training. To ensure sustainability, selection criteriafor utilities needs toincorporate financial viability considerations. The risk that beneficiary utilities may not bein a positon to repay thesub loans needs to be identified at appraisal and mitigated. The selection criteria for utilitiesneeds to take into consideration thefinancialhealth consideration of utilities and their ability to repay financialobligations. Institutional dimension of the project needs to be well defined at appraisal withspecific activities in place. Although this project envisaged preparation of annual business plans by utilities for use asmanagerial and planning tools, there were no project activities that specifically provided assistance to the utilitiesformeeting the targets in thebusiness plans.
P095371 | HT Economic Governance TAG II | Latin America and Caribbean | Haiti | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2006 | 2011 | 2012 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/888831474631230623/text/000020051-20140625082021.txt | http://documents.worldbank.org/curated/en/888831474631230623/pdf/000020051-20140625082021.pdf | This review supports the lessons provided in the ICR, with particular emphasis on the value of keeping the design both simple and focused. The project suffered from an ambitious design which aims to cover the economic governance issues comprehensively. Given the interlinked and cross-cutting nature of the issues related to governance, the attempt to cover a variety of areas is understandable. However, in an environment with constrained capacity, identifying an appropriate entry point for reform is important (though challenging).
P095388 | TN-Integration and Competitiveness DPL | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2009 | 2011 | 2013 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/655471475083933499/text/000020051-20140625184959.txt | http://documents.worldbank.org/curated/en/655471475083933499/pdf/000020051-20140625184959.pdf | The four main lessons learned from the implementation of the ICL are: 1. The importance of grounding DPLs in solid analytical work. The design of the ICL benefited from the Bankâ€™s analytical work on the â€œTunisia: Global integration Studyâ€, as did that of the successor program. As a result, an assessment of many of the key problems and possible solutions were available to Bank and Government staff, which greatly facilitated the design and impact of the ICL. Other DPLs could usefully follow and benefit from this practice.2. The value of locating the TTL in the field. The TTL for the ICL was based in Tunis. This greatly facilitated interactions with the authorities and other key development partners in the design, implementation, and monitoring of the program. Observers believe that this also contributed to the ability of staff to respond quickly and flexible as problems arise. Resources permitting, TTLs for large projects should be based in the field.3. The need to factor political tensions more explicitly into risk assessments. Although no one could have predicted the revolution that occurred mid-way through the project, the risk of such a possibility should have been included in previous assessment. Fortunately, the recent changes in Tunisia did not undermine the implementation of the ICL and are in fact appear to have opened up the development agenda to issues that were previously politically taboo. Nevertheless, risk assessments should include socio-political-economic evaluations on key matters that could affect program implementation, particularly in the case of DPOs which are grounded in the governmentâ€™s program.4. The importance of putting in place an effective monitoring system up front. A well thought out and designed M&E system is critical to assessing the development impact of Bank programs and projects. If the designs and systems are not properly in place up front, there is little that can be done at the M&E Implementation stage to correct for it midstream, especially in a stand-alone, two-tranche DPL. While it is true that it is more difficult to measure long-term results in DPLs, it is nevertheless critical to include good indicators of intermediate outcomes so that one can know if the DPL is likely to achieve its development objectives. The Bank should redouble its efforts to ensure that reasonable appropriate systems are put in place prior to Board approval of operations.
P095389 | District Heating Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2006 | 2010 | 2012 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/129421474908269625/text/000020051-20140624192526.txt | http://documents.worldbank.org/curated/en/129421474908269625/pdf/000020051-20140624192526.pdf | The ICR derived the following lessons from the project's implementation experience:(1) The commitment and ownership of the Borrower and the implementing agency(ies) are important for project success. Where key enabling reforms are needed to achieve project objectives, covenanting reform actions could entail significant risks and would be the less preferable approach compared to asking the Government for the up-front implementation of those reforms.(2) The institutional and regulatory framework needs to already be in place when project implementation begins. (3) District heating projects in the ECA region should be complemented by the economic dialogue underpinning DPLs, in which the politically difficult decisions related to increases in heat tariffs should be integrated (as in Ukraine and Moldova). Given the increases in international energy prices, tariffs for heat and steam supply should be adjusted regularly to avoid very high cumulative cost increases that, in turn, require very large, politically difficult compensatory tariff increases.(4) A simple and focused project design, and continuity in the implementing agency's management team, are important in facilitating efficient project implementation.(5) Financial incentives for apartment building tenants are required to implement DSM measures. Low heat tariffs provide no incentive for apartment owners to invest voluntarily in DSM.
P095389 | District Heating Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2006 | 2010 | 2013 | PPAR | >=25 million & <50 million | Moderately Unsatisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/950081468248096097/text/788750PPAR0P070Box0377365B00PUBLIC0.txt | http://documents.worldbank.org/curated/en/950081468248096097/pdf/788750PPAR0P070Box0377365B00PUBLIC0.pdf | 5. Lessons Lessons 5.1 A supportive regulatory environment is crucial for overcoming risk aversion to adopting new financing instruments for energy efficiency projects; creating a level playing field for a competitive ESCO market; and to ensure sustainability of energy services. * The Energy Efficiency project was unable to stimulate the ESCO market beyond some sectors in the public domain due to remaining regulatory and legal constraints (as for example in the residential sector). * In Croatia, two factors may have inhibited the emergence of a competitive regime for ESCOs\. (a) HEP ESCO's special standing as a subsidiary of the national power utility HEP; and (b) the lack of standardized contract models, budgeting procedures, and public procurement rules. * The capacity of HEP T, the District Heating Company, to provide reliable services in the long run is likely to be impacted if its financial viability is not assured through either remunerative tariffs or well-designed subsidies. 5.2 Ensuring reliable means for verifying energy savings provides a clear basis for sharing the resulting gains between the beneficiary and the financing source, and therefore incentivizes energy efficiency efforts. * Underdeveloped means for monitoring and verification meant that there was an inadequate basis for sharing the gains from energy savings, thus creating a disincentive for adopting the ESCO model. * Given the prospect of HEP increasing District Heating tariffs in the future, demandside management should be promoted to ease the transition to higher tariffs. In particular, individual metering will need to be introduced widely so that each unit can be charged for their actual energy use. 5.3 There is a need for the Government to coordinate its various ministries in order to provide common technical and other support services, with a view to mitigating risks for investors and consumers in renewable energy efforts. * While rights to state-owned land are being handed out to the private sector or for public-private partnerships in solar and wind power projects, energy resource mapping and mature project designs need to be provided as a common service by the government. In the case of biomass projects, where various ministries including forestry and water are involved, horizontal connections between ministries need to be strengthened. These arrangements were lacking during the Renewable Energy Resources project experience.
P095392 | EG-Natural Gas Connections Project | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2008 | 2015 | 2016 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/245211467997255959/text/ICRR14839-P095392-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/245211467997255959/pdf/ICRR14839-P095392-Box394823B-PUBLIC.pdf | The following lessons are paraphrased from the ICR (page 16):Implementing a project that mainly addresses the deployment of physical investments could have the advantage of being less dependent on the political economy of the country, compared to a project which focuses delicate institutional reforms.Part of the rationale of the project was to reduce costs to government by switching from a highly subsidized fuel to a less subsidized fuel, which is the right approach when political economy issues do not warrant a more aggressive approach to subsidy reforms. This project also had an institutional capacity building aspect by improving the expertise of Town Gas in international procurement and safeguards management.Making an effective use of the period between project approval and effectiveness could be very useful to avoid unnecessary project delays.The conditions for effectiveness of a project are often related to legal or process aspects that are not strictly related to the nature of the investments to be financed. As shown above, this project benefited from using the 13 months elapsing from its approval and its effectiveness for Town Gas and EGAS in moving the procurement of works contracts forward. The Bankâ€™s team proactivity and continuity at this stage and throughout the project also contributed to a successful implementation.Embedding a Bank-financed operation within a key strategy of the Government could strongly increase the likelihood of successful implementation and outcomes.The GoE continues to be committed to increasing the coverage of gas connections as shown by the new operation financed by the Bank and approved in 2014. This commitment provided an overall positive environment for the project to support the overall objective of the GOE. The 330,000 householdsâ€™ gas connections of this project were a move towards achievement of the long term goal of the government.
P095460 | Bahia Integrated State Highway Management Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2007 | 2014 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/686681475115742167/text/000012394-20150109134604.txt | http://documents.worldbank.org/curated/en/686681475115742167/pdf/000012394-20150109134604.pdf | Of the following lessons, the first two are taken from the ICR, and the others are drawn by IEG:A performance-based approach to highway improvement projects takes time and requires cultural change. Combined lending instruments and interventions across the Bank Group help to leverage sector results. The project included institutional strengthening activities, which proved conducive to fostering the sector dialogue.Project development objectives and outcome indicators need to be closely aligned, tracing a strong causal link. This proved to be difficult in this project. Weak attribution resulted from exogenous factors driving the outcome indicators. It is important to design a results framework that links inputs-outputs-outcomes clearly, and through which outcomes can be attributed to the project. This should not be restricted to annual monitoring of only the physical progress, but needs to encompass the specified results/outcome indicators. The full and effective financing of road rehabilitation programs needs a clear time horizon, a realistic appraisal of technical capacity, and updated estimates of the cost of civil works. The financing gap that emerged in this project, and the shortfall in physical output, reflected the absence of these elements.
P095485 | Urban Transport in Metropolitan Areas | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/232781608682983056/text/Argentina-AR-Metropolitan-Areas-Urban-Transport.txt | http://documents.worldbank.org/curated/en/232781608682983056/pdf/Argentina-AR-Metropolitan-Areas-Urban-Transport.pdf | The following have mostly been derived and summarized from the ICR, with minor additions by IEG:Scattered smallinterventions have higher transaction coststhan focused major investments.The original project designenvisaged many small,geographically scattered interventions in different cities. These interventions had higher transactioncosts to implement, weremore difficult tosupervise, and hadlimited impact. For instance, the works to improve theaccess conditions around 25 train stations in AMBA demanded lots of discussions, required a large supervision effort, and hadlimited impactcompared to the La Matanza BRT and the Saenz transfer station. At least inArgentinaspoliticaland economiccontext, it seems that concentrating efforts on larger, emblematic projectsis a better strategy in rallyingsupport andpolitical buy-in for a project. It is also more efficient in reducing Banktransaction costsin termsofprocurement, safeguards, and supervision tasks. This does not mean that mean that focused small interventions are notimportant.For projects aimed at smaller cities, without previous Bank experience, addressingtheir technicaland capacity constraints upfrontand reinforcingthe project-agreed implementation mechanisms might increasethelikelihood ofsuccess and sustainability. Under this project, some of the cities originally expected toparticipate in the project did not have astrong technical expertise, so were not ableto justify the project benefitsand provide the necessary data. They had also no experience with World Bank procedures. Therefore, it was very difficult tomove their projects forward. Therefore, project preparation for these cities has to be comprehensive, with detailedagreementson details and capacity strengtheningin advance.Contract flexibility, transparency, and overall goodgovernance is central to projectimplementation.Under this project, the flexibility of the Bank taskteamto adapt to a changing and challenging implementation contextwas critical topromptly take measures to turnaround a problem project with deficiencies in its original design anddeliver theexpected development outcomes. Themeasures taken to respond tofiduciary irregularities, including the forensic audit and fiduciary action plan, significantlyimproved fiduciary performance in the lateryears of project implementation.The introduction of new BRTprojects needs to be adapted to the context of the city, the institutional capacityof the local government, and the busoperatorsbusiness model. The discussions on the main characteristics of this type of transit infrastructure andthe alternatives to structure the service provision led toa BRT design, which differs from the standardsset by theTransmilenio BRT systems in Bogota, Mexico, and Brazil. The ArgentineBRT model, (i) has low-floordoors on the rightside, which provides more flexibility and integration withthe rest of the bus system outside the BRT corridor,(ii) haslonger and open stations, different from theclosed station with ticket pre-payment typical in Bogota, whichprovide aperception of enhanced safety to passengers and lowermaintenance costs,and (iii) rationalizes the existing busservices, but does not require the restructuring of the operators businessmodel, hence making continuity easier.Although this model foregoes some efficiency gains in service provision, (i) it hada huge success with municipalities withlimited capacity and resources to maintain andoperate a more complex system, (ii) hadthe support of bus operators thatbenefitedfrom the reduction ofvehicle operatingcosts, and (iii) was welcomed by users for the traveltimeand safety improvements. Therefore, theArgentine BRT model supported by the project might be a valid model for many citiesworldwide exploring alternatives for sustainable mass transit infrastructure.The following is an additional lesson addedby IEG:Using PDO indicators closely linked to project activities reduces the flexibility to change projectactivities and makes results measuring difficult. Under the original project design,many PDO indicatorswereclosely linked to specific project activities, such as Availability of public bus service along thePapagayocorridor inMendoza to measure the subobjective of improvedquality and performance of urbantransportinfrastructure and/or services.Therefore, when several project activities were replaced, such as in this caseto improvements inthe Papagayo corridor,the whole results framework had to be changed. A more appropriate indicatorcould have been one that measuredimproved quality aspects of public transport in general.
P095509 | Tanzania PRSC-4 | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2006 | 2007 | 2012 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/714031474571401951/text/000020051-20140625065432.txt | http://documents.worldbank.org/curated/en/714031474571401951/pdf/000020051-20140625065432.pdf | There are four important lessons:1. Realistic monitoring frameworks are important tools for effective reform, important for government, but also for the Bank and other donors. MKUKUTA, well intentioned though it was, clearly provided an overly optimistic and ambitious framework for monitoring and evaluation. As the Bank modified its approach to monitoring over this PRSC series, it produced a more meaningful framework. Still, the use of WBI governance indicators is not ideal, as they are measures relative to other countries, whether or not such countries are comparable to Tanzania. Poverty head counts were (and are) only available with a considerable lag, and so cannot reflect current progress, even though having the desirable property of broadly capturing progress, or lack of it. 2. There are drawbacks to long term commitments of budget support which need to be carefully weighed against the benefits, in terms of government efficiency, of being able to count on budget resources over time. In this case, it appears that not only was there a downward trend in performance, but that donor support may have also contributed to what appears to be a sustainability issue -- the high level of government expenditures relative to GDP, and, within that, the high level of wages. 3. Stationing key staff in country offices is important in enabling the Bank to provide good advice, even if that does not always translate into results. This good practice should be continued. 4. Far-reaching reform programs need to be carefully tailored to human capacity constraints. In this case, the sophisticated process supporting implementation outpaced the human resources available, especially on the government side, which was also limited by availability of dependable office communications (such as email). For the future, the Bank should seek to support reform programs more realistically grounded in capacity.
P095509 | Tanzania PRSC-4 | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2006 | 2007 | 2013 | PPAR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/542381468133184866/text/781880PPAR0Tan00Box377382B00PUBLIC0.txt | http://documents.worldbank.org/curated/en/542381468133184866/pdf/781880PPAR0Tan00Box377382B00PUBLIC0.pdf | 4. Lessons 4.1 The implementation of PRSCs 1-8 spanned nearly a decade during a period of sustained macroeconomic stability and fast economic growth, offering lessons both for Tanzania and other countries with similar development challenges. 4.2 Lesson 1\. Direct and sustained focus and clarity of vision over the entire course of implementation of PRSC programs that cover many years is required to facilitate lasting reforms particularly with regard to public sector governance. There is a significant risk of backsliding when attention is shifted to other priorities. Yet joint budget support is a messy attempt to reach a common understanding, always subject to change, with a wide range of domestic stakeholders and international development partners. In Tanzania, intense dialogue and very high government commitment led to early successes in improving public financial management and budget execution in the first PRSC series. But some achievements stagnated or were reversed in the second series, when attention was diluted to include a broad range of sectoral reforms and other aspects of governance. 4.3 Lesson 2\. PRSCs can make little progress without a foundation of trust between the Bank and the government, and among development partners at the institutional and individual levels. Without sufficient trust, negotiated and agreed-upon triggers can quickly be transformed into more heavy handed conditions, whereby the level of future support is determined by strict adherence to pre-identified policy changes. In these circumstances, a scaled-back operation, more tightly focused around areas of agreement might gain more traction than one used as an enforcement mechanism for previously agree reforms that no longer have political backing. 4.4 Lesson 3\. PRSC programs risk becoming irrelevant if the design, scale, and scope are not adjusted as conditions change. The advance expectation that such changes will occur may smooth the transition should events warrant a scaling back of the program. Circumstances changed substantially during the second PRSC series in Tanzania\. reform champions in government and among development partners moved on; the presumption that sustained growth of 6-8 percent would lead to significant poverty reduction proved false; a new President was elected; and the country was affected by higher food and fuel prices and by the global financial crisis. The mechanisms for dialogue also need to evolve so that the program can continue to support and influence policy decisions at the highest strategic level. To avoid misunderstanding, the Bank and government could plan in advance to recalibrate the program at a set point during implementation. 4.5 Lesson 4\. The lack of well-defined and realistic objectives and a fully developed results framework makes adjustment to changing circumstances difficult. A results framework that clearly explains how policy actions are expected to lead to desired outcomes, in light of the support provided through investment lending and by other development partners, can provide a results-focused discipline to the program, improving selectivity in the process. 4.6 Lesson 5\. Regular reporting on key outcome indicators is essential so that data can drive adjustments to the PRSC program. Adequate investment in statistical capacity and the creation of a robust monitoring and evaluation system that addresses each step of the results chain to identify the key drivers of success or failure, while remaining focused on a few key outcome indicators, can help guide long PRSC series as circumstances evolve. Policy makers need to be aware of trends in outcomes in order to adjust the program accordingly. In Tanzania, reliable data on, for example, income poverty were available only once every seven years or so. Interim poverty simulations suggested significant poverty reduction as a result of sustained growth, but these projections turned out to be inaccurate. Household surveys every 3-4 years could provide much more timely and meaningful data to policymakers to allow for evidence-based adjustments during implementation. 4.7 Lesson 6\. Transitioning to the use of PRSCs as the primary instrument for resource transfer is only likely to be successful in rare circumstances, when strong central ministries can fully pursue a sector-inclusive dialogue representing the perspectives of key players throughout government. PRSCs themselves have very limited leverage in sector ministries, and the number and specificity of sector-specific triggers are necessarily curtailed when many sectors are covered. 4.8 Lesson 7\. Elevating to the national dialogue sector-specific structural reforms that stalled at the sector level does not guarantee their implementation. Even as the depth of sector exposure and experience permitted the sector content to be brought opportunistically into the PRSC, there is no evidence that this accelerated sector reforms or achieved greater cross-cutting momentum. Indeed, many of the same obstacles can prevent these reforms from taking hold, as was the case in energy, transport, agriculture, and water. Moreover, policy reforms committed to by central ministries are likely to be seen by implementing agencies, less vested in the PRSC program, as externally-imposed conditions, and subverted rather than adopted.
P095510 | Mexico Environmental Sustainability Development Policy Loan | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2009 | 2010 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/112851474565878789/text/000020051-20140624171011.txt | http://documents.worldbank.org/curated/en/112851474565878789/pdf/000020051-20140624171011.pdf | The ICR lists nine lessons learned (pp. 30-31). Most of these are not formulated as lessons but tend to be findings or recommendations. Several of the more significant ones have been reformulated as lessons and are presented below. (1) Comprehensive mainstreaming of environmental sustainability. If environmental sustainability is to be a cross-cutting priority, not only should the importance of the environment as an entity itself be maintained, but environmental concerns should be mainstreamed into all sectors. The latter requires the adoption of key sustainability principles in each sector involved and identification of specific actions. It also requires delicate intervention and coordination between many stakeholders.(2) Strong leadership of inter-institutional coordination is key. Given a complex institutional framework, mainstreaming of environmental sustainability requires strong leadership, or champions, from central or cross-cutting entities, such as Finance and Environment, as well as encouragement of learning, knowledge sharing, and being prepared to undertake significant behavioral change. (3) Budgetary and instrumental support to inter-institutional coordination is also necessary. Modest but timely grant resources can provide catalytic support for analytical work and stakeholder participation in the preparation of an operation intended to introduce environmental concerns in key economic sectors. However, to make an optimal contribution to mainstreaming and the coordination required, a Memorandum of Understanding (MOU) should also be negotiated, in which the Bank commits to support a series of advisory and analytical activities over the duration of the operation. A Technical Assistance Loan linked to a DPL operation would be another option to overcome some of the constraints to inter-sectoral coordination.(4) Importance of measurable and specific indicators. If the success of a cross-cutting operation with an overarching objective, such as balancing socio-economic development growth with environmental protection and improvement, or mainstreaming environmental sustainability into key economic sectors, is to be attained, relevant and measurable baseline and target values should be specified in advance and consistent outcome indicators be measured.(5) When preparing a new DPL, previous DPLs should be reviewed to ensure consistency over time and avoid duplication of effort. This can be particularly important with regard to DPLs that have a thematic aspect, such as environment, and are relatively close in time, although not part of a series. Each DPL should have its own relevant prior actions, which may build on the prior actions of previous DPLs but not duplicate them.
P095514 | AR Lifelong Learning Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2007 | 2014 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/601431474940524497/text/000012394-20150312070736.txt | http://documents.worldbank.org/curated/en/601431474940524497/pdf/000012394-20150312070736.pdf | The ICR (pp. 20-22) offers useful lessons:Piloting and learning, as well as dissemination of early successes, are key in projects involving innovative mechanisms and approaches. In this case, the Ministry of Laborâ€™s commitment to learning and scaling up related to the competency-based training and certification system â€“ which was piloted starting over ten years before the project began â€“ was crucial to achievement of results.Strategic and comprehensive engagement with the private sector is essential in a project that requires the private sector to provide both data and opportunity. In this case, sector councils played a dual role as both aggregators of technical know-how and conveners of relevant participants from industry, trade unions, and training institutions.A champion can facilitate progress in a variety of ways. In this case, the Minister of Labor provided strategic leadership over a period of ten years, supported senior management in the Ministry, and brought a diverse group of essential players to the table.
P095515 | AR Provincial Maternal-Child Health Investment APL 2 | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2007 | 2013 | 2015 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/537291474664756478/text/000020051-20140626114356.txt | http://documents.worldbank.org/curated/en/537291474664756478/pdf/000020051-20140626114356.pdf | The ICR (p. 18) identifies several lessons:Results-based financing can be implemented in a simple design with only 10 indicators. In this case, the Plan Nacer generated regular transfers from the central to the local governments and health facilities with limited administrative burden.Even if the results-based design is simple, key elements need to be in place. These include formal and transparent payment circuits, extra-budgetary transfers from the Provincial governments to the health facilities, and health facility autonomy. External concurrent audits of results are important management tools. In the Plan Nacer, audits helped to improve monitoring of the process and results, sending warnings if there were errors in reporting, and encouraging greater transparency in the use of funds.
P095520 | UY Promoting Innovation to Enhance Competitiveness | Latin America and Caribbean | Uruguay | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2007 | 2015 | 2016 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/978501468303082602/text/ICRR-Disclosable-P095520-06-09-2016-1465502149299.txt | http://documents.worldbank.org/curated/en/978501468303082602/pdf/ICRR-Disclosable-P095520-06-09-2016-1465502149299.pdf | Lessons drawn from the ICR and adapted by IEG: The time horizon for project impact is an important considerationin designing theresults framework and selectingkey indicators.The concepts in this projects objectivewere difficult to measure and the time horizon needed for the impact of innovation to materialize was beyond the scope of theproject period. Therefore, the indicators for this project largely focused on process and evidence of increasedcapacity. Awell-developedculture of innovation andan associative culture betweenpublic and private sectors are important pre-requisites for fostering transfer and adaptation of new technology. Thesefactors were not sufficiently considered in the project design and contributedto low demand for certain projectactivities.
P095523 | Haiti Transport and Territorial Development Project | Latin America and Caribbean | Haiti | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2006 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/988801475112335446/text/000012394-20150109095930.txt | http://documents.worldbank.org/curated/en/988801475112335446/pdf/000012394-20150109095930.pdf | The ICR Review selected a number of lessons from a longer list identified by the ICR, as follows:Informing beneficiaries and explaining the project execution strategies are particularly important if local population is to take full project ownership. Explaining the road strategy and design choices (gravel vs. paved) could help secure acceptance by the local population. In addition, release of information and rendition of accounts, could help avoid the capture of resources by local elite.Combining road investments with promotion of local development could improve the overall impact on local economy. While the improvement of transport conditions that make access to local markets easier and more reliable, complementary investments are necessary to promote opportunities for self-employment and income generation.As part of project design, it is important to provide resources to provide for emergency measures in post-conflict and disaster prone countries. An emergency component that could be triggered depending on prevailing emergency circumstances would be useful to avoid shifting a project's focus.
P095555 | Rural and Small Towns Water Supply and Sanitation Project II (PRAGUAS) | Latin America and Caribbean | Ecuador | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2007 | 2009 | 2011 | ICRR | Less than 10 million | Highly Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/798311474502049622/text/000020051-20140620065918.txt | http://documents.worldbank.org/curated/en/798311474502049622/pdf/000020051-20140620065918.pdf | 1. The Bank teams must be alert to changes in administration priorities and consider a restructuring of the project early on to make the necessary adjustments if common ground can be found on sound technical principles. The impact of political transitions on project implementation can be significant, in particular when the new administration disagrees with significant aspects of project objectives and design. The Bank should not shy away from sustaining high-level, frank discussions with incoming administrations on the scope and technical principles of on-going or new projects, and consider a mutually agreed cancellation as an acceptable option if no agreement can be found. 2. Rushing through initial implementation shortly before an administration change, despite allowing for more expedited implementation, poses risks especially when it can be expected that the incoming administration might have different priorities from the one preparing the project.3. Insulating the implementing team from staff turnover could have positive results in the case of highly unstable political environments, but also negative consequences, especially when the political context changes and the PMU staff no longer has the trust of the new political authorities. In such cases, it is important to recognize that the Bankâ€™s counterpart is not the PMU but the Governmentâ€™s implementing agency (in this case the Ministry) andthe Bank team must exert special care in identifying possible discrepancies between both.4. In the case of a deteriorating project implementation, it is important for the Bank team not to alienate the Borrowerâ€™s goodwill towards the project. Trade-offs must be made between the need to maintain or improve the quality of project implementation, and the need to maintain working relationships with the client so as to reduce the risk of having to close a project without the support and engagement of the client.
P095563 | PE- (APL2) Health Reform Program | Latin America and Caribbean | Peru | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2009 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/250561490017516386/text/ICRR-Disclosable-P095563-03-20-2017-1490017497194.txt | http://documents.worldbank.org/curated/en/250561490017516386/pdf/ICRR-Disclosable-P095563-03-20-2017-1490017497194.pdf | The ICR (pp. 26-27) identifies a number of interesting lessons, including: The health sector cansuccessfullyinteract with other agencies to push forward the agenda of both agencies. The project was an example ofhow the health sector supported the issuance of birth certificates. While there are many initiatives to encourage the unregisteredto get identification papers, tying the initiative to a useful benefit (health insurance) appears to have to beensuccessful. While having good baseline data and generallyreliable data sources is important, a good resultsframework also requires realistic targets and outcomes that are related to the PDO. While theproject had areasonably strong results framework, the lack of focus on several key outcomes as well as the lack of data for some indicatorsreduced the utility of the results framework. The project could have identified indicators that were better aligned with theprojects underlying model. Likewise, the project could have better assessed what data were currently available and what datawere likely to be difficult to collect; this was not an issue for the key indicators but proved a challenge forafewindicators. Politics can play a major role in designing and implementing investment projects.There is much discussion about political economy and project implementation, and this project can serve as an example of how thiscan affect design and implementation in practice. After initialdelays, the project team was able to work with the newgovernment to implementa project that was consistent with their goals.
P095569 | AR APL2 National Highway Asset Mgt | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2007 | 2014 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/545311475118338845/text/000012394-20150109150810.txt | http://documents.worldbank.org/curated/en/545311475118338845/pdf/000012394-20150109150810.pdf | The following lessons are adapted from the ICR:The policy of independent technical audits during project implementation proved to be extremely valuable as they helped identified a number of deficiencies or needs for improvements in the supervision by DNV, that were subsequently addressed.Institutional reforms or even improvements may or will not take place within a short expected time-frame and without the Borrowerâ€™s consent and ownership. In order to avoid those shortcomings, future projects should concentrate on a achievable tasks for which the Borrower shows to have a genuine appetite.
P095570 | Peru Decentralized Rural Transport Project | Latin America and Caribbean | Peru | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2007 | 2014 | 2015 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/629351467986318683/text/ICRR14674-P095570-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/629351467986318683/pdf/ICRR14674-P095570-Box393183B-PUBLIC.pdf | The following lessons are taken from the ICR with some adaptation of language:Rehabilitating rural roads can be an effective mechanism for increasing access to economic opportunities and social services, and thereby reducing the incidence of rural poverty. However, while having adequate roads is necessary for a variety of production activities, road rehabilitation activities may need to be complemented with interventions in other sectors to enhance their impact. The experience with this project shows that these interventions need to be carefully prepared. Appropriate coordination mechanisms reflecting the commitment of higher levels of Government need to be in place, and the collaboration of agencies representing other sectors needs to be adequately funded.Activities, such as the improvement of NMT tracks, that connect the remote regions with provincial and district capitals had a notable impact in the case of this project, and may be replicable in countries with similar geographic and local governance characteristics.Using local expertise and knowledge, such as participating planning methods, and involving local populations in road maintenance activities can be helpful in both creating local employment and in generating local entrepreneurship.An appropriate legal framework and corresponding institutional arrangements are essential to ensure adequate funding for, and management of, the routine maintenance of the rural road network. While there was significant transfer of resources from the central government to the municipalities for road maintenance in the case of this project, neither Provias Decentralizado nor the Provincial Road Institutes had become permanent government structures by closure.
P095575 | Programmatic Governance Reform & Growth | Western and Central Africa | Sierra Leone | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2007 | 2013 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/866571474631897892/text/000020051-20140625155055.txt | http://documents.worldbank.org/curated/en/866571474631897892/pdf/000020051-20140625155055.pdf | The following lessons are drawn from the ICR and considered especially important by IEG:1. Embedding policy reforms in the Governmentâ€™s reform agenda instills greater government ownership of the program, diminishing the risk of delays or shortcomings in achieving objectives.2. In a country short of management capacity, a detailed M&E framework is not likely to be sustainable without intensive donor inputs and supervision.3. The consistency in team leadership of supervision (as was the case in all three GRG operations) from appraisal of the initial operation and though completion can have a strong positive role in program performance.
P095593 | TP: Energy Services Delivery Project | East Asia and Pacific | Timor-Leste | Blend | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2007 | 2012 | 2014 | ICRR | Less than 10 million | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/415261475114828079/text/000020051-20140626105015.txt | http://documents.worldbank.org/curated/en/415261475114828079/pdf/000020051-20140626105015.pdf | Lessons adapted from the ICR:Effective project implementation in fragile, conflict, and/or post conflict states requires intensive on the ground implementation support. The presence on the ground of more experienced staff could have helped to unblock many of the constraints that affected implementation.For projects that involve a policy reform component, Government ownership and commitment should not only be assured at design stage but should be managed and monitored during implementation. Not much was done to monitor Borrower commitment at early stages in the project until it was too late and there was not time to try and help build consensus around the issue of commercialization of Electricidade de Timor-Leste. Even though a Bank financed project is confined to a small segment in a sector, knowledge and information of the overall sector environment and ongoing investments is critical to be able to appreciate and adjust to factors that may impact the Bank supported operation.
P095617 | Northern Botswana Human Wildlife Coexistence Project | Eastern and Southern Africa | Botswana | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2010 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/632331485904914100/text/ICRR-Disclosable-P095617-01-31-2017-1485904907419.txt | http://documents.worldbank.org/curated/en/632331485904914100/pdf/ICRR-Disclosable-P095617-01-31-2017-1485904907419.pdf | 1.An ME program needs to be established at or before the beginning of a project; with monitorable indicators toassess project outputs and key outcomes; an implementation plan; staffing and training; and a baseline survey as needed. This isparticularly important for a pilot program testing a new approach destined for wider application.TheME program started extremely late, and data on Human Wildlife Coexistence - the heart of the project - only started to becollected at the end of the projects third year. In its establishment and implementation, ME fell short in most of thefeatures above.2. For project data where baseline information is incomplete or non-existent,proxy data, which can partially serve the same purpose, should be considered early in project implementation.For critically needed information, a targeted surveymay also be helpful to obtain the baseline informationrequired. In this case, proxy data, such as the degree to which local communities adoptedproject recommended practices, and community intentions on whether to continue HWC approaches, would have given some indication ofthe perceived utility of theprojects new approach. For critically needed information such as this a small targetedsurveymight have been helpful.3. Stated project objectives and associated indicators need to berealistic in the light of past and anticipatedtrends, measurable by practical means, and achievable within the projecttimeframe.In this case, the original indicator on reduced HWC was too ambitious against a rapidlyrising elephant population and increasing human pressures.
P095626 | Second Family Health Extension Adaptable Lending | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2008 | 2015 | 2016 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/327481468000904756/text/ICRR14854-P095626-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/327481468000904756/pdf/ICRR14854-P095626-Box394823B-PUBLIC.pdf | Lessons drawn from the ICR (pages 25-26), adapted by IEG:Maintaining the relevance of a project (and ensuring its effectiveness) in the context of vastly changed government policy requires both Bank and Borrower involvement. In the case of this project, even with positive developments on the part of the Borrower (increased availability of government budget), the project impact was limited due to the inability to engage in policy dialogue and restructure the project in a timely manner.Inconsistencies between national legislation and Bank procurement processes need to be reconciled to avoid increased transaction costs for the implementing agency and reduce the risk of procurement inactions. In the case of this project, municipal governments were reluctant to risk non-compliance with national procurement guidelines and therefore did not execute sub-projects.
P095657 | Tanzania Fifth Poverty Reduction Support Credit | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2007 | 2008 | 2012 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/714031474571401951/text/000020051-20140625065432.txt | http://documents.worldbank.org/curated/en/714031474571401951/pdf/000020051-20140625065432.pdf | There are four important lessons:1. Realistic monitoring frameworks are important tools for effective reform, important for government, but also for the Bank and other donors. MKUKUTA, well intentioned though it was, clearly provided an overly optimistic and ambitious framework for monitoring and evaluation. As the Bank modified its approach to monitoring over this PRSC series, it produced a more meaningful framework. Still, the use of WBI governance indicators is not ideal, as they are measures relative to other countries, whether or not such countries are comparable to Tanzania. Poverty head counts were (and are) only available with a considerable lag, and so cannot reflect current progress, even though having the desirable property of broadly capturing progress, or lack of it. 2. There are drawbacks to long term commitments of budget support which need to be carefully weighed against the benefits, in terms of government efficiency, of being able to count on budget resources over time. In this case, it appears that not only was there a downward trend in performance, but that donor support may have also contributed to what appears to be a sustainability issue -- the high level of government expenditures relative to GDP, and, within that, the high level of wages. 3. Stationing key staff in country offices is important in enabling the Bank to provide good advice, even if that does not always translate into results. This good practice should be continued. 4. Far-reaching reform programs need to be carefully tailored to human capacity constraints. In this case, the sophisticated process supporting implementation outpaced the human resources available, especially on the government side, which was also limited by availability of dependable office communications (such as email). For the future, the Bank should seek to support reform programs more realistically grounded in capacity.
P095657 | Tanzania Fifth Poverty Reduction Support Credit | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2007 | 2008 | 2013 | PPAR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/542381468133184866/text/781880PPAR0Tan00Box377382B00PUBLIC0.txt | http://documents.worldbank.org/curated/en/542381468133184866/pdf/781880PPAR0Tan00Box377382B00PUBLIC0.pdf | 4. Lessons 4.1 The implementation of PRSCs 1-8 spanned nearly a decade during a period of sustained macroeconomic stability and fast economic growth, offering lessons both for Tanzania and other countries with similar development challenges. 4.2 Lesson 1\. Direct and sustained focus and clarity of vision over the entire course of implementation of PRSC programs that cover many years is required to facilitate lasting reforms particularly with regard to public sector governance. There is a significant risk of backsliding when attention is shifted to other priorities. Yet joint budget support is a messy attempt to reach a common understanding, always subject to change, with a wide range of domestic stakeholders and international development partners. In Tanzania, intense dialogue and very high government commitment led to early successes in improving public financial management and budget execution in the first PRSC series. But some achievements stagnated or were reversed in the second series, when attention was diluted to include a broad range of sectoral reforms and other aspects of governance. 4.3 Lesson 2\. PRSCs can make little progress without a foundation of trust between the Bank and the government, and among development partners at the institutional and individual levels. Without sufficient trust, negotiated and agreed-upon triggers can quickly be transformed into more heavy handed conditions, whereby the level of future support is determined by strict adherence to pre-identified policy changes. In these circumstances, a scaled-back operation, more tightly focused around areas of agreement might gain more traction than one used as an enforcement mechanism for previously agree reforms that no longer have political backing. 4.4 Lesson 3\. PRSC programs risk becoming irrelevant if the design, scale, and scope are not adjusted as conditions change. The advance expectation that such changes will occur may smooth the transition should events warrant a scaling back of the program. Circumstances changed substantially during the second PRSC series in Tanzania\. reform champions in government and among development partners moved on; the presumption that sustained growth of 6-8 percent would lead to significant poverty reduction proved false; a new President was elected; and the country was affected by higher food and fuel prices and by the global financial crisis. The mechanisms for dialogue also need to evolve so that the program can continue to support and influence policy decisions at the highest strategic level. To avoid misunderstanding, the Bank and government could plan in advance to recalibrate the program at a set point during implementation. 4.5 Lesson 4\. The lack of well-defined and realistic objectives and a fully developed results framework makes adjustment to changing circumstances difficult. A results framework that clearly explains how policy actions are expected to lead to desired outcomes, in light of the support provided through investment lending and by other development partners, can provide a results-focused discipline to the program, improving selectivity in the process. 4.6 Lesson 5\. Regular reporting on key outcome indicators is essential so that data can drive adjustments to the PRSC program. Adequate investment in statistical capacity and the creation of a robust monitoring and evaluation system that addresses each step of the results chain to identify the key drivers of success or failure, while remaining focused on a few key outcome indicators, can help guide long PRSC series as circumstances evolve. Policy makers need to be aware of trends in outcomes in order to adjust the program accordingly. In Tanzania, reliable data on, for example, income poverty were available only once every seven years or so. Interim poverty simulations suggested significant poverty reduction as a result of sustained growth, but these projections turned out to be inaccurate. Household surveys every 3-4 years could provide much more timely and meaningful data to policymakers to allow for evidence-based adjustments during implementation. 4.7 Lesson 6\. Transitioning to the use of PRSCs as the primary instrument for resource transfer is only likely to be successful in rare circumstances, when strong central ministries can fully pursue a sector-inclusive dialogue representing the perspectives of key players throughout government. PRSCs themselves have very limited leverage in sector ministries, and the number and specificity of sector-specific triggers are necessarily curtailed when many sectors are covered. 4.8 Lesson 7\. Elevating to the national dialogue sector-specific structural reforms that stalled at the sector level does not guarantee their implementation. Even as the depth of sector exposure and experience permitted the sector content to be brought opportunistically into the PRSC, there is no evidence that this accelerated sector reforms or achieved greater cross-cutting momentum. Indeed, many of the same obstacles can prevent these reforms from taking hold, as was the case in energy, transport, agriculture, and water. Moreover, policy reforms committed to by central ministries are likely to be seen by implementing agencies, less vested in the PRSC program, as externally-imposed conditions, and subverted rather than adopted.
P095673 | Jamaica Early Childhood Development Project | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2008 | 2019 | 2020 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/169571569006781262/text/Jamaica-JM-Early-Childhood-Develop-Proj-SWAP.txt | http://documents.worldbank.org/curated/en/169571569006781262/pdf/Jamaica-JM-Early-Childhood-Develop-Proj-SWAP.pdf | A Sector Wide Approach (SWAp) using disbursement-linked targets (DLTs) can align incentives within Government to achieve aprojects targets and aid intersectoral coordination. In this case, central government authorities were incentivized toengage relevant line ministries, and the implementing entities outside the main implementing agency (the Early ChildhoodCommission, ECC) were encouraged to collaborate to meet project targets. A conventional input-focused project may not havemobilized all agencies in a unified action plan in the same way. Nonetheless, a more streamlined model with fewer DLTs and asimpler results frameworkmay well have reaped the same relative benefits, with less need for changed schedules andrestructurings.Whether a project uses a SWAp or traditionalinvestment project design, it is necessary to ensure thatadequate incentives, authority, and communication mechanismsare in place to sustain commitment and accountability from allpartners, and that cross-sectoral coordination bodies have leverage to drive results. In this case, the ECC initially lacked fullauthority to hold other executing agencies accountable and to sanction non-compliant early childhoodinstitutions.Project targets should be set realistically, accounting for the implementing organizationsexperience. In this case, ECC faced a steep learning curve as it began project implementation. A phased approach to build capacityinitially, or setting more explicit objectives of strengthening overall project management, might haveincreased effectivenessandreduced the need to adjust targets.Building and sustaining effective quality assurance (QA) systems starts withcareful setting of initial standards. In this case, for the certification of well-child clinics, the Ministry of Health createdstandardsthat almost no facilities were prepared to meet, contributing to the projects missing the certificationtarget, and leaving a temporary void in standards.Where project disbursements are against grants to a large number ofdecentralized institutions with improvement action plans, effects on equity need to be monitored. In this project, disbursementswere linked to aggregate targets, for example, the percentage ofECIs and health centers with well-child clinicscertified. Although grants to these institutionsformed the largestshare of disbursements, there was littleevidence in the project documents that the criteria against which grants were made were examined, revised, and/or monitoredthroughout the project with an eye toward effects on results and equity. The desire to meet targets related to standards couldresult in disproportionate resources allocated to facilities that are close to higher standards at the outset, thus serving moreadvantaged areas.
P095673 | Jamaica Early Childhood Development Project | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2008 | 2019 | 2022 | PPAR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099320308182223291/text/IDU01924461909e27042620b46a0b42f9cf5c099.txt | http://documents.worldbank.org/curated/en/099320308182223291/pdf/IDU01924461909e27042620b46a0b42f9cf5c099.pdf | 3. Lessons 3.1 Collaboration, strong national ownership of the NSP, and financial support are requisite conditions but do not ensure performance and outcomes because the World Bank must also provide rigor and candor in its dialogue and advice. During preparation, the World Bank team needed to be more rigorous in its appraisal of the NSP and act as a â€œcritical friend.â€ This is a â€œtrusted person who asks provocative questions, provides data to be examined through another lens, and offers critique of a person's work as a friend.â€7 The value of the critical friend would be to challenge the practices and assumptions supporting the NSPâ€”in this case, to help the project improve. The World Bank team could have offered hard truths and frank assessments that counterparts would otherwise tend to avoid if not managed constructively, supportively, and professionally. The lack of a clear-eyed assessment from the start about what Jamaica could do realistically and effectively in this subsector indicates that the World Bank team may have deferred to government counterparts and avoided frank discussion during preparation. During implementation, the issues became clearer in relation to support for parenting, the CHDP, the early intervention system, and the scale of the task involved in certifying all ECIs. A critical friend would have used a different lens at the Mid-Term Review or during the additional financing negotiations and asked what Jamaican research showed about the parental interventions needed to have an impact on parental knowledge, practices, and educationâ€”particularly in the known contexts of vulnerability and high inequalityâ€”rather than canceling and lowering DLTs. 7 https://www.edglossary.org/critical-friend/ 29 3.2 Country teams need to share and archive lessons and implementation knowledge, including Global Practice knowledge, across projects. The World Bankâ€™s support for the PATH program and HIV/AIDS project offered rich lessons that were applicable to ECDP. IEG became aware of these lessons during interviews in the 2014 case study of Jamaica (World Bank 2015). The World Bank support for the two earlier operations left a legacy of institutional structures and procedures that equipped the ministries for expansion and sustainability at the central and community levels. Preparation for these operations included development of delivery mechanisms that were created from study tours and continuous technical support. The World Bankâ€™s ECDP preparation team may or may not have known about these lessons. Moreover, all relevant Global Practices are repositories of experience with cross-sectoral arrangements that the preparation team might also have drawn on to inform project preparation. The Country Management Unit has an important role as a conduit for such tacit knowledge sharing, particularly in cross-sectoral work where relevant learning in one sector may not be readily accessible to another, or a countryâ€™s experience with making intersectoral coordination effective may have been forgotten. This may require creating a mechanism that TTLs can mine. It may also imply that the Country Management Unit actively build knowledge synergies among TTLs and teams, which is challenging with staff turnover. A mechanism by which the unit could provide essential learning would allow TTLs to act from a knowledge base built on a combination of global evidence and local knowledge gained from implementation. 3.3 The institutional arrangements for cross-sectoral or cross-ministerial action and coordination are less likely to succeed when authority is centered in one of the involved ministers or ministries. Reporting to one of the ministers has been counter to the vision of equal partnership. After the first five years of implementation, and with a change in government, the ECCâ€™s role emphasized functions of a regulatory body for ECIs, which did not require a high level of engagement by the Ministry of Health and Wellness and Ministry of Labour and Social Security. Some of the other shortcomings of the ECDP were caused by budgeting issues that were partly imposed by exogenous factors, but the lack of authorities in ministries other than the education ministry contributed to the implementation difficulties. This was manifest in the lack of funding for certain key activities, such as those related to support for parenting, the effectiveness of the CHDP, and others that did not receive the funding necessary to execute directives from an authority removed from the mainstream of activities in the health and social protection sectors. Perhaps it was inevitable that the ECC, under the direction of its board and answerable to the Minister of Education, would have difficulty delivering on its cross- sectoral mandate without direct influence over the Ministry of Health and Wellness and Ministry of Labour and Social Security. Ensuring that the ECC reported to a higher 30 authority (as is done in some countries) may have prevented or resolved some of the issues that emerged. 3.4 Intersectoral coordination may more likely be sustained with â€œlight mechanismsâ€ and financial resources that empower ministries and national agencies to focus on achieving a convergence of common policies, actions, and results. The ECCâ€™s leadership of intersectoral coordination, including planning and budgeting, was provided through interministerial and intersectoral planning processes. The ECC made efforts to enhance coordination among the partner ministries, and memorandums of understanding were signed. There is no evidence that mechanisms were established within the partner ministries to manage ECD implementation and planning based on decisions made by the ECC. Moreover, planning meetings have ceased since the close of ECDP. Lighter mechanisms built around convergence of common policies and actions may be needed. However, without supplementary financial and human resources to implement additional activities, the expectation of accountability to deliver results is not realistic. 31
P095675 | Second Programmatic Sustainable and Equitable Growth Loan | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2006 | 2008 | 2010 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory |  | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/837651474563365535/text/000146597-20140619151905.txt | http://documents.worldbank.org/curated/en/837651474563365535/pdf/000146597-20140619151905.pdf | It pays off to limit the objectives of an operation to a few that are feasible, realistic, and have the Government's political commitment.
P095681 | OECS (Grenada) Skills for Inclusive Growth | Latin America and Caribbean | Grenada | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2009 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/706411474635822529/text/000020051-20140626124423.txt | http://documents.worldbank.org/curated/en/706411474635822529/pdf/000020051-20140626124423.pdf | Several lessons emerge from the information provided in the ICR:Skills training programs that aim to improve employability of youth need to collect the relevant indicators. In this case, the objective was to improve employability; however, the project did not conduct any tracer survey or employer survey to examine whether training is relevant and improves employability. To strengthen M however, without a clear financing plan for recurrent costs, this agency is likely not to be sustained. Project designs must be kept flexible and adjusted to changing circumstances. Economic downturns and structural changes in the economy are common. Since training programs supply skills to the labor market, these projects should take a comprehensive approach and take into account the various factors that require an adjustment of training to market needs. The IEG youth employment evaluation has highlighted the need for cross-sector collaboration. In this case, collaboration between different teams that work on education and job creation in different sectors would have been useful to better bring together the demand and supply side.
P095730 | Fourth Poverty Reduction Support Credit | Western and Central Africa | Ghana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2006 | 2008 | 2010 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/836611475093934104/text/Ghana-Fourth-Poverty-Reduction-Support-Credit.txt | http://documents.worldbank.org/curated/en/836611475093934104/pdf/Ghana-Fourth-Poverty-Reduction-Support-Credit.pdf | One major lesson is that the dialogue in the context of PRSCs was clearly ineffective in influencing the government's policy of subsidizing electricity. Energy subsidies, including to the state-owned aluminum smelter, are a major drain on the budget, and other means will have to be found to strengthen this dialogue.A second lesson is that the PRSCs, although to a lesser extent than the debt forgiveness in the mid-2000s, while providing resources for social development, were counterproductive in their objective of promoting macroeconomic stability. The provision of generous budget support encouraged excessive public spending which eventually threatened fiscal sustainability.
P095759 | Morocco - Public Adminstration Reform Loan III | Middle East and North Africa | Morocco | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2008 | 2009 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/661781474566109555/text/000020051-20140625061224.txt | http://documents.worldbank.org/curated/en/661781474566109555/pdf/000020051-20140625061224.pdf | Lessons in the ICR are all supported. Of particular merit is the lesson that the visibility of the reform needs to be scaled up. Administrative reforms such as those supported by the series take many years to deliver substantial improvements in administrative processes, and longer to deliver visible outcomes such as better public services and reduced corruption. Given pressure from civil society groups, such as Morocco's February 20th movement, such reform programs need to focus on producing and effectively communicating visible short term results of direct benefit to the general public, using the "rapid results approach" and pro-active, external communications. Another lesson is the critical importance of a package of analytical work, technical assistance, investment operations, and operational support to help governments to use DPLs productively.
P095840 | First Water Sector Development Policy Loan | Middle East and North Africa | Morocco | IBRD | Non-FCS | Sustainable Development | Water | IBRD | DPF | 2007 | 2008 | 2012 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/960971475070713802/text/000020051-20140620072722.txt | http://documents.worldbank.org/curated/en/960971475070713802/pdf/000020051-20140620072722.pdf | Quality analytical work and policy dialogue involved in preparing and implementing a sectoral DPL can help to launch a process of far-reaching changes in the sector, even when all of the loan objectives are not achieved. The DPL preparation, in the opinion of many sector officials, provided an unprecedented forum for all key stakeholders to pursue a dialogue on a coordinated and comprehensive sector reform agenda and to produce a broadly scoped and ambitious reform program with dynamism which will last beyond the immediate timeframe of this DPL operation.A reform agenda and implementation responsibilities should not be assigned to an agency whose situation is precarious. In this case, CIE seemed to be the logical choice to pursue sectoral reform but with the change in government the activation of this agency did not happen, causing much of this project to falter.It is preferable to avoid a coincidence between the inception of a complex reform program and a change in administration in the Borrower country. If this is absolutely unavoidable, then the design of the program, and especially its timetable, should take account of the likely delays resulting from the new government's need to study the program and adopt it as its own.It takes time to develop consensus around by-laws and decrees and their adoption by the appropriate authorities, and this should be carefully considered when planning timelines.
P095847 | Second Water Sector Investment | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2009 | 2015 | 2017 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/222221468528193683/text/ICRR-Disclosable-P095847-07-14-2016-1468528174608.txt | http://documents.worldbank.org/curated/en/222221468528193683/pdf/ICRR-Disclosable-P095847-07-14-2016-1468528174608.pdf | The ICR draws nine lessons, and the three most important are summarized below. Take time and clarify theexact nature of the project. The project design suffered from cross-purpose communication on whether to design the projectas desired by the Borrower, to stop preparation, or to find a poor compromise. Coming to an agreement on the need for institutionalreform is critical, and it would have been a good idea to elevate that discussion to higher levels within the Bank, the Borrower,and the other cofinanciers. In the case of Kazakhstan, for instance, when discussing one of the World Banks first CountryPartnership Strategy, differences of opinion were hammered out in a number of high level retreats in Geneva during the years 2004and 2005 with the participation of a number of mutually recognized global leaders in the areas of discussion. In the end, allparties benefitted. Clarify areas of disagreement, rather than obfuscate, and do that jointly. Theproject would have greatly benefited from a solid institutional analysis at appraisal. Such an analysis would have provided allstakeholders with a comprehensive and level playing field. A typical analysis would include an inventory of all relevant playersand current rules of the game, and propose alternative solutions to achieve agreed goals. Importantly it would be based on analysesof skill-gaps incentive and sanctions, responsibilities, accountabilities, rewards structures, and an understanding of thepolitical economy. During preparation, ensure that components are logically linked to the developmentobjectives. The five components of this project had only one thing in common: they featured in the governmentsWater Sector Strategy Investment plan. The preparation team struggled to put those components into a development objective, andultimately failed. They should have worked in the opposite direction: first determine what constitutes success, and then design thecomponents that will help achieve that goal. To be more specific, the development objective should have included wording aboutsustainable and efficient water management in irrigated agriculture, in order to improve in the long-run incomes and livelihoods ofa given target population. It would have been immediately obvious that that population could not simply improve their irrigationefficiency without a number of supporting services, including research and extension, capacity building, input supply andmarketing.
P095863 | Dominican Republic Municipal Development Project | Latin America and Caribbean | Dominican Republic | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2010 | 2017 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/485691518468171563/text/Dominican-Republic-DO-Municipal-Development.txt | http://documents.worldbank.org/curated/en/485691518468171563/pdf/Dominican-Republic-DO-Municipal-Development.pdf | Based on the ICR, draws three main lessonscan be drawn fromthis project:(1) A communityparticipation approach can enhance municipal service deliverywith increasedcommunity-participation.Thepreparation of Municipal Development Plansand prioritizationofmunicipal investmentsbased oncommunity-expressed needs fostered a high degree of ownership at design.Theownership that was fostered at designcontinued during implementation due to the involvement of thelocalcommunities in the technical,social and environmental aspects ofongoing works in their area.This aided inaddressingconcerns both on site and in the community.(2) Establishing a mechanism for financinginvestments following successful achievement of institutional strengthening targets can yield positive results. In thisproject, activities were sequenced, with institutional strengthening project activities preceding activities aimed at investment inmunicipal works.(3) Maintaining small project teams and employing third parties for institutional strengtheningactions can help in executing local government project.The team in this project was kept small and consultants andfirms were used for activities aimed at institutional strengthening across 31 local governments.
P095873 | Education Sector Support | East Asia and Pacific | Timor-Leste | Blend | FCS | Human Development | Education | IDA | IPF | 2007 | 2013 | 2015 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/888571475118433533/text/000180307-20141203050612.txt | http://documents.worldbank.org/curated/en/888571475118433533/pdf/000180307-20141203050612.pdf | The following lessons are adapted from the ICR:Especially in the context of fragile countries with weak implementation capacity, simple and focused project designs and readiness for implementation provide an enhanced opportunity for success. Ambitious, overly complex designs should not escape the peer review process, the QER and Management reviews.. Intensive consultant support in a weak capacity country is not likely to culminate in strengthened Government capacity, without specifying a number of principles in consultantsâ€™ terms of reference, including: (a) recruitment of qualified local staff to be paired with consultants; (b) a clear mentoring/coaching program for local staff; (c) clear intermediate and final measurable targets to ascertain skills acquisition; and (d) a simple verification mechanism by a qualifying third party. A well-conceived results chain and a functional M&E system are critical inputs for informed policy decisions and resource allocations. Moreover, they make it possible to track the achievement of objectives and targets, which can be catalytic in mobilizing resources and attention to areas of weak performance. Capacity development in these areas is essential for Governmentâ€™s leadership in the strategic management of the sector.
P095877 | Second Programmatic Development Policy Loan for Sustainable Development | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2007 | 2008 | 2011 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/104841475091562162/text/Colombia-Programmatic-Development-Policy-Loan-For-Sustainable-Development.txt | http://documents.worldbank.org/curated/en/104841475091562162/pdf/Colombia-Programmatic-Development-Policy-Loan-For-Sustainable-Development.pdf | The lessons arising from the overall series are presented in the ICRR for Third Programmatic Development Policy Loan for Sustainable Development (P0101301).
P095883 | Reconstruction of Aceh Land Administration System Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2005 | 2009 | 2011 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/417251475098659162/text/000020051-20140624155349.txt | http://documents.worldbank.org/curated/en/417251475098659162/pdf/000020051-20140624155349.pdf | The ICR presents an extensive list of lessons for land administration projects implemented under post-disaster circumstances. Some of the most pertinent are adapted and presented below:A clear commitment on the part of national authorities to protect property rights is critical in avoiding large-scale land grabbing and speculation in the aftermath of a natural disaster such as a tsunami. It is also important to explicitly recognize and build upon the multiple legal systems (i.e., secular, religious, and customary) that determine land rights in the country. Customary land practices are often designed as safety nets to protect the most vulnerable groups, including women. It is critically important not to undermine these safety nets in the transition from customary rights to state-provided land tenure and administration systems.Community-based approaches for land adjudication may be an effective way to accelerate the land adjudication process and facilitate the resolution of land disputes at the village level, especially when other records and evidence of ownership are lacking but where community ties are strong. The use of existing mechanisms can help ensure that benefits flow quickly to communities following a disaster.Partnerships between land agencies and the wide range of actors involved in reconstruction efforts is important, including nongovernmental organizations, civil society organizations, and donors. A key factor contributing to the project's design and its broad acceptance was that strong partnership with multiple stakeholders was achieved at the time of project preparation. The projectâ€™s effectiveness was weakened during implementation when emphasis on collaboration declined.An overly centralized project management is not conducive to the effective implementation of projects in which logistically complex field activities and necessary civil society engagement are at the core of the project. Similarly, implementing emergency response projects through centralized budgetary systems can cause significant challenges to implementation.A Beneficiary Impact Assessment can be an excellent complement to the Results Framework of emergency projects, which, given the inherent time constraints at preparation, might not have robust impact and results indicators. However, the experience from this and other projects shows that such assessments may need to be externally financed and supervised to ensure that they are carried out and to avoid overtaxing the capacity of the implementing agency.
P095925 | Alexandria Coastal Zone Management Project (Under the Investment Fund for the Mediterranean Sea Large Marine Ecosystem) | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2010 | 2017 | 2018 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/157861525389457938/text/Egypt-Arab-Republic-of-EG-GEF-Alexandria-CZM-Lake-Mariout.txt | http://documents.worldbank.org/curated/en/157861525389457938/pdf/Egypt-Arab-Republic-of-EG-GEF-Alexandria-CZM-Lake-Mariout.pdf | The ICR provided comprehensive lessons. The most important follows with some modification oflanguage: Public consultation and engagement are essential to building trust and sustaining an ICZM. The projectdemonstrated some key aspects of an effective ICZM and pilot water treatment interventions in Egypt: (a) continuous transparencyand extensive stakeholder consultations; (b) a design that allowed for an iterative, flexible, and adaptable process; (c) specialattention to strong institutional arrangements and high-level commitment; (d) a mix of top-down and bottom-up approaches tocoastal management; (e) an emphasis on capacity building and awareness raising; and (f) solution-driven implementation andquick wins (sludge drier and potential reuse by cement factories) instead of the conventional approach of treatment and dumping ofwaste(sludge). ICZM adoption and implementation, as wellas water treatment facilities, require time to yield results. The experience from the project showed that it requireschanging the mindsets of populations (fishermen of Lake Mariout and diversion of the El Qalaa drain), decision makers, andinstitutions, which itself requires evidence gathering, capacity building, awareness raising, and advocacy. It also involves policyformulation, extensive consultations, and political endorsement, which are time-consuming and dependent upon manyexternalfactors. Allocating sufficient time to project design and starting these processes as early as possible will avoid having to extendthe project (given that an unforeseen exogenous event does notoccur). Well-defined and quantitativemonitoring indicators are important to guide implementation for ICZM projects, when pollution reduction is the objective.A more systematic approach in designing and monitoring outcome indicators could further enhance project outcomes. Apreliminary hydrodynamic and water quality model can be very useful and could have helped quantify the effects on water quality atthe outflow of the intervention (to measure the actual efficiency of the biofilm and wetland) instead of only the discharge pointto the Mediterranean Sea. In this case an intermediate indicator could have measured the pollution reduction after the interventionat the discharge point of the biofilm and wetland. In addition, since BOD measurements in mg/L are difficult to conduct in thefield and results can fluctuate at the lake-sea interface (after rain events or prolonged dry periods), it is recommended toreframe the indicator in relative terms (such as the 5% reduction of BOD) rather than setting a target in absolute values.
P095949 | Local Urban Infrastructure Development Project | Western and Central Africa | Niger | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2008 | 2013 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/837621475116885075/text/000180307-20150108111756.txt | http://documents.worldbank.org/curated/en/837621475116885075/pdf/000180307-20150108111756.pdf | The ICR includes a lesson stating, â€œProjects in Niger [i.e., in low income, low capacity countries] need a strategic, robust, and multifaceted approach to training and capacity building. The project showed that in spite of identification of capacity gaps in implementing entities, and the construction industry in general, and inclusion of substantial capacity building activities, the starting point typically very low and such a project is vulnerable to institutional and organizational changes. For this reason, training and capacity building should be provided for all project stakeholders, designed to start during project preparation and continue throughout the implementation period in anticipation of elections, institutional changes, and staff turnover.â€ This review seconds this lesson, but adds that appropriate monitoring and evaluation of these human capital efforts must be required. Effective training begins with a needs assessment, followed by curriculum development and piloting, evaluation, revision, and then full implementation. The ICR states â€œDelegated contract management has the potential to mitigate capacity shortcomings in project implementation, but the approach needs to be institutionalized and scaled up to succeed.â€ It behooves the Bank to carefully examine its role in this regard. Stronger assessment of human capital needs should take place in countries like Niger with lower levels of education and experience functioning in a modern economy, and a stronger emphasis on development of human capital should be required of Bank projects in such countries. In particular, the capacity of the main implementing agency responsible for the bulk of project disbursements should be closely assessed on all relevant dimensions and a plan should be developed on how to address human capital weaknesses. When Bank safeguards are triggered, M&E frameworks should be required to include how and when these issues will be monitored and evaluated. Training related to the safeguards and the monitoring of them should take place as soon as possible after the effective date. Participants in the training should demonstrate understanding of the issues and methods to be employed, and the results of the training should be kept within the project files.
P095965 | Siddhirganj Power Project | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2009 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/335071614022741101/text/Bangladesh-BD-Siddhirganj-Power-Project.txt | http://documents.worldbank.org/curated/en/335071614022741101/pdf/Bangladesh-BD-Siddhirganj-Power-Project.pdf | A separate policy-level project component should be included in project design to ensure a closersector-level engagement with the government in addressing fundamental sector governance issues, thereby promoting sustainability ofWorld Bank operations. Projects need to operate in the right policy environment in order to achieve success and givegovernments the full benefits of cleaner generation projects. Fundamental inefficiencies in the Bangladesh power system,specifically relating to out-of-merit-order dispatch of generation assets, may inhibit the achievement of the projects PDOs.The World Bank-financed Power System Reliability and Efficiency Improvement Project (P159807) is supporting the GoB inpursuing needed sector reforms to instill discipline in the dispatch process and enable significant annual savings for the country.As a forward-looking measure, government regulators/dispatchers should link economic dispatch to SCADA so that any possibility toarbitrarily adjust dispatch is removed and discipline is instilled in the dispatch process.Efficiency andflexibility in procurement management are important elements in facilitating implementation success. The World Bankneeds to give rapid decisions on procurement clearances. The Project suffered numerous procurement challenges, which inevitably ledto significant delays in project implementation. A number of these delays resulted from slow decisions and clearances from theWorld Banks side, including lengthy procurement reviews. Detailed Project Procurement Strategy for Development (PPSD) andqualifications of JV partners need to be carefully evaluated. A detailed PPSD should be in place where complex projects are beingprocured to avoid failed bidding processes. Moreover, the qualifications of JV partners must be carefully evaluated to ensure thateach JV partner is qualified to carry out the contract awarded. In the case of the debarment of the major equipment supplied, theWorld Bank/INT should make a significant effort to communicate clearly to country teams where these processes are ongoing at thecorporate level to ensure that clients are aware of potential implications and can avoid delays. Finally, robustcontract management mechanisms, including a comprehensive TA and capacity building component, need to be in place to ensure thesuccessful completion of complex projects.In designing the results framework, indicator targets need to beindependent of external factors and remain within the control of the project implementing units. The indicator tomeasure performance of the power plant, as designed in the original PAD and restructured RF, made the Project outcomes dependent onand measurable against external factors that were outside the control of EGCB and/or the Project itself. To ensure an accurateassessment of project outcomes, the indicator targets, against which PDOs indicators are measured, need to be designed such thatthe achievement of these targets remains (to the extent possible) independent of external factors outside of the control of aproject or project implementing units.Good community relations are important and should be a key feature ofproject implementation. These should include personal visits to the communities together with a well-functioning GRMand established Grievance Redress Committee (GRC). Both the components implemented by PGCB and GTCL involved the relocation ofpeople. In both cases, the implementing agencies together with the World Bank team helped to ensure that effective GRMs andwell-functioning GRCs were in place. In particular, the GRC should hold frequent meetings with the communities to deal withgrievances raised through the GRM. The GRC should be involved early on in all disputes with local communities to ensure timelyproblem-solving with the community, as was demonstrated effectively in theProject.
P095982 | Electricity Distribution and Transmission Improvement Project | South Asia | Pakistan | Blend | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2008 | 2014 | 2016 | ICRR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/565951468186275027/text/ICRR14881-P095982-PUBLIC.txt | http://documents.worldbank.org/curated/en/565951468186275027/pdf/ICRR14881-P095982-PUBLIC.pdf | The ICR draws the following lessons from the implementation experience of this project.(1). It is better not to overload investment projects with policy reforms. The experience of this energy sector project demonstrated that it would be better to implement an investment project and then complement it with broader sector and governance reforms. (2) A relatively flexible project design, which would enable the Bank to adapt to the needs of the multiple implementing agencies as in case of this project, without requiring administrative approvals and formal amendments to the legal agreements, can help in making the required changes during implementation. This flexibility can also aid in creating competition among the implementing agencies and thereby provide incentives for routing financing to the better-performing entities.(3) Identifying key issues at the preparation stage through lending or non-lending technical assistance activities can help in avoiding implementation delays. (4)Technical specifications should be prepared at the design stage, so that the project is ready for implementation upon approval. (5) Given the challenges associated with creation of new utilities after unbundling, it would have been better to start at a smaller scale with few utilities, help them develop a Business Plan to identify priorities and provide them with capacity-building and institutional strengthening support during the project preparation period. This experience, together with consultation workshops involving utility officials, could be used for developing a robust project design that could be expanded to other utilities with additional financing.(5) Project design should carefully establish a direct relationship between articulation of the PDO and the information needed to measure progress against that PDO.
P096017 | LAC Regional Sustainable Transport and Air Quality Project | Latin America and Caribbean | Latin America and Caribbean |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2009 | 2013 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/968251475112653946/text/000012394-20150108124300.txt | http://documents.worldbank.org/curated/en/968251475112653946/pdf/000012394-20150108124300.pdf | The IEG review endorses the three lessons filtered from the project implementation as detailed below: Design of Regional Projects: This operation raises a series of questions regarding the most appropriate way of structuring regional or umbrella type projects. More research is needed to shed more light on how better frame a regional umbrella project that is consistent and complementary with country projects.Aligning the Results Framework and the relevance of PDO indicator: The definition of appropriate and easily measurable set of indicators to reflect most objectively the level of achievement of the project PDOs was a challenge. That is particularly critical for projects that operate for several years in a changing environment when often the original results framework, or part of it, may become less relevant to the evolving context Adequate institutional arrangements matter: The implementing agency needs to be capable of exercising its implementation capacity since the grant/loan effectiveness. Trying to strengthen and build the implementation agency while in parallel trying to advance execution is not recommendable and often leads to delays in project implementation.
P096018 | Assam State Roads Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2012 | 2020 | 2020 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/849731593210515490/text/India-IN-Assam-State-Roads-Project.txt | http://documents.worldbank.org/curated/en/849731593210515490/pdf/India-IN-Assam-State-Roads-Project.pdf | The following lessons are adapted from the ICR (paras 80 to 90): The active engagement of policy makersand road agency staff is critical for road sector investments and reform. The Government of Assam showed strong commitmentand collaborated closely with the Bank, and actively supported the project at a high-level to steer the project when progress waslagging. Continued commitment during project implementation led to the acceptability of the PWRD reforms, accountability forprogress, and sustainability of the works. For clients with weak capacity, the Bank task teamsneeds to provide hands-on guidance while building client capacity. The initial weak capacity of the client was addressedthrough frequent handholding support for construction supervision, project management and contract management, along with anemphasis on key institutional reforms. The project context of a previously conflict-prone region with weak institutions made thishands-on approach a necessity for turning this project around from problem status. Subsequently, the mutual trust and clientconfidence developed led to the expected outputs and outcomes. Timely decision making for contractre-tendering is the primary corrective measure to rectify poor contractor performance. In this project, delays in civilworks contracts were mostly attributable to the lack of timely action by the big local contractors. The decision to terminate thesecontracts and re-tender the split packages (suitable for middle-size local contractors) resulted in speeding the progress of worksand improved construction quality.
P096019 | Himachal Pradesh State Roads Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2007 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/147151519773335799/text/India-IN-HP-State-Roads-Project.txt | http://documents.worldbank.org/curated/en/147151519773335799/pdf/ICRR-Disclosable-P096019-02-27-2018-1519774238033.pdf | IEG has selectedfour lessons from the ICR, with some adaptation of the language: To achievesystemic policy and institutional improvements in road financing and asset management, it is essential toengage proactivelywithgovernments on policy and institutional reform in an intensive and sustained manner. The project period spanned10 years, however itlargely failed in bringingmeaningful reforms and structural changesin roadfinancing androad asset management in HP. Theproject team focused on business as usual engineering approach and did notprovide sufficient attention toinstitutional issues. The project is seen as a missed opportunity to focus oninstitutional reforms as the key element of the Banks value proposition. When aproject involves a substantial amount of road works, it is important to first focus on strengthening in-house capacity fortechnical quality assurance and contract management. Under this project, inadequate capacity in these areasledthe implementing agencyto rely unduly on thecontract supervision consultantand the disputeresolution/arbitration mechanisms, which proved to be adversarial and ineffective. Flaws in detailed designs leading to majorvariation orders and cost escalations can best be prevented by the employers careful ex-ante quality review.Theimplementing agencyneeds toassess the key areas of competence required at each level of management and design acapacity building and technical assistance program in contract management and qualityassurance. The implementing agency and its head should be vested with appropriateauthority for most management decisions. Under this project,the lack of independent authority of the chiefengineer/project director in the implementing agency was a significant contributor to implementation delays. Most decision makingwas centralized at higher levels, including a board which did not convene often. Forroad investments, a market study of local contractors should be carried out during project preparation to guide the packaging ofworks so as to maximize the participation of contractors and obtain the best value for money. The BanksProject Procurement Strategy for Development (PPSD) should in the future increase the likelihood of attracting well-performingbidders for road improvement contracts.
P096021 | Andhra Pradesh & Telangana Road Sector Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2019 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/375331580232575614/text/India-IN-AP-and-Telangana-Road-Sector-Project.txt | http://documents.worldbank.org/curated/en/375331580232575614/pdf/India-IN-AP-and-Telangana-Road-Sector-Project.pdf | The ICR presented a few lessons and recommendations from this operation that may benefit future similar operations. Some ofthese are noted below: Establishing forward and backward linkages to existing systems may better sustainproject outcomes. In this project, the Road Asset Management System (RAMS) and management information system (MIS)replaced the ad hoc decision making of Andhra Pradesh in prioritizing budget allocations for investment planning and roadmaintenance. The RAMS and MIS allowed the state to usea rolling, multi-year planning strategy using evidence from the reportsgenerated by the systems to justify priorities. Andhra Pradesh also established a command and control center that integrated RAMSand MIS with web- and GIS-based maps and linked other systems, such as contract administration and decision support tools for itsRoad Development Corporation (RDC) and Roads and Building Department (RBD). For example, the RDB in Andhra Pradesh used a long termperformance based management contract worth INR3,000 million (equivalent to US$42 million) for a new maintenance plan covering4,600 km of state highways. This contract was linked to the MIS system to monitor physical and financial progress. The lesson fromthis project was that the capacity of an implementing agency capacity to plan investments and budget for road maintenancemay be improved by providing forward and backward linkages to existing systems. Having a focal point for roadsafety management at the state level may be useful to achieve efficiencies.In this project, Andhra Pradeshestablished a cell inthe states transport departmenttasked with planning andmonitoring the impact of roadsafetyinitiatives, managing data for road safety indicators, and coordinating with other agencies and constituents.Thisone-stop shop for road safety measures made availablecredible data and fostered coordination. The lesson learned from thisproject was that by creating a focal point forroad and safety management, the state achieved better coordinationandefficiency in delivering relevant, credible data to end users. Ensuring fair compensation in land acquisition,resettlement, and rehabilitation avoids implementation delays. In this project, in Andhra Pradesh, by January 2014, only55 percent of land acquisition was completed, with 24 percent of project affected families receiving resettlement andrehabilitation assistance. By March 2015, a reported three year delay in payment to land owners; and payment of cash assistance tovulnerable families remained outstanding.By June 2019, after the project closed, there were reports in Andhra Pradeshofoutstanding compensations to 65 landowners, partial resettlement assistance to 363 project affected persons and additionalcompensation to 542 landowners who became landless. In Telangana, partial land acquisition compensation to 10 landowners andadditional compensation to 33 landowners who became landless remained pending. The Bifurcation Act followed by the implementationof a new Land Acquisition and Resettlement Act, also contributed to the delays in releasing compensation. In some cases, landownerslitigated even after being compensated.The lesson from this project was that by adjusting for inflation, fair compensationfor land acquisition, resettlement, and rehabilitation for project affected persons fosters confidence in the governmentsintention to be fair, avoid prolonged litigation to settle differences, andovercome implementationdelays. Continuous capacity building efforts helps new institutions. In this project, the 2014Bifurcation Act introduced a new implementing entity in the new state of Telangana to replicate the sector in Andhra Pradesh.Resources were allocated to Telangana with little support for capacity building.The unbalanced attention to building thecapacity of Telangana was evident in theunmet projecttargets. The lesson learned from this project was that when newgovernment entities areformed continuous technical assistance and training help build adequate institutionalcapacity. Appropriate data should be generated to inform adequate response to road safety issues. Inthis project, overloading was a leading cause of road accidents involving trucks. To check the overloading violations, electronicweigh bridges were proposed on the demonstration corridors. According to the task team, the two states planned and budgeted forthese weigh bridges to support their road safety programs. The lesson learned from this project was that credibledatacould be used to justify investments in infrastructure such as weigh bridges to optimize road safety.
P096023 | India Orissa State Roads Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2009 | 2016 | 2017 | ICRR | >=50 million & <100 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/303681498055210826/text/ICRR-Disclosable-P096023-06-21-2017-1498055181315.txt | http://documents.worldbank.org/curated/en/303681498055210826/pdf/ICRR-Disclosable-P096023-06-21-2017-1498055181315.pdf | The ICR included a number of lessons of which following have broad applicability: The project teamneed to ensure that all of the readiness criteria were met and project management issues were addressed before Board submission. Incases where project management issues do arise, a project management consultant should be recruited to support the ProjectImplementation Unit. Readiness criteria in procurement, safeguards and ME are as important as financial management and projectmanagement. The activities such as Land Acquisition (LA), Resettlement and Rehabilitation (RR), andimplementation of the Environmental Management Plan (EMP) should begin as early as project preparation. Contracts should not besigned if encumbrance-free road sections are not available for immediate construction works. This should be agreed with the clientahead of implementation to avoid delays during implementation. The roles and the relationship between theConstruction Supervision Consultant (CSC) and the implementing agency should be clearly defined. Red flags onproject implementation should be monitored progressively to the end. In this project, where the lead Joint Venture (JV) abscondedfrom the site and the junior partner did not have capacity to continue, the Bank team could have compelled the client to invokecontractual provision on the poor performance by the JVs.
P096056 | Second Multisectoral HIV/AIDS Control Project | Western and Central Africa | Benin | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2012 | 2014 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/954541474593686104/text/000020051-20140626115239.txt | http://documents.worldbank.org/curated/en/954541474593686104/pdf/000020051-20140626115239.pdf | The following lessons are drawn from the ICR (pp. 25-26):A thorough understanding of the dynamics of an HIV/AIDS epidemic, by population group and geographic area, is an essential prerequisite for design of effective programs and efficient investment of resources. In this case, M&E data were appropriately used to shift attention and resources toward female sex workers most at risk for contracting and spreading HIV, but attention to other high-risk groups could have been more explicitly focused and reported.Use of a separately contracted fiduciary agency to manage a subproject component can be key to successful implementation. In this case, the PIU was freed to concentrate on coordination rather than getting involved in activities for which it did not have specific expertise.Precise allocation of roles and responsibilities among coordinating and implementing agencies is crucial from the very early stages of a project. In this case, the SP/CNLS, with newly developed capacity and a vague mandate of coordination, experienced problematic â€œmission creep.â€
P096058 | West Africa Regional Biosafety | Other | Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2008 | 2014 | 2016 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/788861467999729603/text/ICRR14792-P096058-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/788861467999729603/pdf/ICRR14792-P096058-Box393191B-PUBLIC.pdf | The ICR included eleven lessons, the following two are emphasized with some adaptation of language and rearrangement: Project activities should not be dependent on the adoption of a law (especially one related to a controversial theme such as biosafety) subject to a political process not under the control of project activities. Most of the projectâ€™s outcomes were dependent on the adoption and implementation of the regional biosafety framework; since the framework was neither adopted nor implemented at the time of restructuring or project closure, these outcomes were not achieved.It is important to carefully review whether a regional approach should be used or whether another alternative would be more particable. Sufficient client demand for a regional project is fundamental to ensure effective and efficient project implementation. Also, before embarking on a comprehensive regional framework, carefully consider the policy context, regulatory regime and institutional set-up for each country and try to use their respective national biosafety regulation to inform the development of the regional framework.
P096102 | Third Poverty Reduction Strategy Credit | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2008 | 2008 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/880721475099517582/text/000020051-20140618193823.txt | http://documents.worldbank.org/curated/en/880721475099517582/pdf/000020051-20140618193823.pdf | Delays in implementation due to weak capacity and weak coordination argue for a stronger dialogue on priorities and realistic timetables.
P096105 | Rural and Private Sector Development | Western and Central Africa | Sierra Leone | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2007 | 2016 | 2017 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/297951483123028949/text/ICRR-Disclosable-P096105-12-30-2016-1483123015840.txt | http://documents.worldbank.org/curated/en/297951483123028949/pdf/ICRR-Disclosable-P096105-12-30-2016-1483123015840.pdf | 1. In an agricultural value chain project, attention needs to be given to all stages in the chain not just thepost-harvest marketing and processing end. Productivity of crop or livestock commodities in terms of both quantity andquality may need particular attention as the base of the pyramid.2. In a project with feeder road funding, inorder to ensure ownership: (i) beneficiaries should be leaders in the process of applying for local resources along with theproject support and this involvement should extend subsequently into the management and implementation of maintenance; and, (ii)local government should be closely involved alongside the beneficiaries at the outset. Respective responsibilities should beplanned and made clear.3. In a value chain project, there are likely to be difficult project designtrade-offs due to the inherent complexity of a project that addresses the majority of the constraints along the whole chain. Thesetrade-offs need to be explicitly recognized and the priority elements in the chain identified. Providing credit forfarmers may be essential to stimulate and support production and marketing yet this also adds a further layer of complexity. Inthis project, lack of finance for farmers was a constraint that might have been partly addressed through input dealer and suppliercredit or from better linkages with other sources of finance. But it should be noted that Bank learning suggests that setting upseparate project-based sources of finance outside financing institutions with the capacity to manage credit is rarely a sustainableor efficient solution.4. In a value chain project with many institutional players, both central and local, it isimportant to identify a single lead agency and to carefully set out the ground rules for how it will ensure, and create incentivesfor,coordination. It is also important to monitor coordination progress. In this case, the dual responsibility setup initially did not work because implementation arrangements simply assumed that coordination would follow from a mandatedcommittee.
P096131 | Zambia Malaria Booster Project | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2006 | 2013 | 2017 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/895801485364941507/text/ICRR-Disclosable-P096131-01-25-2017-1485364933260.txt | http://documents.worldbank.org/curated/en/895801485364941507/pdf/ICRR-Disclosable-P096131-01-25-2017-1485364933260.pdf | The project provides a number of useful lessons (ICR, pp. 44-46), and the following lessons are drawn from the ICR and adaptedby IEG:Effective use of surveillance data in a malaria program contributes to programperformanceand to positive adaptations. As malaria resurged, the project adjusted the insecticides used forspraying in 2008 in response to vector resistance. Rather than spraying in selected districts, malaria hot spots wereidentified. Residual spraying, which was previously thought to be useful only in urban areas, was found to be beneficial inmud houses in rural areas as well. Rather than considering all fever cases to be malaria, new guidelines focused on improvingdiagnosis and treatment of confirmed malaria cases.Adequate implementation of program interventionsis dependent on full understanding of their purpose and on staff motivation. The projects reliance on theteam of a separateAIDS control project to administer the small grantsprogramproduced disappointingresults.Results-based financing is inherently complex and requires a staged approach, with learningby doing and adjusting on the way. The project began with a pre-pilot in one district, followed by a larger scalepilot, which provided useful information onthe potential wider expansionof the RBF mechanism.
P096151 | Nigeria State Education Sector Project | Western and Central Africa | Nigeria | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2007 | 2012 | 2013 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/540821474636962149/text/000020051-20140625154839.txt | http://documents.worldbank.org/curated/en/540821474636962149/pdf/000020051-20140625154839.pdf | The ICR (pp. 26-28) provides lessons that can be summarized as follows:School level governance requires commitment of key local government education authorities. In this project, preparation did not involve local level government officials, and as a result they were not effectively involved during the early implementation stage. It is important to secure local government commitment early, since it is paramount for effective decentralized management. Using existing administrative agencies to implement a project builds institutional capacity and sustainability, but will be successful only if appropriate capacity building efforts are provided, as well as effective coordination mechanisms. In this project, there was a misplaced assumption that agencies would cooperate because of a common efficiency interest. It was necessary for higher level (State) interventions to persuade agencies to take advice and direction from the State Ministry of Education. This project also benefited from the deployment of qualified staff from the beginning to the project support units, which ensured sufficient capacity during implementation.
P096151 | Nigeria State Education Sector Project | Western and Central Africa | Nigeria | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2007 | 2012 | 2014 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/771741468100171314/text/860270PPAR0P090ox385188B00OUO0900NG.txt | http://documents.worldbank.org/curated/en/771741468100171314/pdf/860270PPAR0P090ox385188B00OUO0900NG.pdf | 7. Lessons 7.1 Based on the experience of this project, several lessons can be drawn\. Â· Learning and sustainability of pilot activities are limited when there is an absence of clear design, an explicit mechanism for evaluating, and a sufficient implementation time frame. Initiating the girls CCT during the last year of the project provided insufficient time to implement the pilot. As well, it is difficult to determine the benefits and effectiveness of the pilot ECD activities, given the absence of the monitoring and evaluation system and implementation plan. Without strong design and evaluation, there is no way to identify whether the pilot activity is worthy of scaling-up or sustaining. Pilots generate further interest in sustaining or scaling-up when robust data are collected. Â· Setting up a monitoring and evaluation system takes more time than Governments and TTLs often recognize and provide. An overly complex system was designed and replaced with a simplified one. In environments with low capacity, understanding the critical data needs of the Government is essential, as well as the amount of technical assistance that will be required. During this project, it took considerable time for the States to collect and analyze the Annual School Census. Â· A prior unsuccessful project can result in learning, but it depends upon an accurate understanding of the performance issue. This project avoided some of the shortcomings in the predecessor Bank project, Universal Basic Education Project. DfID's TA was aligned with the objective of this project. However, each partner worked separately to complete respective responsibilities within the project. Better coordination between the work of the Bank and DfID may have enhanced the EMIS, state and local capacity building efforts and teacher professional development. Â· Even with a State-focused project, the involvement of the Federal Ministry of Education is critical given its central role in policy. However, the difficulties related to the Federal implementation in the Universal Basic Education project were not fully understood. During preparation, instead of designing approaches to overcome the challenges experienced by the Federal Ministry of Education with the Universal Basic Education Project, the Federal role was minimal. This reduced the buy-in by the Federal Ministry of Education and likelihood of replicating project activities in other states. Â· Improving inputs into learning (facilities, textbooks, etc.) needs to be accompanied by defining and addressing quality requirements in terms of minimum standards for student learning. While this project improved the inputs and physical conditions for learning, these may not translate into improved student learning, as the key issue of teachers' capacities was insufficiently addressed by the project. When teachers' numeracy, literacy, and language skills are low, children's learning will be compromised. This is particularly true in rural areas as more skill deficiencies were found among rural teachers. There also continue to be issues in how teachers are allocated amongst schools.
P096158 | Follow Up to CRESP Phase I | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2006 | 2012 | 2017 | PPAR | >=50 million & <100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/593581509384426320/text/117156-PPAR-P067625-P067828-P096158-PUBLIC.txt | http://documents.worldbank.org/curated/en/593581509384426320/pdf/117156-PPAR-P067625-P067828-P096158-PUBLIC.pdf | 11. Lessons The main lessons that emerge from the experience of this complex project relate to the following\. Combining institutional development and investments in one package can help overcome difficult challenges\. The comprehensive design of the project integrated three components in one package\. (i) institutional development and capacity building; (ii) technology improvement; and (iii) investment activities. These three components mutually supported and reinforced one another, which was essential for the success of the project. Such a multipronged approach was needed to pursue the regulatory reforms and overcome the resistance of established interests in the sector. Neither a standalone technical assistance nor an investment project would have been so likely to achieve the necessary momentum to successful and simultaneously address the main identified challenges. Adequate time and resources for preparation and consultations should be planned and allowed\. The extensive efforts undertaken by the World Bank, beginning with a genesis workshop in 1999, through workshops, study tours and studiesâ€”supported by $1.35 million in GEF project preparation grantsâ€”during the preparation and early implementation period of the project were necessary to achieve consensus and cohesiveness about key policy directions and reforms. This early investment in partnership built trust between the World Bank team and relevant government agencies for the pursuit of key policy decisions, and the adjustment of project components needed to respond to evolving conditions, which resulted in their efficient implementation in the later years. Cost-shared grants enhance selectivity and efficiently leverage knowledge transfer, technology improvement, and counterpart funding\. The project's experience suggests that a program of costshared subgrantsâ€”where the grant provides 20â€“25 percent of total research and development costsâ€”can be a cost-effective tool for the improvement of technology. Such an approach leverages the value of the grant with substantially greater investments by the implementing counterparts, building ownership and commitment. The substantial counterpart funding requirement also enhances selectivity, which contributed to the mostly successful outcomes of these subgrants. A long-term, predictable price signal can provide an effective stimulus for continuing investments in renewable energies. The NEA's issuance of a multiyear national tariff for wind and other renewable energies replaced a previous system whereby the feed-in tariff had been approved for each specific project based on the lowest-cost bids. This had been much riskier for investors because of the frequent technical performance problems with the cheapest-cost equipment. The establishment of long-term, predictable, and financially attractive price signal, as recommended by project-supported studies, provided an effective stimulus for continuing and expanding investments in renewable energy.
P096174 | National Program Support for Environment and Natural Resources Management Project | East Asia and Pacific | Philippines | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2007 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/235361475112724391/text/000020051-20150113005135.txt | http://documents.worldbank.org/curated/en/235361475112724391/pdf/000020051-20150113005135.pdf | Some of the main lessons identified by the ICR, with some reformulation of language are as follows: Â· A Sector Investment and Maintenance Loan (SIM) is appropriate only when the client agency is fully committed and operationally prepared to implement and mainstream reforms during the project period. When this commitment is lacking during the early years of a project, implementation will become more difficult than for a Specific Investment Loan (SIL) that focuses on discreet interventions, or a Development Policy Loan (DPL) that focuses on policy reforms including conditions/triggers. When agencies do not show readiness to undertake far reaching reforms, more focused SIL-type projects would appear to be more appropriate.Â· Project Implementation Units can serve an important function when institutional capacity is weak, but should lead to strengthening of existing institutional arrangements. As institutional capacity develops, such units may stifle development of capacity A management committee composed of relatively senior representatives of relevant government entities should take increased responsibility for overseeing project/ program implementation and individual bureaus/implementing units need to be more proactively engaged in implementation in line with their institutional responsibilities. Â· The Bank should enter the reform picture when reforms are already well entrenched among key client entities, especially among the managers. Thus, until there are clear operational manifestations of these reforms in the concerned agencies, the Bank should focus its involvement on helping establish a solid foundation for reform. This could be undertaken through focused SILs and TAs to pilot innovations and build capacities and building awareness and constituency for the reforms.
P096181 | Energy Sector Cleanup and Land Reclamation Project | Europe and Central Asia | Kosovo | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2006 | 2017 | 2017 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/197711498763965249/text/ICRR-Disclosable-P096181-06-29-2017-1498763955076.txt | http://documents.worldbank.org/curated/en/197711498763965249/pdf/ICRR-Disclosable-P096181-06-29-2017-1498763955076.pdf | The ICR presents 5 lessons, but the two most important and relevant to other Bank operations, with some adjustment oflanguage,are the following:1. Client ownership andfull client commitment andengagementfrom the outsetin Project design enhances effectiveness, efficiency and sustainability. In this case, theKEKs strong ownership of the Project was demonstrated with the provision of significant funding to cover the financing gapto remediate ash dumps using a technological approach not envisaged at appraisal. If such fundinghad not been provided by theClient, the Project would probably have failed to meet its objectives. Also in this case, embedded mechanisms of mainstreaming ofthe remediation operations in the design, led, in turn,to strengthening institutional development and capacity. As a result,the KEK, while implementing the Project, established a new Reclamation Department, which was engaged in all remediation operationsand now is capable tosustain clean-up operations on its own.2. Highly technical projects, such asclean-up and reclamation operations, require intensive investigations as part of project preparation and design. Theseinvestigations demand significant time and resources to generate the design with specific required inputs and activitiesidentified. In cases of limited time and resources for preparation, and wherean optimal remediation strategy cannot beconclusively determined at appraisal, the Project Development Objective needs to be crafted for flexibility to allow alternativetechnical solutions.
P096198 | Multi-Sector Demographic Project | Western and Central Africa | Niger | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2007 | 2013 | 2014 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/933131474487930226/text/000020051-20140626121923.txt | http://documents.worldbank.org/curated/en/933131474487930226/pdf/000020051-20140626121923.pdf | These lessons are drawn from the ICR (pp. 24-25): Evaluator observations are included in bullet points two and three. Bullet point 4 is introduced by the evaluator and the panel reviewer.Addressing the population agenda needs to be anchored in the highest level of government. A multi-sectoral population agenda cannot be the sole responsibility of a single sector ministry. Rather, it should be managed through a high-level representative multi-sectoral body or through an entity such as a Prime Ministerâ€™s office.While there are no data to confirm it, the ICR notes that IEC/BCC campaigns may be more successful in raising awareness when they are linked to womenâ€™s empowerment programs that engage women more directly in transmitting behavioral change messages. Empowerment programs raise social status and may create economic opportunities, strengthening the demonstration effect that empowered women have on their surroundings To be effective, IEC/BCC design and implementation need to take into account local culture, needs, and issues, and follow-up and M&E structured to detect locally sensitive issues. In this project, a particular effort was made to tailor messages to Islamic sensibilities on raising the age of marriage for girls and boys, and on girlsâ€™ schooling. Again, there are no data to measure the impact of such culturally sensitive messages.There can be considerable value in drawing on outside data sources for setting baselines, developing milestones, and measuring outcomes, as a complement to information that is being collected under the project. This project was framed by demographic and health surveys that provided baseline data and data for 2012, towards the closing of the project. Neither appears to have been directly generated by the project intervention.
P096198 | Multi-Sector Demographic Project | Western and Central Africa | Niger | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2007 | 2013 | 2016 | PPAR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/769441469178140384/text/106254-PPAR-P157357-Box396280B-PUBLIC-disclosed-7-18-16-ppar-niger-0716.txt | http://documents.worldbank.org/curated/en/769441469178140384/pdf/106254-PPAR-P157357-Box396280B-PUBLIC-disclosed-7-18-16-ppar-niger-0716.pdf | 4. Lessons 4.1 Looking across these two very complex projects, three lessons emerge that are relevant to both. Box 4-1. Basic Attributes of the Sectorwide Approach in Health A sectorwide approach to health development is\. A sustained partnership, led by national authorities, involving different representatives of government, groups in civil society, and one or more donor agencies; With the goal of achieving improvements in people's health and contributing to national human development objectives; In the context of a coherent sector, defined by an appropriate institutional structure and national financing program; Through a collaborative program of work (PoW) focusing on\. The development of sectoral policies and strategies, which define the roles of the public and private sectors in relation to the financing and provision of services, and provide a basis for prioritizing public expenditures; The preparation of medium-term projections of resource availability and sector financing and spending plans, consistent with a sound public expenditure framework; The establishment of management systems by national government and donor agencies, which will facilitate the introduction of common arrangements for the disbursement and accounting of funds, procurement of goods and services, and monitoring of sector performance, and Institutional reform and capacity building in line with sectoral policy and the need for systems development; With established structures and processes for negotiating strategic and management issues, and reviewing sectoral performance against jointly agreed milestones and targets. Source\. Cassels 1997. 4.2 The potential of SWAPs (and Program-wide support) to strengthen capacity is not likely to be achieved in the absence of\. clearly laid out capacity-strengthening objectives, intermediate objectives, a plausible results chain, relevant performance indicators, and proactive M&E. ISHSSP did support a capacity building component, but it did not articulate capacity-building objectives as part of its PDO; nor did it include indicators to track progress, and its capacity building results chain was both complex and weak. The overarching objective of the Multi-Sector Demographic project focused squarely on strengthening Niger's capacity to address its demographic challenges. Although it did include an intermediate objective (to enable MoP to design and implement a nationwide multisector population program) and indicators (AWPs adopted and implemented; and M&E system in place and in use), it fell short of developing a coherent results chain and of capturing and measuring the extremely ambitious goals\. of establishing a new, multisector population program for which there was less than total buy-in in the country and of ensuring its coordination, financing, monitoring, and evaluation by a new, weak ministry, which had no real authority over other more senior and well-established ministries. The anticipated capacity benefits of the SWAP (or Programwide approach), suggested in an IEG study of health SWAPs (improved sector coordination; greater harmonization and alignment of development assistance; and enhanced sector stewardship) and related indicators (itemized in that report) may provide guidance for better definition and measurement. These objectives and indicators were derived from the original definition of a Health SWAP, which is still relevant today and helpful in sorting out both capacity needed and themes for capacity strengthening (Box 4-1). 4.3 The evaluation of these two projects corroborates IEG's findings that the success (or failure) of a SWAP (or Program wide approach) depends upon four critical factors\. (1) the quality and relevance of strategies and AWPs; (2) country capacity and systems for financial management, procurement, and strategic management; (3) the quality and functionality of partnerships with national and international actors and stakeholders; and (4) the predictability and flow of funds and absorptive capacities of implementing agencies Â· Improved quality and relevance of strategies and plans for health and population might have contributed to the support of fewer, more relevant activities and a higher impact. For health both the five-year plan and AWPs exceeded the available capacity and financing to implement them. Annual plans were only implemented at an average rate of 50â€“60 percent and it is not clear whether, or to what extent, they were sufficiently prioritized to address program objectives, including quality. Likewise, it is not clear to what extent the multisector population AWPs were sufficiently strategic and prioritized to address the highest-impact interventions or aligned with available capacity and resources. The results orientation of these plans was mixed. Â· Had the strength of the Bank's fiduciary capacity-building support been also applied to building the capacity for strategic management, including M&E, the allocation of resources might have been better aligned with the highest-impact interventions and the results focus might have been stronger. The Bank was largely effective in assessing and addressing country capacities and systems to respond to fiduciary policies and standards for the two projects. Both design and supervision of fiduciary capacities and systems were thorough and well-resourced, with frequent visits and oversight of Bank technical expertise and guidelines. In contrast, Bank expertise, technical supervision, and guidelines for strategic sector management (including the whole cycle of policy formulation and policy dialogue, planning, programming, budgeting, andâ€”especiallyâ€”M&E design, implementation, and use) is weak. This weakness undermines the ability for overall managementâ€”linking resources to resultsâ€”and for establishing and enforcing accountabilities for results. Â· Stepped-up efforts to infuse biannual reviews with policy dialogue and to hold partners accountable for supporting national priorities may have improved both the quality of partnerships and their outcomes. Enhanced partnerships with national actors and stakeholders might have been instrumental in better understanding and addressing pockets of resistance to population activities. For health, partnerships with donors might have been improved through the biannual review meetings. But the support of many development partners is still driven by their HQ and global initiatives, and designed as parallel projects, with multiple reporting requirements and management procedures, which put a strain on limited capacity and on national 42 efforts to allocate all resources available to the sector in line with national priorities. Joint review meetings are reported to focus more on plan implementation and review with, inadequate time devoted to substantive and policy dialogue and the assessment of results. For population, partnership among national actors and stakeholders has been undermined by\. the inadequate convening authority of the MoP; and persistently significant pockets of resistance. The failure to ratify the National Population Policy was a missed opportunity for needed national-level dialogue and leadership. The ICR reports that MoP was resistant to contracting NGOs to undertake critical outreach work. Â· Inadequate predictability and flow of funds risks undermining absorptive capacity and efficient use of resources. A long and tedious process by the Bank and AFD for reviewing annual health action plans (to assess their eligibility for financing and ultimately to approve them for disbursement under the Common Fund) caused these plans to be financed several months after the start of the year. This compression of the implementation period precipitated a low (50â€“60 percent) implementation rate and intensive end-of-year spending that is unlikely to have been efficient. 4.4 Beneficiaries are unlikely to take full advantage of information and services offered by social sector programs if their situations, perspectives, needs, and priorities are not documented and factored more systematically into program design, monitoring, and evaluation. This involves (a) both quantitative and qualitative information and trends; and (b) a segmentation of information to capture inequities and vulnerable groups the projects were designed to address. Qualitative information that might have provided value added includes\. baseline, midterm and end-of-project surveys on service quality and affordability (for health services); and baseline, midterm and end-of-project surveys on knowledge, attitudes, and behaviors of various groups on population issues, fertility regulation, and various underlying determinants for tailoring and fine-tuning messages and other interventions. For projects aimed at poor and vulnerable populations, the breakdown of trends by urban or rural residence and by income quintile is critical for fine-tuning interventions during implementation and for end-of-project efficacy assessment.
P096200 | Land Registration | Europe and Central Asia | Bosnia and Herzegovina | IBRD | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2006 | 2012 | 2014 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/193011474633606461/text/000020051-20140625235817.txt | http://documents.worldbank.org/curated/en/193011474633606461/pdf/000020051-20140625235817.pdf | The following lessons are adapted from the ICR:In ECA countries, facilitation of emerging real property markets requires efficient registration systems to be quickly established so that (sporadic, on-demand) registration can keep pace with the rising number of transactions.It may be advisable for projects to take an incremental approach to upgrading information technology rather than financing a large development contract to introduce sophisticated real property registration systems, which may take years to prepare and implement and are not guaranteed to work.Where land registration responsibilities are divided between central, municipal and local governments (the case for that half of Bosnia and Herzegovina governed by the Federation), the coordination of information and the sustainability of financing may be harder to achieve compared to administrations (like the Republic, which controls the other half of the country) where services are fully integrated. In addition, IEG derives the following lesson:To minimize costs and increase the credibility of land administration services, a case can be made for strengthening sporadic adjudication by giving first priority to customers wishing to register property. Rather than striving to perfect and harmonize cadastral and registry data in a limited area (systematic adjudication), in certain countries it makes sense to work with the existing (incomplete) cadastral data, allowing for piecemeal improvements to be made in line with customer demand (and willingness to pay). In other countries where people are poorly informed about land rights and where the poor cannot afford land administration services, systematic adjudication may be more appropriate.
P096205 | Development Policy Loan (DPL) | Europe and Central Asia | Albania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2008 | 2011 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/409661474488788153/text/000020051-20140624201433.txt | http://documents.worldbank.org/curated/en/409661474488788153/pdf/000020051-20140624201433.pdf | The experience of the DPO1 indicates that for governments committed to improving economic policy the size of the loan may be of secondary importance, as their main objective is to signal the direction of policy to the private sector, government agencies, and development partners.The DPO teaches that programs with a small number of conditions and focused and achievable objectives are more likely to succeed than â€œcatch-allâ€ operations with broad objectives and large number of conditions (like the previous PRSCs). It also shows that such design lends itself to having a results framework that makes it easier to manage and assess the program. The experience with this program design also shows the wisdom of leaving sectors with difficult problems (e.g., electricity) out of the program and dealing with them in sector specific operations that permit testing the authoritiesâ€™ commitment to deal with them.
P096207 | Power Transmission Project in Support of the Energy Sector Reform & Development Program | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2008 | 2016 | 2018 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/958131506716496625/text/ICRR-Disclosable-P096207-09-29-2017-1506716483541.txt | http://documents.worldbank.org/curated/en/958131506716496625/pdf/ICRR-Disclosable-P096207-09-29-2017-1506716483541.pdf | The ICR presents nine lessons of which IEG selects three as most important. Combining anambitious sector reform program with significant investment activities in a fragile political economy carries high risks. In thesecircumstances a single focus infrastructure project may be the most efficacious choice. This risk is higher in countrieswhere the borrower has a low track record of sector reforms. One of the objectives of this project was to support the GoU toachieve the opening up of the electricity market. This was a rather ambitious objective for a project which primarily aimed atrehabilitating a part of the aging transmission system. As a result of political instability and frequent government changes,GoUs commitment to the sector reform decreased during the course of the project and both the implementation of the Grid Codeand the WEM concept could not be achieved.The experience level of the procurement/projectmanagement consultant is crucial for a successful start and implementation of the project. In this project, the selectionof the consultant company was slow and the company lacked sufficient experience in managing procurement in line with theBanks rules. This led to delay in concluding contracts which consequently resulted in a longer project completionperiod.On-the-job training is crucial in improving the implementing agencys capacity tocomply with the World Bank procurement and financial management standards and procedures. The World Bank worked closelywith UE to assist in handling procurement and FM, which resulted in the upgrade of the projects ratings in procurement andFM to Satisfactory and maintaining those ratings until the closing date. The support has also created a solid foundation for theimplementation of the follow-on project, the Second Power Transmission Project.
P096213 | NATIONAL WATER SUPPLY & SANITATION | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2007 | 2017 | 2019 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/458681539703942993/text/Azerbaijan-NATL-WATER-SUPPLY-SAN.txt | http://documents.worldbank.org/curated/en/458681539703942993/pdf/Azerbaijan-NATL-WATER-SUPPLY-SAN.pdf | The following three lessons were derived from the ICR:1. Efficient projectdesign is critical to a projects success. For example, this project was affected by a poorly designed resultsframework and inadequate feasibility study. As a result, the project was unable to deliver on the original scope of work and itbecame necessary to radically decrease its targets. Improved project readiness would have helped avoid unforeseen lags andcostly implementation support (ICR, 121).2. When designing water supply andsanitation projects, remember that massive construction of utilities does not translate to sustainable services. Forexample, while one rayon center was built and is operational, it is currently not operating at capacity, with less than half ofresidents connected to the sewer system (ICR, para. 120). Therefore, future water projects need to be designed taking into accountthe barriers that prevent citizens from shifting away from their septic tanks towards connecting into utility services. Thisis crucial if the Bank also advocates for increasing tariffs to ensure financial sustainability of services (ICR, para.122).3. A turn-key design and build contracts for the Wastewater Treatment Plantsproved to be the right choice when expected frequent modification to the original design. For example, the designmodifications did not affect the original employer requirements and the contacts could be modified within the original lump-sumprice (ICR, para. 124).
P096214 | ROAD MAINTENANCE & REHAB 3 | Europe and Central Asia | Poland | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2006 | 2012 | 2014 | ICRR | >=100 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/580381474555154486/text/000020051-20140625184559.txt | http://documents.worldbank.org/curated/en/580381474555154486/pdf/000020051-20140625184559.pdf | A combination of the key lessons learnt based on the ICR and on IEG's review are summarized below:ii. The use of country systems, combined with adequate ex-post audits can contribute to fast disbursement of quality works. The Sector Wide Approach adopted for the implementation of civil works using the borrowerâ€™s own systems worked well in a country where there is already a functioning system. Fiduciary and safeguards oversight can be based on ex-post audits of the efficacy of internal controls. Quality control based on third party technical audits also proved adequate and efficient.ii. Objectives are more likely to be achieved when they have comprehensive monitoring indicators. While proper indicators were set for most objectives, there were no indicators linked to the objective of achieving financial viability. This may have contributed to the programâ€™s failure to achieve progress on this sub-objective.iii. It is crucial to take into account the budget constraints when using HDM-4 analysis in order to complete the rehabilitation program within a finite number of years. Using HDM-4 to analyze only the rates of return on rehabilitation projects ignores the financial viability of the program, and this does not eliminate the maintenance backlog. The rehabilitation program should be designed to deliver a maintainable network within a reasonable time frame, and this requires taking into consideration a realistic budget envelope over the program period.iv. It is important to ensure that sufficient disbursement leverage is retained to ensure the satisfactory implementation of the institutional development components, as well as a realistic time-frame for the operation. This was the third project and the disbursements were fast but the Bank experienced difficulty leveraging over the policy actions and institutional development programs which took longer to mature.
P096214 | ROAD MAINTENANCE & REHAB 3 | Europe and Central Asia | Poland | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2006 | 2012 | 2014 | PPAR | >=100 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/756861468093565458/text/832510PPAR0P07040Box382077B00OUO090.txt | http://documents.worldbank.org/curated/en/756861468093565458/pdf/832510PPAR0P07040Box382077B00OUO090.pdf | 5. Lessons 5.1 The assessment of three consecutive projects supporting Poland's road maintenance and rehabilitation projects have found that when planning sequential operations that involve sector reforms, it is important to ensure that sufficient disbursement leverage is retained to ensure the satisfactory implementation of the institutional development components, as well as a realistic time-frame for the operation. In retrospect, a critical issue raised by the experience of Poland's Road Maintenance and Rehabilitation Program is the appropriateness of a strategy of funding fast disbursing physical works, coupled with an institutional development program which required a much longer period for implementation. A majority of the funding for physical works, which constituted about 90 percent of the loan amounts, had been disbursed in the first three years of the program, 2004 through 2006. When subsequent issues arose, most particularly with respect to maintenance funding and the availability of the National Road Fund for maintenance and rehabilitation of the network, the Bank did not have effective recourse to the usual remedies of suspension of loan disbursements. While principled persuasion is always possible, the added leverage of withholding funding is often needed to get the attention of senior policy makers. 5.2 The second lesson relates to the use of country systems which worked when combined with adequate ex-post audits, as it contributed to fast disbursement of quality works. The Sector Wide Approach adopted for the implementation of civil works using the borrower's own systems worked well in a country where there is already a functioning system. Rehabilitation works using country systems for small contracts (each worth less than EUR 6 million) led to a cost effective program with high rates of return. Fiduciary and safeguards oversight can be based on ex-post audits of the efficacy of internal controls. Quality control based on third party technical audits also proved adequate and efficient. This modality for implementation is not used often in Bank projects, and the experience here suggests that for future Bank funded operations, upfront assessment should be made systematically to see whether the country systems can be used. Packaging of the works into smaller contracts also appears to have benefitted the local construction industry and allowed faster implementation of the rehabilitation program. 5.3 The third lesson regards the use of HDM-4 to ensure the efficiency of the rehabilitation program. While it is important to ensure that individual rehabilitation projects have an adequate ERR, it is also important to clear the maintenance backlog in a reasonable period of time within available budgets. This requires that maintenance budget constraints be factored into the choice of maintenance interventions. The roads in poor condition at the start of the program in 2003 totaled about 30 percent of the national roads network. In 2011, there were still about18 percent of the network in poor condition. This means the program over a 8 year period had not managed to eliminate the maintenance backlog of roads in poor condition. This failure relates principally to the shortfalls in maintenance budgets, and could probably have been avoided if the HDM-4 analysis had considered the budget constraints and chosen rehabilitation alternatives that fitted within the budget envelope. 5.4 Finally, it is important that all objectives set for the program be reflected in the monitoring indicators for the program. Absent this the objective is unlikely to receive the attention needed. The absence of clearly monitorable indicators for maintenance funding may have contributed to the inadequate attention given to establishing a stable and reliable source of funding for maintenance of the national roads network. Road safety, on the other hand, was identified as a critical issue for the country to address at project design stage, and consequently components and monitoring indicators were included but lacked a specific objective in the first two projects. While the third project explicitly included a road safety objective, the related indicators were under ambitious compared to the country's overall goal.
P096234 | Iraq Third Emergency Education Project | Middle East and North Africa | Iraq | IBRD | FCS | Human Development | Education | IDA | IPF | 2006 | 2014 | 2015 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/968831475118218157/text/000020051-20150312114517.txt | http://documents.worldbank.org/curated/en/968831475118218157/pdf/000020051-20150312114517.pdf | Lessons drawn from the ICR (pages 33-34):In a conflict-affected country where the Bank has limited, or no, access on the ground, an external contractor can help to mitigate some financial risk but should not be considered a substitute for full Bank implementation support. In the case of this project, the fiduciary monitoring agent was useful for monitoring physical progress and verifying appropriate use of funds; however, it could not provide the technical expertise necessary to ensure full development impact.For reform efforts that require significant international technical assistance (and not available in-country), project preparation would need to include an assessment of the availability and quality of such technical assistance. In the case of this project, the efforts to train teachers and modernize the curriculum had significant shortcomings due to lack of available and experienced international firms.Lessons drawn by IEG:In a conflict-affected country with low capacity, a functional M&E system can be implemented, through a simple design and M&E capacity building efforts. In the case of this project, the Bank team made targeted efforts to explain the concept and importance of M&E and assisted the borrower in tracking and reporting on key project outputs.
P096248 | Community-based Settlement Reconstruction and Rehabilitation Project for NAD and NIAS | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2006 | 2010 | 2012 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/870521475081767794/text/000020051-20140624203721.txt | http://documents.worldbank.org/curated/en/870521475081767794/pdf/000020051-20140624203721.pdf | The main lessons adapted from the ICR are:The quality of facilitators is one of the main drivers of community based implementation quality. The project experience showed that many of the implementation issues could have been avoided if more funds and attention were given for facilitatorsâ€™ capacity building.The project demonstrated that "on-budget" financing i.e. channeling project funds through the Governmentâ€™s regular budgeting system rather than foreign-financed disaster relief builds commitment at the various levels of Government and creates capacity within to prepare and implement similar projects. Implementation delays can, however, result from slow budget release.
P096262 | Avian Influenza & Human Pandemic Preparedness & Response APL 2 Project | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2006 | 2012 | 2014 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/899751475092886398/text/000020051-20140625230131.txt | http://documents.worldbank.org/curated/en/899751475092886398/pdf/000020051-20140625230131.pdf | The ICR reports a number of lessons, including:It can be difficult to implement complex multi-sector and multi-donor projects and capacity building in the limited timeline of an emergency operation. In this project, coordination caused delays, and extensions were needed in order to complete project activities.When designing emergency interventions, a focus broader than the specific needs of the emergency can provide flexibility that may be useful once the urgent needs have been met. In this project, the objectives could have been more relevant if they had included zoonotic diseases other than avian influenza.Costly and complex infrastructure investments need to be properly assessed before undertaking the investment. In this case, the project design was changed during implementation to add an additional BSL 3 laboratory without adequate analysis.Monitoring and evaluation can be more complicated in multi-sectoral projects, and will be more effective if there is a single overall unit managing M&E or if every unit has their own dedicated M&E expert.
P096263 | Land Administration and Management Project (LAMP) | Europe and Central Asia | Albania | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2007 | 2014 | 2015 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/687691467986335758/text/ICRR14777-P096263-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/687691467986335758/pdf/ICRR14777-P096263-Box393191B-PUBLIC.pdf | Multi-sector projects are difficult to manage, particularly when there are several implementing agencies, each of limited capacity. Projects are more likely to succeed when the Bank has a thorough understanding of political and institutional obstacles in the client country and is realistic in framing reform objectives. The Bank's quality assurance process has an important role to play in ensuring that the findings of analytic work and a proper understanding of political economy are thoroughly reflected in project design.Although the Bank can influence the pace and the quality of implementation, there is a limited extent to which intensive Bank supervision can make up for implementing agencies' lack of contract management skills.
P096285 | Micro and Small Enterprise Finance Project | East Asia and Pacific | China | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2007 | 2011 | 2012 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/853181475099686850/text/000020051-20140625080601.txt | http://documents.worldbank.org/curated/en/853181475099686850/pdf/000020051-20140625080601.pdf | The ICR is candid, clearly written, and analyzes the project well. In preparation to writing the ICR field visits were made to the 6 participating financial institutions and the ICR Annex included write-up on two of the banks and a credit cooperative. IEG concurs with the ICR lesson that the success of financial intermediary loans, particularly involving institutional changes, can be supported by providing the institutions with access to technical assistance. A third obvious lesson, raised in the ICR, is that external factors can affect projects. Negative macroeconomic developments may be a potential problem that needs to be highlighted in the risk section of the PAD and actions taken in the loan to ease the problem. Government actions, such as commercializing the CDB, can also affect project outcomes, as occurred in the case of this loan. Loan preparation needs to closely follow the likely developments in the financial intermediary loan counterpart institutions.
P096302 | Sustainable Management of Mineral Resources | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2009 | 2019 | 2021 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/573861597066501685/text/Tanzania-TZ-Sustainable-Mgt-of-Min-Resources-TAL.txt | http://documents.worldbank.org/curated/en/573861597066501685/pdf/Tanzania-TZ-Sustainable-Mgt-of-Min-Resources-TAL.pdf | The ICR provided lessons mainly on the political environment and ASM reforms. This review summarized the two important lessonsin the ICR and drew a third lesson.1. Responding and incorporating politicaluncertaintiesA project involving sectoral reforms needs to take into account a sudden reversal of policy.Political reversals can cause unforeseen political, institutional, or sectoral changes with direct or indirect implications thataffect the proper implementation. During the project, the split of the Ministry of Minerals and Ministry of Energy necessitated theestablishment of a new Ministerial Tender Board, which took almost five months and caused a delay in the implementation of theproject. The project was responsive to the political changes in two ways. The project provided additional training and a refreshercourse for the new PMU staff to better understand Banks procedures. The Bank team closely reviewed and analyzed thepolitical implications of the project. These reviews were conducive to guiding the projects adaptation to politicaluncertainties.2. Holistic approach to reform small-scale miningThe project took acomprehensive approach to enable reforms for small-scale miners, which were mainly characterized by three interventions. One was tostrengthen the legal and regulatory framework. The mining legislation strengthened the socio-economic benefits of mining andreduced adverse social and environmental impacts. The second was to provide small-scale miners with financial incentives andtechnical assistance. Loans or small grants were provided to miners, and decentralized licensing and geological information led toa rise of legalization and registration of small-scale miners. The third was to establish the center of excellence, which providedcomprehensive support for small-scale miners. The center enabled miners to establish formal small-scale and medium-scale miningbusinesses. Interventions to small-scale miners are often politically sensitive and potentially adversely impacted. Themulti-approach covering the legal framework to ground-level support would reduce the risks of political adversaries and enable thesuccessful reform of small-scale mining in such a volatile circumstance.3. Establishingoperationally feasible theory of change and results frameworkThe lack of an effective theory of change andcorresponding results framework hinders the proper assessment of the project. Although the project implemented a wide array ofactivities (four components and 13 subcomponents), the causal chains were not fully recorded in the results framework. Theinadequate results framework stems from the less structured theory of change at the design stage. Since the theory of change wasnot articulated adequately, the project was not clear about which activity was linked to what results and for which outcome. Thetheory of change needs to correspond with the results framework in order to provide a sufficient basis tor understanding andmeasuring the projects achievements.
P096323 | Tana & Beles Integrated Water Resources Development | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2008 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/399451512426482109/text/ICRR-Disclosable-P096323-12-04-2017-1512426464049.txt | http://documents.worldbank.org/curated/en/399451512426482109/pdf/ICRR-Disclosable-P096323-12-04-2017-1512426464049.pdf | Â The ICR providedseveral lessons. TheÂ most importantÂ follow with some modification oflanguage:Â Implementation capacity challenges need to be addressed up front during the projectdesign period especially for multi-sectoral projects with multi-stakeholdersThe project was expected to delivermultiple outputs and outcomes engaging several implementation institutions that were not sufficiently developed andcapacitated.Project experience showed that project scope as well as project time frame should be examined carefullyand potential institutional capacity gaps should be addressed in advance before engaging in other development/investmentactivities.Â Integrating livelihood development activities within natural resources managementmay foster positive incentives to the communities to be fully engaged and promote sustainable watershedmanagement.Linking farmland treatment with animal forage development, degraded landtreatment and area closurewith bee keeping and animal fattening, gully treatment with forage, and fruit and tree development have simultaneously promoted thecommunity livelihood and reduced watershed degradation.Â Post-project transition arrangementsare critical for sustainability of project outcomes. Particular issues that need to be addressed include retaining theskilled capacity or staff; the exit strategy for financiers ,and direct government support that enabled active participation of thecommunity and implementing partners at the local level.
P096328 | Rural Education and Development (READ) Project (formerly Rural Education Support Project) | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2006 | 2013 | 2014 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/596341474633249037/text/000020051-20140626120659.txt | http://documents.worldbank.org/curated/en/596341474633249037/pdf/000020051-20140626120659.pdf | The ICR (pp. 19-20) notes three generic lessons:Simple innovative designs that focus on quality, when administered well, can have substantial impact. Focus on project implementation during preparation can have a highly positive impact on the quick start-up of project implementation.There should be early agreement with Single Source providers that they will be required to use Bank standard bidding documents.IEG notes that there is also a lesson to be learned in the timing of baseline and impact evaluation surveys, which in this case were conducted too early in the project cycle to assess the impact of project-financed interventions. It takes time for teaching and learning processes to change and for the impact of these changes to become measurable through surveys. It is also noted that enthusiasm on the part of project participants is not necessarily representative of the amount of sustainable change that takes place as the result of project activities. Comments from the Borrower (ICR, p. 47) include helpful lessons learned on the teacher training activities, including:Piloting training and other activities, with subsequent changes to adapt materials to local needs, is important to ensure project success.It is important to ensure good communication among teachers working in a changing environment. In this project, communication was difficult to due the lack of an effective communication network. Similarly, some schools could not be adequately monitored due to their distance away from urban areas and traveling conditions.
P096332 | ProMaputo, Maputo Municipal Development Program | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2012 | 2013 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/236821474502981118/text/000020051-20140625155147.txt | http://documents.worldbank.org/curated/en/236821474502981118/pdf/000020051-20140625155147.pdf | The ICR has identified a number of lessons and the most important ones are listed below:Mainstreaming project management helps to build and sustain capacity of government entities. Although relying on a weak government entity with no previous experience in executing a Bank- financed project can be risky, it also powerfully assists in building sustainable capacity of the entity through learning by doing.Building effective institutions requires a long-term commitment. Organizational change is a slow and difficult process that often stalls due to resistance of those who fear they may be made worse off due to the changes or due simply to inertia. Convincing people that change is in their interests requires solid analysis, considerable consultation and willingness to address concerns, investments to upgrade skills of existing staff to give them a place in the new organization, and determined leadership.Combining institutional strengthening with improved delivery of services. Combining institutional reforms with service delivery helps in building the capacity of the implementing agency to carry out its mandate through learning by doing. It also helps to facilitate engagement with the citizens who are benefiting from the improved services.Design of financial management information systems must be appropriate for the institutional context to succeed. Both governments and external advisors often propose the most modern system for managing financial and other information. However, such systems often do not function where organizational, technical, and human capacity is weak.
P096332 | ProMaputo, Maputo Municipal Development Program | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2012 | 2020 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/777631588168466281/text/Mozambique-ProMaputo-Maputo-Municipal-Development-Program-MMDP-I-and-II.txt | http://documents.worldbank.org/curated/en/777631588168466281/pdf/Mozambique-ProMaputo-Maputo-Municipal-Development-Program-MMDP-I-and-II.pdf | 3. Lessons 3.1 In low-capacity settings, where cities are barely able to meet service delivery needs, it may be necessary to deliver critical services while incrementally building municipal capacity for sustained service delivery over time. The World Bank's approach in Maputo was appropriately sequenced to support strengthening the capacity of the CCM, especially by helping it to increase tax collection and revenue raising potential. It also helped deliver critical services that simultaneously improved the well-being of the city's citizens, providing opportunities for learning by doing. 3.2 Interventions in land administration require a thorough analysis of the local, institutional, and political economy conditions. Rapid urbanization often requires immediate action, even in contexts of low capacity, poor governance, and dysfunctional land markets. However, given the high risk, a deeper understanding of ways to navigate the complex environment could help shape the interventions, with adequate tools and mitigation measures to achieve sustainable reforms. 3.3 Excessive reliance on external expertise can undermine knowledge transfer and ultimately sustainability in municipal development projects. The World Bank's support to the CCM is instructive\. attempts to mainstream implementation within the structure of CCM in the first phase led to contractual oversight challenges and implementation delays. These delays prompted a switch to a dedicated program management unit in the second phase that relied heavily on international consultants. Although the switch improved project implementation, the hiring of and excessive reliance on external technical consultants, remunerated at a much higher rate than local staff, and the urgent need for the external consultants to focus first on service delivery created tension between the local and international staff. This situation resulted in a lack of knowledge transfer between the two groups. When selecting an approach, good project oversight must be balanced with long-term sustainability by ensuring that adequate capacity is transferred to local staff. 3.4 Achieving outcomes in solid waste management in low-capacity contexts requires a viable financial plan and mechanisms for capital and recurrent expenditures which may include contributions from national and local governments, private partnerships, and user fees. As the World Bank's investments in Maputo show, such a financial plan requires a certain level of public sector support to deliver basic services and to manage and supervise private sector contracts. Also, in such contexts, it is unlikely that the local private sector can fill all service delivery gaps. The project demonstrates that in such contexts, where service delivery needs to be rolled out incrementally, it is unrealistic to expect full cost recovery from the sector's own fees and resources. Rather, a viable financial plan for sustained service delivery requires mechanisms that involve multiple actors (providers and users) across the solid waste management value chain. 3.5 Although achieving universal access to solid waste management is a significant achievement in low-capacity contexts, outcomes are undermined if investment in waste disposal is insufficient, especially for the most vulnerable. The World Bank's support for solid waste management in Maputo lacked a value chain approach\. universal access was achieved but the plan (outside of project financing) to build a sanitary landfill to ensure safe disposal was not achieved. Because the existing dump site in Maputo was already at maximum capacity, this plan was a vital part of the city vision to promote human welfare by improving the solid waste management sector. Waste disposal currently poses significant health and environmental risks to city residents. Risks are also associated with the health problems experienced by the trash-picking community at the site and with the need for alternative livelihoods as part of a resettlement package. A modern sanitary landfill could also contribute to cost recovery by lowering operation and maintenance costs and by producing revenue from biogas generation. 3.6 Land use transformation brought about by infrastructure investments can contribute positively to the local tax base, but it can also negatively affect poorer residents when land and housing prices rise. As shown by the World Bank's support for infrastructure investments in Maputo, land use change (such as that resulting from road and drainage improvements) can stimulate private investment in housing and business development. If systems are in place, new formal housing units can be entered into the land registry and cadastre, and increased property tax collection can strengthen capacity for sustained service delivery. Likewise, business development can have multiplier effects on local job creation and growth. At the same time, an unmanaged process can quickly drive up housing and land prices in a way that forces poorer residents to migrate far from their places of employment or even to unsafe living areas (such as slums).
P096336 | Second National Water Development Project | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2007 | 2016 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/263221492695508325/text/ICRR-Disclosable-P096336-04-20-2017-1492696409752.txt | http://documents.worldbank.org/curated/en/263221492695508325/pdf/ICRR-Disclosable-P096336-04-20-2017-1492696409752.pdf | A number of lessons have emerged from the ICR. Key ones include the following:1. Integrating catchment areaprotection initiatives and water supply interventions is important for the sustainability of a water development project.The encroachment of catchment areas negatively impacts on the quality (and quantity) of water resources available for utilization.Water supply works may face increased operating costs due to the sedimentation resulting from inappropriate land use practices intheir respective catchment areas. Thus, proper catchment management and water source protection is necessary for the sustainabilityof water supply investments2. Budget allocation decisions need to be in-tune with the sector priority constraintsand challenges. It is obvious that sanitation coverage significantly lagged behind water supply coverage in Malawi, whichwas evident at the time of project preparation and appraisal. There was also disparity in water supply coverage between rural andurban areas.3. Partial water system improvements may limit effectiveness of investments provided.Planning of water systems production capacity enhancement would be more effective if distribution capacity is also taken intoaccount. This is in view of the fact that partial system improvements that do not address distribution or other aspects of thewater systems are likely to be constrained by old and limited distribution networks.4. Reaching vulnerablepopulations with sanitation and water supply services requires persistent commitment and innovative approaches. Inclusionof the vulnerable populations requires deliberate measures including targeting vulnerable households with specific assistance. Inthis regard, the project adopted some innovative approaches such as: (i) communities participating in sanitation technologyselection so that it fit their circumstances; (ii) linking of Village Savings and Investment Loans to sanitation promotionactivities, which was an effective mechanism to ensure that households were able to finance construction of improved latrines; and(iii) innovative sanitation promotion approaches such as targeting schools, arranging sanitation and hygiene promotion open daysand involvement of local institutions such as sanitation clubs and mother clubs to facilitate the dissemination of messages andadoption of technologies ona larger scale.One important lesson that has emerged from the ICR Review by the IEG is thefollowing:5. Formulation of PDOs should be consistent with project activities. The second objective ofthe project was formulated as improving water resource management at national level, whereas project activities were designed weretowards improving capacity of sector institutions and preparing water resource investment strategy, investment plan, and conductingdiagnostic studies to assist decision making in the sector. Similarly, the first objective was formulated as improving access tosustainable water supply and sanitation services in target areas, but there were no activities designed to improve access tosanitation services. This led to an internally inconsistent Results Framework which affected efficacy of the project in achievingstates project outcomes.
P096360 | AO-Water Sector Institutional Development | Eastern and Southern Africa | Angola | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2009 | 2019 | 2021 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/586951598824542157/text/Angola-AO-Water-Sector-Institutional-Dvlp.txt | http://documents.worldbank.org/curated/en/586951598824542157/pdf/Angola-AO-Water-Sector-Institutional-Dvlp.pdf | The following lessons werederived from the project implementation experience, and were summarized and formulated by IEGbased on the ICRs lengthier discussion:A well-structured theory of change coupled with stronggovernment commitment can significantly enhance prospects for successful project implementation and achievement ofobjectives. The success of this project was enabled by GOAs strong commitment, consistent support from otherstakeholders, and stable continuity between the Financial and Contract Management Unit (FCMU) and the Bank project teams. Asa guiding framework, the projects theory of change was effective in capturing the needs for short-term investments toaddress water supply access constraints while also reflecting the activities to strengthen sector institutions and implementinstitutional reforms in well-defined stages. This integrated approach helped ensure the long-term sustainability of the new assetsand service provision.Utilities and government agencies require differentiated approachesfor achieving their institutional strengthening and capacity-building objectives. In this project, the utilities(i.e., PWSUs) were supported through management contracts (MCs) that incorporated key knowledge exchange and TA activities. Thisenabled learning-by-doing among PWSU staff, and INRH as well, under the supervision of international experts. For governmentagencies, institutional strengthening was approached as a separate objective from project implementation. Internationallycompetitive implementing contractors were tasked with overseeing the implementation of project activities, while using projectresources to support the short, medium and long-term capacity building activities needed across sector institutions. This mixedapproach could be critical in relatively young infrastructure sectors within fragile, conflict and violence-affected (FCV)countries.Flexibility to make adjustments is essential for supporting successfulproject implementation. In this project, the governments adaptabilitywith the Banks supportthrough restructuring--allowed the GOA to re-prioritize activities within the various project components, while remaining alignedwith the PDO. This flexibility was enabled by the projects effective ME framework, both at the Results Framework level,and also through the complementary data collection from the INRHs monitoring system, the MC indicators, and othersources.IEG adds the following lesson that related to the replicability and broader applicability of theprojects successful experience:Well-designed and properly targeted physicalinfrastructureinvestments, when accompanied by effective institutional capacity-building and associatedreforms, couldresult in attracting additional support to the sector. As evidence,The ICR (page 18) indicates Thesuccess of the project has led the GOA to replicate the approach in other projects in the sector. Further, the approach hasattracted other donors to the sector, namely the AfDB has a project modelled strongly off of WSIDP and for WSIDP-2, the FrenchDevelopment Agency (Agence Franaise de Dveloppement) is a co-financer. Further, the World Bank (WB) hasrecently approved the first IBRD guarantee in the water sector for support to the sector in Luanda (Luanda Bita Water SupplyGuarantee Project, P163572) and the WB is supporting a pilot PPP arrangement inCabinda.
P096367 | WATER AND SANITATION SERVICE IMPROVEMENT PROJECT | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Sustainable Development | Water | IDA | IPF | 2008 | 2020 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/162691610548033491/text/Kenya-KE-Water-Sanitation-Srv-Impr-FY08.txt | http://documents.worldbank.org/curated/en/162691610548033491/pdf/Kenya-KE-Water-Sanitation-Srv-Impr-FY08.pdf | IEG derives the following lessons drawn from the ICR:1. Setting realistic expectations for complexinvestment components could lead to smoother implementation: The NCT was the first large water tunnel of its kind inEast Africa, and many aspects related to its construction were unknown at the time of its inclusion in the project. Given theuncertainties, it would have been better to have erred on the conservative side as regards the timetable for its construction; inwhich case a decision might well have been taken to initiate a new project, rather than to introduce it to the existing operationvia an AF. This might have made it easier to address the complexities around safeguards, and the additional supervision thatwas required.2. Ensuring that the implementing agencies establish a strong safeguards team from the start ofthe project would make for a smoother preparation and implementation of Resettlement Action Plans (RAPs) and Environment and SocialManagement Plans. The projects implementing agencies did not initially have strong safeguards teams, whichled to some non-compliance with the Banks safeguards policies and delays in preparation of RAPs, ESMPs and safetyprocedures. Even after the Bank worked with the agencies to strengthen these teams, the project closed with severalsafeguards issues still outstanding.3. A strong regulator can help achieve transparent and accountablegovernance of institutions in the sector: The project helped to strengthen WASREB (Water Services Regulatory Board)through training and technical assistance, which helped it to become a more effective institution, in dealing with customer-relatedissues, enforce license conditions, engage on tariff issues, and establish complaints-handling systems thereby establishingthe value of investing in strengthening the role and capacity of the regulator.
P096389 | Development Policy Loan 2 (DPL 2) | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2008 | 2008 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/908861474574723237/text/000020051-20140625061447.txt | http://documents.worldbank.org/curated/en/908861474574723237/pdf/000020051-20140625061447.pdf | The ICR has appropriate lessons.First, while the flexibility in DPLs allows adjustments when domestic political circumstances or external events compel these adjustments, it may be preferable for the Bank to focus on more narrowly defined and specific reforms with a different lending instrument in order to have impact and success. Second, joint action with other donors is at times imperative to obtain the desired result such as, in this case, procurement reform. Third, a good M&E system should ensure that the necessary information to monitor progress is readily available.
P096400 | Energy Community of South East Europe APL 3 Project | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2006 | 2011 | 2014 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/330341475090847055/text/000020051-20140625065909.txt | http://documents.worldbank.org/curated/en/330341475090847055/pdf/000020051-20140625065909.pdf | The following three lessons are taken from the ICR with some adaptation of language:The projectâ€™s experience shows the importance of sustained political commitment and policy dialogue over time for effective electricity sector reform. In this regard, a long term instrument, such as the APL, was useful.Regional markets require strong national market operational capabilities and close attention to the design and operation of component national electricity markets.When, as in this case, reform implies unbundling, commercialization, and privatization, it is important that the system and market operator (here, TEIAS) has the capacity to react rapidly to an evolving operating environment in a pro-active and timely manner. There were indications during implementation that TEIAS capacity could be reinforced in these respects (particularly in terms of being able to attract and retain high quality staff).
P096407 | Abidjan-Lagos Trade and Transport Facilitation Project (ALTTFP) | Western and Central Africa | Western and Central Africa |  |  | Infrastructure | Transport | IDA | IPF | 2010 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/312381519750058142/text/ICRR-Disclosable-P096407-02-27-2018-1519750966715.txt | http://documents.worldbank.org/curated/en/312381519750058142/pdf/ICRR-Disclosable-P096407-02-27-2018-1519750966715.pdf | The ICR provides several recommendations based on the lessons learnt from the project (para 99). Four are presentedbelow: The project was designed as a regional project but the implementation arrangements were atnational level, and as such the project was implemented as three separate national projects. Throughout implementation,therewas amajor disconnect between customs related activities in the three countries. A higher-level corridorsupervision and coordination layer would have assisted with implementation and ensured better synergy of activities and theircomplementarity. The Abidjan Lagos Corridor Organization (or similar regional level entity) could have been given a larger role, inaddition to results dissemination, of coordination for the national facilitation committees, as well as supervision andcoordination of country PIUs or implementing agencies, and overall supervision of activity plans. Future regional corridoroperations should seek strong regional stakeholder support and encourage implementation as a regional-levelentity. For regional projects, donor concentrated efforts are needed to ensure that financing gaps arecovered. However, the fragmented approach with different timelines over the corridor proved to backfire in the long term. Forexample, in Togo, the joint border post activities under the project were reallocated to the AfDB halfway through projectimplementation. However, works were at an incipient stage at project closing in June 2017. Similarly, the joint border posts fundedunder ECOWAS registered significant delays in operationalization. Closer long term coordination with other regional partners andclients should be sought and continuous dialogue should be encouraged on theattribution of activities and proposed timelinesof implementation. For roads in coastal areas that might be affected by coastal erosion, the technicalstudies and designs should propose mitigation actions. Differences in country implementation capacity cannegatively impact projects overall performance. The performance of one country (Ghana) during implementation negatively impactedthe overall performance of the project in terms of timeline, achievement of objectives, and efficiency because of substantial costoverruns. This consequentlyovershadowed the performance of Togo which, despite challenges during implementation, couldcomplete its activities and achieve its objectives before the initial closing date of the Project (September 30, 2016).
P096409 | Second On-farm Irrigation Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2007 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/105591517350287806/text/Kyrgyz-Republic-OIP-2.txt | http://documents.worldbank.org/curated/en/105591517350287806/pdf/Kyrgyz-Republic-OIP-2.pdf | The ICR provided comprehensive lessons. The most important follows with some modification oflanguage:Capacity increase for WUAs is crucial for sustainable irrigation services. Technical Assistance(TA) contributes to enabling WUAs to become self-sustaining and to appropriately manage their rehabilitated and modernized on-farmID systems. Important elements of this TA are asset management, conflict resolution, and planning. For WUAs that need longersupport, it is also important to get additional donor support as well as government budget support to continue improvement of theircapacity and ID system.Design of ID schemes to be rehabilitated need to be carefully carried outthrough sufficient beneficiary engagement. The project experience showed that a significant number of the ID scheme designsproved to be of insufficient quality once construction work began, this was due to oversights in the planning phase and/or lack ofcommunication with the potential beneficiaries. More interaction among farmers, WUAs, PIUs, oblast and raion staff as well asproject preparation staff is needed when designing the next irrigation rehabilitation project.Investmentsthrough the whole value chain is needed to increase incomes of farmers and also to satisfy market demands. Irrigation investment isonly one component of the agricultural value chain and it needs to be accompanies by other investments along the chainincluding creation of enabling environment for processing, marketing and export facilities and opportunities.
P096411 | Rural and Social Sector Policy Reform Credit 1 | Western and Central Africa | Niger | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | DPF | 2006 | 2007 | 2009 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/164061475069509715/text/Niger-Rural-and-Social-Sector-Policy-Reform-Credit-I.txt | http://documents.worldbank.org/curated/en/164061475069509715/pdf/Niger-Rural-and-Social-Sector-Policy-Reform-Credit-I.pdf | The following lesson complements the lessons offered in the ICR:A key lesson from this DPL series pertains to the complementarity between financing instruments. The RSRC series was a good example of complementarity between two instruments: investment and DPL lending. Under the RSRC policy and process issues were addressed that constrain the development effectiveness of the investment operations.
P096418 | Land Administration Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2008 | 2015 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/364621476387656130/text/ICRR-Disclosable-P096418-10-13-2016-1476387646880.txt | http://documents.worldbank.org/curated/en/364621476387656130/pdf/ICRR-Disclosable-P096418-10-13-2016-1476387646880.pdf | The following lessons are summarized from the ICR (p. 26-27): By nature, land administration projects need a longtime to gain a foothold. They require political will and adequate management capacity from all levels of government. Challenges areacute when new efforts introduce changes, not only in market structures but in service orientation as well, as was the case in thisproject. A successful endeavor would probably require multiple, successive, and incremental operations that would build uponmodest, well formed designs that consider capacities of the entities providing the service at all levels of government and astrong awareness-raising communications strategy that would engage users of the service from both the general public and privatesectors. When selecting which subnational entities could showcase appropriate approaches, it is important to assess carefullyreadiness to implement. There is value in utilizing soft investments in training, and awareness raising,particularly when behavioral changes are necessary to accompany the transition from a centrally planned to a marketbasedeconomy. In addition,independent assessments of implementation and impact could foster innovations and creativeapproaches to optimal service delivery at the local level. Learning opportunities based on these innovative practices could then besystematically shared and disseminated.
P096439 | MN-Sustainable Livelihoods II | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2013 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/869151474942067708/text/000012394-20150108123046.txt | http://documents.worldbank.org/curated/en/869151474942067708/pdf/000012394-20150108123046.pdf | The following lessons are taken from the ICR with some reformulation of language:Decentralized service delivery mechanisms with the participation of communities can have substantial impacts on livelihoods. The project demonstrated that community empowerment. can be achieved through communities leading the identification, planning and execution of sub-projects. Such an approach results in ownership and commitment by the beneficiaries which is instrumental in the successes achieved by the project. Training and learning-by-doing is key to community empowerment. The project not only provided training to rural communities but also the opportunity for them to attempt hands-on planning and implementing projects. In doing so, the communities acquired the skills necessary for project execution which enhanced significantly their capacity to participate in decision making.Institutional and policy reforms require long term engagement, and an APL is an effective instrument to facilitate such reforms. It is evident that the institutional changes would not have been achieved with a normal investment lending operation of 4-5 years. The APL mechanism or long term engagement with the government enabled a consensus to develop among various stakeholders over time.Decentralizing project management functions to provincial and local governments is instrumental in ensuring smooth implementation of subprojects. The project implementation unit was establish with project coordinators and accountants at aimag (province) level and a project coordinator at soum (district) level. The staff were provided with needed capacity building through training so that they could closely monitor, supervise, and resolve implementation issues on day-to-day basis, and report progress to SLPO at the national level on a regular basis. Easy access to local government administrations enabled a faster response to emerging issues.
P096439 | MN-Sustainable Livelihoods II | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2013 | 2022 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099807405052217103/text/IDU01aac9bd204ec6045750ad7701004ab7a1dff.txt | http://documents.worldbank.org/curated/en/099807405052217103/pdf/IDU01aac9bd204ec6045750ad7701004ab7a1dff.pdf | 3. Lessons 3.1 Sustained engagement in CDD, combined with positive political momentum and internal champions, can lead to legal and regulatory changes that support sustainability of the mechanism. Through its three-phased approach, SLP demonstrated to the client a comprehensive blueprint for fiscal decentralization and increased citizen engagement in rural development. When sufficient domestic demand materialized, this groundwork and consistent cooperation with the client government and reform champions within resulted in SLP having a transformative effectÃ¢â‚¬â€that is, the passage of the IBL that formalized SLPÃ¢â‚¬â„¢s CDD model. This illustrates how a strong demonstration effect can lead to positive governance changes, which, if enshrined in national law, can achieve a high sustainability. 3.2 In environments where there is an increasing and unsustainable pressure on the natural resource base, the vulnerability of resource users cannot be reduced successfully without comprehensively addressing the drivers of resource degradation. Although SLPÃ¢â‚¬â„¢s support for community-based pasture management was highly relevant, it was ultimately ineffective in addressing pasture degradation. The project could have benefited from a better and evolving understanding of the complex vulnerabilities of resource users and the underlying governance, market, and sociocultural factors driving degradation, which changed significantly during the life of the project as Mongolia transitioned into a market economy. SLPÃ¢â‚¬â„¢s community-based pasture management intervention was not backed with sufficient complementary governance (for example, dialogue, national-level policy, enforcement, and so on) and market support to manage rising livestock numbers and curb overgrazing. Without such measures, the incentive system leading to overstocking remained intact, leaving both degradation and vulnerability reduction results at risk of being nullified by the continued decline of pasture health. 3.3 Ensuring social inclusion is key in the implementation of group-based interventions to avoid unintended consequences, such as exacerbating distributional inequities or free-rider problems. SLPÃ¢â‚¬â„¢s interest-based approach to herder group formation was found, in some cases, to reinforce resource access issues. Socially marginalized individuals lost out on accessing quality productive resources because group-based activities inadvertently reinforced informal power relations and existing disparities. Alternatively, the engagement of poor resource users without the active involvement of wealthier resource users led to free-rider problems when those with the 31 largest herds and impact on pasture degradation did not participate. In the case of group-based activities, vigilance and careful targeting are required to avoid such results, along with sufficient support to foster genuine collective action, which can help address potential exclusionary effects and free-rider problems. Alternative options include using a spatial approach, which endeavors to include all resource users within a geographic area, or smaller socially or kinship-based groups. While there are invariably pros and cons to these alternatives, it is paramount that limitations are assessed and mitigative measures are determined when designing group-based interventions. 3.4 Risk forecasting and early-warning systems may not be sustained if the technology is incompatible with or not embedded in local institutions. The SLP-financed LEWS ultimately became disused and ineffective because it was not embedded successfully in local institutions and used technologically incompatible systems. It lacked the coproduction and institutional strengthening necessary to (i) mitigate technological incompatibilities, (ii) build sufficient capacity to operate and maintain the system, and (iii) foster local ownership. Without adequate attention to such measures, risk forecasting or early-warning systems are unlikely to achieve sustainability. 3.5 Increasing the availability of rural finance does not automatically lead to livelihood diversification and may contribute to additional livelihood vulnerability in high-risk sectors. Although SLP was successful in contributing to the market penetration of rural financial services, the expected livelihood diversification did not occur. The implication is that beneficiary decisions on livelihood activities are guided by a multitude of factors (for example, social, economic, contextual, and so on), of which access to credit is just one. These factors were not sufficiently addressed with appropriate complementary activities to support alternative livelihoods. Lacking livelihood diversification, coupled with increased borrowing for high-risk activities, may have contributed to an increase in herder vulnerability. This further demonstrates the need for a comprehensive understanding of the drivers of vulnerability and the barriers to livelihood diversification. 3.6 Efforts to implement index-based insurance programs should thoroughly assess factors that will determine feasibility and sustainability, including the appetite for insurance within the target customer base. IBLI uptake was limited because of several socioeconomic factors. For example, herder households may be opting to rely on existing risk mitigation strategies or they may not perceive the benefit of using sparse resources to purchase insurance. Even though IBLI uptake was successfully increased through extensive and costly project-financed marketing efforts, the expected traction and insurance coverage have not been maintained postproject. Rigorous market and anthropological research at the initial stages is needed to understand whether sufficient insurance demand can be cultivated within the existing socioeconomic environment. 32 3.7 A mismatch between project ambition and support can impair the provision of sufficient capacity building needed for desired behavior change and long-term outcomes. SLP I and SLP II were ambitious projects whose financial and human resources were spread very thin after SLPÃ¢â‚¬â„¢s rapid scale-up to the national level. Except for the CDD component, SLP lacked the required resourcing and institutional support necessary to achieve the desired outcomes, which contributed to many of its shortcomings. Long-term and frequent capacity building is needed for institutions and communities to reinforce key skills and knowledge and to engender ownership and genuine community engagement. Community-based interventions and desired behavior change require a strong local presence with effective backstopping and oversight from the national level. Intensive but one-off training is less efficient, not least because staff turnover can be high at the local level. 1 Ã¢â‚¬Å“Project design therefore incorporates the strategic choice that support for livestock-based livelihoods be enhanced through initiatives in risk management; while parallel support for Ã¢â‚¬Ëœexit strategiesÃ¢â‚¬â„¢ and livelihood diversification for those who would prefer to make a living by means other than pastoral livestock production also be provided, through micro-finance outreach and associated technical assistance, and support for community-level investments in the infrastructure needed for private-sector led growthÃ¢â‚¬ (World Bank 2002, 12). 2Ã¢â‚¬Å“The risk forecasting, preparedness and response planning subcomponent suffered from delays for almost two years after effectiveness due to protracted signing of contracts with an NGO [nongovernmental organization] to support the development of the Livestock Early Warning System (LEWS). The implementation of the pasture land management, tenure and use and demonstrating good practice in pastoral livelihood improvement, delayed considerably. This was also related to procurement as the tendering process for major technical assistance (TA) contract to provide support to pastureland planning and demonstration areas prolonged Ã¢â‚¬ (World Bank 2013a, 8). 3Since July 2021, the government of Mongolia has implemented a tax on livestock ownership, the revenue of which should be directed to rangeland and livestock management activities. Although a noteworthy development, successfully implementing and enforcing this law will require substantial political will and local governance capacity. As of now, it is too early to tell whether it will prove effective in incentivizing smaller herds and facilitating rangeland recovery. 4Exchange rate effective November 18, 2013: $1.00 = 1,748 Mongolian tughriks (Tog; World Bank 2013a). 5Rangeland degradation entails changes in plant communities, biodiversity, productivity, and in severe cases, soil structure and fertility away from reference conditions expected for a particular agroecological zone (Jamsranjav et al. 2019). 6Ã¢â‚¬Å“The risk forecasting, preparedness and response planning subcomponent suffered from delays for almost two years after effectiveness due to protracted signing of contracts with an NGO 33 [nongovernmental organization] to support the development of the Livestock Early Warning System (LEWS). The implementation of the pastureland management, tenure and use and demonstrating good practice in pastoral livelihood improvement, delayed considerably. This was also related to procurement as the tendering process for major technical assistance (TA) contract to provide support to pastureland planning and demonstration areas prolonged Ã¢â‚¬ (World Bank 2013a, 8). 7Sharing pastures can facilitate the survival of herders escaping harsh conditions, but it can also increase the exposure and overall vulnerability of communities hosting otor (seasonal long- distance migration) herds. 8According to the Sustainable Livelihoods Program (SLP) phase I completion report, pasture maps developed included Ã¢â‚¬Å“(i) base map, by winter-spring and summer-autumn seasons (scale 1:100.000); (ii) pasture stocking rate map by 4 seasons and by annual means (5 separate maps differently scaled, depending on the size of soum [district] territory); (iii) well mapping with surrounding areas; (iv) seasonal pasture division map; (v) current stocking density map; and (vi) estimated carrying capacity mappingÃ¢â‚¬ (World Bank 2008, 30). 9As of 2018, there were 1,516 monitoring sites representing all bags (subdistricts) in Mongolia. Soum officers collect the primary data yearly. Aimag (province) staff ensure quality control and enter the monitoring data into the National Rangeland Monitoring Database. 10In 2016, according to the classification by degradation level, 42.4 percent of sites were in a nondegraded state, 13.5 percent were slightly degraded, 21.1 percent were moderately degraded, 12.8 percent were heavily degraded, and 10.3 percent were fully degraded. Compared with conditions in 2014, the proportion of sites that were heavily to fully degraded increased by 5.9 and 4.3 percentage points, respectively. 11The national legislative and policy framework broadly underscores the importance of pastoral resources and livelihoods, including through (i) constitutional protection of land as public property to be managed by communities as common property and (ii) the Land Law, which allows local governments to set and enforce stocking rates, grazing reserves, and seasonal movements. 12The most recent draft was produced in late 2019; however, progress in introducing it to parliament stalled likely because of the June 2020 national elections. 13 MongoliaÃ¢â‚¬â„¢s livestock sector has grown prolifically from 25 million animals at economic liberalization in 1992 to 70 million animals in 2019, albeit at the cost of pastoral mobility and a rise in localized congestion (for example, near soum and aimag centers), overgrazing, and conflict over pasture (Gao et al. 2015). 14 In recent years, there have been some initiatives oriented toward sustainability certification for livestock production, such as the Sustainable Fibre Alliance, and initiatives by the Wildlife Conservation Society, Swiss Agency for Development Cooperation, and Agronomes et VÃƒÂ©tÃƒÂ©rinaires Sans FrontiÃƒÂ¨res. 34 15The Livestock and Agricultural Marketing Project (2013) and Livestock Commercialization Project (2019) have aimed to improve livestock competitiveness, while continuing to support pastoral herder group capacity building regarding sustainable livestock production and associated policy reforms to further incentivize herders to prioritize quality over quantity. 16In total, 313 nongovernmental organizations were established and registered, with 6,313 members from 2,532 households; 42 cooperatives and 189 informal herder groups were strengthened (World Bank 2008, 31). 17Examples include the Swiss Agency for Development and Cooperation Green Gold Project that used a territorial approach; and the United Nations Development Programme, German Agency for International Cooperation, and United States Agency for International Development groups that were high performers in terms of social outcomes (for example, achieving desired behavior change and fostering genuine and endogenous collective action; Ulambayar and FernÃƒÂ¡ndez- GimÃƒÂ©nez 2019). 18Most Mongolians are apprehensive about fencing, which clashes with their values of common land ownership and nomadic mobility. 19The climate data were up to date at the time of this assessment but not the forage forecast maps. However, the climate maps are not granular and consequently are of limited use to herders. The climate maps are also courtesy of the International Research Institute for Climate and Society at Columbia University, thus not produced by LEWS. 20 P088816 and P115119: Index-Based Livestock Insurance Project (2005Ã¢â‚¬â€œ16). 21By the end of SLP I, approximately $7.13 million had been allocated to the participating financial institutions as wholesale loans, from which $17.0 million was onlent to rural residents (World Bank 2008, 15). During the SLP II, the Microfinance Development Fund instrument disbursed Tog 24 billion wholesale loans to participating financial institutions, of which Tog 4.5 billion went to nonbank financial institutions and Tog 19.6 billion went to commercial banks (World Bank 2013a, 33). The US dollar to Tog exchange rate on June 30, 2013 (at project close) was Tog 1437.50; https://freecurrencyrates.com/en/exchange-rate-history/USD-MNT/2013/yahoo. 22The Household Socio-Economic Survey (HSES) is representative of the nation, region, urban and rural areas, residential location, and aimags. It was enumerated in 320 soums and 9 districts of Mongolia. In total 16,488 households were randomly selected for the HSES 2018. The list of all households of Mongolia or the list of households registered in the population and households Ã¢â‚¬â„¢ database at the National Statistics Office of Mongolia was used for HSES as a sampling frame. The sample size is estimated at 95 percent confidence level; the probability of error is 1.5 percent, key parameter p = 0.33, and the design effect is deff = 3, and the sample size was taken proportionally throughout the 12-month period of the survey. 23Pension loans allow pensioners to borrow up to six times their monthly pension, which is automatically deducted from future payments. These loans enable pensioners to control their cash flow and serve as an alternative to borrowing from the informal sector (Dyer, Morrow, and Young 2004). 35 24Borrowers can borrow up to seven times their monthly salary for a term of up to one year. Loan payments are made directly through a deduction from their regular salary (Dyer, Morrow, and Young 2004). 25Average US dollar to Tog exchange rate in 2018: Tog 2431.1129. Source: https://www.exchangerates.org.uk/USD-MNT-spot-exchange-rates-history-2018.html. 26 Comprehensive data on informal sector borrowing trends and behaviors were not found. 27 Ã¢â‚¬Å“Project design therefore incorporates the strategic choice that support for livestock-based livelihoods be enhanced through initiatives in risk management; while parallel support for Ã¢â‚¬Ëœexit strategiesÃ¢â‚¬â„¢ and livelihood diversification for those who would prefer to make a living by means other than pastoral livestock production also be provided, through micro-finance outreach and associated technical assistance, and support for community-level investments in the infrastructure needed for private-sector led growthÃ¢â‚¬ (World Bank 2002, 12). 28The economic and financial analysis in the Index-Based Livestock Insurance Project Appraisal Document indicated among its Ã¢â‚¬Å“with-project assumptionsÃ¢â‚¬ that Ã¢â‚¬Å“herders use IBLI [Index-Based Livestock Insurance] as their main means for risk mitigation instead of an ever-increasing herd size. Thus, it is assumed that the Ã¢â‚¬Ëœwith-projectÃ¢â‚¬â„¢ herder will start with an initial herd size of 200 animals in 1993, but will limit the herd size to 225 animals in each of the following years Ã¢â‚¬ (World Bank 2005, 50). 29Under SLP I and SLP II, the fund financed 1,729 and 5,066 subprojects, respectively. In the education sector, the fund rehabilitated and equipped school dormitories, kindergartens, and cultural centers. In the health sector, hospitals and maternal homes were also rehabilitated and equipped, in addition to the provision of ambulances and motorbikes for bag doctors. Other activities undertaken were rehabilitating public bath houses, potable wells, roads, bridges, and small business centers. 30The SLP I completion report noted that Ã¢â‚¬Å“one major factor within the government control was a reversal from fiscal decentralization policy. While the Public Sector Financial Management Law of 2002 has streamlined budgeting procedures, limited fiscal resources of the government in fact reversed even the existing degree of decentralization. At midterm, it was decided to modify the sub-component and refocus it to enhance state-citizen engagement in fiscal decision making, transparency and accountabilityÃ¢â‚¬ (World Bank 2008, 9). 31Because of low local revenue levels, local governments were heavily dependent on central government transfers (which represented 70 percent of subnational revenue from 1990 to 2002) to finance their education, health, and public service delivery (World Bank 2015). 32The community-driven development activities in SLP I and SLP II were project based, whereas the SLP III directly supports the governmentÃ¢â‚¬â„¢s fiscal transfer mechanism (that is, the Local Development Fund) and the associated institutional framework. 33 Exchange rate effective November 18, 2013: $1.00 = Tog 1,748 (World Bank 2013a). 36 Glossary Aimag A provinceÃ¢â‚¬â€that is, the first administrative division of Mongolia. Bag A subdistrictÃ¢â‚¬â€that is, the third and lowest administrative and territorial unit in Mongolia (soums are divided into bags). Dzud Summer drought followed by a severe winter, generally causing serious loss of livestock; extreme weather events or conditions that can be caused by sudden heavy snowfall, long-lasting or frequent snowfall, extreme cold, or storms that cause often massive livestock deaths from hunger, exhaustion, and cold. Mongolian herders distinguish different types of dzud caused by snow, cold, ice, lack of grass because of drought in previous year, or combinations of these. Otor Long-distance migration of Mongolian herders, typically in autumn, to fatten livestock for winter. Soum A districtÃ¢â‚¬â€that is, the second administrative and territorial unit in Mongolia (an aimag is divided into soums). 37
P096481 | Municipal Services Improvement | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2009 | 2021 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/533481623436162323/text/North-Macedonia-MUNICIPAL-DEVELOPMENT.txt | http://documents.worldbank.org/curated/en/533481623436162323/pdf/North-Macedonia-MUNICIPAL-DEVELOPMENT.pdf | The ICR (p. 34-36) included several lessons: Identifying municipal demand at appraisal stage is criticalfor informing project design. In this project, due to the limited borrowing capacity of most of the participatingmunicipalities, the average investment size was relatively small. Therefore, being realistic about potential results and managingexpectations accordingly is important. Allowing participating municipals to apply for sub-loans on a rollingbasis provides adequate flexibility. This project used a flexible approach and participating municipalities were able toapply for sub-loans whenever they had sufficient borrowing capacity instead of a specified call for proposals approach, whichresulted in a more balanced implementation pace and sustained disbursement as well as minimized the volume of uncommitted funds atproject closure. Collaboration among multiple beneficiaries with similar interests can allow for exploitingeconomies of scale. In this project, the IPA rural window where the PMU, the Bank and the European Commission were able toswiftly use the saved amount for the purchase of the photovoltaic installations and back-hoe loaders forpoorer municipalities.
P096482 | BENIN: Malaria Control Booster Program | Western and Central Africa | Benin | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2006 | 2011 | 2013 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/309071474481587845/text/000020051-20140625082433.txt | http://documents.worldbank.org/curated/en/309071474481587845/pdf/000020051-20140625082433.pdf | Lessons from the ICR (page 29):Active, rigorous supervision of a project, particularly by way of a dedicated, field-based task team leader, can contribute to building the country's capacity to implement project activities. The guidance of the task team leader was consistently cited as being a critical success factor for this project. Strong collaboration among government and partners can achieve significant synergies and efficiencies in planning, financing, implementation, and evaluation. Joint studies and evaluations, the second mass LLIN campaign, and the provision of essential commodities are examples of such collaboration from this project.Addressing a single disease through a health systems approach, while leading to some inefficiencies and weaknesses, can be a vehicle for health systems strengthening. The project-supported malaria program, with its clear set of inputs, activities, outputs and outcomes, contributed to improved capacity in the health sector.Lessons drawn from IEG:A dedicated project component on M&E (with the dedicated resources) can highlight the importance of monitoring and ensure focus on results. In the case of this project, a full M&E component was designed to ensure sufficient attention and support.
P096532 | Dam Operational Improvement and Safety | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2009 | 2024 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/462741512055590798/text/ICRR-Disclosable-P096532-11-30-2017-1512055576559.txt | http://documents.worldbank.org/curated/en/462741512055590798/pdf/ICRR-Disclosable-P096532-11-30-2017-1512055576559.pdf | Dam safety projects that contain a large portfolio of dams can benefit from a programmatic approach, which is a suitablewayto scale up project interventions and strengthen capacity over time. DOISP was designed and implemented as aprogrammatic approach, which allowed for a significant scale-up of interventions and gradual institutional strengthening. Startingwith a smaller set of interventions in the initial phase can enable implementing agencies to learn and strengthen their capabilityto expand activities in the second phase. While the project utilized the Additional Financing mechanism to scale up activitiesinstead of developing a new second-phase operation, the scale-up over time was a logical choice.Sedimentmanagement requires multi-institutional coordination and a clear strategy for next-generation dam safety investments.Sedimentation is a complex challenge for dam safety projects as the causal factors stem from land use patterns farupstream of dam facilities. Governmental institutions that may be responsible for the regulation of land use (e.g., ministries ofenvironment or agriculture) are likely to be different than those who manage and operate dam facilities. The complexity of theissue is increased as mitigation involves changing behaviors and incentives of private landholders who are upstream and likely tonot directly receive the downstream benefits of the dam facility (e.g., flood protection, water supply). Nevertheless,sedimentation can pose serious risks to investments in dam rehabilitation and new construction reducing the impact of theinvestment. While DOISP was cognizant of this issue, the impact of the sedimentation mitigation activities was limited. The designof next-generation dam safety projects should incorporate robust interventions that will likely require multi-institutionalcoordination to address the challenge, or explicitly do so in concert with other projects.If dam risk indices are to be used as PDO-level indicators, the indicator definitions and targets should beset with the recognition that they measure relative risk within a portfolio of projects and not actual risk reduction(i.e., the product of the probability of failure and the consequences). There are some risk parameters that can and willchange in response to the implementation of dam safety measures, and others will be influenced by factors beyond the control of theproject. Given this, risk indices may be better suited as intermediate outcome indicators. Regardless, the agreed approach tomeasuring risk must be applied consistently throughout the project to be able to track project-induced changes. Since the selectionof parameters and weights of risk indices introduces some element of subjectivity, these assessments must be done by or under theguidance of experts and according to a common guideline or standard. (ICR, p. 29)
P096556 | Eco-Farming Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2009 | 2018 | 2015 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/419071467998479478/text/ICRR14713-P096556-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/419071467998479478/pdf/ICRR14713-P096556-Box393183B-PUBLIC.pdf | Favorable national regulatory frameworks and policy instruments are key drivers of successful project implementation.- Project design benefits greatly from looking at the institutionâ€™s (and other donors) previous experience and lessons learned from other operations in the country and elsewhere.- Stakeholdersâ€™ commitment, dedication and capabilities are critical in ensuring a projectâ€™s success, sustainability and ownership.
P096572 | THIRD NATIONAL FADAMA DEVELOPMENT PROJECT (FADAMA III) | Western and Central Africa | Nigeria | Blend | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/565201619098690591/text/Nigeria-NG-Fadama-Development-III-SIL-FY08.txt | http://documents.worldbank.org/curated/en/565201619098690591/pdf/Nigeria-NG-Fadama-Development-III-SIL-FY08.pdf | The ICR provides 6 brief lessons, of which the following lessons are retained (with language adapted):1.Decentralization of decision-making and coordination to local communities ensures buy-in and commitment. Thedecentralization of decision making, management, and coordination to Management Committees of FCAs, Desk Officers, and Facilitatorsin addition to the State Project Implementation Unit enhanced empowerment, social inclusion, participation, ownership, andsustainability.2. The presence of good local institutions, and strengthening of their institutional capacity, isimportant to translate local aspirations into collective action, and it is a core element of a good CDD project. FadamaIII created and supported several local institutions, most of which have remained operational, albeit at different capacities, andcontinue to provide vital services to project beneficiaries.3. An integrated and demand-driven approach to servicedelivery is important to ensure that project investments will be effectively and sustainably used. The project combinedhard investments (FUG asset creation and community infrastructure) with soft technical support (capacity building andadvisory support). The integrated package of interventions simultaneously addresses the multiple constraints to agriculturaldevelopments to reap the synergetic effects of a package of interventions. The project implemented a demand-driven approach toinvestments in infrastructure, implying that local communities had to decide on the type of investments (from a menu of options)that they deemed most necessary for the community. This creates local ownership, commitment, optimum use, and sustainability of theassets provided to communities, even after the project ended.
P096586 | UA - ENERGY EFFICIENCY | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2011 | 2017 | 2018 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/207911521582196819/text/Ukraine-UA-ENERGY-EFFICIENCY.txt | http://documents.worldbank.org/curated/en/207911521582196819/pdf/Ukraine-UA-ENERGY-EFFICIENCY.pdf | The following lessons were abstracted from the ICR: It would be useful to pre-appraise severalfinancial intermediary institutions for participation in the project, so as to avoid the problem encountered in this project whereone of the two these financialinstitutions originally chosen had to drop out. The project could havebenefitted from early-stage assistancein promoting the project among potential clients, including assistance in developing acountrywide communication campaign. UEB lack of specific experience in communicating the benefits of the EE financing was one ofthe elements that led to lower-than-expected interest in EE investment during the first few years of theimplementation. The project relied exclusively on a direct onlending financing model for extending financingto companies interested in pursuing EE investments. Future projects should explore additional financing models, including partialrisk guarantees, leasing, and possible types of leveraged financing. In some circumstances, such as inUkraine, which at the time of project appraisal had an effective financial system and a strong public sector bank, a projectcan succeed without the need for additional technical assistance or policy reforms.
P096605 | Dominican Republic Youth Development Project | Latin America and Caribbean | Dominican Republic | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2006 | 2013 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/193691474496491020/text/000020051-20140626124123.txt | http://documents.worldbank.org/curated/en/193691474496491020/pdf/000020051-20140626124123.pdf | These lessons are drawn from the ICR (pages 21-22) and adapted by IEG: Specific project design features play a role in determining program efficacy, but exogenous factors such as the level of economic activity and the structure of labor markets are also likely to play a role. Ultimately, this type of program can help better align the supply and demand of labor skills, albeit within the envelope determined by exogenous factors.There are trade-offs between equity and efficiency objectives in skills development programs such as PJE. Targeting the most vulnerable, particularly poor at-risk youth who may have less access to jobs than their peers from other socio-economic groups, is a priority from an equity perspective. But the impact on labor outcomes among this group may be limited given the short nature of the training provided and the often dramatic deficiencies in skills and education among this population group.Focusing on soft skills can improve effectiveness of training programs. Both employers and trainees appear to value these soft skills more than technical skills. Results from the project's impact evaluation suggest that training in soft skills might be more effective, in terms of employability, than technical training.
P096635 | Lao PDR Second Poverty Reduction Support Operation (PRSO2) | East Asia and Pacific | Lao People's Democratic Republic | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2006 | 2007 | 2010 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/775001474906657552/text/000146597-20140619160709.txt | http://documents.worldbank.org/curated/en/775001474906657552/pdf/000146597-20140619160709.pdf | There are two major lessons which follow from the evaluation of this PRSO series.First, good ESW and TA are absolutely essential for reforms to succeed in a country with capacity constraints as severe as they are in Laos.Second, the efficacy of Bank and other donor interventions cannot be judged adequately in the absence of a minimum of basic data. The Bank should make a major effort to help strengthen the information and data base in the country.
P096643 | Business Environment Reform and Institutional Strengthening | Europe and Central Asia | Albania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2007 | 2012 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/704161475099764716/text/000020051-20140626110034.txt | http://documents.worldbank.org/curated/en/704161475099764716/pdf/000020051-20140626110034.pdf | There are four main lessons that can be drawn from the experience of this project:Changes to a projectâ€™s monitoring and evaluation framework need to be carefully considered and, if needed, carried out as early as possible. Changes should in particular take into consideration comparability of results with any baseline, and be timed in such a way that a project is not judged based on different indicators compared to those used to manage it.Innovative implementation modalities should be adequately supported and monitored. When borrowers first try to manage Bank operations without a project implementation unit, the Bank should provide strong support for the managing unit within the implementing ministry, and careful consideration of how project tasks can be effectively carried out by civil servants.High turnover of staff is an issue that can be addressed. Staff changes on the Bankâ€™s and Borrowerâ€™s side can cause loss of institutional memory. While there is no easy fix, the issue emphasizes the importance of documenting progress and institutionalizing processes, as well as of selecting TTLs from the project team, so that the consequences of changes in staff are less disruptive.Changing the way regulations are implemented is one of the most difficult improvements to the business environment and cannot be achieved by investment projects alone. While the use of policy lending can support policy change, regulatory reform often affects powerful vested interests and requires strong and committed leadership on the Borrowerâ€™s side.
P096647 | Community Recovery in Earthquake Affected Areas through UPP | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2006 | 2010 | 2012 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/958661475078749634/text/000020051-20140624200611.txt | http://documents.worldbank.org/curated/en/958661475078749634/pdf/000020051-20140624200611.pdf | Lessons from the ICR that reflect IEG's experience with natural disasters reconstruction were the following:CDD-type projects can be effective and can be set up at short notice to mitigate the impacts of natural disasters. This was demonstrated by using the design of the Project to prepare two other disaster relief projects on short notice (to rebuild community infrastructure destroyed by earthquakes that hit Yogyakarta in 2006 and Padang in 2009, respectively). Moreover, the Project did not only support much-needed investments, but also contributed to the psychological recovery of the victims by involving them in the decision-making processes. Flexibility in design and implementation arrangements are essential for disaster recovery projects. Because of a high level of uncertainty during preparation, the Project design should allow the Bank and the Grantee to adapt to changing circumstances during implementation when more information becomes available.Efficient use of funds for disaster relief programs requires coordination with long-term development plans. Such coordination is needed to ensure appropriate levels of rehabilitation for infrastructure that will be reconstructed on a large scale at later stage, whilst at the same time considering the benefits of short-term rehabilitation to get communities â€œback on their feetâ€ and develop productive activities.
P096648 | Commercial Agriculture Development Project | Western and Central Africa | Nigeria | Blend | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/405651521757130496/text/Nigeria-NG-Commercial-Agriculture-Development.txt | http://documents.worldbank.org/curated/en/405651521757130496/pdf/Nigeria-NG-Commercial-Agriculture-Development.pdf | The ICR presents six lessons, which mostly relate to general project preparation requirements, such as a need to undertake abroad institutional assessment of participating institutions to tailor a capacity-building program to identified needs and gaps;and to design a flexible and adequately funded ME system with proper baseline data to enable a meaningful evaluation of theoutcomes and impacts. Other lessons are generic to value chain development, such as effective stakeholder collaboration, the roleof productive member organizations, and alliances in agribusiness development.One specific lesson, whichcould be useful for other similar interventions, concerned the OPRC method for contracting companies for road construction andrehabilitation. The lesson on the OPRC method suggests that for such an approach to be attractive to construction companies, theworks should be bundled into lots, contractors should be trained on the method if it is new to the country, and guarantees need tobe provided to ensure payments for maintenance beyond the Projects life.Another lesson learnedconcerned procurement arrangements in a decentralized project, when resources are targeting activities in different administrativeunits. In such cases, allocating resources through competitive processes is more effective and efficient than earmarking funds foreach unit. Under such a competitive allocation principle, there is an additional incentive for administrative units (states incases of the CADP) to perform and implement activities without unnecessary delays.
P096707 | Guangdong Technical and Vocational Education and Training Project | East Asia and Pacific | China | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2009 | 2015 | 2016 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/911971467987909907/text/ICRR14858-P096707-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/911971467987909907/pdf/ICRR14858-P096707-Box394823B-PUBLIC.pdf | IEG has synthesized the lessons presented in the ICR (p. 23-24) to the following:Policy development is most effectively linked to school-level reform. The project front-loaded technical assistance and training to accelerate capacity development of teachers to develop new curricula, and then tied the buildings and equipment to the new courses that were developed. Linking these aspects, incentivized curriculum reform and ensured infrastructure improvement was not the aim.Exposure to international best practice can facilitate school reform. School administrators and teachers found the study tours pivotal to helping them understand CBT and student-centered techniques. These tours and other training were positive factors in enhancing implementation of CBT curricula. The sharing of experiences among project schools also helped increase teachersâ€™ commitment to the reform.
P096710 | Third Lao PDR Poverty Reduction Support Operation Grant | East Asia and Pacific | Lao People's Democratic Republic | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2008 | 2010 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/678141474592245398/text/000146597-20140619160800.txt | http://documents.worldbank.org/curated/en/678141474592245398/pdf/000146597-20140619160800.pdf | There are two major lessons which follow from the evaluation of this PRSO series.First, good ESW and TA are absolutely essential for reforms to succeed in a country with capacity constraints as severe as they are in Laos.Second, the efficacy of Bank and other donor interventions cannot be judged adequately in the absence of a minimum of basic data. The Bank should make a major effort to help strengthen the information and data base in the country.
P096711 | Second Programmatic Private Financial Sector Development | Europe and Central Asia | Serbia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2009 | 2010 | 2012 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/872231474854897739/text/000020051-20140624213637.txt | http://documents.worldbank.org/curated/en/872231474854897739/pdf/000020051-20140624213637.pdf | 1. Some flexibility in implementing programmatic lending is important if the Bank is to be able to adjust programs to meet needs as they appear, this case, due to changing world market conditions. PFSPDL II, in this case, was productively modified to help Serbia pro-actively reform its banking and financial sectors to address problems that could have arisen from the world financial crisis. 2. Good coordination remains an imperative. In this case, close coordination with the IMF and EU donors were key to insuring the resources needed for reform, as well as the incentive of EU membership.
P096745 | PK Punjab Barrages Improvement Phase II Project (PBIP-II) | South Asia | Pakistan | Blend | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2011 | 2017 | 2018 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/203351525040994680/text/Pakistan-PK-Punjab-Barrages-Improvement-II-Proj.txt | http://documents.worldbank.org/curated/en/203351525040994680/pdf/Pakistan-PK-Punjab-Barrages-Improvement-II-Proj.pdf | The ICR (p.26-27) includes lessons learned: Establishing an independent panel of experts to reviewdesigns and provide advice on implementation issues can be useful for project implementation. In this project anindependent panel of experts provided guidance on design, construction and safety issues through periodic consultations allowing totake timely corrective actions and ensuring quality. Ensuring implementationreadiness through a thorough preparation allows for a timely completion of project activities. In this project theproject preparation phase included detailed planning for the construction phase such as determination of location forcontractors camp site and development of a daily construction schedule. This detailed planning had a positive impacton addressing environmental and social issues adequately and avoiding delays in project implementation.
P096774 | Emergency Disabilities Project | Middle East and North Africa | Iraq | IBRD | FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2006 | 2011 | 2012 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/687601475083540419/text/000020051-20140625065033.txt | http://documents.worldbank.org/curated/en/687601475083540419/pdf/000020051-20140625065033.pdf | Security challenges and other contextual factors limiting normal supervision missions can be overcome, at least in part, through the employment of an fiduciary monitoring agency to monitor physical implementation of projects and verify that funds are spent for the purpose intended and in accordance with Bank rules and procedures.Allocating more time for thorough project preparation, even in an emergency situation, saves time during implementation. Speeding up the preparation process does not allow for developing essential aspects of some project details. A common result of accelerated preparation is implementation delays during the early years, particularly in countries that are not familiar with Bank requirements and procedures. A deliberate investment in careful preparation can actually result in faster and more effective implementation.Project design should aim not only for assumed best practice, but also for best fit to country conditions. This project was designed in 2005 based on similar projects financed by the Bank in other countries; however, Iraqâ€™s security situation and many years of isolation produced a starkly different context. At the design stage, it would have been appropriate to involve the client more fully in discussions and studies to identify the projectâ€™s essential and unique requirements.In fragile, post-conflict states, the design of emergency projects should be simple, manageable in scope, and suitable to the country context, and should include straightforward M&E arrangements. In such contexts, low institutional capacity and high staff turnover should be assumed.Planning should begin early for mainstreaming of project activities into regular ministry structures, even when the project is dealing with an emergency situation. A system should be established that will continue activity after the project has closed, one that can live within the constraints of ministry budgets. In this case, the project management team was disbanded even before project closing, and some day-to-day project functions have not been continued.
P096777 | Palestinian NGO Project III | Middle East and North Africa | West Bank and Gaza |  | FCS | Infrastructure | Urban, Resilience and Land | SPF | IPF | 2007 | 2012 | 2013 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/743791474665477376/text/000020051-20140625190606.txt | http://documents.worldbank.org/curated/en/743791474665477376/pdf/000020051-20140625190606.pdf | Lessons drawn by IEG:Sustainability of NGO services remains an issue, particularly as the follow-up Bank operation will provide substantially less financing and the political and security situation continues to be highly volatile.Continuous Bank engagement with the NGO sector through multiple projects has helped to sustain capacity strengthening efforts by building upon steps taken by previous projects.Lessons from ICR (page 20):The project's targeted approach was effective in providing "often the only means for reaching marginalized population groups and marginalized geographical areas without duplication of efforts of other organizations."
P096801 | Electricity Distribution Rehabilitation Project | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2007 | 2013 | 2015 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/151481475113009694/text/000012394-20150108104800.txt | http://documents.worldbank.org/curated/en/151481475113009694/pdf/000012394-20150108104800.pdf | The following lessons are drawn by IEG:Where there are clear signs, as in this case, that the Implementing Agencyâ€™s degree of commitment to the project and its goals is either lacking initially or likely to wane significantly during implementation, a review of the desirability of proceeding with the operation should be undertaken before Board presentation.If, despite lack of ownership by the implementing agency, the project nonetheless proceeds because the Government is initially committed to it, such engagement by the Government should be used to facilitate either the adoption of appropriate remedial actions to enhance implementation, or conversely the decision not to proceed further with the project if it were considered unlikely that Implementing Agency performance would improve. Proceeding with a public sector investment program already strongly supported by other external partners in a sector that is being privatized can lead to indifference or even to resistance on the part of the leading sector entity towards the Bank supported interventions. The following lessons are summarized from the ICR:Differences between the Bankâ€™s Procurement Guidelines and national laws and regulations can contribute to implementation delays and difficulties. In this case, there was confusion concerning the eligibility of a certain bidder, who was eligible according to Bank Guidelines, but not under Turkish law. An urban infrastructure project, especially one spread over a large geographical area, is likely to involve private land acquisition and affect those currently using public land, whatever assurances to the contrary may be given to the Bank at the preparation stage. Although, at the time this project was prepared, the Bankâ€™s approach did not require a prior triggering of the relevant safeguard (OP 4.12) in the absence of an identified need to acquire private land, it would nonetheless have been prudent to have prepared a Resettlement Policy in order to minimize risks of potential negative effects.
P096812 | Yunnan Urban Environment Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2009 | 2017 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/810021537799979631/text/China-CN-Yunnan-Urban-Env.txt | http://documents.worldbank.org/curated/en/810021537799979631/pdf/China-CN-Yunnan-Urban-Env.pdf | The lessons are adapted from the ICR with some modification of language: 1 . Ifrelevant income sources are overlooked in the calculation of projections, projections become skewed and this may negatively affectproject design and achievement. To ensure consistent projected returns, financial viability, and project success fromappraisal to close, utility cost recovery projections must rely on and take advantage of all income sources at disposal (such asgovernment subsidies).2 . Complex project designs with multiple objectives may lead to implementation delays andrestructurings. Overly complex designs with multiple objectives may lead to implementation delays and restructuring. Thiscan be avoided by dropping peripheral objectives (such as cultural heritage dialogue renewal in this project).3 .Institutionalization of inter-jurisdictional coordination may ensure and reinforce cooperation. Institutionalizingcooperation through inter-jurisdictional recurring meetings or through indicators may ensure and reinforce the institutionalcapacity underpinning inter-jurisdictional resource allocation, thereby fostering lasting, effective cooperation acrossjurisdictions.
P096823 | Delivery of Improved Local Services Project | Europe and Central Asia | Serbia | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2008 | 2015 | 2016 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/610921468144540847/text/ICRR-Disclosable-P096823-06-20-2016-1466465980784.txt | http://documents.worldbank.org/curated/en/610921468144540847/pdf/ICRR-Disclosable-P096823-06-20-2016-1466465980784.pdf | Lessons drawn from the ICR (page 22), adapted by IEG: The lack of a robust results framework, including a complexsingle objective statement and lack of measurable indicators, can pose a challenge to project management and assessment of projectachievements. A subsequent restructuring of the results framework clarified indicators according to each sector, which wasparticularly critical as the inter-sectoral coordination of activities did not take placeplanned. Aprojectsresults chainthat depends heavily upon passage of legislation as an early outputcan be tenuous, especially if the legislationdoes not materialize and then negatively impacts subsequent implementation ofactivities. The loss in momentum in converting to a per-pupil funding formula in the education sector led to shortcomings inimplementing the relevant activities. The disbursement schedule needs to take into account the nature of theactivitiesbeing financed and the time needed to implement those activities. The primary focus of early activities wastechnical assistance, which is slow-disbursing and supervision-intensive.
P096823 | Delivery of Improved Local Services Project | Europe and Central Asia | Serbia | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2008 | 2015 | 2018 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/577021533802173505/text/124854-PPAR-P096823-P090418-PUBLIC-Disclosed-8-9-18-Serbia-Local-Services-PPAR.txt | http://documents.worldbank.org/curated/en/577021533802173505/pdf/124854-PPAR-P096823-P090418-PUBLIC-Disclosed-8-9-18-Serbia-Local-Services-PPAR.pdf | 4. Lessons 4.1 Eight lessons that could help improve future World Bank operations are identified and presented below. The first lesson arises from both projects and is followed by three lessons from PARP and four lessons from the DILS. 4.2 Clarity around the overall vision and data architecture is needed for successful MIS investments. Several steps are needed to build an MIS\. analysis of the business processes, design of the data architecture, procurement of hardware and software, installation and testing, and training users. The likelihood of success in this process is improved if business processes and the underlying data architecture are well defined. This occurred in the development of CROSO. Even if the first step (the definition of the overall framework) took a long time, it permitted finalizing of the MIS after project completion. In contrast, the vision of the social assistance MIS was not well defined, which contributed to the failure of the MIS investment. PARP 4.3 A stakeholder analysis can be a useful to identify potential supporters and resistance when reforms involve several actors. The reform of the social contribution collection and reporting system involved several parties. A stakeholder analysis of the participating institutions would have yielded crucial insights to identify potential reasons for support and resistance, the areas where cooperation was natural, and where more attention was needed from high-level officials able to resolve institutional problems. 4.4 The tax administration can be usefully included in the administrative reform process. Many countries have to consider the role of the tax administration in collections and complianceâ€”should it be a lead agency, a participant, or a nonparticipant? Whatever the option chosen, it is important to involve the tax office early on, not only because of their mandated role as a tax collection agency but also because they tend to have the strongest human and technical capacity, and legal instruments of enforcement at their disposal, and they often have the strongest political support. In Serbia, CROSO was chosen for the collections function, but with some difficulty because insufficient attention was paid to coordinating with the tax authority. 4.5 Rationalizing the social insurance system takes time. In Serbian administrative reform, the country chose to rationalize the social insurance system information and contribution flows. Experience from other countries shows that this process may be slow, sometimes taking one to two years. Therefore, ample time should be reserved to do the work needed to alter budgets and to conduct strategic planning to accommodate institutional changes. The potentially most complex and time-consuming task will be to ensure all past service data are accurate and complete, and to modernize and automate the key benefit calculation and payment business processes. DILS 4.6 Multisector projects have the advantage of providing bridge financing that allows continuity and deepening of reforms policy, but this design feature may negatively affect other project ratings. DILS was effective in providing bridge financing that allowed the World Bank to sustain sector support and policy dialogue in three sectors. However, the wide scope of the project weakened the capacity of the M&E framework to monitor the complex causal chains between activities, intermediate outcomes, and objectives. In addition, this design feature may negatively affect other aspects of project design. 4.7 Activities carried out by entities with a clear institutional status can be better sustained than those implemented by ad-hoc bodies. DILS activities performed by permanent government institutions and bodies (such as the department of a ministry and permanent agencies such as the agencies for accreditation or Institute of Public Health) were better sustained after project completion than those undertaken by temporary entities such as ad-hoc committees created under the project. Another example is the PPB, which was expected to provide intersectoral coordination but met only sporadically. 4.8 The employment of contractual staff (consultants) in the project implementation unit does not build sustainable capacity in the ministries. DILS established a FSU and three Project Administration Teams in each of the three leading ministries to manage the project. These units were to last only for the duration of the project and were staffed with contractors. The alternative is to involve regular staff in the administration of the project, who would remain in the ministry at the end of the project. The latter solution can both improve buy-in in the ministries and help strengthen the capacity of the participating ministries. 4.9 Projects that aim at strengthening locally delivered services should ensure alignment between local functions, capacities, and financing to succeed. DILS showed that although the project could improve LSG capacity in service provision, it was not able to change the legal framework related to the competencies and financing of the LSGs. This misalignment explains the difficulties in implementing financing reform in the health and education sectors. 49 The two constituent republics functioned separately throughout the period of the federation, operating under separate economic policies, as well as using separate currencies. In a PAYGO pension plan, the contributions paid by workers are shared between the retirees. This contrasts with fully funded pension plans where the individual contributions are saved in a fund and blocked until retirement. Roma in Serbia amount to 147,604 (2.1 percent of the population) according to the 2011 census. Founding international partner organizations of the initiative consisted of the World Bank, the Open Society Institute, the United Nations Development Programme, the Council of Europe (CoE), CoE's Development Bank, the Organization for Security and Co-operation in Europe, the United Nations Human Settlements Programme, the Office of the United Nations High Commissioner for Refugees, the United Nations Children 's Fund, and the World Health Organization. Additional health financing and organizational reforms promoted in Serbia during DILS preparation, but not related to PHC and LSGs included the introduction of prospective payment system based on Diagnosis-Related Groups to finance the provision of hospital-based care; the provision of lower-cost (community-based) long-term care; and a more extensive use of outpatient surgeries. The implementation of capitation payments in PHC was also supported by the European Union with a â‚¬5 million project implemented over 2007â€“10. PISA is a reliable metric of student ability to perform successfully in economies where knowledge and skills are needed. Since PISA results are based on samples, it is not possible to report the exact rank order position, but the range of rank order positions within which the country mean lies with 95 percent likelihood. Official Gazette of the Republic of Serbia, 12/72/2009/09. Only Roma living in Roma settlements are covered by Serbia Multiple Indicator Cluster Surveys. Pedagogical assistants contribute to the learning and social participation of Roma pupils and establish cooperation between school staff and Roma parents (Starcevic, Dimitrijevic, and Milovanovic 2016). Within a few years Serbia had adopted The Law on Prohibition of Discrimination of Persons with Disability (April 2006), the 2006â€“2015 Strategy for Promoting Position of Persons with Disabilities (2017), and had ratified the United Nations Convention on the Rights of Persons with Disabilities (in July 2009). The ICR and ICR Review arranged the PDOs in the same manner. Specifically, the PIO needs information about the work history of the insured person to determine eligibility and calculate a pension. The NES uses the data on the status of insured persons (beginning and termination of insurance) for keeping records of the unemployed persons, as well as data on the total work engagement (years of service) of the insured person, data on the reason for termination of insurance and data on paid contributions, to determine eligibility and termination of the right to unemployment benefits. The HIF needs more current data, primarily confirmation of insurability and payment of insurance, to determine health rights. Reflecting the unqualified opinion of the auditors that project financial statements were accurate, complete, and produced in accordance with Generally Accepted Accounting Principles. The Law on the Central Registry of Compulsory Social Insurance was published in the Official Gazette No. 30/10 of May 7, 2010, and entered into force on the eighth day after the date of publication, on May 15, 2010. Eurostat requires member states and accession countries to report on indicators defined by the European Commission in the field of pension\. 11 primary indicators, 11 secondary indicators, and 5 context indicators grouped under the objectives of adequate, sustainable, and modernized pensions (SIPRU 2017, 5). First, it raised the retirement age for women to 65, equalizing it with that of men (with a gradual transition between 2015 and 2032); introduced actuarial reductions of 0.34 percent of the benefit per month of early retirement for both men and women; and tightened extended service requirements. Second, it precluded any increases in pensions before the system reaches a pension expenditure level of 11 percent of GDP. Third, pension benefits were temporarily reducedâ€”by 22 percent for pensions above RSD 25,000 per month and by 3 percent for those above RSD 40,000. The ICR review considered four distinct PDOs\. improve access to, efficiency, equity, and quality of local delivered health, education, and social protection services, in a decentralized environment. It is worth noting that all indicators measuring access to health, education, and social protection services measure improvement refer to vulnerable population groups, such as Roma, students with special needs, and people with disabilities (Indicators 1.3, 1.4, 1.5, 2.4, 2.5, and 2.10 in table B.2). The new payment method chosen for hospital-based services was based on Diagnosis-Related Groups. In the efficiency measurement literature, the allocative efficiency of a production unit is defined as the ratio of cost efficiency to technical efficiency (Fried, Lovell, and Schmidt 2008). The agency was created in 2008 as an independent government agency with responsibility for quality improvement and patient safety in health care institutions of Serbia, under the oversight of the Ministry of Health. The 2005 Health Care Law provides the legal framework for the agency. Its role was further defined by the bylaw on Accreditation of Health Care Institutions and by the National Strategy for Continuous Quality Improvement and Patient Safety (both approved in 2009). School improvement grants were adopted in the World Bankâ€“financed Education Improvement Project that was executed in Serbia from 2002 to 2007. They were assessed positively in empowering local communities to take responsibility for their schools (World Bank 2008). Previously, children with disabilities were entering the education system through the so-called categorization committees, which had been tasked with making a diagnosis and recommending a special educational program to correct the defect. The Rulebook on Additional Educational, Medical and Social Support to Children and Pupils, adopted on the basis of the 2009 Law on Fundamentals of the Education System, regulated the requirements for assessing the needs for additional educational, medical, or social support to children and pupils, and the composition and operation of the intersectoral committee responsible for the assessments. DILS support to capitation was complemented by the European Union that provided â‚¬5 million to finance the project Implementation of Capitation Payment in Primary Health Care in Serbia, that was implemented over 2007â€“ 2010 (Venekamp, Makarova, and McGreevy 2010). The OECD classification is as follows\. Category A â€“ children with disabilities; B â€“ children with learning difficulties; C â€“ children from socioeconomically vulnerable groups. Source\. Statistical Office of the Republic of Serbia. Source\. Dositej database. The last figure was provided by the MOESTD during the PPAR mission. The Grant Operations Manual was piloted through two projects\. sign interpreting service and companion services for persons with disabilities. The sign interpreting service received worldwide recognition as one of the best projects for persons with disabilities.
P096858 | Fourth Export Finance Intermediation Loan (EFIL IV) | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2008 | 2015 | 2016 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/888421473923907937/text/ICRR14937-P096858-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/888421473923907937/pdf/ICRR14937-P096858-Box396299B-PUBLIC.pdf | Drawing from the experience of this operation, the ICR offers six lessons, some of which challenge conventional wisdom and offer new perspectives. For example:Sector and regional targets or restrictions (for sub-loans of the PFIs) are unnecessary and could be counter-productive. This project shows that at times sectoral restrictions exacerbate the shortfall in loan demands, as with Eximbank's situation in 2009. After the restriction was lifted, Eximbank's performance improved.The World Bank's prudential standards tend to diminish its ability to reach smaller and under-served firms. For example, the requirements on sub-borrower's capital and leverage ratios are difficult for smaller firms to comply with. The project was able to relax some of the rules to reach smaller borrowers in under-served areas.
P096861 | Public Sector Reform TA | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2007 | 2012 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/976381475096667164/text/000020051-20140625184825.txt | http://documents.worldbank.org/curated/en/976381475096667164/pdf/000020051-20140625184825.pdf | The following lessons are taken from the ICR with some adaptation of language: Given the political sensitivity around public sector reform processes, a robust institutional arrangement that will ensure leadership and buy-in at the highest level is essential for carrying the program forward. Such an arrangement would strengthen the timely implementation of activities, and reinforce the sustainability of the reform process after project closure. There are large inherent risks, especially In challenging political contexts, in focusing Bank support on "prerequisites" and then relying on the Government to implement the reforms after project closure. In addition, IEG draws the following lessons:Without a considerable effort dedicated to strengthening the sustainability of the process by building up the buy-in of reforms in the government and implementing agencies, or stimulating public awareness and external support, it is unlikely that a reform process that may be politically divisive will be sustained. Restructuring projects by focusing on reducing the number of activities and concentrating efforts toward the full completion of a smaller number of them, rather than keeping the full scope and confining the support to the preparation phase, stands a better chance of achieving sustainable results.
P096920 | Ningxia Highway Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2015 | 2017 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/812411469821073732/text/ICRR-Disclosable-P096920-07-29-2016-1469821060034.txt | http://documents.worldbank.org/curated/en/812411469821073732/pdf/ICRR-Disclosable-P096920-07-29-2016-1469821060034.pdf | The ICR draws 7 lessons. IEG selected four main lessons and they, with editing, are as follows:(1) The Bankneeds to develop criteria to ensure that retroactively approved civil works, and works involving safeguards, satisfy Bankpolicies.(2) Public participation in rural roads can enhance the local ownership. Inthis project, the villagers became involved during construction and public consultations. Andlocal promotions of roadmaintenance also raised the residentsawarenessof protecting their roads. Some villages were alsoinnovativeand increased benefits more by using locally available material to good results.(3) Application oflocal experiencesto ecological protection can help in enhancing results. In the case of this project, at theexpresswaysection crossing Baijitan, extensive grass- squares were used to stabilize sands and slopes.Thistechnique has been practiced in the northwestern China steppe areas for several decades and has proved effective in controllingmobile sands.There also were other examples of ecological benefits from using the indigenous practices in construction andmaintenance of rural roads.(4) A collaboration between different agencies may be required to prevent theoverloadeding of trucks and damage tohighways.Overloading is a complex issue and cannot be solved alone by theroad agency. Ningxia already has a provincial government level leading group to address the issue beyond overloadmonitoring.In addition to building weighing stations more strategically, it would be useful to adopt the measures that havebeen applied successfully in other countries such as working with the trucking industry and with the industries having or leasingtruck fleets, lapse of insurance coverage in accidents of overweight vehicles, waybill payments only up the maximum allowableweight, tire and axle regulations and so on.
P096921 | National Program for Community Empowerment in Urban Areas (PNPM UPP) | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2008 | 2015 | 2016 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/545301468197982538/text/ICRR14905-ICRR-PUBLIC-P096921-Box396265B.txt | http://documents.worldbank.org/curated/en/545301468197982538/pdf/ICRR14905-ICRR-PUBLIC-P096921-Box396265B.pdf | Seven lessons are given in the ICR and the three most important are: 1. 1. Strong and sustainable support from the local government are important to urban CDD program. Financial incentives, intensive socialization and training of local government officials and their consultants are effective means to create a sustained interest from the local governments in supporting small-scale infrastructure projects for the communities. 2. Local government's support together with larger concentrated investments, improve the impact and effectiveness of small-scale of block grants in improving the accessibility of the urban poor to economic and social services3. The intensive use of ICT helps to maintain a high level of transparency in all aspects of the project cycle, and information disseminated effectively strengthened public confidence in the projectâ€™s openness and fairness.IEG draws two additional lessons: 4. Fundamental to the flourishing of Indonesiaâ€™s urban CDD program has been the communitiesâ€™ strong ownership built through transparency and good governance. The programâ€™s popularity is demonstrated by the peoplesâ€™ willingness to participate in the planning allocation of small grants for community development priorities, provide voluntary labor for the projects, and in some instances to freely give up parcels of land for the communal good. 5. Community participation is a necessary, but in itself an insufficient measure to ensure sustainability of improved infrastructure. Greater attention is needed to strengthen the technical capacity of communities to enable them to operate and maintain the facilities established and to harmonize planned new investments with appropriate maintenance programs and budgets. The facilitators can play a stronger role in stressing the importance of maintenance when Community Development Plans are drawn up.
P096923 | Shanghai Urban Environment (APL Phase III) | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2009 | 2017 | 2018 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/626131528751294374/text/China-CN-Shanghai-APL-III.txt | http://documents.worldbank.org/curated/en/626131528751294374/pdf/China-CN-Shanghai-APL-III.pdf | The IEG selected the following main lessons from the ICR, with some adaptation of language.(1) Long engagementwith the client in fast growing cities can be better accommodated by the use of an APL type instrument that provides gradual andincremental support to improving urban infrastructure. The experience of this project can be useful for African countrieswhere large scale urbanization is just starting.(2).Heavy initial investment focused ondeveloping a bold, long term vision, supported by policy frameworks, is useful for building an enabling environment. Theexperience of this project showed that for priority infrastructure investments, it would be useful to concentrate on a fewinvestments in one operation.(3). Financial covenants may not always be a good instrument for measuring financialsustainability. The experience of this project in Shanghai may not provide a proper picture of the financialsustainability of the stakeholders. In the case of this project, given the country-specific conditions, outcomes were satisfactory,despite the dropping of the financial covenants(such as full cost recovery and the government taking over all liabilitiesassociated with wastewater tariffs). Furthermore, for financial covenants to be effective, contractual penalty must be linked tonon-compliance with financial covenants.
P096925 | China Bengbu Integrated Environment Improvement Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2008 | 2015 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/646171489789625064/text/ICRR-Disclosable-P096925-03-17-2017-1489789617495.txt | http://documents.worldbank.org/curated/en/646171489789625064/pdf/ICRR-Disclosable-P096925-03-17-2017-1489789617495.pdf | The ICR draws the following main lessons from the experience of implementing this project.(1) Inter-Countycollaboration for wastewater treatment and collaboration between two jurisdictionscan contribute tocost-effective principles in planning, design and construction of public utilities.In the case of thisproject, unlike other places in China where Waste Water Treatment Plants (WWTPs) were being built in each county, HuaishangDistrict and Huaiyuan County reached a formal agreement to share the facilities of a preexisting WWTP. Before the pipelines werebuilt, Huaishang WWTP used only 32% of its full capacity. The wastewater conveyed from Huaishang WWTP enabled Huaishang to utilizeits spare capacity and at project closure Huaishang was operating 72% of its capacity.(2) Appropriate arrangementsshould be made at preparation to build indigenous capacity particularly when sophisticated systems are envisaged atappraisal. In the case of this project, during project preparation, the French government providedfinancing for aconsulting firm to provide key guidance on the methodology for the feasibility study, design approaches and principles for theflood and drainage component. One of the highlights of the design was introducing a computerized hydrodynamic model to assess floodrisks. However, given that little or no thought was given to strengthening capacity to use the model, this aspect of designcould not be utilized due to the lack of indigenous capacity.(3). Reforms relating to tariff policies needto be considered in the country context and should be addressed through policy dialogue. In the case of this project, oneof the financial covenants required the implementation of a cost recovery program to eliminate government subsidies for wastewaterservices through increased tariffs. The waste water tariff in Bengbu was not increased during the project implementation phase, asits pre-existing level was deemed to be fully consistent with government policy.
P096926 | Jiangsu Water and Wastewater | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2009 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/527931489674742016/text/ICRR-Disclosable-P096926-03-16-2017-1489674725863.txt | http://documents.worldbank.org/curated/en/527931489674742016/pdf/ICRR-Disclosable-P096926-03-16-2017-1489674725863.pdf | The ICR draws seven lessons and the three following are the most important:(1) Strong provincial leadership cancontribute to providing a supporting enabling environment and this can contribute to the success of a project. In the caseof this project, the provincial governments strategy and experienced staff contributed to achieving goodoutcomes.(2)Subsidies may be justified for social welfare and equityreasons.In China, it is common practice for municipal governments to set tariffs at levels that they consideraffordable and provide annual subsidies to water and wastewater companies in order to cover any revenue shortfalls.Untilagreement is reached with the governments on the appropriateness of such subsidies, it would be useful for individual projects tofocus on strengthening the capacities of utilities to operate efficiently and ensure that municipal governments confirm that theywould provide the required subsidies if the tariff levels are not raised to recover costs.(3) Well designed,targeted and focused Technical Assistance activities that is implemented in a timely manner can achieve goodresults. In the case of this project, the Provincial Project Management Office was well supported by technicalassistance, and this contributed to successful project implementation.
P096928 | Fourth Poverty Reduction Strategy Credit | Western and Central Africa | Benin | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2008 | 2013 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/344761474558359159/text/000020051-20140625225901.txt | http://documents.worldbank.org/curated/en/344761474558359159/pdf/000020051-20140625225901.pdf | The ICR draws a number of important and appropriate conclusions about defining realistic objectives and selecting results indicators that can be attributed to actions supported by the operation; and pursuing narrower, but deeper reforms, with more coherence across policy areas. (p. 52)Two lessons from this review are first, that linking the various triggers and prior actions more tightly to AAA, and to Benin's development challenges, explicitly defining objectives and expectations, and ensuring that accompanying measures would be undertaken could have improved outcomes, or at least strengthened the dialogue and monitoring.Second, while oversight during preparation of the various operations flagged potential problems, more explicit guidance from best practice findings would have been beneficial, for instance keeping the focus on a single sector in infrastructure, or maintaining a consistent dialogue in education and civil service reform throughout the series.
P096930 | Programmatic Development Policy Grant 2 | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2008 | 2011 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/849911474593042097/text/Tajikistan-Programmatic-Development-Policy-Grant.txt | http://documents.worldbank.org/curated/en/849911474593042097/pdf/Tajikistan-Programmatic-Development-Policy-Grant.pdf | There are several good lessons in the ICR, three of which stand out. First, a good understanding of the political economy of a country is basic for the program design to be realistic and the expected outcomes to be achievable.Second, a focus on results helps in creating government appreciation of and commitment to the program, because it helps direct the focus of the dialogue to a concrete discussion of how to best achieve the desired outcomes.Third, in an environment of low capacity, technical assistance to expedite implementation is essential.
P096931 | Tonga Transport Sector Consolidation Project | East Asia and Pacific | Tonga | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2009 | 2019 | 2020 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/174191568988888814/text/Tonga-TO-Transport-Sector-Consolidation.txt | http://documents.worldbank.org/curated/en/174191568988888814/pdf/Tonga-TO-Transport-Sector-Consolidation.pdf | The following are lessons from the ICR with adaptions in language based on the discussions with the taskteam: The promotion and use of local resources for road maintenance requiresadequate policies tomanage these resources. The project made it a priority to use and promote local resources. This included(i) thetraining and use of the domestic industry for road maintenance and quarry operations, (ii) the adaptionoftools to thelocal context, such asimple and practical road asset management system, and (iii) the use of local materials, suchasintroducing Otta seals which were most appropriate given local aggregate supplies. This created employment andbusiness opportunities, affordability of road maintenance, and improvement in accountability, transparency, environmental andsocial safeguards considerations.However, the policies to better manage these local resources still need to be established.For example, high-quality materials should be restricted for use in asphalt concrete for roads and cement concrete for buildingsand structures. In addition, there should be a regulation that encourages a more extensive use of Ottaseals. For countries exposed to frequent natural disasters, a zero-budget disaster recoverycontingency funds component can help mobilize resources for reconstruction quickly without delaying project implementation.Under this project, when Tropical Cyclone Ian devastated part of the country in 2014, the project had to be restructuredto broaden its geographical scope to carry out aviation investments in the affected areas. This delayed project implementation andthedisaster response. Similarly, for such countries, to incorporate climate resilience in civilworks and maintenance of roads is essential. During project implementation, the country was hit twice by cyclone. Thismade it evident that, given the climate risks Tonga faces, mitigation/adaptation measures should be considered to ensure theplanning and sustainability of civil works and maintenance services in the long term. Climate mitigation/adaptation were not aimedat when the project was prepared. Analytical work, technical studies, and additional audits can provideananchor forthe reform process and shield it from political interference and changes in leadership. When theMinisters changed, it frequently happened that the new Minster wanted to change the course of the reform. In such cases, additionalstudies or audits of the activities already carried out helped take advantage of the reform principles but realign the reformprocess. For instance, when the Minister wanted to return to in-house road maintenance, an additional study helped to convince himabout the advantage of outsourcing to the private sector. Focusing onrural roads should bebalanced with attention to urban roads needs. Most road investments under the project focused on rural roads, but withincreasing urban traffic and population expansion, it became clear that urban roadsplanning and maintenance need adequateattention, too. Areas where more work is likely neededare (i) physical investments for pedestrian mobility, includingsidewalks and safe crossings with many co-benefits linked to climate change, disability and health, and(ii) the drainage ofroads in urban areas. Surface flooding (including over footpaths) because of blocked drainagewas an issue.This area ofwork would require clear division of roles and responsibilities between the central level and the municipalitylevel. Training and strong Bank support are needed in low capacity countries, especially if theimplementation agencies are not familiar with Bank rules and procedures. In this case, the misprocurement under a contractbid by Tonga Airport Limited was caused by their lack of familiarity with Bank rules and procedures. More training right from thebeginning, the support from an experienced procurement specialist, and more hand holding by the Bank team might have avoidedit.
P096962 | Punjab-Irrigation Sector Development Policy Loan | South Asia | Pakistan | Blend | Non-FCS | Sustainable Development | Water | IBRD | DPF | 2006 | 2007 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/772761474943713060/text/000020051-20140626075327.txt | http://documents.worldbank.org/curated/en/772761474943713060/pdf/000020051-20140626075327.pdf | The following lessons are adapted from the ICR: Keep DPLs simple: This lesson was specifically learnt from the implementation of the National Drainage Program and was applied to the DPL Program. The Program was simple and had one main implementation agency (the Irrigation and Power Department) which made its implementation easy. The the program was strategically designed to engage the highest decision-making officials through an Inter-Departmental Reforms Steering Committee which provided oversight and guided decision-making as well as their quick implementation.Any program that generates demand can be considered a success: The institutional architecture that evolved under the Program provided a strong base for farmersâ€™ participation and decentralization of irrigation management responsibilities. A well-designed communication plan ensured that all stakeholders â€“ especially farmers â€“ are aware of the steps being taken through the reforms. This not only created the demand for transparency in information sharing, it also challenged the government agency to keep pace with increased demand for timely and accurate information.Institutional change needs time to take roots: The short lifespan of the DPL series was designed for quick outcomes in setting forth the reforms processes. However, the expected pace of implementation on some policy areas could not be sustained by the new Farmer Organizations and their governance arrangements that needed time to mature. It was expected that this lacunae would be addressed through follow-up investment programming built on the lessons learned.
P096965 | La Guajira Water & Sanitation Infrastructure and Service Management Project | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2007 | 2018 | 2019 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/884261555959116119/text/Colombia-La-Guajira-Water-and-Sanit.txt | http://documents.worldbank.org/curated/en/884261555959116119/pdf/Colombia-La-Guajira-Water-and-Sanit.pdf | 1. A complex project environment requires flexibility and strategic planning. The project was implemented in apolitically sensitive region. The political environment had changed almost continuously throughout the project life. This requiredthe project team to respond quickly to these swift changes. The Bank was successful in managing such fluctuations through (i)adapting inputs of rural components; (ii) incorporation of a new Government policy and plan; and (iii) continuous dialogue with theCentral Government and the concerned authorities. However, the Banks flexibility had an impact on the efficiency of theproject. Numerous extensions of the project delayed the timing of service delivery. The project at a later stage established a moreeffective ME system, which enabled the Bank and the client to strategically identify the key issues associated withtheproject.2. Leveraging a convening power of the Bank is an effectiveinstrumentfor coping with the changing political environment. In a politically sensitiveenvironment, there are typically multiple levels of stakeholders. An accurate understanding of the perspectives of each level isessential to bringing about intended results. The Banks multi-layered approach in the project was effective in this regard.The Country Manager was regularly involved with the missions in La Guajira and held monthly breakfasts with key stakeholders fromthe central to local level. The task team and the CMU were actively engaged with project supervision over the last two years ofproject life, which included monthly supervision missions to identify key actions and any associated events. Since timelyinformation from reliable sources contributes to project course correction, the Bank should leverage its convening power to copewith changing political and implementation challenges.3. Capacity constraints should be diagnosedand unlocked to deliver results. The project encountered capacity constraints from the very beginning. The lack ofthe PIUs capacity led the Bank to outsource the function to a third party, which was replaced later in accordance with theincreasing demand by the local communicates to deliver rapid results. The replaced PIU performed relatively well, however theprolonged delay prompted the Bank to have to closely supervise the implementation. This required an iterative process to diagnoseand discover an entry point to improve institutional performance. When dealing with capacity constraints, the constraints need tobe disentangled (decomposing the elements of capacity) and finding a strategic entry point to improve performance.
P096993 | Agricultural Investments and Services Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2008 | 2013 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/680651475113168705/text/000012394-20150310080403.txt | http://documents.worldbank.org/curated/en/680651475113168705/pdf/000012394-20150310080403.pdf | The ICR provided lessons, but some were actually conclusions. Two lessons were:A sound and experienced implementation agency is of crucial importance for the successful mobilization of project stakeholders and the smooth coordination of multiple donors. An appropriate legal framework is necessary for the sustained and successful implementation of a community-based development program. This Review would add the following lessons from this project:The necessity of a clear and measurable project objective without repeated amendments and a logical results framework that shows (a) the results chain from project effectiveness through intermediate outcomes to the project objectives; and (b) the main activities and institutions which support the results chain.For complex pilot projects adequate funding is required for successful and accountable implementation, especially when results are expected to be gleaned from participatory monitoring and evaluation.
P096998 | Customs Development Project | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2008 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/441661479715870299/text/1478543061712-0000A8056-ICRR-Disclosable-P096998-11-07-2016-1478543046702.txt | http://documents.worldbank.org/curated/en/441661479715870299/pdf/1478543061712-0000A8056-ICRR-Disclosable-P096998-11-07-2016-1478543046702.pdf | The IEG concurs with the lessons drawn by the ICR (ICR p. 29), with some minoradaptations: When the CMU managessignificant ICT investments the role of an on-board, dedicated ICT Project Manager may be critical, in addition to therelevant ICT and procurement experts. In this case, the project design overestimated the CMUs capacity to manage ICTprocurement. The revision of the monitoring and evaluation (ME) arrangements during aproject lifecycle is critical to diminish the chances that the PDO and/or intermediate indicators become irrelevant, and to addother pertinent ones, keeping a plausible connection between project components and activities on the one hand, and the ME onthe other. In the case of the CDP, the logical chain between PDO, components and activities was correct, but there was almostno direct connection between the PDO and the ME arrangements made it almost impossible to prove the contribution of thisproject to the achievements in the indicators. The assessment against various scenarios of thefeasibility of mobilizing counterpart funds, when planned in projects financing, is a crucial element of the project design. Inthis case, the counterpart original planned financing was really significant, covering almost 70 percent of the project, but themacroeconomic risks were underestimated and a sudden change in the economic context (the dramatic decline of oil prices) led to alack of counterpart financing of CDP. When the project design ensures that different levels ofgovernment are involved in the policy-making process throughout its implementation, it is easier to deal with requiredinstitutional reforms and legislative requirements to support the reforms. In the case of CDP, many of the recommendations providedby consultants through the activities of Components 1 and 2 required formal legislation or high level Executive approval, but therigid legislative environment in Kazakhstan and the lack of priority assigned by the Government to institutional developmentmatters, CCC first, and SRC later, granted little room to achieve major successes in this field. Afifth lesson should be added: Frequent changes and high turnover in Project Implementation Unit leadership andstaff leads to slow project implementation and the loss of institutional memory, hampering timely decision making. This is whathappened in CDP, with negative effects on project management.
P097026 | Nigeria Public Sector Governance Reform and Development Project | Western and Central Africa | Nigeria | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2010 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/791301542810307849/text/Nigeria-NG-State-Gov-CB-TAL-2-FY10.txt | http://documents.worldbank.org/curated/en/791301542810307849/pdf/Nigeria-NG-State-Gov-CB-TAL-2-FY10.pdf | The ICR pages 79) draws the following fourlessons from the experience ofimplementing this project.(1) A realistic assessment of federal and state level ownershipof ambitious institutional reforms projects is essential at design. In the case of this project, the commitment of someparticipating states remained weak. This in conjunction with the weak capacity of the National Project Implementation Unitcontributed to delays during implementation.(2) Project implementation timelines need to matchimplementation capacity. This is particularly so where reforms are difficult or involve design and installation ofInformation Communication Technology (ICT) such as the Integrated Financial Management InformationSystems.(3) In federal countries, when supporting implementation of reforms at the statelevel, it would be desirable to give appropriate autonomy to state implementation entities. In this project, there weredelays instate-level implementation, due to the failure of coordination arrangements at the federallevel.(4) In designing operations intended to be implemented by states in federal countries, it isdesirable to haveclear and predictable criteria for selecting participating states. This would helpin addressing issues relating to capacity and commitment variations across states and entities.IEGdraws the following lesson.(1) A robust theory of change requires a clear causal chainbetween project activities and expected outcomes, as well as indicators which enable progress in meeting objectives to be measured.In this case, there were nooutcome indicators suitable for monitoring performance with respect to the objective ofimproving the quality of public finance and Human Resource Managementsystems.
P097030 | AF: Civil Service Reform Project | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2007 | 2012 | 2012 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/166031474487432990/text/000020051-20140625111430.txt | http://documents.worldbank.org/curated/en/166031474487432990/pdf/000020051-20140625111430.pdf | The lessons from the ICR are all supported. The need for greater flexibility in making changes for projects in difficult contexts is of particular importance. Such changes may be needed to address, inter alia, loss of key counterparts, and rising insecurity that can affect project performance. For example, some amount of funds for technical assistance, say 20 percent, could be held back for contingencies. Likewise, contracts with consulting firms could specify only 80 percent of the work in TORs, saving the remainder to be adjusted based on evolving needs. Furthermore, such contracts should have provisions to ease adjustment when projects are restructured. It is important to calibrate carefully the ambition level to the realities on the ground. Public Administration Reform is a long term effort. Results frameworks should be ambitious, but not unrealistic. Bank teams should use political economy analysis, in depth consultation, and realism in calibrating initially less contentious reforms that can help build coalitions and gradually gain momentum and monitoring mechanisms, and leading to more difficult reforms at a later stage. Another lesson is that project designs should include as implementing agencies the key principal agencies needed. In the case of pay and grading reforms, this includes both the Ministry of Finance, to handle the financial implications, and the civil service authority to manage the HR side.
P097036 | Orissa Socio-Economic Development Loan/Credit II | South Asia | India | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2007 | 2008 | 2010 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/799491474652573745/text/000146597-20140619163146.txt | http://documents.worldbank.org/curated/en/799491474652573745/pdf/000146597-20140619163146.pdf | 1. Results can be achieved even in the low-capacity environment of a poor and lagging state, through persistent work, establishment of close working relationships and trust with the client, and laying strong analytical foundations through state-level ESW. Early engagement with the authorities allows for the development of technocratic ownership and capacity to match political ownership. 2. State level fiscal reform can be a robust entry point for a larger sub-national engagement in federal states. Success, however, requires a robust intergovernmental fiscal framework supported by the central government authorities. 3. Direct and broad engagement with states in large federal countries like India has few other alternatives as an important modality to deliver development assistance, be it lending or analytical products. 4. Early analysis of the governance and fiduciary issues within sectors is key to determining the feasibility and likely impact of actions supported by a DPL series. Failure to analyze the political economy of reforms can undermine selectivity.
P097104 | BERMUTU-Better Education through Reformed Management and Universal Teacher Upgrading | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2008 | 2014 | 2015 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/356761475115544843/text/000020051-20150113011615.txt | http://documents.worldbank.org/curated/en/356761475115544843/pdf/000020051-20150113011615.pdf | Lessons drawn by IEG:Rigorous project preparation, including prior analytic work and project readiness activities, can help ensure successful project implementation. In the case of this project, prior analytic work ensured the technical soundness of the project design and numerous documents were prepared prior to effectiveness to support project readiness.Effective policy dialogue, based on rigorous analytic work and evidence from ongoing assessments, can be a key support to project achievements. In the case of this project, policy dialogue helped to strengthen the working relationship with the government and evidence from the real-time assessments of specific project activities was shared with the government and helped to inform decision-making processes.
P097141 | OECS (LC) Skills for Inclusive Growth | Latin America and Caribbean | St. Lucia | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2007 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/413441475080513269/text/000020051-20140626130512.txt | http://documents.worldbank.org/curated/en/413441475080513269/pdf/000020051-20140626130512.pdf | The ICR presents some interesting lessons, that have been adapted by the IEG as follows:It is possible to measure employability of graduates without conducting a randomized control trial. While not done in this project, the experience from other countries shows that training institutions can conduct tracer surveys of their graduates to assess employment and wage data. The PAD (p. 12) envisaged a tracer study to identify the impact of the investment. In addition, employer surveys provide information on satisfaction with training and how it affects employability. Several life factors affect dropout rates that are beyond control of trainers. When training institutes receive an output based payment per graduate, factors they cannot influence should be considered in the payment formula. Also, if vulnerable youth are the target groups for training, adding a social worker or counselor may be helpful for youth and trainers, to keep them in training and enter employment In this case, there were only 5 counselors, which was not enough for more than 1,000 trainees (ICR p. 33). Administrative workload for internships can pose obstacles. In this case, employers complained about the excessive administrative work which was complex and time consuming for employers and training providers. Administrative complexity creates extra cost that can be prevented.The IEG youth employment evaluation has highlighted the need for cross-sector collaboration. In this case, collaboration between different teams that work on education and job creation in different sectors would have been useful to bring together more effectively the demand and supply side.
P097159 | FINANCE AND GROWTH Development Policy Loan | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2006 | 2006 | 2009 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/253071474496880901/text/000020051-20140619111812.txt | http://documents.worldbank.org/curated/en/253071474496880901/pdf/000020051-20140619111812.pdf | IEG concurs with the lessons drawn in the ICR. While other factors cited in the ICR (e.g., the utility of programmatic approaches, the Bankâ€™s cross country experience) were undoubtedly important, in this case, the Governmentâ€™s clear vision, commitment, and unquestioned leadership role with regard to the content of the reform agenda and the Bankâ€™s understanding of its supportive but subsidiary (to the Government) role in this were the critical factors in the overall satisfactory outcome. The ICR also makes an important technical point concerning behavioral responses to reforms in capital markets, namely, that market-acceptance of new instruments and new policies is context dependent, and may be very slow in some countries due to â€œintrinsic differencesâ€ in market actorsâ€™ perceptions and values. Parenthetically, these behavioral barriers to diversification, access, and so forth that are reflected to some extent in Mexico, may in part be responsible for the relative success Mexico has had, to date, in coping with the international financial crisis.
P097181 | Nutrition Enhancement Program II | Western and Central Africa | Senegal | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2007 | 2014 | 2015 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/526131467993503742/text/ICRR14725-P097181-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/526131467993503742/pdf/ICRR14725-P097181-Box393183B-PUBLIC.pdf | The ICR (p. 28) identifies several valuable lessons, including:In vulnerable situations, it is critical to also take desirable longer term outcomes (in this case, households being less vulnerable to external shocks) into account in order to increase the sustainability of project outcomes. This project transitioned from improving nutrition intake to providing households with better mechanisms to deal with food insecurity through fostering the development of over 1,300 backyard gardens in the intervention areas. Combining nutrition related activities with activities for other areas such as malaria prevention or maternal health can take advantage of synergies between the different interventions and lead to better results.
P097181 | Nutrition Enhancement Program II | Western and Central Africa | Senegal | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2007 | 2014 | 2017 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/314151497365405800/text/110290-FR-PPAR-P070541-P097181-P115938-PUBLIC.txt | http://documents.worldbank.org/curated/en/314151497365405800/pdf/110290-FR-PPAR-P070541-P097181-P115938-PUBLIC.pdf | 6. Lessons Â· These three projects demonstrate that formidable results can be achieved within the time frame of a four-year project. Phase I was highly successful in establishing a new innovative program, a strong capacity for its successful management and 61 implementation, and tangible results in the intervention areas. The three projects together also demonstrate that capacity and institution building is a medium-term, incremental process. The gradual decentralization of program oversight, the evolving roles and involvement of local governments, CEAs, and other sectors could not have happened all at once. The time invested is well worth the quality of this program's mature design and capacity. Â· Cross-sectoral coordination and teamwork coalesce around shared objectives. A truly multisectoral approach cannot be achieved solely through an organigram or sectoral work plans with resource allocations. Rather, a shared objective and sense of mandate and accountability to contribute to that objective light the way. This applies to local and central levels alike. Â· A management style that supports an evidence-based, participatory learning culture will culminate in strong ownership of the program and the continual improvement of its performance and effectiveness. The evidence base of the program has been strong and continues to grow with new evidence about sector wide coverage and support of other partners. There is scope for the further enhancement of evidence and learning by prioritizing and supporting research. Senegal has untapped technical capacity in nutrition that could be exploited. Â· Senegal's nutrition policy and program have attracted many partners, both national and international, but inadequate coordination of this financial and technical support has undermined its overall effectiveness. Considerable scope exists for enhancing the aid effectiveness of nutrition interventions by preparing and brokering a fully costed, prioritized multiyear program with a fully developed inventory of available financing and technical support. Â· The measurement of coverage is complex but critical to assess program efficacy. It was difficult to reconcile the robust outcomes in the intervention areas with modest trends at the national level, in the absence of detailed data on program coverage. It is not enough to measure geographical coverage. Even program coverage by target group (for example, children under age five years) does not provide sufficient detail. The REACH survey is a landmark in the program's capacity to define and assess coverage by specific intervention and by specific age group. 63
P097201 | AFCC2/RI-Regional and Domestic Power Markets Development Project (Southern Africa Power Market Project: APL-1b) | Other | Africa |  |  | Infrastructure | Energy & Extractives | IDA | IPF | 2007 | 2018 | 2020 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/494331585859852244/text/Africa-Reg-Domestic-Pwr-Mkt-Dev-FY07.txt | http://documents.worldbank.org/curated/en/494331585859852244/pdf/Africa-Reg-Domestic-Pwr-Mkt-Dev-FY07.pdf | IEG derives the following lesson, drawn from the ICR: Attempting to address multiple objectives in a megaprojectin a fragile environment with limited technical capacity is likely to lead to implementation difficulties: Thislarge-scaleproject (over $800 million, after the Additional Financing) included multiple objectives and components. The two keyobjectives of meeting regional demand as well as domestic demand for energy were mostly at conflict with one another, leading tothe non-achievement of one objective and less-than-optimal achievement of the other. Performance in achieving the overarchingobjective of improved efficiency and governance was also modest, with implementation taking over a decade. A disaggregation of theproject into a series of smaller operations, with more focused objectives and more in keeping with the limited technical capacityof national counterparts, designed within an overall electricity reform framework, might conceivably have produced better outcomesand more timely implementation. In the design of investment projects aimed at rehabilitatingelectricity infrastructure, detailed feasibility studies need to be undertaken during preparation, to minimize costoverruns: Much of the overruns in cost and implementation delays that took place on account of contract modificationsand procurement problems could be attributed to an absence of knowledge regarding the extent and real costs of repair andrehabilitation of critical equipment. For rehabilitation projects, it is essential to carry out detailed feasibility studies duringproject preparation, to better determine the scope and associated cost and timeline of the rehabilitation work.
P097271 | Accelerated Electricity Access (Rural) Expansion | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2006 | 2013 | 2014 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/276411475099831532/text/000020051-20140626120831.txt | http://documents.worldbank.org/curated/en/276411475099831532/pdf/000020051-20140626120831.pdf | The following lessons that have broad applicability are derived from the ICR, with some paraphrasing in this ICR Review:(1) The identification of all risks and mitigation measures is critical at the project preparation stage. The risk of delays in the supplying hydropower plants was not considered and mitigation measures were not agreed at the outset, thus leading to much time lost in implementation when the delays did materialize.(2) Win-win solutions for both the Government and the Bank need to be identified, in order to resolve differences and avoid a stalemate. The scaling-up of the CFL distribution activities allowed the Bank to continue supporting the project while helping EEPCo reduce its peak load requirements.(3) Institutional capacity needs to be adequately strengthened to match expected growth in electricity consumption. EEPCo's inability to adapt and reach a level of capacity that that is commensurate to its increased business has led to inefficiency in billing and collection, as well as a failure to close its accounts on time.(4) The ownership of technical assistance and M&E needs to be anchored solidly with the country clients, to avoid jeopardizing the sustainability of project development outcomes.One final lesson specific to Ethiopia is that for future projects, the Bank needs to stress the value of maintaining independent, external engineering supervision.
P097292 | Malawi Emergency Recovery Loan | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2006 | 2007 | 2008 | ICRR | >=25 million & <50 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | High | http://documents.worldbank.org/curated/en/762171474903804382/text/000020051-20140618061024.txt | http://documents.worldbank.org/curated/en/762171474903804382/pdf/000020051-20140618061024.pdf | Simpler is better. Key decisions (a) to pursue a resource transfer objective via a separate, dedicated operation instead of piggybacking on the existing Fiscal Management and Accelerating Growth (FIMAG) adjustment operation or other operations, (b) to stick to a single clear objective, to adopt a streamlined positive list, and(c) to tailor documentation requirements and procedures to the ability of Malawi's systems to deliver were key design factors contributing to the success of this operation. The ICR correctly notes that the positive list of imports played no essential role in the outcome of this operation, and that documentation requirements in effect created unnecessary paper flow - although in this case, not burdensome to the point that it negatively affected the implementation of the project. The ICR also correctly notes that drought is a foreseeable risk to the development of Malawi's economy, and that - as suggested in IEG's recent CAE, CASCR Review, and evaluation of Bank assistance for Natural Disasters - this needs to be addressed strategically through a combination of structural measures to reduce or mitigate vulnerability, macroeconomic management tailored (e.g., through foreign exchange reserve management policy) to co-insure against external shocks, development of other insurance schemes, as well as emergency external support when the foregoing are insufficient.
P097325 | Uganda Ninth Poverty Reduction Support Credit | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2013 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/659111475118027824/text/000012394-20150312070957.txt | http://documents.worldbank.org/curated/en/659111475118027824/pdf/000012394-20150312070957.pdf | IEG draws the following lessons from the review of the program.The experience of PRSCs 8 and 9 shows that paying more attention at what the program is trying to achieve is likely to lead to a more careful and realistic formulation of the results framework, making it easier to monitor and measure results. In countries known for their weak governance, such as Uganda, programs of budget support need to take into consideration issues of corruption and accountability in their design to improve their performance and their execution. The experience of Uganda indicates that the government was ready to deal with issues of corruption when the problems surfaced; it also indicates that dropping actions aimed at confronting corruption, as it happened in PRSC 9, may send conflicting signals about the Bankâ€™s stand on it, thereby weakening the governmentâ€™s commitment to carry out the actions agreed to.
P097325 | Uganda Ninth Poverty Reduction Support Credit | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2013 | 2015 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/942871468188377758/text/Uganda-Fifth-Ninth-Poverty-Reduction-Support-Credit-Project.txt | http://documents.worldbank.org/curated/en/942871468188377758/pdf/96202-PPAR-P090881-P090219-P101231-P101232-P097325-Box385353B-OUO-9-IDA-SecM2015-0150.pdf | Lessons Several lessons emerge from this assessment of PRSC5-7 series. They relate to the design, implementation, and proactivity and learning. Â· Lack of clear, concrete objectives impedes both implementation and evaluation of DPOs. General statements of broad support of government policies (as in PRSC5- 7) are best avoided. Â· Design of DPOs and implementation can be adversely affected by lack of focus and selectivity in policy areas. Â· Inadequate accounting of political economy factors in the design of major reforms can adversely affect the design, implementation and outcomes of DPOs. Lack of focus on domestic revenue mobilization is a prime example. Â· Pressures to extend budget support within the broader, coordinated donor support framework without hard conditionality to raise domestic revenues can undermine incentives for domestic revenue mobilization. This, in turn, can undercut macroeconomic adjustment needed for sustainable fiscal policy as well as the adequacy of funding for basic services. Â· Implementation and evaluation are frequently undermined when objectives are not tightly linked to prior actions and there is no measurable and relevant results framework, when outcome indicators are ambiguous, and when targets do not incorporate an explicit and convincing theory of change.
P097329 | Public Sector Capacity Building | South Asia | Sri Lanka | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2008 | 2014 | 2015 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/902171468001177270/text/ICRR14664-P097329-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/902171468001177270/pdf/ICRR14664-P097329-Box393183B-PUBLIC.pdf | The ICR (pp. 22-24) identifies several valuable lessons, including the following:The Implementing Agenciesâ€™ leadership is critical for the successful implementation of a project and should be addressed by the Bank accordingly. In this project, the two Implementing Agencies performed differently despite being in the same operating environment. This was mainly due to AGDâ€™s strong leadership and ability to retain staff. It would have been useful if the Bank had assessed the leadership abilities of the Implementing Agencies during project preparation and tailored capacity building efforts and supervision accordingly. Discussions with a range of stakeholders to choose appropriate performance indicators will ensure that indicators are measurable and realistic and will be owned by all different parties. In this project, many of the indicators were not clearly defined, lacked baseline values, and/or were not measurable leading to M&E challenges.
P097402 | Pakistan: Second Partnership for Polio Eradication Project | South Asia | Pakistan | Blend | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2006 | 2008 | 2009 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/279371474595788293/text/000020051-20140619105429.txt | http://documents.worldbank.org/curated/en/279371474595788293/pdf/000020051-20140619105429.pdf | The lessons below complement the lessons listed in the ICR: Successful polio elimination requires intensified Supplemental Immunization Activities as well as a strong routine immunization program. The project experience showed that polio re-emerged in previously polio-free areas in part because the routine immunization program did not maintain the minimum level of routine immunization coverage to prevent new outbreaks in the face of migration of cases from polio reservoir areas.The buy-down mechanism is a successful vehicle for creating incentives for governments to invest in communicable disease control. As remarked by the Borrower (ICR, p26), it provided the necessary results-orientation and momentum for the implementation of the other parts of the overall Polio Eradication Initiative.The choice of indicators should take into account the availability of the necessary infrastructure to realistically meet the KPI. The lack of refrigeration in district-level facilities made the 5 day requirement (as the cut-off for timely arrival of vaccines) inappropriate and modification of the KPI to 3-5 days seems more reasonable.
P097471 | Pakistan NWFP Development Policy Credit Two | South Asia | Pakistan | Blend | Non-FCS | Human Development | Education | IDA | DPF | 2007 | 2008 | 2011 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/665381474565843573/text/Pakistan-NWFP-First-Development-Policy-Credit.txt | http://documents.worldbank.org/curated/en/665381474565843573/pdf/Pakistan-NWFP-First-Development-Policy-Credit.pdf | The ICR contains an important lesson: Consideration should be given to allowing more than 10 prior conditions for DPCs. For example, if it is known that supervision will be difficult (due to, for example, security concerns), both the Borrower and the Bank may see benefits in shifting some part of what would in other circumstances be implementation to prior conditions. The ICR also suggests that a large number of secondary conditions may be where circumstances suggest that implementation may be difficult. However, IEG recommends that in cases where government capacity suggests that implementation may be challenging, it may be useful to specify the proposed program and reforms in greater detail, including the monitoring and evaluation framework. However, care should be taken not to impose a large number of conditions. In addition, this review notes the synergy in having multi-sector reforms encompassed in one operation rather than distributed among several sector operations, especially with a government which has limited capacity.
P097535 | ID Community Recovery Through the KDP | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2006 | 2010 | 2011 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/176001475083475195/text/000020051-20140624170325.txt | http://documents.worldbank.org/curated/en/176001475083475195/pdf/000020051-20140624170325.pdf | The ICR offers a number of lessons, although this review believes there were a number of potential lessons unexplored. The most important of the ICR lessons, with some adaptations and additions, are the following and the last lesson is added by IEG:An ongoing project with established processes, structures and staff is a promising means for rapid and effective response in a disaster situation. However, when using an established project approach it is still important to make the processes more flexible to fit the emergency situation. Greater fiduciary risks have to be taken in emergency situations.Training is particularly important in disaster response situations. The urgency of the situation should not blind planners and implementers to the need for training which will inevitably take time away from immediate response.In an emergency response situation it can be assumed that there will be great competition between agencies for skilled staff and between contractors and the public sector for essential materials, the latter in short supply partly due to increased demand and partly due to transport problems. With Bank support the borrower needs early on to develop some ground rules to optimize the distribution of such resources.In a disaster response situation effective communication with communities and stakeholders is particularly important and can be enhanced by the use of information facilitators. In the design of M&E and in the ex post evaluation of a disaster response project it is important to attempt to answer the obvious question of the extent to which the affected people were able to regain their prior standard of living.
P097604 | UY Institutions Building TAL | Latin America and Caribbean | Uruguay | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2007 | 2017 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/966701522937325849/text/Uruguay-UY-Institutions-Building-TAL.txt | http://documents.worldbank.org/curated/en/966701522937325849/pdf/Uruguay-UY-Institutions-Building-TAL.pdf | This review supports the following ICR lessons, with some revisions to the wording (ICR,pp.20-21): Institutional strengthening projects in broad areas can be successful withinthe right context of small countries with a high level of political commitment and implementation capacity, translated into strongexisting coordination mechanisms. IBTAL was successfully implemented because of the Governments high level ofcommitment and clear identification of needed reforms, as well as high capacity implementing entities, fostered in part bythe significant stability of the civil service, and pre-existing natural coordination mechanisms between entities. The IBTALprovided high value added on substantive areas of institutional strengthening with the Governments broader reform agenda andits complementarities. IBTAL demonstrates that even small loans can bring important support to reformprograms. Contemplating space for a more flexible approach to some activities withinproject design allows inevitable adjustments in reform trajectories. The flexibility created within each of the maincomponents allowed for mid-course adjustments to activities to align them with the natural evolution of institutional strengtheningreforms over the multi-year course of implementation without necessarily requiring a formalrestructuring. The Bank needs to give more emphasis to sharing innovative reformpractices with other high-capacity countries in the region. For example, this project could have benefited from more suchknowledge sharing; likewise, the successful implementation of innovations in tax administration and social protection systemsthrough the SISCA and SIIAS, which received international awards, would provide useful lessons to other upper-middle income LACcountries. By correctly sequencing a series of reforms, greater support formore challenging issues can be generated. The Governments decision to initiate work on a fiscal riskmanagement system within the institutionally stronger BPS was very strategic. The successful implementation of the SISCA toevaluate fiscal risk associated with the new personal income tax allowed for the lessons learned from that experience to be appliedto the subsequent development of a similar model for application to all the other taxes.IEGprovidesone additional lesson: Results frameworks with clear and plausible resultchains can be helpful to effectively monitor project implementation and assess project impact. The complex resultsframework of IBTAL with some weakness in the causal chain made it more difficult than necessary to monitorprogress.
P097605 | ID SPADA in Aceh and Nias | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2007 | 2012 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/802321473921122011/text/ICRR14920-P097605-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/802321473921122011/pdf/ICRR14920-P097605-Box396299B-PUBLIC.pdf | The following lessons can be drawn from this project: - Despite the well prepared M&E plans and Results Framework, the M&E component was not implemented. M&E is extra challenging in post-disaster situations and would need specific incentives to ensure its implementation. - M&E and reporting becomes extra challenging in participatory planning processes, as the planning and implementation of the projects are removed from the donor. Situations like these require that the donor provides clear requests and clear incentives for M&E reporting with a minimum set of standards.
P097635 | Lignite Power Technical Assistance Project | Europe and Central Asia | Kosovo | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2007 | 2012 | 2014 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/668721474648832513/text/000020051-20140625233143.txt | http://documents.worldbank.org/curated/en/668721474648832513/pdf/000020051-20140625233143.pdf | The ICR has made a commendable effort at deriving lessons from this project experience. The lessons relate to project design and implementation in a politically complex and economically challenging situation; coordination with donors with their own agendas; effective supervision with strong sector expertise; rethinking on the Bankâ€™s own sector policies; and mid-stream changes in Bank procurement rules. Based on the ICR, and this review, the following lessons are drawn:Flexibility, and commitment to the projectâ€™s long term objectives, are key for the Bank in a politically complex and dynamic situation in which the other principal actors - the government, donors â€“ are not able to chart a consistent path towards the projectâ€™s outputs and outcomes. In this project, the Bank worked with the Government and donors in matters relating to changes in project design and procurement, while providing objective advice and adhering to procurement norms. Again in a complex project situation, the Bank should supplement its team with the best available sectoral and transaction-related expertise to improve the credibility and acceptability of its advice. In this project, other major donors, like European Agency for Reconstruction and KfW, had a substantial energy sector presence on the ground, and USAID had contracted for technical advisors in the Ministry of Energy and Mining and the Ministry of Economy and Finance while fielding a seasoned energy professional on its own staff. A similar World Bank presence could have ensured earlier and stronger agreement between the donor institutions and alerted the Bank on a continuous basis to any emerging obstacles during project implementation.
P097671 | SB Health Sector Support Project (TA) | East Asia and Pacific | Solomon Islands | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2008 | 2012 | 2013 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/937141475071753380/text/Solomon-Islands-Health-Sector-Support-Project.txt | http://documents.worldbank.org/curated/en/937141475071753380/pdf/Solomon-Islands-Health-Sector-Support-Project.pdf | Based on the findings of this review, it is important for a project that has as one of its objectives to improve performance monitoring to ensure that the proper monitoring systems are in place prior to, or very early on in, the project period. In the case of this project, the shortcomings in the MIS could not be overcome once the project became effective and thus the project activities intended on taking the monitoring "to the next level" could not be implemented and led to shortcomings in achieving the objective.According to the ICR lessons (page 18), this relatively small but high risk project was worth the high transaction costs because the Bank was able to add value across core domains in the sector. This work on core domains was then leveraged throughout the entire health sector, including in preparing the new health sector strategy and improving planning and budgeting systems.
P097818 | Rw: Sustainable Energy Development Project (GEF) | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2010 | 2015 | 2016 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/491561468197983655/text/ICRR14914-ICRR-PUBLIC-P097818-Box396265B.txt | http://documents.worldbank.org/curated/en/491561468197983655/pdf/ICRR14914-ICRR-PUBLIC-P097818-Box396265B.pdf | The ICR provided useful lessons that are well grounded in the project's implementation experience. These are paraphrased below:Government leadership and focus on results is paramount to achieving the expected impacts from technical assistance. For example, the Rwandan Government acted upon the recommendations or studies done under the project, such as the renewable energy feed-in tariff, light-handed regulations, and standardized Power Purchase Agreements (PPAs). These actions have greatly reduced the transactions cost for micro hydro developers by shortening the time required to negotiate PPAs and having prior information about the price of the generated energy.Realism is needed when funding from multiple donors and co-financiers is involved in a project. Projects with multiple sources of financing need to be structured such that the different administrative procedures governing funding are fully taken into account, optimized, and leveraged in a manner that minimizes the risks of mismatching funding with project activities. The AFREA funds, for example, could have been considered as parallel financing instead of co-financing, given the risk that any non-extension of the AFREA Trust Fund could have negatively impacted the implementation of the co-financed GEF activities. An Incubation Program is a useful approach to build the local capacity of private companies. An entrepreneur incubator can help in developing business plans and feasibility studies, as well as train local technicians and trainers. This could be instrumental equipping small and medium start-up companies with the basic framework to understand the RE business, and take advantage of local skills. Using public resources in awareness-raising and promotion campaigns is a key tool in promoting increased uptake of new products, especially those offered by small and medium businesses. The use of improved cooking stoves, for example, can have a huge impact, but in most cases the end-users may not be aware of such products. Project complexity and the number of activities need to be well balanced with the targeted project impacts. Operations that target policy and institutional development need to be addressed in an integrated manner, as the lack of one intervention or wrong sequencing could hinder the achievement of the intended outcome. Realism is also needed with regard to what the project and other complementary operations can directly influence.
P097921 | Malaria Control Booster Project | Western and Central Africa | Nigeria | Blend | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2007 | 2015 | 2017 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/706551475866886057/text/ICRR-Disclosable-P097921-10-07-2016-1475866869155.txt | http://documents.worldbank.org/curated/en/706551475866886057/pdf/ICRR-Disclosable-P097921-10-07-2016-1475866869155.pdf | From the ICR:Flexibility and ability to respond to changing environment. Given the paceof research and development of new knowledge about diseases and their management, projects that assist countries in disease controlmust be capable of responding to innovative and current changes to strategies. In this case, the project quickly and promptlyunderwent additional financing to assist Nigeria in enhancing its activities in support of the NMCP and in a reallocation of fundsin order to provide universal access to LLINs. This allowed the country to be at the forefront ofmanagingmalaria.Utilizing a comprehensive Malaria Plus approach. Although mostmalaria projects are single-disease vertical projects, the MCBP employed a Malaria Plus approach that situated malaria within theoverall maternal and child health landscape. This clearly pushed the Bank and the government at both levels to engage broadly andseek ways to strengthen the delivery of a comprehensive package of services, moving beyond the immediate boundaries of justmalaria.Utilizingsurveys to understand implementation performance. Qualityassurance sampling (LQAS) survey, HFA survey, and malaria indicator surveys were strong and credible survey methods that providedimplementation information for timely management decision making. Incorporating these into the Projects monitoring systemwas key in driving the wider Bank health portfolio to invest in ME measures forfollow-on Projects such s Saving OneMillion Lives.Enhanced coordination between the Federal Government and the States. Becauseof the distinct roles that the Federal and the States had in ensuring the Projects success, it was critical to ensure acoordinated effort and unity between the two. Among other things for example, greater involvement and feedback from the States atthe beginning might have resulted in more rapidly and smoothly incorporating PIFs into the Project. This would have preventeddelays and boosted implementation from the outset as had been anticipated in the design. Also, the MCBP managed the lack of humanresource and technical capacity at both levels of government, including across different States, by seconding Federal staff to theState project implementation units and with contracts to experts who could quickly bring in skills at both levels and provideinstitutional training.
P097962 | Multidonor Rehabilitation Education Project | Eastern and Southern Africa | South Sudan | IDA | FCS | Human Development | Education | RETF | IPF | 2006 | 2013 | 2014 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/256831474566613897/text/000020051-20140626112541.txt | http://documents.worldbank.org/curated/en/256831474566613897/pdf/000020051-20140626112541.pdf | The following lessons are adapted from the ICR (pp. 24-25):A comprehensive MDTF approach across sectors can facilitate more successful preparation and implementation. Many issues are similar across projects and sectors, related to state-building and the development of government systems. Failure to coordinate across projects may amount to unnecessary reinvention of the wheel.Tension between the need for rapid preparation of a project and readiness for implementation should not always be resolved in favor of the former. This project would have benefited from a more rigorous assessment of readiness for implementation, realism of targets, and time frame. As capacity building is a slow process, particularly in a post-conflict environment and with a newly emerging state, unrealistically high expectations should be avoided. Furthermore, if essential full-time qualified staff (financial management procurement, M&E, and safeguards) are in place from effectiveness, delays are less likely. Overall, challenges and delays from moving toward implementation too quickly can generally be avoided through a more patient, deliberative preparation process.The following additional lesson is offered by IEG:Lack of clarity in a project's statement of objectives can undermine its results focus and design, even in the best of circumstances. But this potential confusion can be especially damaging for project relevance, efficacy, and efficiency in a country such as South Sudan, both a brand new country and a post-conflict country. In this case, an opportunity was missed (both at design and at restructuring) for introducing more clarity of design and objectives.
P097974 | Multisectoral Water and Electricity Infrastructure Project | Eastern and Southern Africa | Burundi | IDA | FCS | Sustainable Development | Water | IDA | IPF | 2008 | 2013 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/979761475116552095/text/000012394-20150109095600.txt | http://documents.worldbank.org/curated/en/979761475116552095/pdf/000012394-20150109095600.pdf | The first three lessons are taken from the ICR with some adaptation of language, the fourth is drawn by IEG: Field-based key staff members are critical in fragile and post-conflict countries: The Bank provided strong support to this project through field-based presence of key team members, who continuously convened other external partners in the two sectors and coordinated interventions. There was good collaboration between these partners, REGIDESO, and the Government throughout project implementation.Well-prepared performance contracting can be a sound approach: Having a contract with clearly specified performance criteria known by management and staff was instrumental in improving the performance of REGIDESO. The establishment of an internal control unit contributed to the good results. To have the full effect, however, management evaluation and motivation could have been tied to the performance contract, and audit results could have been published to assure transparency and oversight by the public as part of the reform element.Specific attention to procurement is needed when the Borrower has a small market for international suppliers: Few suppliers and contractors participated in tenders and some replacement parts for HV and MV stations had to be custom-made. These difficulties need to be factored into project design. Attention could advantageously be paid to packaging procurement of goods and works to increase contract amounts and incorporating ongoing maintenance beyond the project period if needed. This would be accompanied by appropriate training for the staff involved. For infrastructure projects, an appropriate balance between construction and institutional strengthening has to be maintained. In this case the key objective of boosting the technical capacity of key institutions was, to a degree, sacrificed to infrastructure.
P097975 | Multi-sector Infrastructure Rehabilitation Project | Western and Central Africa | Guinea-Bissau | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2006 | 2014 | 2015 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/824581467992458949/text/ICRR14759-P097975-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/824581467992458949/pdf/ICRR14759-P097975-Box393191B-PUBLIC.pdf | The following two lessons from the ICR are given here with some adaptation by IEG.The willingness of the private sector to invest in fragile states can be expected to be limited and should be realistically assessed in project design. While private sector investments are needed in fragile states, a realistic analysis of the willingness of the private sector to get involved in such a context should be conducted. A high level dialogue with the interested private sector entities would help identify the issues in such scenarios and possible measures that could be adopted to mitigate the risk.M&E design should be simple in a weak institutional setting. Realistic and measurable core indicators that directly link to the project activities could be primarily tested out in the early phases of implementation. Any difficulties noted in gathering reliable data on these indicators could then be quickly addressed. Broad indicators should be avoided since they may be difficult to interpret. In the case of this project, indicators were not linked to the project led activities alone, but relied on activities to be achieved by the PRSDO, EEWRD, and the BOAD operations, which though interrelated proved difficult to monitor. Given the difficulties in gathering reliable data right from the start, it would have been desirable for the Bank team to pro-actively address this issue early in implementation.
P097985 | Integrated Coastal Zone Management | South Asia | India | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2010 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/404141622855878378/text/India-IN-Integrated-Coastal-Zone-Mgmt-Project.txt | http://documents.worldbank.org/curated/en/404141622855878378/pdf/India-IN-Integrated-Coastal-Zone-Mgmt-Project.pdf | The ICR (p. 31-32) included the following lessons learned: Adopting a flexible and participatory approachis critical when the development issues are multi-sectoral and require cooperation from several stakeholders at different levels.This project was flexible and innovative when attracting private-sector interest through the implementation of state-levelICZM demonstration investments. While the project funded the approximately US$ 10.6 million of the Jamnagar sewage treatment plant,the risk of financing was assumed by the operator for the 15-year duration as part of the Design-Build-Operate-Transfer (DBOT)contract. For ensuring system-wide and policy-level changes it is critical for development projects and programsto provide sufficient resources and allow for engagement, support and collaboration with and between decision-makers, technicalexperts and civil society. This project was able to generate scientific knowledge to support the development of policiesand the planning, designing, implementing and managing of project activities and foster engagement and collaboration betweendifferent stakeholders. An integrated approach, with a regional and comprehensive outlook that goes beyondadministrative boundaries, agencies or sector is critical for ensuring overall development and sustainability. Thisproject demonstrated that sustainable, scientific management of coastal resources can increase the income of localcommunities and businesses.
P098031 | Second Multi-sectoral HIV/AIDS Project | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2007 | 2012 | 2013 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/435191475096746697/text/000020051-20140625190337.txt | http://documents.worldbank.org/curated/en/435191475096746697/pdf/000020051-20140625190337.pdf | These lessons are taken from the ICR, with adaptation:Ensuring harmonization of development partners requires agreement to adopt shared processes and systems, moving beyond â€œconsensus rhetoric.â€ In this case, differences among donor M as a result, smaller projects (such as this one) received insufficient attention.A heterogeneous, diversified, and evolving epidemic requires detailed and regularly updated information to guide interventions, as well as persistent follow-up to implement recommendations that follow from ongoing studies. In this case, epidemiological reports called attention to the identification of high-risk groups and the need to focus prevention interventions on these groups, resulting in appropriate targeting.
P098052 | Integrating Environment and Forest Protection into the Recovery and Future Development of Aceh | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | RETF | IPF | 2006 | 2013 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/227151474555958417/text/000020051-20140626112807.txt | http://documents.worldbank.org/curated/en/227151474555958417/pdf/000020051-20140626112807.pdf | The ICR presents several useful lessons as follows (the first one slightly modified by IEG). IEG adds a fifth: 1. In environment-focused projects with a forest protection element, even where there is effective community protection, Government action is essential, especially for law enforcement and prosecution.2. Demonstrating how conservation and protection activities directly benefit communities is more effective than rhetoric alone.3. Conservation work, especially in a post-disaster context, needs to take the need for jobs and livelihoods into account, both for economic and local political reasons. 4. An environmental project, such as the present one, can effectively leverage resources for its stakeholder communities and vulnerable groups such as the poor and women.5. The statement of the PDO in the legal agreements should fully reflect actual project objectives and content. A more specific lesson from this particular case is that, given the longer-term effective protection and sustainable management needs of the two forests in question, greater attention could have been given to: (i) supporting and strengthening the pertinent public sector policies and institutions with responsibilities over these issues; and to, (ii) measures to enhance the longer-term sustainable protection and management of these forests since they will continue to be threatened, especially once the current logging moratorium is lifted.
P098078 | Huai River Basin Flood Management and Drainage Improvement | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2011 | 2017 | 2018 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/767861504805762204/text/ICRR-Disclosable-P098078-09-07-2017-1504805750781.txt | http://documents.worldbank.org/curated/en/767861504805762204/pdf/ICRR-Disclosable-P098078-09-07-2017-1504805750781.pdf | The ICR points out five lessons (ICR, paragraphs 89-93) condensed below: Identifying skills gaps duringprojectpreparation and targeting capacity building effortstoacquireappropriate skill sets prior to projectapproval strengthen project implementation. This approach may include customizing a Management Information System(MIS) thatuses near real-time monitoring to help in day to day monitoring and critical follow up to overcome obstacles. In addition, anindependent agencymay betasked to strictly monitor safeguards compliance and freePMOs to focus on core projectmanagement and project coordination needs. Community participation helps build stronger ownership andiscrucial to optimizing project impacts by helping to target appropriate project sites. For example, consulted famers showedincreased commitment to pay water charges that generated revenues for regular OM. In another case, participants helped locatebridges thatwould benefit children from poorer communities, whichimproved their access toschools. DelegatingOM to a self-selected, self-managed association can help sustain infrastructureinvestments. For example, Farmer Drainage and Irrigation Associations managed specific pumping stations(based onhydraulic, not administrative boundaries), determined their own water pricing model, collected water fees, and dedicated OMresources from these fees and charges with continuous local government guidance, training, and technology support.
P098093 | Productive Safety Nets APL II | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2007 | 2010 | 2012 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/354271474630922387/text/000020051-20140624194647.txt | http://documents.worldbank.org/curated/en/354271474630922387/pdf/000020051-20140624194647.pdf | The lessons from the PSNP are many and have been published in a separate document "Designing and Implementing a Rural Safety Net in a Low-Income Setting". Some of the most important lessons from the APL II are:Up-front financing is necessary for safety nets to truly be â€˜scalableâ€™ in responding when crises hit. With the international food price hikes and drought in 2008, the DRF mechanism had already put resources in place up front which resulted in a quick response which protected the incomes and assets of households. Putting in place ex-ante contingent financing was an innovation of APL II and indeed for the safety net experience internationally and created the ability to respond swiftly to crisis. The pace of graduation from a safety net needs to be set against a realistic assessment of overall economic trends and conditions. Graduation cannot be expected to result only from the safety net and needs to be viewed with an understanding of the multiple paths out of poverty.Cash and food transfers can be combined successfully in a safety net as long as there is flexibility. Despite PSNPâ€™s â€˜cash firstâ€™ principle, the food price spikes during APL II caused erosion in the basic purchasing power of the cash transfer. PSNP switched to a mixture of cash and food which helped respond to beneficiary preferences and stabilize the protective benefits of the basic transfers.
P098118 | Sustainable Development of Natural Resources | South Asia | Afghanistan | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2006 | 2013 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/643431468190184141/text/ICRR14642-P098118-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/643431468190184141/pdf/ICRR14642-P098118-Box393183B-PUBLIC.pdf | The ICR provides the following key lessons: Â· Project Design: The SDNRP project illustrates the advantages of keeping project design simple when operating in a fragile post-conflict country environment, with a complex environment, limited capacity and weak country implementation record. At the same time, environmental and social safeguards are important to improving governance and transparency, in the effort to attract new investment.Â· Team Staffing and Supervision: The constitution of the Bank team and frequency of missions is critical to overall implementation of such projects. The inclusion of an experienced mining specialist and social and environmental expert from the Bank, plus increased frequency of supervision missions (every 6-10 weeks) can be crucial to enabling a project to respond effectively to meet the challenges relating to such resources as a major mineral deposit, especially regarding environmental and social protection.Â· Procurement Capacity: Building implementation capacity in procurement calls for deep capacity building within the PMU of procurement processes, procedures and planning. There is a need for experienced international staff to train national staff, working side-by-side in the PMU. The progress made in a first project, can enable follow-on projects to begin a process of introducing computerized procurement management systems and migrating procurement functions of the PMU into the Ministry.Â· Inter-Ministerial Coordination: The involvement of a range of Ministries (and Ministers) on a range of issues, such as land acquisition compensation and consultation, means that there is a need for efficient coordination, if implementation is to proceed smoothly. Independent Verification: The establishment (and success) of an International Advisory Panel (IAP) to provide high quality review of transactions demonstrates the role that independent experts and agencies can play in verifying that transactions procedures have been properly followed and that transactions have taken place in a transparent and non-corrupt manner.
P098129 | Third Poverty Reduction Strategy Grant | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2008 | 2009 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/860021474632363039/text/000020051-20140619090256.txt | http://documents.worldbank.org/curated/en/860021474632363039/pdf/000020051-20140619090256.pdf | The ICR contains good lessons from the experience with DPLs in Rwanda, three of which stand out.General budget support can be much more effective than individual projects in promoting better resource allocation among and within sectors as well as in promoting appropriate sector strategies and policy reform.Continuous dialogue and continuity in Bank teams are essential for success.Coordination and harmonization with other donors and their policies is greatly enhanced by joint analytical work.
P098132 | Tourism Development | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2009 | 2016 | 2017 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/233421475270588742/text/ICRR-Disclosable-P098132-09-30-2016-1475270566523.txt | http://documents.worldbank.org/curated/en/233421475270588742/pdf/Ethiopia-ET-Tourism-Develop-Project-SIL.pdf | The five lessons are drawn from the ICR (page 25), with some adaptation.One, to achieve a sustainable outcome, itis important that a tourism project encourage private participation and crowd-in private investment. Thecommunity involvementactivitysupported the establishment of 54 new business ventures in Addis Ababa, Axum and Lalibela. The matching grant schemedisbursed US$2.1 million to 79 participant firms in the hotel, restaurant, tour operator, tourism promotion and marketing, andhandicraft businesses for purposes of product and service improvement, business systems improvement, marketing, and training.Two, integrating community development into tourism development can foster pro-poor growth. Thecommunityinvolvement activitydisbursed US$1.1 million for the training of participants in the tourism industry to enhance their rolesas employees, suppliers and business operators in the industry. The matching grant scheme also provided training to employees offirms participating in the scheme. Some 1,608 permanent jobs in Addis Ababa, Axum and Lalibela were created from the implementationof the two sub-projects. Approximately 1,490 employees benefitted from training activities.Three, where resettlementis indicated, it is vital that there be broad coordination in planning and implementing the resettlement with stakeholders at thecommunity, regional and national levels. An independent audit found the resettlement of displaced residents of the project site inLalibela to have been successful because of the active participation of the community members and of the local administrationsapart from the national government. The resettlement neighborhood was developed with the necessary infrastructure and the communitymembers were provided with livelihood and job opportunities.Four, the Bank should carefully consider theGovernments capacity for project implementation as early as during the project preparation stage. The scale and scope, aswell as the timeline, of a project should be well aligned with the implementing agencies capacity for operations management,procurement, contract management, financial management, environmental and social safeguards compliance, and staff recruitment.Where necessary, the Bank should consider front-loading the training of government staff, embedding experts in projectimplementation units, and more rigorously supervising the weaker aspects of project implementation.And five, outcomeattribution is inherently difficult in a tourism project because the natural choice for a project outcome --- the increase intourist volume --- can be the result of many factors, other than the project activity.
P098146 | Public Procurement Reform Project II | South Asia | Bangladesh | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2008 | 2017 | 2018 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/166581524751306692/text/Bangladesh-BD-Public-Procurement-Reform-Project-II.txt | http://documents.worldbank.org/curated/en/166581524751306692/pdf/Bangladesh-BD-Public-Procurement-Reform-Project-II.pdf | The following lessons are drawn from the ICR:Challenges and enabling conditions for sustainablereform. Enabling conditions for sustainable reform are not straightforward, especially when influenced by factorssuch as vested interests, and corrupt practices. In such circumstances, facilitating factors can be understanding of thecountrys operating context and political economy; recognition ofthe Governments role as a driver for reform andidentification of a political leader to manage reform; andworking with reform-minded public officials at core ministries andimplementing agencies, and influential stakeholders outside government.Commitment and ownership.Successful and sustainable procurement reforms require on-going high-level commitment and ownership on the part of keystakeholders. And it also requires ownership on the part of mid-level public officials in key agencies. In thisparticular case, progress was also facilitated by a young and computer-literate environment. As e-GP became popular at fieldlevel, as it reduced rampant bid-rigging, appreciation also started growing at higher levels.Sustainableinstitutional mechanism. Having an in-built institutional mechanism within the Government framework, can make reformmore sustainable in the long term. An example is the CPTU it is fully funded by the Government, as opposed to afree-standing implementation unit supported by project funds.Continuity of engagement. Therelatively slow process of procurement reform required sustained engagement by the Government as the lead agent, along with otherstakeholders including the development partners, to bring about desired changes in institutions and systems.
P098151 | Clean Air and Sustainable Environment Project | South Asia | Bangladesh | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2009 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/279431590064346685/text/Bangladesh-BD-Clean-Air-Sustainable-Environment.txt | http://documents.worldbank.org/curated/en/279431590064346685/pdf/Bangladesh-BD-Clean-Air-Sustainable-Environment.pdf | The following lessons are taken from the ICR with some modification of language:Air quality managementoperations require an integrated cross-sectoral approach. The project design focused on two major air polluting sources(brick kilns and transport sector) and institutional coordination between environment and transport departments and local municipalcorporation. While this approach did encounter some challenges during implementation, the overall performance and results of theproject indicate that such an integrated cross sectoral approach is critical for sustainable air quality managementinterventions.A combination of policy, institutional and demonstration investments are critical for buildingcapacity and awareness on Air Quality Management. Lack of technical capacity, weak regulatory framework and limited orunreliable data are the most common challenges faced in the development and implementation of air quality management plans acrossdeveloping countries. The project tried to address these challenges by combining analytical work such as source apportionmentstudies, capacity building activities, improving the regulatory framework and demonstrating investments for air qualityimprovement.Long-term project sustainability depends on proper project design. The operational capacityof stakeholders, partners and governmental authorities responsible for the project deliverablesand/or those assumingownership and enforcementmust be assessed with the view to ensure long term impact, functionalityandmaintenance.Well-developed ME systems and appropriate level of data collection are essential forefficient project implementation. The borrowers ME system for projects must be developed in the early stagesof the project life cycle, such as at appraisal or preparation. Adequate resources are necessary for productive ME functionand capacity for collection of these adequate baseline data is collected at the start of the project. Such preparation facilitatesthe developmentof appropriate results indicators and sufficient data to ensure the results framework can capture theco-benefits of the project for a more complete understanding of resource efficiency and programmatic impact.
P098217 | Education System Realignment & Strengthening Program (APL #2) | Europe and Central Asia | Georgia | IBRD | FCS | Human Development | Education | IDA | IPF | 2007 | 2012 | 2013 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/574401475097716050/text/000020051-20140625155009.txt | http://documents.worldbank.org/curated/en/574401475097716050/pdf/000020051-20140625155009.pdf | While the ICR (p. 27-28) reported several lessons, the overarching lesson that it derived was:Education reform in countries with declining student demographics need to understand and account for these changes while still attending to quality and efficiency in the system. When school consolidation is proposed, Bank staff need to have adequate understanding of local political issues in order to gain support from stakeholders, design reasonable solutions, and avoid damaging the interests of specific groups.Another important lesson drawn by IEG is that government hiring of project implementation staff can result in significant capacity strengthening for government ministries. In this case, the absorption of PCU staff into the Ministry of Education enabled the ministry to execute the project smoothly and oversee all of its responsibilities.
P098248 | Adaptation to the Impact of Rapid Glacier Retreat in the Tropical Andes | Latin America and Caribbean | Andean Countries |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2008 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/808221467993502519/text/ICRR14683-P098248-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/808221467993502519/pdf/ICRR14683-P098248-Box393183B-PUBLIC.pdf | The ICR listed a number of lessons, although some of them were conclusions rather than generally applicable lessons. The following is a summary of the most significant lessons in the ICR.The ability of countries to increase their long term resilience to climate change is directly linked to their capacity to generate and analyze data to assess vulnerability to future events. Therefore robust, well managed and well funded institutions with appropriate analytical capacity are crucial for relevant adaptation to climate change.Legal agreements for projects should allow for flexibility in implementation arrangements so as to avoid the need for subsidiary agreements if modest changes are required for those arrangements during implementation. Project legal agreements should therefore provide for operational flexibility.This Review suggests another lesson, namely:A technically qualified and experienced project implementing agency is critical for a project's success. The choice of implementing agency for this project was not appropriate because SGCAN (even with the support of a PIU) and despite its sound credentials as a regional organization, did not have the institutional capacity to provide the vision and leadership on technically complex environmental issues.
P098256 | Afghanistan: Horticulture and Livestock Productivity Project | South Asia | Afghanistan | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2006 | 2013 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/101101475070818646/text/Afghanistan-Horticulture-And-Livestock-Productivity-Project.txt | http://documents.worldbank.org/curated/en/101101475070818646/pdf/000020051-20140626114924.pdf | The Implementation Completion Report offers a number of lessons of which the following are the most important (with some reformulation of language)::Project design as an emergency operation should be carefully weighed. Projects that require longer term sectoral improvement and institutional capacity building should be designed as regular operations with extensive background work. A clear identification of, and consultation with, project stakeholders, mapping of skills gaps/needs, and coordination with other donor funded projects in the country are all essential for such operations. The quick preparation needs of emergency operations limit this important preparatory work. Heavy dependence on the Facilitating Partner model can be high-cost and a potentially low-return approach prone to problems; however if it is implemented well it can be valuable in countries where institutional capacity is limited. Facilitating partners and especially foreign expertise should be used to build capacity. TORs for such support should be clearly defined and agreed with the implementing agency, and advance procurement action taken so that TA teams are mobilized by project effectiveness. International Technical Assistance should be selective, temporary and for pre-identified technical issues, and with priority for local capacity building. The transfer of core technical and operational functions to trained nationals and sector agencies should be carried out at the earliest opportunity.In post-conflict, â€œemergencyâ€ environments and for reconstruction efforts, establishing the foundation for transition from emergency recovery to medium to long term reconstruction and development is important. If productive activities with long lead/maturation times extending beyond project completion are essential, the expected phasing of activities and appropriate indicators for each phase should be established.
P098273 | Local Governance Support Project | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2006 | 2012 | 2015 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/422601475093011606/text/000012394-20150409075911.txt | http://documents.worldbank.org/curated/en/422601475093011606/pdf/000012394-20150409075911.pdf | The ICR provides five lessons and two most important are: Using an incremental approach can be useful for decentralization programs. Phasing block grant disbursements provided a good opportunity for â€œlearning-by-doingâ€ and ensured that the formulas used for allocating the block grants were appropriate prior to the scaling-up of the program. Arrangements for project management are an important part of project design. There is a trade-off between a dedicated Project Management Unit and attempting to mainstream project management into regular government processes. This project and experiences elsewhere have shown that weak capacity is an issue at the central as well as at the local level, and since projects of this type are intended to address these capacity gaps, mainstreaming the project management function is consistent with the larger agenda of institutional strengthening. However, great care has to be taken at appraisal to ensure that government staff have the willingness and capacity to multi-task, and the time to do it.
P098299 | MX Competitiveness DPL | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2006 | 2007 | 2010 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory |  | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/537001474632016516/text/000146597-20140619153401.txt | http://documents.worldbank.org/curated/en/537001474632016516/pdf/000146597-20140619153401.pdf | An economy gains competitiveness when its real costs of producing goods and services fall. When the Bank supports a program that seeks to improve competitiveness and neglects to point out the reductions in costs arising from the program, a flaw might be present in the diagnosis of the problem, the design of the program, or the indicators selected to evaluate impact. Adopting procedural conditions is unlikely to lead to visible and immediate outcomes, but they do not preclude thinking about desirable medium or long-term outcomes that could help strengthen the design of the project. The prior actions in the electricity sector exemplify this situation, whereby setting a pre-determined goal for the sector might have helped evaluate the potential effectiveness of prior conditions.
P098328 | Social Protection Project | Latin America and Caribbean | Panama | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2008 | 2015 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/787091468000888368/text/ICRR14768-P098328-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/787091468000888368/pdf/ICRR14768-P098328-Box393191B-PUBLIC.pdf | The ICR (p. 24) identifies several valuable lessons, including the following:When designing a Results Framework, it is critical that the availability of data and feasibility of collecting currently unavailable data are taken into account. In this project, the Results Framework included a large number of indicators, and monitoring of most of these was dependent on the development and implementation of a well-functioning MIS. Since the MIS had significant shortcomings, several indicators could not be tracked, and progress towards PDO achievement could not consistently be measured. When developing and implementing an MIS, it is important that the implementing agency has the necessary capacity to operate the system and that the MIS be modifiable if circumstances change. In this project, the MIS could not be adapted due to technical and legal restrictions by the vendor, which limited the possibility to adapt the MIS to the needs of the RO.
P098328 | Social Protection Project | Latin America and Caribbean | Panama | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2008 | 2015 | 2018 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/340911499270013440/text/110617-PPAR-P098328-P106445-PUBLIC.txt | http://documents.worldbank.org/curated/en/340911499270013440/pdf/110617-PPAR-P098328-P106445-PUBLIC.pdf | 4. Lessons 4.1 Chapters 2 and 3 have documented the implementation of the two projects that supported strategies to stimulate human capital accumulation and expand access to basic health services in rural and indigenous communities through CCT and PBF. A joint look at these two programs reveals lessons that could help improve future World Bank operations. 4.2 Attention to possible synergies across interventions within a World Bankâ€“financed project and across two or more World Bankâ€“financed projects when they are being implemented in the same place at the same time can be beneficial. In this case, achievement of such synergies was plausible, for example, through the integration of the management information systems (MISs) of the RO/Social Protection and HEPI projects. The RO MIS makes available a registry of program beneficiaries that may also serve as the basis for an integrated registry of beneficiaries for social programs across the country. The integration of the RO and EEC MIS could have allowed for updating of the RO beneficiary roster using information on household composition collected by the mobile health teams, and the prioritization of RO expansion in communities where utilization of health services is suboptimal among the poor. However, these synergies did not materialize in Panama, indicating that opportunities for improvements in efficacy and efficiency may have been missed. 4.3 To ensure adequate provision of basic health services, the supporting PHC network, including public clinics and hospitals, needs to be strengthened. Mobile health teams cannot provide the whole range of health services that are critical to reducing maternal and child mortality (Kuruvilla et al. 2014). Thus, as recognized in the original design of the HEPI project, it is necessary to strengthen the entire PHC network, which includes the public clinics and hospitals that serve these vulnerable populations, but this was not accomplished in Panama. 4.4 The use of short-term contracts by private health providers can have negative impacts on turnover. The contractual terms offered to private providers of the basic health package (PAISS and PAISS+N) were for one year (renewable to up to four years). In turn, private providers offered short-term contracts (usually for 6 months) to the doctors, nurses, technicians and drivers comprising the mobile health teams. These short-term contracts led to very high staff turnover, which in turn became an extra burden for the regional governments as they had to provide all the training for newly appointed staff. 4.5 Verification systems need to be lean and efficient and set up before RBF payments are made. Processes, roles, and responsibilities, especially in complex RBF payment and reporting systems, need to be clearly identified upfront and kept at a minimum. Modern management systems and technological solutions should be identified beforehand and used to reduce administration costs and avoid potential delays. Unfortunately, the specific operational aspects of the PBF scheme in the HEPI project, including its payment and verification mechanisms, were not fully defined before starting implementation. In particular, the role of the DRSs in verifying and authorizing payments to mobile health teams created bottlenecks and delays that affected the provision of health services. 4.6 Successful impact evaluations require both technical capacity and commitment from the government side and technical support from the World Bank. The impact evaluations envisaged in the Social Protection and the HEPI programs were complex. They required the collection of primary data using household surveys at baseline and at endpoint, and maintaining a clear distinction between those that received the interventions and those that did not. However, the initial delays in contracting the firms to conduct the impact evaluations and the change in government following the presidential election reduced the buy-in from the counterpart in charge of decisions regarding the expansion of the programs, thus reducing the feasibility and quality of the evaluation.
P098376 | Public Finance and Institutional Development Policy Loan | Latin America and Caribbean | Panama | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2007 | 2007 | 2008 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/109111474577282488/text/000020051-20140618090736.txt | http://documents.worldbank.org/curated/en/109111474577282488/pdf/000020051-20140618090736.pdf | The ICR contains a number of useful lessons, including:Government ownership of reform is critical for success. Analytical underpinnings (e.g., PER and CFAPAR) are essential for designing DPLs.
P098378 | Second Phase Community Based Rural Development Project, | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2013 | 2014 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/254771475115067571/text/000180307-20141203041647.txt | http://documents.worldbank.org/curated/en/254771475115067571/pdf/000180307-20141203041647.pdf | The following lessons are emphasized from the ICR with some rearrangement by IEG:Effective harmonization of approaches around Government policies is critical for program success. The sustained success of the program as a whole reflects its efforts to support the Governmentâ€™s evolving vision on decentralization. In Phase 1, the operation supported the existing Village Management Councils in developing and implementing their annual investment plans. With the election of local councils in rural areas in 2006, phase 2 supported local municipalities in developing and implementing their PCDs. Phase 3 seeks to ensure continued alignment with government policy on decentralization, rural development, and land tenure security. Capacity building is more effective when it focuses on sustainable institutions and occurs through learning-by-doing. The programâ€™s close partnership with legally mandated entities such as Village Development Councils, local municipalities, decentralized agencies, civil society, and the private sector has enabled the program to transfer skills to established institutions. Providing training through local expertise (civil society organizations) has also enabled capacity-building to reach the micro level (villages) throughout the country. Experimental learning at the village level was one of the key capacity-building successes of Phase 1. Phase 2 also espoused â€œlearning-by-doing,â€ shifting the focus to the newly created municipalities. Communication and collaboration are critical for ensuring community ownership of project activities and social cohesion. The projectâ€™s approach, including the procedures used to implement local financing, were critical to give more responsibility to the different actors involvedâ€”not only in government institutions but particularly in the communities themselves. This orientation fosters greater ownership of local investments and should increase awareness of what must be done to maintain and sustain those investments appropriately. These positive achievements can be undermined by ineffective communication and conflict, which occur more frequently in villages and municipalities that lack sound mechanisms for collaboration and communication. For that reason, the project strengthened the local capacity to communicate effectively based on tools for conciliation and mediation. With such tools, communities can manage local problems before they escalate into conflicts. A programmatic approach, with adequate flexibility to incorporate innovations and sufficient technical assistance for piloting and testing at each stage, is a key success factor for decentralization efforts. This involves building the confidence of staff and communities, helping to fine-tune the model, and enhancing the prospects for achieving development outcomes. At the level of the Borrower and World Bank, the long-term (12-year) commitment (in the form of an APL) and consistency in team leadership were without doubt critical for providing detailed technical and goal-oriented support for programmatic learning. Such commitment and support have been shown globally to be essential for successful scaling up.
P098410 | Strengthening the National Statistical System | Europe and Central Asia | Tajikistan | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2006 | 2011 | 2012 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/110961475076914554/text/000020051-20140625075743.txt | http://documents.worldbank.org/curated/en/110961475076914554/pdf/000020051-20140625075743.pdf | This review confirms three lessons identified by the ICR: (i) For a project to be successful, ownership by the client, and mutual trust between the Bank team and the Government's counterparts play a critical role, (ii) A PIU embedded in the Government's public administration services is more effective than a stand-alone and independent unit, and (iii) The Consortium arrangement created a virtuous circle, as it mobilized more resources, and provided a pool for technical expertise and effective oversight. Twining a PIU with external stronger institutions in a specific sector could be a recipe for good project implementation.
P098423 | Sustainable Energy Financing Program | East Asia and Pacific | Pacific Islands |  |  | Infrastructure | Energy & Extractives | GEF | IPF | 2007 | 2022 | 2024 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099122123165597794/text/P0984231c43f8f06b1b67a15074265d158a.txt | http://documents.worldbank.org/curated/en/099122123165597794/pdf/P0984231c43f8f06b1b67a15074265d158a.pdf | The ICRR draws the following main lessons from the experienceof implementing this Project, with some adaptation oflanguage from the ICR.1. Striking a balance between the scope of work that is suitable for a regional approachand that issuitable for country-based operations, may raise the potential for project success. While this Projectwas envisaged to be a regional project, there was little synergy between the operations in different countries. and theProjects success and failure depended more on country-specific factors.2. An in-depth assessment of thedemand side profile as well as the financial landscape may help in providing tailored financial services for the targetsegments. Under normal commercial banking practice requirements, local private financial institutions would be unable toprovide loans to borrowers who were deemed to be non-creditworthy. Of the three targeted end-user groups in this project,households in rural areas were not considered as creditworthy by commercial banks. This group could have been better served bymicrofinance institutions. The lesson is that providing financial services may require a detailed understanding of the targetmarket segments for designing appropriate financial products that match their risk profiles.3. Alternativefinancing instruments could help in reaching the rural poor. This Project aimed to catalyze lending to rural poor throughestablishing a risk sharing fund to incentivize private financial institutions by guaranteeing a portion of their potential losses.However, most of the rural people either had seasonal income or insufficient credit history. The lesson is that for suchhouseholds, a different financing approach could have helped to reach the rural population.
P098426 | Governance Assistance Project | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2006 | 2015 | 2016 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/387721475092388888/text/854120PUB0FREN0B011Aug201400PUBLIC0.txt | http://documents.worldbank.org/curated/en/387721475092388888/pdf/854120PUB0FREN0B011Aug201400PUBLIC0.pdf | The ICR (p. 18) presents several valuable lessons including the following:Using the projectâ€™s mid-term review to evaluate technical and operational performance is critical. In this project, the mid-term review failed to identify and address technical and operational issues, in particular for tax administration. Furthermore, the mid-term review could have been used to address the shortcomings of the original Results Framework.A clear definition of project outcomes is important to ensure tracking progress towards those outcomes. In this project, activities were linked to objectives, however, outcomes were not sufficiently defined
P098426 | Governance Assistance Project | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2006 | 2015 | 2020 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/938151583969268984/text/Mongolia-Governance-Assistance-Project.txt | http://documents.worldbank.org/curated/en/938151583969268984/pdf/Mongolia-Governance-Assistance-Project.pdf | 7. Lessons 7.1 This PPAR suggests the following lessons\. â€¢ In a low-capacity environment, major benefits can be realized from relying on base-level technical solutions and incremental step-by-step reform strategies. The implementation of large, modern, integrated IT-based systems often fails because they exceed local absorptive capacity. The GAP strategy of first introducing stand-alone, relatively simple e-governance solutions for fiscal and economic management has demonstrated effectiveness and sustainability. â€¢ Several large and comprehensive e-government solutions can be introduced gradually, even in a low-capacity environment, if there are enabling factors in place, such as strong client ownership, good fiberoptic infrastructure, adequately trained local IT staff, and a sufficient budget for local training and technical support, especially for remote users. â€¢ Implementation risks related to the project's complexity and multiple government implementing agencies can be successfully managed if there is strong leadership from the core agency (such as the Ministry of Finance) and an experienced PCU that is empowered to make day-to-day decisions and impose project discipline across participating agencies. In the case of the GAP, the leadership of the Ministry of Finance and the robust operations of the PCU made a significant contribution to successful project outcomes. â€¢ Technical assistance projects with multisectoral coverage require significant supervision support from the World Bank and a larger than normal supervision budget. Lack of budget can limit the ability of the World Bank to provide the specialized technical support needed to help the client make better design and implementation choices. In the case of the GAP, with more resources, the World Bank might have provided better advice in several cases related to the implementation of large IT systems (design of PMMIS, contracting requirements for GFMIS). â€¢ Effective use of local talent and expanding local partnerships in project implementation can be beneficial for project outcomes. The GAP was quite successful in its mobilization and flexible use of local consultants. At the same time, a stronger partnership with local civil society organizations (especially under the accountability component) could have helped the government of Mongolia better use the newly built e-governance infrastructure. â€¢ In technical assistance projects with a considerable training component, more attention to formal assessments of efficiency and effectiveness of project investment in training might be appropriate. In the case of the GAP, lack of respective indicators in the monitoring and evaluation framework prevented learning more about the actual impact of project training on capacity development.
P098459 | Morocco Oum Er Rbia Sanitation | Middle East and North Africa | Morocco | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2010 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/661251554990896681/text/Morocco-MA-Oum-Er-Rbia-Sanitation.txt | http://documents.worldbank.org/curated/en/661251554990896681/pdf/Morocco-MA-Oum-Er-Rbia-Sanitation.pdf | Five lessons from this project listed in the ICR (with some editing by IEG) may apply tosimilar operations(paragraphs 95-99): A well-structured results framework (RF) that captures a projectsresults chain provides a framework for monitoring a projects achievements. In this projects sanitationcomponents, attention to household connections led to identifying intermediate outcome indicators that further refined and adjustedthe RF to better document how to achieve the PDOs. This strategy used the restructuring mechanism to adjust the RF twice, redefineoutcome indicators previously missed at appraisal and punctuated by implementation problems. Pilotingtechnologies calls for a robust ME system thatprovides the evidenceabout new technologies to adopt in improvingsystem performance. Just in time training, study visits, and south-south knowledge exchanges as well as continuinginnovations learned led this project to construct a firstUpflow Anaerobic Sludge Blanketfor domestic wastewatertreatment. The use of country systems, under OP/BP 4.00 Piloting the Use of Borrower Systems to AddressEnvironmental and Social Safeguards Issues in Bank-Supported Projects for environmental and social safeguards can succeedwith additional time and support during project preparation and implementation. In this project, when gaps between WorldBank requirements and the country systems were identified, mitigation measures were agreed during preparation, but sufficientunderstanding of what use of country systems meant needed to be reinforced and given adequate time for counterpartparticipation. Projectsthat require land acquisition caneffectively recognizeandresolvecitizen concerns during preparation. In this projectaddressing these concernsearlythrough the adoption of local practices toresolve grievances resulted in an effective citizenengagement,allowed for smooth implementation, andavoided significant constructiondelays. Coordination and constant communication among the various actors are key totroublefreeproject implementation. Thekey stakeholders inthis project- namely the implementingagencys project teams, communes in the 14 participant cities and towns, the technical assistance consultants, and theBanks own team learned that a workable institutional framework that uses mutually agreed appropriate technically andfinancially sustainable solutions can lead tosuccessful project implementation. .
P098483 | Sudan Multi-donor Trust Fund for Decentralized Health System Development Project | Eastern and Southern Africa | Sudan | IDA | FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2007 | 2013 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/724221474501322813/text/000020051-20140626122909.txt | http://documents.worldbank.org/curated/en/724221474501322813/pdf/000020051-20140626122909.pdf | The ICR (pp. 34-35) offers the following main lessons (adapted for this ICRR): Projects overloaded with activities create implementation problems. Post-conflict challenges are many, and it is easy to overload load a project with activities that are all priorities, creating burdens that exceed implementation capacity and reduce the efficiency and effectiveness of project activities. This is especially tempting when projects are subject to an abundance of government requests. Project restructuring should be done as soon as possible when its desirability becomes apparent. Restructuring early to resolve implementation problems provides sufficient time to respond to constraints. Delayed restructuring makes reorientation difficult and slows down the process; in some instances, the scope for change becomes constrained by actions already undertaken.Observations adapted from the Government's ICR (ICR, pp. 84-85):Integration of processes promotes sustainability. The integration of project coordinating units into the responsible federal and state ministries (of health) is seen as an important means of strengthening sustainability of the processes initiated under the project.Policy development should be an integral part of a project. Policy development is more effective when it is more directly linked to the implementation of other project activities.
P098493 | MDTF-National: Technical Assistance Facility (TAF) | Eastern and Southern Africa | Sudan | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2006 | 2010 | 2011 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/558491474508466286/text/000020051-20140624185338.txt | http://documents.worldbank.org/curated/en/558491474508466286/pdf/000020051-20140624185338.pdf | Clearly defined and realistic objectives are prerequisites for the success of project. The objectives of TAF were too ambitious given the amount of financing, timeframe of the project, available staffing arrangements, including procurement and financial management staff.Institutional arrangements and size and quality of staff are critical for the success of a project.Simple but measurable performance indicators are of utmost importance for easy, systematic and objective monitoring and evaluation.Technical assistance and capacity building projects in post-conflict and re-engagement situations should be very conservative in terms of devising results and time frameworks, as well as maintain maximum possible flexibility in terms of their content. The TAF listed upfront in a detailed manner studies and training sessions it was to undertake. At the end, very few of them materialized as planned, and those that were actually implemented rarely, if at all, translated into active policies or concrete projects.Ex-ante quality enhancement reviews for projects in fragile environments could be of important value in terms improving their design.
P098495 | Southern Sudan Umbrella Program for Health System development | Eastern and Southern Africa | South Sudan | IDA | Non-FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2006 | 2010 | 2012 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/907331474496904976/text/000020051-20140625060614.txt | http://documents.worldbank.org/curated/en/907331474496904976/pdf/000020051-20140625060614.pdf | Where Government is relatively weak and inexperienced and infrastructure is poor, project design must be simple and focused, with a realistic technical design, carefully considered sequencing of activities, and appropriate attention to capacity building. In this case, existing capacity was not adequate to absorb such a large grant over such a short period of time, and project design was overly complex without consideration of the relationships between a large number of components.M more frequent interaction and communication; consensus on program status among different stakeholders; prompt reactions to emerging issues; hands-on support for application of the Bankâ€™s fiduciary system; and prompt support for implementation details.
P098496 | Science & Technology Higher Education | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2008 | 2016 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/941451481130546533/text/ICRR-Disclosable-P098496-12-07-2016-1481131428257.txt | http://documents.worldbank.org/curated/en/941451481130546533/pdf/ICRR-Disclosable-P098496-12-07-2016-1481131428257.pdf | Lessons drawn by the ICR (pages 22-23), adapted by IEG: The use of a competitive financing mechanism to providesupport to higher education institutionscan contribute to ownership and sustainability of activities, as well as draw uponcomparative advantages. The mechanism employed by this projectwas developed into a financing facility that will be usedby the government to continue support to the tertiary education sector. Key outcome indicatorsrequirecarefulconsideration at the start of the project design, including the feasibility of collecting quality data. In the case of thisproject, the source of data for learning outcomes was deemed unreliable, and therefore the indicator needed revision.However, the alternate indicatorsdid not adequately measure the intended outcome of improved quality.
P098531 | HT Electricity Project | Latin America and Caribbean | Haiti | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2007 | 2014 | 2015 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/775031475117659468/text/000012394-20150112124542.txt | http://documents.worldbank.org/curated/en/775031475117659468/pdf/000012394-20150112124542.pdf | The following lessons can be drawn from this project.Better recognition and knowledge of the implementing agencies' capacity to execute sophisticated technical equipment is particularly important, while designing projects for fragile countries. And if the lack of capacity is identified as a concern, it would be helpful to address this at the design stage itself through adding a technical assistance component.When addressing the issues of poorly run state institutions, it is necessary to focus not only on the capacity of lower level of management, but also on the commitment of higher management. In the case of this project, although the (lower level) Direction team were committed to the project, the higher level management was not, and this in turn delayed execution.Selection of realistic indicators, and more importantly addressing the issue of data collection, is essential for M&E implementation.
P098538 | Sustainable Land and Water Management | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2011 | 2021 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/099430006012213707/text/P0985380df98ec0ce0bd730396beccc0519.txt | http://documents.worldbank.org/curated/en/099430006012213707/pdf/P0985380df98ec0ce0bd730396beccc0519.pdf | The ICR (para 114-120) provided seven lessons. Some of them are summarized below because they may provide lessons of interestsfor other Sustainable Land and Water Management (SLWM) projects.Financial incentives combined with technicalassistance and biophysical investments can lead to higher adoption of SLWM practices by communities. The project supporteda package of interventions to provide comprehensive support for adoption of SLWM practices, including provisions of seedlings,training, and agricultural extension services, together with provisions of incentives for planting trees on farms through thePayment of Environmental Services (PES) and access to finance through Village Savings and Loans Associations (VSLA). According tothe Development Impact Evaluations survey (page 9), an adoption of the SLM practices in 2020 was higher for the samplefarmers who participated in the projects SLM activities and the PES pilots in 2016-2017 than for the farmers who did notparticipate in any of them.Recognition of communities needs and readiness through consultations can lead to ahigh level of their participation and commitment. Through an extensive demand driven consultative process, the projectsupported the: (i) enhancement of community cohesion and benefits through activities in the management plans of Community ResourceManagement Areas; (ii) enhancement of community livelihoods by providing an incentive for improved patrolling and monitoring of thebiodiversity landscapes; and (iii) establishment of water holes at the fringes of the Gbele Resource Reserve to address communalneeds and helped reduce pressure from livestock on the protected reserve.Proactive engagement of women in SLM planning anddecision-making and gender sensitive targeted interventions can enhance overall project performance and achievement of results. Thecustomary tenure system in northern Ghana allocates lands to only men, limiting womens access to lands (ICR, para 71). Theproject addressed the cultural and administrative barriers to womens participation through discussions withcommunity leaders and elders (ICR, para 71). As a result, female charcoal producers and farmers who participated in theproject accelerated achievements of results by more quickly adopting changes in production methods or dropping unsustainablepractices. The VSLA model established by the project also supported female farmers to fund livelihoods diversification activities,childrens education, and agricultural inputs (e.g., seedlings) to expand SLWM practices on larger areas.TrustFunds can offer great value for piloting and demonstrating innovations. The project was supported through three phases ofgrants from the GEF Trust Funds in a programmatic manner, which financed approximately US$29 million over a duration of 10 years.While the total grants for the project was comparatively small among the World Banks operations, the GEF TrustFundsfinancing induced a critical change in terms of investing in challenging issues for which clients typically wouldnot borrow unless there was evidence of translation of concepts to practice and successful implementation. With the sequence ofgrants from the GEF Trust Fund, the project was successful in piloting activities and expanding target areas, which resulted inleveraging larger lending by the Government of Ghana for follow-on projects such as Ghana Landscape Restoration and Small-ScaleMining Project (P171933).
P098548 | Second Programmatic Development Policy Loan | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2007 | 2008 | 2010 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/901651474634837145/text/000146597-20140619171421.txt | http://documents.worldbank.org/curated/en/901651474634837145/pdf/000146597-20140619171421.pdf | A prime lesson from this program is that exogenous forces, in this case the prospect of eventual EU accession, can play a dominant role in assuring government commitment to reforms.A second lesson is that continuity of champions for reform on the government side and continuity in Bank teams are essential for successful reform outcomes.
P098639 | Core Fiduciary Systems Support Project (TF056336) | Eastern and Southern Africa | South Sudan | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2007 | 2013 | 2015 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/720871475117143362/text/000180307-20150113073109.txt | http://documents.worldbank.org/curated/en/720871475117143362/pdf/000180307-20150113073109.pdf | An important lesson learnt presented in the ICR (section 6) concerns the importance of, and difficulties in balancing the need to ensure outsourced consultants complete the short-run work they have been hired for, while at the same time undertaking parallel capacity building and skills transfer in areas fairly narrowly related to the project logic, while avoiding taking on broader Government functions. Other more generic lessons listed include the importance of timely appointment of counterparts and ensuring stakeholders have realistic expectations about the project from its outset.Another lesson mentioned concerns the observation that individual consultants may provide more efficient and cost effective services, and quicker knowledge than firms. This observation may be correct but cannot be drawn from the ICR write-up. It also ignores the possibility of capture, possible internalization of security and certain other costs by firms, and seems partly contradicted by experience elsewhere cited in project documents. A final lesson from this review is that difficult post conflict situations require an innovative and flexible approach towards procurement, which may include upstream outreach to qualified firms prior to launch of tenders to gauge their interest and, if needed, adjust terms of reference.
P098654 | Thermal Power Efficiency | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2009 | 2014 | 2015 | ICRR | >=10 million & <25 million | Satisfactory |  |  | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/243171468000886224/text/ICRR14755-P098654-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/243171468000886224/pdf/ICRR14755-P098654-Box393191B-PUBLIC.pdf | Two lessons were selected from the ICR, with some adaptation of the language:Significant demonstration effects can be attained for rehabilitation through proper selection of technology based on cost-effectiveness and replication potential, as well as extensive dissemination activities. Under this project, six thermal plants collectively hosted more than 30 study tours for staff from other thermal plants located both inside and outside their respective provinces. Several demonstrated technologies (CHP, waste heat utilization, variable frequency control) have been turned into standard industrial practices. Flexibility is required to adapt project implementation to evolving government priorities. The rapid government interventions, along with the project delay at the outset of the project, necessitated a revision to the project sub-components.One lesson is selected from the Recipient's report (ICR's Annex 7):Dissemination efforts at the national level should be included as a major design element to promote the application of knowledge and project outputs. The potential impacts of knowledge outputs could have been more significant if the project was designed to have a greater link to line ministries at the national level and targeted a broader range of stakeholder at the national level.
P098654 | Thermal Power Efficiency | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2009 | 2014 | 2018 | PPAR | >=10 million & <25 million | Satisfactory |  |  | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/880011530296222333/text/ppar-chinathermal.txt | http://documents.worldbank.org/curated/en/880011530296222333/pdf/ppar-chinathermal.pdf | 5. Lessons 5.1 Piloting and demonstrating potential technological improvements to lower costs and improve environmental performance works well in environments where operators are risk averse and constrained by government policy. The impact of this project illustrated the benefits of interventions that show and don't tell. Seeing how easily the changes could be made to their plants and experiencing the benefits first hand led to considerable uptake amongst other operators. Experience in the China energy market is significantly determined by government oversight and regulation. Experiencing the immediacy of project benefits led to spillover effects with other plants instituting similar changes both for cost reasons and to respond to government emission reduction requirements. 5.2 The World Bank's international experience and expertise has the capacity to make an important contribution to pollution reduction in the thermal power sector. This project showed that even in 'undesirable' sectors, such as coal fired thermal power production, where there is a reticence to commit project resources, the World Bank can have considerable impact on pollution reductions. With a relatively small financial outlay, this project showed that\. (a) the World Bank's presence in the sector can have catalytic impacts on policy level dialogue and decisions leading to smooth closure of inefficient generation assets; and (b) dramatic efficiency improvements can be retro-fitted to existing coal-fired energy plants with considerable pollution reduction benefits through low cost rapid response measures. This project provides a strong case for the World Bank to strengthen its focus on efficiency enhancement opportunities in thermal power sector. 5.3 External help and international expertise provided by World Bank projects at the provincial level in middle income countries helps support and reinforce successful central government policy. In this instance, the project showed that taking global knowledge and international expertise to a given development problem, instituting a set of pilots and then demonstrating the benefits of applying the model was a necessary conduit for shifting opinion amongst small energy plant operators in China. The project's efforts at bringing international experience to the regions and taking plant operators to demonstration sites provided the necessary assurance that plant improvements would be cost effective and low impact. Working at the provincial level gave authority to the regional governments, ensured the pilots were 'hands-on' and it amplified 'spill-over' opportunities as the communication of benefits took place amongst and between provincial leaders. This decentralized approach empowered provincial governments to make necessary changes by seeing the immediate benefits, while knowing that these reforms had central government support. 5.4 Analytical work needs to respond to the immediate needs of the sector rather than being determined by supply-side factors. The analytical work completed by various organizations with project funds was of a high standard and rigorously prepared. However, the organizations procured to undertake the research acknowledged that there were other more pressing issues that required investigation and would have been more useful for the provincial energy sector. Decisions on the scope of work and the associated topics was determined early in the project cycle. As circumstances changed, the analytical work did not evolve leading to the preparation of technical papers that had marginal value. The various institutions charged with completing the research tried to communicate these issues, but having committed to the topics the World Bank and the government did not provide the space and time to make potentially useful changes. This limitation was amplified by the lack of a dissemination strategy for the completed research. 5.5 A 'hands-off' approach by the World Bank in high capacity environments can lead to missed opportunities in maximizing a project's potential. In this project, the strong performance of relevant project management units amongst the provincial governments resulted in efficient disbursements and good implementation project ratings. While this reflects well on the capacity and abilities of the local project team, it also led to more limited World Bank oversight which diminished the potential value of global dissemination of ideas and research. The limited interaction between the World Bank and its partners also amplified frustration amongst project recipients and prevented greater learning amongst counterparts. Providing sufficient supervision time and energy to well performing projects has the potential to amplify the project's gains. 5.6 Barriers to the closure of small inefficient power units are often political. Fostering the key relationships with partners is essential in knowing what and how reforms can be implemented in challenging environments. The closure of the small plants during the project's implementation was only indirectly linked to the project. Consultations with the Department of Energy in Beijing revealed that closing small inefficient plants had been mandated since 2001, but the pressure on supply and government inertia had made the policy ineffective. The World Bank's conversations in the project preparation period incentivized provincial governments to prioritize the implementation of shut down protocols and compensation arrangements that partly contributed to the closure of nine small coal-fired plants. The value added through the project was the policy dialogue, the relationships at the provincial level and the profile of the World Bank as a contributor to the broader energy strategy.
P098837 | SD - National Emergency Transport Rehabilitation Project | Eastern and Southern Africa | Sudan | IDA | FCS | Infrastructure | Transport | RETF | IPF | 2007 | 2013 | 2015 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/774881475113675842/text/000012394-20150108124134.txt | http://documents.worldbank.org/curated/en/774881475113675842/pdf/000012394-20150108124134.pdf | IEG found that the following lessons identified in other similar environments were observed in the case of this project:(i) Early engagement in post-conflict environment is the way to go for the Bank, but much attention must be paid to risks.(ii) Agreement of key stakeholders since the beginning. Local governments insisted for the upgrading of the roads to a higher asphalt road standard, which caused delays in the startup of the project and excessively increased the project cost. Therefore, it would be prudent to agree with key stakeholders, at the planning stage, on priorities and sequencing of interventions(iii) TA for capacity building needs to be planned at project inception and has to focus on institutionalizing capacity development at all levels.(iv) In a post-conflict environment, selectivity in project activities can improve outcomes: The activities selected were many and diverse in scope. Some of the activities could not be completed in the original project period, and had to be dropped, and some were scaled down requiring restructuring of the project.
P098850 | Infrastructure Pre-Investment Facility | Europe and Central Asia | Georgia | IBRD | FCS | Infrastructure | Transport | IDA | IPF | 2006 | 2011 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/590081474491458773/text/000020051-20140625065650.txt | http://documents.worldbank.org/curated/en/590081474491458773/pdf/000020051-20140625065650.pdf | The ICR provides several lessons, of which four are adapted and highlighted here. .Allowance must be made for cost overruns in Hydropower studies, which are very likely because the geology of a dam site is typically not fully known at project start. This project was no exception to this experience, and additional funds were needed to top up the outlay for technical feasibility studies.Large scale hydropower development must be set in the larger river basin context to account for possible multi-dam development in the future. In the case of Khudoni, the government already had elaborate river basin development plans, but they were over a decade old, and had to revisited to confirm the adequacy of the original Khudoni dam location. Undertaking a Strategic Environmental Assessment (SEA) is prudent policy whenever new power generation is contemplated and past SEAs are non-existent or dated. Undertaking a SEA was originally not part of this projectâ€™s hydropower component, and the Government was originally of the opinion that sufficient studies of this nature had been made. However, it became clear that an updated SEA would be important to make a convincing case to civil society that environmental impacts are identified and addressed.The Bank should ensure that the borrower commits sufficient time and resources for preparation of feasibility studies and designs for complex infrastructure projects. Any short-cuts in this regard are likely to impact implementation negatively and result in far greater costs later. In this project, only 6 months were provided for technical designs, when the scale of work would have justified 12 months. Similarly, the budget allocated for designs was only at about 1.5% of the construction costs against 5% that is allocated for projects of similar size and complexity,.
P098889 | Cotton Sector Recovery Project | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2007 | 2013 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/814311467998241085/text/ICRR14638-P098889-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/814311467998241085/pdf/ICRR14638-P098889-Box393183B-PUBLIC.pdf | The ICR (p. 23) identifies several lessons, including the following highly relevant two:Providing all different actors with information is useful for increasing competition. In this project the PMU provided all associations and farmers with world market cotton prices on a daily basis. This gave farmers more knowledge and increased competition which contributed to farmers receiving cotton prices close to world market prices.Engagement with all relevant stakeholders and partners is essential when a wide sectoral reform is needed. The Bank worked closely with the Asian Development Bank and the International Monetary Fund which allowed for the implementation of several complementary projects and therefore address the challenges more effectively.Lesson learned identified by IEG:It is important to build consensus between the Bank and the Borrower on the objectives of a project prior to its implementation. In this instance such prior consensus might have prevented the necessity for a more ambitious reform of the agricultural sector and the implementation of the original project objectives.
P098915 | GEF Sino-Singapore Tianjin Eco-City | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | GEF | IPF | 2011 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/410191498065513549/text/ICRR-Disclosable-P098915-06-21-2017-1498065503309.txt | http://documents.worldbank.org/curated/en/410191498065513549/pdf/ICRR-Disclosable-P098915-06-21-2017-1498065503309.pdf | From IEG Fostering efficient urban expansion. Adhering to fundamental urban planningprinciples,it is necessary to avoid fostering supply driven discontinuous urban expansion which promotes urban sprawl andinherent resource inefficiencies. SSTEC design principles of ecological design would be enhanced bytaking into account landuse and spatial considerations. Population estimates need to be realistic.Population growth estimates of newly established urban settlements require careful and independent verification which canrely on objective methodologies. Overly optimistic growth scenarios which rely on supply driven projections of employment requireappropriate risk mitigation to ensure the flexible implementation of urban expansion.From the ICRwith some adaptation of the language: Timely upstream technical assistance to cities canhave a significant impact on urban planning and strategy. Despite the relatively small amount of funding, especially incomparison with the massive investment made in the eco-city by the GOC, the impact of TA on the strategic direction of theeco-citys low carbon development and resource management was substantial. The TA activities were initiated during theplanning and development phase of the SSTEC, thereby ensuring inputs for shaping the modality of the citys resourcemanagement and transport mode. Understanding connectivity of acity. City planning in China often places an overt thrust on the physical infrastructure within cities suchas roads, buildings. However, the livability of a city is not only dependent on physical conditions, but also on its people, theirsocial networks, community, and culture. The factors that drive peoples decision to move from a familiar social andenvironmental setting to a completely new city are manifold. Providing physically better living conditions is not be sufficientcondition to foster urban expansion, as the experience of the eco-city. Engagement anddialogue are critical for maximizing the impact of technical assistance. The project produced numerous reports andanalytical products. Utilizing the recommendations of the reports requires putting in place a process and making considerableefforts for dialogue with the relevant agencies. For example, after the submission of the reports by the consultants, workshops andwork meetings could have been organized by the World Bank to facilitate the policy dialogue and support the clients for theimplementation of the recommendations. Also, the supervision missions for a TA type of project could be enhanced by expert meetingswith policy makers in the relevant areas.
P098926 | eRwanda Project | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2007 | 2011 | 2013 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/491851474497141969/text/000020051-20140625071025.txt | http://documents.worldbank.org/curated/en/491851474497141969/pdf/000020051-20140625071025.pdf | The following are key lessons emerging from the information in the ICR:Targets for output and outcome indicators should be realistic: In the case of this project, targets for the two user satisfaction indicators (satisfaction of the target population with e-services and satisfaction of the target population with access to public information) that were used to measure the progress of the project's second development objective were over-ambitiously set to 100 percent.Readiness for implementation must be assured to avoid later inefficiencies: Since, procurement in the ICT sector frequently makes special demands in terms of knowledge and experience, the task team needs to ensure that the national counterparts are well trained and ready for project implementation. The eRwanda project was not ready for implementation due to limited capacity in technical, administrative, and operational expertise in ICT procurement which became a major challenge during the first half of implementation resulting in significant disbursement delays in the first two years of implementation. Frequent changes in the senior management staff within the implementing agency can result in delays during implementation. Efforts should be made to retain an institutional memory in order to avoid delays during project implementation.
P098948 | Inland Waters Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2007 | 2013 | 2014 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/164621475785627775/text/000180307-20141202135705.txt | http://documents.worldbank.org/curated/en/164621475785627775/pdf/000180307-20141202135705.pdf | Lessons from the ICR:When the time for project preparation is shortened for political reasons, there is a higher risk that problems will occur and special arrangements may be needed to fast track legal processes. If the project is to be implemented very quickly, with designs to be done during the implementation phase, sufficient capacity should be mobilized and trained at the very start of the project to accelerate the preparation of a pipeline of sub-projects. Economies of scale should be considered in utility reform. While some utilities have the capacity to implement, engage beneficiaries, and supervise the works effectively, others require considerable support. In the weakest utilities works can be seriously delayed. This indicates that a further merging of utilities would not only foster financial but also technical efficiency. Political commitment for investment in water utilities must be sustained at the central level to implement reforms to move the sector (in this case towards EU compliance). Municipalities, elected mayors and council members had to make tough choices on tariff adjustments and enforce connection policies.
P098949 | Second Village Investment Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2015 | 2016 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/328621468197955606/text/ICRR14901-ICRR-PUBLIC-P098949-Box396265B.txt | http://documents.worldbank.org/curated/en/328621468197955606/pdf/ICRR14901-ICRR-PUBLIC-P098949-Box396265B.pdf | The following four lessons are taken from the ICR with some adaptation of language:Strong quality assurance processes are critical to the technical quality of civil works, especially when these are implemented by rural communities with low capacity to manage them.The even targeting of all beneficiary communities with small community investments, rather than concentrating larger investments in fewer communities, may serve as a positive approach for building confidence of the population, particularly in a context of high distrust of government and related civil unrest.Solid communication channels are important to mobilizing villagers, facilitating social inclusion, and increasing transparency. Detailed profiles of beneficiary communities and group-specific statements of needs and priorities are useful mechanisms in facilitating the inclusion of different social groups in community investments.
P098949 | Second Village Investment Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2015 | 2018 | PPAR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/687491521119929150/text/123089-PPAR-P073973-P098949-PUBLIC.txt | http://documents.worldbank.org/curated/en/687491521119929150/pdf/123089-PPAR-P073973-P098949-PUBLIC.pdf | 4. Lessons â€¢ Multiple tranches of village-level financing in CDD projects can reinforce and strengthen participatory planning over time. This approach can also lower the risk of elite capture. In the Kyrgyz Republic, the four phases of financing in each village allowed for multiple opportunities for local government and communities to use the local development planning skills imparted by the project. It also helped villagers prioritize and minimize elite capture, as multiple project cycles benefited more villagers, not just those who were involved during the first year of the project. â€¢ CDD programs implemented nationally can enhance political legitimacy, especially in countries with ethnic or regional tensions. Although a move to consolidate project activities can magnify local economic gains, these consolidations carry the risk of perceptions of favoritism of one group over another. VIP 1 and VIP 2 activities covered 100 percent of rural villages, which prevented the perception of favoritism or capture. This model is not replicated in VIP 3, where microprojects and subprojects are allocated on a competitive basis. Fieldwork revealed some perceptions of favoritism along ethnic lines in southern villages, and more outreach may be necessary beyond publicizing selection criteria. â€¢ In rapidly scaled out CDD programs there is a need to pay simultaneous attention to social outreach and infrastructure quality. Poor infrastructure can undermine program legitimacy and also create a public safety risk. In the Kyrgyz Republic, a lack of initial attention to infrastructure contributed to additional costs and implementation delays. However, when the project teams learned of issues with the quality and safety of project-financed infrastructure, they took the proper steps to ensure a complete accounting of deficient infrastructure and retrofitting of infrastructure that caused a public safety hazard. These corrective actions mitigated reputational risk to the World Bank and bolstered the legitimacy and creditability of both the project and the implementing agency. â€¢ Investments in small-scale enterprises require an upstream diagnosis of capacity and constraints and the interventions should be targeted to address known binding constraints. Interviews with project teams revealed that the small-scale enterprise development grants in VIP 1 and VIP 2 used a light touch approach. There was minimal consideration of the constraints faced by small-scale enterprises (that is, access to market, value chain analysis, enterprise development training, access to finance, market analysis, access to inputs, and so on). Because of the limited data collected on these investments, little is known about their viability. If the World Bank is going to invest in small-scale enterprise development, it should be a primary focus, not an add-on. This lesson aligns with the IEG evaluation of the rural nonfarm economy, which recommended more systematic diagnostics (on constraints and performance) for micro, small, and medium enterprises in countries where the rural economy is a key part of the solution to ending poverty.
P098956 | Post-Primary Education | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2006 | 2013 | 2014 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/855261474502833977/text/000020051-20140626112008.txt | http://documents.worldbank.org/curated/en/855261474502833977/pdf/000020051-20140626112008.pdf | The ICR presented useful lessons (pp. 26-27), two are presented below: Sub-sector reforms are as challenging as sector reforms, notably in countries where the stakes are high. This argues for (i) an intensive and detailed action plan at the start of the project, with more specific indicators, notably when there is limited capacity among the local and decentralized levels where the reform impact should actually happen, and (ii) a more intensive M&E effort with appropriate technical studies before, during, and at the end of a project. In sub-sector reform projects, detailed standards for measuring school performance in terms of the quality of learning, the quality of teaching, and the overall performance of the school are critical. This would involve technical and standardized agreements on measures of quality and learning along with appropriate and measurable monitoring indicators. Adequate monitoring and reporting supports decision- making processes to enhance quality.
P098956 | Post-Primary Education | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2006 | 2013 | 2009 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/714911468021283501/text/491420PPAR00P01isclosed0Sept0102009.txt | http://documents.worldbank.org/curated/en/714911468021283501/pdf/491420PPAR00P01isclosed0Sept0102009.pdf | 7. Lessons 7.1 This assessment provides a number o f lessons for the education sector\. To obtain job-relevant skills from school enrollment students must first and foremost acquire pertinent and suitably organized knowledge. If secondary education does not impart the necessary knowledge, the labor market may be unable to use the graduates when demand arises (paras. 4.12,4.16-4.18). In low-income countries where substantial numbers o f students fail to acquire basic skills, application o f the available curricula and textbooks may be more important than development o f new curricula. New curricula may be in principle desirable, but UN Integrated Regional Information Networks 2009. T h e national university in Ouagadougou was created in 1974 with 533 students and had expanded to 9,400 students by 1996. 23 1 Pass rates in a sample o f countries are in h~\.//fi.excelafiica.com/archive/index.ph~/t-237.html. 24An example i s Madagascar, where faculties make selections based on t he Baccalaureat scores or conduct separate examinations (World Higher Education Database (www.unesco.org/iau/onlinedatabases/systems_data/mg.~~ they should be realistically implementable in low-income classrooms (para. 3.5, 4.19). 0 Subsidizing private secondary education may help increase access in countries where secondary education i s constrained. Where student demand i s high, increasing the availability o f private schools may enable the government to concentrate public resources o n lower income and underserved groups (para. 3.1 1). Textbooks or systematically reproduced materials are a prerequisite for knowledge management at all levels o f education. Their availability should be a policy priority. Without textbooks and training o f teachers in their use (particularly where teachers themselves have studied without them), knowledge becomes constricted and systemic efficiency i s low. The cost and availability o f Francophone textbooks has been a longstanding problem, for which clear solutions have not emerged (para.4.15,6.3).
P098963 | Rural & Social Policy DPL II | Western and Central Africa | Niger | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | DPF | 2007 | 2008 | 2009 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/430041474503738907/text/000020051-20140619104435.txt | http://documents.worldbank.org/curated/en/430041474503738907/pdf/000020051-20140619104435.pdf | The following lesson complements the lessons offered in the ICR:A key lesson from this DPL series pertains to the complementarity between financing instruments. The RSRC series was a good example of complementarity between two instruments: investment and DPL lending. Under the RSRC policy and process issues were addressed that constrain the development effectiveness of the investment operations.
P098964 | PRSC III | Western and Central Africa | Senegal | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2008 | 2009 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/525561475084691398/text/000020051-20140619084816.txt | http://documents.worldbank.org/curated/en/525561475084691398/pdf/000020051-20140619084816.pdf | Two lessons emerge from this review which, although not new, deserve to be emphasized. The first is that mere implementation of prior actions - especially when these involve actions such as setting up legal and regulatory frameworks, improving budgetary processes, and creating new institutions - is not sufficient to achieve expected results. It is also important to ensure that the steps necessary to make the reforms operational are taken. The second and related lesson is that clearly defined monitoring indicators and the use of realistic quantitative targets can help support progress towards expected results. The credit appears to have been relatively more successful in achieving its objectives where indicators were easy to identify and statistical data were available to monitor quantitative targets, such as in the area of budgetary reforms and in some aspects of health reforms.
P098979 | Iraq: Household Survey and Policies for Poverty Reduction | Middle East and North Africa | Iraq | IBRD | FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | RETF | IPF | 2007 | 2013 | 2015 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/684641475112386427/text/000012394-20150109094942.txt | http://documents.worldbank.org/curated/en/684641475112386427/pdf/000012394-20150109094942.pdf | IEG adapts the following two lessons cited in the ICR: (i) In a fragile environment, one cannot be expected to produce results quickly, particularly when public institutions are weak (page 26). This provides more evidence to a common lesson observed in post-conflict environment that building technical capacity is the most urgent and sensible activity to engage in during the first years of social-economic recovery.(ii) The combination of a Bank-executed trust fund with a recipient executed trust fund proved to be an effective approach in building capacity in a post-conflict environment (page 26). This operational mode proved effective because it allowed the Bank to provide its technical assistance, and to give the opportunity to the Iraq administration to be exposed to Bank practices, and to deliver key products in the area of poverty assessments, and strategy preparation. In addition, IEG identified the following three lessons: (i) Risks identification and mitigation are of paramount importance when operating in post-conflict countries. In this situation, there is need for simplicity and flexibility to accommodate the changing priorities of the borrower, and of other stakeholders in the donor community. (ii) The Bank needs to pay closer attention to projects that are experiencing significant implementation delays. Delays in project implementation affect negatively the efficiency of resources, and the change in TTLs affects continuity in the dialogue and the speed of project implementation. (iii) Finally, given the difficulties associated with the design and implementation of small projects supported by Trust Funds, streamlining and integrating TFs into larger Bank operations can have efficiency gains. Such a move would be cost-effective and might create stronger synergy between the normal Bank operations, and those areas supported by specific donors through TFs.
P099047 | India: Vocational Training Improvement Project | South Asia | India | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2007 | 2019 | 2019 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/212791561140690308/text/India-IN-Vocational-Training.txt | http://documents.worldbank.org/curated/en/212791561140690308/pdf/India-IN-Vocational-Training.pdf | The following lessons are drawn from the ICR and edited.Pilot models need to beassessed before scaling them up. Teams need to make sure that the challenges of scaling up innovative pilots are wellunderstood by the authorities as well as the team. The COE model that was piloted by the MOLE during VTIP preparation andthen underpinned VTIP design was never sufficiently assessed before scaling up. Consequently, COE implementation challengeswere neither anticipated nor sufficiently addressed during implementation.Project design must bedimensioned to country capacity. While sector challenges may be many and diverse, task teams need to focus onapproaches that are implementable within the time frame of the project. VTIP attempted to address all the major challengesfacing better employability and earnings within a relatively short five years. As a result, the project stretched over tenyears and still came off with relatively modest results.
P099051 | AR Santa Fe Road Infrastructure | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2007 | 2012 | 2014 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/527931475098623710/text/000020051-20140626115511.txt | http://documents.worldbank.org/curated/en/527931475098623710/pdf/000020051-20140626115511.pdf | The hiring of a single consultancy firm to take charge of environmental studies, and to work in coordination with the various consultancy firms in charge of technical design, helps ensure that environmental standards are unified across the various road segments and contractors and provides a feedback loop to make certain that designs meet environmental and social criteria.The establishment of formal channels for continuous feedback from users and civil society provides a vital instrument for successful project implementation, enabling inclusion of citizensâ€™ perspectives and knowledge in the actual design of projects. This strengthens ownership by local communities, and democratizes the overall process.Appropriate due diligence is required in urban projects to minimize the risk of encountering unforeseen contingencies, particularly in the provision of utilities (electricity, water), which, if not scheduled correctly, can increase costs and delay implementation.The Bank could increase its work with strong sub-national governments. The fact that this ambitious project was completed on time with no extension or request for additional financing demonstrates that capacity can exist at the sub-national level to execute direct loans from international financial institutions and to comply with the required norms and standards.
P099059 | Dokan and Derbandikhan Emergency Hydro Power Project | Middle East and North Africa | Iraq | IBRD | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2007 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/330441467986319590/text/ICRR14680-P099059-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/330441467986319590/pdf/ICRR14680-P099059-Box393183B-PUBLIC.pdf | In an emergency situation, project design should be kept simple and manageable. In this project, the components were kept simple, and designed as the first stage of a longer term rehabilitation effort of the identified hydropower plants. Again, in an emergency situation, appropriate capacity should be ensured in the implementing agency, and physical proximity to the project site where possible, is valuable. In this project, even with attention being paid to capacity and proximity, there were unforeseen delays arising from procurement and financial management processes.
P099062 | ShiZheng Railway Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2008 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/708791488986137645/text/ICRR-Disclosable-P099062-03-08-2017-1488986128873.txt | http://documents.worldbank.org/curated/en/708791488986137645/pdf/ICRR-Disclosable-P099062-03-08-2017-1488986128873.pdf | The ICR drew the following threelessons from implementing this project with some adaptation andediting.(1) Effective unified control over railway program and other large developments, design, financing andimplementation can achievesuccess, even when the Banks financial contribution is very small. In the caseof this project, the China Railway Corporation was solely responsible for planning, financing and implementing individual projectsand creating delivery mechanisms. The unified control over the project coupled with the overall commitment of the Governmentand the implementing agencies enabled timely completion of activities, despite the relatively marginal financial contribution fromthe Bank.(2) A large and linear infrastructure investment project requires not only good preliminary design andstrict control over compliance with standards but also a focus on post project measures to ensure sustainability. In thecase of this project the detailed design as implemented did not deviate significantly from the preliminary design, thus enablingsmooth progress in construction. Strict control over standards and technical specifications for railway construction and materialinputs supportedsmooth implementation of the project. Experiencefrom recently opened railway lines underlined thesignificance of Catenary Maintenance Vehicles (CMVs) to provide high levels of services to customers and based on thisChina developed a priority program aimed at strengtheningmaintenance and operation of its HSRnetwork through theCMVs.(3) Addressing passenger needs in the context of affordability is critical for achieving the full impact ofthe high speed rail network. Given that HSRnetworksrequire major budget allocations,investments in suchnetworks require economic and financial justification. Hence work on tariffs and services that address the specific needsofdifferent usersof rail transport, including estimating the price elasticityof demand among potential passengersfor high speed rail,is required for justifying future investments in suchnetworks.
P099062 | ShiZheng Railway Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2008 | 2016 | 2019 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/900521549297769514/text/129933-PPAR-P099062-P166863-PUBLIC.txt | http://documents.worldbank.org/curated/en/900521549297769514/pdf/129933-PPAR-P099062-P166863-PUBLIC.pdf | 7. Lessons from the Project Experience The following lessons are drawn from the project experience\. â€¢ Sound technical design, project preparation, and implementation management, combined with assured financial resources and effective interinstitutional collaboration, are a recipe for success for a complex HSR project. Like the NanGuang Railway Project, the ShiZheng Railway Project was completed on time with high quality and at a relatively low cost. This success was attributable mainly to sound preliminary design, meticulous planning, and strict control over compliance with standards and specifications, for which the CRC and the Ministry of Railways deserve major credit. The project's success was also attributable to the smooth coordination between the Ministry of Railways and the CRC with local governments on land acquisition and timely provision of counterpart financing. The World Bank contributed to the project's success through its guidance and support to ensure that the project's preparation and implementation met high standards, especially on social and environmental matters, even though its financing accounted for only about 5 percent of the total project cost. â€¢ Effective HSR system require certain preconditions. This and the other HSR projects in China showed that for a HSR system to be effective, a high and concentrated travel demand in an already congested corridor and customers with sufficient purchasing power are essential. This finding is confirmed by analytical work carried out under the parallel policy dialogue with the Chinese authorities. This work shows that the main prerequisites or success factors for embarking on a high-speed rail project are\. (a) an already congested trunk rail corridor (or if there is no rail link, a congested transport corridor) operating in markets with strong underlying growth; (b) a corridor of exceptionally high and concentrated travel demand; (c) even if there is demand, passengers need to have the purchasing power as HSR fares are expensive compared to the conventional rail; and (d) high interconnectivity to other modes16. â€¢ Successful reforms in large and complex infrastructure sectors such as railways involve sustained policy changes supported through long-term policy dialogue and engagements. When the ShiZheng Project was approved, China had already pursued many significant policy reforms in the railway sector for about 10 to 15 years while collaborating with the World Bank on capacity building and institutional development in multiple dimensions across the system. The government had also developed a framework for further reforms in the railway sector, was committed to these reforms, and asked the World Bank to provide advice on relevant international experience. The World Bank continued its policy engagements with the government on a parallel but separate path from implementation of this and other investment projects. The World Bank's policy advice was important in informing the reforms in China's railway sector, especially the 2013 landmark reform that separated the commercial management of railway services from the railway regulatory function, and established corporations for railway services delivery. â€¢ Agglomeration effects are an important benefit of high-speed rail development and could be incorporated in the cost-benefit analysis of such projects. In addition to traditional benefits, such as user time savings, operating cost savings for traffic diverted from the conventional lines, and reductions in environmental externalities, experiences of this and other projects in China and elsewhere have shown that a high-speed rail project also has significant agglomeration benefits. The magnitude of agglomeration benefits depends on local circumstances, such as industry structure, local conditions, and governance. The project appraisal did not assess the project's agglomeration benefits because the methodology for assessing agglomeration effects for HSR projects was still relatively new. The project completion report also did not assess agglomeration benefits to maintain comparability with the appraisal report. However, the IEG field mission observed signs of remarkable economic development in station cities along the ShiZheng HSR line that were more significant than those observed along the NanGuang Railway line were. If the agglomeration benefits were taken into account in the economic analysis, as in the NanGuang Railway Project, the ERR of the ShiZheng Project would be much higher. â€¢ Good connections of HSR lines with other transport modes and between the rail stations and urban centers are critical to achieving the full benefits of high-speed trains. Like the NanGuang Railway Project, the experience of the ShiZheng Project again shows that an HSR line involves a major investment and requires high traffic density to be economically viable. Integration of the railways with other transport modes is important to achieving high traffic density throughout the system and high-quality services to customers. Therefore, it is important to take measures at the design stage to ensure that rail station cities have detailed plans for a timely buildup of complementary infrastructure and the provision of services necessary for good local transport connections to the railway stationsâ€”for example, reliable and safe public transport and taxi services.
P099110 | PK: Pakistan Earthquake ERC | South Asia | Pakistan | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2006 | 2011 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/946961474628114902/text/000020051-20140625083333.txt | http://documents.worldbank.org/curated/en/946961474628114902/pdf/000020051-20140625083333.pdf | The following lessons are taken from the ICR with some adaptation of language:Clarity of Implementation Arrangements: One of the major factors that contributed towards timely completion of the project was the clearly defined implementation mechanism covering the federal, provincial/state, district and local level governance of the earthquake response. For the reconstruction activities, ERRA created parallel structures at the provincial/state levels and at the district level in the form of reconstruction units. In addition, partnerships were established with national and international NGOs with clearly defined roles and responsibilities which helped in ensuring timely and equitable assistance to the communities.Importance of coordination with all stakeholders: The earthquake response operation at its peak involved more than 80 stakeholders involved in housing reconstruction alone. To ensure coherence and avoid duplication, a Housing Strategic Working Group was established. By doing so, ERRA ensured strong commitment to common principles from among a very diverse range of partners. Coordination mechanisms were also set in place at federal level between ERRA, the army, and institutional partners. At village level coordination was carried out between the army, assistance and inspection teams, training mobile teams and village reconstruction committees.Owner Driven Reconstruction: The dividends of such a large reconstruction project can only be fully realized if an owner-driven, pro-poor policy ensuring equity is uniformly applied across an entire disaster affected area. Under the project, individual families used the financial assistance to rebuild their houses. The money was disbursed in installments and in accordance to compliance with earthquake resistant building standards.Anticipating and planning for cost escalations and capacity of construction industry: The increased investment in construction of destroyed houses placed pressure on the local capacity of the industry and saturation of the market due to increased demand and ultimately resulting in cost escalations. The project had to face serious risks in meeting the high demand for materials by allowing importation from neighboring countries.Mainstreaming disaster preparedness in emergency reconstruction projects can be of high value provided it does not delay the provision of urgent assistance to populations in need. This project was able to focus on reconstruction and livelihood support, while also supporting the creation of a culture of preparedness in the earthquake affected areas that was later replicated in the entire country.
P099112 | Anhui Highway Rehabilitation and Improvement Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2008 | 2012 | 2013 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/531301475089425650/text/000020051-20140625234102.txt | http://documents.worldbank.org/curated/en/531301475089425650/pdf/000020051-20140625234102.pdf | The ICR draws two lessons from the experience of preparing and implementing this project:A careful choice of M&E indicators, well tailored to the cause and effect relationships between the project interventions and their intended outcomes, is necessary in order to monitor not just progress in physical implementation, but also to gauge how much of the achievement of the project development objectives could be attributed to the project.The pilot performance based road maintenance contract could have yielded more useful lessons if the duration of the contracts had been longer and if they had been larger covering more road sections.
P099126 | Institutional Capacity Building Project for Procurement | South Asia | Bhutan | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2008 | 2011 | 2013 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/128051474943838882/text/000020051-20140626104040.txt | http://documents.worldbank.org/curated/en/128051474943838882/pdf/000020051-20140626104040.pdf | The main lessons that can be drawn from the experience of the ICR and IEG's review are:A capacity building project should focus on the "capacity to build capacity" during and after the project.Conditions relating to the establishment of units or institutions should focus not only on their formal creation but also on the provision of adequate financial and human resources.A detailed capacity needs analysis should have been carried out at the outset.The lessons identified by IEG are as follows:Exceptional procurement methods such as sole sourcing and turnkey solutions can have cost and quality implications if they are not properly justified at the outset, and verified during implementation. For instance, consultants involved in project preparation are best used in a supervisory role during implementation, especially when the Borrower has limited monitoring capacity. Extra efforts are needed to ensure that alternative suppliers have been identified, even in seemingly remote settings.Strong M&E is necessary, particularly in capacity building and institutional development programs. Any exclusion of indicators from ISR reports should be explained and followed either by a subsequent inclusion or a formal revision.
P099139 | Strengthening Public Information, Monitoring, Evaluation for Results Management in Colombia | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | IBRD | IPF | 2009 | 2015 | 2016 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/971281468197978000/text/ICRR14853-P099139-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/971281468197978000/pdf/ICRR14853-P099139-Box394823B-PUBLIC.pdf | The ICR (p. 25-26) identifies several relevant lessons, including the following:Taking technical and political economy considerations into account is essential when designing and implementing a whole-of-government M&E system. In order to ensure technical soundness and effective utilization by intended users, this project tailored the design of dashboards to the needs of the Office of the Presidency and line ministers. The time of project preparation can be used to ensure a sound project design but also to build capacity and consensus among key stakeholders. In this project, activities implemented during project preparation helped to align funding from various development partners.
P099166 | Poverty Reduction Support Credit (PRSC) | Europe and Central Asia | Moldova | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2008 | 2012 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/541601474906353493/text/000020051-20140624202629.txt | http://documents.worldbank.org/curated/en/541601474906353493/pdf/000020051-20140624202629.pdf | There are two key lessons: The experience of PRSCs 1 and 2 indicates that the Bank overestimated the ability of the government to execute the program and underplayed the interaction between parliament and government. The experience suggests that overlooking how organizations work and who is responsible for approving and implementing laws and regulations is likely to derail a reform program or parts of it and to delay its execution.The experience of PRSCs 1 and 2 also suggests that policy reforms that pay insufficient attention to the constraints of the government's institutional capacity are likely to lead to less than satisfactory results.
P099185 | EMERGENCY REHABILITATION OF THE DRAINAGE AND FLOOD PROTECTION SYSTEM OF BANDA ACEH | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Transport | RETF | IPF | 2006 | 2010 | 2011 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/238531474486679432/text/000020051-20140624185508.txt | http://documents.worldbank.org/curated/en/238531474486679432/pdf/000020051-20140624185508.pdf | 1.In an emergency situation where a government agency may be overburdened, a competent, experienced and well supported NGO can implement a project successfully while still fully involving the government agency. In this case the NGO was also able to make sure the local public works agencies developed ownership2. Emergency project design may need revision during implementation when all factors are known and more information is available. Flexibility of the government, implementing agency and the Bank is essential to agree on the necessary modifications to the project scope.3. Ample supervision resources, (in this case, supplemented by a trust fund) can make a difference to turn around an at-risk operation which had a rough start and to keep it on track 4. If an extra program or initiative is needed - but had not been included in the original project design and budget - and the implementer has the technical and community capacity to do so, it should be added in. In this case, it also responded directly to the priority concerns of the local population, as expressed during the community consultation meetings. Here, the immediate need for trash management to keep trash from damming up the valves and drainage systems was instituted and proved to be one of the most successful parts of the project.
P099201 | Judicial Modernization Project | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2006 | 2015 | 2017 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/636601483630390090/text/ICRR-Disclosable-P099201-01-05-2017-1483630373595.txt | http://documents.worldbank.org/curated/en/636601483630390090/pdf/ICRR-Disclosable-P099201-01-05-2017-1483630373595.pdf | Lessons in the ICR are supported, including the need to explicitly acknowledge and address the risks of hurried and elasticproject design and its impact on a projects empirical basis, government support, and efficacy. The ICR rightly identifies Bankcomparative advantage of smart court infrastructure that drives efficiencies and capacity to handle futuredemand.A lesson for future Bank engagement is that increasing client public sector capacity must be matchedwith authentic activities to drive increased demand via Bank comparative advantage in citizen engagement and citizen information.This is particularly applicable for Bank engagement in the justice sector (See World Bank, 2014, Strategic framework formainstreaming citizen engagement in World Bank Group operations: engaging with citizens for improved results; World Bank,2011. World Development Report 2011).Another lesson is that pursuit of project components thatlack government buy-in, often drives inadequate funding for those components, and may undermine implementation of otherproject components due to component interdependence.A further lesson for Bank practice in the justicesector is that government commitment may be particularly precarious around areas of justice sector practice that confront executivepower. Clarity of government commitment and of Bank intention for project components should be made clear prior to projectfinalization.
P099211 | Rural Distribution Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2008 | 2013 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/724401468186252673/text/ICRR14648-P099211-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/724401468186252673/pdf/ICRR14648-P099211-Box393183B-PUBLIC.pdf | In projects involving multiple implementing agencies early coordination and consultations between them and relevant authorities is of prime importance. In this project, the performance of implementing agencies was impacted to varying extents depending on the timing and coverage of engagement with all levels of government to resolve land acquisition and clearances in the rural areas of Vietnam. Community supervision of environmental safeguards can be a highly effective means of ensuring community ownership, minimizing disputes, and having rapid and ongoing compliance with environmental management plans. In this project, community supervision worked well with 22/35 kV system sub-projects where the distribution network is closer to the users.Flexibility in design and application of funds is essential when a project has a large number of sub-components that have to be implemented in challenging circumstances. This project gained from allowing flexibility for changes in design and gaining approvals, in order to allow for adaptation to unexpected changes in circumstances such as changes in costs, delays in procurement and implementation, and difficulties in land acquisition.Lack of provision for internal audit in implementing agencies can impact their overall accounting function and control framework. In this project, there were clear indications that the quality of financial reports and statements was below expectations, in the absence of arrangements for internal audit.
P099224 | Liaoning Third Medium Cities Infrastructure | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2008 | 2016 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/781721508334618969/text/ICRR-Disclosable-P099224-10-18-2017-1508334605939.txt | http://documents.worldbank.org/curated/en/781721508334618969/pdf/ICRR-Disclosable-P099224-10-18-2017-1508334605939.pdf | The ICR draws the following main lessons from implementing this project, with some adaptation oflanguage.(1) It would be more realistic to include asmaller number of sub-projects inmunicipal utility sectorsthat include a number of participating cities. This is particularly so when investmentsinvolve multiple sub-projects, borrowers, and implementing agencies across disparate geographic locations. Concentration on fewersub-projects could help in providing better implementation support.(2) A carefulassessment of the implementation timeline is required before making a decision asto whether to include a sub-project in aproject. In the case of this project, the delays associated with finalizing sub-projects in the wake of the financial andeconomic crisis in China contributed to delays during implementation, and eventually one sub-project could not be completed atproject closure.(3) The country context needs to be taken into account while deciding onfinancialcovenants, and these should be included at the utility level only when deemed to be absolutelynecessary.In the Chinese context, compliance with financial covenantsat the utility level depends largely ontariffs that are set by local governments often at below cost-recovery levels, for political reasons.However,localgovernments often provide financial support to compensate for the loss-making tariffs. Under these circumstances, non-compliancewith the covenants may not affect the ability of the project utilities to implement project investments.
P099226 | Juba Rapid Impact Emergency Project (TF055976) | Eastern and Southern Africa | South Sudan | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2006 | 2013 | 2015 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/792891475117854232/text/000180307-20141203053229.txt | http://documents.worldbank.org/curated/en/792891475117854232/pdf/000180307-20141203053229.pdf | The ICR lists a number of practical generic lessons, which as reformulated here include: (a) it is appropriate to rely on MTDFs to flexibly finance priorities in post-conflict countries; (b) a good results framework is critical to monitor and report on progress. An additional observation from this review is that M (c) approaches where donors or TA become a substitute for strengthening and empowering Government counterparts are counter-productive and undermine sustainable capacity building; and (d) lack of harmonization amongst donors results in reduced efficiency.Two other lessons emerge from the present review:1. Timely and sufficiently deep project restructuring and its PDOs and realistic reporting would contribute to improved project outcomes. In the case of this project, the restructuring came too late and was incomplete. In this case the first two restructurings were narrow and did not address fundamental design issues, notably with respect to redefining PDOs, which were misaligned and too ambitious given country circumstances. The ratings in ISRs appear to have been quite optimistic and this appears to have contributed to lack of timely recognition of project shortcomings.2. Fundamental changes to project design should be thought through and only pursued if it is consistent with concept and avoids significant increase in complexity. This project was designed to provide a fast response to emergency needs and stalled once the civil works component and another component (dropped later) was added.
P099231 | Financial Sector Support Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2006 | 2013 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/693001468184469923/text/ICRR14643-P099231-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/693001468184469923/pdf/ICRR14643-P099231-Box393183B-PUBLIC.pdf | The ICR offers a few lessons, which IEG supports. The Borrower highlights the importance of early involvement of implementing agencies, starting from the time of appraisal and negotiations. The Borrower also stresses the value of getting the results framework right from the beginning, including documenting the sources and ensuring availability of data to be collected.In addition, when a fundamental reform (of the oversight framework and approach to supervision) is being undertaken, it is likely that some of the smaller financial intermediaries in the system may face challenges in adapting to the new requirements. There is an opportunity to involve the IFC in the provision of advisory services, if the client so desire, to help those institutions adapt more effectively to a new environment. Such process would support a more effective implementation of the new oversight framework by strengthening financial intermediaries, buttressing system resiliency, and potentially market competition which in turn could lead to tighter spreads.
P099287 | Fifth Poverty Reduction Support Credit | Western and Central Africa | Ghana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2008 | 2010 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/735701474398218707/text/000020051-20140620084338.txt | http://documents.worldbank.org/curated/en/735701474398218707/pdf/000020051-20140620084338.pdf | One major lesson is that the dialogue in the context of PRSCs was clearly ineffective in influencing the government's policy of subsidizing electricity. Energy subsidies, including to the state-owned aluminum smelter, are a major drain on the budget, and other means will have to be found to strengthen this dialogue.A second lesson is that the PRSCs, although to a lesser extent than the debt forgiveness in the mid-2000s, while providing resources for social development, were counterproductive in their objective of promoting macroeconomic stability. The provision of generous budget support encouraged excessive public spending which eventually threatened fiscal sustainability.
P099295 | Emergency Social Protection Project | Middle East and North Africa | Iraq | IBRD | FCS | Human Development | Social Protection & Jobs | RETF | IPF | 2006 | 2013 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/368261474665144814/text/000020051-20140626122738.txt | http://documents.worldbank.org/curated/en/368261474665144814/pdf/000020051-20140626122738.pdf | Lessons derived from the ICR (pp. 20-21):Partnerships with other organizations on the ground can become an important factor in moving ahead when Bank teams' on-the-ground presence is constrained. In Iraq, the Bank was able to benefit from an ongoing USAID project in MOLSA that complemented Bank activities, and was able to provide on-the-ground preparation and implementation support to the project Flexible adaptation of procurement methods that recognizes exceptional market conditions while remaining within Bank guidelines may be essential for timely implementation. Under this project, while implementation was not timely, modifying the strategy for procurement allowed the project to move forward, albeit not as fast as expected, and introduced unexpected cost savings. Lesson offered by IEG:Risk assessment should be rigorous and expectations regarding mitigating measures particularly cautious when entering an environment of still-great uncertainty regarding security, and one where skills and capacity have eroded over time and the loss of even a few trained implementing agency staff can lead to severe setbacks. In this instance, thorough preparation did avoid substantive setbacks during implementation, and risk factors were mainly reflected in implementation delays
P099296 | NP Irrigation & Water Resources Management Project | South Asia | Nepal | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2008 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/930011558532856868/text/Nepal-NP-Irrig-Water-Res-Mgmt-Proj.txt | http://documents.worldbank.org/curated/en/930011558532856868/pdf/Nepal-NP-Irrig-Water-Res-Mgmt-Proj.pdf | IEG has drawn following lessons based on those in the ICR (p.29-30) with some changes inlanguage: Errors in cost assumptions at project preparation can lead to significant cost overruns,implementation delay, and subsequent reduction of the final project scope. In this project there wasinadequate attention to the accuracy of unit construction costs and to realistic future inflation of costs overthe project implementation period. These shortcomings resulted in the need for additional financing, delayed procurement and areduced scope of the project. To minimize implementation delay, terms of reference for technical studiesrequire careful discussion and agreement among stakeholders during project preparation and appraisal. Initialdelaysin the development of the River Basin Management Plans in this projectunderlined the importance of finalizing terms ofreference for technical studies at appraisal in order to have an agreed and precisely specified terms of reference fortheconsultancy services required and hence provide for an early start to the procurement of consultants to undertake thetask. The design of an integrated user-driven ME system for a multi-agency project should beaccompanied bya practical implementation plan. Despite strong coordination between DoI and DoA on theimplementationof this projects activities, there were challenges to establishing, maintaining and utilizing theintegrated ME system as envisaged during appraisal. For projects that involve ministries or departments as counterparts, anintegrated ME system that collects and evaluates critical information on a projectsperformance for a centraldatabase is a vital tool to monitor andassess a projects progress and achievements.
P099313 | MW-PRSC-1 | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2008 | 2012 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/725301474854089207/text/000020051-20140625083421.txt | http://documents.worldbank.org/curated/en/725301474854089207/pdf/000020051-20140625083421.pdf | The ICR highlighted six key lessons learned from the implementation of the PRSG series that are appropriate, noteworthy, and should inform the preparation of future DPOs. 1. The importance of government ownership. Key institutional reforms in agriculture and social protection were not implemented because of a lack of buy-in across the government. 2. The need to assess the political economy of sensitive reforms. The political economy dimensions of certain key reforms under the PRSG series (i.e., maize marketing, fertilizer subsidy, and social protection) were underestimated. As result, progress in implementation in these areas was slow and policy reversals occurred. 3. There is merit in working within a harmonized framework. CABS provided the authorities and Bank staff with a harmonized framework for the provision of budget support that also enhanced the quality of policy dialogue across donors and provided political leverage for good governance. 4. Flexibility in the program assessment framework should be encouraged. It is difficult to foresee all the relevant issues and internal/external developments at the beginning of a DPO series. 5. A robust and flexible M&E framework is important for tracking progress in PDOs. The MGDS M&E framework did not generate sufficiently comprehensive information for monitoring outcome indicators, particularly regarding tobacco market, fertilizer market, and commercial justice reforms. 6. The bar for policy reform should be set sufficiently high enough to mobilize change while avoiding overly ambitious and complex measures. An important lesson learned from earlier DPOs was that programs should be focused given existing institutional capacity constraints.
P099321 | Renewable Energy for Rural Access Project (REAP) | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2007 | 2012 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/182811475080172467/text/000020051-20140625234238.txt | http://documents.worldbank.org/curated/en/182811475080172467/pdf/000020051-20140625234238.pdf | The lessons of broader significance from the ICR are the following: (i) Transfer of international experience requires care and adaptation: International experiences in energy efficiency promotion are generally transferable, but to be effective they have to be carefully selected and customized to suit local conditions. (ii) Smart subsidies are effective: Targeting subsidies are effective in promotion of, and removal of barriers to, energy efficiency. The effectiveness of such subsidies would be better if distortions in fuel subsidies are minimized or removed (e.g. diesel subsidies to utilities would reduce incentives to select other renewable options).(iii) Safe handling and disposal of batteries is essential: In addition to the above two lessons noted in the ICR, the project has highlighted the need for adopting appropriate safety and mitigation measures for ensuring proper handling and disposal of batteries with hazardous chemicals, including adequate funding and institutional responsibility for ensuring implementation.
P099321 | Renewable Energy for Rural Access Project (REAP) | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2007 | 2012 | 2018 | PPAR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/868691530296027073/text/127225-P099321-P167001-PPAR-PUBLIC.txt | http://documents.worldbank.org/curated/en/868691530296027073/pdf/127225-P099321-P167001-PPAR-PUBLIC.pdf | 7. Lessons â€¢ An appropriate balance between affordability and cost recovery is essential for scaling up the adoption of portable renewable energy systems by those who cannot afford the full investment costs. Smart subsidies to the targeted populations help to make the acquisition of renewable energy equipment possible. Cost recovery ensures the targeted population's ownership of the equipment so that it is used and maintained on a sustained basis. Cost recovery also allows funding to be leveraged by redeploying the recovered costs to finance smart subsidies for additional consumers, thereby expanding the scale of technology adoption. In Mongolia, although smart subsidies allowed a 50 percent reduction in the investment costs of herders, those costs still entailed about a third or more of annual cash income for 40 percent of the herder households. Nonetheless, the herders were expected to cover the remaining 50 percent of investment costs to ensure ownership and demonstrate ability to maintain and service the equipment. â€¢ Proper market assessments are an essential requirement for projects that rely on the private sector for distribution of equipment, after-sales service, or the operation of local off-grid utilities. In small dispersed markets, scale may be insufficient for profitable private sector participation. In those circumstances it is important to determine whether the private sector has the financial capacity to benefit from purchasing the equipment at wholesale prices or to take on utility operation and maintenance. In Mongolia, owing to limited financial capacity, concentration in the capital city, and logistically challenging and small-scale market of herders, sales of SHS equipment by private dealers were slow. Similarly, owing to weak institutional and operational capacity of soum center utilities, the project-installed RDHT systems were transferred to be managed by aimag utilities. â€¢ To be sustainable and to realize the potential for expansion in demand, RETs require established and regulated equipment quality standards to guide purchases, and proper handling and disposal of used SHS batteries. The equipment supplied through the project met international technical standards, but the Mongolian market has an abundance of poor quality products sold by individual entrepreneurs at a low price. Experience with such products may adversely affect demand for RETs. Similarly, early attention and support is needed to build local capacity for proper battery management and recycling to avoid adverse effects on health and on the environment from improper handling and disposal of used SHS batteries that contain toxic chemicals. Although the project supported a feasibility study for a used battery recycling factory, no investment in such a facility had materialized by closure. â€¢ Regular dialogue and consultation at the appropriate client government level regarding government policy intentions and their consequences are critical to inform project design and implementation. In this project, accelerated connection to the main grid affected both the demand for renewable energy technology and the optimal technical solutions to be adopted. Institutional, regulatory, and managerial arrangements were modified by the decision to hand over the newly rehabilitated RET systems to the nearest centralized energy supply companies at the aimag level. In another instance, the adoption of a Renewable Energy Law in January 2007 largely eliminated the anticipated need for the project to support the development of a regulatory framework and associated legislation for grid-connected RDHT systems.
P099327 | Fifth Population Census of Sudan | Eastern and Southern Africa | Sudan | IDA | FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2006 | 2009 | 2011 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/517361474593024814/text/000020051-20140620080931.txt | http://documents.worldbank.org/curated/en/517361474593024814/pdf/000020051-20140620080931.pdf | As part of the CPA process, and as a key input to sensitive electoral and resource sharing negotiations, conduct of a census is by its nature a politically sensitive exercise, particularly in a setting such as Sudan. By focusing on assuring a high level of technical support through close coordination with UNOPS and UNFPA, which both Bank and Borrower acknowledge performed in a highly satisfactory way, the Bank was able to contribute to success despite its relative lack of expertise in census implementation and oversight. The ICR importantly documents that census operations are highly specialized, and need major technical support, particularly in countries with little relevant expertise and major logistical and political challenges. It is clear that the UNFPA is a qualified international organization able to provide the necessary technical and managerial support, albeit at high cost, but effective management of this relationship relied on good support from the country mission as well as considerable effort to iron out Bank/UN agreements on fiduciary and audit arrangements.
P099357 | Sierra Leone Mineral Sector Technical Assistance | Western and Central Africa | Sierra Leone | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2010 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/976361521829519555/text/Sierra-Leone-SL-Mineral-Sector-Technical-Assistance.txt | http://documents.worldbank.org/curated/en/976361521829519555/pdf/Sierra-Leone-SL-Mineral-Sector-Technical-Assistance.pdf | The ICR (pages 25-26) draws the following main lessons from the experience of implementing this project (with some modificationof language).(1) Technical assistance for increased transparency in regulation in extractive industries can providesubstantial value for money in diminishing country risk perception by investors/licensees and expanding sectorrevenues.(2). A strong and functional regulatory agency with professional capacity can aid in improving the performance ofthe extractives sector by: (i) providing clear guidelines and information to investors: (ii) efficiently managing mining licenses:(iii) developing regulations for mining operation and production, ensuring the correct collection of royalties and taxes: and, (iv)better managing community relations.(3) Project scope needs to address key issues either during entry or sequentially. Theoriginal funding for this project was inadequate in relation to the challenges of the mineral sector. The project design followed aportfolio design with the Bank financing some activities and some complementary activities financed by other donors (discussed insection 2e). Following the AF approval, the project focused on activities aimed at Extractive Industries Transparency Initiative(EITI) validation.(4) The project design needs to be kept relatively simple, particularly in countries with a weakimplementation record.
P099369 | Ceara Regional Economic Development: Cidades do Ceara | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2009 | 2017 | 2018 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/827191507731701271/text/ICRR-Disclosable-P099369-10-11-2017-1507731677414.txt | http://documents.worldbank.org/curated/en/827191507731701271/pdf/ICRR-Disclosable-P099369-10-11-2017-1507731677414.pdf | From ICR ReviewerThe impacton stakeholders of changes in land valueresulting from infrastructure investments needs to be considered in the design and during the implementation ofoperations. In the case of the Ceara Regional Development Projectan important impact has been the increase in landvalues around Bypass and the Seminary Neighborhood. The impact waspredictable andprovisions should have been madeto ensurethat there would not beshort and long term adverse effects on vulnerablepopulations.From ICR with adaptations in languageEnsuring that a critical number ofdetailed designs and resettlement action plans are ready by appraisal should be standard practice to reduce risks of delays andcost overruns during implementation. As the project lacked detailed engineering designs and resettlement action plans withclear cost estimates, significant efforts during supervision were devoted to preparing technical designs and addressing safeguards.Many changes in overall project scope and the frequent changes in designs hampered project implementation. In addition, theprohibitive costs of resettlement for municipalities required the team to seek alternatives during project supervision thatminimized resettlement.Municipal level investments identified by local authorities have a much higherlikelihood to succeed than regional level investments without clear ownership. The project had difficulties building necessarysupport to the regional landfill, a key regional activity, due in great part to delays stemming from lack of ownership by themunicipalities. It was eventually dropped due to the increase in costs. Conversely, municipalities showed strong ownership forlocal, smaller scale initiatives from the Seminrio District urban upgrading to the plazas in historic Barbalha and provided support to ensure completion of these investments.Financing Metropolitan/regionalinfrastructure can bring different actors together and requires leadership and incentives.In Cariri, the discussions around the construction of a long awaited regional landfill were intended to catalyze ametropolitan management approach that would eventually extend to other sectors and address governance issues. The process ofdeveloping the regional landfill succeeded in bringing together mayors and different municipal agencies. However, the process wasmostly driven by the Bank team and lost momentum when financing for the landfill was dropped from the Project and the Committee wasbasically dissolved.Changes in the composition and high turnover of the Bank and Government teamshindered project implementation. The Project had seven task team leaders on the Bank side, as well as numerouspersonnel changes on the Government side. In addition, the Bank team engaged expert consultants and staff in private sectordevelopment at preparation but in later stages of the project staff lacked the necessary technical profile.The PIU alsoappeared to lack sufficient senior staff who are able to convene the various public agencies and private entities that needed to bemobilized across the diverse project activities.
P099420 | Poverty Reduction Strategy Credit | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2009 | 2013 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/586191475084021997/text/000020051-20140625220452.txt | http://documents.worldbank.org/curated/en/586191475084021997/pdf/000020051-20140625220452.pdf | IEG supports several of the lessons identified by the ICR (with some modifications), including:The ICR correctly notes that the decision to suspend budget support series can serve a strong signal in countries undergoing governance crises. At the same time, it raises important questions about the readiness of countries to sustain DPL series over the long term (or their demonstrate their readiness to revive a DPL-supported program). It is important for various donor partners to be clear about the benchmarks for withdrawing or reviving support.DPLs that support governance reforms should be based on rigorous political economy analysis, including a review of larger dynamics that threaten political stability. There is also need for much greater clarity on what constitutes feasible governance reforms and monitorable indicators of progress (for instance, measurement of actual levels of corruption are nearly impossible to determine with accuracy and precision, whereas assessments of opportunities to exercise discretion are doable).The provision of supplemental financing in parallel to the withdrawal of PRSC support can send mixed signals and should be thought through carefully.In capacity weak settings, there is often a needed to complement a DPL series with a more extensive capacity building and technical assistance program in parallel.
P099453 | Avian Influenza Control & Human Pandemic Preparedness & Response Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2006 | 2012 | 2014 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/495381474502427630/text/000020051-20140625223600.txt | http://documents.worldbank.org/curated/en/495381474502427630/pdf/000020051-20140625223600.pdf | The ICR reports a number of lessons, including:A global template can enable rapid, good project design. The GPAI template was in place and was used as the basis for the preparation of this project;Crisis response can be an opportunity for supporting long term capacity improvements. This longer-term vision opened the opportunities for progressive improvements and establishment of sustainable systems;Expanding objectives to beyond a single disease can help to support a more comprehensive solution. In this case, the project maintained relevance by expanding objectives to address other needed diseases, and this help to support a longer term One Health approach through a follow up regional project
P099460 | Vietnam PCB Management Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2009 | 2015 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/886721468435533382/text/ICRR-Disclosable-P099460-07-13-2016-1468435528250.txt | http://documents.worldbank.org/curated/en/886721468435533382/pdf/ICRR-Disclosable-P099460-07-13-2016-1468435528250.pdf | A number of useful lessons were identified in the ICR. These included that establishment of a proper regulatory framework forPCB management is a priority, that inventory design needs to take into account actual data availability and quality, and thatpublic outreach activities need to be carefully designed, tailored to the right audiences, and appropriately timed.A moregeneral lesson not mentioned in the ICR, however, is the need to ensure that adequate project management -- including PMUprocurement -- capacity is in place at the time of project start-up in order to avoid potentially costly implementation delays,which can also have an adverse effect on project outputs and outcomes, as, indeed, appears to have occurred in the presentcase.In addition, while the project is to be commended for containing a specific monitoring and evaluation component, withthe allocation of considerable resources for its implementation, it is likewise important to design project performance and impactevaluation arrangements up-front as part of preparation and to assess them as part of the appraisal process, which appears not tohave been done in this instance.
P099469 | Second National Environmental Project - Phase II | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2010 | 2016 | 2017 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/701601497031596330/text/ICRR-Disclosable-P099469-06-09-2017-1497031585794.txt | http://documents.worldbank.org/curated/en/701601497031596330/pdf/ICRR-Disclosable-P099469-06-09-2017-1497031585794.pdf | The following lessons are taken from the ICR with some adaptation of language.(1) Client ownership needs to beaccurately assessed at each stage in project preparation. The case of this project showed that the political andinstitutional context may change from project preparation through appraisal, and this may entail changes in priorities andinterests.(2) Institutional strengthening activities should be based on addressing specified, identified problemswith specific measures at project start. In the case of this project, project preparation did not adequately analyze theweaknesses in federal and state agencies. Activities were left to be proposed by the agencies after approval and this resulted indelays associated with preparing sub-projects.(3) An adequate ME and Results Framework isrequired. Even if the PDO was broad as in the case of this project, it would have helped if the PDO was complementedwith specific and more concrete special activities and verifiable results indicators.
P099542 | PK Earthquake Disability | South Asia | Pakistan | Blend | Non-FCS | Human Development | Social Protection & Jobs | SPF | IPF | 2007 | 2010 | 2011 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/374031474904760226/text/000020051-20140624164208.txt | http://documents.worldbank.org/curated/en/374031474904760226/pdf/000020051-20140624164208.pdf | A strong results framework without adequate associated outcome and output indicators is ineffective. The aftermath of an earthquake may not be the best opportunity to introduce programs with new and untested approaches, because there is need for building ownership of the new approach at the government, local government, and community levels before its introduction.
P099585 | AR Cordoba Road Infrastructure | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2007 | 2014 | 2015 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/710821475115788578/text/000180307-20150112081235.txt | http://documents.worldbank.org/curated/en/710821475115788578/pdf/000180307-20150112081235.pdf | The following lessons are taken from the ICR with some modification of language.Projects that facilitate direct interaction with sub-national Borrowers have a better chance of success. In the case of this project, direct lending to a sub-national government (the Province), obviated one layer of bureaucracy, and coupled with Bank field based support to the implementing agencies, greatly helped in implementation.Projects aiming at securing and timely budgetary allocation need to take a comprehensive view of issues related to "fiscal space." These include (i) a thorough assessment of the present and future needs for road rehabilitation and maintenance, and (ii) an assessment of the financial and institutional capabilities of the Borrower. Based on this assessment, the project needs to develop the right mix of instruments (taxes, user fees, debt, or mobilization of private financing) to create the fiscal space necessary to achieve the intended objective.The lessons from this project indicate that, In countries with records of high inflation, operations should be guided by an analysis which would include : (i) sensitivity analysis around the impact of price changes on physical targets; (ii) transparency measures through strengthening the governance framework around the project; ,(iii) creating incentives for cost control by proactively addressing inflation concerns in bidding documents;, and (iv) strict supervision and management control during implementation to ensure projects are completed on time and hence do not create cost burdens relating to unanticipated price adjustments.
P099618 | MA-Energy Sector DPL | Middle East and North Africa | Morocco | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2007 | 2008 | 2010 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/753151474492331897/text/000020051-20140620073151.txt | http://documents.worldbank.org/curated/en/753151474492331897/pdf/000020051-20140620073151.pdf | A number of lessons can be drawn from the preparation and implementation of this operation:Implementation arrangements for a complex reform program such as this should ensure a robust institutional structure remains in place, with clearly assigned responsibilities and accountability at both the political and technical levels.It is preferable to avoid a coincidence between the inception of such programs and a change in administration in the Borrower's country. If this is absolutely unavoidable then the design of the program, and especially its timetable, should take account of the likely delays resulting from the new government's need to study the program and adopt it as its own.A solid M&E system which can be used by both the Borrower and the Bank, and which enables, inter alia, an evaluation of the impact of reforms, is an essential precondition for timely success of such a reform program as this.A sound, thorough, and collaborative analytical preparation is a necessary but not a sufficient condition for success-- due attention must also be paid to the time needed for the implementation of legal reforms and sector strategies, including the preparation and application of the decrees and ministerial decisions required to give new laws practical effect.
P099626 | Energy Sector Support Project | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2019 | 2020 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/202531578409075979/text/Malawi-MW-Energy-Sector-Support-Project.txt | http://documents.worldbank.org/curated/en/202531578409075979/pdf/Malawi-MW-Energy-Sector-Support-Project.pdf | 1. Contract management without the EngineerThe project encountered a unique situation where the Engineer was unable toprovide their services due to the debarment in another country. Given the remaining time for the project and unrealistic situationto procure another supervision consultant, the project decided to allocate the supervision role to the Owner for the last year ofthe project. The project was closed successfully largely due to the better relationship between the Owner and the Contractorbecause the Contractor had worked with the ESCOM and known the working environment. However, the fundamental basis of the contractdocument is the tripartite relationship among the Owner, the Engineer, and the Contractor. The absence of the Engineer might haveintroduced unfairness to the Contractor given the General Conditions of Contract unless the Special Conditions of Contract amendedit. For instance, when conflict occurs between the two parties, the Engineers judgment is not mobilized and automaticallylead to higher dispute resolution mechanisms. When such a situation occurs in the future, a careful review of the contract documentis essential to allow a level playing field for the parties involved in the contract.2. Improving the sustainability ofthe project through partnershipThe project demonstrated an exemplary partnership engagement with MCC. Given theindependent nature of achieving the PDO and expected results, the project chose a stand-alone project. Nevertheless, the projectclosely worked with MCC partly because the reform of financial and operational management policies and procedures were executed bythe MCC project. The Bank closely coordinated with the MCC from the design of the MCC project to the reform of the program ofpolicy reforms. The project benefited from the two tariff reforms, which were not in the conditions or requirements of the projectand were recognized as one of the binding factors in the electricity sector in Malawi. The outlook for financial riskswas consequently mitigated with the tariff reforms. Leveraging other players in the sector is crucial when the project entails acritical factor that the project cannot address.
P099630 | Judicial Reform Project 2 | Europe and Central Asia | Armenia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2007 | 2013 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/300201475093032819/text/000012394-20150409083115.txt | http://documents.worldbank.org/curated/en/300201475093032819/pdf/000012394-20150409083115.pdf | The ICR notes four lessons, one being that selective use of independent project monitoring mechanisms, especially of an expert character, can bring credible feedback on project performance. Although the lessons are correct, the lesson concerning use of independent monitoring mechanisms (in this instance the American Bar Associationâ€™s JRI) is broad and it is worth noting that such use of outside indices is open to manipulation and distortion given that selection bias of indicators within the external index source can occur and as is noted the external index may also be discontinued during project implementation, as happened with BEEPS. In addition to the lessons noted in the ICR are the following :- 1. For a project that consists predominantly of civil works there needs to be a clear plan for the construction activities and what can realistically be achieved, with a blueprint for buildings, list of civil works and rationale and a project implementation plan rather than a prioritized list dependent on the extent of the funding, and an operational manual to guide project implementation. 2. A complex area such as judicial reform requires considerable analysis and design of different means of support to achieve greater efficiency, reliability and transparency in the sector. The provision of buildings and hardware with minor training and technical assistance is not enough. Careful analysis of strategic change, governance issues, regulatory lacunas, the profession and judicial sector staffing needs, and introduction of professional standards and accreditation may be the most effective way to achieve the objectives.3. Where there is a strong donor presence and several donor agencies are active in the sector it is necessary to have donor coordination and collaboration and a united strategy. This is particularly true when the objectives (efficiency reliability and transparency) hinge on the success of donor sponsored programs and the Bank is financing IT and rehabilitation and infrastructure which can only be part of the changes required to achieve the objectives.
P099738 | Local Government Support Project - Scale-up | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2006 | 2012 | 2016 | PPAR |  | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/560671468197929695/text/103701-PPAR-SecM2016-0082-Box394870B-OUO-9.txt | http://documents.worldbank.org/curated/en/560671468197929695/pdf/103701-PPAR-SecM2016-0082-Box394870B-OUO-9.pdf | 7. Lessons 7.1 The lessons from this operation are as follows\. Â· First, decentralization is a long and complex process and requires strong government commitment and broad-based support and buy-in from key stakeholders in government to ensure its successful implementation. While donor support is important, no amount of technical and financial support from donors can compensate for the lack of commitment from government. In the case of Tanzania, the decentralization agenda starting in the 2000s was driven by the donors and government commitment was not sufficiently broad to encompass the diverse range of stakeholders. The government had a primary interlocutor through PMO-RALG but buy in of the decentralization reforms did not include key stakeholders including the President, Parliament and the Ministry of Economy and Finance. Â· Second, rapid scaling up poses challenges to capacity. In a nascent intergovernmental transfer system where capacity is uneven and resources are limited, covering a small number of LGAs and building on success before scaling up (versus spreading quickly to respond to political pressure) is preferable and needs careful sequencing. In the case of Tanzania, the decision to do it gradually at the outset was warranted but the subsequent rapid expansion to all LGAs created challenges that seriously strained capacity and credibility of the system. Â· Third, the decentralization agenda cuts across sectors. Hence, interventions within and across sectors and in support of broader government public sector reforms need to be well coordinated to guarantee real synergies and impact. In the case of Tanzania, decentralization is led by the urban sector and the project's design and implementation did not include explicit linkages to broader public sector reform interventions such as Public Sector Reform Project and general budget support that could have improved the project's impact and sustainability. Â· Fourth, the provision of unconditional capital grants transfers along with recurrent grants is critical to ensure sustainability of assets created under the project. In the case of LGSP, the separate provision of capital grants from the recurrent grants, combined with lack of clear accountability for O&M, increase the likelihood that development outcomes are not sustained. Â· Fifth, improving local revenue raising opportunities enhance fiscal autonomy of decentralized local government authorities; however, political support and clarity of accountability are needed to make it work. In the case of LGSP, enhanced local revenue performance was included in project design, but it did not gain much traction due to lack of political support and buy-in from key stakeholders, and lack of clarity in accountability between local and national level authorities.
P099751 | Sustainable Development in Poor Rural Areas | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2010 | 2016 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/567111476311629931/text/ICRR-Disclosable-P099751-10-12-2016-1476311621695.txt | http://documents.worldbank.org/curated/en/567111476311629931/pdf/ICRR-Disclosable-P099751-10-12-2016-1476311621695.pdf | The following lessons are drawn largely from the ICR with some amendment of language. An effectiveME system from the outset is critical, particularly for an innovative CDD operation with multiple indicators and manyagencies. Unfortunately, in this case, the lead implementing agency was initially reluctant to spend funds on monitoringand evaluation despite the fact that it represented less than one half of 1% of total project costs. Communityfacilitators can play an important role particularly in a situation where many educated villagers and youth migrate to cities foremployment. In this case, community facilitators were able to fill a number of roles including: mobilizing villagers;liaising with the project office, local government and village groups; maintaining records, particularly financial records; andensuring transparency. A CDD project can help to greatly improve and change the relationship between governmentofficials and households at community level. In this case, in a situation where past approaches had been predominantlytop-down, the project was able to develop and demonstrate processes and procedures to involve beneficiaries through the entireprocess of identifying and selecting activities, contracting, supervising implementation, and operation andmaintenance.The ICR notes in the lessons section that it was unfortunate that the Rural MigrantsSupport component was dropped and the Municipality concerned did not take the opportunity to test innovative solutions to thissubstantial social challenge. The ICR notes that there remains an urgent need to test and develop solutions to address challengesfaced by poor rural migrants in China.
P099757 | Geothermal Power Generation Development | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2008 | 2013 | 2015 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/740131475328189385/text/000012394-20150108151139.txt | http://documents.worldbank.org/curated/en/740131475328189385/pdf/000012394-20150108151139.pdf | The ICR presents four lessons and the most important was: In preparation for public-private partnerships and investments all the necessary regulatory and financial incentive mechanisms should be put in place and discussed with all stakeholders before project preparation even begins. This is necessary when private investors are expected to come forward with financing for the investments expected to result from project interventions in order to reduce risks and cost of entry, as for example in geothermal power. IEG adds another lesson: Before considering support for projects in renewable energy, particularly in geothermal power, it is important to establish that data on below-the-ground conditions are reliable and accepted by the investor community.
P099808 | Avian Influenza Control & Human Pandemic Preparedness & Response Project | Europe and Central Asia | Georgia | IBRD | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2006 | 2011 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/670501475090871935/text/000020051-20140625074237.txt | http://documents.worldbank.org/curated/en/670501475090871935/pdf/000020051-20140625074237.pdf | The ICR notes that:Flexibility in the design and implementation of an emergency project is important. With less time for design and with the chance that project priorities may change as events unfold, the design cannot be set up to envision all possible needs.Developing multi-sectoral contingency plans is an important aspect of disaster preparedness. Such plans can enable a more effective and better coordinated response.IEG also notes that:Monitoring and evaluation systems that only track completion of outputs will not be effective in assessing project impact.Biosecurity Level 3 laboratories may not be needed or justified on a cost-effective basis for small countries.
P099811 | TN-Tunis West Sewerage | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2007 | 2015 | 2017 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/430131472846308011/text/Tunisia-TN-Tunis-West-Sewerage.txt | http://documents.worldbank.org/curated/en/430131472846308011/pdf/Tunisia-TN-Tunis-West-Sewerage.pdf | The ICR presents nine (9)lessons some of which are formulated rather as recommendations, hence this review selects and slightly rephrases thefollowing: Candid project ratings are key to timelyproactivity to address project shortfalls and manage problem projects effectively:Throughout projectimplementation, project ratings where not adjusted to reflect emerging issues and risks. This concurred to misalignments in thatproject management were unable to independently verify the projects capacity to achieve the development outcome andrecommend corrective and timely actions where needed. More systematic procurement and contract managementguidance and support could prevent major contractual shortcomings and mitigate their impacts.Despite thegenerally compliant procurement status throughout the project implementation, broader and more effective approach would haveminimized some of the implementation hindrances that can compromise the achievement of the PDO. According to the TOR, theBank, in the case of Tunisia, is addressing these problems through (i) technical assistance and sector dialogue with the nationalprocurement board since 2015 and through (ii) the establishment of new procurement guidelines. Aproject-specific technical assistance is key for efficient and effective project implementation and for capacity building of theimplementing entities if strategically used.Regardless of the amount of experience the implementingagencies might have, as was the case of ONAS in Tunisia, the ICR acknowledges that implementation of large infrastructure contractsrequires strengthened capacities to monitor and sustain progress. One of the says to do that is, according to the TOR,through a better utilization of Technical Assistance and a successful example from Tunisia is that of Northern Tunis wastewaterproject where two separate firms provide supervision of the land and marine works for that project. This arrangement,however, would require a well elaborate definition of roles and responsibilities and cost-effectiveness analysis to avoidduplication and a cumbersome structure if two firms are overseeing the same project.
P099832 | Avian Influenza Preparedness Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2006 | 2011 | 2012 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/545551474483652099/text/000020051-20140624200522.txt | http://documents.worldbank.org/curated/en/545551474483652099/pdf/000020051-20140624200522.pdf | The ICR proposes the following lessons:Some aspects of emergency response (e.g., procurement of protective gear) can be carried out quickly and do not require detailed preparation; this is not the case for institutional strengthening.If donor coordination is to work, the implementation schedules of the various agencies need to be flexible and the costs entailed by coordination need to be acknowledged up front.If M&E is to be an effective management tool, indicators and targets need to be realistic and progress needs to be reported regularly so that problems can be identified early on and prompt corrective action taken.Project-specific coordinating bodies located outside the civil service create parallel lines of communication and weaken the engagement of the line agencies that should be responsible for the sector.
P099832 | Avian Influenza Preparedness Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2006 | 2011 | 2012 | PPAR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/563821468004474881/text/704880PPAR0P090C0disclosed070110120.txt | http://documents.worldbank.org/curated/en/563821468004474881/pdf/704880PPAR0P090C0disclosed070110120.pdf | 7. Lessons 7.1 There are three lessons\. * A three-year emergency project is appropriate for quickly building some surveillance, diagnosis, and response capacity to rapidly tackle an immediate threat but is unsuited to a deepening and broadening of institutional capacity for more systemic reforms. An alternative would have been to launch a quick emergency project followed by an overlapping longer term institutional reform and capacity building project with the broader animal disease focus designed in a more measured way. * In projects aimed at preventing or preparing for a potential disease threat with an uncertain probability and magnitude of impact, the results frameworks need to anticipate how success will be measured both in the event that the anticipated threat materializes and in the event that it does not. Indicators would need to measure changes in preparedness in terms of changes in the efficacy and the efficiency of surveillance, diagnosis, and control response to understand attribution of the results to the project's interventions. * Failure to effectively manage communications can lead to unproductive panic, insufficient public knowledge, and erosion of faith in public authorities. In the case of this project, while the early crisis awareness materials themselves were generally well conceived, there were some unexpected responses and some lessons. Carefully designed, timed and targeted public communication following established protocols and communication principles, drawing on professional communications skills, is likely to facilitate emergency response when there is little time to plan. There is an established science of communications that can be locally adapted and tested to ensure communications readiness and to develop national and sectoral strategies. In this case, the opportunity for a comprehensive communications strategy and capacity development for the future was not seized.
P099833 | Economic & Monetary Community of Central Africa Financial Institutions | Other | Africa |  |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2009 | 2016 | 2017 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/560941498854312395/text/ICRR-Disclosable-P099833-06-30-2017-1498854300798.txt | http://documents.worldbank.org/curated/en/560941498854312395/pdf/ICRR-Disclosable-P099833-06-30-2017-1498854300798.pdf | IEG agrees with thelessons learned and presented in the ICR, which underscore thefollowingmain themes: (i) theimportance ofa good theory of change and a results framework to track and report progress, (ii) the central role of adequateimplementation arrangements, (iii) the need for simplicity in the project design and the rigorous selection of implementableactivities, (iv) the irreplaceablerole of Banks internal coordinationto ensure that every stakeholder in theBanks Global practices providetheexpertise and experience that the Bank can bring to bear for each operation,and(v) the implementation of regional projects needs special attention, because broader geographical coverage presentspecific ownership and coordination challenges.An IEG lesson arising fromprojectimplementationisthat shortcomings inproject design lead to major consequencesfor a projectsperformance. When a project is not well designed, itssuccess will almost always require a restructuringfor anychance for the project to generate theoptimal results. When the restructuring does not take place like in thiscase,project performance will likely beaffected.
P099840 | Public Financial Management Modernization | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2009 | 2015 | 2016 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/436141468335528057/text/ICRR-Disclosable-P099840-06-23-2016-1466709624604.txt | http://documents.worldbank.org/curated/en/436141468335528057/pdf/ICRR-Disclosable-P099840-06-23-2016-1466709624604.pdf | The ICR (pp. 21-22) offers valuable lessons, including:Active integration of relevant ministerialmanagement structures in preparation and implementation ensures that commitment is sustained and work plans are realistic. Inthis case, a wide array of key MoF officials -- two Ministers of Finance, Deputy Ministers, department heads, Treasury managers,program coordinators, and APST staff -- held key ownership and decision authority throughout. However, more active engagementat even higher levels (in this case, the Presidential Administration) would have avoided somedelays.Flexibility during implementation can enhance achievement of desired outcomes. In this case,although the adoption of the Turkish SGB.ET FMIS system was not foreseen during preparation, the willingness of the MoF to considerit as an alternative, the Bank teams flexibility in putting the question on the agenda, and all parties acceptance of theresults of an independent assessment led to the establishment of a reasonably robust FMIS quickly and at low cost (ICR,p. 22).
P099841 | Avian Influenza Control & Human Pandemic Preparedness & Response Project | Europe and Central Asia | Moldova | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2006 | 2011 | 2013 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/463201474592037236/text/000020051-20140625072034.txt | http://documents.worldbank.org/curated/en/463201474592037236/pdf/000020051-20140625072034.pdf | The ICR reports the following lessons (page 22-23):Effective coordination of emergency interventions may have higher impact when integrated in overall sector reforms. The veterinary laboratories and health information system will provide wide benefits beyond the specific project objectives.Coordination between stakeholders is necessary for maximum impact, and this is time consuming. Such coordination cannot usually be achieved during the limited 3 year time period of an emergency operation. Similarly, complex and technical procurement and institutional strengthening cannot be carried out in the limited emergency time period.Rehabilitating existing buildings and infrastructure can be less efficient than constructing new facilities in the case of complex and technically challenging structures such as infectious disease laboratories and hospitals. Procurement of equipment for these facilities is highly technical, and specialized consultants should be on hand to assist in developing precise specifications.IEG finds that the project also demonstrates the effectiveness of using field simulation exercises as a means of assessing improvements in the capacity to deal with disease outbreaks, and of identifying weaknesses in response that can then be addressed. Capacity levels for emergency response are otherwise difficult to observe, because they are not utilized if no emergency occurs. Other projects aimed at building capacity to respond to disease outbreak emergencies would benefit from incorporating similar simulations.
P099882 | Third Poverty Reduction Support Operation | Europe and Central Asia | Georgia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2008 | 2011 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/390911474551831521/text/000020051-20140620075853.txt | http://documents.worldbank.org/curated/en/390911474551831521/pdf/000020051-20140620075853.pdf | IEG broadly concurs with the lessons outlined in the ICR. In particular, the lessons about the importance of strong Government ownership of the reform program, good donor coordination, and the focus by the government on results are unexceptionable. Using the flexibility available under the programmatic lending to adapt the programs to the actual implementation experience is also sound advice for the Bank TTLs.
P099894 | ROAD INFRASTRUCTURE REHABILITATION PROJECT | Europe and Central Asia | Bulgaria | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2007 | 2013 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/133251475115238647/text/000180307-20141203060102.txt | http://documents.worldbank.org/curated/en/133251475115238647/pdf/000180307-20141203060102.pdf | The ICR identified important lessons:When implementing a Road Management System (RMS) for the first time, the adoption of a twin-training approach needs to be considered during the project design stage. The project experience showed that despite the implementation of RMS hardware and software, the system was not fully effective because of limited trained personnel and lack of management support. Twin-training approach at both technical and managerial levels might have been more useful as this approach would ensure that: (i) technical capacity in operating the system is optimized and (ii) management can take ownership of the system and fully utilize it for multi-year programming of maintenance and rehabilitation.When planning for maintenance, adopting area-based hybrid contracts which include traditional methods for rehabilitation (input-based), followed by Performance Based Contracts (PBC) for summer and winter maintenance may be effective in improving the condition of the network. However, these contracts are long in duration (5 â€“ 10 years) and therefore very dependent on long-term budget allocation â€“ therefore financial commitment is a perquisite.Road safety value engineering at the design review stage can be effective in enhancing road safety. Many of the completed road sections under the project incorporated road safety improvements such as re-designed junction layouts, crossing points and traffic calming measures.
P099895 | MUNICIPAL INFRASTRUCTURE DEVELOPMENT | Europe and Central Asia | Bulgaria | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2010 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/427591604090194128/text/Bulgaria-MUNICIPAL-INFRASTRUCT-DEVT.txt | http://documents.worldbank.org/curated/en/427591604090194128/pdf/Bulgaria-MUNICIPAL-INFRASTRUCT-DEVT.pdf | The Review selected two lessonsfrom the ICR,with some adaptation of the language: Complexprojects require laser focusin assessing readiness to implement. This project lacked technical and operationalreadiness in designing and implementing at the time of approval and those risks delivered the delays. Corrective measures could notkeep pace withthe implementation challenges. The timeline was underestimated and unrealistic. Convention for the sectorpointed to an even lengthier period toimplement such a complex project. Recognizing these challenges may reduce frustrationand repeated project extensions. Some of the readiness factors to consider include adequately assessing capacity to manageoperationally complex projectsand large contracts (e.g., capacity to respond to complex technical issues that may ariseduring implementation and resolving these in a timely manner) and adopting a procurement strategy that respondsto marketconditions (e.g., availability of local contractors to undertake complex projects). Other vital readinessfactorsincludehaving key contracts atadvanced stages of procurement prior to approval, orbundlingprocurement packages for efficiencyso that timely technical studies are undertaken in time toimplementsub-project investments. Institutional capacity building may be apowerful developmenttool that could trigger further investmentsin support of infrastructure development.In this project,themaster planning component, which focused on capacity building at the local level, generateddiscrete investments in water andsanitation of more than one billion euros.Clients are usually reluctant to borrow for capacity building alone. The rest ofthe Bank, both at the central office through its global practices, and in the region, could advertise the positive outcomesofstrong institutionsbuilt over the years. In addition, technical breakthroughs or procedural efficiencies or emerging bestpractices in the sector arising from project experience would also prove useful in increasing client interest in enhancingnativetechnical capacity. For example, in this project, lessons learned from the use of technical elements related togeomembrane attachments and working with divers would be useful todesign and implementfuture dams.
P099918 | HT Education For All Adaptable Program Grant Phase 1 | Latin America and Caribbean | Haiti | IDA | FCS | Human Development | Education | IDA | IPF | 2007 | 2012 | 2017 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/162971495658830132/text/ICRR-Disclosable-P099918-05-24-2017-1495658818211.txt | http://documents.worldbank.org/curated/en/162971495658830132/pdf/ICRR-Disclosable-P099918-05-24-2017-1495658818211.pdf | Lessons drawn from the ICR: A projects implementation arrangements and mechanismscanhelpto sustain the provision of basic services in the context ofa fragile environment. In this case, theearthquake had severely damaged physical and institutional infrastructure, while the PCU was able to maintain functions and evenserve as a mechanism for channeling additional donor funds to thebasic education sector. The use of non-publicsector institutionscan helpto ensure service provision in a fragile state. In this case, the use of privateschools (to deliver primary education) and NGOs (to deliver school feeding programs) was effective in delivering servicesespecially to poor populations.
P099924 | Corporate and Public Sector Accountivility Project | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2008 | 2015 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/617101467320012643/text/ICRR-Disclosable-P099924-06-30-2016-1467319987565.txt | http://documents.worldbank.org/curated/en/617101467320012643/pdf/ICRR-Disclosable-P099924-06-30-2016-1467319987565.pdf | Three main lessons from thisICR are the following: Financial Management Information Systems are a key element of PublicFinance Management and a critical tool for appropriate financial auditing. In the case of this project, this tool (FARABI) was onlyincluded after the first restructuring and it was one of the most successful project achievements. This system even had theadvantage that its cost was modest compared with similar systems in other countries. Substantial training isessential to improve institutional capacity for implementing new tools. This project devoted significant resources to deliverquality training in Azerbaijan drawing on best practices and international standards on financial auditing. Theinclusion of new activities through project restructuring requires a deep evaluation and a risk analysis of their feasibilitybefore the projects closing, especially when their final achievement depends on external decisions. In the case of CAPSAP,the inclusion of the establishment of an association of professional accountants (ARPA) that follows international standardsdepended not only on the creation of an internal registry of the association, but also on the recognition by IFAC. Furthermore, atthe closing of the project ARPA only complied with 7 of the 47 actions required by IFAC, which is one of the main shortcomings ofthis project.
P099930 | Health Service Delivery Project | Eastern and Southern Africa | Mozambique | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2009 | 2018 | 2019 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/410541543261961065/text/Mozambique-MZ-Health-Service-Delivery-SIL-FY09.txt | http://documents.worldbank.org/curated/en/410541543261961065/pdf/Mozambique-MZ-Health-Service-Delivery-SIL-FY09.pdf | The ICR (pp. 30-31) provided several lessons and recommendations restated byIEG:The lack of ownership and political support delay project implementation. Theproject was perceived as an exogenous investment within the health sector. The follow-on project opted for performance-basedfinancing to support the governments own programs under its established institutional arrangements andprocedures.Adequate capacity for monitoring and evaluation can potentially facilitate the provisionof reliable evidence on project performance. Under the project,ME deficiencieswere largely duetocapacity constraints at all levels, and notably at the communitylevel,throughout the implementationperiod.A multi-sectoral approach to nutrition interventions with sufficiently longimplementation periods can potentially enhance theimpact of interventions. The project indicated that theinclusion of educational activities at schools was insufficient, and that behavioral changes at the community level required moreexposure time for effective community penetration.
P099979 | Capacity Building for Urban Development Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2012 | 2018 | 2019 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/233511555421348699/text/India-IN-CBldg-for-Urban-Development.txt | http://documents.worldbank.org/curated/en/233511555421348699/pdf/India-IN-CBldg-for-Urban-Development.pdf | IEG selected three lessons from the ICR, with some adaptation of the language: Provisionoftechnical assistanceis not a guarantee of interest on the part of local bodies to undertake capacity-buildingexercise. Under this capacity building project in India, given the large deficit in basic service delivery, urban localbodies (ULBs) are predominantly concerned with building infrastructure and the day to day service delivery. While officials mayappreciate the long term positive impactfrom technical assistance, they might not prioritize it. Knowledge exchangeworkshopscould help to createincentives of undertaking technical assistance. Outputs should enable ULBstoleverage other funds/programs, planning for service delivery which is critical to the city and for which investments have beenidentified, increase in own source revenues and trainings linked to current work programs. Being able to clearly identify suchincentives has two benefits: (a) increase in the likelihood that TA activities will be in areas which are prioritized for on-groundimplementation and (b) World Bank-funded activities becoming upstream works which leverage further funding or enable ULBs to doso. Funding of wholesaleTA may bring larger benefits versusretail TA. In India, most state-level urban projects have TA components and these have been formulated ascomprehensive studies, which are implemented across all ULBs in the states. The impact isconsidered deep and sustained. Manyof them have similar scope to what theproject intended to fund, e.g.,double entry accounting, geographic informationsystem (GIS) mapping, e-governance systems, property tax enhancement, city level service planning, and training. Consequently, thecontracts are large, implemented across a range of ULBs to enable cross-learning and coordination, and anchored in a departmentthat has the mandate and capacity to implement those. If working directly with ULBs, TA assistance could provide apackage of assistance to few ULBs versus several dispersed studies to a large number ofULBs. There is a trade-off between complexity of fiduciary requirements and effortsand ownership of outputs produced. This TA project attempted to fund a large number of consultancies/studies. The decisionwas made to have centralized procurement as it simplifies fiduciary assessments during preparation and monitoring duringimplementation. Consequently, the centralized implementation structure became a critical bottleneck, andthe projectintroduced the decentralized procurement.The ownership of outputs was higher when the ULBs (beneficiaries) were made a partyto the procurement and also led to an increase in demand for TA as ULBs were able to customize contracts based on their needs. Thedownside of decentralized procurement was the increased need for monitoring the contracts. Thus, this trade-off between fiduciaryrequirements and demand and ownership for TA should be carefully assessed and implementation arrangements should be designedaccordingly. This approach should be combined with increased PMU staff for fiduciary monitoring.
P099980 | Public Financial Management Reform Project | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2007 | 2012 | 2013 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/453061474589881024/text/000020051-20140625192132.txt | http://documents.worldbank.org/curated/en/453061474589881024/pdf/000020051-20140625192132.pdf | The following lessons are taken from the ICR with some adaptation of language: Continuity of the team working on a project, specially the TTL is very important for both the Bank and the Borrower as it will engender consistency and follow-up in the dialogue and provide expertise to help the government to analyze issues and implement actions as they emerge during supervision. It is important to recognize that an operation aimed at changing institutions is fundamentally about changing behavior and attitudes, social relationships and organizational culture, not strictly installing technical solutions. When there is no tradition of public accountability, there is a need for sustained additional efforts to raise the level of willing adoption of new auditing concepts and practices. The phasing out of foreign consultants in PFM may take longer than anticipated. The PFMR provided heavy support for using contractual consulting services to actually perform many PFM functions, even though a longer term goal was to develop a Ministry of Finance led system managed by the civil service. The Bank team resisted understandable impatience on the part of the government to take responsibility for financial operations, but was correct in working towards a more macro-level outcomeâ€”maintaining transparency and accountability acceptable to those providing the resources.Another important lesson drawn by IEG is that building up a countryâ€™s public financial management system in countries that do not have a tradition of public accountability and transparency cannot be done in a short time or under one operation. It takes a number of technical assistance operations in which incremental improvements are made in the legal, institutional and human resources involved in public financial management. The PFMR was the fourth Bank operation to support PFM and reforms in the Afghanistan public sector, and was complemented by the Civil Service Reform Project, also aimed at strengthening core business practices within the Afghan government. The efforts to achieve the objectives of developing an efficient and effective public financial management system continue under the PFMRII and the Capacity Building for Results projects.
P099992 | Liaoning Medium Cities Infrastructure Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2006 | 2014 | 2015 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/634401475786092208/text/000180307-20150112085048.txt | http://documents.worldbank.org/curated/en/634401475786092208/pdf/000180307-20150112085048.pdf | The ICR (p18-19) discussed lessons with most of them focused on how to design a project which would suit the capacity of the implementation entities. The lessons highlighted here are:1. Enhancing the project design and contract packaging. The project design had five components scattered over six cities. The project procurement involved more than 100 contracts for civil works and goods packages and 17 consulting contracts. However, the project appraisal document had only a summary of the procurement plan without detailed procurement packages. The necessary revisions in the procurement packages were substantial but delayed the project schedule. For future projects, the project design and contract packaging should be enhanced, so that serious revisions are avoided during implementation.2. Training to enhance the knowledge and compliance of the Bankâ€™s procedures and requirements. The project encountered financial and quality problems in Fushun city and Panjin city, which could be partly attributed to the weak concepts on compliance of the Bankâ€™s procedures and requirements. In future projects, education and training should be enhanced, especially to medium and small cities which have never before implemented projects financed by international agencies. At the same time, supervision should be also enhanced, especially in the early stages of project implementation.3. Enhancing the coordination among Government Line Agencies. In most of the project cities, the coordination among different government line agencies appeared to be a problem. For example, in Panjin city, the weak coordination between the finance bureau and the implementation agencies delayed payments to contractors and suppliers. The delay in implementing the Beidi Bridge in Benxi was also caused by weak coordination with the railway authority. Close coordination between related government agencies is needed for efficient project implementation. Measures include setting up a project leading group at municipal level, form a joint PMO, and establish a coordinating mechanism.
P100026 | National Initiative for Human Development Support Project (INDH) | Middle East and North Africa | Morocco | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2007 | 2012 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/817541475092702301/text/000180307-20141120030237.txt | http://documents.worldbank.org/curated/en/817541475092702301/pdf/000180307-20141120030237.pdf | The ICR offers the following lessons (with some aggregation and adjustment of language): Social mobilization teams acting as animators and facilitators can play an important role in ensuring diversity in participation and in particular in drawing in poor members of the community into the decision-making process.A poorly thought-out results framework, that does not draw clear links between inputs, outputs and outcomes, can critically influence the design of the M&E system in essential areas.Supporting grass-roots associations (often focal points for the poor) by strengthening their mandate and ensuring that they are representative of local communities can affect community ownership of projects and their sustainability.
P100047 | EG-Ain Sokhna Power Project | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2009 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/474351588777611592/text/Egypt-Arab-Republic-of-EG-Ain-Sokhna-Power.txt | http://documents.worldbank.org/curated/en/474351588777611592/pdf/Egypt-Arab-Republic-of-EG-Ain-Sokhna-Power.pdf | In times of political instability, keeping a dialogue, to the extent possible, with project implementing agencies mayresult in a faster and smoother resumption of project activities once the political situation stabilizes. During thepolitical instability in Egypt between 2011 and 2013, the Banks project team and the project implementing agencies of EEHCand EDEPC continued working on the project preparation and implementation through dialogue. The presence of the Banks TaskTeam Leader in Cairo was critical in that process. Once the political situation stabilized in 2013, the project implementationresumed without significant delay and the power plant construction was completed before the original project closingtime.A large expansion of the project scope to utilize project cost savings may adversely affect overall projectimplementation. The project scope was expanded by including a large transmission component in 2013, four years intoproject implementation, to utilize the savings that materialized due to the lower cost of the power plant construction than thecost estimated at appraisal. When the project scope was expanded, the power plant construction was nearing completion. The projectclosing date had to be extended. Furthermore, the transmission component implementing unit was different than that of the originalproject; this resulted in delays in procurement because the project implementing agency did not have staff experienced inBanks procurement procedures. Assuming that there is room for increasing the development impact of a project, using savingsto finance new project activitieshence expanding the project scopemight be the right decision, but, proper measuresshould be taken to minimize the impact of such scope expansion on the overall project implementation.Recruitingpeople with experience in the Banks procurement guidelines, rather than trying to train existing staff in Banksprocurement procedures, can result in a faster and smoother procurement process. Even though the existing staff of theproject implementing agency were given training in how to apply the Banks procurement procedures, they might find itdifficult to shift away from using the local procurement systems and procedures. This was what EEHC experienced in other projects.Therefore, the Banks project team agreed to the EEHCs request and new employees experienced in Banksprocedures were hired for the procurement of the Ain Sokhna Power Plant. The procurement of the power plant component was completedwithout any significant problems, whereas the transmission component faced delays because the EETC staff in charge of theprocurement of this component did not have sufficient experience in Bank procedures (ICR, p.24).
P100081 | Avian and Human Influenza Control and Preparedness Project | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2006 | 2012 | 2014 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/734091474501621376/text/000020051-20140625234737.txt | http://documents.worldbank.org/curated/en/734091474501621376/pdf/000020051-20140625234737.pdf | Lessons drawn from the ICR (page 29-30), with adaption from IEG:A more formalized arrangement among the Bank's sector units can help to ensure multi-sector collaboration and input, and minimize the risk of misalignment of sector approaches. In the case of this project, the HNP sector team had sole formal project management responsibility but could have benefited from involvement of the agriculture sector, given that a significant portion of the National Plan was implemented by the Ministry of Agriculture.The transition from emergency response to longer-term systemic improvements should be a consideration in project design, including in situations where disease prevention efforts are successful and thus commitment to prevention efforts begins to wane. In the case of this project, the risk of a significant decline in donor resources and technical support following the end of the emergency was not considered or effectively mitigated.
P100084 | Avian and Human Influenza Control and Preparedness Emergency Project | East Asia and Pacific | Cambodia | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2008 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/717771475112578448/text/000012394-20150312112304.txt | http://documents.worldbank.org/curated/en/717771475112578448/pdf/000012394-20150312112304.pdf | The ICR reports the following lessons:In the absence of a mechanism to compensate farmers for birds culled by government veterinary workers, disease reporting by farmers is likely to remain weak. The problem of resisting to cull the poultry will be alleviated once the smallholders can be paid appropriate compensation. Poverty hinders disease control and prevention. Poverty is identified as a driver of certain behaviors such as preparation of sick and dead poultry for food, and non-reporting of disease. Any measures that help to reduce poverty will assist in preventing zoonotic influenza (H5N1). Farmers will also need constant training and awareness raising for the necessary behavioral changes. When working with UN agencies, if procurement and financial management arrangements are not clearly established in advance at the corporate level then there may be serious delays in implementation. Most of the delay related to legal procurement issues that should be anticipated in any new projects in which these agencies are involved. IEG also finds that: Failing to improve biosecurity in small holder farms can contribute to an inability to eradicate avian influenza. However, this is also very a difficult objective to achieve, as it requires many years and significant amount of funds. The project tried to demonstrate the importance biosecurity by implementing the Healthy Livestock, Healthy Village, Better Life program as a pilot. Lengthy delays in emergency operations are particularly problematic as the situation can get worse due to inaction. Although there was no pandemic in Cambodia during the project implementation, if it occurred the project delays would pause major issues for pandemic response efforts.
P100101 | Coal-Fired Generation Rehabilitation | South Asia | India | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2009 | 2018 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/140401570457504771/text/India-IN-Coal-Fired-Generation-Rehabilitation.txt | http://documents.worldbank.org/curated/en/140401570457504771/pdf/India-IN-Coal-Fired-Generation-Rehabilitation.pdf | Four lessons are selected from the ICR with some adaptation of the language.Robust monitoring and evaluation(ME) arrangements and close supervision donot onlyhelp monitor the progress of project activities and take timelymeasures to address implementation issues, but also create an important knowledge base to be used in replication projects or inpolicy decision-making. Being a pilot in energy efficiency renovation and modernization (EE RM) of coal-fired powergeneration units, the project had a robust ME system embedded in the participating generation utilities operations. TheME findings and close supervision of the project implementation, especially during construction, helped the projectimplementing teams and the Bank project team to intervene when implementation issues arose. The project also provided importanttechnical, operational and procurement related information from which future replications could benefit. Furthermore, the MEfindings were communicated to the national authorities to provide input to policy decisions about the future of thermal generationin the country.At project preparation, services of a design consultant for the preparation of detailedrehabilitation scope through residual life assessment (RLA) studies for entire power plant may not be necessary. In thisproject, the RLA studies were completed with the anticipation that the project activities would start without delay. However, bythe time the project activities started after a significant delay, the RLA studies had already been redundant. Furthermore, due toconflict of interests, the design consultant could not continue working for the project during implementation. Therefore, it couldbe more practical and efficient if the boiler-turbine-generator contractor decided what the scope of replacements and modificationsshould be.Energy efficiency renovation and modernization (EE RM) of coal-fired power plants after25 or 30 years of operation can result in a longer shut-down time than estimated. The shut-down time for both power plantswas estimated to be six months. However, due to technical issues, which hadnot been foreseen before the project activitiesstarted, the shut-down periods extended to two years. When EE RM works are implemented after a very long operation period, thelikelihood of having unexpected technical issues with the mechanical systems in a coal-fired plant increases. Therefore, as theexperience of this project shows, it might be advisable to break EE RM operations into phases consisting of separate smallerworks, such as turbine improvements, and boiler area retrofits, which would require shorter shut-down periods.For complex rehabilitation projects, it is critical to have a dedicated project implementing team with high technicaland project management capacity for the entire duration of the project. Frequent change of officials in the projectimplementing teams of the participating generation utilities and the low technical and project implementation capacity of theseteams adversely affected project implementation. Some complex contracts had to be tendered twice. Inadequate workforce planningresulted in a shortage of labor force. A program evaluation review technique, detailing out all project activities, was notprepared. Coordination among various contractors was inadequate. The governments decision to shift strategy in favor ofconstruction of supercritical coal-fired plants rather than energy efficiency renovation and modernization of aging power plantscontributed to the weakening of the project implementing teams ownership of the project.
P100122 | Avian Influenza Control and Human Pandemic Preparedness and Response Project for Nigeria | Western and Central Africa | Nigeria | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2006 | 2011 | 2013 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/490891474566190757/text/000020051-20140625072957.txt | http://documents.worldbank.org/curated/en/490891474566190757/pdf/000020051-20140625072957.pdf | Most of the lessons in the ICR, while useful, are specific to the project. IEG has drawn the following lessons of more general applicability from the experience of preparing and implementing this operation:Preparation of operations based on a template (here, that of the Global Program for Avian Influenza and Human Pandemic Preparedness and Response)should ensure that the template is adequately adapted to take account of country realities. In this case, care was taken to do this, particularly with regard to securing stakeholder buy-in and implementation arrangements.For an emergency operation, the use (with the agreement of the Borrower) of both financial and technical resources from other ongoing Bank-supported operations in related fields and sectors can help to provide a â€œjump startâ€ and get activities in motion before effectiveness. Here, this was done by reallocations (only a part of which needed to be used) from the Second FADAMA Project in rural development and the Second Health System Development Project. Procurement and M&E arrangements from these two operations were also used.Transparency and effectiveness of compensation schemes can be assisted by full disclosure of the identity of the recipients, encouraging reporting of outbreaks, and some self-policing by communities of distribution of compensation among smaller beneficiaries.Containment, control and prevention of epidemics can benefit substantially from heightened public awareness. Awareness creation is likely to be enhanced if campaigns are conducted in a professional manner by institutions with the requisite experience, country knowledge and technical expertise. Here, the fact that the public awareness component was implemented by specialists within the Federal Ministry of Information and Communication was, according to the ICR (page 12), an important reason for the campaignâ€™s success.Application of proven good practices elsewhere can be a positive contribution to a project's success and sustainability. In this case, the adoption of the concept of model live bird markets, which had worked well in Vietnam, and its adaption to Nigerian conditions assisted the countryâ€™s efforts to address zoonotic disease epidemics.
P100122 | Avian Influenza Control and Human Pandemic Preparedness and Response Project for Nigeria | Western and Central Africa | Nigeria | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2006 | 2011 | 2013 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/511131468096840524/text/750680PPAR0P100C0dislcosed040170130.txt | http://documents.worldbank.org/curated/en/511131468096840524/pdf/750680PPAR0P100C0dislcosed040170130.pdf | 7. Lessons 7.1 The project offers a range of lessons, both for similar health/animal health projects and for broader operations. These include\. 7.2 Government and implementing agency prioritization and enthusiasm will wane as perceived threats decline, with consequences for implementation. If longer term capacity building activities are not commenced while enthusiasm is high (rather than being left to be worked on once the crisis has passed) then implementation of these activities may be slow. In this project, the fact that procurement of civil works and longer term capacity improvements did not begin during the early project stages contributed to implementation delays and to the lack of completion of laboratory upgrades by project closure. 7.3 Pilots may have little impact in the absence of a rigorous assessment of the benefits and a clear plan for scale-up. The model live bird markets may be a potentially valuable innovation if widely adopted (though the biosecurity benefits were not assessed), but project-supported markets had little impact because the project include a clear mechanism of demonstration that might lead to replication and scale up. 7.4 An epidemic communication strategy requires inputs from all stakeholders, including the private sector. This can make it more likely that harmful or inaccurate messages are avoided. Alarmist messages can backfire by harming the private sector and may trigger a hostile response from affected industries. Even once messages are adjusted, the change in message can confuse audiences. 7.5 Including communications professionals can improve the quality of communications strategies. Communication experts can devise an effectively targeted campaign for projects where public awareness is important. But communications with farmers may be more effective when done through agriculture agencies, which will likely have existing relationships and trust with farmers. 7.6 Compensation systems can support disease reporting if compensation rates are at a level high enough to allow farmers to restock. In this project, compensation rates of roughly 70 percent of market value supported sufficient reporting to allow for disease control. Compensation systems can track market values more effectively if they allow payment rates to vary based on key determinants of value such as type and age of animal. 7.7 Compensation systems can be made more transparent by publishing names and amounts of compensation awards in local newspapers, online and through other media, as was done in this project. This can increase confidence in the mechanism, assist in encouraging other eligible groups to apply for compensation, and instill a degree of selfpolicing. 7.8 Centralized procurement systems can lead to inefficiencies if they do not consult end-users. While procurement centralization may reduce governance risks and reduce costs, insufficient consultation with end-users (such as checking that equipment is functional and works are satisfactory before processing and completing payments) can lead to gaps in capacity, redundant capacity, or buildings that are not used. 7.9 Reducing diagnostic response times relies on rapid sample transportation systems. Effective transportation systems can be achieved by engaging transporters, setting up contracts beforehand so they have confidence they will be paid immediately on delivery, and discussing biohazard risks openly and providing advice on appropriate safety measures. Reducing sample transport times may be cheaper and easier than reducing diagnostic testing times. 7.10 In projects involving multiple ministries, cooperation across ministries may be difficult in the absence of a single coordinator and if project management unit staff for different components are housed in different locations. These can assist in increasing the degree of cooperation between ministries, and in speeding project implementation. Implementation of this operation initially suffered from the lack of a single coordinator, which was later rectified. 7.11 Lack of experienced procurement staff in the project management unit at project inception can compromise the timely response to an emergency. In this project, a lack of procurement staff led to significant delays. 7.12 There were some additional secondary lessons. Radio ads and programs can be an effective way of reaching rural populations. Decentralizing outbreak response to state and local government levels can allow rapid response to containment operations. Laboratory systems need to be clearly tied into ongoing surveillance programs to ensure that capacity is maintained. Housing surveillance and diagnostic laboratories in universities, where they can be part of training programs, can increase the likelihood that capacity will be sustained in the long term. UN agencies can provide technical expertise that the World Bank lacks. Border control is unlikely to be effective in countries with highly porous borders.
P100198 | Critical Ecosystem Partnership Fund 2 | Other | World |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2008 | 2019 | 2020 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/665081593553155732/text/World-CEPF-2-Japan-EU-P-A-SPN.txt | http://documents.worldbank.org/curated/en/665081593553155732/pdf/World-CEPF-2-Japan-EU-P-A-SPN.pdf | The ICR presents several useful lessons including:1. Regional and global projects working at several levels andwith small grants have to includea consistent Results Framework that logically links the reporting from each level usinguniform indicators that allow for ease of measurement and aggregation to the project level and adequate resources need to beprovided for monitoring and reporting in order to make the ME system an effective project management tool. In thepresent project, ME was not mentioned in the grant agreements, thus no dedicated resources were included for this purpose. Inaddition, the project design did not anticipate the substantial need for ME resources or the low capacity of the projectbeneficiary civil society organizations (CSOs) to use relatively sophisticated tools such as METT.2. A World Bankproject that supports a multi-donor partnership hasto be carefully designed, including appropriate governance structures andpolicies.Decisions made by a multi-donor partnership should be carefully reviewed and potential implicationson and inconsistencies with the WB project assessed and appropriately addressed. In the case of the CEPF, decisions made bythe Donor Council (which included the World Bank) were not regularly reviewed and relevant amendments to the WB project were notmade. For example, changes in the CEPF Partnership Framework were not reflected in the WB project Results Framework. In addition,influence and application of decisions made in the governing body on managing a WB project, and operational policies and proceduresfor the WB project need to be clear and reviewed on a regular basis to ensure their relevance to the achievement of the projectobjective and results, and alignment with WB policies.3.The preparation of an investment projectrequiresthe expertise necessary to design an effective and coherent operation and to ensure ownership and alignment withWBs country priorities.The staff leading the preparation and appraisal of the project, who were from thecentral Environment Department (ENV), should have involved specialists who had sufficient operational experience and expertise toaddress all operational challenges associated with its design as well as to ensure greater linkage with other WB priorities andactivities at the regional and country levels.4. World Bank involvement in high visibility partnershipsrequirescarefuldesignand managementand for expectations from both the WB and implementing agency to beclarified upfront, including with respect to the applicable WB policies and procedures.The roles andresponsibilities of the WB in these partnerships need to be clarified with all involved parties early on to avoid confusion onapplicable policies and accountabilities. This is especially important when partnerships are initiated and agreed at a verysenior managerial level.IEG adds the following lessons:5. If additionalresources are made availableto a project thatis already under implementation in order to increase its territorial scope and/or permit additionalachievements, the project needs tobe formally restructured and its Results Framework updated to reflect thesechanges.This did not occur in the present case, and thus, for purposes of assessment, the performance targets werenot appropriately update to reflect the projects significantly expanded resource envelope and associatedactivities.6. If global partnerships require more flexible arrangements than are typical of World Bank investmentprojects, a different instrument needs to bebe utilized for this purpose.The present project experience isrife with examples in which normal Bank procedures and requirement failed to be followed, including with respect to AdditionalFinancing, restructuring, financial management, procurement, and safeguards, as well as supervision and insufficient resources wereprovided for the latter. In short, Partnership arrangements cannot readily -- and should not --beprojectized and this should be avoided.7. The Bank needs to avoid creating situations in whichprofessional staff are asked to prepare, appraise, and supervise projects, no matter how worthy their objectives may be, if thedont have full management support to ensure that they meet all pertinent Bank policies, standards, andrequirements.This was clearly the case with the present operation in which a succession of TTLs and other projectteam members were constrained in their efforts to have the project adhere with applicable Bank policies and normalprocedures.
P100218 | ID-Aceh-Infra. Reconstr Enabling Program (IREP) | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2006 | 2012 | 2014 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/793911475096826108/text/000020051-20140625194305.txt | http://documents.worldbank.org/curated/en/793911475096826108/pdf/000020051-20140625194305.pdf | 1) While it is sound practice to limit increases in the signed contract amount, it is not necessarily always the best policy to reduce the scope of the works because of this. The concept of grouping incomplete works into an additional separate package tendered separately may turn out to be more costly than funding a cost overrun.2) Implementation entities created to facilitate and speed up assistance in a disaster situation should be designed with a limited lifetime to enable the line ministries to resume their normal roles seamlessly after the entity's emergency work is done. It is useful for such an entity to have its own procurement unit to manage the procurement activities.3) The opening of a local office supported by the donors can greatly facilitate implementation of post disaster recovery on a day to day basis and provide continuous support to the client.; in the case of IREP, the opening of a field office in Banda Aceh was facilitated by funding from the MDF.
P100273 | Avian Influenza Control and Human Pandemic Preparedness and Response Project | Europe and Central Asia | Albania | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2006 | 2011 | 2013 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/389921474574380109/text/000020051-20140624213546.txt | http://documents.worldbank.org/curated/en/389921474574380109/pdf/000020051-20140624213546.pdf | The ICR (page 19) notes that:A global template for projects can enable rapid and effective project design. The standard design for the Global Program on Avian Influenza was in place prior to this project and was used as the basis for project design, providing the structure of the components and laying out the logic for the need for containment of outbreaks among animals.Projects formulated for a specific disease can be too narrow and may require restructuring. This project's original focus on avian influenza alone meant that restructuring was needed after no further avian influenza outbreaks occurred.Too many indicators for an emergency project can make M&E cumbersome. The large number of indicators for this project overwhelmed its limited M&E capacity and contributed to the project's inability to implement and utilize the M&E plan.Cooperation with UN agencies can enhance the quality of technical assistance. WHO, UNICEF, and USAID provided technical expertise and support that was not otherwise available from the Bank's project team or implementing agency.
P100273 | Avian Influenza Control and Human Pandemic Preparedness and Response Project | Europe and Central Asia | Albania | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2006 | 2011 | 2012 | PPAR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/223911468006898596/text/704660PPAR0P100C0disclosed070110120.txt | http://documents.worldbank.org/curated/en/223911468006898596/pdf/704660PPAR0P100C0disclosed070110120.pdf | 7. Lessons 7.1 Building on the project experience this assessment identifies five main lessons\. 7.2 In designing an emergency intervention, it is important to distinguish between immediate response and longer-term capacity building activities to deal with future emergencies. However, the latter usually benefit from longer preparation and coordination with other sector interventions. In the Albania project several activities were included that were not of an emergency nature. The quick preparation that was needed in an emergency situation did not allow for adequate consideration of the findings of analytical work or for building coordination with other relevant ongoing Bank sector projects. 7.3 Stronger Management oversight is needed to ensure that project M&E is actually utilized as a management tool for effective project implementation. In the Albania project an M&E system was set up but was not utilized for effective management of the project. Had it been used, the Bank would have known that, given the weaknesses in the implementation of the animal health component from the very beginning, it was unrealistic to expect that the permit for the Animal Health Laboratory would become available and the construction completed in the short time available before project closing. 7.4 Persistent occurrence of H5N1 infections in poultry around the world means that conditions for the mutation of the virus continue to prevail, including in Albania, where biosecurity levels remain weak on poultry farms. Greater effort is needed, both globally and in Albania, to improve surveillance in backyard poultry systems and wildlife to reduce risks. While increasing awareness, diagnostic and treatment capacity is important, attention to what all three technical organizationsâ€”the WHO, FAO and OIEâ€”have emphasized the need to contain highly pathogenic avian influenza at sourceï¿½? needs to be given priority attention. As Albania strives to conform to EU standards it is likely that efforts will be made to improve enforcement of biosecurity norms. However, it is too soon to tell when this would happen. Biosecurity levels are very weak in backyard poultry systems in Albania where about 85 percent of birds are reared. Even in commercial poultry houses the level to which sound management practices are adopted is variable. Improving biosecurity would be important for reducing the chances for the mutation of the virus and hence the risk that the pandemic occurs. 7.5 Early cooperation with UN agencies and international technical organizations can offer synergy and provide a basis for sustaining at least some programs on project closure. Even though budgets are tight, in the case of this project awareness raising activities will likely not face a shortage since several international organizations came together in preparing the communication strategy and resources from one or the other source could be made available were an emergency to arise. 7.6 More effective ways of working with the media to communicate disease risks are needed to avoid panic and build public confidence. While the communication campaign supported through the project successfully spread the information on the disease, it also created panic and led to a large number of people moving away from consuming poultry meat which was harmful for the industry.
P100304 | India: Uttar Pradesh Health Systems Strengthening Project (UPHSSP) | South Asia | India | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2012 | 2020 | 2020 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Highly Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/925321592408324743/text/India-IN-UP-Health-Sys-Strengthening-Project.txt | http://documents.worldbank.org/curated/en/925321592408324743/pdf/India-IN-UP-Health-Sys-Strengthening-Project.pdf | The ICR (pp. 27-29) offered lessons and recommendations, including the following lessons restated byIEG:The design and implementation of social accountability schemes empower communities to monitorand demand better services, and ultimately contribute to improving the quality and utilization of health services, as wasobserved under the project.Better synchronization of supply-side and demand-side initiativescould result in greater community ownership of quality of care interventions.Apart from social accountabilityinterventions, and given the context of UPs health system, the primary approach was focused on improving supply-sidefactors.A more targeted approach to involve the community, especially for beneficiaries utilizing district hospital services,and measuring patient experiences, could have further strengthened the bottom-up approach to qualityenhancement.Institutional capacity building and the establishment of specialized technical cellswithin the Department of Health promote evidence-based approaches, support strategic planning, and enhance preparedness to tacklehealth systems challenges in the future. Under the project, added technical expertise at the Directorate of Medical andHealth Services strengthened informed decision-making and planning, and improved institutional processes andguidelines.The quality of service delivery at district hospitals can be improved through adecentralized and tailored approach.Under the project, and in addition to conforming with quality standards foraccreditation, the hospitals undertook tactical revamping of their infrastructure, redesigned facility layout for better patientflow and equipment condemnation, deployed capable hospital managers, and secured safety certification.
P100311 | Solomon Islands Sustainable Energy | East Asia and Pacific | Solomon Islands | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2009 | 2019 | 2021 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/763971595020865967/text/Solomon-Islands-SB-Solomon-Islands-Sustainable-Energy.txt | http://documents.worldbank.org/curated/en/763971595020865967/pdf/Solomon-Islands-SB-Solomon-Islands-Sustainable-Energy.pdf | This review has drawn three lessons based on the ICR incorporating material on lessons listed on page 42 of theICR.A robust legal framework and strong political commitment can significantly affect the transformation ofstate-owned enterprises. The State-Owned Enterprise (SOE) Act of 2007 and its regulations provided a robust legalframework for the improvement of the management and operational efficiency of the six SOEs in the country, including SIEA.Profitable operation, rigorous director selection and appointment process, corporate planning and reporting requirements, andtransparent identification, costing, and financing of community service obligations are regulated by the law. Thegovernments commitment to the implementation and enforcement of the legal framework was strong, which manifested itselfthrough the restructuring of SOE debts and enforcing disconnection of delinquent customers, including government institutions. Thelegal framework provided a strong foundation for the project to support SIEA in its transformation from an insolvent utility into afinancially strong one through management strengthening, and the strong political commitment was an indispensable part of thisprocess.A simple and focused initial intervention can increase the possibility of achieving the intended outcomes,while laying the groundwork for subsequent more complex interventions. The project originally had a low budget and focusedon the improvement of the management and operation efficiency of SIEA, while supporting some limited investment activities toimprove system reliability in a short period of time. The intention of the project was clearly defined in the PAD (p.6): Afollow-up Bank operation in the sector may be considered if this program is successful. The project was successful inimproving the management and operational efficiency of SIEA; therefore, even during project implementation an Additional Financingwas processed to support additional investments in distribution to improve system reliability, and two new projects were approved,i.e., the Electricity Access Expansion Project to increase access to electricity through the distribution and installation ofpre-payment meters and the Electricity Access and Renewable Energy Expansion Project.Appointment of experiencedprofessionals to key management and board positions on a long-term basis rather than hiring short-term consultants cansubstantially increase the prospect of improving the management and operational efficiency of state-owned economic enterprises inremote island nations. Capital Honiara is more than a three-hour flight away from Brisbane, the closest major city in theregion. The island country is not easily accessible to deliver technical assistance support by short-term consultants. In thisproject, the General Manager, whose expatriate package cost was covered by the project funds for the first three years, stayed withthe utility for four years; the first Commercial Manager and his successor as Chief Financial Officer, served for about two yearseach; and the external Director, whose contribution to the transformation of the utility was critical, served on the Board of SIEAfor more than six years The project design had benefited from the successful reorganization of Fiji Electricity Authority in 2002through the appointment of five expatriate managers.
P100314 | Tax Modernization Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2006 | 2012 | 2013 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/401541474628191025/text/000020051-20140625191436.txt | http://documents.worldbank.org/curated/en/401541474628191025/pdf/000020051-20140625191436.pdf | Both the ICR and IEG identified the following lesson:A well designed M&E framework that is aligned with the PDO is essential for monitoring and guiding project implementation. It is important to select relevant and measurable indicators with realistic targets at the start of project. The baseline data also needs to be properly selected. These indicators should be modified from time to time based on data collection to provide timely inputs to ensure their continued relevance.
P100330 | Railway Reform Programmatic Development Policy Credit | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Transport | IDA | DPF | 2007 | 2008 | 2010 | ICRR | >=25 million & <50 million | Unsatisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/629311474631981292/text/000146597-20140619153452.txt | http://documents.worldbank.org/curated/en/629311474631981292/pdf/000146597-20140619153452.pdf | The project was one of the first transport sector DPC projects in the Bank and the modalities for the DPC/DPLs were not well-established. DPC/DPLs is a complex instrument. The Bangladesh DPC project experience suggests three lessons, which may be context specific.1. DPC/DPL projects should have a clear statement of the PDO and identify supervision components that relate to it. Because of the inherent complexity and uncertainty surrounding the acceptance, adoption and implementation of policy proposals, the time line of the project should allow for flexibility. This uncertainty and flexibility in project implementation requires that there are intermediate output or outcome indicators to guide the project's supervision. 2. The PD should include a cost table for the supervision requirements of the components. The supervision plan should also indicate the kind and level of management involvement. This is necessary because without high level management involvement DPC/DPL policy projects may falter, especially if there are political changes. 3. The DPC/DPL projects can (in fact, are likely to) be supervision intensive. Therefore, the supervision budget for the DPC/DPL instrument may need to be higher than results from using the customary coefficients. For this project supervision costs were only 58 percent of the project preparation costs (excluding the sector strategy paper). This ratio was too low. For DPC/DPL the supervision costs should be indicated in the PD to reflect the difficulty of the project and to indicate the Bank's commitment for delivering desired development policies.
P100332 | Bhutan Second Rural Access Project | South Asia | Bhutan | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2007 | 2013 | 2014 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/275371474487852204/text/000020051-20140626105810.txt | http://documents.worldbank.org/curated/en/275371474487852204/pdf/000020051-20140626105810.pdf | Adapted from the ICR:The performance indicators should be linked to intended outcomes. Indicators that are likely to be affected by externalities should be avoided unless there is sufficient attention to constructing counterfactuals. During implementation indicators should be assessed for their continued relevance.In situations where low density populations live in mountainous terrain, socio-economic and political factors may weigh more heavily then simple cost-benefit considerations. Even so, conventional cost benefit analysis can be used to rank and select the most cost-effective road option among the choices available.Although the Environmental Friendly Road Construction framework is considered the best response to the environmental concerns in road construction in Bhutan, some of the specific guidelines need to be tailored to local situations.
P100342 | Avian Influenza Control Project | South Asia | Nepal | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2012 | 2013 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/708301475069553490/text/Nepal-Avian-Influenza-Control-Project.txt | http://documents.worldbank.org/curated/en/708301475069553490/pdf/000020051-20140625111345.pdf | The ICR identified a number of lessons (page 17), including:Investment in biosecurity level 3 laboratories should be carefully considered at appraisal. Level 3 laboratories are expensive and have significant maintenance costs and capacity requirements, and may not be justified for small or low income countries.Collaboration with UN and donor agencies can strengthen technical institutional capacity. Other agencies can provide expertise in areas where the Bank lacks capacity.Engagement of UN agencies in global programs should be conducted at a headquarters level, not at the individual project level. It can take up to a year to contract UN agency partners, so project implementation will be delayed if issues are not negotiated until after project approval.
P100342 | Avian Influenza Control Project | South Asia | Nepal | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2012 | 2013 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/509981468289199264/text/783170PPAR0Nep0Box0377354B00PUBLIC0.txt | http://documents.worldbank.org/curated/en/509981468289199264/pdf/783170PPAR0Nep0Box0377354B00PUBLIC0.pdf | 7. Lessons 7.1 The project offers a broad range of lessons, both for animal health/human health projects and for broader operations in countries like Nepal. The main lessons include\. Â· Investments in laboratory equipment and civil works may be inefficient if they outstrip the financial and technical capacity of staff to operate and maintain them. Including training programs for technical staff is not sufficient without an ability to retain these staff (Para 5.4, 6.9). In particular, Biosecurity Level 3 laboratories are expensive and have significant maintenance costs and capacity requirements. Experience with and solid capacity for operation and maintenance of Biosecurity Level 2 laboratories would seem to be an important prerequisite before advancing to level 3. (Annex B4) Â· Failure to adjust compensation rates for inflation and other price increases can reduce the real value of compensation payments. If compensation rates fall relative to the market value of birds, then farmers may be unable to restock even if compensated, and may have weak incentives to report disease outbreaks early. Flat rate compensation mechanisms may be simple, but can cause problems when they do a poor job of tracking the value of what is compensated (for example, ducks may be worth much more than chickens). (Box 1) Â· Attempts to control spread of HPAI in poultry at the border may have limited effectiveness countries with long, porous borders. Quarantine resources might be more effectively used to build capacity to conduct visual inspection and rapid diagnostic tests at internal transport bottlenecks such as major highway junctions and international airports. (Para 4.25) Â· Containing an influenza epidemic or pandemic among humans is likely to be extremely difficult in countries with modest public health infrastructure. Influenza containment in humans may require an ability to rapidly implement pharmaceutical interventions (ring vaccination and use of antivirus) and nonpharmaceutical interventions (physical distancing policies such as quarantine and school or workplace closures). Resources might be used more efficiently on pandemic mitigation, such as through improving vaccine distribution systems, rather than by attempting a containment strategy. In Nepal, screening incoming passengers at the sole international airport may have delayed the 2009-10 pandemic by one month, but it was not possible to prevent the spread of the pandemic to Nepal through ground transport. (Para 4.41-42) Â· Collaboration with United Nations agencies can provide technical expertise that the World Bank lacks, but there can be delays in implementation if there is insufficient engagement of these agencies at a headquarters level. The World Bank has only moderate capacity on animal health or pandemic preparedness, and so projects can benefit from advice and assistance from FAO and WHO. But in Nepal a working agreement with UN agency partners was not negotiated until after project approval, which took roughly a year and delayed project implementation. (Para 2.18, 3.4) Â· Emergency projects require significant procurement capacity early on. The lack of dedicated procurement expert can contribute to delays in implementation and an inability to meet emergency goals. Procurement capacity needs to be frontloaded to get good procurement plans finished early on, to hasten rollout of emergency projects. (Para 3.17) 7.2 The experience in Nepal also confirms a number of technical findings specific to avian influenza\. Â· Serological testing of apparently healthy chickens may be of limited use in detecting highly pathogenic avian influenza. The virus sickens and kills chickens so quickly that the likelihood that apparently healthy birds are infected is extremely low. In ducks and some wild birds, the disease has a longer incubation period and there are often asymptomatic carriers, so active surveillance may still be useful. In Nepal, active surveillance of healthy chickens failed to detect many cases and was discontinued. (Annex B3) Â· Outbreak containment need not require mass culling. Culling birds at the source of an outbreak and nearby farms can be sufficient if done quickly enough. Culling in a full 3.5 kilometer radius can be much more expensive, can anger farmers, and may strain compensation budgets. In Nepal, no adverse consequences were observed from adjusting the culling policy to reduce the area where culling was required. (Para 5.3) Â· Vaccination of poultry may be the wrong strategy to use for reducing disease risk in low capacity countries. In Nepal, planned use vaccination was abandoned. (Para 3.7) Â· Conventional polymerase chain reaction technology â€“ rather than real-time PCR technology â€“ is easier to maintain and operate (though is slightly less accurate and is slower), and may be a better technological choice for countries with weak staff capacity. In Nepal, some laboratories were equipped with real time PCR technology but were unable to operate and maintain it, but still conducted diagnoses using the conventional technology. (Annex B3)
P100383 | Istanbul Municipal Infrastructure Project | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2007 | 2013 | 2015 | ICRR | >=10 million & <25 million | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/118451474942738679/text/000012394-20150108145942.txt | http://documents.worldbank.org/curated/en/118451474942738679/pdf/000012394-20150108145942.pdf | IEG draws the two lessons from the ICR:Decision meeting with peer reviews should be required for Level 1 restructuring.The challenge of an implementing agency with no previous experience of Bank-funded project should not be underestimated. Training and technical support may be required to ensure a full understanding and acceptance of Bank policies and procedures.In addition, IEG draws two additional lessons:Criteria for readiness for implementation need to extend beyond the Regional level. While this project met the Regional criteria for readiness (PAD page 17), Bank processes need to be in place to not only clearly define such criteria, but also ensure that they are verified by sector and country management.The potential for the safeguard policy on International Waterways being triggered should be carefully assessed in relevant project preparations. This is essential in order to prevent compliance problems during project implementation as happened in this project.
P100390 | Sri Lanka: Puttalam Housing Project | South Asia | Sri Lanka | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2012 | 2013 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/157371474566900817/text/000020051-20140625193413.txt | http://documents.worldbank.org/curated/en/157371474566900817/pdf/000020051-20140625193413.pdf | The following three lessons are drawn from the ICR with some adaptation: The projects that provide basic infrastructure such as housing, water, sanitation, and roads (which are closely related to each other) require integrated planning covering technical design aspects, staffing, and sequencing of implementation. For example, the National Water Supply and Drainage Board was contracted to study the sanitary situation in the IDP settlement. The study was expected to provide timely and suitable solutions. However, it took long to finalize and was not sequenced with the rest of the project activities (ICR page 16). There were delays in completion of roads contracts, partly because these were closely linked to the completion of some water schemes.The homeowner driven approach coupled with necessary technical assistance fosters ownership of the program among participants. The homeowner driven approach provided an effective platform for beneficiary participation and as a result, the houses not only conformed to technical specifications but also met the preferences of the beneficiaries.Community involvement through community based organizations especially for the management of water supply assets that are common property water can promote social integration. The project experience showed that both host and Internally Displaced Persons can work together to share and manage water assets.From IEG: Grievance Redressal Mechanism should have an independent assessors and judges. The assessor and judge should not be the same unit as it may compromise the objectivity with which the grievance issues are addressed (ICR page 12).
P100397 | MA-Regional Potable Water Supply Systems Project | Middle East and North Africa | Morocco | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2010 | 2016 | 2018 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/756751504635006340/text/ICRR-Disclosable-P100397-09-05-2017-1504634995403.txt | http://documents.worldbank.org/curated/en/756751504635006340/pdf/ICRR-Disclosable-P100397-09-05-2017-1504634995403.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.(1).Adequatepreparation is required before projectlaunch. Launching projects before they are fully prepared as in the case of this project increases the risk of inadequatedesign andimplementation delays. Thisprojects low level of readiness resulted in nearly two years ofimplementation delays and the delays contributed to the non-completion of severalproject activities at projectclosure.(2) Consensus onthe application of safeguards at the country level atpreparation isnecessary for compliance with safeguards. The experience with this project showed that clearer andstrict guidance during preparation could have helped the National Electricity and Potable Water Board (ONEE) in identifying therequirements and steps that it needed to take follow to reach OP 4.12 compliance and that addressing land acquisition issues priorto effectiveness and ensuring timely engagement of Project Affected Peoples in the compensation process could have reducedimplementation delays, which contributed to the non-completion of many project activities.(3) Integrating citizenengagement activities in the project cycle can be useful ensuring compliance with safeguards. The integration of a socialanalysis in the preparation of technical designs can be useful in reducing the need for land acquisition. Pipes, plants and otherhardware could be positioned to avoid, whenever possible, the need for land acquisition. For instance, in the preparation oftechnical designs for an ongoing Bank financed project, the social teams presented alternative plans that reduced the need for landacquisition by 50% (from 2000 plots to 1000 plots).(4). Downgrading projects can aid in speedingaction. The experience of this project showed that candor in project ratings when appropriate during implementationpromotes transparency and can be important in raising the level of dialogue and attention to the issue at hand. The decisionnot to extend the projects closing date due to pending land acquisition issues led to high-level discussion on landacquisition and motivated the ONEE to pay greater attention to compliance in an ongoing project.(5). Appropriatelending instruments can help in strengthening strategic partnerships. Given that this project was mainly an infrastructureproject, the Banks contribution on sector strategy was limited. Engaging in a Program for Results or Sector WideApproach (SWAP) may have encouraged a higher level of dialogue between the Bank and the client during implementation.
P100406 | AFCC2/RI-Lake Victoria Environmental Management Project Phase II | Other | Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2009 | 2018 | 2019 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/893191559326427552/text/-.txt | http://documents.worldbank.org/curated/en/893191559326427552/pdf/-.pdf | The ICR has nine quite useful lessons, the first four are derived from the most important of them but withadjustments of language, the fifth is an IEG added lesson. The level of ambition stated in projectdevelopment objectives needs to be realistic and attributable, even if the objectives are nested within a moreambitiouslonger-term vision,while measurable indicators need to be consistent with those objectives and notinconsistent witha counterfactual. In this case, the expectation of water quality improvement in the lake was unrealisticagainst a deteriorating trend and some of the fishery improvement expectations were alsounrealistic for similarreasons. Collaboration should be measured not onlythrough agreed end products such as frameworks, policies, andplans but as improvements at an intermediate outcome level inthe following areas:institutional collaborative processes;modalities and pathways of communication;qualities of collaborative interactions;nodes of responsibilities; and extentand quality of sharing of data. In this case, the deliverable frameworks and policies were originally covenanted asoutcomesbut were not necessarilyuseful indicators of changed processes and capacities. In a regionalpartnership program, it is important for realistic planning to understand the political economies and the incentivesforindividual partners within each sectorto supportthe proposed reforms and investments. In this case,there were some unrealistic expectations related to partner incentives for collaborative action, for example the water releaseprotocol. In a long-term lake basin partnership program aimed at enhanced collaboration between partners and agencies,and involving many national players, it is important to ensure ownership of investmentsat the level ofnational andlocal authorities, sanitation companies, asset operators, and community groups. In this case, more could have been done inrequiring formal agreements and operating budget commitments, particularlyin the case ofthe Resource Efficient andCleaner Production (RECP) activities, and more attention could have been paidtoperformance incentives. In a long-term program aimed at environmental improvement over a series of projects, it is important to treat any one project as a phasein the pursuit of the larger vision and to ensure continuity of funding, staffing, strategy, and institutions. In this case, therewere a number of discontinuities including, several years hiatus between the first and second project, and now, it appears again,between the second and a possible third. There was a lack of consistency in partner agencies with all three of the first projectnational agencies changingbefore the second project. Similarly, there was alack of continuity in the ME systemfrom the prior project, probably partly due to the hiatus between the two projects. Bank planning of long-term programs needsparticular focus on sustained support to allow each project to build on theprior project andto ensurecumulativelearning.
P100415 | Avian Influenza Preparedness Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2011 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/161831474592089248/text/000020051-20140625074850.txt | http://documents.worldbank.org/curated/en/161831474592089248/pdf/000020051-20140625074850.pdf | The ICR identifies the following lessons:A global template can enable rapid, good project design. The Global Program on Avian Influenza assisted the project in establishing a project design that covered the most important elements needed to reduce the risk of avian influenza.Close coordination with specialized UN agencies can enhance technical assistance. WHO, UNICEF and FAO provided technical assistance in close coordination with the Bank and the project implementing agencies.It is difficult to map progress on implementation without full time project coordinators.IEG also notes that:The Bank can play a useful role in facilitating discussions between multiple agencies and ministries in complex institutional environments.
P100438 | Adaptation to Climate Change Impacts on the Coastal Wetlands in the Gulf of Mexico | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2011 | 2017 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/119041498682205675/text/ICRR-Disclosable-P100438-06-28-2017-1498682196171.txt | http://documents.worldbank.org/curated/en/119041498682205675/pdf/ICRR-Disclosable-P100438-06-28-2017-1498682196171.pdf | The ICR (p. 27-28) included several lessons learned with some adaptation by IEG. The two most importantlessonsare: Complex institutional implementation arrangements can have a negative impact on projectimplementation. In this project, the involvement of a large amount of agencies and a relatively small sized amount of funds led tolittle commitment by the agencies resulting in implementation delays. Community involvement is critical for thesuccessful implementation of local adaptation measures. In this project, community participation was important throughout theproject implementation but will also be critical for the sustainability of the implemented activities.
P100451 | Avian Influenza and Human Pandemic Preparedness and Response Project | Europe and Central Asia | Tajikistan | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2006 | 2011 | 2012 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/465111475101337574/text/000020051-20140624201132.txt | http://documents.worldbank.org/curated/en/465111475101337574/pdf/000020051-20140624201132.pdf | The ICR offers three lessons which are summarized here with some adaptation:1. Effective coordination of activities with other donors and projects requires time and can delay implementation therefore it should be planned for. Where cross-donor coordination is envisaged, it is prudent to attempt to project the sequencing and critical paths of the different elements and to incorporate flexibility into implementation schedules.2. Early cooperation with internationally experienced UN agencies working in the same or related fields can offer synergy and provide a basis for sustaining programs in tight budgetary situations.3. Refurbishing old buildings for laboratories or wards of hospitals is likely to be fraught with unpredictable design constraints that are costly to remedy. While it may appear desirable and pragmatic to take advantage of already available buildings and infrastructure, in cases of facilities such as laboratories and hospital wards the remedial costs may be prohibitive. This is particularly applicable to laboratories and other facilities for handling highly pathogenic and contagious materials that must abide by international standards.
P100451 | Avian Influenza and Human Pandemic Preparedness and Response Project | Europe and Central Asia | Tajikistan | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2006 | 2011 | 2013 | PPAR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/839221468305044219/text/709550PPAR00Bo0C0disclosed070230120.txt | http://documents.worldbank.org/curated/en/839221468305044219/pdf/709550PPAR00Bo0C0disclosed070230120.pdf | 7. Lessons 7.1 The lessons emerging from the experience of the project focus around the challenges going forward, of turning a promising beginning of good cross-sector work, into institutionalized sustained approaches, recognizing that the threat of avian influenza remains, albeit not necessarily in the immediate neighborhood of the country. With a view to draw lessons of experience, it would be appropriate to keep in mind two important perspectives, and their implications. 7.2 Firstly, the project was designed as an emergency response to a perceived threat, but one which had not actually materialized in Tajikistan at the time that the project was appraised. Secondly, the project was designed in a low institutional and human resource capacity environment, where the prevailing systems for surveillance and detection, as well the regulatory environment in the context of managing animal diseases, were old and had not changed much from the Soviet times. In such an environment, it is quite likely that there would be tensions between ensuring rapid implementation start up in the face of an imminent threat in a low capacity environment, and the need to ensure that the implementation experience gets embedded in ongoing operations of ministries, and hence contributes more broadly to building capacity in a sustainable manner. 7.3 Emergency responses run the risk of low sustainability. The preparedness built by this emergency operation will be rapidly eroded in the absence of a program (externally or internally funded) that goes beyond the life of the project, for securing the sustainability of preparedness to deal with future outbreaks. Tajikistan was among the poorest of the former Soviet republics, it faced major budget constraints, and development programs have been largely externally funded. In this environment, there is a high likelihood that the government would find it difficult to sustain high budget allocations to sustain operations put in place. As also noted by one of the funding partners, a transition phase is indispensable for emergency projects which among others, should focus on managerial, institutional, and long-run financial sustainability. 7.4 The use of a Project Management Unit that is not fully integrated into the main ministries or operational departments runs the risk of compromising country ownership and sustainability. Clearly the need to get implementation underway quickly weighed heavily on the minds of the appraisal team, given the risks that were clearly there; the use of an existing PMU with the necessary capacity on procurement and financial management did facilitate start up of implementation. However, the arrangement compromised on government ownership, and contributed to some inefficiency in the implementation of components in sectors that had not been the domain of the agriculture sector staff. The issue became more pronounced in this multi-sectoral project, where the PMU was unable to establish effective links equally with both of the main sectoral ministries. 7.5 The engagement of international organizations to support implementation of the emergency project had benefits in terms of technical rigor, but also potential consequences in terms of reduced ownership. These agencies provide good crosscountry links in situations where an issue straddles national boundaries, and where it is necessary to link up with technical institutions internationally. However, execution responsibilities for components need to be embedded within a government agency. In the case of this project, UNICEF was given responsibility for implementing the component on Public Awareness Building, leaving no government agency that felt ownership for the activities once the project ended, weakening sustainability of the program. The risk of reduced ownership would hold equally in the event that private contractors were enlisted for implementing an emergency operation. 7.6 Where a project is aimed at mitigating a disease threat with an uncertain probability of occurring, the results framework should cover both scenarios when the disease strikes and when it does not. Intermediate outcomes need to be monitored to assess whether capacity is improving, and whether there are sustainable changes in preparedness, irrespective of whether the threat materializes. Given the prevailing institutional weaknesses, such measures would have been helpful to highlight to policy makers the need for concerted follow up action to ensure sustainability of preparedness. 7.7 The use of a horizontal Adaptable Program Loan did not pose a problem in the case of Tajikistan, with regard to the choice of component and the use of a common template. However, that template was geared toward emergency measures for preparedness. Going forward, the challenge for the Government, and also for the Bank as it considers areas of focus in supporting the country, is how to maintain readiness to deal with avian influenza or other emergencies over the longer term in the absence of an outbreak in the immediate future.
P100455 | Henan Ecological Livestock Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2010 | 2016 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/424191484176052231/text/ICRR-Disclosable-P100455-01-11-2017-1484176031510.txt | http://documents.worldbank.org/curated/en/424191484176052231/pdf/ICRR-Disclosable-P100455-01-11-2017-1484176031510.pdf | The ICR suggested three lessons from the project which are summarized briefly below highlighting their broader relevance todevelopment programs.(a) Actions to Address Environmental Hazards Require Supportive Policies andRegulations. A range of national and provincial policies and regulatory frameworks relevant to livestock wastemanagement can provide the legal basis and opportunities for financial incentives in a successful project to support improvedmanagement of livestock waste.(b) Government Commitment to the ProjectsObjective is Essential to Successful Outcomes. Stakeholders commitment, dedication and capabilities arecritical to ensure project success, sustainability and ownership. These were demonstrated through exceptional commitment and strongleadership by the government at provincial, municipal and county levels in making key decisions and providing policyguidance.(c) Public Goods Generated by Environmental Investments Need to be Valued Accurately to Reward PrivateInvestors Equitably. To achieve public good benefits from an investment project a financial subsidy to participatingprivate investors is essential. The final cost sharing contribution from the private investment provides an estimate of theparticipating private investors direct benefit and hencethe amountthat investor arewilling to payasa share of the total cost.IEG would addthe following two lessons from this project.(a) SustainingaGovernment Subsidized Program of Livestock Waste Managementmay be Excessively Costly. The results ofthis project show that even a 50 percent average government subsidyto participating enterprises to cover the capital costs oflivestock waste management practices may not be enough to sustain thewaste management operations.This raisesquestions about the capacity of governmentsto payadequate subsidies to ensure thesustainabilityof projectssuch as this one implemented in some Henan counties.(b) Need to Sustain Environmentally Appropriate WasteManagement. If projects such as this one are pursued then recipients of subsidiesaimed at encouraginglivestock enterprisesto invest in environmentally appropriate livestock waste management practices need to agree tosustainthose management practices in the longer termfor periods suchas the expected life of the investment.
P100470 | Avian Influenza Control & Human Pandemic Preparedness & Response Project | Europe and Central Asia | Romania | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2007 | 2011 | 2013 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/819821474630145394/text/000020051-20140624214742.txt | http://documents.worldbank.org/curated/en/819821474630145394/pdf/000020051-20140624214742.pdf | IEG finds that an emergency project may not be the right tool for long term capacity building. It can be difficult to implement civil works projects and purchase of complex specialist equipment under the time constraints of an emergency project. When the country already has significant emergency response capacity, then using an emergency instrument may not be necessary.
P100470 | Avian Influenza Control & Human Pandemic Preparedness & Response Project | Europe and Central Asia | Romania | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2007 | 2011 | 2013 | PPAR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/183321468294312625/text/787810PPAR0P1000Box377380B00PUBLIC0.txt | http://documents.worldbank.org/curated/en/183321468294312625/pdf/787810PPAR0P1000Box377380B00PUBLIC0.pdf | 7. Lessons 7.1 Building on the project experience this assessment identifies the following lesson\. 7.2 Countries that have already effectively controlled avian influenza outbreaks in poultry many not need an emergency project, but rather long term capacity building. In this case, Romania controlled avian influenza outbreaks in 2005, 2006, and 2010, and already had a passive surveillance system, centralized diagnostic capacity, and a functioning veterinary service agency. The real emergency issue was EU accession, but after accession was achieved the government lost interest in the project. 7.3 The evaluation also notes that following this project, avian influenza is still a threat to Romania. Avian influenza risks cannot be minimized without ensuring adequate capacity in the animal health sector and adequate biosecurity in the poultry sector. Interventions that target only the human health sector will miss the most effective way of reducing the risk to humans â€“ by controlling the disease among poultry. Project designs that do not improve biosecurity on commercial farms or backyard systems will miss an opportunity to reduce the likelihood of avian influenza outbreaks.
P100478 | Managing Healthcare Waste and PCBs | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2013 | 2017 | 2018 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/382091522283133901/text/Tunisia-TN-GEF-Managing-Healthcare-Waste-and-PCB.txt | http://documents.worldbank.org/curated/en/382091522283133901/pdf/Tunisia-TN-GEF-Managing-Healthcare-Waste-and-PCB.pdf | The following lessons have been identified and/or adapted from the ICR:Well designed, thoroughlyprepared and diligently supervised projects can be sustained even through challenging times. In spite ofthedifficult country context, including several political changes in the first year ofproject implementation, theproject closed on time andachievedsatisfactory results. Timely supervision and close monitoring from the Bank wererequired to keep the project on track.Centralizing procurement removes friction at the operationallevel. In structuring the contractual arrangements of the waste management process, the project initially left it up toeach individual public-sector health care facility to procure the services of a private-sector provider for HCW collection,treatment and disposal. As such, the processing of HCW from public health care providers depended on each entitys capacityfor timely and reliable procurement and fulfillment of payments. This led to interrupted service and improper management of HCW,thereby undermining the project objectives. By centralizing procurement in geographic regions at the level of the competent,responsible entity, namely the MOH, procurement and contractual management was more effectively handled, leading to improvedservice provision at the operational level.Arrangements for ME should receive close attentionduring the assessment of project readiness. The project intended to have a full ME system in place andoperational by the end of the first year, however, this target was not reached until towards the very end of the project.Defining explicitly what the ME system should consist of and explaining what was meant by in place andoperational would have aided the implementation phase. Often, when preparing Bank projects, ME is briefly dealt with bydelegating the responsibility to the implementing unit and referring to the results framework. If ME formed a more substantialpart in assessing project readiness, projects would benefit through better tracking of progress, thereby increasing the capacity ofthe project to make informed adjustments. This is an old lesson, but repeated here as also mentioned in the ICR.
P100530 | INDIA - Financing Energy Efficiency at MSMEs | South Asia | India | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2010 | 2019 | 2020 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/956561588902923072/text/India-IN-Egy-Effcy-at-MSMEs.txt | http://documents.worldbank.org/curated/en/956561588902923072/pdf/India-IN-Egy-Effcy-at-MSMEs.pdf | The ICR proposes several lessons. Among the most important with general application to similar projects were thefollowing:1. Given a well designed and implemented project, it is possible to show that good environmentis good business too.In fact, the key to convincing entrepreneurs, independently of the size oftheir establishments, to adopt EE and other environmentally-friendly technologies and practices is to be able to demonstrate thatthis willresult in reduced costs and greater profits in the future. The lesson is that this project was successfully able todo this for key energy-intensive MSME clusters.2. The model of a partnership between afinancialinstitution(such as SIDBI) and a technical organization (such as BEE) provides an effective environment for largerinterventions in MSMEs across the country and in multiple sectors.In the present project, thispartnership proved to be an effective way of first piloting then expanding an innovative approach to working with MSMEs in variousparts of India and then possibly scaling up these interventions and creating a market for EE improvements in various industrialsubsectors. The lesson is that institutions with different roles but common objectives can collaborate on complex developmentchallenges.3.Financial incentives along with ensuring a financial stake of MSMEs at the initial stagecan spur an effective EE market.Experience under this project revealed thatthe greater thefinancial stake that an MSME has in implementing EE improvementand other clean production measures, the more likely is itscommitment to complete the required investments in a meaningful way. The lesson is that well designed financial incentives canstimulate environmentally beneficial investments.4. Intermediaries such as Industry Associations and localleaders can play a key role in building trustamong MSMEs that need or seek EE and/or clean production solutions and serviceproviders. Here too, this projects experience showed that the role of such intermediaries was important also inhelping the implementing agencies and the Bank to understand the nature of the problems and barriers faced by MSMEs that needed tobe overcome and to identify first-movers and communicate positive results of pilot projects to their member MSMEs. Thelesson is that engaging appropriateintermediaries can enhance a projects outcomes by helping all stakeholders(i.e.,the ultimate beneficiaries, implementing agencies,and the Bank) to better understand and address keyobstaclesto their achievement.IEG suggestsanotherlesson.5.Timely AdditionalFinancing can play an essential role both in increasing the outputs and enhancing the outcomes of a project and extending its lifeand, thus, its effectiveuse of the available external and domestic resources in pursuit of itsobjectives.In the present case, it should be recalled that only 38 percent of the original GEF grant hadbeen disbursed by the time of the original closing date and 67 percent was disbursed by the time of the second two yearslater. The AF permitted the addition ofanother two and a half years to the life of the project as well as moreresources, thereby permitting its geographic expansion and greater ultimate use of a larger volume of grant resources. The lessonis that strategic additional financing providing more time for the use of existing resources as well as additional resources canhave exponential benefits for a well-managed project.
P100534 | Jordan Employer Driven Skills Development Project | Middle East and North Africa | Jordan | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2008 | 2014 | 2014 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/305851474491085042/text/000020051-20140626130611.txt | http://documents.worldbank.org/curated/en/305851474491085042/pdf/000020051-20140626130611.pdf | The ICR (pp. 23-25) identifies several valuable lessons:It is important to allow for enough time and a gradual change process. Complex changes need a gradual implementation process, buy-in from all stakeholders, and leadership capacity among relevant stakeholders. In this case, a paradigm shift from supply-driven to demand-driven E-TVET programs was more difficult to implement than originally planned. Problems with technical assistance can severely slow down progress. In this case, several delays in project implementation resulted from problems with technical assistance, including the rejection of inception reports and the need to rebid one major contract. Better results were achieved when all stakeholders participated in the formulation of relevant terms of reference and in the implementation of activities.Training on Bank procurement and financial management supports smooth implementation. The borrower's ICR also identifies the need for training of all relevant stakeholders in Bank fiduciary rules during project preparation. Early training will provide a clear understanding on the additional resources needed in terms of staff and time to follow Bank rules.
P100546 | Jordan Social Protection Enhancement Project | Middle East and North Africa | Jordan | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2008 | 2014 | 2014 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Highly Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/742931475076935854/text/000020051-20140626124338.txt | http://documents.worldbank.org/curated/en/742931475076935854/pdf/000020051-20140626124338.pdf | The ICR (pp. 26-28) identifies several valuable lessons:Problem projects require intensive implementation support to become successful. Restructuring can be used at the beginning of a project to adjust its scope to changing contexts. In this case, the restructuring was done too late and was inadequate to affect project performance. Poorly performing projects should not be maintained just to sustain policy dialogue. In this case, the project was not closed, in part because it was seen as providing a vehicle for policy dialogue (ICR, p. 27). However, this dialogue appeared to be ineffective, and the government has to pay a lending rate for this fixed spread loan. Projects need to be kept flexible. In many countries, a combination of targeting mechanisms are used to reach the poor. In this case, the Bank's focus on proxy-means tested targeting was not flexible and did not respond to the government's concerns with this method. The Bank could have used an opportunity for consensus building early on and adjusted the targeting methods to the local context.
P100564 | Haiti Economic Governance Reform Operation II | Latin America and Caribbean | Haiti | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2010 | 2011 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/673571474906261952/text/000020051-20140624185943.txt | http://documents.worldbank.org/curated/en/673571474906261952/pdf/000020051-20140624185943.pdf | Spreading an operation thinly over several objectives can lead to an incoherent whole that in a post-conflict, weak-capacity country will result in an unfocused reform effort and poor achievement of outcomes.- Adopting the appropriate outcome indicators is as critical as adopting an achievable set of coherent objectives. In this program, the objectives could have been better defined to suit the available policy actions and indicators.
P100568 | Avian and Human Influenza Prevention and Control Project | Middle East and North Africa | West Bank and Gaza |  | FCS | Infrastructure | Urban, Resilience and Land | SPF | IPF | 2007 | 2009 | 2010 | ICRR | Less than 10 million |  | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/513591474483817931/text/000020051-20140620071409.txt | http://documents.worldbank.org/curated/en/513591474483817931/pdf/000020051-20140620071409.pdf | In fragile situations such the West Bank and Gaza, project design should be simple, minimizing the need for coordination among a significant number of actors. If the operation may have to undertake emergency actions, such as carrying out mass vaccination campaigns to counter a pandemic, arrangements with an external agency to ensure the availability of trained staff is necessary. In these conditions projects that are primarily based on the concerns of external actors have limited chances of success. Considerable emphasis should be placed during preparation and appraisal on building demonstrable ownership in local institutions and securing the basis of close collaboration and coordination between ministries, and with UN agencies where this is essential. In such situations all conditions should be met before Board presentation to ensure that the operation can move swiftly to effectiveness and implementation. The project's outcome raises the question of whether, in high risk situations such as were faced by this operation, the Bank's rather ponderous procedures for approval and supervision of projects, and for procurement, allow it to effectively use its comparative advantage in mobilizing financial resources and in helping introduce international best practices.
P100580 | Roads and Safety Improvement | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2009 | 2015 | 2016 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/369601468302038180/text/ICRR-Disclosable-P100580-02-09-2016-1455055191719.txt | http://documents.worldbank.org/curated/en/369601468302038180/pdf/ICRR-Disclosable-P100580-02-09-2016-1455055191719.pdf | The main lessons generated by the ICR generated are summarized below:1. An integrated road safety approach would improve the road safety more effectively. Investments in infrastructuretogether with substantial measures to strengthen institutions and enforcement as well as change road user behaviors would be moreeffective in improving the road safety than theinfrastructure investment only.2. TheBank should consider financing 100 percent of project cost where the country macroeconomic risk was identified as high orsubstantial and the government budget capacity was limited, so as to avoid the situation that the counterpart funding could not beprovided in a timely manner, resulting in delays in project implementation.3. Consultationswith stakeholders during the design phase could contribute to the improved design of civil works and the compliance with safeguardpolicies. For this specific project, consultation with the local communities was carried out both at the engineering design stageand during the implementation stage, the feedbacks from the local communities were reflected into the engineering design, by doingso, the design was improved and the compliance with safeguard policies was enhanced.
P100582 | REAL ESTATE REGISTRATION | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2007 | 2016 | 2017 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/133341485905694921/text/ICRR-Disclosable-P100582-01-31-2017-1485905683651.txt | http://documents.worldbank.org/curated/en/133341485905694921/pdf/ICRR-Disclosable-P100582-01-31-2017-1485905683651.pdf | The first two of the following lessons are taken from the ICR. The third is drawn byIEG.1 Collaboration withother external partners can be effective in dealing with implementation challenges. In thisproject, closecollaboration of the team with other donors, such as Swedish State Secretariat of Economic Affairs (SECO) and The GermanDevelopment Bank (kfW) prevented a duplication of work in the Digital Cadastral Map (DCM) and this in turn helpedaddressingthe challenges that rose during implementation.2 It would be useful to provide capacity building programs beforethe start of an IT system development. A capacity building program that begins at preparation and continuesthroughoutcan be beneficial for countries like Azerbaijan with capacity constraints to address procurement issues.3Indicators reflecting the full range of intended outcomes are necessary for the assessment of the projectsefficacy. In this case, there were no specificor quantitativeindicators relating to two of the writtenobjectives (reliability and transparency of real estate registration services).
P100584 | Chiller Energy Efficiency | South Asia | India | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2009 | 2015 | 2020 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/747381588903439577/text/India-IN-Chiller-Effcy-GEF.txt | http://documents.worldbank.org/curated/en/747381588903439577/pdf/India-IN-Chiller-Effcy-GEF.pdf | The ICR offers a number of lessons with regard to project design, implementation, institutional arrangements, governance,ownership, and Bank management support. Among the most important of these were the following:1. Pilotinnovative risky approaches before scaling up. In this project it was assumed thata 20% up-front subsidyorthe prospect of later receipt of CER revenues would be sufficient to induce chiller owners to seek resources from theproject in order to convert their equipment to non-CFC use. Thisoccurred, but to a much lesser extent than initiallyexpected. The lesson is that piloting innovative approaches to assess risks associated with such innovations may have beenbeneficial before launching into a comprehensive implementation.2. Keep the rationale for intervention underconstant watch, in particular, if the project start is delayed. Beyond this, once significant changes with respect toa projects likelihood of achieving its development objectives and/or associated results indicator targets occur during earlystages ofimplementation, an appropriate project restructuring is usually indicated but that did not occur in this project andas a result the projects outcome was unsatisfactory. The lesson is that if project restructuring is indicated arrange itas soon as possible for it to have a positiveimpact on the projects outcome. .3.CFC recoverywas an important aspect of the project to ensure sustainable outcomes, making the issue of ready and safedisposalofCFCsa key consideration.Knowing at the time of appraisal that there were no CFCincineration or recycling plants in India, the project could have been clearer as to how the recovered CFCs would be disposedof. The lesson is that if the infrastructure for a projects implementation does not exist or is weak, incorporatethat building of that infrastructure into the project design and appraisal.
P100619 | Ghana Urban Transport Project | Western and Central Africa | Ghana | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2007 | 2016 | 2017 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/693091497031730021/text/ICRR-Disclosable-P100619-06-09-2017-1497031717106.txt | http://documents.worldbank.org/curated/en/693091497031730021/pdf/ICRR-Disclosable-P100619-06-09-2017-1497031717106.pdf | Lessons included in the ICR are considered below as they have broader applicability:: Counterpart financing iscritical for the success of the project. However, if counterpart funding becomes unavailable, the project both theobjectives and components - may need to be restructured to ensure that the revised project development objectives can beachieved. Urban transport sector reform and the development of an urban transport system need to beimplemented sequentially. Furthermore, a new transport system is best achieved by establishing institutional arrangements with aclear mandate and involving various local government units before designing the new system. Strongstakeholder commitments (especially from bus operators) is crucial while introducing BRT or bus schemes which require relocation ofbus routes and rationalization of urban transport system. Implementation of a BRT system is complex. Communications with the publicto explain the BRT systems benefits are very important.The potential benefits to users are:affordable, fast,reliable, and comfortable transport systems.
P100620 | Forest and Nature Conservation Project | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2009 | 2015 | 2017 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/442031473302248522/text/Congo-Democratic-Republic-of-DRC-Forest-and-Nature-Conserv-PFCN.txt | http://documents.worldbank.org/curated/en/442031473302248522/pdf/Congo-Democratic-Republic-of-DRC-Forest-and-Nature-Conserv-PFCN.pdf | The ICR presents a number of valuable lessons including:(i) Avoid reliance on policy or regulatory pre-conditions asGovernment commitment with respect to themcan change over time. In this project the promised government decrees for thetimber production control and monitoring program and community forestry, were not met;(ii) Governancereforms insettings with a complex political economy should consider phased approaches with incentives for delivery, such asperformance-related disbursements; and(iii) Reliance on co-financing is inherently risky in countries with constrainedfiscal space. In the case of this project, unwillingness to set a budget led to cancellationof theconstruction ofMEDDs headquarters.IEG draws the following additional lessons:(iv) Substantial up-front training and otherinstitutional capacity building by the Bankis needed whenborrower capacity for procurement, financial management,environmental and/or social safeguards compliance, and/or monitoring and evaluation, is weak, together with frequent and proactivehands-on supervision; and(v). Formal restructuring should be administratively processed in a timely way following mid-termor other critical project performance reviewswhich identify significant implementation problemsthat can be tracedback directly to poor project design.
P100635 | OECS E-Government for Regional Integration Program (APL) | Latin America and Caribbean | OECS Countries |  |  | Infrastructure | Transport | IDA | IPF | 2008 | 2014 | 2016 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/203141473933568199/text/ICRR14946-P100635-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/203141473933568199/pdf/ICRR14946-P100635-Box396299B-PUBLIC.pdf | The ICR draws six lessons from the experience of preparing and implementing this project. The four most useful (after IEG editing) are:(1) Adequate project preparation time versus other considerations must be explicit. In the case of this project, the projectâ€™s preparation time was constrained by the existing timing to be able to use regional IDA resources for the OECS region. The project readiness was affected by the limited preparation time.(2). Project coordination affects implementation. Bank management has to be careful that projectsâ€™ ICT elements are neither duplicative nor contradictory.(3) Regional approaches for small island states has merits. However, a regional approach may entail a slower pace of implementation as more time and efforts are required for consensus building among regional countries. (4) In a fast changing and innovative sector such as ICT, it would be useful to consider programmatic approach to frame the Bank's commitment over the longer term. In the case of this project, a second phase was envisaged to provide continuity. However, given the delays in the initial years of the project, there was little time for the actual implementation of the e-government systems. Since the countries had not enough time to understand the implications of the e-government, they had little incentive to opt for a second phase of the project.
P100638 | Complementing EU Support for Agricultural Restructuring Project (CESAR) | Europe and Central Asia | Romania | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2008 | 2015 | 2015 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/650651468186253575/text/ICRR14766-P100638-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/650651468186253575/pdf/ICRR14766-P100638-Box393191B-PUBLIC.pdf | The ICR (p. 23) identifies several lessons, but some were not based on material in the ICR:Memoranda of Understanding are necessary to ensure effective collaboration among institutions. In this project, there was little coordination between ANCPI and MARD and lessons learned by one implementing agency, which could have been useful for the other implementing agency as well, were not shared between them. During project design, the governmentâ€™s policies should be carefully evaluated to ensure that the project objectives complement/support those policies. In this case, the implementation of the socio-economic guidance services were negatively impacted since MARD was not provided with the necessary information to understand how these services could be aligned with MARDâ€™s vision of a chambers of agriculture.
P100639 | Agricultural Pollution Control Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2008 | 2013 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/596881474897110818/text/000020051-20140626112949.txt | http://documents.worldbank.org/curated/en/596881474897110818/pdf/000020051-20140626112949.pdf | The ICR offers several lessons of which the following are the most important (with some reformulation of language):Investments for mitigation of environmental pollution measures in agriculture depend on public support and incentives, the latter being influenced by farm size. Switching to organic fertilizer makes sense economically when farms have significant livestock holding. These investments in most countries only take place with targeted support and adequate information programs. Such investments can only make financial sense on farms of a certain minimum size above the small or subsistence farmers or those with fragmented parcels. Partnering with other donor organizations such as the EU, FAO, GEF and the Dutch Embassy, with coordination across a common objective, can be highly beneficial. In this case, aid coordination across the common objective helped Croatia meet the EU accession agenda in the agricultural sector. The approach has potential to be replicated in other neighboring countries aspiring for EU membership.
P100639 | Agricultural Pollution Control Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2008 | 2013 | 2017 | PPAR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/142191498574097469/text/115691-PPAR-P100639-PUBLIC.txt | http://documents.worldbank.org/curated/en/142191498574097469/pdf/115691-PPAR-P100639-PUBLIC.pdf | 7. Lessons 7.1 IEG's performance assessment of the APCP experience suggests the following lessons, grouped under three interrelated categories\. ACHIEVING LONG-TERM BEHAVIOR CHANGE Â· Local stakeholder involvement\. Innovative projects require strong involvement of local stakeholders to generate advocates of behavior change. The involvement of farmers, government institutions, academia, and nongovernmental organizations is highly important to secure interest at the local level and to stimulate the sustainability of new practices. Â· More than infrastructure\. Combining support for infrastructure and activities to promote behavior change can be effective. Addressing constraints of a physical and social nature at the same time through complementary activities is essential to incentivize and enable beneficiaries to adopt new practices. Â· Realistic objectives\. Objectives of pilot interventions need to be realistic, especially when aiming at longer term goals that require behavior change. The environmental objective of the APCP was unattainable in the given project time frame and scale. Midlevel outcomes consistent with a longer time frame are more useful in illustrating progress against the objectives. ADEQUATE IMPLEMENTATION Â· Enabling environment\. Early analysis and addressing constraining factors in a project's enabling environment can reduce implementation delays. The APCP struggled with significant delays due to land titling issues. Tackling this issue from early on allowed the team to diminish the effects on implementation. Â· Effective pilots\. Pilot interventions are most effective when they can take a practical approach to implementation considering future scale-up. The ability of the APCP implementing agencies to test processes and refine them was crucial for the smooth transition to managing EU funding activities. Â· World Bank involvement\. The World Bank team leadership's consistent presence and responsiveness is crucial to ensuring the success of innovative project approaches. The APCP project planning and execution was smoother when the TTL was easily accessible, especially during innovation launches or when intense support was required. CLIENT COMMITMENT AND INCENTIVES Â· Lack of client incentives\. Small, stand-alone grant investments without government contribution risk not obtaining a sufficient level of attention. Both the World Bank and the client had little concern for the APCP implementation because of its small scale and because it was not combined with a loan. Â· Effective communication\. A successful project requires effective communication beyond the technical level to secure political buy-in and future funding. The APCP did not emphasize reaching out to key decision makers, and without the EU requirements related to agricultural pollution, current funding for APCP-like activities might not have been secured.
P100657 | SOCIAL INCLUSION PROJECT | Europe and Central Asia | Bulgaria | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2009 | 2016 | 2017 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/578511497994220781/text/Bulgaria-SOCIAL-INCLUSION-PROJECT.txt | http://documents.worldbank.org/curated/en/578511497994220781/pdf/Bulgaria-SOCIAL-INCLUSION-PROJECT.pdf | Arealistic risk assessment conducted not only at entry but also continued during implementation canhelptoanticipatedissues that arise during implementation (such as, in this project,the large amount of specialistsneeded to provide social services at scale), and, consequently, can help identify timely mitigationmeasures.Changes during implementation should be adequately reflected at the timeof restructuring and also in the results framework. Delays in getting the necessary funding from the government changed the designof the project giving insufficient time of exposure to the social services (from the expected 18 to 24 months at entry to 12months). This was not properly reflected inany of the restructurings nor it was reflected in the resultsframework.Cancelling the impact evaluation limited the expected learning from this pilot project. Whilepilotingwas not an explicit objective in the PDO/Financing Agreement, the PAD indicated this was a pilot project.Due tothe government ceiling spending and issues affecting the selection of municipalities, the impact evaluationwas cancelled. ThePDOwas assessedbya comprehensiveschool readiness test applied at baseline and end line tochildrenbenefitting from SIP supported formal kindergarten without a proper control group. Funding for this assessment came from theproject supervision budget, but otherassessments (quantitative or qualitative) were notconducted.
P100657 | SOCIAL INCLUSION PROJECT | Europe and Central Asia | Bulgaria | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2009 | 2016 | 2018 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/758411532018432539/text/124861-PPAR-P100657-P166293-PUBLIC.txt | http://documents.worldbank.org/curated/en/758411532018432539/pdf/124861-PPAR-P100657-P166293-PUBLIC.pdf | 7. Lessons 95. Official databases are important, but may need to be complemented with mapping of target communities and households and their needs, constraints, priorities, motivations, and dynamics undertaken by those with intimate knowledge of the community and with community development expertise. Exclusive reliance on official databases (whether at the national or municipality level) risks undermining the full and accurate identification and quantification of target groups necessary for designing and setting priorities for interventions, assessing real coverage, and effectively reaching those in need. Baseline and endline beneficiary assessments may have helped to identify target groups and their needs more accurately and track their outcomes. 96. Mobile services and mediators face challenges in reaching target populations, especially when mediators are few relative to their target populations and do not share the language, culture, and living conditions of those populations. Leveraging their efforts with NGOs, CBOs, and other leaders and actors trusted by the community has the potential to enhance the coverage and effectiveness of services. NGOs, CBOs, local institutions, and community leaders and representatives have a crucial role to play in brokering supply and demand for services and giving voice to target communities. Their potential roles and comparative advantages include troubleshooting, problem-solving, prioritization, targeting of services, listening to leaders and other community members. This nurtures mutual trust, constructive dialogue, and a learning-by-doing process. 97. Low appreciation of evidence for learning, program refinement, and policymaking can undermine the effectiveness of programs and policies, especially where piloting is intended. The development of M&E capacities could provide MLSP with a critical management tool for ensuring continuous learning and accountability for ECD results and increase its potential for resource mobilization and future replication. As the government of Bulgaria moves toward the development of a policy on ECD, it needs to articulate an M&E plan and framework; articulate roles and responsibilities for data collection and analysis and reporting; develop M&E capacity and systems; and establish a process for vetting and acting on data. 98. Experience under the SIP reveals the scope and opportunity to clarify roles and responsibilities to optimize comparative advantages and synergies of the many actors involved, both horizontally (across partners at each level of the system) and vertically (up and down the various levels of national, regional, and municipal government). The fuller analysis and refinement of the institutional and organizational framework is critical for growing the SIP experience into a nationwide school readiness program (or ECD policy). Insights gleaned from field visits and discussions indicate opportunity for enhanced effectiveness of ECD efforts through\. (i) fine-tuning decentralization arrangements, including a better alignment of responsibilities and financing across levels; municipality capacity building in program management and M&E; clearer articulation of quality assurance responsibilities and accountabilities; more facilitation of cross-municipality learning and exchange; and research and studies to document collective and individual effectiveness of the various levels; and (ii) fuller exploitation of partnerships at each level of governmentâ€”cross-sectorally (within the public sector) and between government and its various development partners\. international, for-profit, nonprofit, civil society, and communities. This could ensure coordination of actors at each level and culminate in greater efficiency and effectiveness through joint and holistic oversight of financing and performance. 99. Investments in ECD and social inclusion activities targeted to low-income and marginalized children ages 0â€“7 years and their parents are necessary, but they are insufficient to ensure the children's success and inclusion in primary school and beyond. Continued delivery of integrated social services and social inclusion interventions during their primary school years (and beyond), support for teachers for coping with the challenges of social inclusion in the classroom, and improved education quality are also critical. Opportunity exists for strengthening networks and partnerships between the integrated social services and social inclusion activities delivered at the municipality level and primary school teachers and administration to ensure cohesive and continued support to children and their families. The inclusion of low-income, marginalized, disabled, and/or special needs children in mainstream classrooms generates considerable, additional challenges and workload for teachers and administrators. Such challenges include discipline, poverty and social issues at home, language barriers, learning accommodations, and physical accommodations, among many others. Teachers need additional support to take on these challenges and workload, which could otherwise undermine their ability to teach all children. Whether children attend primary schools with mixed ethnicities or single-ethnicity schools in Roma neighborhoods, all students of all schools deserve a quality education. Investments in education quality are critical to ensure returns on the SIP investment.
P100706 | Development Policy Loan | East Asia and Pacific | Philippines | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2007 | 2007 | 2010 | ICRR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/676921474659674923/text/000020051-20140620072816.txt | http://documents.worldbank.org/curated/en/676921474659674923/pdf/000020051-20140620072816.pdf | The DPL1 experience points to several lessons that are applicable to DPLs and DPL series more generally.The efficacy of reforms depends in part on proper sequencing. Design of DPLs should consider phasing in related public financial management measures in ways that maximize the credibility of the budget process. For instance, transparency measures should ideally be implemented after the quality of fiscal data is verified, and effective controls are in place. Similarly, DPLs should balance the need for effective implementation of cross-cutting public finance and public sector reforms (for example, the roll-out of an MTEF) with the achievement of tangible sector-specific measures that deliver results on the ground (for example, in the social and infrastructure sectors). Forestalling expansion of service delivery until cross-cutting public sector reforms are implemented may not be a developmentally desirable or politically feasible. Technocratic reforms are subject to the vicissitudes of volatile politics, including to sudden changes in cabinet level or technical level leadership. In such settings, it may be very difficult to assess levels of country ownership and donor cohesion/coordination without considering political economy and historical factors. To the extent possible, DPL series should be launched under conditions of political stability or in clear turnaround cases, in coordination with donors. Donor coordination arrangements, like Borrower implementation arrangements, should be assessed to ensure that they are more robust to political shocks.It is important to assess the political economy of sector-specific initiatives in determining operational risks and identifying more viable design alternatives. This is particularly important in sectors (for example, the Philippines power sector) with a long history of ambitious yet difficult reform efforts.Even in middle income countries, programmatic TA provides an important complement to DPL prior actions and triggers. As such, TA can be critical in supporting the institutionalization of reengineered processes or systems in the public sector. Over time, it can also help generate the reform content necessary for the roll-out of successive DPLs in a series. As such, TA and capacity building should be packaged alongside DPLs to help improve their productivity.In designing DPLs, the Bank and Borrowers should be aware of both the promise and pitfalls of using aggregate quantitative targets for fiscal or sectoral performance as DPL triggers, particularly where attribution problems are significant.
P100735 | IN Orissa Community Tank Management Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2009 | 2016 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/993601496670258953/text/ICRR-Disclosable-P100735-06-05-2017-1496670244132.txt | http://documents.worldbank.org/curated/en/993601496670258953/pdf/ICRR-Disclosable-P100735-06-05-2017-1496670244132.pdf | The three key lessons are based onseven lessons presented in the ICR (ICR, p. 22) are the following:Sustainability of WUAs requires substantial investments in capacity building of both WUAs but also of the responsiblegovernment institutions to ensure continuous technical support to WUAs during and after Projectscompletion; Sustainability of project-financed improvements in irrigation depends on adequateOM. This requires appropriate institutional arrangements and a legal foundation for reliable funding, such ascollection of water use charges; Maximizing the production potential of tanks requires amulti-disciplinary approach. Project-financed non-irrigation activities and building the capacity water managementagencies to coordinate with other government ministries concerned with agriculture, agricultural engineering, agriculturalmarketing, horticulture and fisheries provide synergy to maximize development impact.
P100766 | ID-KDP Nias | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2007 | 2011 | 2013 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/831841474487405857/text/000020051-20140625083152.txt | http://documents.worldbank.org/curated/en/831841474487405857/pdf/000020051-20140625083152.pdf | The following lessons are taken from the ICR. 1. An impending project closing date can bring about the necessary actions to get aproblem project back on track. The clearly stated and achievable conditions set by theBank for agreeing to an 18-month extension were effective in focusing theGovernment agencies on essential actions to improve the quality and pace of projectimplementation.2. Frequent and intensive supervision by small specialist teams can help greatly toresolve problems and bottlenecks in the field. Two World Bank consultants were based in Nias from the beginning of the project until June 30, 2009. When the project experienced serious problems and implementation delays during 2008, a series of six targeted supervision missions between December 2008 and March 2009 (made possible because of the availability of grant fund sources forsupervision) were helpful3. It is important for the Bank to be supportive when a project is delayed and may beclosed before its completion so that any commitments made by the Government to thecommunities can be met, and the Governmentâ€™s credibility is not undermined. The Bankwas cooperative in assisting the Grantee in meeting the agreed conditions for theextension of the closing date. 4. Proactive supervision by the Bank and implementation by the Government are crucial. The availability of legal and reasonably priced timber was identified as a major problem and a potential supply bottleneck, butGovernment and Bank staff cooperated to produce a sensible â€œtimber managementplanâ€ which helped to minimize timber use, trained local officials in certification oflocal timber, ensured a supply of legal local timber, and included a tree replantingprogram, all with associated training programs.
P100785 | West and Central Africa Air Transport Safety & Security Project - APL Phase 2 | Western and Central Africa | Western and Central Africa |  |  | Infrastructure | Transport | IDA | IPF | 2008 | 2013 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/928371475117228038/text/000012394-20150109151130.txt | http://documents.worldbank.org/curated/en/928371475117228038/pdf/000012394-20150109151130.pdf | The following main lessons are the most important ones from the longer list presented in the ICR.Need to address adequately in project design the lack of managerial autonomy of the implementing agencies. Although the project design envisaged some independence for the implementing agencies, in reality their activities were affected by political factors outside their control, and this in turn was a cause of delays in the implementation phase.The political economy context is particularly important in sectors like the aviation sector.Bureaucratic processing can take much longer than expected. The delays experienced in getting the required government approvals were quite severe and this in turn almost jeopardized the achievement of the development objective. This needs to be mitigated with clear commitments in advance and realistic project preparation and implementation schedule.
P100789 | IN Andhra Pradesh and Telangana State Community- Based Tank Management | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2007 | 2017 | 2017 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/734211494856941279/text/ICRR-Disclosable-P100789-05-15-2017-1494856919710.txt | http://documents.worldbank.org/curated/en/734211494856941279/pdf/ICRR-Disclosable-P100789-05-15-2017-1494856919710.pdf | The ICR included seven lessons. The following twoare emphasized with some adaptation oflanguage: To increase net economic benefits, diversification needs to be complemented withwell-designed marketing strategies and value chain analysis. Diversification was a crucial part of the project wherecultivating non-paddy crops were encouraged. While the project realized overall net economic benefits from diversification, therewere cases where the market opportunities remained limited despite farmers allocating more areas under non-paddy crops. Theproject could have been more effective if a careful marketing analysisidentified market opportunities, developed productstrategies, pricing, distribution channels, and promotional methods were conducted during the course ofimplementation. Simplifying the responsibilities of the WUAs so that they focus primarily on waterdistribution and agricultural activities ensures better performance. WUAs performed well on some issues, but to expectthem to address a wide array of responsibilities is unrealistic. WUAs not onlymanaged themselves in an organizational sense,but also had to carry out some minor civil works as well as OM of rehabilitated tanks. The projects experience showedthat WUA performance was much stronger on administrative matters than on the financial and technical aspects.There shouldalso be a more stable and predictable flow of funds to WUAs, with assured governmental assistance in extreme weatherevents.
P100789 | IN Andhra Pradesh and Telangana State Community- Based Tank Management | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2007 | 2017 | 2020 | PPAR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/489591578586892069/text/India-Andhra-Pradesh-and-Telangana-State-Community-Based-Tank-Management-Project.txt | http://documents.worldbank.org/curated/en/489591578586892069/pdf/India-Andhra-Pradesh-and-Telangana-State-Community-Based-Tank-Management-Project.pdf | 7. Lessons 7.1 The potential economic benefits from improved irrigation infrastructure cannot be adequately realized by beneficiaries without the coordinated and ongoing support of multiple government agencies and research extension services in agriculture. The improved availability of water from the project could have been leveraged to a greater extent by providing coordinated and ongoing support for improved water management and sustainable agricultural practices, crop diversification to reduce risks and expand income sources, and developing better market linkages. This could have been attempted through this project or parallel projects, as had been done in other states in the country. 7.2 Continued support to WUAs in terms of resources and social intermediation, such as through nongovernmental organizations, is key to enhancing their capacity for improved water management in drought-prone areas. Support provided under this project enabled WUAs to improve their performance on administrative functions but less so on financial and technical aspects. A lack of stable and predictable technical and financial support after project completion has limited the efficacy of WUAs. Although WUAs can be expected to take care of minor repairs and maintenance and clearing of vegetation, they need access to services and technical support for repairs of any significance and for mainstreaming sustainable agriculture and water management practices. 7.3 Benefits from increased water availability can be further increased if cropping decisions by smallholder farmers in drought-prone areas are informed by water budgeting and collective governance principles for sustainable use. This project undertook significant initiatives to raise awareness and provide technical support to beneficiaries for making informed cropping decisions and applying water budgeting principles. However, to mainstream these practices and overcome social and political barriers for their adoption, appropriate policies and incentives need to be instituted, as suggested by experience from similar projects in other states in India. Such efforts can be usefully supported by introducing increasingly affordable measurement techniques using sensors and information and communication technology tools, making it increasingly feasible and affordable to reliably measure water conveyance and use.
P100792 | ROAD INFRASTRUCTURE AND SAFETY PROJECT | Europe and Central Asia | Bosnia and Herzegovina | IBRD | FCS | Infrastructure | Transport | IDA | IPF | 2008 | 2012 | 2014 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/762831475092722275/text/000020051-20140626002433.txt | http://documents.worldbank.org/curated/en/762831475092722275/pdf/000020051-20140626002433.pdf | The key lessons drawn from the ICR are:1. Project site visits are essential prior to cost estimation of components. Also, the more preliminary the estimates, the higher physical contingencies should be in order to mitigate likely cost overruns; with this project, the bridges to be rehabilitated should have been visited. This could have led to a more correct assessment of needed repairs and better estimation of associated costs.2. To sustain institutional strengthening achievement, it is necessary to have programmatic projects; There was a series of Bank financed projects in this country to help build up the roads management capacity. For example, the road directorates in both FBH and RS have acquired the ability to use the road asset management system developed under the previous Bank financed Road Management and Safety Project in their decision making. A follow-on Bank project to the Road Infrastructure and Safety Project could help built more directly on experiences relating to road safety and the OPBM pilots under the RISP project. 3. Promotional activities/public campaigns are important components of the road safety activities; The road safety campaigns carried out under the project made people more aware of the impact of their actions and the need for behavior change within society;4. Exposure to international good practice can be useful in building local knowledge. For example, in the RS, it helped to bring new perspectives to the Prime Ministerâ€™s Office and the Ministry of Finance who now see more than before the need to improve road safety and reduce maintenance costs.
P100806 | AR Sustainable Natural Resources Management (formerly Sustainable Forestry Development) | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2008 | 2016 | 2017 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/762481496237982386/text/ICRR-Disclosable-P100806-05-31-2017-1496237961728.txt | http://documents.worldbank.org/curated/en/762481496237982386/pdf/ICRR-Disclosable-P100806-05-31-2017-1496237961728.pdf | The followinglessons are taken from the ICR with some adaptation of language.(1)Althoughchallenging, Inter- institutional synergies areimportant for sustainable natural resource management. In thecase of this project, the project made significant efforts to bring together three different institutions at thefederal levelto try and coordinate programs. Given that each agency had its mandate,coordination was difficult. Howeveraproject with a multi-year implementation period generated long-term tiesthat ensured that institutions were aware of eachothers actions. In this case, coordination carried over following project closure withongoing programs between theNational Parks Administration and native forests to expand their reach and increase efficiency in reachingbeneficiaries.(2). Long term commitment is needed for sustainable natural resource management and landscapeapproaches. In the case of Argentina, the successive investments built from the early forest sector studies in 1996,followed by two lending operations in succession, contributed to the institutions having trained personnel.(3).Protected areas in infrastructure construction can be a significant hurdle. Based on theexperience of this project,park infrastructure works take a significant amount of time and logistics, particularly if they arein remote locations.More complicated works should be flagged at design and if possible front-loaded to make good progress on these uponeffectiveness.(4). Restructuringsneeds to considered realistically and resource allocation distributedappropriately to produce impacts within project timelines. In the case of this project while the restructurings aided ininstitutional changes, they did not strategically consider the difficulties associated with infrastructure development in protectedareas. Given this, remaining resources could have been better allocated to other parts of the program that had requested and couldhave utilized them to advance the PDO.
P100807 | POVERTY REDUCTION SUPPORT CREDIT III | Western and Central Africa | Cabo Verde | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2008 | 2009 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/632231475099533201/text/000020051-20140619074500.txt | http://documents.worldbank.org/curated/en/632231475099533201/pdf/000020051-20140619074500.pdf | 1. The use of several task team leaders sharing a leadership role can work well and should be considered where operations have broad content and where many staff are involved in project preparation and implementation. 2. Monitoring and Evaluation needs to be front and center as DPLs are prepared and operationalized, with government fully on board in terms of commitment and capacity. 3. Budget Support Groups can play an effective role in harmonizing aid flows and donor support for reform programs. 4. It is important for the government to carefully assess political support for reforms and to take into account relevant aspects of the country's political system in so doing. Equally, the Bank should be fully aware of these constraints as it prepares its assistance program. In the case of Cape Verde, government was prohibited from re-introducing in less than a year any proposed legislation which was defeated in the Parliament.
P100835 | Rural Water Supply and Sanitation | Eastern and Southern Africa | South Sudan | IDA | Non-FCS | Sustainable Development | Water | RETF | IPF | 2007 | 2011 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/692451475117615494/text/000180307-20141203051650.txt | http://documents.worldbank.org/curated/en/692451475117615494/pdf/000180307-20141203051650.pdf | The following lessons are derived from the ICR:Flexible ICR guidelines are required for post-conflict emergency situations since these projects do not undergo the full appraisal process. There is need for balancing rapid service delivery, capacity building and sustainability in post conflict situations. Unless the government can clearly communicate the need for this balance, the priority for reconstruction will remain higher than for sustainability issues. Emergency projects also need operation and maintenance arrangements introduced and build upon during the life of the project. To address huge infrastructure challenges, the country must first prepare long-term development plans with medium term prioritized programs and include the participation of relevant institutions to ensure continuity and reduce the risk of plans being questioned or changed to due to political expediency.
P100846 | Sindh DPC | South Asia | Pakistan | Blend | Non-FCS | Human Development | Education | IDA | DPF | 2007 | 2008 | 2011 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/150711474650361403/text/000020051-20140620074856.txt | http://documents.worldbank.org/curated/en/150711474650361403/pdf/000020051-20140620074856.pdf | The following lessons can be formulated from the implementation and assessment of the SEDPC: 1. Strong, broad, and deep Bank engagement with government officials -- not just in the Ministry of Education but in related sectors like to Ministry of Finance, and not just senior officials, but program managers -- can help to keep momentum and commitment to a financial support program even when there is a change in political leadership. 2. There is good logic and sense to a government program which supports simultaneous reforms in interconnected government agencies, representing an advance in the reform strategy compared to earlier sector-based structural adjustment programs of the 1990s. In this case, the success of education sector reforms was enhanced by accompanying increases in, and sustainability of, financial allocations to education made by Finance Department offices, increases in budgetary devolution to districts exemplified by conditional transfers of discretionary funds, and improved fiduciary management (reduced corruption). 3. Efforts to design and use sophisticated assessment and diagnostic instruments for tracking student achievement is a good step towards improving student learning outcomes, but until the results are made public and specific commitments are made to raising achievement levels, these efforts will not leverage the kind of improvements they were created for. Strong learning outcomes data could also be used in assessing the impact of increased government investment in education and improved delivery of educational services. 4. Development Policy Credits, which have been popular in Pakistan and other countries for their quick disbursement features, are often, because of their short time spans, not well suited to influence medium term performance outcomes such as improved learning outcomes and changes in management behavior.
P100854 | Ministry of Public Works DPL | Latin America and Caribbean | Chile | IBRD | Non-FCS | Infrastructure | Transport | IBRD | DPF | 2007 | 2009 | 2010 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/364841474632492888/text/000146597-20140619164831.txt | http://documents.worldbank.org/curated/en/364841474632492888/pdf/000146597-20140619164831.pdf | When executing a reform program, selecting the â€˜wrongâ€ group within the executing agency can reduce the speed and effectiveness of reform. This lesson is evident from the experience in the Ministry of Public Works. After the authorities transferred responsibility for coordinating the program from the Directorate of Accounting and Finance to the Directorate of Public Works (DirecciÃ³n General de Obras PÃºblicas, DGOP) the execution of the program improved because the DGOP had hierarchical authority over the Ministryâ€™s Directorates charged with managing the components of the program.Reforms of organizations are likely to stall or to face more difficulties than they would otherwise if the stakeholders within the organization are left out or included late in the process of change. Therefore, it is important to design a communications plan to maintain staff and agents of change in the organization properly informed. The process by which the goal is attained can be as important as the goal itself.
P100916 | Vietnam Third Rural Finance Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2008 | 2014 | 2015 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/280141475116829424/text/000020051-20150113005650.txt | http://documents.worldbank.org/curated/en/280141475116829424/pdf/000020051-20150113005650.pdf | The Implementation Completion Report offers a number of lessons of which the following are the most important (with some reformulation of language):Â· Micro-finance institutions have an advantage to expand access to finance in rural areas but they need support through an enabling regulatory framework and system; and also the possibility of consolidating these into larger and stronger institutions could give a wider operational jurisdiction and enable them to offer a wider range of financial services.Â· An approach that links line of credit to compliance with accreditation criteria has significant potential to effect institutional change. The project demonstrated that institutional improvement in the participating banks can be achieved through continuous monitoring of their performance against key performance standards and adjusting the size of their lines of credit in response to their operational performance and ability to manage riskiness of the portfolio. Setting eligibility criteria at bank supervision standards for banks and micro-financial institutions to participate in the project seems to work well by creating a three-tier system. Â· Capacity building in banks and micro-financial institutions is an important pre-requisite for them to function effectively in rural areas. It is however difficult and financially sub-optimal for such institutions to organize training courses for their limited staff on their own. A better approach to achieve economies of scale is to identify training needs and conduct training courses for such institutions at an aggregated level on a cost-sharing basis through local or international experts.This Review finds that:Â· When the objective is to expand access to finance in rural areas, the credit line and institutional capacity building efforts need to be accompanied by strong policy dialogue so that right policy framework that would ease private financial institution to enter the market, can also be instituted. This is essential for the sustainability of outcomes. Particularly when there are series of projects on the same topic, these projects can be designed under an APL type of instrument, which would include policy measures as well.
P100929 | Road Sector Program Support Project | Europe and Central Asia | Moldova | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2007 | 2011 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/959121474635837590/text/000020051-20140626123401.txt | http://documents.worldbank.org/curated/en/959121474635837590/pdf/000020051-20140626123401.pdf | The ICR has identified a number of lessons, of which the most important are listed below with some adaptation:Relatively small Bank's investment could help leverage significant external resources with a programmatic approach. Under this project, EBRD and EIB funding could not be raised without some amount of concessional financing provided by IDA credit. The Bank team support to the development of a long-term road sector investment strategy and implementation arrangements provided a foundation for the external partners to select the road sector for their investments.Coordination with development agencies makes operations more efficient for a greater development impact. This project formalized cooperation among the IFIs. During project preparation, the PAD was partly written by EBRD and EIB staff, who also used much of the World Bankâ€™s PAD text for their own project documentation. The Bank took the lead in organizing joint preparation and supervision missions and communicating shared positions.In a joint project design, attribution of program success to specific institutions is difficult. The PDO indicators in this project were not limited to the results of planned Bank-funded road sections but also included sections financed from EBRD and EIB.
P100935 | Avian Influenza Control and Human Pandemic Preparedness and Response Project | South Asia | Afghanistan | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2010 | 2011 | ICRR | Less than 10 million | Unsatisfactory | Highly Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/634351474665176651/text/000020051-20140624185639.txt | http://documents.worldbank.org/curated/en/634351474665176651/pdf/000020051-20140624185639.pdf | The three main lessons are as follows:1. In a country situation with major security and capacity issues, the starting point for project design should be the country constraints and an assessment of what is possible. An imposed supply-driven standard design package, while potentially offering some cost saving for a global initiative, is wholly unsuited to unusual or highly challenging circumstances.2. Contractual issues with other international agencies need to be resolved during preparation.3. In certain exceptional circumstances and conflict situations, where there is weak capacity, there may be advantages for speed of implementation to have donor financing channeled outside the government budget although funding through government can help strengthen systems for the longer term. Since the Bank cannot normally do this, key components on the critical path may be better handled by those agencies that can.
P100954 | Water Sector Improvement Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2010 | 2019 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/110421555941666186/text/India-Water-Sector-Improvement-Project.txt | http://documents.worldbank.org/curated/en/110421555941666186/pdf/India-Water-Sector-Improvement-Project.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptationof language (ICR, pages 28-29).(1) Climate change risk screening mayberequired for large infrastructure projects during preparations. The performance of this projectwas adversely affected by persistent low water levels in the Nagarjuna Sagar dam in part due to prolonged drought. The projectcould have benefitted from climate change screening to better understand the potential impacts of climatevariability.2) Integrated River Basin Planning and Transboundary Water ResourcesManagement approaches may be useful for major inter-state irrigation systems, irrespective of whether or not they crossinternational boundaries. This may be particularly important in countries with decentralized/federal governance systemswhere water resources management may be within the purview of the national government.(3)Demonstrations of pilots can help in fast-tracking innovative concepts for better project performance. Successfuldemonstrations and pilots on improved agricultural practices and conjunctive surface and groundwater use for selected WUOs helpedthis project in achieving significant development outcomes of improving aggregate crop yields.
P100965 | Debt Relief Grant Under the Enhanced HIPC Initiative | Western and Central Africa | Cameroon | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2006 | 2007 | 2008 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/990331474508299854/text/000020051-20140618060937.txt | http://documents.worldbank.org/curated/en/990331474508299854/pdf/000020051-20140618060937.pdf | Since SAC III and the HIPC process were supported by this grant, lessons learned from the former are relevant here. According to the ICR Review, lessons learned from SAC III included 1. well targeted TA is needed to support privatization; 2. privatization should be sequenced over a long time frame; 3. different levels of commitment between political and administrative actors need to be addressed; 4. single, multi-sector regulatory authorities should be encouraged for capacity-constrained countries. Lessons reported in the HIPC Completion Point report include the need for continued political commitment to strong macroeconomic management and structural reform to prevent deterioration in countries highly vulnerable to external shocks.
P100968 | Shanxi Coal Bed Methane Development and Utilization | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2009 | 2017 | 2019 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/821111544822922831/text/China-CN-Shanxi-Coal-Bed-Methane-Development.txt | http://documents.worldbank.org/curated/en/821111544822922831/pdf/China-CN-Shanxi-Coal-Bed-Methane-Development.pdf | IEG draws the following lessons from the ICR:1 . It is essential toprepare for the deployment of new technologies even during implementation: The project entity made an effort to deploy newtechnologies that it felt would work better than those that were originally planned for, though this led to some delays inconstruction and implementation. It is however important however to evaluate the availability and cost-effectiveness of all newtechnologies that are potentially available at the time of project preparation, to ensure that the most appropriate ones arechosen.2. In some project situations, it can be more cost effective to (i) bundle small separated works andprocurements into a consolidated EPC (Engineering, Procurement and Construction) contract with a single responsibility; and (ii)outsource a part of construction management tasks. In the initial phase of LNG plant construction of the project, individualprocurement packages were often too small to be attractive to potential bidders which contributed to construction delays andgenerated additional costs. Subsequently, many packages were consolidated into a larger EPC package, which turned out to be moreefficient and cost-effective.
P100980 | Institutional and Human Development in South Sudan | Eastern and Southern Africa | South Sudan | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2007 | 2011 | 2012 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/638021475071185446/text/000020051-20140625072906.txt | http://documents.worldbank.org/curated/en/638021475071185446/pdf/000020051-20140625072906.pdf | Building effective, efficient and accountable institutions in fragile and conflicted settings takes place in a highly contested political setting that leads to difficult trade-offs. While basic laws and regulations are needed to set standards that can be used by oversight bodies, the approval of such measures can be stymied by deep personal and political divisions among politicians. While PFM systems can become legitimate sites for social contest about what resources would become public revenue, how they would be allocated and used to procure particular outcomes, and about who would be held to account for the effects of those decisions, responsibility for addressing such contests also can be given to individual hiring and spending authorities, letting them use their discretion to achieve peaceful solutions. While use of technology systems can be used to connect disparate groups, helping to build trust and come to consensus, such systems can be difficult to implement successfully in environments without the most basic building blocks. While donors can use their leverage of funding and knowledge of successful efforts in similar settings to persuade governments to adopt policy and institutional reforms, governments may turn down this advice for more expedient practices, particularly when they have considerable own source revenue as a financial cushion. Other trade offs concern the use of Bank resources. While there are many reasons for drawing on the expertise of the World Bank Institute in training programs (as was called for in the ISN 2008-9), Bank staff may not be allowed sufficient access to work in insecure environments. Given this, the Bank may need to rely on private contractors, and to adequately budget for the high costs they face to work effectively and to provide for the safety of their staff.The challenge for the Bank is to successfully navigate through this maze of tradeoffs, using its leverage with a particular government to attain the best possible progress towards an effective, efficient and accountable public service.
P101076 | Climate Change Adaptation Program | East Asia and Pacific | Philippines | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2010 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/187901512769741749/text/ICRR-Disclosable-P101076-12-08-2017-1512769734641.txt | http://documents.worldbank.org/curated/en/187901512769741749/pdf/ICRR-Disclosable-P101076-12-08-2017-1512769734641.pdf | Following is a selection of lessons from the ICR (paragraphs 88-90):1. Pilot projects such as PhilCCAP requirea clear and upfront methodology for assessing costs and benefits, in order to properly assess the pilot. The pilot projectis essentially an experiment to understand if an approach is feasible, and replicable. A critical aspect of feasibility is thebenefits and costs of implementing the project. If adequate attention is not spent on this aspect, it ultimately challengesconclusions about the pilots feasibility, and decision on replication and scale up. The PhilCCAP as a pilot was not designedto capture this aspect of feasibility, andcollected costs and benefits data for only one intervention.2.Climate change is a cross-cutting issue which requires multi-sectoral and multi-agency engagement; such engagement requiresproject design that is flexible, and accommodates the time it takes for cross-sectoral collaboration. PhilCCAP facilitatedconvergence of DA, DENR, and other government agencies on a number of CCA interventions, and subsequent lessons emerging from theexperience of these convergence opportunities are that they require (i) time and space to learn how to work with multiple sectorsand agencies; and (ii) an iterative processto ensure that agencies derive sufficient benefits from convergence.3.Buy-in and sustained engagement of local government is essential to achieve progress in climate change adaptation andsustainability of introduced interventions. A challenge in the Philippines, and in other countries, is the high turnoverof local government staff, which occurs every three years. With changes in local government there are likely to be changes inpriorities, and therefore government and financial support at the local level are important. The experience of PhilCCAP wasthat early engagement with new local government, and sustaining this engagement through integrating local government in projectactivities, was important for the progress of the project, and is likely to impact on its sustainability. Related to this point isthe need to align CCA with the development priorities of the local government.
P101084 | BO: Investing in Children and Youth | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2008 | 2015 | 2017 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/158991467994804240/text/ICRR-Disclosable-P101084-07-08-2016-1467994776420.txt | http://documents.worldbank.org/curated/en/158991467994804240/pdf/ICRR-Disclosable-P101084-07-08-2016-1467994776420.pdf | The ICR (p. 22-24) identifies several valuable lessons, including the following: High-level project objectiveslead to attribution difficulties. In this project, the objective to reduce malnutrition was overly ambitious and was influenced byseveral factors beyond the projects intervention scope. Therefore, outcomes cannot be solely attributed to thisproject. Testing programs on a smaller scale allows for the modification of program design and for buildingimplementation capacity where needed. Originally, it was planned to pilot the BJA program with a focus on a high-priority targetpopulation. However, the program ended up being implemented on a national level, leading to implementation challenges giving theMoHs limited capacity. The main aim of CCTs is to attract the target population. In this project, the CCTs did notadequately reflect the transportation costs of the primary target group, low -income populations in rural areas. Also, the programdid not ensure that CCTs remained attractive when economic circumstances changed and employment opportunities improved. However,the MPED took transport and opportunity costs of the target population into account, and stipends were adjusted to reflectanincreasein the minimum wage, resulting in a low rate of abandoning the program.
P101086 | Results and Accoutability (REACT) DPL | Latin America and Caribbean | Peru | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2007 | 2010 | 2016 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/257451468066830281/text/Peru-Results-and-Accountability-REACT-Development-Policy-Loan-Project.txt | http://documents.worldbank.org/curated/en/257451468066830281/pdf/Peru-Results-and-Accountability-REACT-Development-Policy-Loan-Project.pdf | This review highlights the following lessons from the ICR:Ownership. Acritical success factor was the high level of government ownership of the policy reforms supported by the program. The Peruviangovernment strongly endorsed the case for more transparency about outcomes. Support for the program came both from the Ministry ofEconomy and Financeand from line agencies. This was coupled with broad public support (among civil society, the privatesector, and the press) for many of the reforms being implemented under the REACToperation.Participation. Support was also reinforced by the government of Perusgenerally participatory approach to policy reform. Multi-stakeholder dialogues were carried out at critical stages of policy designand implementation. This dialogue helped boost support from governmental and nongovernmental actors and counteract the resistanceof interest groups potentially affected by some reforms. Stakeholder engagement also helped mobilize the necessary politicalsupport for additional budgetary assignments to fund critical interventions to strengthen accountability and improve results ineducation, health, and nutrition. Perhaps more importantly, the participatory approach was at the core of the bottom-upaccountability measures promoted by the reform agenda, which encouraged the establishment of voice and client power mechanisms topromote awareness of poor quality in the provision of services among parents and policy makers and demand and track improvementsand results.Strong AAA work and accompanying operations. Much of the initialmomentum for the REACT Program was attributable to the impulse from RECURSO. RECURSO used mass media as a way to mobilizesupport for change and as a communication channel to inform parents about what they should expect for their childrensdevelopment outcomes. In addition, a package of services --includinglending and technicalassistanceinhealth, nutrition, social protection, and education --was critical in strengthening the implementation and sustainability ofthe policies supported by the REACT series.
P101103 | Egypt National Railways Restructuring Project | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2009 | 2021 | 2022 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/099010001272242207/text/Egypt00Arab0Re0ilways0Restructuring.txt | http://documents.worldbank.org/curated/en/099010001272242207/pdf/Egypt00Arab0Re0ilways0Restructuring.pdf | The following lessons are adapted from the ICR:For a railway project thatincludes a reform agenda andcomplex civil works, adequateimplementation time needs to be built into project design, and a clear definition of theresponsibilities of the Borrower, project management unit, contractors, supervision engineers, and the World Bank needs to beincluded. For this project, the 5-year timeline at appraisal was unrealistic given the projects complexity and thelimited experience of ENR with Bank projects. Moreover, expanding the project scope through additional financing two years afterthe original loan approval is not good practice because of the financial and administrative costs for the WBG and theBorrower.It is essential to assess stakeholder capacity early during the design stage to address gaps and ensuresmooth implementation. Reforming the railway sector is challenging in all countries. Railways are public institutions andpublic employers. Railway staff must be motivated while, at the same time, substantial reforms are instituted. It is important forthe World Bank to be realistic about client capacity and, for example, provide more training or closer supervision at the start ofa project.
P101156 | Demand for Good Governance Project | East Asia and Pacific | Cambodia | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2009 | 2015 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/445221468189275167/text/ICRR14774-P101156-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/445221468189275167/pdf/ICRR14774-P101156-Box393191B-PUBLIC.pdf | The ICR lists a number of lessons, some for demand-side governance and social accountability, and some for wider application. Four key lessons are summarized here:Where citizen voice is constrained, working at the local level and using collective rather than individual platforms can help produce improvements in public services. The ICR stated that Component 2 provided lessons that suggested that individual grievance redress mechanisms were rarely used and far less effective than collective platforms for social accountability, especially when facilitated by independent actors, with established local relationships to citizens and officials. In a project that addresses both the demand and supply sides of good governance, the self-reinforcing dynamic can lead to improvements in voice-accountability-responsiveness -- sometimes in surprising ways. Positive changes in policy and practice around citizen engagement, social accountability, administrative accountability, and transparency can take place in a challenging governance context. These positive changes may not be uniform or consistent, or even expected.Improvements in government accountability and responsiveness arise from utilization of information, not from information alone. In this project, information-only activities turned out to have limited effectiveness. Where information targeted to inform and empower citizens was combined with monitoring processes, however, responsiveness improved.When project design, scope, and measurement are too complex, it's important to simplify, even when doing so takes extra time and effort in supervision. At appraisal, this project had six implementing agencies, and a results framework with over 90 indicators, and project performance early on suffered. Revision at the mid-term review, along with intensive supervision attention to tracking using both the results framework and the good governance framework, helped to turn the project around.
P101156 | Demand for Good Governance Project | East Asia and Pacific | Cambodia | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2009 | 2015 | 2018 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/987321500652281850/text/116799-PPAR-P101156-PUBLIC.txt | http://documents.worldbank.org/curated/en/987321500652281850/pdf/116799-PPAR-P101156-PUBLIC.pdf | 7. Lessons There are three key lessons\. 7.1 First, timely identification of key changes in policy during implementation can substantially impact project results. The World Bank project team reacted promptly to changes in government commitment to DFGG work in public financial management, natural resource management, and with MONASRI and Radio National of Kampuchea. More important, the project team was strategic in using the opportunity to influence the design of the Strategic Accountability Framework through the learning from experience of civil society organizations and implementing agencies. This, in turn, significantly increased the outreach, focus, and impact of project-funded activities. 7.2 Second, the additional resources and time needed for direct support to nonstate actors to be effective should not be underestimated. Many governance projects recognize the importance of working with both state (supply side of governance) and non-state actors (demand side of governance) to make sustained governance changes in the performance of an individual agency. Yet projects need to be more realistic about what this entails, considering the limited capacity and experience of both the Bank and the civil society organizations in this area and the multiplicity of actors involved. 7.3 Third, projects aiming to strengthen accountability should pay more attention to the political economy. The DFGG Project used political economy analysis at entry to identify the leaders and state institutions that were likely to support social accountability approaches in the government. And, to some extent, this was an effective approach. But the focus of the political economy analysis needs to be broader. Better understanding of the underlying structures of power, interests, incentives, and institutions that could enable or prevent changes (for example, MEF support for the decentralization agenda; Ministry of Labor incentives with regard to the sustainability of the Arbitration Council; MOI incentives with regard to strong independent monitoring by civil society organizations) could have helped set more realistic and strategic objectives and define more concrete risk-mitigation measures.
P101160 | Health Sector Development Support | Eastern and Southern Africa | Burundi | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2009 | 2017 | 2018 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/619061529689950497/text/Burundi-BI-Health-Project-FY09.txt | http://documents.worldbank.org/curated/en/619061529689950497/pdf/Burundi-BI-Health-Project-FY09.pdf | The ICR (pp. 30-32) offers several useful lessons, including the following lessons restated byIEG: Linking performance-based financing with national funding priorities facilitates effectiveimplementation. The selective free health care policy for pregnant women and children was already a national policy declaredby the President of the Republic in 2006. Hence, the project built on pre-existing ownership and commitment (see Section3). Strengthening local capacity facilitates RBF approaches. Under theproject, training was provided to hundreds of community-based organizations and thousands of community health workers (see Section4). Non-governmental organizations, health committees, and community health agents were also sensitized to health prioritiesand operations (ICR, p. 22). Publicly accessible performance data can potentially enhance oversight (seeSection 9). The projects performance-based financing data was publicly accessible, and the ICR noted that thisenhanced credibility, including with development partners (ICR, p. 31).
P101170 | Second State Modernization | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2007 | 2015 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/151621433333986498/text/854120PUB0FREN0B011Aug201400PUBLIC0.txt | http://documents.worldbank.org/curated/en/151621433333986498/pdf/854120PUB0FREN0B011Aug201400PUBLIC0.pdf | The following lessons are adapted from the ICR (pp. 23-24):Political priorities and reform space can change, requiring a project design that accounts for these possibilities, particularly for reforms that engage the center of government. In this case, many of the reforms required significant and time-consuming effort to nudge ministries and agencies forward, impacting the pace and scope of project implementation.Especially in an environment of fluctuating high-level political commitment, horizontal cross-agency reforms are feasible in only a small number of areas at a time. Under this project, diffusion of effort across a large number of reform areas required considerable coordination and incentivizing.Reforms involving the design and implementation of large information technology systems are challenging with shifting policy priorities, and without a broadly accepted strategy, leading to delays in procurement and other implementation processes.
P101171 | AR SOC&FISC NTL ID SYS II | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2009 | 2014 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/380731468184739231/text/ICRR14668-P101171-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/380731468184739231/pdf/ICRR14668-P101171-Box393183B-PUBLIC.pdf | The ICR presents a number of relevant lessons: (1) importance of institutionalizing key functions (i.e., moving from enclave project approach to mainstreaming key structures within Government) as a key to sustainability; (2) technology-intensive projects need to be aware of new evolutions and adopt these when feasible; (3) proactive collaboration between the Borrower and the Bank and good mutual understanding is a key to successful procurement of technology products; and (4) excessive complexity in M&E needs to be avoided.A lesson for the review herein, somewhat related to the last lesson cited in the ICR, is that when information on key indicators cannot be collected due to political or other technical reasons, the Borrower and the Bank should pursue second-best approaches. For instance, ad hoc surveys and/or independent assessments of a sample of agencies might have been carried out to shed light on what percentage of potential fiscal benefits were realized.
P101177 | Second Results and Accountability (REACT) Development Policy Loan-Deferred Drawdawn Option | Latin America and Caribbean | Peru | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2009 | 2016 | 2016 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial |  |  | This review highlights the following lessons from the ICR:Ownership. Acritical success factor was the high level of government ownership of the policy reforms supported by the program. The Peruviangovernment strongly endorsed the case for more transparency about outcomes. Support for the program came both from the Ministry ofEconomy and Financeand from line agencies. This was coupled with broad public support (among civil society, the privatesector, and the press) for many of the reforms being implemented under the REACToperation.Participation. Support was also reinforced by the government of Perusgenerally participatory approach to policy reform. Multi-stakeholder dialogues were carried out at critical stages of policy designand implementation. This dialogue helped boost support from governmental and nongovernmental actors and counteract the resistanceof interest groups potentially affected by some reforms. Stakeholder engagement also helped mobilize the necessary politicalsupport for additional budgetary assignments to fund critical interventions to strengthen accountability and improve results ineducation, health, and nutrition. Perhaps more importantly, the participatory approach was at the core of the bottom-upaccountability measures promoted by the reform agenda, which encouraged the establishment of voice and client power mechanisms topromote awareness of poor quality in the provision of services among parents and policy makers and demand and track improvementsand results.Strong AAA work and accompanying operations. Much of the initialmomentum for the REACT Program was attributable to the impulse from RECURSO. RECURSO used mass media as a way to mobilizesupport for change and as a communication channel to inform parents about what they should expect for their childrensdevelopment outcomes. In addition, a package of services --includinglending and technicalassistanceinhealth, nutrition, social protection, and education --was critical in strengthening the implementation and sustainability ofthe policies supported by the REACT series.
P101190 | Water Supply and Sanitation Project | Europe and Central Asia | Belarus | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2009 | 2020 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/763851591290538528/text/Belarus-WATER-SUPPLY-AND-SANITATION.txt | http://documents.worldbank.org/curated/en/763851591290538528/pdf/Belarus-WATER-SUPPLY-AND-SANITATION.pdf | The ICR (paras. 93 to 97) lists five lessons and recommendations all of which are relevant. For the ICRR, these have beenre-organized and condensed into the following two lessons which have relevance to preparation and implementation of projects insimilar environments.Balancing infrastructure investment with sector reform to deliver the right mix of results isdifficult, and client ownership is paramount: Projects that pursue delivery of physical infrastructure can also seekto advance a reform agenda. However, client ownership is paramount to successful delivery of reforms. The inclusion ofan efficiency and sustainability agenda under the project were largely World Bank driven and proved somewhat premature in theprevailing circumstances. An alternative approach would have been to focus this project on successful and visible delivery ofphysical infrastructure investments, thereby building trust and paving the way for a progressive introduction of more complexreform agendas. The reform agenda should be embedded in the overall design of the project rather than tagged on as a separateelement. Under the project, inclusion of efficiency and sustainability objectives were closely linked to subprojectinterventions. Finding a way to embed these objectives better in the design, and to evaluate their impacts, may havedemonstrated benefits while not requiring large-scale changes to the choice of subprojects.When engaging in a newcountry, teams should invest more effort in understanding the sector financing model and the Governments policy vision inthat regard: While sustainability of development outcomes should be a key objective under any project, financialsustainability of utilities is an important means to that end. The approach taken in Belarus, with strong centralization ofthe WSS sector, ensures sector sustainability to a degree. However, the centralization of implementation through the PIU andthe ministries can preclude the project team from the necessary degree of interaction with the utilities to understand and assessthe financial and operational implications and risks at the level of the utilities. Efforts at institutional strengthening,at a utility level, may be constrained for this reason.
P101201 | Cairo Airport Development Project-TB2 | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2017 | 2018 | ICRR | >=100 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/554491506352075319/text/ICRR-Disclosable-P101201-09-25-2017-1506352056059.txt | http://documents.worldbank.org/curated/en/554491506352075319/pdf/ICRR-Disclosable-P101201-09-25-2017-1506352056059.pdf | To the extent the World Bank is involved in the preliminary design stage, it should play an active role in advising onthe need for and scope of related studies. It should also ensure a rigorous review of the design and the contract beforeit is tendered.To ensure better compliance with HSE aspects, responsibilities and consequences of HSE violationsneed to be clearly defined in the tender and contract documents. Part of the challengewith the project was toelevate Egyptian standards to internationally accepted, World Bank standards. The World Bank can helpits clients by advisingon provisions for HSE breaches in contracts, particularly related to fines and penalties.The management andoperations of airport terminals can be greatly enhanced through private participation in the form of a management contract.Given the challenging political and investment climate, the management contract for TB2 can be considered a favorableoutcome, particularly in a country with minimal history of private engagement in the sector. It is, however,considered goodpractice to have the same operator manage the entire airport for seamless integration across terminals and to ensure thatoperational efficiencies are gained.Greater clarity needs to be provided on the application ofa priceadjustment formula. In general, there appeared to be a lack of understanding across stakeholders on how to correctly applythe formula stipulated in Clause 13.8 on the Adjustments of Changes in Cost in the General Conditions of Contract in the standardbidding documents. In future projects, to reduce uncertainty and potential cost implications, it would be advisable to have anexample of the application of the clause in the bidding documents. As good practice, bidders could also be requested to run samplescenarios based on existing indexes as part of the evaluation. It would also be beneficial to have examples or illustrative guideson the World Bank Groups website for potential bidders to access. This should be brought to the attention of ProcurementManagement staff.The above lessons are adapted from the ICR.
P101206 | Expanding Access to Reduce Health Inequities Project (APL III)--Former Health Sector Reform - Third Phase (APL III) | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2008 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/308031498846527919/text/ICRR-Disclosable-P101206-06-30-2017-1498846511839.txt | http://documents.worldbank.org/curated/en/308031498846527919/pdf/ICRR-Disclosable-P101206-06-30-2017-1498846511839.pdf | The ICR offers the following relevant lessons from the preparation andimplementation of thisproject: The implementation of project activities cannot depend on the promise of approving a law. The design of this APLIIIincluded activities towards the increase of insurance coverage under a new unified health insurance scheme (SUS), whichin theend wasnot established. By anticipating that risk, the project design could have included support for passing the law or forother financial protection coverage strategies. Carefully estimating times required to complete transitions isessential to project design and implementation. The shift of the implementing unit into the MSD organizational structure took moretime than originally estimated and delayed project execution at the beginning of the project. Efforts to mitigate these risks toimplementation at project design could have allowed formore timely implementation. The implementation ofinformation systems requires effortsalong two separate fronts: in the collaborative design of the systems, and in thecreation of the demand for the information generated by the systems. In its support of the design and implementation of theinformation systems, the project made great efforts to ensure that systems were designed to collect data that was valuable tomanagers and policy makers by conducting careful analyses of needs. The project also made sure to build the demand for the use ofnewly available data by conducting manager and decision-maker trainingworkshops.This ICRR highlights an additional lesson in terms ofassessingattribution:A project designed tocoordinatewithother governmentprograms with similar goals canenhance efficiencyby minimizingduplication of efforts.If the collaboratingprograms do notdesign their MEarrangements to specifically collect information that will enable them to separate out their respective contributions,however,such collaborationlimitsboth programsability to attribute any achievement of developmentoutcomes to the activities of eitherprogram.ME design that supports attribution of collaborating partner programsis possible, but a framework must be in place as collaboration begins, and must be supported by adequate data collection andanalysis. This APL III was originally designed to complement the Zero Malnutrition and Social Protection programs, both aiming toincrease demand for health care services and reduce malnutrition. Without a clear counterfactual, it is difficult to disentangleeffects of this APL project and other program effects.
P101206 | Expanding Access to Reduce Health Inequities Project (APL III)--Former Health Sector Reform - Third Phase (APL III) | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2008 | 2016 | 2018 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/748801532017664145/text/126362-PPAR-P060392-P074212-P101206-PUBLIC.txt | http://documents.worldbank.org/curated/en/748801532017664145/pdf/126362-PPAR-P060392-P074212-P101206-PUBLIC.pdf | Lessons 5.10 The experience of the APL program indicates the following lessons\. 5.11 The definition of a common results framework is useful to align the efforts of different government levels. The M&E design of APL I was innovative in that it strategically defined a common set of indicators as APL phase triggers, the local management and accountability tool (that is, performance agreements), and KPIs. Although some of the indicators were initially ambiguous and later modified, this focus on common results helped different stakeholders (central government, local governments, World Bank staff) to concentrate efforts on the achievement of these selected areas. There is a risk though of not tracking lower-level indicators measuring progress in activities and outputs. 5.12 A robust results-based approach needs to define a clear mechanism of rewards/sanctions to function well. Otherwise it risks turning into a mere monitoring tool that could lead to perverse incentives. Performance agreements did not have a standard methodology for setting targets at the local level, altering the judgment of performance based on the stringency of targets set. In addition, the approach did not have a clear mechanism for rewards to ensure compliance of local governments with the targets and to sustain the level of effort and interest. Rather, it seemed to be used to monitor results sporadically and improve the capacities of local governments lagging behind through investment subprojects. While a traditional results-based approach (financially) rewards the achievement of results, these performance agreements seemed to act as a tool to flag allocation of funds to those local governments struggling to achieve targets. 5.13 Project design coordinating efforts with parallel programs that have similar goals has a great potential for efficiency, but it raises methodological concerns about the attribution of outcomes. In APL III demand components were sought to be articulated through the Zero Malnutrition and Bono Juana Azurduy programs, aimed at reducing malnutrition and increasing demand for health care services. While coordination with other government programs that have similar goals can enhance efficiency by exploiting synergies and minimizing duplication of effort, it creates challenges for the attribution of results to the activities of either program. Initial piloting and evaluation intentions were not possible because the conditional cash transfer program was directly launched at the national level, which limited the development of specific M&E arrangements to disentangle program effects. 5.14 While continued focus on quality objectives is certainly commendable, it needs to be accompanied by more robust outcome measures to prove quality enhancements. The prevalence of structural aspects of quality reflects the low baseline of health facilities' infrastructure conditions as well as the high costs of collecting process quality indicators. It is also consistent with the type of first-generation reforms APL I and II aimed to address (such as expansion of service coverage by ensuring financing for vaccines and public health insurance and infrastructure). APL III aimed at reducing the occurrence of risk factors affecting maternal and child health, but it did not identify appropriate measures, especially on process quality, and instead used complete prenatal coverage and user satisfaction surveys, and other narrow aspect of structural quality. 5.15 Programmatic approaches are suitable where sector knowledge is strong, program objectives are long-term and clear, and country ownership is established. The choice of an APL instrument for the overall program was appropriate because the government's goals to reduce infant and child mortality were well articulated and would take an extended time, requiring consistency and deepening of reforms over several phases. Strong government ownership of these goals, and a vision for how to pursue them over time, further strengthened the case for an APL. Sufficiently robust triggers, moreover, ensured they did not become inappropriate over time, thus securing continuation of the APL phases. These are useful lessons for the new Multiphase Programmatic Approach. 5.16 Ambitious projects partially relying on a government promise to pass a reform law are likely to need a restructuring. Reallocation of project funds in response to ad hoc government requests may lessen the logic of the results chain and risk the M&E framework from providing sufficient evidence of project achievements. Building on the success of the previous phases, APL III designed activities based on the government's expectations to transform the health insurance system, which did not occur. The cancellation of related activities and the inclusion of less-aligned activities affected the M&E framework, which was ultimately insufficient to provide evidence of the project's achievements. Additional data outside the M&E frameworks had to be used by the end of the project. This example highlights the value of evidence-based policy and reform versus less-aligned changes. A reform process could benefit from articulating a learning agenda and process for fine tuning reforms based on evidence and lessons.
P101209 | Honduras Rural Competitiveness Project | Latin America and Caribbean | Honduras | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2008 | 2021 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099540006302242709/text/P101209043bd720df08ab20e961f8e3f71c.txt | http://documents.worldbank.org/curated/en/099540006302242709/pdf/P101209043bd720df08ab20e961f8e3f71c.pdf | The ICR presents six main lessons from this project (ICR, para. 78). The four most relevant lessons have been consolidated andfurther sharpened below. These lessons are based on project-specific implementation experience and conclusions, and which can beapplicable and contextualized to other projects in Honduras (as being done for COMRURAL I and II) and other countries which areconsidering a similar strategy.Lesson 1: Promotion of appropriate, profitable, sustainable and productivetechnologies, and associated prioritized and transparent public investments, combined with improved access to markets, providedfarmers with improved incentives for adoption and participation, and proved to be an effective strategy. The Projectpromoted adoption of profitable, sustainable production and processing practices (integrated pest management, drip irrigation,solar drying for coffee, etc.) and helped many beneficiaries acquire certifications that allowed them to access markets thatprovided price premiums for quality and reliability of their increased production and marketable surpluses. The project alsostrengthened farmer-based organizational capacity and scale, which contributed to enhanced farmer bargaining power, all ofwhich contributed to higher productivity and production sales.Lesson 2: Given the inherent risksin lending to the agricultural sector, an integrated package of prioritized public investments and supporting measures can increaseconfidence of PFIs and private capital mobilization, and lead to sustainable financing relationships with rural producers.The integrated approach reduced risks, increased bankability of business plans implemented by the beneficiaries, and contributed tosustainableincreased value of production and marketed surpluses, which can be scaled-up in Honduras and customized in othercountries.Lesson 3: A strong monitoring and evaluation (ME) system is an essential tool totrack, enhance and sustain project performance and sustainable results, especially involving a project that isserving as a model for both within and beyond Honduras. Moreover, gathering timely baseline data and more disaggregated data onrelevant key indicators can generate further insights into the precise nature and scope of project benefits, including theeffective inclusion of vulnerable target groups.Lesson 4: Identifying, tracking and implementing relevant factorswhich foster the active inclusion of vulnerable groups should be incorporated into project design and objectives. Projectdesign should explicitly address factors that prevent vulnerable communities from engagement in project activities. While COMRURALsuccessfully reached large numbers of women and Indigenous Peoples with support that closed gaps in access for them, their overallparticipation in rural organizations grew at a below-average pace. A specific design feature that has been included in the new,ongoing COMRURAL projects, in addition to a dedicated window for subsistence farmers, is that additional points and priority areassigned during in the evaluation process for the approval of BPs to RPOs with a higher proportion of members from vulnerablegroups. Revitalizing the rural economy while modernizing the agri-food sector requires both improved technologies to boostproductivity and a range of specific measures to ensure greater inclusion and generation of direct and sustainable benefits fortraditionally marginalized groups.
P101211 | Support for the Second Phase of the Expansion of the Program of Conditional Transfers-Familias en Acción Project | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2009 | 2012 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/841871475098388567/text/000020051-20140625224850.txt | http://documents.worldbank.org/curated/en/841871475098388567/pdf/000020051-20140625224850.pdf | Lessons 1 and 2 come from the ICR, lesson 3 comes from IEG.1. Integration of different data sources is crucial to fully assess impacts. The impacts of the program were derived from both an impact evaluation in large cities, which was meant to test the effects of alternative incentive structures, and the monitoring information system. The use of administrative data for the targeting instrument (SISBEN) at two points in time allowed the evaluators to calculate the impact for the whole group of beneficiaries and also to supplement the baseline and endline datasets in the large cities, when it became evident that the insufficient sample size of the large cities impact evaluation could not allow the estimation of some of the impacts. Moreover, the data from the monitoring information system were essential to assess progress in program quality and process outcomes. The ICR stresses that using administrative data is also cost effective (ICR, p. 21).2. Good public communication of program rules is important. Many beneficiaries of the transfer in large cities did not understand the benefit structure that was being tested by the impact evaluation, even two years into implementation. In addition the empowerment of indigenous assemblies was key to ensure proper information and outreach to indigenous people. 3. Rapid expansion of a program comes at a cost and needs to be accompanied by extra measures to ensure that quality of the program is maintained. The rapid expansion of the program by more than 60% in one year (2.7 million household were reached at the end of 2009 from 1.7 million at the end of 2008) caused stress to the program and delayed to some extent the progress made on some quality improvements. The impact evaluation in large cities had to be adjusted and the project extended by one year. Moreover, this expansion delayed coordination and integration between Familias and Juntos, which was a very relevant political goal.
P101213 | Agriculture and Rural Development Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2007 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/727581491494106697/text/ICRR-Disclosable-P101213-04-06-2017-1491494082817.txt | http://documents.worldbank.org/curated/en/727581491494106697/pdf/ICRR-Disclosable-P101213-04-06-2017-1491494082817.pdf | The ICR included four lessons, three were project specific and only one was of general applicability. That generallessonistherefore emphasized here with some editing: Having a realistic development objectiveanddesign areimportant fora projects successfulimplementation. When a project has avery broad objective and inadequate design thatare beyond the reasonable purview of the project, full achievement of the PDOsbecomes very difficult. It is, therefore, very important to take advantage of the Mid-Term Review or a restructuring to help guidepotential re-formulation of the PDO and its design.
P101214 | Real Estate Cadastre and Registration | Europe and Central Asia | Kosovo | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2010 | 2018 | 2019 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/316091561730009466/text/Kosovo-REAL-ESTATE-CADASTRE.txt | http://documents.worldbank.org/curated/en/316091561730009466/pdf/Kosovo-REAL-ESTATE-CADASTRE.pdf | Twolessons were selected from the ICR, with some adaptation of the language: Bank-financedprojectsbenefit fromtargeting the gender sensitization ofan implementing agency, as this helps to mainstreamgender into regular agency operations and ensures the drive for sustainability of gender-related outcomes beyond the life ofBank-financed projects. The gender focus can include public outreach activities to raise womens awareness of theirproperty rights and the importance of including their name as co-owners. These activities need to be client designed andimplemented to improve the achievement of the Banks corporate commitments. To avoid delays ineffectiveness it is important to explain the projects benefits to key officials in charge of projectratification. This requires a proactive awareness attitude which equally engage a diversity of ruling parties andopposition to generate widespread support for an important reform agenda.IEG-definedlessons Robust PDOindicators are the ones that are directly affected by project activities or outcomes,and relatively shielded from market fluctuations. Under this project, the shock caused by the global financial crisis and thesubsequent dropping of indicators linked to the real estate market exposes an important issue in the design ofindicators. An economic analysis of Land Administration projects requires well-reasoned and realistic estimates ofexpected benefits. These estimates should be justified using empirical historical performance data under similarsettings as the project being appraised.
P101216 | Agriculture Strengthening and Accession Project | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2007 | 2013 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/312671474593744524/text/000020051-20140626115946.txt | http://documents.worldbank.org/curated/en/312671474593744524/pdf/000020051-20140626115946.pdf | The ICR offers a number of lessons of which the following are the most important (with some reformulation of language):1. World Bank partnering with the EU can be highly beneficial and strong aid coordination across a common objective helps meet the EU accession agenda in the agricultural sector. The partnership approach applied here has a potential to be replicated. 2. Institutional development of irrigation management is a long and continuous process, continued Government commitment is essential. The period to make irrigation institutions fully demand-driven and financially sustainable may take many years and reach beyond a single project calling for sustained commitment. 3. If the objective is not limited to building systems and institutions for EU accession but also includes a focus on better absorption of pre-accession funds, then additional components would be necessary. The project experience suggests that measures to help farmers with pre-accession fund applications as well as improved access to finance for co-funding of investments are essential in order to increase EU pre-accession fund absorption.
P101218 | Honduras Education Quality, Governance, & Institutional Strengthening | Latin America and Caribbean | Honduras | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2008 | 2013 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/307261475092747877/text/000020051-20140626123555.txt | http://documents.worldbank.org/curated/en/307261475092747877/pdf/000020051-20140626123555.pdf | Lessons from the ICR (p. 21), adapted by IEG: â€¢ Withdrawal conditions with no direct link to project activities or outputs should be avoided in investment lending operations. Policy-related conditions are better suited to a complementary DPL operation.â€¢ Project design in countries with known capacity constraints should remain simple and focused, with fewer activities that are more clearly tied to fewer and narrower objectives and outcomes.â€¢ Implementation arrangements for complicated projects with associated high risks should include considerations for: (i) all ministry and PMU staff likely to be involved in project implementation; and (ii) modalities for project supervision by the Bank. Lessons from IEG: â€¢ An inadequate results framework and changing performance indicators make an effective assessment of project achievement difficult.â€¢ Discussions with the Task Team confirmed the importance of a sector champion with the political will and power to make governance and accountability reforms happen.
P101229 | Sixth Poverty Reduction Support Credit (PRSC6) | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2009 | 2010 | 2012 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/714031474571401951/text/000020051-20140625065432.txt | http://documents.worldbank.org/curated/en/714031474571401951/pdf/000020051-20140625065432.pdf | There are four important lessons:1. Realistic monitoring frameworks are important tools for effective reform, important for government, but also for the Bank and other donors. MKUKUTA, well intentioned though it was, clearly provided an overly optimistic and ambitious framework for monitoring and evaluation. As the Bank modified its approach to monitoring over this PRSC series, it produced a more meaningful framework. Still, the use of WBI governance indicators is not ideal, as they are measures relative to other countries, whether or not such countries are comparable to Tanzania. Poverty head counts were (and are) only available with a considerable lag, and so cannot reflect current progress, even though having the desirable property of broadly capturing progress, or lack of it. 2. There are drawbacks to long term commitments of budget support which need to be carefully weighed against the benefits, in terms of government efficiency, of being able to count on budget resources over time. In this case, it appears that not only was there a downward trend in performance, but that donor support may have also contributed to what appears to be a sustainability issue -- the high level of government expenditures relative to GDP, and, within that, the high level of wages. 3. Stationing key staff in country offices is important in enabling the Bank to provide good advice, even if that does not always translate into results. This good practice should be continued. 4. Far-reaching reform programs need to be carefully tailored to human capacity constraints. In this case, the sophisticated process supporting implementation outpaced the human resources available, especially on the government side, which was also limited by availability of dependable office communications (such as email). For the future, the Bank should seek to support reform programs more realistically grounded in capacity.
P101229 | Sixth Poverty Reduction Support Credit (PRSC6) | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2009 | 2010 | 2013 | PPAR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/542381468133184866/text/781880PPAR0Tan00Box377382B00PUBLIC0.txt | http://documents.worldbank.org/curated/en/542381468133184866/pdf/781880PPAR0Tan00Box377382B00PUBLIC0.pdf | 4. Lessons 4.1 The implementation of PRSCs 1-8 spanned nearly a decade during a period of sustained macroeconomic stability and fast economic growth, offering lessons both for Tanzania and other countries with similar development challenges. 4.2 Lesson 1\. Direct and sustained focus and clarity of vision over the entire course of implementation of PRSC programs that cover many years is required to facilitate lasting reforms particularly with regard to public sector governance. There is a significant risk of backsliding when attention is shifted to other priorities. Yet joint budget support is a messy attempt to reach a common understanding, always subject to change, with a wide range of domestic stakeholders and international development partners. In Tanzania, intense dialogue and very high government commitment led to early successes in improving public financial management and budget execution in the first PRSC series. But some achievements stagnated or were reversed in the second series, when attention was diluted to include a broad range of sectoral reforms and other aspects of governance. 4.3 Lesson 2\. PRSCs can make little progress without a foundation of trust between the Bank and the government, and among development partners at the institutional and individual levels. Without sufficient trust, negotiated and agreed-upon triggers can quickly be transformed into more heavy handed conditions, whereby the level of future support is determined by strict adherence to pre-identified policy changes. In these circumstances, a scaled-back operation, more tightly focused around areas of agreement might gain more traction than one used as an enforcement mechanism for previously agree reforms that no longer have political backing. 4.4 Lesson 3\. PRSC programs risk becoming irrelevant if the design, scale, and scope are not adjusted as conditions change. The advance expectation that such changes will occur may smooth the transition should events warrant a scaling back of the program. Circumstances changed substantially during the second PRSC series in Tanzania\. reform champions in government and among development partners moved on; the presumption that sustained growth of 6-8 percent would lead to significant poverty reduction proved false; a new President was elected; and the country was affected by higher food and fuel prices and by the global financial crisis. The mechanisms for dialogue also need to evolve so that the program can continue to support and influence policy decisions at the highest strategic level. To avoid misunderstanding, the Bank and government could plan in advance to recalibrate the program at a set point during implementation. 4.5 Lesson 4\. The lack of well-defined and realistic objectives and a fully developed results framework makes adjustment to changing circumstances difficult. A results framework that clearly explains how policy actions are expected to lead to desired outcomes, in light of the support provided through investment lending and by other development partners, can provide a results-focused discipline to the program, improving selectivity in the process. 4.6 Lesson 5\. Regular reporting on key outcome indicators is essential so that data can drive adjustments to the PRSC program. Adequate investment in statistical capacity and the creation of a robust monitoring and evaluation system that addresses each step of the results chain to identify the key drivers of success or failure, while remaining focused on a few key outcome indicators, can help guide long PRSC series as circumstances evolve. Policy makers need to be aware of trends in outcomes in order to adjust the program accordingly. In Tanzania, reliable data on, for example, income poverty were available only once every seven years or so. Interim poverty simulations suggested significant poverty reduction as a result of sustained growth, but these projections turned out to be inaccurate. Household surveys every 3-4 years could provide much more timely and meaningful data to policymakers to allow for evidence-based adjustments during implementation. 4.7 Lesson 6\. Transitioning to the use of PRSCs as the primary instrument for resource transfer is only likely to be successful in rare circumstances, when strong central ministries can fully pursue a sector-inclusive dialogue representing the perspectives of key players throughout government. PRSCs themselves have very limited leverage in sector ministries, and the number and specificity of sector-specific triggers are necessarily curtailed when many sectors are covered. 4.8 Lesson 7\. Elevating to the national dialogue sector-specific structural reforms that stalled at the sector level does not guarantee their implementation. Even as the depth of sector exposure and experience permitted the sector content to be brought opportunistically into the PRSC, there is no evidence that this accelerated sector reforms or achieved greater cross-cutting momentum. Indeed, many of the same obstacles can prevent these reforms from taking hold, as was the case in energy, transport, agriculture, and water. Moreover, policy reforms committed to by central ministries are likely to be seen by implementing agencies, less vested in the PRSC program, as externally-imposed conditions, and subverted rather than adopted.
P101230 | Tanzania Seventh Poverty Reduction Support Credit | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2009 | 2011 | 2012 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/714031474571401951/text/000020051-20140625065432.txt | http://documents.worldbank.org/curated/en/714031474571401951/pdf/000020051-20140625065432.pdf | There are four important lessons:1. Realistic monitoring frameworks are important tools for effective reform, important for government, but also for the Bank and other donors. MKUKUTA, well intentioned though it was, clearly provided an overly optimistic and ambitious framework for monitoring and evaluation. As the Bank modified its approach to monitoring over this PRSC series, it produced a more meaningful framework. Still, the use of WBI governance indicators is not ideal, as they are measures relative to other countries, whether or not such countries are comparable to Tanzania. Poverty head counts were (and are) only available with a considerable lag, and so cannot reflect current progress, even though having the desirable property of broadly capturing progress, or lack of it. 2. There are drawbacks to long term commitments of budget support which need to be carefully weighed against the benefits, in terms of government efficiency, of being able to count on budget resources over time. In this case, it appears that not only was there a downward trend in performance, but that donor support may have also contributed to what appears to be a sustainability issue -- the high level of government expenditures relative to GDP, and, within that, the high level of wages. 3. Stationing key staff in country offices is important in enabling the Bank to provide good advice, even if that does not always translate into results. This good practice should be continued. 4. Far-reaching reform programs need to be carefully tailored to human capacity constraints. In this case, the sophisticated process supporting implementation outpaced the human resources available, especially on the government side, which was also limited by availability of dependable office communications (such as email). For the future, the Bank should seek to support reform programs more realistically grounded in capacity.
P101230 | Tanzania Seventh Poverty Reduction Support Credit | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2009 | 2011 | 2013 | PPAR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/542381468133184866/text/781880PPAR0Tan00Box377382B00PUBLIC0.txt | http://documents.worldbank.org/curated/en/542381468133184866/pdf/781880PPAR0Tan00Box377382B00PUBLIC0.pdf | 4. Lessons 4.1 The implementation of PRSCs 1-8 spanned nearly a decade during a period of sustained macroeconomic stability and fast economic growth, offering lessons both for Tanzania and other countries with similar development challenges. 4.2 Lesson 1\. Direct and sustained focus and clarity of vision over the entire course of implementation of PRSC programs that cover many years is required to facilitate lasting reforms particularly with regard to public sector governance. There is a significant risk of backsliding when attention is shifted to other priorities. Yet joint budget support is a messy attempt to reach a common understanding, always subject to change, with a wide range of domestic stakeholders and international development partners. In Tanzania, intense dialogue and very high government commitment led to early successes in improving public financial management and budget execution in the first PRSC series. But some achievements stagnated or were reversed in the second series, when attention was diluted to include a broad range of sectoral reforms and other aspects of governance. 4.3 Lesson 2\. PRSCs can make little progress without a foundation of trust between the Bank and the government, and among development partners at the institutional and individual levels. Without sufficient trust, negotiated and agreed-upon triggers can quickly be transformed into more heavy handed conditions, whereby the level of future support is determined by strict adherence to pre-identified policy changes. In these circumstances, a scaled-back operation, more tightly focused around areas of agreement might gain more traction than one used as an enforcement mechanism for previously agree reforms that no longer have political backing. 4.4 Lesson 3\. PRSC programs risk becoming irrelevant if the design, scale, and scope are not adjusted as conditions change. The advance expectation that such changes will occur may smooth the transition should events warrant a scaling back of the program. Circumstances changed substantially during the second PRSC series in Tanzania\. reform champions in government and among development partners moved on; the presumption that sustained growth of 6-8 percent would lead to significant poverty reduction proved false; a new President was elected; and the country was affected by higher food and fuel prices and by the global financial crisis. The mechanisms for dialogue also need to evolve so that the program can continue to support and influence policy decisions at the highest strategic level. To avoid misunderstanding, the Bank and government could plan in advance to recalibrate the program at a set point during implementation. 4.5 Lesson 4\. The lack of well-defined and realistic objectives and a fully developed results framework makes adjustment to changing circumstances difficult. A results framework that clearly explains how policy actions are expected to lead to desired outcomes, in light of the support provided through investment lending and by other development partners, can provide a results-focused discipline to the program, improving selectivity in the process. 4.6 Lesson 5\. Regular reporting on key outcome indicators is essential so that data can drive adjustments to the PRSC program. Adequate investment in statistical capacity and the creation of a robust monitoring and evaluation system that addresses each step of the results chain to identify the key drivers of success or failure, while remaining focused on a few key outcome indicators, can help guide long PRSC series as circumstances evolve. Policy makers need to be aware of trends in outcomes in order to adjust the program accordingly. In Tanzania, reliable data on, for example, income poverty were available only once every seven years or so. Interim poverty simulations suggested significant poverty reduction as a result of sustained growth, but these projections turned out to be inaccurate. Household surveys every 3-4 years could provide much more timely and meaningful data to policymakers to allow for evidence-based adjustments during implementation. 4.7 Lesson 6\. Transitioning to the use of PRSCs as the primary instrument for resource transfer is only likely to be successful in rare circumstances, when strong central ministries can fully pursue a sector-inclusive dialogue representing the perspectives of key players throughout government. PRSCs themselves have very limited leverage in sector ministries, and the number and specificity of sector-specific triggers are necessarily curtailed when many sectors are covered. 4.8 Lesson 7\. Elevating to the national dialogue sector-specific structural reforms that stalled at the sector level does not guarantee their implementation. Even as the depth of sector exposure and experience permitted the sector content to be brought opportunistically into the PRSC, there is no evidence that this accelerated sector reforms or achieved greater cross-cutting momentum. Indeed, many of the same obstacles can prevent these reforms from taking hold, as was the case in energy, transport, agriculture, and water. Moreover, policy reforms committed to by central ministries are likely to be seen by implementing agencies, less vested in the PRSC program, as externally-imposed conditions, and subverted rather than adopted.
P101231 | Seventh Poverty Reduction Support Credit (PRSC7) | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2008 | 2010 | 2011 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/862971474491194701/text/000020051-20140624165839.txt | http://documents.worldbank.org/curated/en/862971474491194701/pdf/000020051-20140624165839.pdf | The lessons for the overall series are presented in the ICRR for "Republic of Uganda: Poverty Reduction Support Credits (PRSCs) 5, 6 and 7" (P101231).
P101231 | Seventh Poverty Reduction Support Credit (PRSC7) | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2008 | 2010 | 2015 | PPAR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/942871468188377758/text/Uganda-Fifth-Ninth-Poverty-Reduction-Support-Credit-Project.txt | http://documents.worldbank.org/curated/en/942871468188377758/pdf/96202-PPAR-P090881-P090219-P101231-P101232-P097325-Box385353B-OUO-9-IDA-SecM2015-0150.pdf | Lessons Several lessons emerge from this assessment of PRSC5-7 series. They relate to the design, implementation, and proactivity and learning. Â· Lack of clear, concrete objectives impedes both implementation and evaluation of DPOs. General statements of broad support of government policies (as in PRSC5- 7) are best avoided. Â· Design of DPOs and implementation can be adversely affected by lack of focus and selectivity in policy areas. Â· Inadequate accounting of political economy factors in the design of major reforms can adversely affect the design, implementation and outcomes of DPOs. Lack of focus on domestic revenue mobilization is a prime example. Â· Pressures to extend budget support within the broader, coordinated donor support framework without hard conditionality to raise domestic revenues can undermine incentives for domestic revenue mobilization. This, in turn, can undercut macroeconomic adjustment needed for sustainable fiscal policy as well as the adequacy of funding for basic services. Â· Implementation and evaluation are frequently undermined when objectives are not tightly linked to prior actions and there is no measurable and relevant results framework, when outcome indicators are ambiguous, and when targets do not incorporate an explicit and convincing theory of change.
P101232 | Uganda Eighth Poverty Reduction Support Credit | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2012 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/659111475118027824/text/000012394-20150312070957.txt | http://documents.worldbank.org/curated/en/659111475118027824/pdf/000012394-20150312070957.pdf | IEG draws the following lessons from the review of the program.The experience of PRSCs 8 and 9 shows that paying more attention at what the program is trying to achieve is likely to lead to a more careful and realistic formulation of the results framework, making it easier to monitor and measure results. In countries known for their weak governance, such as Uganda, programs of budget support need to take into consideration issues of corruption and accountability in their design to improve their performance and their execution. The experience of Uganda indicates that the government was ready to deal with issues of corruption when the problems surfaced; it also indicates that dropping actions aimed at confronting corruption, as it happened in PRSC 9, may send conflicting signals about the Bankâ€™s stand on it, thereby weakening the governmentâ€™s commitment to carry out the actions agreed to.
P101232 | Uganda Eighth Poverty Reduction Support Credit | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2012 | 2015 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/942871468188377758/text/Uganda-Fifth-Ninth-Poverty-Reduction-Support-Credit-Project.txt | http://documents.worldbank.org/curated/en/942871468188377758/pdf/96202-PPAR-P090881-P090219-P101231-P101232-P097325-Box385353B-OUO-9-IDA-SecM2015-0150.pdf | Lessons Several lessons emerge from this assessment of PRSC5-7 series. They relate to the design, implementation, and proactivity and learning. Â· Lack of clear, concrete objectives impedes both implementation and evaluation of DPOs. General statements of broad support of government policies (as in PRSC5- 7) are best avoided. Â· Design of DPOs and implementation can be adversely affected by lack of focus and selectivity in policy areas. Â· Inadequate accounting of political economy factors in the design of major reforms can adversely affect the design, implementation and outcomes of DPOs. Lack of focus on domestic revenue mobilization is a prime example. Â· Pressures to extend budget support within the broader, coordinated donor support framework without hard conditionality to raise domestic revenues can undermine incentives for domestic revenue mobilization. This, in turn, can undercut macroeconomic adjustment needed for sustainable fiscal policy as well as the adequacy of funding for basic services. Â· Implementation and evaluation are frequently undermined when objectives are not tightly linked to prior actions and there is no measurable and relevant results framework, when outcome indicators are ambiguous, and when targets do not incorporate an explicit and convincing theory of change.
P101243 | Punjab Education Development Policy Credit - IV | South Asia | Pakistan | Blend | Non-FCS | Human Development | Education | IDA | DPF | 2007 | 2008 | 2011 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/258911475093907050/text/000020051-20140620074945.txt | http://documents.worldbank.org/curated/en/258911475093907050/pdf/000020051-20140620074945.pdf | Strong, broad, and deep Bank engagement with government officials (across many sectors and down to the operational level) can help to keep momentum and commitment to a financial support program even when there is a change in the political leadership of the client. In large federated countries such as Pakistan, where sector policies and implementation mechanisms are managed at the provincial level, and where there are wide disparities across provinces, it makes sense to develop sector support programs at the Provincial level. Development Policy Credits, which have been popular in Pakistan and other locations for their quick disbursement features, are often, because of their short spans, not well situated to influence medium term performance outcomes such as improved learning outcomes and changes in management behavior. In locations like Punjab Province that are mobilizing to accelerate progress towards Education for All goals, it is important to simultaneously address the problems of access and quality. From recent history in the Province it is clear that if increased enrollments outstrip the capacity of the government to create or maintain quality (e.g., by allowing student teacher ratios to climb too high), students lose their motivation to attend school, reversing earlier enrollment gains. Matching enrollment gains with improvements in quality can help to reduce student attrition rates, leading to higher levels of educational attainment which itself sends messages that school is worthwhile.
P101258 | Hubei Yiba Highway | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2009 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/499441486688810372/text/ICRR-Disclosable-P101258-02-09-2017-1486688803712.txt | http://documents.worldbank.org/curated/en/499441486688810372/pdf/ICRR-Disclosable-P101258-02-09-2017-1486688803712.pdf | The ICR draws the following four lessons from the experience of implementing this project.(1)Forexpressway projects in challenging topography, sufficient time should be allowed for investigations and design.Inthe case of this project, the expressway contractors experienceddifferent geological conditions during construction comparedto the conditionsassumed during project design.This necessitated additional geological investigation and increasedconstruction costs.A combination of measures taken during project preparation, including sufficient time for investigations,realistic construction timeline and preparation of back-up plans could have helpedin preventing cost overruns duringimplementation.(2) Successful procurement of large scale civil works contracts requires good procurement planning,packaging, quality review and sufficient advance training to the implementing agency. The experience with this projectshowed that it is essential to avoid procuring a large number of packages within a short time period and further the Bank shouldcarefully monitor the procurement capacity prior to large procurements being undertaken and ensure that appropriate training isprovided to the relevant staff.(3). Innovativemeasures can be helpful in enhancing environmentalmanagement focus. The project has demonstrated that establishing a comprehensive management framework and a bundleof measures can help in minimizing adverse environmental impacts and thereby aid in enhancing environmental compliance inexpressway projects. The innovative measures includedchoosing the alignment and adopting an engineering design tominimize environmental impact, involving independent environmental supervision to monitor and evaluate compliance, and creatingincentives for all parties to ensure good environmental management (such as launching a Green Award Competition among contractorsand supervision engineers and presentation by finalists on good examples of environmental management measures to increase theawareness of the general public).(4) Successful resettlement activities can be helpful in contributingtoprosperity for project affected people. In the case of this project, project resettlement activities werecarried out with the aim of minimizing land acquisition because villagers rely on farming and shortage of farmland in themountainous region. In some areas the alignment was modified during design stage to protect farmland. The project also provideddisplaced families significantly improved local living conditons through rural road upgrading, new land reclamation, electricitysupply, sanitation improvements, drinking water improvements, pension insurance, career development and housingimprovements.
P101279 | Solid Waste Management Program Project | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2010 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/111071497021274664/text/ICRR-Disclosable-P101279-06-09-2017-1497021264175.txt | http://documents.worldbank.org/curated/en/111071497021274664/pdf/ICRR-Disclosable-P101279-06-09-2017-1497021264175.pdf | The ICR included seven lessons, several of which this Review adapted. Some lessons were added that appear relevant given thesignificant design, implementation and funding issues encountered by the project.1. Global, andregional lessons learned from the other operations in the sector are not always suitable for replication due to specific country,sector conditions and priorities. The original design of this project adopted global and regional lessons learned (ICRpp9-11) and adopted similar institutional arrangements used in water and sanitation sector projects. However, as pointed out in theICR (p. 27), the latter projects, owing to their long record, higher visibility and established procedures, tended to relegatesolid waste investments to lower budget priority in the PDA budget structure. Restructuring highlighted the need to consider thesolid waste sector separately and adapt investment financing frameworks accordingly.2. A conducivelegal framework should be in place prior to project implementation. Prior to effectiveness, the Bank should understand thelegal framework and be prepared to offer workable alternatives in the event that legal issues should arise duringimplementation. Colombia has a highly regulated public sector with public audit and control functions established in theconstitution and national regulations governing government activities at all levels including basic services. (ICR p1).A) Laws related to subnationalaccounts. In 2011, the Bank requested reimbursement of US$1.07 million of the loan from the Special Account due to lack ofexecution, and discussed the options of closure of the project and partial cancelation. But it was determined by Colombianauthorities that this would have raised legal barriers due to the Constitutional provision that requires money to be used fordesignated purposes in designated Departments). In this project an alternative solution was developed entailing an increase to theSpecial Account and an agreement to work toward project restructuring rather than closure (ICR,p.13).B) Legal barriers related to social inclusion. The Government did not prioritize the social waste pickers astheir activities were not supported by the prevailing law and there was strong opposition to changing the law. A subsequent SupremeCourt ruling resulted in waste pickers being designated as within the public service. Near project closure, the Bank used itsown funds to provide technical assistance leading to incorporation on a pilot basis of informal recyclers in two sites of thesystem. (Team Interview).3. The importance of committing funds in advance of project implementationto help obtain stakeholder consensus. The regional landfill operations involved multiple municipalities and requiredextensive negotiation and consensus building across municipal parties which spanned a period of municipal elections and transitionof administrations. Political consensus could not be obtained until funding was assured. (Teaminterview).4. The role and importance of performance targets to improve accountability and improveproject implementation. Project execution did not advance throughout 2010 and for a significant portion of 2011.The GoCand Bank agreed on a set of performance targets, which played a catalyst role in incentivizing the MVCDT to take action to speed upthe process. (ICR p13).5. Importance of closer coordination and continuous oversight by the Bankand Borrower to identify and mitigate risks in a timely manner. The project faced multiple risks at different levels, someof which were identified and mitigated better than others. Some risks pertaining to budget and staff allocations at higher levelswere perceived but also seen as being of limited scope for influence by the Bank or implementing agency. There were two key risksthat were not identified at appraisal. The high staff turnover at Departmental-level management entities for the PDA (GestoresDepartmentales) was not considered in the risk analysis and in consequence, the mitigation measures regarding capacity buildingwere not effective. The risk of using the subnational account structure and a ring-fenced project sub-account within a singlenational level (Patrimonio Autonomo) structure was not adequately identified and addressed. (ICR p11)6. Best practices related to technical standards merit dissemination. The Projecthelped increase technical standards within the sector by providing examples of good practice including examples of concessionagreements, operational contracts, public management of small landfills (Quinchia) and the Colombian tariff system (as noted inSection 10d above; also see references in ICR, annex 7). These examples were re-disseminated in Colombia and globally. (ICR p 24,footnote 59)
P101289 | GZ-Gaza Water Supply & Sewage System Improvement | Middle East and North Africa | West Bank and Gaza |  | FCS | Sustainable Development | Water | SPF | IPF | 2013 | 2018 | 2019 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/144301535682594540/text/West-Bank-and-Gaza-Water-Supply-Sewage-System-Improvement.txt | http://documents.worldbank.org/curated/en/144301535682594540/pdf/West-Bank-and-Gaza-Water-Supply-Sewage-System-Improvement.pdf | The ICRlists five lessonsrelated toproject implementation (ref. ICR,Paras. 76-80). As presented,all five are generic and they draw unevenly on specific experience from within the project itself. That being said, theyprovide some valid observations that are applicable to projects in fragile or conflict-affected states. Theseinclude: In fragile and conflict-affected states, effective institutions and qualified, high-performingstaff are limited commodities, andthey can be quickly over-burdenedwith multiple projects anddonor-mandatedrules. In the case of the CMWU and the PWA, the complex financial management and procurementrequirements putin place due to the political situation in Gaza led to high risks of conflicts of interest and overlapping responsibilities amongthe individuals and institutions involved. Mitigating this risk required very careful oversight by the Banks supervisionteam that was compromised by travel restrictions on Bank staffthat were imposed due to the political situation inGaza.The lack of oversightcreated the conditions for the misprocurement that was identified in the final year ofthe project. In fragile and conflict-affected situations, capacity building, emergency preparedness, flexibility,and active engagement are imperative. The project wasplanned in a fragile setting with close attention to capacitybuilding of staff responsible for implementation of a projectin the aftermath ofan earlierconflict inGazaduring the period20082009. The capacity building and prior experience resulted in the CMWUspreparednessto respond quite quickly with a damage and needs assessment immediately following the 2014 conflict. Closemonitoring of the situation in Gaza was also required for the World Bank team working on the project to make surethe CMWU wasable to implement the project. Among other factors, thisnecessitated coordination with theGovernment ofIsraelto push for more easyentry of construction material to Gaza. This active engagementhas beennoted bythe client (ref. client ICR, 2018). Following the 2014 conflict, the flexibility and rapid response of both the Bank and theClient allowed forclose to real-time damageassessment, quick preparation and release of additional financing, and rapidrehabilitation and recovery of services. Close coordination with other donor partners from projectinception is key to success. The World Bank used two mechanisms to leverage and coordinatedonor partner financingfor this project - parallel financing from the IsDB, and the Bank-executed Partnership for Infrastructure Development Multi-DonorTrust Fund (MDTF). The MDTF allowed the World Bank to manage financial contributions from Croatia, Denmark, Finland, France,the Netherlands, Noway, Portugal, and Sweden for a broad array of infrastructure development initiatives in the West Bank andGaza. MDTFs have an uneven reputation globally, but in the case of this project specifically, and the West Bank and Gaza moregenerally, the MDTF has proven to be an effective mechanism to allow relatively rapid mobilization of resources for emergencies aswell as for coordinated infrastructure financing. The MDTF also streamlined transactions costs for the Palestinian Governmentand the donors by providing and common reporting framework. The principal reasons for the MDTFs effectiveness appear tohave beenabroad agreement on a World Bank-led development strategy among the bilateral donors, andclose andtransparent communications among the MDTF partners. It is understood that the strength of the donor partnership and the levelof World Bank oversight of the projectwere important factors in IsDB s decision to provide parallel co-financing for theproject.
P101296 | PDPL 3 | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2008 | 2009 | 2010 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/232441474483777029/text/000146597-20140619171508.txt | http://documents.worldbank.org/curated/en/232441474483777029/pdf/000146597-20140619171508.pdf | A prime lesson from this program is that exogenous forces, in this case the prospect of eventual EU accession, can play a dominant role in assuring government commitment to reforms.A second lesson is that continuity of champions for reform on the government side and continuity in Bank teams are essential for successful reform outcomes.
P101298 | Second Participatory Rural Investment | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2008 | 2014 | 2015 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/137591475788726797/text/000180307-20150409085056.txt | http://documents.worldbank.org/curated/en/137591475788726797/pdf/000180307-20150409085056.pdf | The following are the main lessons from the ICR (para 84 and Annex 5, pages 45 to 47):Regional development requires consensus building and takes time: This project has clearly demonstrated that territorial development is a long term process. The lesson learnt is that more emphasis needs to be placed on building consensus involving multiple stakeholders, and continuous capacity building in multiple disciplines and competencies to achieve the goals of territorial development.Strategic communication. Importance of strategic communication "to build consensus through raising public understanding and generating a well informed dialogue among stakeholders" (ICR, Annex 5, paragraph 17)Importance of a robust M&E framework: Experience from this project as well as earlier projects, such as the Participatory Rural Investment Project (which preceded the current project) points to the importance of a carefully designed M&E system. This is a lesson learned in many times in the past but needs repeating.This Review would add one lesson as follows:Importance of political economy in project design and reforming public sector institutions: This project highlights how critical political factors were in influencing the design of the project â€“ and the need for developing both quantitative and qualitative indicators for measuring the outcomes and impact of these factors in the achievement of project objectives.
P101301 | CO Third Sustainable Develop DPL III | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2009 | 2010 | 2011 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/582691474577800000/text/000020051-20140624165054.txt | http://documents.worldbank.org/curated/en/582691474577800000/pdf/000020051-20140624165054.pdf | The lessons arising from the overall series are presented in the ICRR for Third Programmatic Development Policy Loan for Sustainable Development (P0101301).
P101311 | GT DPL III | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2008 | 2009 | 2010 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/886711474652615126/text/000146597-20140619171119.txt | http://documents.worldbank.org/curated/en/886711474652615126/pdf/000146597-20140619171119.pdf | DPLs are more likely to achieve their objectives when they support the governmentâ€™s reform program and the time frame for the actions they support takes into account the political barriers to reform and the capacity of the government to carry out the reforms. Trying to push for reforms beyond what is politically feasible may endanger the potential success of the program.Broadly designed DPLs are more likely to be more effective when complemented with technical support from Bank-financed projects, projects financed by other International Financial Institutions, government programs, or local institutions. This technical support for the DPLs reviewed made it easier to achieve their development objectives in a timely manner and on a yearly schedule coordinated with the national budget.When the government owns the reform agenda and its process, the Bank can design the program to accommodate risky environments as that ownership permits targeting other areas for reform when some part of the program proves intractable. As reforms in PPP became difficult, the DPL program gave more weight to reforms in the financial sector, which needed the reforms and the government supported it.
P101321 | Fiscal and Debt Sustainability Development Policy Loan | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2009 | 2010 | 2012 | ICRR | >=100 million | Moderately Satisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/857641475080388749/text/000020051-20140624195454.txt | http://documents.worldbank.org/curated/en/857641475080388749/pdf/000020051-20140624195454.pdf | The ICR brings out three important lessons. First, timing of engagement for a DPL is important. When new government comes to power, it may request a support from the international financial institutions, including the Bank, to implement its reform program; this creates opportunity and momentum. Second, going with a stand-alone DPL when there is a difficult reform agenda ahead may not be a good decision as difficult reforms entail longer time frame than the one agreed to for a single tranche DPL. Third, investing efforts in strengthening coordination among government agencies will pay off and using technical assistance where needed helps build local capacity. One of the lessons which IEG has found out is that engaging the client's technical-level staff at the design stage would ease the risk coming from lack of capacity for implementation. The earlier the technical staff is involved in the dialogue, the easier is the coordination at the implementation stage.
P101322 | GD TAC | Latin America and Caribbean | Grenada | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2008 | 2012 | 2013 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/891851474560339459/text/000020051-20140625234823.txt | http://documents.worldbank.org/curated/en/891851474560339459/pdf/000020051-20140625234823.pdf | The ICR draws a number of valid and important lessons, including the importance of thorough technical preparation and cost estimation for projects with major IT components, and adopting a region wide approach where possible for small island states to share overhead costs efficiently.
P101324 | Minas Gerais Partnership II SWAP | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2008 | 2015 | 2016 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/714121467995077486/text/ICRR14890-P101324-Box394872B-PUBLIC.txt | http://documents.worldbank.org/curated/en/714121467995077486/pdf/ICRR14890-P101324-Box394872B-PUBLIC.pdf | There are four main lessons that can be drawn from the experience of this project:Â· Political commitment is key in a project that aims at supporting public resource management reform, where some degree of resistance from line ministries is to be expected. However support from top management at key Ministries is as crucial, particularly for institutional reform projects where the timeframe of implementation is usually very long. Political commitment can in fact vary with changes in government, but top management support ensures deeper rooting of reforms, and makes policy reversals more difficult.Â· Large multi-sector SWAPs with disbursement-linked indicators can offer stronger incentives for reform, ensuring that a wider array of policy changes can be implemented more smoothly and expeditiously, as noted in the ICR. Sector-specific SWAPs cannot address as well issues that require cooperation of different line ministries, some of which may not have any financial stake in the successful implementation of the reforms supported by the project.Â· Impact evaluations are key for learning and they should be properly timed. Impact evaluations in multi-sector SWAPs are particularly challenging, but should not be replaced by partial evaluation carried out immediately after the SWAP closes. The presence of a Technical Assistance component offers the opportunity for diversified completion schedules. The Bankâ€™s know-how can be as important as its ability to mobilize significant financial resources. The Government of Minas Gerais â€“ see ICR p. 22 - made clear that one of the key factors for choosing the Bank as the projectâ€™s financier was its ability to provide valuable inputs on the design of the program, and advice during its implementation.
P101335 | Fiscal Management and Competitiveness Development Policy Loan | Latin America and Caribbean | Peru | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2007 | 2008 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/208431474588004209/text/000020051-20140625224545.txt | http://documents.worldbank.org/curated/en/208431474588004209/pdf/000020051-20140625224545.pdf | The following lessons were identified by IEG's review and the ICR:Sweeping and sustained reforms (such as Peru's) require strong borrower ownership, a well-defined strategy, a highly consultative approach with country stakeholders, and a response donor consortium. Close coordination with international actors helped the Government to implement its comprehensive reform programs over several years.Sustaining fiscal and related public sector management reforms can be challenging. They place a premium on a 'building blocks' approach (for example, ensure aggregate fiscal policies are in place before undertaking expenditure re-prioritization). At the same time, it is important to be flexible in launching various reform initiatives when public institutions demonstrate a readiness to undertake and internalize institutional changes. An important lesson from Peruâ€™s experience is the need to design flexibility into the program in order to respond to new challenges over the course of reform implementation. Peru was successful in adjusting to the changes in global financial markets while remaining faithful to the objectives of its reform program. The Bank acted as a responsible partner and provided both financial resources and technical advice as needed to enable government to carry on its reform program. The use of the deferred drawdown option (DDO) can be helpful in managing the uncertainties for a volatile global environment. It enables countries to have additional insurance to weather the global financial crisis as the availability of financing from the World Bank increase market confidence and access. It also provides a stamp of approval of good housekeeping.
P101335 | Fiscal Management and Competitiveness Development Policy Loan | Latin America and Caribbean | Peru | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2007 | 2008 | 2017 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/725661488828202108/text/110742-PPAR-PUBLIC.txt | http://documents.worldbank.org/curated/en/725661488828202108/pdf/110742-PPAR-PUBLIC.pdf | 6. Lessons 6.1 The experience of this DPL series highlights what can be expected from the World Bank's engagement with a well-performing middle-income country. 6.2 A programmatic DPL series is a powerful tool for supporting long-term reforms. When a strong ownership of the client is demonstrated, a programmatic series of operations can offer the World Bank and its client win-win solutions. For the World Bank, a multiyear program of support gives it a chance to pursue an extended and coherent analytical agenda that may not be feasible in multiple one-off operations. To the client, the programmatic series offers a real-time opportunity to engage with the reforms (including both the costs and benefits) and to make adjustments along the way. In the case of Peru, the government was able to advance its investment climate agenda early on and to learn about the need for deeper and longer-term challenges of upgrading the quality its workforce and technologies. The successive rounds of ever deeper reforms on trade and competitiveness, while incomplete and not implemented with maximum efficacy, would have been difficult to accomplish through separate operations, which are invariably interrupted by changes of priorities and political mandates. 6.3 World Bank supervision of the implementation of these operations should cover all aspects of the program to take full advantage of the learning opportunities offered by a programmatic series. It should pay greater attention to not only emerging risks during the period of program implementation, but also factors affecting the sustainability of the achievements in long-term policy reforms. In the case of Peru, supervision of the core program seemingly focused only on a few development objectives and outcomes, and left unattended a complete pillar of reforms. No explanation is given for this in any of the Implementation Status and Results Reports. This may have resulted in issues not being identified and therefore not addressed, in time leading to less progress than expected or reversal of outcomes achieved. It limited the ability of the World Bank and other stakeholders to fully understand and learn from the experience of this DPL series. 6.4 Reforms move to subnational levels, though their implementation may pose a challenge depending on the framework of fiscal decentralization. Despite all the positive steps that the government had taken to enhance efficiency in the allocation of fiscal resources, there remains a pressing need to rationalize the fiduciary and regulatory norms and the multiplicity of control and auditing instances. According to MEF officials interviewed for this evaluation, these have proliferated and seem to be driving a wedge between the central and regional governments' capacity to focus on results rather than procedures, a central objective of results-based budget management. Another area of clear priority is for the government to continue to place strong emphasis at the central and subnational levels on a robust and rigorously appraised public investment program, and enhance its assistance to subnational governments in identifying, designing, and implementing their own programs, particularly in meeting infrastructure deficits (for example, roads, water and sanitation). To do so, the government should consider placing greater emphasis on subnational tax revenue collection and more efficient distribution of fiscal transfers to subnational governments, areas that proved somewhat lagging during the implementation period of this DPL series. 6.5 The application of the DDO in this DPL series illustrated the World Bank's willingness and ability to support Peru at the time of the global financial crisis. It also showed the extent to which the World Bank's new arsenal of financing instruments was able to respond to the needs of middle-income countries where both the volume and the timing of financing are important for risk management purposes. As a tool for risk management, the DDO gives clients access to a large line of credit that is affordable and fast disbursing, which helps maintain the confidence of investors and deter the resolve of speculators. As a debt management tool, the DDO offers the government an insurance policy on its debt-service and priority expenditure commitments without raising the level of external debt in advance. The discretion to call on the World Bank loan in the amount it needs when it needs to allows the government to optimize its debt structure. Moreover, by extending the loan period by up to six years and not requiring the client to draw down the loan, the DDO facilitates World Bank engagement with clients who do not need World Bank financing but value its formal and sustained support for their policy reforms. This is particularly valuable for engaging with well-performing middle-income countries. 6.6 Yet, the present example also illustrates possible tensions between the independent selection of IBRD-financing terms and the monitoring of the World Bank's development effectiveness. In this DPL series, the DDOs were requested and approved for risk management and crisis response purposes, but this important development objective, for which two large loans were granted in record time, was not tracked. Although monitoring of the macroeconomic framework and program implementation continued until closure of the DDOs, the depth of supervision was restricted to verification of preconditions for drawdown, as required for all DDOs, and did not try to capture the effectiveness of the loans for all their development objectives. This raises a question as to whether overall program design or continued periodic supervision should attempt to explicitly include indicators of risk management and crisis containment, to capture overall development impact of the DPL series. As this practice was repeated in multiple DPL series in Peru (and elsewhere), a substantial amount of World Bank resources is at stake. 6.7 A parallel issue is that with its longer drawdown period and its renewal feature, the implementation period of a DPL-DDO extends beyond the program implementation period of a normal DPL, which has consequences on the expected outcomes. This calls for attention especially in situations where the DDO was added to an ongoing DPL series, such as in Peru, which had a set of coherent, noncrisis-related policy objectives and a predetermined program period that did not (and could not) anticipate the additional crisisrelated objective and the extended program implementation period. The World Bank's DDO guidelines only require the monitoring of macroeconomic stability and the continued implementation of the program. Questions can thus be raised on whether there should be any more detailed supervision or scope for review of the overall program at the time of a DDO's approval and renewal or readjustment of the IBRD-financing terms with regard to repayment options as the country's debt management profile may have altered. Notwithstanding, the trade-off relative to the flexibility of the loan instrument is also important. These issues merit further debate.
P101336 | Strengthening Statistical Capacity and Informational Base for Evidence-Based Planning | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | IDA | IPF | 2011 | 2019 | 2020 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/463801593536904216/text/Bolivia-BO-Streng-Stat-Capacity-Inf-Based-Evi.txt | http://documents.worldbank.org/curated/en/463801593536904216/pdf/Bolivia-BO-Streng-Stat-Capacity-Inf-Based-Evi.pdf | The following are key lessons from the ICR: The PDO definition needs to be clear. The resultsframework under this project did not fully support the PDO. A clear objective is critical to translate to effectiveindicators to measure outcomes. Utilization of technology for data collection requires an assessment of theadaptability of local knowledge. As discussed in Section 5, field personnel required considerable training to ensureproper use of mobile devices to enable collection of quality data.
P101342 | MX Affordable Housing and Urban Poverty Reduction Development Policy Loan III | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2008 | 2008 | 2010 | ICRR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/533011474419595371/text/000146597-20140619151240.txt | http://documents.worldbank.org/curated/en/533011474419595371/pdf/000146597-20140619151240.pdf | From the ICR:There are trade offs between ambitious and comprehensive sectoral reform programs, which are potentially more beneficial, but inherently more risky, and more focused programs that address a limited range of issues for which both the potential benefits and risks are lower. The Programâ€™s relevance decreased when there was no coherent Government policy established in the sector where the Bank intervened, like urban development.A policy-based loan is not the best instrument to address technical issues requiring considerable investment and which are not backed by an adequate policy framework. Instead, a combination of policy and investment loans might have been more effective in meeting the Programâ€™s goals. Combining policy and investment loans at the same time, however, might have crowded out other important activities. Inefficiencies and redundancies were produced due to the involvement of too many institutions, which were often at odds with each other over policy issues. This was largely due to the large number of components and sectors under the umbrella of the Program. A more focused approach, as previously mentioned, could have reduced these inefficiencies and redundancies.The comprehensive nature of the Program required that adequate M however this was not done until preparation of the second operation was well advanced. HUTAL should have played a role in fixing the shortcomings of the Program and its implementing institutions in this area.The timing of HUTAL should have been better aligned with the Program in order to provide added value to each component.Additional lessons from IEG:The expected outcomes and scope of an operation should be subject to several reality checks at appraisal. An important one is to ensure that essential partnersâ€”such as INFONAVIT in this caseâ€”are fully on board and committed to the operation. If they are not, or cannot be engaged for reasons of political economy, then the scope should be contained to cover more modest outcomes that can reasonably be obtained without such partners. In large and sophisticated middle-income countries like Mexico, an operation should avoid promising sector-wide reforms when commensurate results cannot be realistically achieved in the short timeframe and with the relatively modest scale of assistance offered. Housing finance through mortgage lending encounters an affordability floor. Experience in Mexico shows that poorer households below the 40th percentile of the income distribution cannot afford the cheapest formal housing unit through a market-based mortgage loan without a subsidy. An affordability floor like this will vary from country to country depending upon household income levels, house prices and interest rates.Operations aiming to support affordable housing and urban poverty reduction need to be explicit about their target beneficiary populations, with quantification of baselines and targets, and at completion, achievements.
P101342 | MX Affordable Housing and Urban Poverty Reduction Development Policy Loan III | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2008 | 2008 | 2010 | PPAR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/370121468281080187/text/541930PPAR0Box1Disclosed0May0602010.txt | http://documents.worldbank.org/curated/en/370121468281080187/pdf/541930PPAR0Box1Disclosed0May0602010.pdf | 6 . Lessons 6.1 The expected outcomes and scope of an operation should be subject to several reality checks at appraisal. An important one is to ensure that essential partners-such as INFONAVIT in this case-are fully on board and committed to the operation. If they are not, or cannot be engaged for reasons of political economy, then an operation's scope should be contained to cover more modest outcomes that'can reasonably be obtained without such partners. 6.2 In large and sophisticated middle-income countries like Mexico, an operation should avoid promising sector-wide reforms when commensurate results cannot be realistically achieved in the short timefiame and with the relatively modest scale of assistance offered. 6.3 Housing finance through mortgage lending encounters an affordability floor. Experience in Mexico shows that poorer households below the 40th percentile of the income distribution cannot afford the cheapest formal housing unit through a marketbased mortgage loan without a subsidy. An affordability floor like this will vary from country to country depending upon household income levels, house prices and interest rates. 6.4 Operations aiming to support affordable housing and urban poverty reduction need to be explicit about their target beneficiary populations, with quantification of baselines and targets, and at completion, achievements. 6.5 Contrary to down-market aims, establishing a sound reputation in financial markets and sustaining a high quality and expanding portfolio can lead a new mortgage financier up-market, by targeting higher income borrowers with larger loans. Markets perceive such loans as less risky. They are also less costly to manage and contribute more to business growth.
P101369 | Compensatory Education | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2010 | 2014 | 2015 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/800151468184740056/text/ICRR14739-P101369-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/800151468184740056/pdf/ICRR14739-P101369-Box393183B-PUBLIC.pdf | Since the project piloted a number of innovations, the ICR (pp. 18-19) draws valuable operational lessons from these innovations. These include:Holding father-only sessions on ECD is not sufficient to get fathers to attend. Fathers are more inclined to attend sessions together with mothers, but such sessions need to be designed with attention to the cultural and gender norms prevailing in a particular target area. Furthermore, sessions need to be held after working hours to increase chances of fathers attending.When pairing students or low performing schools with tutors (API system), care must be taken to ensure that tutors can speak the local language in indigenous areas.High illiteracy in marginal areas calls for tutors to be trained to assist illiterate students.Engagement of parents is an important aspect of the tutoring model. Hence tutors need to make house calls on weekends to increase chances that both parents are at home, as mothers alone may be reluctant to receive a tutor in their houses.
P101388 | South Kordofan State Emergency Project | Eastern and Southern Africa | Sudan | IDA | FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2007 | 2012 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/471911474628207718/text/000020051-20140625191828.txt | http://documents.worldbank.org/curated/en/471911474628207718/pdf/000020051-20140625191828.pdf | There are three lessons from the ICR that can be applied more broadly to the Bank's work in Fragile and Conflict affected settings. There are tensions and trade-offs between the need to act quickly to stabilize conflict affected populations and longer-term capacity development objectives. Where there is an inherent tension between the need to respond quickly, as in an emergency operation, and the need to build local capacity, project design needs to acknowledge this tension, the potential trade-offs and ways in which these can be resolved during project implementation.The need to act quickly does not remove the desirability of ensuring some level of stakeholder involvement and consultations, which can be deepened as the project is implemented. The importance of stakeholder consultation at project formulation, during implementation and for project performance evaluation cannot be overemphasized. Preparing counterpart agencies to deal with Bank procedures and systems may require a more concerted effort a new implementing unit is being established, where capacity is low (which is the case in most conflict and fragile situations), and where government counterparts have not worked with the Bank for a long period (as was the case in Sudan). A detailed Project Implementation Manual, drafted during preparation and finalized after incorporating stakeholdersâ€™ suggestions, could be used as a Handbook by the Project Management staff. Another key lesson is the need to provide comprehensive training to the project management staff in Bank procedures at project start-up because of their non familiarity with these procedures. A one day orientation does not serve the purpose.
P101392 | Emergency Energy Assistance | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2009 | 2012 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/889621474648845912/text/000020051-20140625231501.txt | http://documents.worldbank.org/curated/en/889621474648845912/pdf/000020051-20140625231501.pdf | These lessons are taken from the ICR with some adaptation of the language: Projects that are prepared in a short time frame in response to an emergency, have to be designed as simply as possible, in order to deliver quick results and to respond rapidly to evolving needs on the ground.Although emergency operations are not designed to address long-term policy issues, they do serve as good entry points for a longer term engagement. As such, it would be prudent for emergency operations to be followed by a longer-term engagement, as was the case in this project.
P101414 | Eastern Caribbean Energy Regulatory Authority (ECERA) | Latin America and Caribbean | OECS Countries |  |  | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2019 | 2020 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/795841572278243132/text/OECS-Countries-6O-ECERA-Eastern-Carib-Engy-Reg-Auth.txt | http://documents.worldbank.org/curated/en/795841572278243132/pdf/OECS-Countries-6O-ECERA-Eastern-Carib-Engy-Reg-Auth.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptationof language.1.For regional projects, acareful consideration of politicaleconomyis required, both at design and during implementation.The motivation for designing a regionalapproachstemmed from two key regional developments: (a) excess generation capacity from geothermal investments in Dominica,that could have resulted in regional power trade; and (b) plans for Trinidad and Tobago to export liquified natural gas toregionalcountries.Dominica did not joinECERA from the outset and exports of liquified gas from Trinidad andTobago did not materialize. The lack of substantial regional buy- in at project approval undermined regional levelactivities.2. Variations in national sector-specific factorsneed to be considered foraregional project. The key aspects of design of this project,establishing a regional regulatory agency,was based on the success of the model used in aprior Bank-financed regional telecommunications project. However thetelecommunications sector had unique features such as the same company providing telecom services across the regionalcountries.The situation in the energy sector wasquite different, where eachcountry had a different structure andholding forpower utilities (state-owned in some countries and private sector-ownedin others). Therefore, the keydesignof the telecommunications sectorcould not be directly applied to a regional energy sectorproject.3. Timely restructuring of the project could aid in project implementation. Giventhat the key driver for the regional project no longer existed during implementation and there was noregional power/energymarket asenvisioned, the project should have been restructured much earlier (and not four years aftereffectiveness).
P101415 | SENEGAL: TRANSPORT & URBAN MOBILITY PROJECT | Western and Central Africa | Senegal | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2010 | 2020 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/358291608324914100/text/Senegal-SN-Transport-Urban-Mobility-FY10.txt | http://documents.worldbank.org/curated/en/358291608324914100/pdf/Senegal-SN-Transport-Urban-Mobility-FY10.pdf | The ICR draws the following three main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Given that sustainability of the road assets is contingent upon road maintenance, a proper roadmaintenancestrategy is required. In this project, budgeting for road maintenance fellshort of therequirements, due to the governments budget constraints. The lesson from this project is that where road maintenance isconcerned, alternative lending instruments or triggers in a future lending operation, may need to be considered.2.While counterpart funding can signal government commitment, its adequacy and timeliness can have an impact onimplementation. Implementation ofactivities in this project weresubject to delays due to lack of counterpartfunding. The lesson from this project is that issues relating to counterpart funding need to be carefully considered in the countrycontext.3. Stakeholder capacity building is particularly required in urban road projects, in countries where urbanroads are the responsibility of sub-national agencies. The lesson from this project is that where communes and cities areresponsible for road maintenance, capacity building of the beneficiaries can allow for a qualified local workforce to take care ofroad maintenance.
P101426 | Lake Titicaca Local Sustainable Development | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2008 | 2015 | 2017 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/590891467988722756/text/ICRR-Disclosable-P101426-07-08-2016-1467988695988.txt | http://documents.worldbank.org/curated/en/590891467988722756/pdf/ICRR-Disclosable-P101426-07-08-2016-1467988695988.pdf | Implementation Support in Low Capacity Environments ( Bolivia is an IDA country) should be better identified atappraisal and project supervision, including direct technical support using practical international experience should beoffered from the start in order to avoid delay in implementation and provide hands-on assistance when bottlenecksoccur. Adopting appraisal stage readiness criteria for subprojects to avoid delays inimplementation and in reducing risks. Taking the market of contractors and suppliersinto account with regards to contracting and their preferred packaging and terms of contracts is important in order toavoid project risks and ensure timely implementation. Learning from other projects in country and applyinglessons both at the design stage andduring implementation, particularly if they face the same implementationchallenges.
P101432 | UY APL2 OSE Modernization & Systems Rehabilitation Project | Latin America and Caribbean | Uruguay | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2007 | 2013 | 2015 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/201941475115323621/text/000180307-20150108120420.txt | http://documents.worldbank.org/curated/en/201941475115323621/pdf/000180307-20150108120420.pdf | The ICR has a number of lessons and the most relevant are:The Bankâ€™s global knowledge and convening power can play a key role in modernizing utilities. Prior to the project, OSE had a reputation for being an inward looking utility. The Bank facilitated knowledge sharing between water utilities by bringing international experts to the utility, financing participation in international seminars, and including knowledge exchange indicators in the APL II.Focusing on best practices is oftentimes more important than focusing on numeric results. The APL2 played a key role in supporting OSEâ€™s adoption of best practices in customer service, corporate management, environmental management and non-revenue water among other areas. These best practices may enable sustainable growth.Impact evaluation can deliver new insights into cause and effect. The impact evaluation, undertaken during the project, examining the health impact of household sewerage connections on young children is highly relevant in terms of demonstrating the link between access to sewerage and the reduction to exposure to parasites causing illnesses. This link which seems intuitive is not regularly emphasized in either sanitation or health systems decisions. Human capacity development is key to sustainably reducing non-revenue water. OSE found that human capacity development was perhaps the most essential tool for reducing water losses and that company-wide day-to-day operations have the greatest impact on non-revenue water loss reduction.
P101434 | Transport Sector Program Support Project | Western and Central Africa | Niger | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2008 | 2016 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/377491525389579550/text/Niger-Transport-Revised-Final-2018.txt | http://documents.worldbank.org/curated/en/377491525389579550/pdf/Niger-Transport-Revised-Final-2018.pdf | The following three lessons learned were derived from the ICR: The size and scope of a contractshould take into account local capacity and experience. For example, at the beginning of this contract, local contractorsdid not have the managerial or technical skills to execute alarge road works contract, which led to delays and overrun ofcosts. Contacts that were smaller (road lengths of 50Km) proved to be more effectively executed (ICR, p.10). Risk assessments should take into account technical design, such as construction materialcosts. For example, this project when designed did not take into account country-specific construction materialcosts and potential unexpected contingencies. For instance, the project experienced overrun of costs due to aheavy rainyseason that took place between studies and civil works. Budgetary planning did not take into account the impact of the rainy seasonon construction material costs. Use policy or effectiveness conditionality on Investment PolicyFinancing only if Government committed to make change. For example, the additional funding for thisprojectintroduced an effectiveness condition for the Government to pass a law directly transferring fuel levy revenue to theRoad Fund. While this was an important accomplishment of the project, it was achieved through considerable difficulty, six yearsafter the projects approval and under duress (i.e. with serious threat of withdrawal of Bank support to complete an unfinishedinvestment) (ICR, p.9).
P101446 | Enhanced Justice Sector Services Project - Mongolia | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2008 | 2013 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/232331475116422439/text/000012394-20150309080023.txt | http://documents.worldbank.org/curated/en/232331475116422439/pdf/000012394-20150309080023.pdf | The ICR draws several general lessons from the operation: 1. Changes in agency operations and justice outcomes are largely dependent on changes in institutional culture which often takes longer than the typical lending project cycle, and need to be taken into account in designing an operation of this nature. The ICR also notes that legal covenants are not a replacement for project preparedness. 2. Government actions by the government may be preferable to effectiveness conditions. Reliance on project conditionality to replace project readiness can only impede and compromise implementation.3. Where effectiveness conditionalities are included to mitigate risk such conditions require a discussion with government and thorough review by the Bank team on whether these are critical and realistic and could be met and do not impede implementation if these are not met. IEG draws several additional lessons: 1. Where co-financing is included in the project design as necessary for implementation of activities, such co-financing needs to be agreed upfront to avoid delaying project approval and implementation. Dialogue and the resultant necessary restructuring need to take place swiftly so that the objectives and design and implementation steps are clear and agreed by decision-makers for all parties to improve likelihood of achieving the projectâ€™s development objectives.2. M&E design needs to be aligned with project design and realistic and to capture lessons from innovative approaches. New approaches were introduced under this project, but absence of M&E did not permit such learning lessons from experience. 3. Where implementation capacity is weak the project needs to focus on a few mutually compatible activities to ease the difficulty of supervision rather than having a broad base with several different components each requiring different skill sets to monitor and implement and different stakeholders with which to interact. Over diverse components risks stretching capacity of the implementing unit to negatively affect project implementation.
P101453 | Institutional Reform Development Policy Grant | Middle East and North Africa | Yemen, Republic of | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 2008 | 2012 | 2013 | ICRR | >=25 million & <50 million | Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/903701474631622802/text/000020051-20140625191045.txt | http://documents.worldbank.org/curated/en/903701474631622802/pdf/000020051-20140625191045.pdf | The main lessons from the experience of preparing and implementing this operation are:1. A tight causal chain linking the measures being supported to the objectives that are sought is an important dimension of good preparation. Without this, much effort could be expended on measures of little consequence. In this case, addressing deep rooted poverty or increasing non-oil growth require a wel- considered strategy and a sharp focus in project design.2. Better economic analysis using available data would have focused the project and set priorities. The team could have benefited from the participation of a macro-economist who would have analyzed the extent to which the measures being supported could lead to higher non-oil growth. 3. "Stroke of the pen" measures (e.g. passing a law, reducing a tariff) and those that require persistent effort should be distinguished. Civil service reform in particular requires consistently good budgetary oversight and continued broad public support, and it should have been clear at the outset that neither was present.
P101456 | Liberia Infrastructure Rehabilitation Project | Western and Central Africa | Liberia | IDA | FCS | Infrastructure | Transport | SPF | IPF | 2007 | 2011 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/119991474569476671/text/000020051-20140626104708.txt | http://documents.worldbank.org/curated/en/119991474569476671/pdf/000020051-20140626104708.pdf | Two of the identified in the ICR are especially noteworthy: i) If emergency projects, especially in post conflict situations, are not focused on the most urgent and critical tasks, implementation difficulties will accrue and divert management attention away from the critical work at hand. ii) Estimating costs for major works in post conflict countries is challenging. A different set of tools, including market surveys and larger contingencies might be needed to get a better ballpark estimates.
P101471 | Peru First Progrmmatic Environmental Development Policy Loan /DDO | Latin America and Caribbean | Peru | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2009 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/652371495472826193/text/Peru-PE-DDO-First-Prog-Environ-DPL.txt | http://documents.worldbank.org/curated/en/652371495472826193/pdf/Peru-PE-DDO-First-Prog-Environ-DPL.pdf | Five lessons are drawn from the ICR (pages 32-36), with some adaptation.One, strengthening environmentalgovernance by public institutions and mainstreaming environmental sustainability in private industry are long-term processes andneed considerable time to implement. The ENVDPL benefitted from the decision to structure the ENVDPL1 as a deferred drawdownoperation (DDO), which kept ENVDPL1 active for five years, well beyond the original one-year life of the operation. The longer timeperiod accorded the Bank the opportunity to systematically help strengthen the institutional capacity of the Government, enablingpublic agencies to meet the prior actions of the reform program.Two, building a reform program requiresextensive analytical work, including not just of the technical and the institutional but also the political economy dimensions ofthe reform effort. Perus Country Environmental Analysis (CEA) of 2007 served as the organizing analytical documentunderpinning the environmental management reform plan advanced by the ENVDPL. The CEA thoughtfully: examined the shortcomings ofthe national environmental management system in the country, and identified priorities that were consistent with thecountrys development agenda and could be linked to poverty reduction.Three, government ownership is essentialto the effective implementation of policy reforms. Political commitment was secured across the spectrum of agencies responsible forenvironmental management in the country, and at key levels of the organization in these public agencies. The top-line agenciesresponsible for implementing the reforms measures --- MEF, the newly created MINAM, PRODUCE, MEM, and MTC --- were individually andcollectively committed to the reform agenda.Four, framing poor air quality as detrimental to poverty reduction helpscatalyze action to address the air pollution problem. The negative effects of air pollution were demonstrated to be significantlyhigher on the poor and on the vulnerable in Peru --- women, the elderly, and children. Poor air quality stunted productivity andeducational performance, constraining the opportunities of the poor and the vulnerable for economic advancement. By highlightingthese findings, the Government succeeded in raising an awareness of the air pollution problem and in mobilizing a broad base ofstakeholders for the ENVDPL to address the problem.Five, measures to address MELs need to be constantly evaluated.The Government completed all the measures designed to completely identify MELs and to commit resources to remediate the high-risksites. Yet, mining-related social conflict has not decreased in Peru, where at least a fourth of the social conflicts in 2008-14were mining-related. The 2016 study Peru: Policy Options to Enhance Environmental Sustainability in the Mining Sectoridentified five issues: the fear of pollution; competition over land and water resources; cultural and social issues that are notadequately addressed, leading many communities to oppose mining activities; the asymmetry of power relations between industry andthe communities; and, the lack of confidence among communities that the Government can adequately protect the environment.
P101473 | Urban Water Supply and Sanitation Project | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2007 | 2018 | 2019 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/504231538336138167/text/Ethiopia-ET-Urban-WSS-SIL-FY07.txt | http://documents.worldbank.org/curated/en/504231538336138167/pdf/Ethiopia-ET-Urban-WSS-SIL-FY07.pdf | The ICR presented the following lessons from the operations: Using a revolving fund, such as WRDF to provideon-lending to city utilities after they provide matching funds may leverage resources and help ensure buy-ins from participatingutilities. Evidence was provided by repayment patternsby these utilities. Project design for self supportingutilities needs to focus on a realistic cost of connections to the infrastructure trunk, the willingness and ability to pay ofthose who will be connected, and access preferences at the household level. When investments require access to energysupply, and if target communities may be outside the existing grid,alternative technologies that rely on low energyrequirements may need to be adopted.
P101474 | Urban Local Govt Development Project | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2008 | 2015 | 2016 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/721021468178189880/text/ICRR14844-P101474-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/721021468178189880/pdf/ICRR14844-P101474-Box394823B-PUBLIC.pdf | The ICR draws the following lessons from the experience of preparing and implementing this project.(1) It is always important to include funds or incentives to regional entities or agencies in the context of a urban development project when many regional entities are involved. The experience with this project demonstrated that although the regional agencies were expected to perform key project tasks, the project did not provide any funding to the agencies for undertaking these tasks. This in turn compromised their ability to complete the project tasks in a timely fashion.(2) Where cities are expected to continue to invest in maintain infrastructure, it is important to ensure that capacity building support is provided to the cities. In the case of this project, cities were expected to prepare revenue enhancement plans and identify potential sources of funding for infrastructure investment through their own sources. Although all cities prepared revenue enhancement plans as required, most did not do so based on a through analysis of the potential of various revenue sources, but did so based on projections of revenue achieved in the previous years.(3) Where many cities are involved in a project, it would be useful to support large cities with a stand alone project, rather than through a project which includes both large cities and multiple secondary cities. This project included a mix of many secondary cities and large cities like Addis Ababa. Funds available to Addis Ababa were inadequate to encourage the city to make the required changes since the project provided only a small portion of its overall revenues.
P101474 | Urban Local Govt Development Project | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2008 | 2015 | 2019 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/841941549388049518/text/132824-PPAR-P101474-P167797-PUBLIC.txt | http://documents.worldbank.org/curated/en/841941549388049518/pdf/132824-PPAR-P101474-P167797-PUBLIC.pdf | 6. Lessons 6.1 There is a trade-off between scope and development outcomes in municipal operations that use performance-based grants. It is critical to ensure that funding is sufficient to both incentivize behavior at the city level and offer a meaningful level of technical assistance. The government of Ethiopia often chooses breadth over depth when scoping its operations for reasons related to social cohesion and perceptions related to regional inequality. The ULGDP is an exampleâ€”it includes all 117 cities with a population of more than 20,000 persons. By contrast, only 18 cities were included in the first project. Such reduced scope was a major success factor that enabled meaningful transfers at a scale that could incentivize transformational behavior. Targeted cities adopted participatory planning, capital and maintenance planning and budgeting, and own-source revenue enhancement, and provided access to all-weather roads. Such outcomes are unlikely if only modest amounts of transfers per city are available. 6.2 A one-size-fits-all approach is ineffective in urban development projects that target multiple cities at various stages of development. To achieve development outcomes, the World Bank should instead offer a flexible package of infrastructure, service, and technical support options aligned with clients' differentiated needs. In rapidly urbanizing areas, client needs can evolve and diverge, even during the life of a single project. In Ethiopia, some cities require support that is more sophisticated for city management and advanced infrastructure, which differ from the needs of newly created cities. Such a differentiated approach could have solved the misaligned incentives to reform in Addis Ababa, for example. 6.3 Performance-based grants should be considered as a preferred method of intermediating intergovernmental fiscal resources to ULGs in the context of emerging urban systems. In urban operations, performance-based grants can create a significant level of bottom-up demand for capacity building and governance strengthening that has proven to be more successful in World Bank operations in Ethiopia than supply-led approaches have been. The performance-based payments that the project offered and the associated support and training incentivized cities, regions, and the associated ministry to put needed institutional procedures in place. 6.4 Promoting autonomous decision making at the city level while ensuring that operational rules and supervision are in place are necessary conditions to ensure the intended use of funds in municipal finance projects. In the ULGDP, the World Bank initially decided not to intervene in the fund allocation process, beyond the assignment of broad categories. This approach proved insufficient, however. The World Bank tried to insert more selectivity at the time of additional financing by adding specific indicators, but these fell short of ensuring that the funding was fully allocated as intended (for example, cobblestone roads were sometimes located in relatively upscale or underpopulated areas, and roads were built without proper drainage). 6.5 Urban development projects need to balance targeting core city administrative functions as well as improving city management and planning competencies. The ULGDP primarily addressed back office functionsâ€”getting systems in place and helping them to function effectively. Consequently, some of the core city management and regulatory functions in the targeted municipalities progressed slowly. For example, in the cities targeted, there was little progress on enforcing building codes, construction quality, integrated drainage, and traffic management. The balance requires designing projects that can emphasize addressing each city's binding constraints.
P101486 | Fourth Poverty Reduction Support Credit | Europe and Central Asia | Armenia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2009 | 2010 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/335271474512521374/text/000020051-20140620070928.txt | http://documents.worldbank.org/curated/en/335271474512521374/pdf/000020051-20140620070928.pdf | IEG broadly concurs with the lessons outlined in the ICR but would like to highlight the following two lessons in particular:First, a sound PRSP, prepared in a participatory manner and owned by the government is a critical input for a successful PRSC program. However, it should not be treated as a straightjacket and the PRSCs should not shy away from supporting difficult actions that go beyond the PRSP but are critical to sustained growth. Such an approach should, however, only be used in cases where; (i) there is robust analytical basis for supporting the proposed reforms; and (ii) there are important constituencies within the government and outside who are keen to use the leverage of the PRSC to change the status quo.Second, the weak results framework and inadequate M&E still remain an important constraint to realizing the full potential of the PRSCs. Assuring a pragmatic design up front and a systematic follow through during the implementation should continue to be the priority agenda for the task teams.
P101502 | Afghanistan HIV/AIDS Prevention Project | South Asia | Afghanistan | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2008 | 2013 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/293391474629339995/text/000020051-20140626114310.txt | http://documents.worldbank.org/curated/en/293391474629339995/pdf/000020051-20140626114310.pdf | Lessons drawn from the ICR (pages 27-28), adapted by IEG:Technically strong and evidence-based project interventions may have limited influence on program directions without a supportive political and social environment. In the case of this project, the controversial nature of the IDU interventions was not effectively mitigated by advocacy among opinion leaders or the general population.The importance of timely surveillance data needs to be balanced with ensuring quality and reliable results. In the case of this project, the conflicting expectations of timely data to inform project design and policy vs. high quality data to inform research led to implementation delays. These expectations should be clarified during project preparation.
P101504 | Second Bolsa Família | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2011 | 2019 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/849741581102417623/text/Brazil-BR-Bolsa-Familia-2nd-APL.txt | http://documents.worldbank.org/curated/en/849741581102417623/pdf/Brazil-BR-Bolsa-Familia-2nd-APL.pdf | The ICR (pp. 33-34) offered several lessons and recommendations, including the following lessons restated byIEG:A comprehensive and regularly updated beneficiary registry facilitates the implementation notonly of a cash transfer program, but also its use by other targeted programs.Under the project, BFPs singleregistry of beneficiaries was used by 29 programs.The development and disclosure of a large body ofevidenceon a large conditional cash transfer program enhances credibility and stimulates further knowledge and studies byexternal groups at no cost to the government.Under the project, MDS made data available on its external website,thereby promoting transparency and enabling the use of rich data for further studies undertaken by externalgroups.Initial positive results generated by a social protection program help in building furthersupport and increasing prospects for sustainability.Despite political turnover, commitment to BFP remained strong,as the program was perceived as an effective scheme in confronting poverty, as documented by its earlyresults.
P101508 | Rio de Janeiro Sustainable Rural Development Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2010 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/313101574087638465/text/Brazil-BR-RJ-Sustainable-Rural-Development.txt | http://documents.worldbank.org/curated/en/313101574087638465/pdf/Brazil-BR-RJ-Sustainable-Rural-Development.pdf | The ICR provided several lessons, many of which overlapped and mainly related to demand driven approaches for mobilizinginvestment support in rural areas. Such lessons have already been learnt under many projects in the past. However, one lesson thatstands out relates to the importance of accurately assessing theimpact of project benefits. Thus IEG concluded that thefollowing was a key lesson:ME design needs to be adequate to accurately capture projectbenefits.The projectsupported rehabilitation ofmore than 7,000 km of rural roads rehabilitation,whichis known to be acrucial precondition for market access in rural areas.Based on two roads 7-9 km long theproject estimated that the benefits of theroad rehabilitationprogram were a 92 percent reduction of days ofnon-trafficability, a reduction of production losses (20 percent in the case of milk and 36 percent in the case of vegetables),reduction of 50 percent of travel time due to increase in traffic speed, reduction of 4060 percent of the average cost ofvehicle maintenance, and 2050 percent reduction in average fuel consumption. This review questioned the veracity ofthese benefits determined on the basis of information from only two stretches of roads of 7-9 kmunderlines the lesson that aprojects ME program needs to be designed to accuratelyassess project outcomes.IEG also concluded thefollowing related lesson:A complex project requires a clear Theory of Change and a robust results framework.This project included many aspects ranging from environmental sustainability to productivity as well as marketinglinkages, road infrastructure and decentralization, and local capacity building. When suchcomplexity is introduced thisshould be supported by a very clear objective and well-defined theory of change as well as a robust results framework as a basisfor measuringoutcomes. Unfortunately, the project failed to do that. Even though the project financednumerousinvestment proposals, sufficient outcome evidence on increased productivity and improved competitivenesswas notcollected.
P101525 | CN Yunnan Honghe Prefecture Diannan Center Urban Transport | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2014 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/099300512232240984/text/P1015250ad979108409bd20b41ba64ab8ba.txt | http://documents.worldbank.org/curated/en/099300512232240984/pdf/P1015250ad979108409bd20b41ba64ab8ba.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Strong government commitment can help in converting historical areas into pedestrian-onlyzones.In this project, the Government banned motorized traffic from the historic downtown area and made this areainto pedestrian-only zones.2. Given that road safety is emerging as an urban issue globally, it would helpif more attention is paid to designing better road safety indicators. The ICR notes that there is no widely availablemethodology for forecasting road accidents and fatalities. It would also help if trends in road fatalities in project-intervenedareas are compared with the national or state trends to indicate the extent to which the outcomes could be attributed to projectactivities.3. An approach which combines supply-side road safety and demand-side measures can help in addressingroad safety issues. The lesson from this project is that combining both supply-side road safety measures (such asincorporating road safety infrastructure investments on roads) with demand-side measures (such as, rigorous enforcement of parkingmanagement) are likely to help addressing road safety issues.
P101570 | Mauritius Development Policy Loan | Eastern and Southern Africa | Mauritius | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2007 | 2008 | 2013 | ICRR | >=25 million & <50 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | High | http://documents.worldbank.org/curated/en/713521475098269117/text/000020051-20140625192948.txt | http://documents.worldbank.org/curated/en/713521475098269117/pdf/000020051-20140625192948.pdf | IEG concurs with the ICRâ€™s findings that the success of the reform program in Mauritius was largely due to strong government ownership and a participatory approach which involves all key stakeholders in society. Close coordination with key donors in harmonizing conditionality enabled the government to implement a single comprehensive reform program. An important lesson from Mauritiusâ€™s experience is that the ability to respond to new challenges is essential for successful implementation of the reform program. The program was also sharply focused and internally consistent and therefore easier to implement and monitor.
P101578 | PNG Energy Sector Development Project | East Asia and Pacific | Papua New Guinea | Blend | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2013 | 2020 | 2021 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/320491612292252487/text/Papua-New-Guinea-PG-Energy-Sector-Development-Project.txt | http://documents.worldbank.org/curated/en/320491612292252487/pdf/Papua-New-Guinea-PG-Energy-Sector-Development-Project.pdf | The ICR has identifieda number ofimportant pointslisted on pages 32-33, but most of them are eitherfindingsor recommendations. Drawing from the ICRs material, this review identified the followinglessons:Ensuring implementation readiness can better lead toresultsthan trying to build the neededcapacity during project implementation: At appraisal, institutional and technical capacity weaknesses wereidentifiedin the project implementation units, particularly in the fiduciary areas. Mitigating measureswere ineffective, and thissituation led to delays in the project implementation,restructuring andextension of theproject closingdate.The projectimplementation experience confirms that ensuring thatimplementation unitsare ready in termsof staff quality and fiduciary expertiseis essentialfor the timely project launchand implementationperformance.Having the technical and institutional expertise in place ahead of project launch is better than trying to remedythe situation in the course of project implementation.Matching the scope and size of the project activities toexisting institutional capacitymay better contribute to achieving the expected outcome. A key goal of this projectwas to achieve a bankable scheme for the development of the hydropower plant by a private investor. In hindsight, thisoutcome ended up being a very ambitious attempt, because of the absence of therequired institutional capacity.Theachievement of this outcome within four years was unrealistic giventhat suchwas a complex transaction process that hadto tackle multiple challenges. The developer was expected to be selected by the end of the second year of project implementation,and the financiers due diligenceto be completed by the end of the fourth year. Because ofthe countrysinstitutional weaknesses, progress toward outcome was minimum, and the Government opted to discontinue the hydropowerplantideain favor of anIPP gas generation.The completion ofstudies analyzing theaspectssurrounding theproject activities can help designa more realistic project. The development of the NaoroBrown Hydropower Plant Project was a major undertaking requiring a comprehensive grasp of thecountrys powercontext.The construction of the new hydropowerplant required adetailed preparation and development, including thecompletion of thethree-river basin study that would form the basis for the hydropower supply plan for the Port Moresby area,as well as the Least-Cost Power Development Plan. The absence of a least-cost power development plan resulted in an unrealisticproject design, becausethe 2018 findings of the Least-Cost Power Development Plan supported the rehabilitation of existinghydropower capacity and development of gas-to-power projects are lower cost options compared to the option of launching the NaoroBrown Hydropower Plant Project. It is essential to complete therequired keystudies before embarking on any hydropowerproject.
P101590 | Second Programmatic Fiscal Mgmt and Competitiveness Development Policy Loan | Latin America and Caribbean | Peru | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2009 | 2015 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/208431474588004209/text/000020051-20140625224545.txt | http://documents.worldbank.org/curated/en/208431474588004209/pdf/000020051-20140625224545.pdf | The following lessons were identified by IEG's review and the ICR:Sweeping and sustained reforms (such as Peru's) require strong borrower ownership, a well-defined strategy, a highly consultative approach with country stakeholders, and a response donor consortium. Close coordination with international actors helped the Government to implement its comprehensive reform programs over several years.Sustaining fiscal and related public sector management reforms can be challenging. They place a premium on a 'building blocks' approach (for example, ensure aggregate fiscal policies are in place before undertaking expenditure re-prioritization). At the same time, it is important to be flexible in launching various reform initiatives when public institutions demonstrate a readiness to undertake and internalize institutional changes. An important lesson from Peruâ€™s experience is the need to design flexibility into the program in order to respond to new challenges over the course of reform implementation. Peru was successful in adjusting to the changes in global financial markets while remaining faithful to the objectives of its reform program. The Bank acted as a responsible partner and provided both financial resources and technical advice as needed to enable government to carry on its reform program. The use of the deferred drawdown option (DDO) can be helpful in managing the uncertainties for a volatile global environment. It enables countries to have additional insurance to weather the global financial crisis as the availability of financing from the World Bank increase market confidence and access. It also provides a stamp of approval of good housekeeping.
P101590 | Second Programmatic Fiscal Mgmt and Competitiveness Development Policy Loan | Latin America and Caribbean | Peru | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2009 | 2015 | 2017 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/725661488828202108/text/110742-PPAR-PUBLIC.txt | http://documents.worldbank.org/curated/en/725661488828202108/pdf/110742-PPAR-PUBLIC.pdf | 6. Lessons 6.1 The experience of this DPL series highlights what can be expected from the World Bank's engagement with a well-performing middle-income country. 6.2 A programmatic DPL series is a powerful tool for supporting long-term reforms. When a strong ownership of the client is demonstrated, a programmatic series of operations can offer the World Bank and its client win-win solutions. For the World Bank, a multiyear program of support gives it a chance to pursue an extended and coherent analytical agenda that may not be feasible in multiple one-off operations. To the client, the programmatic series offers a real-time opportunity to engage with the reforms (including both the costs and benefits) and to make adjustments along the way. In the case of Peru, the government was able to advance its investment climate agenda early on and to learn about the need for deeper and longer-term challenges of upgrading the quality its workforce and technologies. The successive rounds of ever deeper reforms on trade and competitiveness, while incomplete and not implemented with maximum efficacy, would have been difficult to accomplish through separate operations, which are invariably interrupted by changes of priorities and political mandates. 6.3 World Bank supervision of the implementation of these operations should cover all aspects of the program to take full advantage of the learning opportunities offered by a programmatic series. It should pay greater attention to not only emerging risks during the period of program implementation, but also factors affecting the sustainability of the achievements in long-term policy reforms. In the case of Peru, supervision of the core program seemingly focused only on a few development objectives and outcomes, and left unattended a complete pillar of reforms. No explanation is given for this in any of the Implementation Status and Results Reports. This may have resulted in issues not being identified and therefore not addressed, in time leading to less progress than expected or reversal of outcomes achieved. It limited the ability of the World Bank and other stakeholders to fully understand and learn from the experience of this DPL series. 6.4 Reforms move to subnational levels, though their implementation may pose a challenge depending on the framework of fiscal decentralization. Despite all the positive steps that the government had taken to enhance efficiency in the allocation of fiscal resources, there remains a pressing need to rationalize the fiduciary and regulatory norms and the multiplicity of control and auditing instances. According to MEF officials interviewed for this evaluation, these have proliferated and seem to be driving a wedge between the central and regional governments' capacity to focus on results rather than procedures, a central objective of results-based budget management. Another area of clear priority is for the government to continue to place strong emphasis at the central and subnational levels on a robust and rigorously appraised public investment program, and enhance its assistance to subnational governments in identifying, designing, and implementing their own programs, particularly in meeting infrastructure deficits (for example, roads, water and sanitation). To do so, the government should consider placing greater emphasis on subnational tax revenue collection and more efficient distribution of fiscal transfers to subnational governments, areas that proved somewhat lagging during the implementation period of this DPL series. 6.5 The application of the DDO in this DPL series illustrated the World Bank's willingness and ability to support Peru at the time of the global financial crisis. It also showed the extent to which the World Bank's new arsenal of financing instruments was able to respond to the needs of middle-income countries where both the volume and the timing of financing are important for risk management purposes. As a tool for risk management, the DDO gives clients access to a large line of credit that is affordable and fast disbursing, which helps maintain the confidence of investors and deter the resolve of speculators. As a debt management tool, the DDO offers the government an insurance policy on its debt-service and priority expenditure commitments without raising the level of external debt in advance. The discretion to call on the World Bank loan in the amount it needs when it needs to allows the government to optimize its debt structure. Moreover, by extending the loan period by up to six years and not requiring the client to draw down the loan, the DDO facilitates World Bank engagement with clients who do not need World Bank financing but value its formal and sustained support for their policy reforms. This is particularly valuable for engaging with well-performing middle-income countries. 6.6 Yet, the present example also illustrates possible tensions between the independent selection of IBRD-financing terms and the monitoring of the World Bank's development effectiveness. In this DPL series, the DDOs were requested and approved for risk management and crisis response purposes, but this important development objective, for which two large loans were granted in record time, was not tracked. Although monitoring of the macroeconomic framework and program implementation continued until closure of the DDOs, the depth of supervision was restricted to verification of preconditions for drawdown, as required for all DDOs, and did not try to capture the effectiveness of the loans for all their development objectives. This raises a question as to whether overall program design or continued periodic supervision should attempt to explicitly include indicators of risk management and crisis containment, to capture overall development impact of the DPL series. As this practice was repeated in multiple DPL series in Peru (and elsewhere), a substantial amount of World Bank resources is at stake. 6.7 A parallel issue is that with its longer drawdown period and its renewal feature, the implementation period of a DPL-DDO extends beyond the program implementation period of a normal DPL, which has consequences on the expected outcomes. This calls for attention especially in situations where the DDO was added to an ongoing DPL series, such as in Peru, which had a set of coherent, noncrisis-related policy objectives and a predetermined program period that did not (and could not) anticipate the additional crisisrelated objective and the extended program implementation period. The World Bank's DDO guidelines only require the monitoring of macroeconomic stability and the continued implementation of the program. Questions can thus be raised on whether there should be any more detailed supervision or scope for review of the overall program at the time of a DDO's approval and renewal or readjustment of the IBRD-financing terms with regard to repayment options as the country's debt management profile may have altered. Notwithstanding, the trade-off relative to the flexibility of the loan instrument is also important. These issues merit further debate.
P101608 | VN-Avian & Human Influenza Control &Prep | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2007 | 2014 | 2015 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/655541468186529844/text/ICRR14717-P101608-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/655541468186529844/pdf/ICRR14717-P101608-Box393183B-PUBLIC.pdf | The ICR (p. 26) identifies valuable lessons, including:In case of an emergency situation a move to a systematic improvement is critical for achieving better long-term outcomes. Vietnam took advantage of the situation to get political and financial support to improve its veterinary and human health system which is critical for addressing future disease outbreaks.Cross-sectoral approaches are critical but require good leadership. The collaboration between the Ministry of Health and the Ministry of Agriculture and Rural Development facilitated information sharing, joint analysis of results and efficient use of resources. However, this required the support of senior leaders from both ministries.Decentralization of project activities to lower government levels might be challenging but may lead to positive long term impacts. In this project, the decentralization of activities to the provincial and district levels built capacity in various areas. Also, the decentralization led to more project ownership at the lower government levels.
P101614 | Public Sector Modernization Project | Europe and Central Asia | Kosovo | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2010 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/367121516720142871/text/Kosovo-PUBLIC-SECTOR-MOD.txt | http://documents.worldbank.org/curated/en/367121516720142871/pdf/Kosovo-PUBLIC-SECTOR-MOD.pdf | The first three lessons are drawn from the ICR, with some adaptation of language. The last two are drawn byIEG. A simple project design with a few critical activities and a minimum number of implementingagencies is most suited to complex, post-conflict environments and low client capacity: Kosovo was newly independent andthe project was the Banks first lending operation. The political environment was volatile, and there was no consensusconcerning some of the reform areas addressed by the project. Despite the constraints associated with such an environment, theproject included three stand-alone sets of objectives and related components which could have been designed as three differentprojects. It involved two principal implementing agencies (MFE and MPA) and nine beneficiary and implementing institutions withimplementation responsibilities. This coupled with low client capacity led to delays and resistance to change. Athorough political economy analysis is especially useful for countries in Kosovos circumstances. Such an analysiswas in fact recommended by the Quality Enhancement Review meeting, but was not carried out. The analysis could have provided astronger assessment of the interests and motivations of stakeholders and hence have aided the selection of activities less likelyto encounter resistance. It would also have supplied a stronger underpinning for advice to the Authorities on such matters as themembership of the Inter-Governmental Steering Committee. Continuous sharing and exchange of information andimplementation experience among beneficiary agencies can yield important benefits. This was impeded in this case in thatcapacity building for PFM was provided to five budget organizations separately and in isolation. Different consultants workeddirectly with each organization, and there was no experience sharing. This led to a silo approach as no one looked at the lessonslearned from other budget organizations. An operation to improve public financial management is likely to have agreater beneficial impact when the Ministry of Finance is a key beneficiaryorganization: In this case, there was no provision for capacity building in the Ministry of Finance. Unless the Ministryof Finance also benefits from capacity building, other Ministries would be constrained to continue applying its procedures, evenwhen they were in need of improvement. The Ministry of Finance was only added as a beneficiary organization at a late stage in theimplementation process. Project impact can be increased when the same beneficiary organizations participate undereach component. In this case, the organizations benefiting from capacity building to enhance performance in budgetplanning and execution were not targeted under other components. Had they been so targeted, the consolidated impact of projectinterventions on all sides would have been increased.
P101645 | TZ-Energy Development & Access Expansion Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2008 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/800771539868430329/text/Tanzania-TZ-Energy-Development-Access-Expansion.txt | http://documents.worldbank.org/curated/en/800771539868430329/pdf/Tanzania-TZ-Energy-Development-Access-Expansion.pdf | IEG derives the following lessons, drawn from the ICR: Technical assistance can play an importantrole in alleviating the constraints imposed by capacity limitations for complex projects. To help the client deal with thelarge scope and complexity of the projects activities, the project allocated resources to build technical capacity not only ofthe government implementing agencies, but also of the private sector and participating financial institutions (PFIs).Thoughnot all of the capacity building was fully implemented, this TA was helpful inovercoming some of the capacity challengesarising. Less prescriptive approaches allow for better adaptation to dynamic markets. TheSustainable Solar Market Packages (SSMP) sub-component of the project faced challenges in implementation arising predominantly fromthe design of the project, which relied heavily on government procurement. And was not sufficiently adaptable to changing marketcircumstances. With the growth of private sector providers in the solar home system market, technological innovation has led to thedevelopment of innovative business models. In such a dynamic market, an adaptable approach addressing key market failures withoutimposing unnecessary constraints is likely to work best. Such an approach is in fact increasingly being adopted across the regionfor off-grid electrification. For projects with transmission and distribution (TD)infrastructure components, and especially in densely populated settings,social and environmental safeguards aspectsneed to be systematically addressed and dealt with during preparation and appraisal of the project, in order to ensure smoothimplementation.Many of the delays experienced by the project arose from shortcomings in procuring goods and in gettingthe right-of-way cleared for TD lines, including related resettlements. Particularly in densely populated settings, the designof TD infrastructure needs to give priority to identifying RAP requirements at an early enough stage, to make sure that theright-of-way is securedwhen the project is launched. A conducive and consistentoperating environment is an important factor for successful implementation. Government policies in favor of lowering connectionfees and tariff adjustments increase the ability of the utility to deliver on access and efficiency targets. At the sametime, a transparent and comprehensive regulatory framework for SPPs helped stimulate the industry and increased the effectivenessof the support provided under the project. Conversely, the shift in the Governments policy on tariff determination andprivate sector participation that took place in recent years had adverse implications on the project, putting pressure onTANESCOs finances and its ability to make timely payment of bills of SPPs connected to the TANESCOgrid.
P101650 | IN Andhra Pradesh and Telangana Rural Water Supply and Sanitation | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2010 | 2018 | 2019 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/775901532958912985/text/India-IN-AP-TS-RWSS.txt | http://documents.worldbank.org/curated/en/775901532958912985/pdf/India-IN-AP-TS-RWSS.pdf | The first two lessons are taken from the ICR (p. 33-34) with some modification oflanguage: Decentralizing service deliveryrequires sufficient analysis and understanding of the political economy of the project counterpart. In this project,the Banks support to the states in managing the investment program for access expansion was critical. However,additional support was required to change the entrenched way of providing service delivery through a centralizedapproach. Communities having access to water is a pre-requisite to move towards open defecation freestatus. Users reported that it is easier to maintain latrines once water is available to keep them clean, supporting thehypothesis that latrine use is higher once water access is ensured.Additional lesson byIEG: Implementing a sustainable ME system is critical forensuring an adequate assessment of the threats to the financial sustainability of water and sanitations services. Inthis project, inadequate data for two important indicators, contribution to OM and average collection efficiency, does notprovide sufficient information to assess the financial sustainability of the sector, nor the granularity to better respond tocontinued needs.
P101653 | POWER SYSTEM DEVELOPMENT PROJECT IV | South Asia | India | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2008 | 2015 | 2015 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/684871468186254738/text/ICRR14748-P101653-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/684871468186254738/pdf/ICRR14748-P101653-Box393191B-PUBLIC.pdf | Some of the key lessons provided by the ICR (pages 29-31) are quoted below:Long-term programmatic engagement results in a successful partnership. The Bank's long-term support for POWERGRID has resulted both in a strong transmission system and deep institutional strengthening, as shown by the continuous improvements in POWERGRID's technical implementation, procurement, and safeguards systems, which are now used as standards by other companies.Repeater operations contributed toward effective implementation of POWERGRID projects. Early preparation while the previous PSDP III was still being implemented helped to minimize the issues for PSDP IV. Moreover, the use of the same eligibility criteria helped to maintain the Government's commitment to the project.Timely measures are required for overcoming Right-of-Way (RoW) issues. POWERGRID seeks early assistance from local government authorities and has adopted an innovative tower design that reduces the width of RoW requirements, thus minimizing conflicts and delays in obtaining RoW. Due focus on safeguards help in obtaining forest clearances with a shorter turnaround time. The strengthening of POWERGRID's environment and social department, and its allocation of one officer in each region for regular follow-up and monitoring of forest proposals with the relevant officials, helped expedite obtaining forest clearances.
P101684 | Trade and Transport Facilitation II | South Asia | Pakistan | Blend | Non-FCS | Infrastructure | Transport | IDA | IPF | 2009 | 2014 | 2015 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/714251475118188412/text/000020051-20150312120043.txt | http://documents.worldbank.org/curated/en/714251475118188412/pdf/000020051-20150312120043.pdf | The ICR (page 20-21) draws the following main lessons from this project.Developing realistic project outcomes and objectives that are measurable within the timeline of the project is crucial. While the project may be contributing to higher level goals, these should not be used as key indicators.If the government's commitment to the project wavers, it is important to preempt this by either restructuring the project or canceling the project. While mitigation of political risk may be difficult to incorporate in the project design, it is important that the team remain pro-active in managing the government's commitment through the project implementation period.It is important to keep the implementation structure simple. The experience of this project showed that involvement of too many players (such as the Planning Commission and the line ministries) can result in implementation delays caused by cumbersome administrative processes.
P101716 | Jilin Agricultural Product Safety and Quality | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2010 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/308621525863035072/text/China-CN-Jilin-Food-Safety.txt | http://documents.worldbank.org/curated/en/308621525863035072/pdf/China-CN-Jilin-Food-Safety.pdf | The ICR presented positive and negative lessons as well as recommendations. This Review hashighlighted the followinglessons (with some editing) because they were potentially relevant to other World Bank operations. :1. Aconducive and supportive legislation and policy environment is key to the successful implementation and sustainability of projectinterventions and innovations (ICR, paragraph 3).As this Review has noted, a law on product quality and safetywas issued in 2006, followed by an upgrading in 2009 and another law in 2015. Experience from the project may have served as atesting ground influencing the drafting of the 2015 law. By the time the project was approved, food quality and safety werereceiving increasing priority in budgeting and planning and Government support for this project was strong. The lesson isthat projects aimed at major changes in strategy need a clear legal and policy support to besuccessful.2.. Significant Turnover of task team leaders and other key staff isdisruptive.The project had three task team leaders (TTLs) during supervision. (ICR, Section 8b, and ICR para53). The turnover of TTLs and other key staff impeded decision making, slowed implementation and consequently negativelyaffected the quality of Bank support to the Government and the implementing agency. The lesson, while not new bearsrepeating: changes in TTLs and other key supervision staff during project implementation are usually highly detrimental to projectperformance.3. Establishing a produce quality and safety program takes time, iterative testing, andsignificant learning. The time needed for this, or the scope of the project, is best factored in during projectdesign.The project implementation period of seven years (including the extra year extension) was relatively short forthe intended project scope and complexity (ICR, Sections 4 and 8, ICR para 82, and Borrower comments at ICR, Annex 5.). Thelesson is that a reduced and more simple project scope and/or a follow-on project, while less ambitious, can be a more attainableprogram4. Procurement capability for project staff is a key driver for the pace and quality of projectpreparation.The projects primary implementation constraint was the limited skills of the project procurementstaff. Training in procurement for such staff, and appointment of a senior level procurement manager would have helped reducethis difficulty (ICR, Section 9b, and ICR paras 85, 49 and 73). The lesson is that knowledge of Bank procurement guidelinesby staff in implementing agencies is critical to the success of most Bank-financed projects.IEG has drawn the followinglesson from this project:Successful implementation of a pioneering and complex project can besignificantly bolstered through a team of competent specialists.Project preparation involved 11 staff or consultantin different specialistfields. Of these, eight were technical specialists in food safety and quality and the rest coveredenvironment, social, economics and finance (ICR, Section 8a).
P101724 | Vietnam Poverty Reduction Support Credit 6 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2009 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/469551474895234248/text/000020051-20140626112326.txt | http://documents.worldbank.org/curated/en/469551474895234248/pdf/000020051-20140626112326.pdf | Lessons from the ICR are supported, in particular that donor coordination can strengthen the policy dialogue and deliver benefits to the client. A PRSC series can serve as an effective framework for policy dialogue and interactions between the government and donors. The benefits can be fundamental and manifold, as supported by a number of outside evaluations. PRSCs can be the â€œone-stop shopâ€ of the policy dialogue, supplemented by sector/thematic DPLs as reform dialogue deepens, and hence raised to a more senior level of government attention than any individual sector effort would have. The role of co-financiers under the PRSC can evolve over time from providers of financing to partners engaged in the preparation of the operations and the policy dialogue with the government. Information flows from the government will expand as trust with the Bank and other partners deepens. This coordination also greatly reduces the transaction costs for the government ministries and agencies (ICR, p. 34).Another lesson is that an incomplete causal chain can lead to difficulty in evaluating the effectiveness of an operation or series in achieving its objectives. When prior actions and targets are directly linked to target outcomes from a PRSC series, there will be a clearer link between the series and the achievement of objectives.Other lessons include the importance of continuity in task team leader (TTL) -- PRSCs 7-10 had the same TTL, and the value of combining policy operations with parallel technical assistance to allow for necessary capacity building. When a government has a sound medium term framework and the program supported by a policy operation is ambitious and broad, a longer series may offer the opportunity to achieve results sought and the flexibility to redirect actions based on experience. In addition, countries facing particularly difficult sectoral challenges should consider a sectoral policy operation to supplement a broader policy operation, allowing more extensive consideration and support to the most difficult issues.
P101724 | Vietnam Poverty Reduction Support Credit 6 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2009 | 2015 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/721331467986245693/text/96203-PPAR-REVISED-PUBLIC-VIETNAM-PPAR-FINAL.txt | http://documents.worldbank.org/curated/en/721331467986245693/pdf/96203-PPAR-REVISED-PUBLIC-VIETNAM-PPAR-FINAL.pdf | 6. Conclusions and Lessons Learnt Conclusions 6.1 This review presented an overview of Vietnam's economic and social performance. It assessed the extent to which World Bank DPOs during 2007-12 contributed to its achievements and their sustainability. The main conclusion that emerges from the historical overview is that the country's growth performance during the 1990s and until the mid-2000s was very strong. Effective poverty alleviation also took place during that period, and has been sustained since. This was thanks to transformative measures (especially land reform, enterprise reform and WTO accession) that were taken by Government during the first half of the 2000s (in turn building on earlier reforms) with substantial development partner advice and support, which was generally led by the Bank. 6.2 However, during the period under review (2006-2013) the next generation of transformative reforms (notably as highlighted in the 2007 and 2009 VDRs) were either postponed or diluted, and were thus less effective. Areas such as SOE and financial sector reform, more efficient public investments, anti-corruption, and more effective environmental policies, received insufficient attention. Over the same period, Vietnam departed from the prudent macro-fiscal stance that characterized it in the 1990s early 2000s. 6.3 Past reforms continue to drive strong FDI and buoyant exports. Vietnam can build on these strengths to avoid further loss of growth momentum. This could be based on the implementation select transformative reforms aimed at strengthening the role of the private sector, facilitating the emergence of mediumto large domestic enterprises, and sustainably expanding infrastructure in an efficient manner. The progressive elimination of the stock of contingent liabilities and reducing other risks to the sustainability of fiscal policy would create a more stable macroeconomic environment. One of Vietnam's strengths lies in its social compact, the main elements of which should be maintained, while progressively evolving towards a less paternalistic approach based on stakeholder empowerment. 6.4 The Bank and other development partners can help the country address these priorities through more selective budget support instruments. This is indeed envisaged in the Country Partnership Strategy (2012-16). The 2016-2020 SEDP also provides an opportunity to generate political consensus around these issues in the context of an increasingly complex economy. 6.5 The Bank should be more willing to cease supporting programs should they become so weakened as to make it likely that key objectives would not be achieved. Technical and policy dialogue would be maintained. In this context, high caliber knowledge products will need to continue being prepared, and the relationship of trust that supports frank dialogue with Government needs to be reinforced. Harmonization with all key stakeholders, external and internal, will be important. Strong commitment to deeper reforms would help to sustain Vietnam's economic performance while addressing the challenges of an increasingly complex, middle-income economy, and deepening global integration. Lessons from the Bank's macroeconomic engagement through DPOs. 6.6 The model of the Bank's engagement in macroeconomic and fiscal policies through DPOs in Vietnam since 2007 has not been effective. An important finding emerging from this PPAR is that, while diagnosis of macroeconomic risks was adequate, this was not reflected in program design, despite a highly volatile environment exacerbated by sub-optimal policy choices. This situation was, moreover, aggravated by the lack of an IMF program and the relative weakness of macroeconomic policy dialogue between the Government and the Bretton Woods Institutions. The Bank may have been exposed to reputational risks if its policy lending had been seen as a de-facto endorsement of controversial macro policies. DPOs following those reviewed in this PPAR are still not underpinned by relevant macro policy content, although macroeconomic risks persist. This indicates that the lessons learned during the 2007-2013 period do not appear to have been fully learned. 6.7 Macroeconomic dialogue could advantageously be consolidated in a presence of multiple parallel DPOs. The fragmentation of policy lending into multiple DPOs implemented in parallel in Vietnam during the period of increased macro risks might have weakened Bank's focus on macro framework and even resulted in inconsistencies in policy dialogue. The Bank should have avoided situations when preparation of one operation is held back for concerns over the macro-framework while a parallel DPO is approved and disbursed in the same macro environment. To avoid the repetition of such a situation, there should be a unique and consistent approach towards assessing the adequacy of macroeconomic underpinning of DPOs. When substantial risks are present, policies underpinning the most suitable, in terms of scope and objectives, budget support operation should be reoriented to alleviate them. 6.8 Combining the objectives of external financing for crisis response and promotion of long-standing institutional reforms may not be effective in cases where risks to nonimplementation of reforms are high. The Bank's experience with the Vietnam PIR series indicates that, when financing needs are urgent, it will find itself under pressure to go ahead with disbursements even if the reform implementation is not satisfactory. Crisis response operations should first of all focus on ensuring the sustainability of macro and fiscal framework, and should be underpinned by critical macro, fiscal and structural actions, especially in cases when the IMF is not present operationally. Lessons Learnt â€“ Results and M&E Framework 6.9 Wide-ranging DPOs need to be based on stronger and better quality actions. The importance of each individual prior action increases in multi-sectoral operations with many policy areas because of the implicit limit on the number of total prior actions for operational purposes. If in a series of five operations, for example, each policy area can have a maximum of two or three prior actions in the course of five to six years it is important to ensure that those prior actions have sufficient institutional depth, relevance and criticality. Related to this, in multi-sectoral complex operations there might be no substitutability between the prior actions of unrelated policy areas, which means that weaknesses of prior actions in one sector cannot be offset by relevant and critical prior actions in another sector. 6.10 Lack of focus on and delays in implement essential triggers can weaken the program. In terms of indicative triggers, the Bank has flexibility and discretion in its treatment of the triggers. The transition from Bank's former conditionality framework to the model applied in the series reviewed in this PPAR puts a high premium on sequencing the reforms and ensuring continuity, thus giving considerable significance to the role of triggers for the operations and the overall reform program. Dropping a trigger should be considered as an exceptional event, rather than a regular occurrence, permissible only if the risks to nonimplementation of reforms are duly addressed. 6.11 Partially met triggers require greater attention. Sometimes partially met triggers become prior actions even though they may be less relevant and critical than the originally proposed action. The dilution of content may be to such an extent that these actions would probably not have been considered as prior actions if proposed at the outset. The Bank should pay special attention to possible risks in adopting partially met triggers as prior actions, especially when there is not any realistic expectation that the full original reform will not implemented in a reasonable timetable thereafter. 6.12 It is crucial to have a strong knowledge base for upstream design of reforms and parallel technical assistance to support their implementation. Development partners were willing to put significant resources in these areas, in order to complement Bank financing and dialogue (Vietnam, prefers not to borrow, even on concessional terms, for TA). Selectivity is therefore needed to ensure that the most pressing needs are addressed. Should unmet demand remain, this may be tackled through complementary Bank TA operations, for instance in support of reform teams.151 However, these operations need to be carefully designed in order to match the timing and sequencing needs of DPOs (an issue that arose in the case of P135), and to ensure that the bulk of resources is allocated to meet specific implementation requirements, as opposed to general capacity building (such as purchase of vehicles and equipment, and training). Furthermore, this approach calls for outsourcing knowledge generation and advice to an appropriate mix of experts, both national and international, who can accompany the reforms in medium-term.152 6.13 The design and implementation of M&E for DPOs remains a challenge, and needs to be reconsidered each time a new operation is considered within a series. The PD.153 for the second PIR mentions a lesson learnt elsewhere, whereby an effective M&E mechanism should not just be based on administrative reporting. However, both the PIR and the PRSC suffer from this issue as M&E is not used as a mechanism for feedback and readjustment of activities to improve impact. The P135 is more successful in this area 151 FIAS 2008\. Reform Teams How the Most Successful Reformers Organized Themselves Reform teams consist of a small group of national experts who together with world-class expertise help Governments implement ambitious reforms. 152 In order to achieve such continuity, the experts' contracts may be based on a retainer model. Sorter procurement may also be achieved through framework contracts, whereby a short-list of competitively prequalified consortia/firms expected activities are called upon to provide experts within short delays of 2-4 weeks. The EU has successfully implemented this approach. 153 para. 71 124 because the mid-term review provided a venue for reassessing the implementation of the program. Even there, the change in PRSC indicators took place only for the last operation, although it had become clear much earlier that the relaxation of policy actions required an adjustment in indicators and goals. In both the PRSC and the PIR series there is a disconnect between development objectives, actions and indicators. In the case of the PRSC, there was a logical chain between objectives and indicators, but it is hard to see how some of the reforms would lead to the intended results (the attribution issue). The issue with the PIR is that while there is strong relationship between the reforms and results, their logical link to the development objectives is weak, especially after key reforms were dropped. Lessons Learnt â€“ Bank Approach 6.14 There is a need to reexamine how the Bank approaches sectoral DPOs and how this instrument is differentiated from investment lending. In Vietnam, the distinction between DPOs and investment loans has become blurred, especially with the practice of earmarking funding for the sector the programs support. It can be argued that the four sectoral DPOs might have been best supported by SWAPs and investment lending. The advantage of DPOs is that they disburse rapidly, support to the consolidate budget, and in practice promotes the use of national fiduciary and safeguards systems. However, this approach limits Bank inputs (say on a key study) on the ultimate use of the resources and their underlying processes. To avoid sharp trade-offs that may discourage the use of the most appropriate lending instrument, it seems that in the case of investment lending, it may be desirable to experiment, at least on pilot basis, with further harmonization/convergence between Bank fiduciary and safeguard procedures and national ones. 6.15 The Bank and other development partners should be willing to walk away from an unproductive policy dialogue and withdraw their support of low impact reforms. The delays in P135 (second operation), the second PIR operation and PRSC 10 appear to have been caused by concerns with the quality of the program. In the case of P135, the mid-term review largely addressed the main concerns. However, the last operations in both PIR and PRSC series cannot be readily justified by the contribution to objectives of the weak reform they supported. 6.16 The Bank's recent guideline that suggest to limit the number of operations in a series to three constitutes an appropriate measure. Long-term DPO series need to be kept relevant by maintaining a high level of ambition with respect to the reforms they support. As evidenced by the second PRSC series, a longer-term approach may be hard to sustain. 6.17 Knowledge generated and/or embodied in Bank operations should be properly documented and made public. Bank disclosure policy call for documents it produces being made public, unless classified as confidential. Furthermore, to the extent possible, documents on which policies are based should be easily identifiable and retrieved. In order to preserve knowledge and improve transparency, PDs should properly refer to studies (in some cases the title cited was incorrect) and provide URL links. There is also a question whether disclosure policy is strictly respected (e.g., some energy studies do not appear to have been made public). 125 6.18 It is difficult to evaluate the performance of DPOs in Vietnam without the benefit of a clear reference on what constitutes the norm. This review identifies strengths and weaknesses in the Vietnam DPOs by referencing their own internal logic. However, it is unable to systematically address questions such as how did the Vietnam second PRSC series compared to other PRSCs in terms of ambition, design, results etc. This may result in inconsistency in ratings across countries and projects (ratings contain a subjective element based on the skills, experience and perception of the evaluation team, as well other factors). This issue seems to argue in favor of a new meta-evaluation154 of completed PPARs on similar DPOs, with lessons learnt and recommendations on a more consistent cross-country approach to be reflected in future individual operation evaluations and/or PPARs. Specific Lessons Learnt from P135 6.19 Budget support may not be the best instrument for financing a sector investment program. While a budgetary support operation for a CDD-type program turned out to be moderately satisfactory in the case of Vietnam, the Bank and other development partners had taken a considerable risk. For most countries, it would be highly advisable that the training, at least of the critical personnel (which in a highly decentralized program means a very large number of people), would be done in advance and that an M&E system were in place at the start of the program. There was much retro-fitting under the P135 series that could have been avoided. 6.20 The state of decentralization needs to be fully factored into the design and implementation of targeted poverty programs. Decentralization of government institutions and introducing greater participation at the commune and village levels was an objective of the program as a tool to empower the targeted communities. Various monitoring indicators were used to measure progress on this front. But they did not provide an idea of what would have been good practice in terms of an optimal level of decentralization and participation given the stage of development. An alternative approach could have been to select a control group of provinces that had been decentralizing on their own and could serve as a comparison group for the provinces attempting to develop decentralized structures under P135. That could have enabled the selection of a group of indicators to be used for measuring success before the start of the operation 6.21 Production support to poor communities needs to be tailor-made and well thought through. Much was made of expanding the production component of the program. But the targeted communities were seriously underdeveloped for good reasons. They were remote, mostly mountainous, often forested, and inhabited by people who have eked out livings in these places for centuries. Such places are notoriously difficult to develop and there are few success stories around the world to give guidance. Packages that had worked in other parts of Vietnam (typically used in the more hospitable lowlands) were not likely to be relevant, and subsidies are not sustainable in the long run. This portion of the program could have been better thought through and explored through a series of pilot projects rather than being a part of a budget support operation. See IEG 2010 for an evaluation of PRSCs based on operations completed and evaluated by 2008. 6.22 Good analytical work, economic and other, contributes to success. Populous countries with large externally financed programs, such as Vietnam, are likely to benefit from an amount and variety of analytical work, typically using standard economic tools. Smaller countries with more modest analytical programs can probably learn useful things from a selective reading of the analytical work performed in more abundantly staffed countries. But Vietnam also profits from relevant non-economic analytical work that illuminates the likely behavior of the people involved both at the highest levels as well as at the village level in a way that informs the design of the programs. This sort of work is important but by its nature country specific.155 6.23 Well-designed impact evaluations are a valuable dimension of M&E. The impact evaluation turned out to be very important in assessing the impact of P135, not only regarding poverty but also non-income components of welfare, participation, decentralization and empowerment. This has direct relevance to other National Targeted Programs in Vietnam and elsewhere. It is important that funding of such activities be included in the original project design as their late inclusion may lead to implementation difficulties. 6.24 Vietnam's social compact was instrumental in supporting certain achievements, but may not be readily replicable elsewhere. Vietnam's reforms have relied on a top-down approach, which nevertheless draws in various stakeholders into the program and strengthens their ownership and voice. This is notably the case for targeted programs such as P135. While the country's history and social compact are quite specific, there are generic elements, such as effective engagement of local political authorities and communities that may be useful elsewhere. An example was Martin Rama's Making Difficult Choices\. Vietnam in Transition (2008). For behavioral implications at the village level the best example would be Edwin Shanks et al CDD in Vietnam (2003).
P101745 | DEMOCRATIC REPUBLIC OF CONGO - High Priority Reopening and Maintenance Project | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2008 | 2020 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099215003012232086/text/Congo00Democra0pening000Maintenance.txt | http://documents.worldbank.org/curated/en/099215003012232086/pdf/Congo00Democra0pening000Maintenance.pdf | The ICR draws the following four lessons from the experience of implementing this project, with some adaptation oflanguage.1. Community-based Grievance Redressal Mechanisms (GRMs) should be establishedat an early stage ofimplementation. This project had an under-resourced GRM in place before the suspension of the loan. Akeylesson from this project is that simple, realistic and community-based GRMs should be in place and operational before the start ofworks, especially for projects in large areas of intervention in rural areas or with security issues.2. Specifictraining is required while using military staff for the protection of project staff and worksites. The use of militarypersonnel to ensure security of project staff in this project highlighted the need to develop a formalized partnership with MONUSCO(the United Nations Organization Stabilization Mission in the DRC. The partnership with MONUSCO aided in training the militarypersonnel assigned to protect the road worksites basedon humanitarian law, with training funded by theproject.3.Capacity building activities needs to a core project component in post-conflict and fragileenvironments. Given the country context at appraisal with post-conflict period and governance issues, this projecteventually completed most of its planned activities. This was mainly due to the relatively simple design, identifyingweaknesses in institutional arrangements, and providing a large component substantially funded with technical assistance activitiesaimed at building capacity of the respective road agencies.4. Strengthening the local construction industryis important in post-conflict settings. This project at an early stage identified the need for strengthening the localconstruction industry, which had been devastated due to themany years of conflict. The project included several technicalassistance activities for the Small and Medium sized enterprises through workshops, hands-on-training and worksite visits thatbenefitted the project, as well as another project in the urban sector.
P101750 | Lao PDR Customs and Trade Facilitation Project | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2008 | 2017 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/817781518713237920/text/ICRR-Disclosable-P101750-02-15-2018-1518714128057.txt | http://documents.worldbank.org/curated/en/817781518713237920/pdf/ICRR-Disclosable-P101750-02-15-2018-1518714128057.pdf | The ICR draws the following main lessons, which IEG supports, from the experience of implementing thisproject:(1) Political commitment and client ownership may benecessary butnotsufficient for successful project implementation. In the case of this project, the Laos customsdepartment performed much better in implementing activities associated with customs automation but was less successful inimplementing activities associated with customs modernization and reforms which were hampered by procurement delays on the IT side.While the former activities were standardized, required external support and were less complex, the latter set of activitiesrequired a range of complex regulations and procedures that required internal support from customs. The experience of this projectshowed that in addition to adequate project supervision, hands on support for institutional support may be required for ensuringproject success.(2) In-country supervision may aid in relatively complex customs reform programs. Theimplementation of this project was aided significantly from intensive supervision by the Bank team who were based in-country.(3) Regulatory and institutional reforms can be more successful when there are strong pressures andcommitments to be met for regional and international trade integration. Lessons learnt from this project demonstrated thatany reform priority that was linked to international commitments such as the WTO Accession may get political and managerial supportfor action.(4) In a low capacity environment, capacity gaps and training activities need to be identified early todrive the pace of project implementation. The implementation of this project could have been expedited in the early yearsthrough anearly gap assessmentidentifying a priority plan and plan aimed at sequencing of activities with a stafftraining plan.
P101785 | Aceh Infrastructure Reconstruction Financing Facility (IRFF) | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2007 | 2013 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/798891475111726628/text/000020051-20140626111033.txt | http://documents.worldbank.org/curated/en/798891475111726628/pdf/000020051-20140626111033.pdf | In a project responding to a major disaster with multiple donors and stakeholders, project design should be kept as simple as possible to accommodate weak local capacity and consideration should be given to a two pronged approach; the first to finance the infrastructure sub-projects, and the second to fund capacity building. Ideally there should also be a supporting donor local coordination office.When local government administrations with limited capacity are involved, it is essential to ensure they are able to take responsibility, as far as possible, to manage their assets, and to help them mobilize sufficient financial resources in their administrations for the funding of essential maintenance activities for the new infrastructure established.Construction Environment Action Plan (CEAP) implementation could be improved in a number of ways. The training of contractors in CEAP implementation is an important step in getting CEAPs adopted more readily. MOUs for asset transfers from the implementing agency to local governments should include environmental maintenance.
P101829 | Xining Flood and Watershed Management | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2009 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/850401485476365370/text/ICRR-Disclosable-P101829-01-26-2017-1485476350340.txt | http://documents.worldbank.org/curated/en/850401485476365370/pdf/ICRR-Disclosable-P101829-01-26-2017-1485476350340.pdf | Lessons drawn from the ICR (page 20), adapted by IEG: Amix of engineering (infrastructural)andnon-engineering (conservative techniques) measures comprised a well-balanced mix of flood management interventions. Thepromotion of conservative techniques helped to address root causes of soil erosion, while modern equipment and structures helped tosafeguard property during actual flood events.Also, A strong focus on OM arrangements ensuredsmooth post-project transition.This includes financing of OM costs and capacitydevelopment to ensuretechnical and institutional capacity for OM,
P101852 | Health Insurance Project | Western and Central Africa | Ghana | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2008 | 2014 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/971801475113559479/text/000020051-20150312114724.txt | http://documents.worldbank.org/curated/en/971801475113559479/pdf/000020051-20150312114724.pdf | Lessons drawn from the ICR (pp. 22-24) and adapted by IEG:Reality checks on the feasibility of M&E design need to be conducted regularly. In this case, the team missed an opportunity to update the M&E design comprehensively to add indicators for financial management and revise target values. This would have been particularly important given the fact that the NHIS reported annual deficits.Fiduciary aspects need special capacity building. Considering that the implementing agency was a newly created agency, increased support to fiduciary aspects should have been planned from the beginning. The government's ICR (pp. 48-49) provides additional important lessons, including the need to better train and prepare health care providers before capitation payment is introduced, and the need for clearly identifying the roles and responsibilities in the implementation agency. In addition, IEG identifies the following lesson:Bank support to health insurance should be comprehensive and not focus just on operational aspects of insurance. In this case, the project did not give adequate attention to the increasingly difficult financial situation of the fund. Considering that the fund had been running a deficit since 2009, earlier financial projections should have proposed cost containment measures (such as the capitation payment reform) that needed to be implemented at the onset.
P101912 | SD - Livestock and Fisheries Development Project - MDTF | Eastern and Southern Africa | South Sudan | IDA | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2007 | 2011 | 2014 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/123671474497194299/text/000020051-20140625074546.txt | http://documents.worldbank.org/curated/en/123671474497194299/pdf/000020051-20140625074546.pdf | Lessons are derived from IEG's work in Fragile and Conflict States (Lessons 1) and from lessons learned and reported in the ICR (Lessons 3 and 4) with some adjustment of the wording. In fragile and post-conflict settings, development assistance should be flexible, objectives should be realistic, and projects should be designed in a manner that allows them to adapt to changing circumstances. Results frameworks should be aligned with identified projects risks. In the case of countries emerging from conflict and those with nascent institutions, conditions for implementing projects should be kept to a bare minimum as they will have difficulties in fulfilling them in time risking project failure. In the case of difficulties in meeting some of the conditions by such countries, consideration should be given by the Bank to reviewing them and granting waivers, provided that these do not jeopardize the projectâ€™s outcome. The case for integrating business opportunities and business development in service delivery to enhance sector performance and support sustainability of the system should be considered in the conceptual design stages of service delivery projects even in post conflict and fragile environments. While training and equipping community animal health workers is an important step in creating a timely disease surveillance and treatment system, service providers require access to a sustainable and affordable source of vaccines and treatments. The private supply chain model that was developed under this project could develop into a sustainable model for expanding private veterinary services in the future in South Sudan. It may offer lessons for setting up service delivery models elsewhere.
P101928 | Health Sector Technology Transfer and Institutional Reform | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2008 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/535981524748955293/text/Kazakhstan-HLTH-SEC-TECH-JERP.txt | http://documents.worldbank.org/curated/en/535981524748955293/pdf/Kazakhstan-HLTH-SEC-TECH-JERP.pdf | The ICR offers six key lessons, including the need for government commitment and consistency between a project and governmentreform plans; the importance of capacity-building for successive implementation of sequenced government reform programs; the roleof careful project management during complex reforms; the utility of twinning arrangements for strengthening capacity of localpartners; the need to be attentive to continuation of institutional capacity developed under the project; and the importance ofmonitoring and evaluating progress in implementing new technologies and tools, especially clinical protocols. IEG concurswith these lessons, adding the following:A clear and outcome-oriented statement of project objectives iscentral to effective monitoring and evaluation of results. In this case, assessment was complicated by the lack ofinformation about the country health reform strategyreferenced inthe development objective, and by the projectdocuments interpretation of results in terms of outputs rather than outcomes.When coupled withadequate monitoring, review of lessons learned, and communication of achievements to key stakeholders in non-pilot areas,pilots can not only pave the way for reform but also change the mindset of those who may have opposed reforms. In thiscase,effective implementation ofpilots of diagnosis-related groups, quality management systems, accreditationstandards, disease management programs, and medical education helped to generate demand for country-widereform.Membership in international professional and accrediting bodies can be akey incentive forinstitutional reform. In this case, the opportunity to join international associations both enabled and motivated theacquisition of new knowledge and adoption of best practices in key areas.
P101955 | Improving Livestock Production and Marketing Project - A Pilot | Eastern and Southern Africa | Sudan | IDA | FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2008 | 2013 | 2015 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/734471475117096595/text/000012394-20150108122906.txt | http://documents.worldbank.org/curated/en/734471475117096595/pdf/000012394-20150108122906.pdf | The following two lessons from the ICR are emphasized:Working in conflict-affected settings requires proactive supervision and â€˜contingent thinkingâ€™ during project implementation. In a country affected by conflict, supervision cannot be limited to routine follow up, but requires heightened proactivity in anticipating bottlenecks and adjusting accordingly. Relatively minor change in output targets followed some supervision missions, and required a whole level-2 restructuring process, which included drafting the relevant restructuring paper. For similar cases, a mechanism should be explored to provide project teams with enough flexibility to evaluate the context and reallocate funding towards more secure and â€˜contingentâ€™ areas, in case conflicts arise. Such mechanisms would build upon a set of â€˜contingent targeting areasâ€™ to be defined ahead or during project implementation.The use of an independent monitoring agent (MA) in conflict-affected environments is instrumental to provide monitoring services and on-the-job capacity building. The MA was a third-party agent hired to monitor the implementation of the MDTF-NS including this project. The MA played an important monitoring and capacity development role, providing training and on-the-job assistance to the PIU staff and through use of other World Bank training activities. This type of additional partner monitoring and implementation support is quite relevant to countries like Sudan, where fiduciary assessment was lacking during the preparation of the project. If costs associated with an MA are kept manageable, this modality of third party monitoring can be designed in a way that generates economies of scale to include other projects.
P101964 | National Program Support for Tax Administration Reform. | East Asia and Pacific | Philippines | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2007 | 2013 | 2015 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/585361475116607081/text/000012394-20150309075914.txt | http://documents.worldbank.org/curated/en/585361475116607081/pdf/000012394-20150309075914.pdf | IEG draws the following key lessons from this Review:Projects for administrative reform need up-front, accurate assessments of government and institutional ownership for reforms, which were not available for this project.Projects seeking institutional reforms through â€œtechnicalâ€ routes â€“ through technical assistance and IT components â€“may find it difficult to achieve results in the absence of sufficient ownership at the top, which was the case for much of the project period for this project.It is important for strong M&E systems to make sure that baselines for the indicators are available up front and that the indicators can actually be collected during project implementation, which turned out not to be the case for a number of the indicators for this project.
P101988 | Jiangxi Shihutang Navigation and Hydropower Complex Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2009 | 2014 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/149201468188929366/text/ICRR14711-P101988-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/149201468188929366/pdf/ICRR14711-P101988-Box393183B-PUBLIC.pdf | A number of lessons are selected from a longer list identified by the ICR, with some adaptation of the language, as follows:In inland waterway transport development, ship lock development can be combined with hydropower station. The revenue from power generation can provide financial support for the operations and maintenance of a ship lock. Free use of the ship lock in the project province in China was expected to attract more low value commodities to IWT from other transport modes.Need for design flexibility to address unanticipated land acquisition and resettlement issues. Preparation of a RAP acceptable to the Bank is an important, but not sufficient condition for successful project implementation. Project design should be flexible to allow for unanticipated land acquisition and resettlement issues, as was the case with the difficulties in land acquisition for the Donggang diversion canal under this project.The inter-related development initiatives that could have an impact on the project's outcome should be carefully assessed at design. Under this project, the impact of the construction of the Xiajiang complex located 90km downstream from the project area affected the end-of-project achievements.
P102000 | Transport Sector Project | Western and Central Africa | Ghana | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2009 | 2019 | 2020 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/627911576854552812/text/Ghana-GH-Transport-Project-SIL-FY09.txt | http://documents.worldbank.org/curated/en/627911576854552812/pdf/Ghana-GH-Transport-Project-SIL-FY09.pdf | The following lessons have mostly beenderived and summarized from the ICR:Agencies familiar with WorldBank policies and procedures can help build thiscapacity in other agencies by supporting them.A comprehensiveapproach to inter-agency coordination in the transport sector in Ghana showedthat agencies that have worked with World Bankpolicies and procedures can successfully support other agencieswith little knowledge ofsuchpractices.Rigorousproject preparation canreducethe number of challenges facedduring implementation. The issues that delayed the project (very commonly found throughout the region), such as costoverruns, faster than expected traffic growth, and non-timely delivery of compensation to project affected persons, deserved moreattention prior to project approval.The early involvement in the project of all resettlement-related stakeholdersis important when the project requires resettlement. In this project, which required involuntary resettlement,theLand Valuation Division was not involvedat an early stage. This delayedpayment to affected people and projectimplementation. In addition, to involving the Land Valuation Division early, compensation funds shouldbe kept in an ESCROWaccount until needed. A National Resettlement Law would also bringclarity to the existing legal frameworkand strengthenprotection of affected persons rights.Where there are weaknesses in financial managementand procurement systems, additional training may berequired. Under this project, the financial management systemswere not used effectively and the quality and timeliness of financial reportinghad shortcomings.In addition totraining, whileexisting systems and procedures are being improved, there may be opportunitiestoreduce delays bypaying contractors directly, thus avoidingcumbersome in-house approval procedures of invoices and certificates.
P102018 | DPL | Europe and Central Asia | Romania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2010 | 2013 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/150451474555312380/text/000020051-20140625223916.txt | http://documents.worldbank.org/curated/en/150451474555312380/pdf/000020051-20140625223916.pdf | There are three main lessons that can be drawn from the experience of this DPL series:The Bankâ€™s ability to coordinate the design and supervision of its interventions with other key financiers, and to keep a constant dialogue with legislators and other stakeholders is essential to maximize impact and ensure sustainability of reforms, particularly if the latter are long overdue. Dialogue with the opposition is particularly crucial in this respect.The Bankâ€™s ability to assess progress in an independent fashion and demand compliance with agreed policy changes is the foundation of its credibility, particularly in front of the Borrowerâ€™s public opinion. This ability requires a solid analytical capacity, excellent knowledge of the local political economy, ability to withstand pressure to disburse, and willingness to discuss issues with and outside government.Political commitment to reform is crucial and needs to be broad based. The overall reform agenda under extremely difficult circumstances needs to have some degree of support from the opposition, as governments are often short lived during such periods. The Bank can help through dialogue, but without some common ground between government and opposition the risk of policy reversals may be too high.
P102029 | Nigeria Lagos Urban Transport Project | Western and Central Africa | Nigeria | Blend | Non-FCS | Infrastructure | Transport | IDA | IPF | 2007 | 2011 | 2016 | PPAR |  | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/410431469427889576/text/103068-ppa-P074963-PUBLIC-IEG-r-nigeria-0716.txt | http://documents.worldbank.org/curated/en/410431469427889576/pdf/103068-ppa-P074963-PUBLIC-IEG-r-nigeria-0716.pdf | 6. Lessons 6.1 Several lessons are drawn from this assessment, some based on the ICR and others from IEG's own analysis\. Setting up a strong institutional basis for coordinated planning and regulation is critical to the success of urban transport projects. However, such changes take time and need to be supported by strong commitment from top officials and politicians to ensure the integrity of governance changes as in the case of the establishment of LAMATA. Supporting legislation is essential and the roles and responsibilities of all transport entities affected need to be worked through. The recruitment of experienced international staff enabled the creation of a strong authority and the ability to move beyond the project and begin to implement an ambitious reform agenda. The challenges facing cities with respect to urban transport and its governance are of long duration and not quickly fixed. The Bank had its first intervention in the city with the Lagos Urban Transport Project, followed by the second Lagos Urban Transport Project, this continuous engagement by the Bank is a compelling requirement to sustain progress in urban transport sector. It should also be noted that urban transport projects require longer periods for implementationâ€”seven years or longer when many authorities are involved. Critical to the success of the project was steady progress with the institutional reforms and the establishment of a transport fund, which contributed to the positive outcome by improving financial sustainability. The team targeted the right priorities in a comprehensive capacity building program and ensured that the necessary preparations and commitments were made to establish a sustainable transport fund. However, while financial self-sufficiency for institutions is an important longterm goal, it may take longer to achieve than has been previously recognized. World Bank supervision teams need flexibility and the ability to adjust the project to take advantage of opportunities that may arise. In this case, the enthusiasm of the politicians in the State of Lagos to pursue the BRT project presented such an opportunity, and the team was able to use windfall funding to help the pilot BRT project to become a reality by financing the design and related costs and in providing technical advice from the World Bank's global experience. The concept of BRT was adapted to the African context so that it was more affordable to the poor in Lagos. Observing the experience of other countries or cities where new public transport concepts have worked successfully can convince local stakeholders to adopt a new approach. In this case it convinced key stakeholders, including the trade unions, to agree to adopt the franchising and BRT concepts locally. That said, the integration of existing operators into new bus franchise services without fundamental transformation of business models underlying those services is at best a transitional strategy and not sustainable in the long run.
P102031 | MR - Business Environment Enhancement Project | Western and Central Africa | Mauritania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2008 | 2015 | 2016 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/567191468271547241/text/ICRR-Disclosable-P102031-06-12-2016-1465788991542.txt | http://documents.worldbank.org/curated/en/567191468271547241/pdf/ICRR-Disclosable-P102031-06-12-2016-1465788991542.pdf | The ICR (p. 24) includes several lessons including: Establishing a good project implementingunit(PIU), whichhas the governments support, is critical for successful implementation. In this project, however,the government did not want to create a new PIU. Nonetheless, the twoagencies selected by thegovernmenttomanage the project were dissolved and the PIUthat was eventually created had difficulty in recruiting a well-qualified PIUcoordinator. This led to significant delays in project implementation. Selecting indicators that areexternally validated and consistentis essentialfor monitoring progress towards the projects objectives. However,it is imperative that the project is capable of contributing to the outcomes measured by these indicators. This projectrelied on good indicatorsfrom the Doing Business report. But there was a disconnect between theseindicators and the activities supported by the project.
P102040 | Second Government Reform & Growth Credit | Western and Central Africa | Sierra Leone | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2009 | 2013 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/866571474631897892/text/000020051-20140625155055.txt | http://documents.worldbank.org/curated/en/866571474631897892/pdf/000020051-20140625155055.pdf | The following lessons are drawn from the ICR and considered especially important by IEG:1. Embedding policy reforms in the Governmentâ€™s reform agenda instills greater government ownership of the program, diminishing the risk of delays or shortcomings in achieving objectives.2. In a country short of management capacity, a detailed M&E framework is not likely to be sustainable without intensive donor inputs and supervision.3. The consistency in team leadership of supervision (as was the case in all three GRG operations) from appraisal of the initial operation and though completion can have a strong positive role in program performance.
P102095 | Natural Gas Distribution for Low Income Families in the Caribbean Coast. | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2006 | 2008 | 2010 | ICRR | Less than 10 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/624671474852220924/text/000146597-20140619153232.txt | http://documents.worldbank.org/curated/en/624671474852220924/pdf/000146597-20140619153232.pdf | 1. The project has once more demonstrated the potential for output based aid (OBA) as a means of delivering infrastructure services through the private sector to lower income consumers, provided the appropriate institutions are in place and operating satisfactorily. 2. Where OBA is feasible, the project also demonstrates its advantages as against alternative delivery mechanisms, for example through a government grant. These include greater transparency, greater commitment on the part of beneficiaries (who must show their willingness to make a financial contribution themselves), incentives for efficiency through a predetermined subsidy, shifting performance risk to the provider, and facilitation of M&E.3. The project benefited from targeting areas which already had access to natural gas and where many households who could afford it were already connected, thus avoiding the need for heavy infrastructure investments and benefitting from a demonstration effect. 4. Other things being equal, there are advantages in employing an audit firm for financial monitoring and project verification purposes which is already familiar with the operations of the grant recipient and the implementing companies. This was of benefit in this case.
P102117 | Second Education Sector Development Project | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2008 | 2016 | 2017 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/260051497975564590/text/Azerbaijan-EDUC-SECT-DEVT-2.txt | http://documents.worldbank.org/curated/en/260051497975564590/pdf/Azerbaijan-EDUC-SECT-DEVT-2.pdf | The ICR (pp. 20-21)suggests severallessons learned: Long-term programs like an APLseries can benefit from long-term objectives and measuring the progress towards these objectives. This project could have benefitedfrom tracking learning achievements from the beginning of APL1. In a long-term program, timely flexibility to makeadjustments when necessary is important for both the Bank and the government. In this case, both parties demonstrated flexibility;however, the restructuring was delayed, and therefore the short remaining implementation period did not leave enough time foroutcome to be improved.
P102119 | Nigeria HIV/AIDS Program Development Project II | Western and Central Africa | Nigeria | Blend | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2009 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/537281523626105323/text/Nigeria-NG-HIV-AIDS-Prog-Dev-II-FY09.txt | http://documents.worldbank.org/curated/en/537281523626105323/pdf/Nigeria-NG-HIV-AIDS-Prog-Dev-II-FY09.pdf | The ICR (pp. 29-30) offers several useful lessons, including the following lessons edited byIEG: Engaging local civil society organizations and private providers enhances opportunities toextend the reach of interventions to vulnerable populations, notably when such local organizations are already providing servicesto populations not typically reached by government agencies. This approach was pursued by theproject. Rather than covering all the states, a more selective area approach mightfacilitatetechnical and implementation support. The project experienced difficulties in the provision of effective and timelyimplementation support to all 36 states. The institutionalization and empowerment of local agenciesenhance the relevance of responses to the local situation. Under the project, the transitioning of State Action Committees onAIDS to the status of agency provided them with jurisdiction to make their own decisions in the prevention of HIV. Theinstitutionalization of these entities also promoted their sustainability.
P102160 | Social Sectors Institutional Reform Development Policy Loan (SIR DPL II) | Europe and Central Asia | Bulgaria | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2009 | 2012 | 2011 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/835901475100372628/text/Bulgaria-First-Social-Sectors-Institutional-Reform-Development-Policy-Loan-sir-Dpl1.txt | http://documents.worldbank.org/curated/en/835901475100372628/pdf/Bulgaria-First-Social-Sectors-Institutional-Reform-Development-Policy-Loan-sir-Dpl1.pdf | The lessons arising from the overall series are presented in the ICRR for SIRDPL III, project ID 115400.
P102165 | Avian Influenza Control and Human Pandemic Preparedness and Response Project | Europe and Central Asia | Kosovo | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2011 | 2013 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/306171474594265100/text/000020051-20140625073658.txt | http://documents.worldbank.org/curated/en/306171474594265100/pdf/000020051-20140625073658.pdf | The ICR reports a number of lessons, including:A global template can enable rapid and effective project design. The Global Program on Avian Influenza template was effective in reducing project preparation time.Including terms of reference and technical specifications in the operational manual can assist in rapid implementation of an emergency project. Including specifications for basic items such as protective gear and disinfectants sped up procurement of these emergency items.United Nations agencies can offer technical skills that may be lacking in the Bank or in implementing agencies. They can also be effective in supporting outreach to minority ethnic enclaves where implementing agencies may have difficulty in operating.IEG also finds that:Projects that target a single disease face challenges in remaining relevant if that disease turns out to be less serious than thought. This need not mean that single disease projects should never be designed, but that such projects need to be open to restructuring should priorities change.
P102172 | Project in Support of Restructuring of Health Sector | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2009 | 2016 | 2016 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/416431468308041441/text/ICRR-Disclosable-P102172-06-13-2016-1465867399927.txt | http://documents.worldbank.org/curated/en/416431468308041441/pdf/ICRR-Disclosable-P102172-06-13-2016-1465867399927.pdf | The following lessons were identified (ICR pages 23-24): If specific indicators in the results framework clearlytrack advances toward achievement of the PDOs, monitoring of expected development outcomes becomes mucheasier. International technical assistance (TA) can be effective in sustaining health system reforms and improvements.Examples of particular high valued TA provided by this project are: (i) TA and training to enhance quality of care at hospital andprimary health care settings; (ii) TA to estimate the impact of the health sector reform efforts; and (iii) TA to develop capacityat the General Directorate for Health Investments to manage Public and Private Partnership (PPP) investments (e.g. legal, financialand operational aspects of PPP). In general, proper risk identification, monitoring and a flexible design allows themitigation of risks. However, the pilot contemplated under Component B suffered from uncertainty surrounding the legal frameworkthat was not sufficiently considered at appraisal among the possible scenarios. Retaining critical human resources (e.g.civil servants and the consultants) within the MoH Project Management Unit to minimize or avoid delays and challenges in projectimplementation is important, but so are the development of handover arrangements and training to ensure a smooth transition. In thelong term, these are also important for institutional memory. Frequent loss and high turnover of human capacity caused many delaysand created challenges throughout the Project, especially in the areas of project management, financial management, andprocurement.
P102174 | Institutional Development for Education Project | Europe and Central Asia | Kosovo | IDA | FCS | Human Development | Education | IDA | IPF | 2008 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/433771475117271311/text/000020051-20150113005553.txt | http://documents.worldbank.org/curated/en/433771475117271311/pdf/000020051-20150113005553.pdf | The ICR (p. 19-20) provides a number of lessons, which IEG has synthesized to the following:Close attention during preparation and supervision are needed when designing and implementing projects in contexts with limited capacity. In this case, there was a need for less complexity in design and need to ensure project readiness. When Bank staff provided closer supervision over issues that were delaying project implementation, project performance and disbursements improved. This supervision was aided by an understanding of the institutional context of Kosovo. This suggests the need for staff who understand local context, particularly in post-conflict settings. It was necessary to understand the politically sensitive nature of reforms to education financing, school autonomy, student assessment, teacher licensing, and tertiary education. Moreover, implementation was initially slow because of the ambitious nature of so many reforms. Thus, project design needs careful assessment of feasibility of reform and existing capacity, as well as ensuring readiness, An accurate assessment of both enabling conditions and implementation readiness is a prerequisite for effective design and implementation. In this project, there was no analysis of the existing legal framework and the Ministry's capacity to prepare core project documents. Legal constraints that were not identified at preparation limited education financing reforms. Late development of essential project documents caused delays during the initial years of the project.
P102177 | Technical & Vocational Education Modernization (TVEM) | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2011 | 2016 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/270301519415965389/text/Kazakhstan-TVEM.txt | http://documents.worldbank.org/curated/en/270301519415965389/pdf/Kazakhstan-TVEM.pdf | The following lessons are adapted from the ICR(pp. 23-24). The Governments overall commitment toreforming the TVE system helped pass changes to the required legal and regulatory frameworks. Participation of theprivate sector in TVE reforms, especially in setting occupational standards, helps achieve relevance of educational programs.Representation of the private sector on national and sector councils and school boards ensured that the project remained focused onproviding a demand-driven TVE education that adequately met the needs of the labor market. The individual developmentprograms developed a culture of innovation and participation at the school level. School-level assessments of needs and IDPpreparation introduced competency-based programs and improvementsin teaching resources and labs. The participation of theprivate sector in preparing the IDPs provided a direct link to employers competency demands, standards and skillsassessment.
P102262 | Zanzibar Basic Education Improvement Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2007 | 2014 | 2016 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/130751467998239756/text/ICRR14888-P102262-PUBLIC.txt | http://documents.worldbank.org/curated/en/130751467998239756/pdf/ICRR14888-P102262-PUBLIC.pdf | Lessons drawn from the ICR (pages 26-27), adapted by IEG:Â· The formulation of a robust results chain, with an appropriate timeline, is critical for a proper assessment of outcomes. Although this project achieved some positive changes Zanzibarâ€™s education, his project received ratings in the unsatisfactory range (efficacy and overall outcome) because the stated outcomes were not plausibly linked to the project outputs given the sequencing of activities and short implementation period. Other intermediate outcomes, more tightly linked to the project outputs, were achieved but were not included in the statement of objectives.Â· Project restructuring that takes places too late in the project period can have negative consequences on policy dialogue. In the case of this project, the Borrower viewed the proposed changes as having negligible value and therefore did not pursue a more in-depth restructuring that might have set the stage for a more satisfactory outcome rating.
P102284 | Cambodia Second Health Sector Support Program | East Asia and Pacific | Cambodia | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2008 | 2016 | 2017 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/501191492782313295/text/ICRR-Disclosable-P102284-04-21-2017-1492783213518.txt | http://documents.worldbank.org/curated/en/501191492782313295/pdf/ICRR-Disclosable-P102284-04-21-2017-1492783213518.pdf | The project provided a number of lessons (ICR, p. 34):Theharmonization of development partner management and implementation systems is an important aspect of aid effectivenessthatcan support government ownership and sector governance. However, when these harmonization efforts are notaccompanied by a reduction in parallel systems, structures and reporting requirements of individual development partners can alsoincrease the partner Governments transaction costs.The following lessons are drawn from theICR and adapted by IEG:The Sector-wide Management Approach, as followed by the Bank and bydevelopment partners in Cambodia, can be an effectiveapproach for aid delivery and for using government systems.The approach was more flexible than a full sector-wide approach because it did not mandate pooled funding or the adoptionof the same implementation arrangements.Experimentation and theeffective use of evaluation findings are key ingredients for a successful scale up ofhealth interventions. Theproject followed gradual steps inimproving financial protection and inscaling up Health Equity Funds nationwide,building on prior experiencethat started under the First Health Sector SupportProject.
P102288 | Afghanistan: Emergency National Solidarity Project II | South Asia | Afghanistan | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2014 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/423251475110479015/text/000020051-20140625192550.txt | http://documents.worldbank.org/curated/en/423251475110479015/pdf/000020051-20140625192550.pdf | ICRR Lessons are derived from the ICR, interviews with two of the project TTLs and Lead Impact Evaluator, findings from the independent Impact Evaluation of NSP II conducted between 2006-2011, and the findings and recommendations from IEG's Country Program Evaluation of Afghanistan (2002-2011). Since the NSP is an ongoing program, and the findings and lessons of the impact evaluation were not presented in the ICR, this ICRR presents lessons that are specific to the program, that can also inform Bank supported CDD programs elsewhere. There is a need to advise and support the Afghanistan government in transforming the NSP into a more sustainable financial and institutional model to consolidate its gains. This would involve helping to formulate a long-term strategy around the future role of the CDCs. It would involve supporting a dialogue around the relative effectiveness of linking the CDCs to higher tiers of subnational governance, including the tradeoffs associated with transition in the short-term versus the longer term need for regular intergovernmental fiscal transfers for public investments and service delivery. The design of the NSP program has not evolved since its initial start-up phases. There has been a dramatic improvement in data collection, monitoring and evaluation over the lifetime of this program. However, to date, there has been a disconnect between the collection of project level data and the synthesis and incorporation of this data into program design. The program would benefit from a deep consideration of the operational implications of findings that have emerged from the Impact Evaluation and other qualitative studies on subproject selection, gender, elections etc. Building not just capacity but institutional legitimacy is extremely important. In light of thelow level of institutional depth both in line Ministries and at the local level, considerable technicalassistance has been provided to build capacity. In providing such capacity, what has succeeded is whenBank support has helped the Government build institutions, systems and social capital that are seen aslegitimate because they are inclusive and provide services. While the program has made exceptional progress on promoting women's participation in decision making at the local level, the menu of options with regard to women's participation may have been too rigid, suggesting that more women may have participated with a more flexible and intuitive approach. This would require increasing the number of female facilitating partner social organizers, more extensive gender training, and finding ways to build more local ownership into the initiative- taking into account the very different attitudes and perceptions about women across the country's heterogenous provinces. Within the CDCs that have incorporated women's participation, more extensive research is needed on how this participation i has impacted villagers' perceptions about the role of women in society, how this participation has influenced decision-making and sub-project selection, and how women's participation in the CDCs has influenced women's participation outside of the CDCs.
P102299 | Botswana National HIV/AIDS Prevention Support Project | Eastern and Southern Africa | Botswana | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2009 | 2015 | 2016 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/453591468015668497/text/ICRR-Disclosable-P102299-06-13-2016-1465865167777.txt | http://documents.worldbank.org/curated/en/453591468015668497/pdf/ICRR-Disclosable-P102299-06-13-2016-1465865167777.pdf | Among the lessons identified by the ICR (pages 36-37), the following are noted: Even within a limited resourceenvelope, integration of HIV with other communicable disease and non-communicable disease services is possible, through a focus onfunctions (prevention, treatment, and care) rather than disease categories. In particular, this project illustrates thepotential for integration of cervical cancer screening and care into the HIV/AIDS service delivery platform, leveraging HIV-relatedinvestments to cover other diseases that share underlying social determinants, interacting co-morbidities, and commonsolutions. Careful design and implementation of a robust evaluation agenda are prerequisites for an efficiency analysisthat can inform resource allocation decisions and policy formulation. In this case, lack of data on some interventions andprogram costs precluded full assessment of the impact and cost-effectiveness of various behavior changeinterventions.
P102305 | Avian Influenza Preparedness and Response Project | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2013 | 2014 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/766351475111824837/text/000020051-20140626114227.txt | http://documents.worldbank.org/curated/en/766351475111824837/pdf/000020051-20140626114227.pdf | The ICR reports the following lessons:Â· Complex results framework may not be possible to fully implement when they overwhelm the limited local implementation capacity. In this project, there were too many complex indicators which overburdened M&E institutional capacity. Â· When donor coordination is weak, interventions may not be well harmonized and project designs may be unnecessarily duplicative. It is important to streamline and complement donor financing when many donors are involved. The project had to cut down significant amount of funds since other agencies also financed similar activities. Â· Important interventions may not be undertaken if not all relevant agencies are included as implementing partners. In this project, the Department of Forestry was not included, which meant that wild bird monitoring was not carried out, and so the extent and distribution of disease infection in wild birds remains unknown. Â· Failing to improve biosecurity can contribute to an inability to eradicate avian influenza. The project did not pay enough attention to this particular issue both during design and implementation. IEG also finds that: Â· Project objectives should be chosen so that they match the sectors of what is actually planned to be achieved under the specific project. In this case there was a disconnect between the stated objectives and the project design, because the objectives included human health response goals that were not to be achieved under this project.
P102315 | Sudan Microfinance Development Facility Project | Eastern and Southern Africa | Sudan | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2007 | 2013 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/873531474941077403/text/000012394-20150309074937.txt | http://documents.worldbank.org/curated/en/873531474941077403/pdf/000012394-20150309074937.pdf | The ICR gives a number of lessons (paras 100 - 106), mostly of a project-specific nature and especially relevant for a follow-on operation. IEG draws three broader lessons:Where a project includes counterpart funds, it is preferable that the relevant project entity has full responsibility over the funds on a par with funds from outside donors. In this case such responsibility had not been built into the project agreements.Where project entities are considered to be established with autonomy or independence from host organizations, the longer term pros and cons need to be considered carefully in light, inter alia, of local conditions and expectations. In this case the decision to establish the SMDF with autonomy from the CBOS and the microfinance entity of that host organization may have caused complications for implementation without assuring longer term sustainability.Where such autonomous organizations are contemplated, it is also important to address up front the legal structure. In this case, it took time after approval to determine the best legal form for SMDF.
P102319 | MDTF South Sudan Private Sector Development | Eastern and Southern Africa | South Sudan | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2007 | 2012 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/435941474585581623/text/000020051-20140626104845.txt | http://documents.worldbank.org/curated/en/435941474585581623/pdf/000020051-20140626104845.pdf | The following lessons, emphasizing those that would be applicable in other post-conflict environments, are taken from the ICR with some adaptation of language:Complicated projects with a large number of components and sub-components are unlikely to be implementable in post-conflict countries, where institutions are weak and resources meagre. Careful sequencing, following a â€œbuilding blockâ€ approach, is likely to be more successful than pursuing multiple goals simultaneously.The costs and difficulties of attracting and retaining qualified personnel in most post-conflict environments are considerable. Projects besieged by security and infrastructure problems need to assess and budget adequate resources early on to be able to get the right people and firms on board. The outcomes of the project under review might have been significantly improved if it had had the resources to recruit from the right pool of talent. However, even with a large pool of resources, it is not entirely clear that talent would be attracted to fragile states.A well-functioning M&E framework is crucial to achieving outcomes, especially in data-poor and uncertain environments, where attention is too easily and invariably focused towards the immediate problems of implementation rather than the larger problems of monitoring.High-level steering committees have been shown in many countries to be necessary to establish project ownership at the right levels of Government, to ensure sustainability of activities after completion, and to have appropriate oversight in place when problems arise. In this case, such a committee was designated, but failed to meet.
P102329 | Rajasthan Rural Livelihoods Project (RRLP) | South Asia | India | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2011 | 2019 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/476951561383038006/text/India-IN-Rajasthan-Rural-Livelihoods-Project.txt | http://documents.worldbank.org/curated/en/476951561383038006/pdf/India-IN-Rajasthan-Rural-Livelihoods-Project.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some modificationof language.(1) Using community para-professionalscan be a cost-effectiveway for providing technical services in targetedcommunities. In this project, the hiring of youngprofessionals (young graduates) proved very useful in training village level workers.(2) Astructured approach to training is necessary for aproject with extensive geographical coverage and capacitybuilding needs, The capacity building efforts that were effective in this project included, creation of dedicated units(resource cells), standardized modules for all types of training and ensuring enabling environments for trainees such asresidential facilities and counselling family members to support womens participation in suchprogram.(3) Providing capital for the poor needsto be complemented bytechnical support for the design of livelihood programs to ensure sustainability. As this project showed, formarket-oriented livelihood activities, the technical support provided by the projectbenefited from an engagement with privatesector operators in the value chain.
P102330 | North East Rural Livelihoods Project (NERLP) | South Asia | India | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2012 | 2020 | 2020 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/531821593553262725/text/India-IN-North-East-Rural-Livelihoods-Project.txt | http://documents.worldbank.org/curated/en/531821593553262725/pdf/India-IN-North-East-Rural-Livelihoods-Project.pdf | The ICR included eleven lessons and recommendations. The following three lessons are emphasized with some adaptation oflanguage: To ensure financial inclusion, it is criticalto identify and rectify demand and supplyissues that impact bank linkagesearly in the implementation cycle. The projectexperience revealed severaldemand and supply issues. Early stage demand-side limitations included: project timelines, inadequate priority to bank linkages (aslivelihood funds were available), and lack of local income-generating opportunities. Supply side constraints included inertia ofbankers to engage in SHG loans and lack of bank branches in certain project areas. Early identification of the afore-mentionedissues could have helped the project achieve better results. To ensure sustainable income generation, it isnecessary to develop livelihood activities involving markets providing higher order support to livelihoods. The projectexperience showed thatadequate time is needed to establishand allow producer organizations to mature. Also, there needsto be a stronger emphasis on initial cluster development, and sustained group-targeted, specialized business-oriented technical andmanagerial support, to be carried through to adequate group maturity. To ensure sustainability of the developmentoutcomes, it is critical to plan an exit strategy earlier in the implementation cycleto allow enough time for a smoothtransition to local institutions. While the transition of the North East Rural Livelihood Project to theGovernment-supportedNational Rural Livelihood Mission served as a strong institutional exit and sustainability strategy,itshould have been planned earlier. This exit strategy has provided opportunities for mirroring future efforts in thematicareas of financial inclusion, federation strengthening, non-farm skills development and agricultural value chains with the NationalRural Livelihood Mission approaches. These transition arrangements take a long time to plan in government systems. The role of theWorld Bank is of a facilitator in the process. National ministries and state governments should be encouraged to establishsolutions and guidelines through dialogue and consensus.The following lesson is emphasized byIEG: To avoid costly start-up delays, more emphasis should be put on ensuring the clients readiness forproject implementation. The project experience showed that the project took about three years to takeoff. Suchdelays could be avoided or reduced through putting greater focus on ensuring client readiness for project implementation and asimpler design given the limited implementation capacity.
P102333 | Punjab-Irrigation Sector Development Policy Loan II | South Asia | Pakistan | Blend | Non-FCS | Sustainable Development | Water | IBRD | DPF | 2007 | 2008 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/772761474943713060/text/000020051-20140626075327.txt | http://documents.worldbank.org/curated/en/772761474943713060/pdf/000020051-20140626075327.pdf | The following lessons are adapted from the ICR: Keep DPLs simple: This lesson was specifically learnt from the implementation of the National Drainage Program and was applied to the DPL Program. The Program was simple and had one main implementation agency (the Irrigation and Power Department) which made its implementation easy. The the program was strategically designed to engage the highest decision-making officials through an Inter-Departmental Reforms Steering Committee which provided oversight and guided decision-making as well as their quick implementation.Any program that generates demand can be considered a success: The institutional architecture that evolved under the Program provided a strong base for farmersâ€™ participation and decentralization of irrigation management responsibilities. A well-designed communication plan ensured that all stakeholders â€“ especially farmers â€“ are aware of the steps being taken through the reforms. This not only created the demand for transparency in information sharing, it also challenged the government agency to keep pace with increased demand for timely and accurate information.Institutional change needs time to take roots: The short lifespan of the DPL series was designed for quick outcomes in setting forth the reforms processes. However, the expected pace of implementation on some policy areas could not be sustained by the new Farmer Organizations and their governance arrangements that needed time to mature. It was expected that this lacunae would be addressed through follow-up investment programming built on the lessons learned.
P102354 | COMMUNITY ACTION PROGRAM (PAC2) | Western and Central Africa | Niger | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2009 | 2020 | 2014 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/532981475113401496/text/ICRR14382-ICR-Review-P102354.txt | http://documents.worldbank.org/curated/en/532981475113401496/pdf/ICRR14382-ICR-Review-P102354.pdf | The following lessons are taken from the ICR with some rearrangement by IEG:A program implemented in several phases should avoid gaps and delays in initiating each new phase. Gaps not only interrupt the program but carry the risk that experienced staff will be lost. A gap occurred between phase 1 and phase 2 of the program because the government was slow to realize that the project was nearing its end, and disputes arose over the selection of new staff. This meant that all staff had to be laid off. The gap between phase 2 and phase 3 resulted from the accelerated implementation of phase 2 and the full disbursement of funds six months before the project officially closed. The government retained senior personnel to look after other investments under the program.To realize the benefits of local participation, some guidance may be necessary. Given full liberty to set micro project priorities, many communes may identify the same priorities, possibly on the basis of a recent crisis (as occurred under the project, when most microprojects involved seed and grain banks). With limited funds available, the cross-cutting contributions arising from different types of investments may be lost. Although microprojects have been based in individual communes, many investments may be more suited to intercommunal microprojects, such as investments in feeder roads, middle schools, health centers, and even seed banks. Clear, simple procedures should be developed for such cases under the next phase of the program. Adequate supplies to make microprojects effective, such as medicines for health centers and textbooks for schools, should be included in micro project packages.Readiness for mainstreaming should be judged objectively based on a readiness survey. It is easy to underestimate the public sector human and financial resources needed for an effective, countrywide, and multi ministerial response to multiple objectives (decentralization, socioeconomic development, participation of the population). It is also easy to underestimate the additional strains that such integration may place on overburdened government staff, who often lack the necessary training to carry out expanded responsibilities. In Niger, the regional, departmental, and local administrators were not ready to assume the tasks involved in implementing the project in addition to their normal duties, and additional project-funded staff had to be recruited beyond the number estimated at appraisal.Incentives are needed to sustain environmental improvements. Poor people struggling with survival frequently rank microprojects with production benefits as a higher priority than natural resource management microprojects. To ensure adequate interest, natural resource microprojects would benefit from their own priority listing and separately allocated funds. To interest people in long-term natural resource management and environmental protection (including the maintenance of trees), it is absolutely necessary to give them concrete incentives, such as food or cash for work, and perhaps to be more â€œsupply-driven.â€ . To improve efficiency, the public sector environmental staff may also need incentives, such as transport, training, and allowances.
P102354 | COMMUNITY ACTION PROGRAM (PAC2) | Western and Central Africa | Niger | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2009 | 2020 | 2021 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/247381611169237800/text/Niger-Community-Action-Program-and-Community-Based-Integrated-Ecosystem-Management-Project-Phase-I-and-II.txt | http://documents.worldbank.org/curated/en/247381611169237800/pdf/Niger-Community-Action-Program-and-Community-Based-Integrated-Ecosystem-Management-Project-Phase-I-and-II.pdf | 4. Lessons 4.1 Land and resource restoration projects should supportâ€”and make evident how they are supportingâ€”existing customary flexible tenure arrangements to ensure distributional benefits among resource users and to mitigate conflict risks. Traditional land use arrangements in Niger between farmers, agropastoral, and transhumant populations are negotiated in ways that provided mutual land use benefits. However, as the CAP shows, increasing the value of openor pooled-access degraded land without clear, enforceable land use agreements can lead to predation by elites and farmer encroachment. This occurred in the first CAP-supported site, where restored parcels were sold outside of the community. It also occurred in areas that supported intercropping (crop agriculture alongside tree planting)\. Although land restoration activities took place on communal land, the introduction of intercropping facilitated individualized claims on community land. Such projects should be designed with an understanding of the customary flexible tenure arrangements and the coping strategies of vulnerable resource users who access communal lands as a social safety net. The composition of land management committees also requires attention to ensure that they represent different resource user rights and to mitigate the risks of predation. 4.2 The success of natural resource restoration depends on the extent to which private or communal resource users are compensated over reasonable, short-term time frames for abstaining from using those resources until the long-term public benefits of resource restoration are achieved. The assessment of CAP-1 and CAP-2 found that when compensation is too small or takes too long to materialize, it discourages resource users from abstaining from using the resources, which undermines restoration of the resource base. For example, carbon credits were distributed to CAP beneficiaries eventually, but after the sequestration of 152,583 tons CO2 equivalent was verified, the process was severely delayed and caused a significant level of consternation. 4.3 Projects that support land and resource restoration can ensure that women benefit by addressing participation barriers linked to social and cultural norms. In CAP-1 and CAP-2, women benefited less from project activities for multiple reasons. The cash-for-work programs did not include female-only tasks in geographic areas where women could be separated from men. Additionally, these programs did not provide women with alternate options for childcare and other domestic responsibilities during the hours and in the areas where these programs were implemented. Women did benefit from specific natural resource management programs, especially from banquettes that protected their vegetable gardens from soil erosion and flooding. However, wider extension services provided to male farmers (that included the distribution of advice, fertilizer, seed, and tools) were not provided systematically to women, who often farm less-lucrative crops (for example, peanuts) in plots next to their husbands' land. 4.4 Socioeconomic and anthropological analyses, conducted before project elaboration, can support the gender aspects of production and marketing better. In Niger, a very large number of women must fend for themselves and their families because their husbands migrated to other West African countries, such as Cote d'Ivoire, Nigeria, and Senegal, to look for work. However, compared with other Sahelian countries, there were few socioeconomic and anthropological studies conducted during the CAP period that focused on gender issues. The evaluation and research show that direct involvement of women in selling livestock in markets is generally frowned upon in Nigerien society, and though it may differ among the Hausa, women-owned livestock receive lower prices than those owned by men do.
P102365 | Rijeka Gateway II | Europe and Central Asia | Croatia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2009 | 2019 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/685611582563722755/text/Croatia-RIJEKA-Gateway-II-new-FY09.txt | http://documents.worldbank.org/curated/en/685611582563722755/pdf/Croatia-RIJEKA-Gateway-II-new-FY09.pdf | The ICR listed eight lessons which were predominantly concerned with challenges and pitfalls related to the timelyimplementation of large infrastructure projects such as geological conditions, the weather, economic recessions, ensuring effectiveinstitutional collaboration, and identifying aspects that are outside the control of entities responsible for the project.These lessons were elaborated using the experience of this projects implementation at Rijeka and they could be useful forsimilar projects in the Bank and elsewhere, but they were without a doubt lessons that have been learned many times already in awide range of projects.However, one of the lessons in the ICR referred to the cancelled urban renewal project. This wasmore novel than the others but not elaborated. This review takes the opportunity to expand on the lesson in theICR.An explicit theory of change or causal framework provides a clear basis forimplementationThe project aimed to improve the capacity, financial performance, and quality of services in theport of Rijeka but it was also intended to facilitate urban renewal in the area close to the port. The project was explicitlydesigned to improve the capacity and financial performance through the construction of the terminals as well as mobilizing privateinvestments to attract container traffic and improve the competitiveness of the port. However, the strong focus on these two issuesin the projects results matrix diminished the attention to the remaining objectives - urban renewal and quality of services.For example, the ICR noted (page 25) that the responsibility of addressing urban renewal was not assigned to the Borrower, andthere were no activities financed with project resources to this objective. The lesson is that a results framework or theory ofchange needs to be designed in a way that indicates the causal chain between project inputs through intermediate outcomes to thevarious project objectives and identifies the institutions that make the causal chain effective and facilitate the projectsimplementation. Unless project objectives are clearly stated in a projects theory of change it is unlikely that theywill attract the attention needed to be successfully achieved.
P102368 | Integrated Transport | Eastern and Southern Africa | Botswana | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2009 | 2022 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/099081423172594558/text/P102368046ee960ea080530c4376719cde9.txt | http://documents.worldbank.org/curated/en/099081423172594558/pdf/P102368046ee960ea080530c4376719cde9.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some languageadaptation.1. Frontloading capacity-building activities may help to minimize unforeseen complexities duringimplementation. This is particularly so when a new concept is introduced for the first time in a country. This projectintroduced the OPRC concept in Botswana. The design entailed capacity-building activities alongside physical infrastructureinvestments for the new concepts. This contributed to delays during implementation as the Road Directorate could not undertake thenew concept.2. Using the legal sanctioning mechanism available to the Bank (as stipulated in the FinancingAgreement) can help resolve noncompliance issues. In this project, the financing agreement stipulated the establishment ofa dedicated Special Management Unit (SMU). However, the SMU was only established several years after effectiveness.This contributed to the delays and cost overruns during implementation.3. Intensive support from the Bank,including the presence of an experienced task team leader and key team members, helps enhance project implementation. Thisis especially so when the government is unfamiliar with a new concept, such as the OPRC approach in this project.
P102376 | Economic Governance Technical | Eastern and Southern Africa | Comoros | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2011 | 2017 | 2018 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/431401513635056947/text/ICRR-Disclosable-P102376-12-18-2017-1513635049262.txt | http://documents.worldbank.org/curated/en/431401513635056947/pdf/ICRR-Disclosable-P102376-12-18-2017-1513635049262.pdf | The ICR (pp. 25-28) provides several important and widely applicable lessons, including:In afragile, post-conflict, and complex small-state context, attention to political economy drivers is key to ensuring that projectsare appropriately fit and able to adapt to changing environments. In this case, the project was well aligned with anearly dynamic of political support, but changes in government required adaptability and acute analysis of non-technical bottlenecksto sustain ownership and support.Attention to broader government financial incentives can helpsustain government support even in challenging contexts. During the first years of this projectsimplementation, positive reinforcement from the parallel DPO and African Development Bank-financed project was useful formaximizing complementarity, coherence, continuity, and perhaps most importantly, commitment.Forlow-income countries and fragile states where capacity is limited, it is important to set realistic objectives, time frames, budgetenvelopes, and indicators. Ambitious objectives may obscure the importance of focus on fundamental buildingblocks. Also, in this case, while the PEFA framework may have been appropriate as an entry point for dialogue and for settingthe country down the right path, the specific indicators were far too ambitious.Full implementationof complex IT systems takes time. World Bank experience shows a 7.5-year average time to complete full installationand operationalization of an integrated financial management information system. This project needed more time andresources than were planned, and in such a low-capacity environment, adaptable off-the-shelf solutions may have beenpreferable.
P102396 | PG Second Mining Sector Inst Strengthening TA | East Asia and Pacific | Papua New Guinea | Blend | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2008 | 2015 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/182861473882635424/text/ICRR-Disclosable-P102396-09-14-2016-1473882625024.txt | http://documents.worldbank.org/curated/en/182861473882635424/pdf/ICRR-Disclosable-P102396-09-14-2016-1473882625024.pdf | The ICR (page 30) draws the following main lessons from implementing this project.(1) It would be useful toaddress concerns with procurement capacity early during projectpreparation. Although provision of capacitybuilding and training by the Bank helped, shortage of capacity remained an issue throughout implementation for the mininginstitutions in the Government.(2) Designing appropriate gender programs (such as adult literacy programs andselection of leaders among women groups/associations) can help in promoting gender promotion in the EI sector.
P102398 | Road Sector Project | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2010 | 2018 | 2018 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/613341527196624235/text/Lao-Peoples-Democratic-Republic-LA-Road-Sector-Project.txt | http://documents.worldbank.org/curated/en/613341527196624235/pdf/Lao-Peoples-Democratic-Republic-LA-Road-Sector-Project.pdf | These lessons have been adapted from the ICR;Institutional leadershipcan be pivotalto the successofa project.Under MPWTs leadership,improvements in road sector planning and management have beencarried forward into the sectors strategic planning and prioritization system for road improvement and maintenance. Thisincludeslearning fromthe way the Government handled the fiduciary case investigated by the World Bank IntegrityDepartment. The Government has subsequentlyenhanced its transparency of procurement information disclosure and supportedadditional training of all staff involved in procurement decisions to contain and lower the level ofrisk.Disasters are setbacks, but can also be opportunities to try new approaches. Theproject was able to introducea south-south knowledge exchange program, explore PPP possibilities, and introduce performancebased contracting and a sector wide approach.
P102478 | Senegal Sanitation- Supporting Access to on-site sanitation services through OBA scheme in Senegal | Western and Central Africa | Senegal | IDA | Non-FCS | Sustainable Development | Water | RETF | IPF | 2008 | 2012 | 2014 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/439851474750676418/text/000020051-20140625224325.txt | http://documents.worldbank.org/curated/en/439851474750676418/pdf/000020051-20140625224325.pdf | The following lessons are derived from those presented in the ICR (pp. 25-26):Full payment principles can be too rigid. GPOBA principle of full payment of the beneficiary's contribution before work begins was too rigid for this project. The ICR reports that the project discouraged participation by the most underprivileged (p. 25).There is a permanent need for ongoing hygiene-related awareness raising. In this project, the percentage of financing for soft inputs (studies, supervision, social engineering) was underestimated and had to be increased during the project.Where possible, obstacles to rapid project implementation should be promptly identified and removed. The payment schedules mandated by the GPOBA approach were overly complex. The Project Team took a long time to grow familiar with the method of invoicing (p. 26).
P102478 | Senegal Sanitation- Supporting Access to on-site sanitation services through OBA scheme in Senegal | Western and Central Africa | Senegal | IDA | Non-FCS | Sustainable Development | Water | RETF | IPF | 2008 | 2012 | 2015 | PPAR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/532141468294656002/text/9419150PPAR0P00ater0project000final.txt | http://documents.worldbank.org/curated/en/532141468294656002/pdf/9419150PPAR0P00ater0project000final.pdf | Lessons Learned 3.45 Premature cessation of donor engagement could lead to a loss in momentum for major sector reform. The Government of Senegal had high ownership of the adopted a strategy (1995 and 2005) in the water and sanitation sector but this has recently waned. Through sustained commitment of IDA, the Bank was able to (i) play a catalytic role in leveraging investment funding from other donors; (ii) smooth friction and bring a cooperative spirit; and (iii) provide continuous support to the full execution of contractual and regulatory obligations. However, the IEG mission found that the Bank and the donor community have recently shifted their focus away from the relatively well performing urban water and sanitation, to rural water and sanitation sector. As a result, the Government slowed down on its reform agenda, as evidenced by the absence of an updated water sector policy and non-compliance of the lease contract with the private operator, potentially losing the momentum generated to sustain earlier reforms. 3.46 Benefits of water investments may not be realized without adequate attention to sanitation. Recognizing the existence of a comprehensive and integrated approach to sanitation, evidenced by Senegal's urban sanitation strategy which was based on the diversification of technologies, the assessment found that more resources and more attention were devoted to water production and distribution at the expense of the sanitation sub-sector in Senegal. This finding is reflected in the mismatch between the sanitation infrastructure and the country's needs, and the lack of solutions to set up sustainable approaches to manage public and semi-public sewerage networks and wastewater treatment plants. According to the interviews carried out during the IEG mission, the supply of increased urban water facilitated by the Bank's project had led to major pressure on the existing sewerage infrastructure. As the imbalance between the water and sanitation investments and reforms persists, sanitation conditions may worsen, leading to unhealthy conditions and increasing risks of water-borne diseases to the population that benefitted from water services. 3.47 Raising tariffs only for one customer group may not be effective for ensuring long term sustainability. Since 2006, the water tariff for the private consumers had been frozen by the Government in contradiction to the lease agreement prescribing annual water price adjustments in line with the inflation.16 In contrast, while the tariffs increased for the public sector entities, the exploding bills were only partially paid by the government and, as a result, arrears often accumulated and as a consequence, there were limited resources available to fund the sector's major financial needs. In the absence of steady tariff increases, the sector risks a declining quality of the infrastructure and services. 3.48 Determining the right threshold of the beneficiary contribution is vital for the successful delivery of peri-urban sanitation services. The peri-urban sanitation component faced serious start-up problems because the required household contribution was perceived to be too high, and the large-scale NGOs involved in outreach activities were not able to communicate and work efficiently with the beneficiaries. Modification of beneficiary contribution from 50 to 25 percent of the facility cost, and shifting of outreach responsibilities to community-based organizations, increased beneficiary participation in the on-site and the semi-collective sanitation program. 3.49 Complex management and institutional arrangements lead to implementation delays. The procedures for Global Partnership for Output-Based Aid were complex and implementation arrangements were cumbersome. Obstacles to rapid project implementation were not promptly identified and removed during trust fund negotiation and processing. The payment schedules mandated by the GPOBA approach were overly complex, and the Project Team took a long time to get used to the 16. The mission was informed that the Government finally decided to increase the tariffs in September 2014. Trust Fund procedures, leading to delays in launching and implementing the project, causing delays in proper establishment of sustainability enhancing measures. The lesson from this experience is the importance of identifying the institutional issues early and simplifying the management and implementation arrangements to avoid delays in project implementation. It is also important to weight the transaction costs associated with the funding size of GPOBA, and the institutional viability of such approach compared to a larger, project scale initiative that is more integrated with the government program.
P102479 | Bolivia Decentralized Electricity for Universal Access | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2008 | 2013 | 2015 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/662191475117994131/text/000012394-20150108150555.txt | http://documents.worldbank.org/curated/en/662191475117994131/pdf/000012394-20150108150555.pdf | This lesson is from the GPOBA project ICR with some paraphrasing: An output-based approach complemented by medium-term service contracts in providing access to off-grid energy provides additional performance incentives and helps guarantee adequate electricity service during a specific period. However, achieving sustainability of benefits of Solar Home Systems (SHS) is a challenge. It requires an objective assessment during the preparation phase and a project design oriented towards a greater involvement of local communities and/or the long-term involvement of a utility or electricity service provider.The next two lessons are derived from the GPOBA project ICR and lessons from the earlier IDTR-I project. Allowing more flexibility in the design of projects using an output-based aid model is critical to their successful implementation. Early review and adoption of lessons from a similar project (IDTR-I) in the design of the project would have saved the project from multiple restructuring and delayed implementation.
P102487 | Higher Education Reform for the Knowledge Economy | Middle East and North Africa | Jordan | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2009 | 2010 | 2011 | ICRR | Less than 10 million |  | Moderately Unsatisfactory |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/694551474398252090/text/000020051-20140620085045.txt | http://documents.worldbank.org/curated/en/694551474398252090/pdf/000020051-20140620085045.pdf | The following lessons are presented in the Bank's NCO:It is important to include all relevant ministries (in this case the Ministry of Finance) early on in project planning. The World Bank team recognized the need for key decision makers from the MoF to be part of the preparation process. It tried to include the MoF in identification, preparation, appraisal, and technical discussions. However, participation was not always at a level that could positively influence decision making at senior levels of MoF. This weighed heavily in the latter stages of project preparations, once the financial crisis became evident and priority investments took precedence over higher education.In response to a notification of cancellation decision from the Borrower, a quick physical in-country presence by the World Bank is indicated. The World Bank team, involving the sector and country management teams, deliberated intensively on the letter and how best to respond to the cancellation decision. In addition, the country unit held several telephone conversations with counterparts at the Ministry of Planning and International Cooperation on the subject. However, a quicker in-country discussion may have better highlighted to government of the importance of continuing the project, and the overall small impact of this loan on long-term debt dynamics in the country, particularly given the reputational issues that the government would face in canceling a project that was two years in preparation and cost close to $1 million to prepare.Policy dialogue and analysis can play an important role in ensuring a strong reform program and interest by development partners. A key lesson learned from this project is that policy dialogue and analysis were instrumental in building the analytical underpinnings of a strong reform program, and in building consensus within the country around the reforms. The analysis that was supported by the World Bank was widely disseminated within Jordan, which led to wide acknowledgement of the challenges facing higher education, as well as the difficult decisions needed to keep the good standing achieved by the sector regionally. This has also been important factors in raising interest of other donors in higher education, a sector which they traditionally were not engaged in. The presence of resources from the PHRD grant was also highly instrumental in allowing the government to bring international experience in support of project preparation. All the factors led to the subsequent request by the government for World Bank technical assistance in implementation of reforms that emanated from this Higher Education Reform for the Knowledge Economy project.
P102508 | BI-ERSG II | Eastern and Southern Africa | Burundi | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2009 | 2012 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/652431475098487535/text/000020051-20140624211939.txt | http://documents.worldbank.org/curated/en/652431475098487535/pdf/000020051-20140624211939.pdf | The ICR draws several important lessons from the experience of the ERSGs. Most noteworthy are: 1. The program did not focus on â€œoutcomesâ€, but rather â€œactivitiesâ€ and â€œoutputsâ€. Hence, future operations need to be â€œresults-orientedâ€.2. The program also did not focus sufficiently enough on monitoring and evaluation and, hence, there needs to be greater focus on M fraud and abuse of government funds; and voice and accountability.
P102513 | PH-EC TF for Health Sector Reform | East Asia and Pacific | Philippines | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2007 | 2013 | 2014 | ICRR | Less than 10 million | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/948331475111810895/text/000020051-20140626110222.txt | http://documents.worldbank.org/curated/en/948331475111810895/pdf/000020051-20140626110222.pdf | In addition to the lessons included in the ICR, IEG adds one additional lesson: grant-financed projects need significant investment in quality at entry. It appears that the project team treated this project as different than a loan-financed project and did not carry out the full analysis that would normally be associated with a World Bank project.
P102527 | Morocco Urban WS&S Access Pilots | Middle East and North Africa | Morocco | IBRD | Non-FCS | Sustainable Development | Water | RETF | IPF | 2007 | 2012 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/739241475072790828/text/000020051-20140625225728.txt | http://documents.worldbank.org/curated/en/739241475072790828/pdf/000020051-20140625225728.pdf | The following lessons are derived from the ICR with some adaptation:- Social issues including possible land acquisition require identification during preparation, a thorough assessment of operatorsâ€™ role, active involvement and cooperation of local authorities, and capacity building of local authorities based on the adequate strategy. This project experienced unexpected delays due to inexperience in dealing with the slum upgrading and land acquisition for works to be carried out. - A robust Monitoring and Evaluation system is an essential tool to measure, report and assess the project implementation capacity and its outcomes, especially for a pilot operation. In this case, M&E weaknesses impeded an adequate assessment of pilot outcomes. M&E design should incorporate procedures for ensuring that all key financial and other information, necessary for monitoring and for the proper application of the subsidy policy, will be available- The Output-Based Aid (OBA) approach can successfully involve a public utility provider: In the case of Meknes, the public utility proved that it can bear the performance risks involved in the OBA approach, thereby ensuring public service provision to neglected segments of the population.
P102547 | India: Elementary Education (Sarva Shiksha Abhiyan II) | South Asia | India | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2008 | 2013 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/517271474564315745/text/000020051-20140626104930.txt | http://documents.worldbank.org/curated/en/517271474564315745/pdf/000020051-20140626104930.pdf | The ICR mentions a number of lessons learned including:a)" Strong political commitment and ownership are critical for successfully steering a centrally sponsored scheme. Significant and positive results - especially on the access and equity agenda - demonstrated by the program has proved to be the linchpin for sustained political ownership and commitment."b)" SSA provided Development Partners (DPs) with a viable platform to provide consistent and concordant support to the program under a common results framework" The engagement of the DPs not only reduced transaction costs for the government but resulted in timely identification of issues and resolution of implementation challenges.c) "A realistic assessment of capacity is important to inform the design and sequencing of the reform programs for optimal impact." d) Learning assessments themselves are complicated to design and administer and require considerable institutional capacity to be run at scale. They are also only a technical exercise if the results are not shared with stakeholders and acted upon.Page 79 of Annex 7 in the Government response to the ICR, notes additional lessons:-The importance of decentralization and delegation of the planning, management and monitoring of interventions has emerged as a key lesson learned;- The participation of civil society is a crucial factor in ensuring stakeholder participation, and"The most crucial lesson learnt is that interventions for equity and quality have to run hand in hand and not one after the other." Unless education is of uniformly good quality, access to school alone cannot create equity between the disadvantaged and the more fortunate.One further lesson identified by IEG, drawing on the ICR review process, is that identified areas of exceptional need, such as particular regions, States or Districts, require intensive efforts and expenditures to reach acceptable standards in service delivery and to change schooling patterns for the most vulnerable groups. Approaches to these groups may need to vary between geographic area and need specific monitoring and evaluation. Extra effort is needed to ensure that addressing the needs of these vulnerable groups is successfully achieved within a broader program as decentralization in a federal system does not automatically lead to equity.
P102549 | India: Technical Engineering Educational Quality Improvement II | South Asia | India | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2010 | 2017 | 2018 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/323001528210969820/text/India-IN-Tech-Engr-Educ-Qual-Improvement-II.txt | http://documents.worldbank.org/curated/en/323001528210969820/pdf/India-IN-Tech-Engr-Educ-Qual-Improvement-II.pdf | The ICR (pp. 30-32) offers a number of useful and important lessons, modified slightly here:Qualityimprovement involving increased autonomy and institutional leadership can stem from a variety of factors. Support musttherefore be based on a thorough and specific assessment of the challenges and constraints impacting each individual institution:limited capacity, limited initiative, weak state support, or other considerations.Accreditation mechanismsdepend on prerequisite capacity building for quality assurance mechanisms. In this case, some institutions applying foraccreditation experienced significant delays because of changes in accreditation procedures and limited supply of qualifiedaccreditors.IEG offers an additional lesson:Focus on outcomes otherthan those in the project objectives as stated in the legal agreement can result in inadequate measurement of progress andachievement. In this case, the project defined its objectives in terms of institutional strengthening, even though theFinancing Agreement committed the project to more outcome-oriented objectives. Consequently, the project did not collect andreport data sufficient to demonstrate high efficacy.
P102573 | Afghanistan Skills Development Project | South Asia | Afghanistan | IDA | FCS | Human Development | Education | IDA | IPF | 2008 | 2014 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/179541468191036621/text/ICRR14732-P102573-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/179541468191036621/pdf/ICRR14732-P102573-Box393183B-PUBLIC.pdf | Lessons drawn from the ICR (page 22) with some adaptation:In a post-conflict environment, it is important to begin intensive supervision as soon as a project becomes operational and continue throughout the life of the project. In this project, supervision was weak prior to the MTR, and early warning signs were not acted upon quickly.Project restructuring is best undertaken at an early stage as soon as it becomes clear that outcome targets will likely not be achieved or that original targets were too ambitious. Delayed restructuring, when the project funds are almost fully disbursed impacts on the final outcomes of the projectProgress on improving gender equity can be made even in situations with substantial cultural barriers. By focusing on improving the outcomes of women, this project was able to increase women's enrollment in formal TVET from 8% to 32%.
P102576 | Development Policy Operation DPO I FY07 | Western and Central Africa | Central African Republic | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2008 | 2009 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/291541474853671754/text/000020051-20140619075959.txt | http://documents.worldbank.org/curated/en/291541474853671754/pdf/000020051-20140619075959.pdf | The primary lesson is that in post-conflict countries, with weak administrative and technical capacity, the presence of qualified Bank staff in the field is vital for the success of development policy lending. Equally important is close supervision.
P102607 | Higher Education Support Program | South Asia | Pakistan | Blend | Non-FCS | Human Development | Education | IDA | DPF | 2010 | 2010 | 2011 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/953371475092772701/text/000020051-20140624161904.txt | http://documents.worldbank.org/curated/en/953371475092772701/pdf/000020051-20140624161904.pdf | Complete ownership by the Borrower is essential for the momentum of reforms to be sustained. In this case, the Bankâ€™s financing was tied only to the achievement of prior actions. Had the HEC not fully owned the program and not been committed to its own MTDF, substantial progress could not have been attained in implementing other components of the reform program.Flexibility in project design is critical. A large measure of the successful performance of the HEC stemmed from Its commitment to monitor progress and institute corrective measures when it felt that the outcomes of its policieswere not consistent with, or were hampering, the achievement of the overall objectives of the program. While all key players in the higher education sector were on the steep slope of the learning curve, the flexibility and timeliness with which actions were decided and implemented were critical to success.Sustained support by the Bank, outside the realm of assured funding, is important. There were a number of areas in this program where, while progress was made, the provision of technical assistance could have made iteasier for all principal stakeholders to implement the reforms quickly, efficiently, and in a cost-effective manner.For example, the establishment of Quality Enhancement Cells in universities could have proceeded moresmoothly with extended guidance and external support.The quality of the underpinning dialogue supporting a program can be as important as the instruments themselves. In this case, since the Bank's first engagement with Pakistan on higher education in 2006, there was, according to the TTL, continuous and rich interaction that made possible progress on program objectives.
P102608 | Pakistan: Punjab Education Sector Project | South Asia | Pakistan | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2009 | 2012 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/278961474556418517/text/000020051-20140626001803.txt | http://documents.worldbank.org/curated/en/278961474556418517/pdf/000020051-20140626001803.pdf | Several lessons are reported in the ICR (p. 24-26), which IEG has synthesized to the following:A results-based design with the use of disbursement-linked indicators can help sector dialogue to focus on the critical factors necessary for achievement of project development outcomes. Such a design can provide development partners with a viable platform to provide consistent policy advice to the Government under a common results framework. In this case, the development partners all engaged in this dialogue. The results-based investment operation improved donor coordination by linking implementation support to government strategy under a common framework and reduced the Government's reporting burden.Strong political commitment and ownership are critical for successfully steering a sector-wide reform program. In this case, there was sustained political commitment, even when the government changed in 2008. Evaluation evidence can reinforce Government commitment. When rigorous evidence demonstrated that the public private partnership initiative in Punjab generated large and quick gains in enrollment and achievement, the Government continued its partnership with the private sector to address shortfalls in education outcomes in underserved rural communities. Strong analytic work is necessary to select indicators, with great rigor towards establishing, measuring, and forecasting the extent of change expected as result of the successful achievement of disbursement-linked indicators. Clear articulation of linkages in formulating indicators and disbursement targets is important to focus efforts on factors that are critical to the achievement of project objectives. The indicators and targets need to be formulated with precision and avoid ambiguity. Ratio-based indicators are sensitive to slight changes in numerator and denominator resulting in volatility and noise, and therefore should not be included.
P102624 | Kerala Local Government and Service Delivery | South Asia | India | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/831681533824540340/text/India-IN-Kerala-Local-Govt-Service-Delivery.txt | http://documents.worldbank.org/curated/en/831681533824540340/pdf/India-IN-Kerala-Local-Govt-Service-Delivery.pdf | The ICR included four lessons. The following are emphasized with some adaptation of language. Toensure long term sustainability in local government and service delivery projects, capacity building of localgovernmentsshould be an on-going activity delivered, where possible, through local institutes.In thiscase, the project supported the Kerala Institute of Local Administration and the State Institute for Rural Development (the keystate-owned institutes) through infrastructure augmentation and systems modernization for delivery of training programs, curriculumdevelopment and strengthening HR capacities. This had a positive impact on their delivery capabilities and was favorablyacknowledged by the state. This was one of the key sustainability measures put in place to ensure thatthe project-supportedcapacity building interventions (preparation of manuals, training needs assessment, training curriculum and calendar) and continuedbeyond the project on a sustainable basis. To avoid conflicts and consequent delaysduring implementation, project implementation arrangements in local government service delivery projects should be simple andaligned withexisting, or to be improved, government systems. In thiscase, the projectimplementation arrangements involved multiple agencies and the project reporting relationships conflicted with governmentstructural reporting relationships. This led to institutional coordination issues and resulted in substantial delays. Also,implementation arrangements were not robust owing to weaknesses in the PMU, including frequent changes of Project Directors andmany key positions remaining vacant for an extended period during project implementation. Implementationarrangementscouldalso have beensupported by stronger systems for monitoring, evaluation and reportingthrougha bottom up information flow approach. These posed challenges in monitoring the progress of sub-project implementationat the local level. Eventually the project had to rely on district coordinators offices, which presentedits own constraintsand challenges in terms of information flow.
P102627 | India - Bihar Panchayat Strengthening Project | South Asia | India | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2013 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Unsatisfactory | Highly Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/426451608078454705/text/India-IN-Bihar-PRI.txt | http://documents.worldbank.org/curated/en/426451608078454705/pdf/India-IN-Bihar-PRI.pdf | Lessons in the ICR are condensed and augmented by IEG. The first lesson aims to catch the essence of a number of recommendationsin the ICR. The second is an IEG lesson that builds on one of the identified shortcomings of the project. The third lesson is anamalgamation of at least three lessons from the ICR along these lines.1. Flexibility and adaptation tocontext and problem. When implementation delays threaten the achievement of results, proactiveness, adaptation andflexibility in restructuring and implementation is of central importance to bring the project back on track. In the case of thisproject, the initial PDO, results framework and operational design did not sufficiently take into account the scale of thechallenge, the capacity constraints, and the poor governance context in Bihar. Future operations need to calibrate their expectedoutcomes and results framework against the situation on the ground both in terms of capacity, previous experiences, politicaleconomy constraints and the specific problem it seeks to address but must also remain flexible, adaptive and innovative inimplementation to overcome unforeseen challenges and to achieve unexpected results. An example of the latter is the ability to usenewly constructed PSBs as temporary Covid-19 isolation centers. The provision of toilets, water, and electricity was originallythought of as a way of enhancing more inclusion of women and other underserved citizens. In the event, design features have been insome cases repurposed to provide the basic necessities and hygiene required for quarantine, especially for migrant workerstemporarily unable to return to their homes.2. Innovative and tailored tools and approaches areneeded for difficult contexts. During implementation of the project it was determined that the level of ambition ofthe PDO was too high and that comprehensive strengthening of the inclusiveness, responsiveness and accountability of the PanchayatRaj Institutions was overly ambitious. Yet a survey showed some positive results in this regard. The IEG finds that a challengingcontext does not necessarily imply that governance-focused projects cannot be delivered. Success depends on the tools andapproaches applied, which should be relatively innovative, simple, engaging and tailored to the context. For example, theconstruction of the PSBs could have been subjected to a greater level of transparency and citizens engagement in the design andconstruction of the buildings, which would have made them more transformative. This would have complemented innovative mechanismsalready applied such as the e-PMS, other ICT tools and the third-party verification and quality audit. The project could have beenmore innovative in this sense and sought to identify approaches to strengthening transparency and accountability in the publicsector or built budget literacy. Embracing such approaches is critical to make governance-oriented reforms harder to reverse andmore sustainable.3. Ownership, continuity of senior management and staff and capacity-building arecentral to the success of governance reforms, even when outside the direct control of the Bank. In the case of thisproject, IEG finds that expanding the notion of ownership by proactively engaging stakeholders in early discussions about projectsand partnership frameworks could broaden and deepen ownership, creating demand from outside government. Making projectsproblem-driven and focused on addressing real issues can help retain commitment alongside intensive capacity building, technicalassistance and mentoring all tailored to the local context. Continuous capacity building and training increases learning andapplication, especially when there is high turnover of staff.
P102651 | Private and Financial Sector Policy Based Guarantee | Europe and Central Asia | Serbia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2011 | 2011 | 2012 | ICRR |  | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/654061474946153046/text/000020051-20140624212652.txt | http://documents.worldbank.org/curated/en/654061474946153046/pdf/000020051-20140624212652.pdf | 1. Some flexibility in implementing programmatic lending is important if the Bank is to be able to adjust programs to meet needs as they appear, this case, due to changing world market conditions. PFSPDL II, in this case, was productively modified to help Serbia pro-actively reform its banking and financial sectors to address problems that could have arisen from the world financial crisis. And moreso. the decision to proceed with a guarantee rather than PFSPDL III, as noted in the following point. 2. A guarantee instrument can be an important component of Bank assistance, especially for credit-worthy countries facing head-room constraints. 3. Good coordination remains an imperative. In this case, close coordination with the IMF and EU donors were key to insuring the resources needed for reform, as well as the incentive of EU membership.
P102651 | Private and Financial Sector Policy Based Guarantee | Europe and Central Asia | Serbia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2011 | 2011 | 2016 | PPAR |  | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/163751468194944921/text/106176-REVISED-PUBLIC-PPAR-serbia2016-002.txt | http://documents.worldbank.org/curated/en/163751468194944921/pdf/106176-REVISED-PUBLIC-PPAR-serbia2016-002.pdf | 6. Lessons 6.1 With informed hindsight four years after the operation, several lessons are worth highlighting that may be of broader relevance. 6.2 First, PBGs are a potentially important instrument that could be used effectively to support client countries in tapping international markets on favorable terms in combination with other lending and advisory instruments to help countries meet the development challenges of the twenty-first century. These challenges included the need to make structural reforms necessitated by global or regional crises, fund and manage large and complex development projects, work toward meeting the Sustainable Development Goals, and address issues related to climate change. Through this and similar guarantee instruments, the Bank Group could raise its leverage ratio, particularly if it fails to raise its capital base, in order to help its clients meet their development challenges of the next 15-to-20 years. Learning about the PBG in the context of Serbia and other client countries is both timely and important to the Bank Group's business model and strategy going forward. 6.3 Second, this highly satisfactory operation shows that the Bank can productively take informed risks with new and innovative instruments to support client needs in a timely fashion in a manner that would not have been possible with standard instruments of Bank support. The Bank had an option to take a low-risk approach and extend a standard DPL, which would have been in line with the existing Bank strategy. Also, external market turbulence could have suggested a more cautious approach with a standard DPL. In that scenario, however, the borrower would have had to borrow additional amounts in the external markets at much more unfavorable terms, raising its short-term debt service and fiscal pressure. The Bank's innovative approach with the PBG was risky, but it helped deliver the benefits to the client when needed. As a result, it strengthened the relationship of trust with the government. 6.4 Third, this operation shows that the PBG can be a particularly effective instrument of budget support under certain conditions. Those conditions are likely to include the following\. a small, vulnerable economy needing substantial external financing on a timely basis; a solid track record of macroeconomic performance, debt management, and policy reform and a good dialogue with the Bank; and a period of heightened international market risks and worsened access and terms of sovereign borrowing. The instrument should also be relevant for larger countries facing similar borrowing and reform challenges. These conditions are quite prevalent in international markets. Yet PBG use at the Bank has been limited so far. This may suggest that, perhaps with more information disseminated among the Bank Regions and the borrowers, there is scope for a wider use of PBGs in the future. This could also be helped by recent OPCS reform that moved the PBGs to the revised OP8.60 framework governing development policy operations, explicitly recognizing that PBGs are essentially a sui generis type of DPL. 6.5 Fourth, the PBG can unlock multiple benefits to the borrower, which may not be easily captured by alternatives such as a standard DPL\. the borrower was able borrow the larger amount (because of the Bank's set-aside policy, which accounts only one-quarter of the PBG against country's borrower limit) needed at the right time and on favorable terms in the context of the PBG, and its short-term debt service was lower than it would otherwise have been; it was able to open the door to substantial subsequent international borrowing at favorable terms; the borrower was able to establish itself in the eyes of international investors and broaden the investor base; and the borrower was highly motivated to deliver on reforms, in part because of a relationship of trust with the Bank, the large volume of borrowing, and also perhaps because of the presence of the third party (that is, a foreign commercial bank providing funding) supplying additional pressure on the timing and closure of the loan. 6.6 Fifth, it is important to recognize that risks such as a bullet repayment feature could add to the borrower's risk of repayment in the future unless it is accompanied by ex ante provisions equal to the amount required under a standard annual repayment schedule. Repayment options and their pros and cons should be discussed at length with the client. A standard repayment schedule should normally be preferred, and bullet repayments should be accompanied by a Bank recommendation (or requirement) that the borrower make annual provisions. 6.7 Sixth, strong and relevant design and high achievement are much more likely when the operation's design is informed by considerable knowledge work, intensive and longerterm Bank engagement and dialogue, and a relationship of trust between the Bank and the borrower. Developing and maintaining a relationship of trust with the borrower should be explicitly high on the agenda of country management. In its absence, ownership, quality of the dialogue, and the design and implementation are likely to suffer. 6.8 Complex and comprehensive reforms of large socially or state-owned enterprise sectors take time to implement. They also involve political, social, and fiscal risks. This calls for a carefully phased approach and realism in what can be accomplished in the short term and the time frame of a single operation. 6.9 Seventh, Bank staff engagement in innovative operations must be more intensive and accompanied by considerable informal technical assistance. Such stepped-up assistance can be used to inform the borrower of the benefits and risks and help it navigate the preparation of a hitherto little-known instrument or type of Bank operation.
P102675 | Ghana Agriculture DPL | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | DPF | 2008 | 2009 | 2015 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/447151475116261071/text/000180307-20141203062550.txt | http://documents.worldbank.org/curated/en/447151475116261071/pdf/000180307-20141203062550.pdf | The ICR noted three lessons: complementarity of policy agenda with other Bank operations, the need for borrower to internalize monitoring of data and ensure adequate reporting, and the need for overall policy framework that includes complementarity with other donors (in this case CIDA, which provided substantial complementary budget support).Additional lessons that could be considered in future operations:Ensure more concrete development objectives that are easier to link with policy framework, actions, outputs and outcome indicators. The Bank should take into account the size of its interventions relative to the magnitude of the desired objectives as an input into the definition of development objectives. If the size of the loan is very small relative to the size of the economy or sector, then development objectives should be scaled down to what realistically the Bank operation can be expected to influence. Exercise greater selectivity and prioritization in the design of DPOs in terms of the number of policy areas, prior actions, and outcome indicators. Choose prior actions that are less process and documents oriented. Actions that are more geared towards policy implementation that can be quantified and linked more directly with outputs and outcomes have a greater chance of attribution, monitoring, measurement, and impact.Never choose an outcome indicator that depends on a baseline study that is not already available. Each outcome indicator should have an unambiguous, ideally quantitative baseline at the time of DPO design. Also, it should be relatively easy to observe, measure, monitor its updates and rate of change. Indicators that depend on surveys that are yet to be carried out run the risk of becoming irrelevant if a survey is delayed, as is often the case.A macroeconomic framework should include a detailed quantitative assessment of debt sustainability with appropriate sensitivity analysis. It should also indicate whether it is primarily a Bank assessment or joint with the IMF and whether there are any differences in the assessment of the macroeconomic framework and risks.
P102675 | Ghana Agriculture DPL | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | DPF | 2008 | 2009 | 2017 | PPAR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/707151490035515853/text/112622-PPAR-PUBLIC.txt | http://documents.worldbank.org/curated/en/707151490035515853/pdf/112622-PPAR-PUBLIC.pdf | 4. Lessons 189. The experience of these two programmatic DPO series provides the following lessons. 190. In a sector such as agriculture, in which responsibilities are fragmented across many different directorates and agencies, impact could be heightened by broadening engagement beyond key counterparts in the leading ministry to other directorates charged with delivering program results. In this case, the World Bank's dialogue and engagement was largely through counterparts in the MOFA's PPMED. Although other directorates participated in the selection and identification of prior actions, insufficient efforts were put in to sensitization and capacity building for implementation of reforms. There was a limited understanding of the budget support instrument among many key stakeholders beyond PPMED and lack of ownership in implementation of reforms. Weak coordination within MOFA and the weak leverage that PPMED had over other agencies linked to prior actions hampered PPMED's capacity to track subsequent implementation. 191. Rigorous assessment of government commitment and ownership is needed not only at the design stage but throughout implementation. In Ghana, the government engagement was high with respect to identifying and meeting prior actions but subsequent implementation of reforms was weak. 192. Potential synergies between sector and general budget support operations could be enhanced by more effective coordination and monitoring and feedback between the two. In these two agriculture DPOs, it was assumed at the design stage that the general public financial management reforms supported by PRSCs and economic governance DPOs would also benefit MOFA. However, public financial management reforms did not perform as expected. This illustrates the need for feedback to the sector operation so that measures can be taken to compensate. Additionally, in the agriculture sector, many reforms are needed beyond MOFA's jurisdiction, some of the crossjurisdictional reforms may be best incorporated into national-level budget support. In the second series, MOFA was cautioned by MOFEP to only agree on budget support triggers and targets over which MOFA had direct control. This makes sense from the standpoint of ensuring that targets are met in the short term, but it limits the utility of sector budget support in tackling critical bottlenecks in the sector that are covered by other ministries, directorates, and agencies. The completion reports of both series argue that actions beyond the jurisdictional mandate of the sector ministry would be better managed under MDBS. This too requires greater coordination and ongoing feedback and monitoring between sector and macro level teams. Prior actions that can improve coordination across ministries, directorates, and agencies should be considered. 193. Defining DPO series objectives in concrete and measurable terms and scaling ambition down to what the actions in the operations can realistically be expected to influence can improve the demonstration of impact and enhance attribution. In both of the series reviewed the overly general formulation of objectives made it difficult to connect to the outcomes of the various policy areas to the very ambitious series objectives. The results framework did not establish a clear causal chain between the prior actions and the overall series objectives. The mismatch between the identified outcomes and the prior actions and performance indicators added to the difficulty in establishing the contribution of the series prior actions to the series objectives. Prior actions geared toward policy implementation that can be quantified and linked more directly with outputs and outcomes have a greater chance of attribution, monitoring, measurement and impact.
P102709 | Programmatic Support for Institution Building III | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2008 | 2013 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/870751468197964841/text/Afghanistan-First-Second-and-Third-Programmatic-Support-for-Institution-Building-Project-and-Strengthening-Institutions-Development-Policy-Grant-Project.txt | http://documents.worldbank.org/curated/en/870751468197964841/pdf/Afghanistan-First-Second-and-Third-Programmatic-Support-for-Institution-Building-Project-and-Strengthening-Institutions-Development-Policy-Grant-Project.pdf | 4. Lessons Although Afghanistan's history and challenges are somewhat unusual, given the enormous impact of international actors since 1979 and the high profile of the international terrorist threat over the last decade, the experience over the period of these operations offers a few important lessons relevant to other fragile and conflict-affected states\. * Development Policy Operations can achieve important public administration and financial management reforms in high-risk environments with strong government ownership and flexible implementation. Bank investment lending, analytic and advisory services, and Bank-managed multi-donor trust funds, together with close coordination with the initiatives of other donors, can substantially increase the probability of success of development policy operations. Continuity, experience, and quality of Bank staff are necessary conditions for program effectiveness; with location in-country an added advantage. * Emergency consultant support in the shortand medium-term can usefully supplement the skill base in Governments where progress in institution and capacity building is bound to be a slow and time-consuming process. These skilled personnel can help adopt structures, processes, systems, and regulations to enable reforms in, inter alia, pay and grading, administrative reform oversight, human resources monitoring, tax administration, financial management, procurement, and audit. However, ensuring the transition to a more normal administrative structure is crucial for sustainability. * It is crucial to empower senior officials from Government to determine and direct administrative reform, public financial management and other institutional processes that make sense locally and that can promote broadbased consensus inclusive of key political groups, while being sufficiently robust to deal with rapid social and economic change. This PPAR has demonstrated that when such officials are supported by extensive analytical work and parallel technical assistance operations, development policy operations can emerge that succeed in facilitating limited but important progress taking place in a volatile setting. World Bank (2011 a) gives examples of some societies and states that have succeeded in managing these stresses without persistent recourse to violence, while others have not and finds the essential difference to be the ability of a society's institutions to mediate conflict. It is not yet clear whether Afghanistan is on track to succeed. As in other settings, it will take a generation or more of persistent effort to turn ineffective institutions into 'legitimate' entities which are capable, inclusive and accountable. This will be challenging. Creating local and national institutions capable of resolving conflicts peacefully and providing the stability and predictability needed for sustained economic growth are deeply affected by commercial, diplomatic, and security decisions taken beyond the country concerned. Development policy lending can have substantial success in meeting their objectives by walking a thin line between moving towards international standards of public administration, financial management, procurement, and accountability on the one hand, and maintaining local ownership and local face to the reforms on the other.
P102732 | Coastal Cities Pollution Control Project 2 | Europe and Central Asia | Croatia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2009 | 2016 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/763921492699211867/text/ICRR-Disclosable-P102732-04-20-2017-1492699188798.txt | http://documents.worldbank.org/curated/en/763921492699211867/pdf/ICRR-Disclosable-P102732-04-20-2017-1492699188798.pdf | The ICR includes eight lessons and the three most relevantare: Local ownership isgreatly enhanced by transparent communications: In this project, the Bank identified transparent communication as one ofthe key lesson learned from previous Bank engagement in Croatia. Therefore, the Bank hired special communication consultants towork with municipal officials and Municipal Water and Sewerage Companies to increase their interest and capacity in planning anddelivering public awareness and information campaigns. Building capacity at the local level iscritical for a successful project implementation and for the sustainability of its outcomes. In this project, capacity wasbuilt in small municipalities and utilities which allowed them to improve their daily operations and obtain knowledge toparticipate in other donor programs such as by the EU. Customers are willing to pay for improvedwastewater services. In this project, customers were willing to pay an additional surcharge in order to receive wastewatercollection and treatment services that would have a positive impact.
P102733 | Water Sector Investment Project | Europe and Central Asia | Albania | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2014 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/537141624635199211/text/Albania-Water-Sector-Investment-Project.txt | http://documents.worldbank.org/curated/en/537141624635199211/pdf/Albania-Water-Sector-Investment-Project.pdf | The ICR offered five lessons and recommendations as a result of the project operations (ICR, paragraphs 72-75). Two of those,with some editing, are provided below. Insufficient project preparedness can lead to lengthy implementationdelays at project start. In this project,when assessing project readiness, strengthening institutional proceduresaround transparency and coordination may reducefiduciary risks andencourage all stakeholders, including localcommunities to work toward achievingproject objectives. Smooth and effective coordination between involved entities andstakeholders would facilitate procedures, overcome obstacles, and accelerate implementation. Initial implementation delays were dueto missing procurement documents, preparation of the feasibility studies and project designs, preparation of main project biddingdocuments, and securing of construction permits. A poor MEsystem can make it difficult to establishattribution between the projects intervention and outcomes achieved.In this project, the ME system waspoor because indicators capturing the project outcomes were missing, and there was a lack of accurate data at appraisal to informtarget setting. These shortcomings handicapped thedesign of a results framework that could have clearly linked outcomes withthe project interventions.A poorly designed ME system not only limits attributing outcomes to the project but alsodisables triggers for corrective measures when implementation hurdles arise.
P102737 | IN: Bihar DPL | South Asia | India | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2008 | 2010 | 2011 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/127221474491178567/text/000020051-20140624165617.txt | http://documents.worldbank.org/curated/en/127221474491178567/pdf/000020051-20140624165617.pdf | The lessons presented in the ICR are well stated and supported. One additional comment is appropriate. While the complexity of this DPL might attract reasonable questions about the feasibility of its implementation, complexity per se is not necessarily a barrier to a successful outcome if there is broad-based ownership and all objectives are clearly stated and agreed. This is the main additional lesson from this operation.
P102768 | Strengthening India's Rural Credit Cooperatives | South Asia | India | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2007 | 2013 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/117211475118067753/text/000012394-20150309080038.txt | http://documents.worldbank.org/curated/en/117211475118067753/pdf/000012394-20150309080038.pdf | The ICR presents many relevant lessons that may be helpful to similar Bank operations elsewhere. Among them:Reforming rural cooperatives is complex and time consuming. As the task team has learned, it involves a shift in skills, management, governance and culture. Changes are needed in the internal process, operating system and product offerings. Each element takes time to evolve and mature. The projectâ€™s six-year life was not sufficient for the expected outcomes to be fully achieved.Governance reform of credit cooperatives is reinforced by a focus on credit risk management, including enhancing the capacity of staff and monitoring the operations. The outcomes on viability of project entities, which were exacerbated by external factors, could have been improved with stronger risk management capability.Governance reforms, designed to improve the alignment of interests between management, owners, and members, can enhance the efficiency and performance of the financial institutions. This project and the Governmentâ€™s revival package focused on enabling and supporting governance reforms. At project closure, and despite the adverse impact of global economic conditions and the Governmentâ€™s debt waiver decisions, the performance of project entities showed improvements as demonstrated by stronger capitalization and recovery rate rates for most of the participating entities and by the regulator's (NABARDâ€™s) audit results.
P102771 | Financing Public Private Partnerships (PPPs) in Infrastructure through Support to the India Infrastructure Finance Company Ltd | South Asia | India | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2010 | 2016 | 2017 | ICRR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/131541472772385460/text/ICRR-Disclosable-P102771-09-01-2016-1472772376075.txt | http://documents.worldbank.org/curated/en/131541472772385460/pdf/ICRR-Disclosable-P102771-09-01-2016-1472772376075.pdf | The firstthree lessons are drawn from the ICR (ICR, page 26), with some adaptation, and the last two, from IEG.One, the preparation of an infrastructure finance project requires both a conservative approach to projectsizing andintensive effort on pipeline assessment. It is particularly difficult, at the appraisal, todetermine the qualityofthe infrastructure projects to be financedbecause detailed projects assessments are not readily available, includingon safeguards and procurement issues. This calls for a conservative approach to project sizing. It also suggests thatdetailed pipeline analysis is needed. Testing the Banks safeguards andfiduciary standards on a representativesample of projects is necessary.Two, in implementing an infrastructure finance project, thestrategy should be:tostart small, to build in incentives, and to innovate on implementation arrangements. Small low-risk projects allow animplementing agency to gain experience. Financial incentiveshelp motivateproject developersto consider Banksafeguardsrequirementsand fiduciary standards. And new creative implementation approaches enable all parties toaddress bottlenecks.Three, investing upfront on capacity building is critical. Generous amounts oftechnical assistance, and of Bank staff time, are neededat the onsetin support of institutional capacity development atthe implementing agency, particularly for compliance with Bank requirements and for risk assessment and management.Four, some PPP financing schemes make the implementation of Bank safeguards and fiduciary standards inordinatelydifficult.A financial intermediary that takes a minor financial stake in a project exerts little leverage on theproject developer. A financial intermediary thatassumesa last mile financier function takes on aproject for which procurement contracts have been bid and awarded. A lead bank role for the financialintermediary may obviatesome of these difficulties, butofferslittle guarantee that other members of the financialconsortium will necessarilyconform tothe lead banks internal policies.And five, thepersistence of differences between the Bank and borrower governments onsafeguards and fiduciary policies, laws, regulations,standards and practices constitutea serious stumbling block to the design and implementation particularly offinancialintermediary loanoperations. Some convergence may have been achieved over time, but residual risks remain.
P102778 | Revenue Administration Modernization Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2007 | 2015 | 2018 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/116671530127495410/text/Croatia-REVENUE-ADMIN-MODERN-RAMP.txt | http://documents.worldbank.org/curated/en/116671530127495410/pdf/Croatia-REVENUE-ADMIN-MODERN-RAMP.pdf | The following mainlessons are fromthe ICR:Projects that are primarily geared toinstitutional reform should focus on change management components and activities even if these represent only a small part of theproject cost. The projects fundamental task was tax administration reform. The civil works component was adistraction to this.From the outset,during preparation,attention should have focused on building ownership forthe institutional reforms within CTA management and among other key internal and external stakeholders. These institutional reformsshould have remained the focus of the project throughout project implementation.Institutionalstakeholder assessments and regular stakeholder consultationsare a keyrequirement for institutional reform projects.Change management projects are likely to face institutional resistance. Undertaking a broad stakeholder assessmenthighlights where the support and resistance to the reforms would come from. Such anactivity at the institutional level wouldhave allowed the Ministry of Financeand the CTA to develop a change management plan including all the CTA management.Repeating this exercise periodically, when there were changes in institutional leadership would have helped inform and strengthenownership among new stakeholders. Thiscould have helped overcome resistance to use of project proceeds for training, advisoryservices and stakeholder engagement activities. In the event those responsible for leading and implementing the change process werenot sufficiently consulted and involved and the projectsuffered without thiscommitment.Projects should allocate adequate time for the implementation of complex ICT systems andensure that dispute resolution arrangements are in place and used promptly. Complex ICT projects are frequently subject toimplementation delays, often because of disagreements between the purchaser and the supplier. In retrospect, the two-year projectextension approved for the implementation of the CRMS was based on a best-case implementation scenario. When a dispute arosebetween the purchaser and the supplier, there was inadequate time to resolve the dispute and then complete implementation. Therewere dispute resolution arrangements in place, but the parties were slow to bring these to bear. The availability of an experiencedIT professional to advise the authorities could have helped them take this decision at an earlierstage.The World Bank should ensure continuity in task team leadership to the extent possible.Maintaining continuity in task team leadership is difficult, but the Bank could commit to ensuring that the task leaderthat prepares the project also starts the implementation. This would focus more serious thought on implementation, results andME. World Bank management should place more emphasis on the need for athorough handover process. The Bank could alsoempower country office staff to play a more important role as co-task team leaders,where appropriate, to provide forlonger-term continuity.
P102778 | Revenue Administration Modernization Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2007 | 2015 | 2021 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/762091595860605750/text/Croatia-Revenue-Administration-Modernization-Project.txt | http://documents.worldbank.org/curated/en/762091595860605750/pdf/Croatia-Revenue-Administration-Modernization-Project.pdf | 3. Lessons â€¢ Poor quality at entry and lack of readiness for implementation contributed to significant implementation delays and limited results. This occurred despite concerns voiced during the World Bank's internal review process about the adequacy of preparation before the project was sent the Executive Board for consideration. Expedited project preparation left critical aspects of design to the implementation stage, and these were not significantly reversed during implementation. â€¢ Given that the main driver of the tax administration reforms was Croatia's bid for membership of the EU, the project could have better secured the government's commitment to reforms up front. Reforms such as greater administrative and financial autonomy of the CTA, or tax policy reforms to broaden the tax base, would have enhanced the effectiveness of tax administration. â€¢ In projects to improve tax revenue administration, the right balance must be struck between institutional reform and the hardware component (buildings and ICT). The project's theory of change rightly emphasized synergies of business process reform, training, and organizational consolidation. However, proper sequencing is critical to effectively address issues of technical capacity and ownership. Project implementation initially emphasized civil works and IT infrastructure, to the detriment of institutional reform, and as a result little progress was achieved in CTA modernization until the project's restructuring, when the civil works were dropped. â€¢ High task team leader turnover could be mitigated by ensuring adequate capacity in the field with the presence of competent local staff. Had the World Bank secured local expertise to support implementation, the refocusing of the project on institutional gaps might have occurred earlier. More systematic handover of project leadership could have also mitigated the adverse impact of frequent rotation of task team leaders.
P102807 | Avian and Human Influenza Control and Prevention | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2007 | 2011 | 2013 | ICRR | Less than 10 million | Unsatisfactory | Highly Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/834041474509812934/text/000020051-20140625220812.txt | http://documents.worldbank.org/curated/en/834041474509812934/pdf/000020051-20140625220812.pdf | The ICR identifies a number of lessons, including:The emergency nature of an operation should not be a reason to compromise quality at entry. Poor quality at entry in many areas handicapped implementation.Emergency operations should not set an unrealistic timeline (two years in this case) for implementing complex capacity building operations.Long-term underfunding of veterinary service departments leads to weak agencies with little capacity to respond to animal health emergencies when they arise.Tax exempt status for imported goods should be carefully clarified with the government during project appraisal, to avoid slowing implementation.Clear plans and commitments need to be made for how supervision support will be budgeted for trust fund financed operations that do not cover supervision costs.
P102915 | Re-engagement and Reform Support Program | Western and Central Africa | Liberia | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2009 | 2009 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/881091474397747785/text/000146597-20140619152319.txt | http://documents.worldbank.org/curated/en/881091474397747785/pdf/000146597-20140619152319.pdf | IEG concurs with the lessons drawn in the ICR. A well-designed program, strongly supported by the government, is a key for successful implementation of an operation. Close cooperation with other donors is also an important factor in institutional reforms operations. The Bank should continue to support economic reforms in the country as well as target government capacity building and rebuilding data collection institutions in the country.
P102931 | Ministry of Public Works Institutional Strengthening TAL | Latin America and Caribbean | Chile | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2007 | 2014 | 2016 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/227861468180534749/text/ICRR14899-P102931-Box394888B-PUBLIC.txt | http://documents.worldbank.org/curated/en/227861468180534749/pdf/ICRR14899-P102931-Box394888B-PUBLIC.pdf | One important lesson was selected from the ICR, with some adaptation:Institutional change that involves organizational change requires intensive communication and participation of all stakeholders as well as strong ownership of leaders to ensure support and continuity of the reforms. A strong champion for the reforms is not always sufficient; if there is no uptake by other stakeholders. The following lesson was identified by IEG:Technical Assistance and Development Policy loans could complement each other in leveraging institutional reforms, in particular when policy prior actions have sufficient institutional depth to trigger policy/ institutional change. This TA project was designed together with a development policy loan (DPL) to provide technical support over five years following the DPL. The DPL's prior actions, however, were largely process-oriented; the reform laws that were in draft version at the time of DPL have never been adopted- despite Bank's continuous engagement through this complementary TA project.
P102971 | Natural Resources and Environmental Governance Project | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | DPF | 2008 | 2009 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/380701474595840851/text/000020051-20140625083557.txt | http://documents.worldbank.org/curated/en/380701474595840851/pdf/000020051-20140625083557.pdf | The ICR identifies a number of lessons:Shifting from investment projects to sector budget support can increase government ownership and improve dialog between agencies. Government buy-in is much stronger when they feel more completely in charge of the agenda and strategic decision making. Dialog between agencies is improved when they work together on budgeting of a joint program with less direct involvement from the Bank.A lack of upfront sectoral strategic and budgetary plans can reduce the impact of sectoral budget support. If they need to be improved, this should be formalized within the framework.A program framework that concentrates on outputs will not be useful during implementation and will be unable to demonstrate results. A framework should be based on sector strategies rather than substituting for them.Development policy lending has limitations when used as the only vehicle of support, and may be more effective when combined with other instruments (such as a technical assistance facility). It may be difficult to achieve policy reform and to improve sector management systems through a single instrument.The dual complexities of a multi-donor approach across multi-sectoral work add significant challenges to design and supervision, and multiply transaction and processing costs. Alternative approaches may have been for different donors to explicitly lead support different technical areas, to differentiate disbursement triggers across donors based on sectoral leadership, or to coordinate donors based on unity of purpose rather than unity of instrument.Complex policy reforms can be hindered by the annual processing requirements of a programmatic DPO with 12 month projects. This design means that there is only a 6 month gap between disbursal of one operation and the delivery of prior actions for the next operation, leaving very little time to discern outcomes from the previous set of actions.IEG also finds that:The need for consensus and harmonization in multi-donor operations reduces the ability to adjust programs during implementation.There is a risk that sharing design and monitoring of program triggers and indicators with other development partners will lead to a system that does not focus on key policy results and/or does not provide sufficient evidence to meet Bank accountability requirements.
P102971 | Natural Resources and Environmental Governance Project | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | DPF | 2008 | 2009 | 2014 | PPAR | >=10 million & <25 million | Moderately Satisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/816671468030535916/text/889590PPAR0P1000Box385285B00PUBLIC0.txt | http://documents.worldbank.org/curated/en/816671468030535916/pdf/889590PPAR0P1000Box385285B00PUBLIC0.pdf | 6. Lessons 6.1 The experience of NREG offers a number of useful lessons about using development policy operations for sectoral interventions, about donor harmonization, and about natural resource management. Lessons about Development Policy Operations 6.2 Earmarking funds from a DPO to specific agencies can partly undermine the choice of instrument. It can shift perceptions of responsibility by agencies to the Bank rather than to the government, it can disrupt the relationship between the finance ministry and the line ministries by inserting the Bank, and it can mean that responsibility for the operation is delegated from government to the agencies reducing overall government program ownership. In this case, it led to the program to be implemented more along the lines of investment lending projects at the agency level â€“ though without the financial management, procurement, or safeguards required for investment lending. 6.3 There is a risk that in sectoral DPOs with one-year operational cycles, technical and policy advice to the client can be crowded out by processing requirements. In this program, the short period between disbursement of one operation and assessment of triggers for the next meant that only moderate progress could be made under each operation. Combined with the large number of outputs and targets being tracked, this meant that much of the supervision process focused on verification rather than client support and engagement. A short program horizon also led to selection of very intermediate outcomes for program development objectives, which meant that the program framework and monitoring and evaluation progress were not focused on addressing the main outcomes of concern in the sector (resource degradation, environmental damage, etc.). 6.4 Program documents should clearly distinguish between the description of policy areas and the program being implemented, the specific prior actions and triggers, and the indicators needed to assess performance. Prior actions and triggers are disbursement conditions, meant to represent the elements of the program critical for success or reforms that are politically difficult to produce. A DPO does not need to formally track the production of every output in the program. Creating too many output-oriented targets can cause agencies to focus on producing specific outputs, at the expense of more outcome-oriented policy progress. Outcome indicators should be separate from the disbursement condition verification process, and should be selected to provide useful information to guide the program during implementation, and to allow assessment of progress on broad outcomes of interest. Development policy operations require trust in government that they will do the right thing, rather than a design that micromanages the program. 6.5 In this program, some triggers and targets were useful, while others were focused on outputs of secondary importance that arguably could have been included in the program without being formal disbursement conditions or targets. Some triggers and targets were quite subjective, which added tension to the verification process. 6.6 Sectoral development policy operations may need complementary technical assistance and support. Sectoral DPOs are implemented by line ministries that often do not have the skills or capacity to implement policy reform programs quickly, and so may require high levels of client support and engagement. Donors cannot expect that government will necessarily purchase its own technical assistance with budget support funds\. developing country governments are often reluctant to pay for expensive international experts, even when that technical expertise may be valuable. In this operation a lack of technical assistance arguably led to delays and difficulties in some of the more complex activities, like the design and implementation of the wood tracking system. Particularly in sectors with complex political economy and social dynamics such as natural resource management, a lack of accompanying tools (such as rigorous political economy and/or social analysis) conducted upfront make it difficult to address underlying problems. 6.7 Sectoral development policy operation programs should include a long-term plan for addressing what will happen at the end of the program. If budget support funds are used to significantly increase the budgets of specific agencies, then there are risks that progress will not be sustained when donor support ends at the end of the program. Explicitly planning for the transition period at the end of programs might help to reduce these risks. Lessons about donor harmonization 6.8 Donor harmonization is important, but has tradeoffs. Large, harmonized programs can have higher reach and a greater ability to function as a single platform for sector reform. But coordination between donors adds significantly to preparation and supervision burden, which may reduce the time left for wider stakeholder outreach. A clear and formal division of labor between development partners within the harmonized program could help to reduce this burden and improve the accountability of individual donors. If such agreements are informal then they may not last as staff turnover occurs, accountability may be dispersed, agencies may not focus efficiently on providing specialist expertise, and duplication may emerge. There needs to be a clear understanding and formal agreement between partners about monitoring and evaluation and who in government will be accountable. Harmonized programs may also be less flexible, as the agreement of all partners is needed before major design frameworks can be revised. A key challenge for harmonization is that each agency has its own rules and procedures, and there may be significant differences across agencies in expectations (for example, the Bank's DPO instrument is not the same as sector budget support instruments of other donors). 6.9 Introducing parallel financing into a sector with harmonized budget support can fracture harmonization. It can encourage government agencies to focus on bilateral relationships with individual development partners rather than engagement through the harmonized mechanisms. Lessons about Natural Resource Management 6.10 Civil society can play a useful role in natural resource management if government and civil society groups are able to collaborate productively. This requires government ministries and agencies that are willing to listen and act collaboratively, and civil society groups that can coordinate to focus messages and engage in a productive rather than purely adversarial manner. Donor pressure can have a positive role in improving this relationship. 6.11 Addressing social conflict is important, but progress is difficult to assess without social assessment analysis that describes the causes of conflict and measures conflict levels and changes over time. Tracking tools that are not connected to an ability to take actions may have little impact. 6.12 Creating and publishing environmental ratings of large companies can help to provide public pressure on the private sector to improve their environmental performance. Self-reporting backed by audits and inspections can be a cost-effective means of generating ratings if the process is designed in a way to avoid governance risks, such as by having a clear rules-based methodology for translating data into ratings.
P103022 | Ethiopia Protection of Basic Services Program Phase II Project | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2009 | 2013 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/708581474941666410/text/000180307-20141203044050.txt | http://documents.worldbank.org/curated/en/708581474941666410/pdf/000180307-20141203044050.pdf | Drawn from the ICRR process:Â· Setting project outcome targets that support a national program is challenging. While they can promote consistency and Government buy-in, they also lead to the setting of goals that makes it difficult to assess project achievementLessons drawn from the ICR (abridged):Â· The PBS has successfully promoted decentralized service delivery through the use of country systems. While this requires significant implementation support and capacity development, it is crucial for strengthening decentralized service delivery.Â· Some areas of change require more time and are difficult to predict. Areas like social accountability and financial transparency need time for â€œchanging mindsetsâ€ and this factor is difficult to predict when setting targets and evaluating a program. Â· PBSâ€™s strengthened implementation further enhanced aid effectiveness. PBS II provided dedicated resources to strengthen program monitoring, national data collection and M&E systems.
P103037 | Electricity Expansion | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2010 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/159851548970150533/text/Kenya-KE-Electricity-SIL-2010.txt | http://documents.worldbank.org/curated/en/159851548970150533/pdf/Kenya-KE-Electricity-SIL-2010.pdf | The following key lessons were derived from the projects implementation experience (IEG formulated the lessons because theICR provided the underlying discussion but did not explicitly articulate the lessons):The inclusionof mini-grid and off-grid components in a large energy supply expansion and accessproject requires focused attention,substantial implementation support, and sustained monitoring and follow-up. The projects much larger componentsrelated to generation and transmission, anddistribution claimed much of the attention throughout the project cycle, at theexpense of providing the critically needed support for the relatively smaller and newer mini-grid and off-grid components, whicheventually had to be cancelled. The inclusion of such components in acomplex project that covered geographically diversegeneration, transmission and distribution components is not optimal as the smaller components eventually receive littlesupport.Top management support for community-based approaches and the commitment ofsignificantresources are required for the successful scaling-up of electricity connections in poor urbansettlements. The top management of KPLC adopted a strong, community-based approach to (I) connect slum dwellers inurban areas and move them away from informal access to illegal and poor-quality electricity, and (ii) to expand lastmile access. KPLCs focus was less on simply taking down illegal connections, and more on listening to thecommunity members and marketing the safety, reliability and affordability benefits of legalconnections.The output-based aid (OBA) approach can be effective in subsidizing and expandingelectricity connections.The OBA mechanism enabledthe implementation agencies to shorten procurementprocessing periods--typically longer in standard Bank procurement--and be more responsive to their customer base. However, adequateresources need to be available to the agencies in order to fund up-front costs. When resources are scarce, revolving fundscould be used.Renewable energy lends itself toalternative models for scaling-up with privatesector financing. Kenya is seeking to attract long-term private investments to sustain its development of domesticrenewable energy. This approach has already resulted in significant private investments in generation, now accounting for 30percent of installed capacity.The Banks financing helped the Government demonstrate the viability of large geothermalcapacity development; moreover,the projects operational lessons will be useful to the Geothermal Development Company andthe Kenya Electricity Transmission Company in seeking alternative approaches to infrastructure expansion that involve financingother than government sources.The ICRs Section 12 raises two important issues that are notreallyLessons and Recommendations as such(pages 41 and 42).However, given their importance and for learningpurposes, those two issues are noted here, i.e.,the lack of transmission capacity (paragraph 155) and the inadvisable use ofa system loss indicator. Paragraph 155highlights the highly important strategic issue that the government was pushingstrongly for universal access despite the shortage in high- and medium-voltage transmission and distribution (TD)network.At the same time, there was a considerable expansion of the low-voltage network and distribution lines to connect newcustomers. As a result, the power generated could not be evacuated to the burgeoning volume of consumers.Thegovernments strategy in the face of this gap and the Banks advisory and funding role needed further evaluative assessmentin the ICRin orderto arrive at the relevant lessons and recommendations.Paragraph 156 is alsoraisesan issue that merited further analysis. The ICR questionsthe inclusion ofsystem losses asanindicator, by indicating that such an indicator would beappropriate in cases where there is a mature and staticsystem with minimal variations in supply and demand.However, the ICR argues that such a system could not be expected whileimplementing the projects large and dynamic interventions that cover generation, transmission and distribution.Moreover,the optimum loading of the TD components could only be expected one to two years after commissioning.Thus,measuring the system loss indicator during project implementation was premature and inadvisable becauseimprovements in system losses are likely to be realized only after project implementation. While this is a validpoint, the ICR also needed to conduct a linked analysisto the foregoing issue of transmission capacity shortages, whichsignificantly influenced the variability in generating supply and meeting demand (as indicated earlier, OlkariaIsoperation had to be curtailed because the electricity generated could not be evacuated).
P103160 | Pakistan: Social Safety Net Project | South Asia | Pakistan | Blend | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2009 | 2017 | 2018 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/253791529694828105/text/Pakistan-PK-Social-Safety-Net.txt | http://documents.worldbank.org/curated/en/253791529694828105/pdf/Pakistan-PK-Social-Safety-Net.pdf | The ICR (pp. 25-26) presented several useful lessons, augmented here:1. Design of major social safetynet programs benefits from analysis of the shortcomings of past programs in-country as well as international experience.Pastsocial safety netinterventions in Pakistan suffered from inadequate institutional arrangements and lack ofcoordination among diverse agencies andsafety netprograms, as well as political pressures and governanceissuesthat compromised objective targeting. Providing a clear analysis of these past shortcomings to the governmenthelpedBank staff lay the foundation for this project in terms of the needed political leadership, broad ownership and clearorganizational structures, accountabilities, and coordination mechanisms for an improved program. The designofsafety netprograms should start by analyzingcurrent needs, the policy environment, andlessons from pastefforts, and then identify therequired improvements,optimal institutional structure,and best meanstoprovide sufficient technical assistance for that structure. 2. Linking atechnicalassistanceor investment operation to a development policy credit with clear milestones for achieving progress helps toincrease leverage and ensure sustainability of policy and program reforms. In the case of this series of projects, momentum gainedby the pairing of the projects also helped leverage additional donor financing which materialized in the Additional Financing, andthe use of disbursement-linked indicators provided a common framework for donors and incentives to government institutions forspeedy implementation.3. Assembling and maintaining a task team with the necessary background, skills, andcountry knowledge and maintaining their involvement in all related operations, combined with a significant and high-levelpresence in the country -- provides important technical continuity for a complex operation. The depth of involvement and high levelof staff continuity in implementation of these projects (the technical assistanceproject and development policy creditin the first phase,and the additional financingandUK Department for International Development trustfundafter restructuring), provide a good-practice case of staff continuity.4. Calling on all involveddonors to embrace the same umbrella objectives, use a common results framework, and harmonize complementary assistance streams canimprove project outcomes and learning for all. In the case of these projects (technical assistance and development policy credit),the continuous involvement of UK DfID (from preparation through implementation of both phases) provided essential technicalassistance and significant traction for activities to gain momentum. In addition, the involvement ofthe United States Agencyfor International Developmentand Asian Development Bankin providing complementary assistance to programsthat willhelp BISP beneficiaries graduate from cash transfer assistance shows promisealso toyield benefits forexpanded, well-coordinatedsocial safety netprograms in the future.5. In an operation thatinvolves service delivery to the poor, it is important to build in earlyprocess evaluations early that analyze costs to thebeneficiaries, or other factorsthat may limit their access or full value received from the program. In this project,the pairing of process evaluations in the early stages, with piloting of specific solutions (technology-based payment systems), ledto improvementsthat plausibly increased beneficiary satisfaction to 97% by project closing. The use of suchtechnology-based systems may provide useful lessons for implementation of similar programs in other country contexts, but pilotingis recommended to test contextual sensitivity.
P103189 | Africa Stockpiles Programme - Project 1 (Mali, Morocco and Tanzania) | Other | Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2006 | 2013 | 2015 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/451831475093404498/text/000012394-20150409080856.txt | http://documents.worldbank.org/curated/en/451831475093404498/pdf/000012394-20150409080856.pdf | The following lesson is drawn by IEG:Multi-regional, multi-country Adaptable Program Lending operations present considerable implementation challenges which are unlikely to be successfully addressed unless the anticipated synergies, economies of scale or other advantages of the project design are clearly shown to be concrete and readily achievable. Complex regional, multi-country operations like the present one necessarily carry higher risks/barriers to effective implementation than individual country-based projects. The cumulative weight of these risks can severely impede project implementation at both the regional and national levels. For this reason, a thorough evaluation of the anticipated benefits of a regional project design and the likelihood of their achievement should be undertaken before project design decisions are made. In this case, individual country operations would likely have achieved, or even exceeded, the results actually obtained, and at a lower cost in resources.The following lessons are drawn from the ICR with some adaptation of language:The Bank is not presently well equipped to handle multi-regional and multi-country programs. The Bank's internal systems are not geared for administering an umbrella program with multiple sub-projects in more than one region. Bank support for similar approaches in the future should weigh transaction costs and efficiency constraints in designing regional programs. Furthermore, the Bank's internal processing arrangements for regional/multi-national programs should be made sufficiently flexible to accommodate their characteristics and needs rather than applying coding and budget systems that hinder successful implementation.For multi-donor projects, clearly defined roles and responsibilities for all partners and their collaboration need to be agreed and operationalized prior to project effectiveness. The ASP was a complex program, which depended on close collaboration and cooperation among several partners, drawing upon their comparative expertise in pesticide management, project design, implementation, communications, and monitoring and evaluation. To ensure clarity for all partners, each entityâ€™s roles and responsibilities, together with guidance on how the partnership should function, should be defined and agreed on during project preparation. Concise time-bound and budget-related terms of reference for all partners, as well as clearly defined oversight and coordination responsibilities, would greatly improve project design and help to ensure smooth implementation.The dimensions of the task need to be carefully determined and sufficiently well-prepared before implementation. Project activities, such as a national obsolete pesticides inventory and a CESA, are lengthy processes but crucial for determining the dimensions of the disposal task ahead. Ideally, these activities should not be conducted during implementation as was done in this case; they should either be conducted during preparation or during a first implementation phase, followed by a second that comprises adequately timed and budgeted disposal activities. This could include an approach under which the inventory and the CESA are prepared simultaneously.
P103189 | Africa Stockpiles Programme - Project 1 (Mali, Morocco and Tanzania) | Other | Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2006 | 2013 | 2017 | PPAR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/168841477341223021/text/108524-PPAR-PUBLIC.txt | http://documents.worldbank.org/curated/en/168841477341223021/pdf/Ethiopia-Mali-Morocco-South-Africa-Tanzania-Tunisia-Africa-Stockpiles-Program-Project.pdf | 7. Lessons The ASP-P1 offers a number of lessons that may be instructive for similar environmental cleanup projects, as well as for broader environmental management operations. These include the following. Lessons for environmental operations\. Â· Investments in highly technical environmental cleanup operations often face significant unknowns with respect to the nature and extent of the pollution problem and the available options for remedial actions. They can require a rigorous preparation process to fully determine the scope of the operation. Shortcomings in preparation of the ASP-P1, which took more than four years, did not lead to an adequate determination of the scope and budget of the operation's interventions. Preparation of the ASP-P1 failed to fully determine the scope of the obsolete pesticide problem, and thus grossly underestimated both the amount of obsolete pesticides and associated wastes and the funds necessary to deal with them properly. Â· In environmental operations involving pollution cleanup, the design needs to ensure a careful balance between immediate remedial actions to address threats to human health and the environment and longer-term preventive measures to ensure that similar pollution problems do not recur. Project design should account for the fact that prevention is a long-term process and is likely to extend well beyond the timeframe of the remediation activities. Pollution cleanup activities dominated the project design and budget in the ASP-1 relative to important activities to prevent future environmental pollution. Certainly, the ASP-P1 activities aimed at eliminating the existing pesticide stocks and associated waste were important, but in order to break the cycle of re-accumulation and future risks, it would also be necessary to take appropriate measures, such as controlling imports and limiting the purchase/acquisition of pesticides from abroad to meeting specified needs, to prevent future accumulations and their environmental risks. In the end, as noted in the text, total project financing in most of the ASP-P1 countries was not sufficient to address both cleanup and prevention adequately. Â· In complex environmental cleanup operations, it may be more effective to employ existing environmentally sound technologies outside the country than to create new capacity for this purpose in-country. In the ASP-P1, the governments of the four countries that disposed of their pesticide stocks decided to dispose of them in high-technology incinerators abroad rather than install such capacity for a limited waste stream in-country. 28 Lessons for project design\. Â· A horizontal APL may not add efficiencies in preparation or synergies in implementation if country circumstances are significantly different and if there is little opportunity for intercountry cooperation and coordination. In its original conception, the APL should have provided the six countries in the initial phase of the ASP-P1 with greater efficiencies in project preparation and opportunities for increased cross-country cooperation in implementation, as well as prospects for follow-on investments in a subsequent phase. In the ASP-P1, however, the uniform approach to project preparation, with its standard template for project design, complicated rather than facilitated efficient project preparation. And the desired synergies among the countries in project implementation were never realized because of significant differences in country context. In the end, the subsequent phase was never realized because of the poor performance in the initial phase of the ASP-P1. Â· Complex international partnership arrangements, such as those in the ASPP1, can result in conflicts in defining roles and responsibilities, challenges in effective coordination, and confusion in project interventions. The partnership arrangements designed for the ASP-P1 ended up imposing a burden on project implementation rather than delivering the synergies and benefits originally intended. Within the Bank itself, the cross-regional design of the ASP-P1 created significant challenges for Bank supervision, monitoring, and evaluation. Â· During project design, calculating the benefits of reducing pollution risks to human health and the environment can pose a challenge, but should be undertaken to support cost-benefit and efficiency calculations. There were no financial or economic analyses performed for the ASP-P1 at appraisal, although there are simple methods and tools for approaching the valuation of economic and environmental benefits for environmental projects. The DALY tool developed by WHO is one example of an approach that can be used to measure reduced overall disease burden, as expressed in the number of years lost due to ill-health, disability, or early death. Lessons for institutional capacity\. Â· In terms of institutional capacity for project management, the drivers of success may not be readily identifiable in the implementing agency, but they should be nurtured and sustained to promote successful project implementation. The three countries the IEG mission visited had roughly similar levels of institutional capacity for implementing the project, but while Tanzania had a project champion and dedicated staff that drove project success, Morocco and South Africa never found similar leadership. Â· Programs run risks if they are designed relying on coordination and management functions executed by institutions that do not have sufficient capacity to perform these functions. In the ASP-P1, the PCU was designed to perform overall program coordination and management functions from its position within the institutional structure of NEPAD, but in the end, NEPAD did not have adequate capacity to carry out these functions. Â· Complex regional programs with multiple country projects can impose significant demands on Bank capacity and require focused and sustained supervision by Bank staff. The lack of sustained commitment to the ASP-P1 at the program level and rapid turnover of task team leaders managing supervision of country projects contributed to the highly mixed project outcomes and resulted in widely disparate treatment of the various participating countries.
P103238 | Vietnam Renewable Energy Development Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2009 | 2018 | 2020 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/531751567354139531/text/Vietnam-VN-Renewable-Energy-Development-Project.txt | http://documents.worldbank.org/curated/en/531751567354139531/pdf/Vietnam-VN-Renewable-Energy-Development-Project.pdf | The following lessonsare derived from the ICR (p. 33) with some adaptation oflanguage:1. A countrys enabling policy and regulatory environment is aprerequisite to successful project implementation.Due to the timely implementation of the ACT and SPPA, theprojectachievedfavorable results. The projectsubsequently provided regular updates of theACT, whichprovided transparency and confidence for the private developers to invest in RE development.2. Theproject design and stakeholders capacity should be complementary when determining the level ofproject complexity and role for TA. The project implementation period was underestimated, thus the TA was significantlydelayed in the initial years of the project and showed first signs of activity only 6 years after project approval. PMBscapacity was constrainedand had difficulty implementing the numerous and complexTA activities. The Bank teamsclose supervision as thePMB went through institutional changesmade the difference inachieving the favorableresults.3. The role of the private sector wasinstrumental in the projects achievement ofcommercial sustainability. Initially,it was difficult for the private sector to access financial resources todevelop small-scale RE projects. Undercapitalization issues andfew long-term sources of funding make it difficult fordomestic lenders in the long term.Because of the knowledge and capacity created by the REDP, PBs subsequently financed anadditional 1,500 MW of private sector-financed SHPs outside of the REDP lending envelope.
P103277 | Fourth Poverty Reduction Support Credit | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2009 | 2011 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/373701475081881732/text/000020051-20140624160415.txt | http://documents.worldbank.org/curated/en/373701475081881732/pdf/000020051-20140624160415.pdf | IEG broadly concurs with the lessons noted in the ICR, in particular, the lessons pertaining to the importance of government ownership of the reform program and good donor coordination:(i) importance of strong government ownership, taking the time to nurture it, through dialogue and analysis of the political economy of reforms; and (ii) working together with the rest of the donor community through the G-19 is helpful, notwithstanding the difficulties and tensions resulting there from and in particular the rigidity of the PAF.
P103277 | Fourth Poverty Reduction Support Credit | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2009 | 2016 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/746821469129481595/text/106459-PPAR-P083459-P103277-P107313-Box396277B-OUO-9-mozambique-0716.txt | http://documents.worldbank.org/curated/en/746821469129481595/pdf/106459-PPAR-P083459-P103277-P107313-Box396277B-OUO-9-mozambique-0716.pdf | 11. Lessons The following lessons have been drawn from this PPAR\. Â· Carefully chosen objectives and prior actions for policy development operations can provide the basis for the necessary conditions for better macroeconomic policy, good governance, and sound economic development. In the short term a number of reforms can be achieved either because of or in the wake of prior actions. For example the Central Revenue Authority was established in 2007 (a prior action for PRSC-4). Since then it received support from the Government of Switzerland (a member of the donor group providing general budget support) and performed well, raising tax collection from 15.9 percent of GDP in 2007 to 27.3 percent in 2014. Â· Policy development operations can reduce poverty by increasing growth and improving institutions that have responsibilities for poverty reduction, but that focus was not sufficient for significant poverty reduction in Mozambique. For example, GDP growth was sustained at between 6 and 7 percent per annum, prior actions requiring the Government to allocate at least 65 percent of its annual budget to priority sectors maintained the capacity of ministries that had a responsibility for delivering social services to the poor, and a number of social indicators was well maintained. However, the incidence of money metric poverty was reduced by only 4 percentage points over six years from a high poverty incidence of 56 percent in 2002/2003 to 52 percent in 2008/2009. Â· Development policy operations that use general budget support as the instrument for providing assistance can also be appropriate vehicles for the harmonization of donor strategic assistance. The Performance Assessment Framework agreed between the Government and general budget support development partners, if well crafted, can be the basis for fruitful cooperation among these partners. The downside risk is the possible constraint on the Bank's flexibility with respect to prior actions outside the Performance Assessment Framework. For example, the Bank needed to negotiate with general budget support donors to obtain their agreement to include additional actions on food security in PRSC-5 that were outside the Performance Assessment Framework. Â· The political economy context can have critical impacts on the achievement of policy reform. Understanding the political economy context for reforms in policy is critical to assessing the likelihood that reforms will take place. For example, a National Program for Decentralized Planning and Finance was to have been achieved as a prior action for PRSC-5. However, the political barriers to achieving internal agreement on a national plan for decentralized planning and finance were seriously underestimated and a plan was not approved by the Government during the PRSC 3-5 series.
P103343 | National Emergency Rural Access Project | South Asia | Afghanistan | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2008 | 2014 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/774501475115342860/text/000020051-20150113005755.txt | http://documents.worldbank.org/curated/en/774501475115342860/pdf/000020051-20150113005755.pdf | The ICR (page 16) draws the following main lessons from this project.For a country emerging from decades of civil war, close coordination, collaboration, support and training are essential. Continuity of key staffing in both the implementing agencies and the Bank is very important, but hard to deliver, especially where the security situation remains poor. It is essential to keep the project design and the M&E system simple and monitor implementation capacity in countries like Afghanistan where security remains an issue. The experience of this project demonstrated that third party monitoring can be effective in such environments. For a simple project in post-conflict areas, a defined road design standard agreed during preparation can prevent significant cost and time overruns.For projects that warrant measurement of socio-economic indicators, it is crucial that the baseline and endline impact evaluation surveys be designed in a consistent and harmonized manner to ensure the usefulness between the two surveys.
P103441 | Second Public Expenditure Management | Latin America and Caribbean | Chile | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2008 | 2014 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/224871468178156586/text/ICRR14712-P103441-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/224871468178156586/pdf/ICRR14712-P103441-Box393183B-PUBLIC.pdf | The ICR has very thorough coverage of the lessons, which are presented below:Inadequate allocation of time for developing, testing, incorporating user feedback, updating and rolling out an financial management information system (FMIS) can delay planning and implementation of the FMIS. Reflecting on existing wide-scale international studies (that were not available at the time of designing this project) can help in designing future projects in improving the effectiveness and efficiency of FMIS.While the use of the most state-of-the-art and newest technology available can provide benefits, it may also imply additional risks for implementation. It is important to balance these risks against the benefits. Using such technology can confer important benefits, including increased usability, while perhaps lessening the need to engage in as many updates in the future. However, potential risks include more expensive and lengthier implementation periods. In the case of SIGFE II, these risks associated with the use of such technology materialized. There is no easy answer as to whether a big-bang approach or a gradual implementation process for FMIS is the better approach. Both approaches have their challenges, and what is the correct approach depends on the country and its systems. In the case of Chile, the decision to proceed gradually allowed it to initiate implementation (and deal with the issues that arose) without risking impacting the entirety of the government, and shift towards a more aggressive strategy only when such problems had been addressed. Nevertheless, this strategy had its costs â€“ requiring that resources continue to be allocated to both the old system and the new one â€“ and may diminish individual institutionâ€™s incentives to transition to the new system. Project design and supervision needs to manage political transitions in FMIS, as FMIS are designed to extend beyond one political administration. In the case of this Project, while political changes resulted in some slowing of implementation and the re-prioritization of non central activities, roll-out of the SIGFE II was able to successfully continue given the strong technical orientation of the work and an institutionalized foundation that transcended government administrations.
P103457 | Community Based Settlement Rehabilitation for Yogyajarta | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2011 | 2015 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/649821467920706980/text/ICRR-Disclosable-P103457-07-07-2016-1467920689592.txt | http://documents.worldbank.org/curated/en/649821467920706980/pdf/ICRR-Disclosable-P103457-07-07-2016-1467920689592.pdf | The ICR provided a list of 6 lessons, based on which this review highlights the following:1. ExistingCDDcapacity can bequickly mobilizedto launch aneffectivepost-disaster reconstruction project. CSRRP was built on the on-going successful Bank CDDprojects in the project areas. This allowed for a fast mobilization of communities and initialization of the reconstructionprogram, owing to the availabilityof skilled candidatesfor consultants and facilitators and the motivation andcapacityof communities and local governments. To beeffectivein implementingcommunity infrastructureandbasic investment programs, however, the coordination on processes between the communities and local governments and amonggovernment agencies themselves are crucial.2. Post-disaster reconstructionprojectsshouldtake accountof theneedsfor the recovery of livelihoods for affected communities.. Basic investments in livelihoodprogramscan be aligned with and complementary to effortstohelp reconstruct housing and communityinfrastructureafter disasters.It is especially relevant for reconstructionafter a disaster where the affectedpeople need to be relocated tosafer sites and are thus more likely to lose their livelihoods, as in a case of the Merapivolcano eruption.3. Community Settlement Plans (CSPs) can be used forsupportingcommunity-based planningat the local government level. The project initially encountered someissues on the coordination between the CSP processes and local government plans. The first additional financing addressed this byproviding more proactive support ontraining and capacity building in this area, including capacity building for localgovernments. Now CSPs have evolvedinto a medium-term planningtoolof local governments in Indonesia. They are usedas a reference in governments annual planning meetings, for example.To be sustainable, local governments need tofacilitate and support the CSP processesat thevillage level.
P103457 | Community Based Settlement Rehabilitation for Yogyajarta | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2011 | 2015 | 2020 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/405611581458549055/text/Indonesia-Community-based-Settlement-Rehabilitation-and-Reconstruction-Project-for-Central-and-West-Java-and-Yogyakarta-Special-Region.txt | http://documents.worldbank.org/curated/en/405611581458549055/pdf/Indonesia-Community-based-Settlement-Rehabilitation-and-Reconstruction-Project-for-Central-and-West-Java-and-Yogyakarta-Special-Region.pdf | 7. Lessons 7.1 A community-based approach to postdisaster reconstruction can be effective and efficient in a context in which there is prior experience and existing institutions and cultural norms that favor it. Although a community-based approach has certain appeal and can facilitate successful reconstruction after natural disasters, this success is dependent on several preconditions, including a supportive social environment within affected communities. After the earthquakes, the reconstruction benefited from fortuitous circumstances that may not be present in other postdisaster situations. The World Bank learned from its prior experience with the less-effective community-based reconstruction in Aceh and had two ongoing projects, KDP and UPP, in the affected areas that also used a community-based approach and facilitators. Funds from the UPP were available for reconstruction before the JRF became effective. The first interventions after the earthquakes involved more than 150 villages that were part of the UPP, and 200 of the project's facilitators were almost immediately available to work with the CSRRP. The World Bank's team leader for UPP and a community recovery project in the earthquakeand tsunami-affected areas of Aceh and North Sumatra was also the team leader for the CSRRP. Furthermore, the Javanese cultural practice of gotong royong was compatible with the approach, and local and provincial governance, notably in the special region, was strong, effective, credible, and intact (MacRae and Hodgkin 2011).32 The CSRRP adopted UPP's local, provincial, and national oversight systems, and the JRF's executing agency, the MPW, had also worked with the World Bank during the reconstruction in Aceh. Finally, after Mount Merapi's eruptions, most villagers were successfully relocated to land they already owned collectively. This situation solved the common problem of finding suitable areas for relocation after a disaster (Maly, Iuchi, and Nareswari 2015). This was especially meaningful because most of the relocated people were farmers who could still use the land they had farmed before the eruptions. 7.2 Decisions about the suitability of a community-based approach after future disasters need to consider which of these factors are essential before choosing a community-based approach. The availability of a sufficient number of experienced facilitators and a functioning banking system fall into the latter category. However appealing the approach may be, it is not necessarily well suited for other countries or perhaps even for other parts of Indonesia.33 After more than a decade of experience with CDD in Indonesia, including the CSRRP's completion of all earthquake-related construction, the World Bank (2011c, 16) concluded, There is little documentation of what specific aspects of CDD projects work or do not work well in a postdisaster context and why. 7.3 Careful attention is essential in deciding who will be assisted financially in reconstructing homes, the amount of assistance to be provided, and the perceived effects and consequences of these decisions. For the victims of the earthquakes, the CSRRP had to decide how to allocate scarce resources considering the level of damages sustained and occupants' ability to cover their own costs of reconstruction. After the earthquakes, project staff and villagers developed lists of homes that had been destroyed or that had suffered the most damage, but this was often a laborious and timeconsuming process. The CSRRP provided equal amounts of assistance irrespective of their owners' relative wealth or ability to pay. This approach was easy to implement, although it advantaged well-to-do villagers at the expense of the poorest community members, whose homes may not have been destroyed or severely damaged but who could not afford to repair the damage that had occurred. Favoring some groups relative to others can raise concerns about equity and fairness during a period of high social and economic vulnerability. The decisions required are not likely to be simple or straightforward. 7.4 The right level of assistance was not easy to determine. Initially, $2,200 was deemed an appropriate amount. In the special region, the separate government-sponsor reconstruction program provided grants of approximately $1,650 per household. After the volcanic eruptions, the CSRRP increased the per-household amount to $3,300, but this amount was higher than any increases in the rate of inflation and possibly more generous than necessary. 7.5 The disaster resilience of housing can be undermined when projects and processes do not sufficiently consider and accommodate the likelihood of postconstruction renovation and enlargement, especially when there is lax or limited enforcement of building codes. The CSRRP was successful in providing earthquakeresistant core structures, but this did not ensure that homeowners would subsequently retain this resistance after being enlarged or expanded without building permits, without professional supervision, and without considering whether doing so would increase the homes' vulnerability to earthquakes. Such a possibility might be mitigated by changes in the design of reconstructed houses and better enforcement of permitting requirements. Unfortunately, improved postdisaster enforcement of building standards must contend with political priorities that favor the allocation of benefits rather than the imposition of unpopular restrictions. These priorities are well beyond the control or influence of most projects. 7.6 Community settlement or similar development plans may not meaningfully support disaster risk reduction unless these plans meet what may be several essential conditions. Based on the CSRRP's experience, these plans can enhance disaster risk reduction when they are (i) perceived as valuable and comprehensible to their intended users, (ii) well-integrated into the plans of higher-level governments responsible for disaster risk reduction, and (iii) routinely updated. Balancing beneficiaries' essential and immediate needs for housing is a challenge when these plans seek to address events that may never occur. 7.7 Women's participation in CDD is a challenge to ensure when their interests, experiences, and perspectives are not properly considered in a project's design, such as through a gender analysis that identifies potential opportunities and obstacles to their meaningful participation in decision-making. Although the CSRRP mandated that women have leadership roles in the project's community-led reconstruction efforts, the mandates did not guarantee that their participation would be effective or incorporate their perspectives in decision-making. 1 The Special Region of Yogyakarta is a provincial-level autonomous region and the only officially recognized monarchy within Indonesia. The special region is subdivided into four regencies or kabupaten (Bantul, Gunung Kidul, Kulon Progo, and Sleman) and Kota Yogyakarta, its capital city. 2For more information, see the Significant Earthquake Database, National Centers for Environmental Information (formerly the National Geophysical Data Center) at https\.//data.nodc.noaa.gov/cgi-bin/iso?id=gov.noaa.ngdc.mgg.hazards\.G012153;view=iso. The donors included the European Commission (the largest donor), plus Asian Development Bank, Canada, Denmark, Finland, the Netherlands, and the United Kingdom. 4As the World Bank (2008a, 2) explained, the government was unable to disburse funding quickly because of new regulations set by the Ministry of Finance regarding the management of government accounts. The new regulation prohibits the creation of master accounts by the ministry for projects, as proposed in the project. This situation delayed disbursement, but $10 million in retroactive financing had been provided in December 2006. 5See World Bank (2016), Summary of results of stakeholder workshop in Jakarta, November 12, 2015, Annex 6. In fairness to the project, the Ministry of Public Works also noted that many of these activities were undertaken during implementation. 6Although the project appraisal document had projected that as many as 1,000 houses in West Java would be reconstructed, the Community-Based Settlements Rehabilitation and Reconstruction Project did not fund any reconstruction of homes in the province. Local governments and national agencies, including the Ministry of Marine Affairs, assumed responsibility for all housing reconstruction in West Java. 7In contrast to the Java Reconstruction Fund, which initially provided grants of approximately $2,200 per household for reconstruction, the government's much larger reconstruction program provided the same amount per household in Central Java but approximately $1,650 in the special region. 8Each village typically has multiple subvillages. For example, Bantul district has 17 subdistricts and 75 villages, including Srimartani, which has 17 subvillages. The population of Srimartani is typically stated as the sum of the populations of the 17 subvillages. Without the subvillages, Srimartani would have no inhabitants. 9See Jha et al. (2010) for a useful discussion of who should receive support for reconstruction of their homes after a natural disaster. The report emphasizes that each disaster requires its own criteria for determining who receives assistance. 10World Bank (2007b and 2008a) had also identified problems with targeting of beneficiaries. Duplication of benefits is a common occurrence. Immediately after many disasters, multiple organizations provide humanitarian assistance that is not as well coordinated as might be desired. After an earthquake in Pakistan in October 2005, for example, the World Bank worked with 68 partner humanitarian organizations in nearly 22,000 villages. These organizations could intervene for reconstruction only after reaching an understanding with the government 's Poverty Alleviation Fund Project. After an earthquake in Nepal in April 2015, it took some time to streamline the recovery system and to identify who had received duplicate benefits. As of mid- 2019, the government has recovered approximately $2 million from beneficiaries who received housing grants from more than one source. 11See World Bank (2016), Summary of Results of Stakeholder Workshop in Jakarta, November 12, 2015, Annex 6. 12 Concern about the role of the World Bank's country office in Indonesia in the implementation of recipient-executed trust funds (RETFs) is not limited to the CSRRP. The Independent Evaluation Group identified similar concerns about the operational implications of managing the RETF for the Basic Education Capacity Project in Indonesia (World Bank 2014, 6). 13World Bank (2012) provides an e xample of what the project did to preserve Java's cultural heritage. 14 As the World Bank's country office in Jakarta explained, local governments provided approval in principle for the typical design before the reconstruction. Official applications for building permits were submitted only after the completion of reconstruction because of the large number of houses and the related paperwork. The retroactive approval process rendered moot a requirement that an application for a permit include signed permission from all owners of adjacent properties. This requirement should be put in context. Few houses in Indonesia receive building permits because of weak enforcement and limited government capacity. 15These results are also found in the Implementation Completion and Results Report (ICR; World Bank 2016). 16Hodgkin (2016) and Meindertsma and Ludwig-Maarof (2009, 33) reached the same conclusion\. The quality aspect only holds true for the CSRRPreconstructed houses. The high-level quality could not be achieved on reconstructed houses. See the letter from George Soraya, CSRRP task team leader, to Mr. Danny Sutjiono, Ministry of Public Works, October 31, 2007. 18Incremental housing represents a process in which homeowners improve or enlarge their homes as resources, time, or materials become available. For a discussion of some reasons for and benefits of incremental housing, see Wakely and Riley (2011). 19Ikaputra (2008) reported that 97 percent of houses in one village had been expanded. Ikaputra observed that most of the expansion in this village had been done in compliance with guidelines on structural frame extension. Maly, Iuchi, and Nareswari (2015) also found that a majority of new households had been expanded. 20Kwarsa Hexagon (2010) reported the same finding, namely that beneficiaries were not certain whether future expansion of their homes would be in accordance with the project's requirements because of price and economic considerations. See also Idham and Mohd (2018). 21The delays in completing community settlement plans (CSPs) led the government to extend the project's closing date so that the CSPs could be implemented ( World Bank 2008a). 22The independent assessment also found that the reconstructed housing had not been accompanied with appropriate facilities and potentially creates environmental problems in the future, for example, floor elevation at the same level as the yard, poor management of water supply and sanitation, etc. (World Bank 2008a, 30). 23See World Bank (2016), Summary of Results of Stakeholder Workshop in Jakarta, November 12, 2015, Annex 6. 24In the agency's defense, it was not created in the special region until 2011, so it could not have been a recipient of the CSPs from the earthquake-affected villages. 25Almost two years later, the World Bank noted th at the CSPs remain a very weak part of the current planning processes facilitated by the project (World Bank 2010, 3). 26As noted previously, most of the CSPs were completed after the reconstruction grants had been given to Kelompok Permukimans. 27Tickamyer and Kusujiarti (2012) studied gender relations in one village in Sleman and another in Bantul. See also IFRC and RCS (2009). 28Kwarsa Hexagon (2010, 8), in the midterm review, also found low levels of participation among all beneficiaries, noting that the extent of beneficiaries' participation in decision -making was very low. 29World Bank (2016) incorrectly noted that all the project's core houses had been constructed (that is, 17,769 = 15,153 after the earthquakes plus 2,519 after the volcanic eruptions) at 90 percent of the cost envisioned at appraisal ($42 million). In fact, the cost of reconstructing only the earthquake-related houses was $37.98 million. The ICR's calculations omitted (i) the $2.5 million the project received in the second additional financing in November 2010, a portion of which was intended to finance the construction of 172 new housing units after the eruptions, and (ii) the $11.5 million the CSRRP received in March 2011 from the Program Nasional Pemberdayaan Masyarakat Support Facility to provide approximately 2,500 additional housing grants for households displaced by the eruptions. 30The World Bank can execute activities through an RETF only in exceptional circumstances, such as when the recipient is a new member country or inactive borrower or when civil strife has adversely affected a government's administrative capacity. When the World Bank executes activities through an RETF, it can do so only upon a specific written request from the recipient with subsequent approval from a regional vice president, Global Practice vice president, or a managing director (World Bank (2015, 2â€“3). 31The special region has a well-respected hereditary sultan who concurrently serves as the region's unelected governor, in contrast to the elected governors in all other provinces. 32Erin Joakim (2013) provides additional examples of factors that facilitated the success of reconstruction after the 2006 earthquake. 33In July and August 2018, three strong earthquakes struck the island of Lombok causing widespread structural damage to shelter and public infrastructure. A Rekompak approach was used to assist with housing reconstruction and was considered less successful than in the CSRRP's three provinces. The post-tsunami reconstruction in Aceh also relied on a communitydriven development approach but has been severely criticized for its waste, ineffectiveness, and poor outcomes. As one author concluded, Before we become sanctimonious about the superiority and promises of the community development approach, it is important to acknowledge some of the difficulties in practice and the complexity of the relief and reconstruction effort in Aceh, adding, Some groups of survivors fared better than others. The more organized survivors, particularly men, negotiated better support than the less organized or less assertive groups (Kenny (2007, 212). Others who have noted Yogyakarta's unique situation include MacRae and Hodgkin (2011) and Maly, Iuchi, and Nareswari (2015).
P103466 | PRSC 2 | Western and Central Africa | Mali | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2009 | 2010 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/479861474397306532/text/Mali-Prsc-1.txt | http://documents.worldbank.org/curated/en/479861474397306532/pdf/Mali-Prsc-1.pdf | The ICR correctly identifies the two prime lessons from this experience. First, to have impact it is vital to be selective in reform proposals, and understand the political economy for their chance of success. Technical analyses prior to a PRSC series should be complemented by political economy analyses that can serve to identify reforms that have a reasonable chance of being implemented. Second, reform proposals should not be confined to statements of intention to reform but rather concretely focused on outcomes.
P103470 | Sustainable Financing & Management of Eastern Caribbean Marine Ecosystem Project | Latin America and Caribbean | OECS Countries |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2012 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/742711510327666620/text/ICRR-Disclosable-P103470-11-10-2017-1510327658473.txt | http://documents.worldbank.org/curated/en/742711510327666620/pdf/ICRR-Disclosable-P103470-11-10-2017-1510327658473.pdf | The following lessons, with some adaptation of language, have been selected from those presented in the ICR (p.25-26):Countries ability to match donor funds for each year for the next20 years or more needs to be assessed carefully during the project design phase. Especially countries facing economicdifficulties will find it challenging to enact tax laws or work with different industries to come up with the requiredfinancing.Mapping out detailed steps for activities that involve the government or other institutions, can beuseful to identify actions which are necessary to obtain the desired result. Often internal procedures that are requiredare often not obvious to the Bank team at the design stage, making appropriate time and budget allocationschallenging.Involving the Ministry of Finance in a multi-country environment project is critical since thatministry has the capacity to assess the financial aspects of the project and its potential results. In this project,countries that involved the Ministry of Finance demonstrated stronger performance
P103499 | Nigeria - Growth & Employment | Western and Central Africa | Nigeria | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2011 | 2019 | 2021 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/537581599851313782/text/Nigeria-NG-Growth-Employment.txt | http://documents.worldbank.org/curated/en/537581599851313782/pdf/Nigeria-NG-Growth-Employment.pdf | The ICRidentified several lessons and recommendations (ICR, paras 98-116) arising from the experience of the projectdesign and implementation. The most striking lessons are summarized and rephrased below: Toachieveexpected outcomes,the projectdesign needs to match the implementation capacity of the borrower, especiallyfrom the technical and governance perspective.In Nigeria, the activities of thisproject frequently exceededthe implementation capacity of the PIU, which lackedtechnical expertise. Multi-donorand largeprojectscan be effective in a complex environment, but borrower ownership and commitment need to be in place to ensurecoordination.For this project, IDAand DFID funding was brought together in support of theincreasedperformance of firms and competitiveness of strategic clusters. However, there was a lack ofadequate mechanismsforefficient coordination. For a large project to succeed, improved stakeholder assessmentandtransparent communication are central toensuring the buy in by key stakeholders,building partnershipsandmaintaining government commitment.The project team could not bring the new Government on board quickly, soas to carryout the blended DFID/IDA project in acoordinated manner.Under-performance in communicating about theproject goals and processes created a confusion in the public that was used todiscredit the projects goal and hinder itsfull implementation. The Bank team needs to proactively prepare to counter political interferenceduringproject implementation. For this project, incomplete and delayed design and slow implementation provided the opportunityfor lobbying that compromised the project.
P103539 | Conservancy Adaptation Project | Latin America and Caribbean | Guyana | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | GEF | IPF | 2008 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/746541474941214004/text/000020051-20150312115533.txt | http://documents.worldbank.org/curated/en/746541474941214004/pdf/000020051-20150312115533.pdf | IEG draws the following lessons from the experience of preparing and implementing this project:The outcomes of a project can be better evaluated if a restructuring, that significantly alters the focus of the operation, is accompanied by a formally approved change in the development objectives. This was recommended in this case by the project team at the time of the mid-term review, but was not carried out.Where, as here, the Global Environmental Objective is different from the project development objective, it is important to include activities in project design aimed at its achievement.Insufficient research on engineering and safeguard compliance requirements at the preparation stage can negatively impact project implementation and outcomes.The assumption that a project execution unit that has worked with other international development banks may be sufficiently familiar with World Bank procedures as not to require targeted training and capacity building may not be justified. A unit that is financed independently of the project, and continues to work on operations funded by other development banks, may not devote the required effort and attention to the project.A strongly designed M&E framework, with appropriate outcome and outputs indicators, is an essential tool for tracking progress as well as for evaluating results.
P103606 | Madagascar Sustainable Health System Development Project | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2007 | 2010 | 2011 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/367471475083440895/text/000020051-20140624162938.txt | http://documents.worldbank.org/curated/en/367471475083440895/pdf/000020051-20140624162938.pdf | It is critically important to build indicators directly measuring project objectives into the projectâ€™s results chain and M&E framework. In this case, despite great success in implementing a large and complex number of outputs in a relatively short period of time, it is not possible to assess the project as fully satisfactory because of the lack of evidence on achievement of the projectâ€™s specifically stated objectives.Proper attention to constructing pilots that are directly relevant to the objectives of the project, and to effective and prompt evaluation of those pilots, is essential for a successful contribution to long-term strategic objectives. In this case, baseline data were collected, and financing was provided for proper evaluation, enabling an informed decision on whether or not to scale up.
P103631 | Sixth Poverty Reduction Support Credit | Western and Central Africa | Ghana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2009 | 2010 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/301501474903490556/text/000020051-20140620084429.txt | http://documents.worldbank.org/curated/en/301501474903490556/pdf/000020051-20140620084429.pdf | One major lesson is that the dialogue in the context of PRSCs was clearly ineffective in influencing the government's policy of subsidizing electricity. Energy subsidies, including to the state-owned aluminum smelter, are a major drain on the budget, and other means will have to be found to strengthen this dialogue.A second lesson is that the PRSCs, although to a lesser extent than the debt forgiveness in the mid-2000s, while providing resources for social development, were counterproductive in their objective of promoting macroeconomic stability. The provision of generous budget support encouraged excessive public spending which eventually threatened fiscal sustainability.
P103633 | Second Central Transport Corridor Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2008 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/155141526651078531/text/Tanzania-TZ-Second-Central-Transport-Corridor.txt | http://documents.worldbank.org/curated/en/155141526651078531/pdf/Tanzania-TZ-Second-Central-Transport-Corridor.pdf | The first three lessons are taken from the ICR with some modification of language. 1 .In projects that cover more than one sub-sector involving multiple skill sets and several institutions, involvement ofthe main stakeholders, especially those at the leadership level, is essential for smooth project implementation. In thisproject, after initial delays at the start of the works contracts, progress improved remarkably upon the introduction of a BRTSteering Committee as a high-level coordination and decision-making body.2 . Adequate preparation inthe resettlement of PAPs (project-affected persons) is a critical requirement for a well-performing project. Delays in theimplementation of the RAP for the BRT, due to lack of funding, led to contractual disputes and termination of some the workscontracts as the site was not available to the contractor.3 . Ensuring the quality of engineeringdesigns at appraisal cannot be overemphasized. The need to make significant revisions to engineering designs afterproject effectiveness caused considerable delay during the BRT Phase 1 implementation. It also re-doing the PAPs census andproperty inventory, adding to the delays.4. Lack of appropriate indicators makes it difficult to report on relativeachievement of the development objective. The project design lacked relevant indicators to measure central aspects of the PDOwhich made it difficult to report on relevant project achievements.
P103639 | Eastern Nile Planning Model | Other | Africa |  |  | Sustainable Development | Water | RETF | IPF | 2010 | 2013 | 2016 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/601411467993501619/text/ICRR14632-P103639-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/601411467993501619/pdf/ICRR14632-P103639-Box393183B-PUBLIC.pdf | The following lessons were selected, condensed and edited from the Lessons Learned section of the ICR (pp.36-38). Some of the lessons identified in the ICR were more statements of fact than lessons. Flexible Design: One of the key lessons was the need to adopt a project design that focussed on end goals without using rigid implementation modalities. For example, although regional tensions and the environment for regional cooperation were at times difficult, the Bank and ENTRO through adaptive management made project implementation changes which helped the project achieve objectives, meet or exceed key indicator targets.Working Closer with Academia: A key lesson learned was the need to broaden the stakeholder pool for engagement. For a knowledge-driven project such as the ENPM, it is essential to involve academia. ENTRO decided to expanded the academics network to include all the key technical universities in the Eastern Nile countries through these three focal universities. Through collaboration, ENTRO developed a wide range of knowledge and modeling products and disseminated ENPM Project outputs. Based on this experience, the NBI has decided to expand such academic partnerships and internships to all the countries of the Nile Basin in future activities.Variety in Knowledge Products: For effective communication of complex issues in the Eastern Nile and to effect change in entrenched mindsets, it is critical that information be communicated in customized ways to different stakeholders. A lesson in the ENPM implementation is to try to develop a range of knowledge products to help better interface with each stakeholder group.
P103654 | Indonesia-Avian and Human Influenza Control and Preparedness | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2007 | 2010 | 2013 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/255991474594242589/text/000020051-20140625071948.txt | http://documents.worldbank.org/curated/en/255991474594242589/pdf/000020051-20140625071948.pdf | The ICR offers eight lessons of which the first three below are particularly important. They are given here with some change in formulation. The fourth lesson is an IEG formulated lesson drawn from this review.1. Choice of instrument, or package of instruments, is particularly important in a communicable disease emergency situation that calls for the sustained establishment of animal and human disease response preparedness. The choice also needs to weigh single disease preparedness versus longer-term, broader, disease preparedness. The ICR (p. 23) asks the right question: "Does the Bank need to be present in an emergency situation when the issues require a specific technical framework first? Or should the Bank wait to see how such a framework is being established and can be scaled up, while preparing a project?"2. During project preparation on a project that will need rapid budget approval, close coordination is needed with the Ministry of Finance, particularly in a country where there have been previous problems for projects in getting budget approval. 3. A multiplicity of implementing agencies is detrimental to speedy implementation, particularly in an emergency project. If unavoidable, it needs careful institutional design.4. Formal supervision missions are needed even when little implementation is being achieved, first, because management needs to stay informed on, and responsive to, an emerging problem, and, second, because slow implementation may signal a relevance or design flaw that needs to be addressed promptly and at a high level.
P103770 | ALAGOAS FISCAL AND PUBLIC MANAGEMENT REFORM | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2012 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/565381474905770106/text/000020051-20140625200117.txt | http://documents.worldbank.org/curated/en/565381474905770106/pdf/000020051-20140625200117.pdf | IEG concurs with the ICR that the main lesson to be drawn relates to the M&E framework. A great many indicators do not make a good M&E system. Redundancy of indicators especially complicates management and wastes time. Indicators must be well understood by the client and the data sources must be readily available.
P103773 | Business Environment Strengthening Technical Assistance (BESTAP) | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2007 | 2013 | 2014 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/935641474502850460/text/000020051-20140626115058.txt | http://documents.worldbank.org/curated/en/935641474502850460/pdf/000020051-20140626115058.pdf | There are four main lessons that can be drawn from the experience of this project:Projects with vague objectives and weak monitoring and evaluation frameworks are difficult to manage and provide limited operational learning. Even when projects achieve important results, it is essential to understand why and how.Working with co-financiers requires attention to detail from the project design stage, and may delay or complicate implementation. A co-financed project requires that funds are made available as planned as delays in disbursement by one co-financier can affect the performance of the project components funded by others. Such delays can be minimized if all key administrative details are worked out before implementation starts Coordinating many implementing agencies can be costly and inefficient and is not always necessary. Some Bank-funded projects have used private sector entities to manage private sector development activities, while others have distributed responsibilities and allowed autonomy in decision to each implementing agency.The design of private sector development projects can be enhanced by involving a wide range of private sector associations in project design and implementation. The decision to work with one specific association rather than with a group of private sector associations can lead to a narrow base of support for the project.
P103875 | LB - Municipal Infrastructure | Middle East and North Africa | Lebanon | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | SPF | IPF | 2007 | 2012 | 2014 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/340721474576936868/text/000020051-20140625232430.txt | http://documents.worldbank.org/curated/en/340721474576936868/pdf/000020051-20140625232430.pdf | IEG supports the main lessons discussed in the ICR. The lessons, which incorporate revisions to reflect IEG views, are summarized below. In emergency situations, keeping the scope of the project simple and allowing for maximum flexibility facilitates successful implementation. The projectâ€™s design allowed for flexibility in the choice of subprojects which enabled it to be implemented in difficult circumstances. Emergency projects should include features that help lay the groundwork for activities that strengthen the economy and institutions. In this case, the economic development and municipal strengthening activities should help future improvements to municipal finances and overall municipal strengthening. In emergency projects it is particularly important to take advantage of existing implementation capacity and if possible to use an already proven and tested project unit rather than creating new structures. In the case of the FMIP, the use of the existing project unit contributed to the success of the project. Experienced and technically qualified Bank staff, some stationed in the field, greatly contributes to a project success. The Bank was able to deploy a strong team at appraisal and subsequently during supervision which was able to effectively address difficult issues. The ICR notes that the strong team in the Bank office was important in ensuring a rapid response to problems.The speed with which emergency operations are prepared may require that the monitoring and evaluation framework be modified during implementation. Surveys can provide valuable monitoring information.
P103881 | HN Water and Sanitation Sector Modernization Project | Latin America and Caribbean | Honduras | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2007 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/238831512590257619/text/ICRR-Disclosable-P103881-12-06-2017-1512590244431.txt | http://documents.worldbank.org/curated/en/238831512590257619/pdf/ICRR-Disclosable-P103881-12-06-2017-1512590244431.pdf | The ICR (p. 20-22) includes several useful lessons learned that IEG synthesizes as follows:1. Choosing anImplementing Agency outside the sector can be beneficial for project implementation. In this project, the UAP, a non-watersector entity, was responsible for the overall project implementation due to its neutral position among sector entities withcompeting interests, its stronger capacity in financial management and procurement and its ability to mitigate conflict amongdifferent sector entities.2 . Establishing selection criteria and utilizing competition to foster reforms can beuseful tools to increase motivation about the project. In this project, participating municipalities were eligible forproject funds based on size and their willingness to transfer their water supply or sanitation services to a municipal serviceprovider as mandated by the Ley Marco. The ICR highlights that two pre-conditions could have been used: i) the degree to which theproviders were measuring water consumption and utilizing meters; and ii) if tariffs had been adjusted during the last twoyears.3 . Outreach activities and pilot projects are critical for overcoming resistance to watermetering. In this project the communities opposed the introduction of household meters since it was believed that theywould revision and probably an increase in tariff structure.
P103885 | West Beka'a Emergency Water Supply Project | Middle East and North Africa | Lebanon | IBRD | Non-FCS | Sustainable Development | Water | SPF | IPF | 2007 | 2012 | 2014 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/619281474648819947/text/000020051-20140625232910.txt | http://documents.worldbank.org/curated/en/619281474648819947/pdf/000020051-20140625232910.pdf | The following lessons are drawn by the ICR and IEG from the experience of preparing and implementing this project:Â· Given the limited time for preparation, emergency operations require additional attention and review steps during implementation (in this case with regard to M&E, risks, and safeguards) Â· Where policy and institutional reforms are critical to the success of the project, it is important to ensure that they are actually undertaken. If, as in this case, they are meant to be supported by a parallel Bank-supported operation, then it would be appropriate to ensure during preparation and implementation that the interface between the two projects is functioning as intended.Â· Careful attention to consumer incentives to pay for improved water needs to be factored into project design.Â· Coherence between the project development objectives as written and the proposed activities is critical for project success.
P103922 | Agro-biodiversity and Adaptation | Middle East and North Africa | Yemen, Republic of | IDA | FCS | Sustainable Development | Agriculture and Food | GEF | IPF | 2010 | 2015 | 2016 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/354641468329390389/text/ICRR-Disclosable-P103922-06-02-2016-1464908568448.txt | http://documents.worldbank.org/curated/en/354641468329390389/pdf/ICRR-Disclosable-P103922-06-02-2016-1464908568448.pdf | The following lessons are emphasized with some adaptation of language: To improve relevance of a project,utilize participatory beneficiary involvement in planning/design of activities. The project experience demonstrated thatbeneficiary participation made the project more relevant to the needs of a specific community, even when similar activities werecarried out in different locations. This was the case with coping strategies where, because of community participation, there wasoften an increased demand for smaller water tanks. It also led to easier transition to participatory beneficiary involvement duringimplementation. With beneficiary involvement during implementation, temporary jobs were created and targeting improved because theunemployed/under-employed were more available to participate. Global benefits could be achieved andsustained only if they are consistent with national policies and priorities. When the goal is to deliver climatechange-related global benefits,project designmust build national policies and priorities,becauseproject activities at the local level can onlybe sustained if they fit national policies andpriorities. The centrality of developing national policies and priorities cannot be overstated. Specifically,theprojectsapproach to development of national policies relied upon climate modeling and database-related training, amongother things. In addition, much of the priority setting at the national level required focusing on rainfed agriculture, which hadbeen achieved through RALP and which preceded this Project. Building partnerships and understandingamong project implementers and communities over a period of time is critical for the success of community-basedbiodiversity/climate change projects. The understanding was achieved under two Bank projects, Ground Water and SoilConservation Project and Rainfed Agriculture and Livestock Project, which preceded this project. Although the reduction in overheadcost from piggy-backing Project Coordination Unit/Project Support Unit of Bank projects is often acknowledged, this benefit to GEFprojects, from past Bank interventions in building partnerships, is not well understood.
P103941 | Second Poverty Reduction Support Credit | Europe and Central Asia | Moldova | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2009 | 2012 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/541601474906353493/text/000020051-20140624202629.txt | http://documents.worldbank.org/curated/en/541601474906353493/pdf/000020051-20140624202629.pdf | There are two key lessons: The experience of PRSCs 1 and 2 indicates that the Bank overestimated the ability of the government to execute the program and underplayed the interaction between parliament and government. The experience suggests that overlooking how organizations work and who is responsible for approving and implementing laws and regulations is likely to derail a reform program or parts of it and to delay its execution.The experience of PRSCs 1 and 2 also suggests that policy reforms that pay insufficient attention to the constraints of the government's institutional capacity are likely to lead to less than satisfactory results.
P103950 | Governance and Institutional Development Project II | Eastern and Southern Africa | Madagascar | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2008 | 2015 | 2016 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/168401467992518539/text/ICRR14840-P103950-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/168401467992518539/pdf/ICRR14840-P103950-Box394823B-PUBLIC.pdf | This Review draws from lessons from the ICR, including:In politically unstable countries with a changing institutional environment, restructuring a project can be an opportunity to adapt the project to new circumstances. The project was not sufficiently adapted to the often changing political environment and was still too ambitious and complex. This had a negative impact on project implementation and project outcomes. Government commitment and leadership are important for achieving the projectâ€™s objectives. In this project, lack of political commitment, resistance to reform, and little engagement with a large number of stakeholders resulted in not achieving the projectâ€™s objectives. During a period of political crisis working with Civil Society Organizations and local governments can be beneficial to moving the reform process ahead. In Madagascar, while the national government was not focusing on public sector reforms during the political crisis, local governments and non-government entities were interested in reforms and taking actions that were in their area of responsibility. A lesson added by IEG:When a project is not performing well and its progress towards the projectâ€™s objectives is rated Moderately Unsatisfactory and Unsatisfactory over a five year period (with the majority of the time being rated Unsatisfactory), the Bank should consider cancelling the project rather than financing activities that do not lead to the intended results.
P103974 | Conditional Cash Transfers Project | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2009 | 2019 | 2019 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | High | http://documents.worldbank.org/curated/en/938711561833342798/text/North-Macedonia-CCT.txt | http://documents.worldbank.org/curated/en/938711561833342798/pdf/North-Macedonia-CCT.pdf | The ICR (pp. 28-30) presented several insightful lessons, including the following (with some adaptation oflanguage):Management information system investments must be fully in place prior to beginning implementation of programsthat rely on them. In this case, thecash benefit MISwas not complete at project start, delaying launch of theentireconditional cash transferprogram.Government budgetary commitments cannot be considered fully certain ina volatile political environment. In this case, annual allocations from the state budget were not always in line with projectfinancing agreements and needs, requiring later adaptation of project financing arrangements. Careful assessment of the budgetprocess during project appraisal, as well as flexibility during implementation, is required to adapt to changing circumstancesoutside the projects control.Thepoorest and most vulnerable social program beneficiaries are frequentlydifficult to employ. They may be concerned that they will lose benefits if they work, and they may lack skills attractive to locallabor markets. In this case, an individual approach, considering the unique situation and challenges of each beneficiary family,was effective.
P103999 | BD Chittagong Water Supply Improvement and Sanitation Project | South Asia | Bangladesh | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2010 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099520012012139064/text/Bangladesh000B0r0Supply0Improvement.txt | http://documents.worldbank.org/curated/en/099520012012139064/pdf/Bangladesh000B0r0Supply0Improvement.pdf | The ICR (paras. 94to 98) provides a number of lessons learned from the projects experience. Based thereon, IEGderives the following lessons:Defining the scope of the project based on incomplete diagnostics can adverselyaffect project performance. The projects experience has shown that large infrastructure works, such as the watertreatment and transmission/distribution facilities supported under the project, need to be preceded by robust preparation andanalytical works that clearly define the priorities to be followed during implementation. Uncertainty in this regard led to delaysin identifying and initiating priorities to be addressed for improving CWASAs network. It was only after a hydraulic modelingexercise was carried out at the 2014 restructuring that the network improvement priorities were established andaddressed.Establishment of a well-staffed and well-equipped Project Management Unit prior to the startofimplementation is crucial for ensuring efficient implementation: The absence of a strong, well-staffed andwell-managed PMU was a critical factor in the significant delays in the earlier years of implementation.In the case ofthe project, adequate staffing of the PMU, including consultants, dedicated staff with designated functions, and a project managerwere not in place until after the 2014 restructuringi.e. four years into project implementation. This contributed in part tothe delayed completion of the project.Adequate attention needs to be paid throughout projectimplementation to ensuring that the projects ME system remains updated and functional: The experienceunderthe project showed that ME analysis and data were not readily available to PMU staff to monitor implementationprogress and initiate remedial actions.The ICR notes that this contributed to the delays inimplementation.Institutional development of a utility is a long process and,if possible, shouldbuild on the clients own program/platform: The ICR assesses that CWASAs ownership of the institutionalstrengthening and reforms supported under the project was reinforced by the fact that this was built on the already ongoingGo-Ahead Program that was being implemented by CWASA. CWASAs continuing strong commitment to institutional reformwould be crucial in sustainingthe institutional improvement gains made under the project.
P104015 | Nepal: Enhanced Vocational Education and Training | South Asia | Nepal | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/747891527264681639/text/Nepal-NP-Enhanced-Vocational-Educ-Trng.txt | http://documents.worldbank.org/curated/en/747891527264681639/pdf/Nepal-NP-Enhanced-Vocational-Educ-Trng.pdf | Lessons drawn from the ICR, adapted by IEG: The multiplicity of key institutionsinvolvedinasub-sector projectcan beeffectivelycounterbalanced by strong design and implementationsupport. In the case of this project, given theperceivedfragmentation of the TVET sub-sector,theBankteam adopted a participatory approach to project preparation, involving different government agencies and donorsactive inthe sector. The active participation of the multiple stakeholders both at design and during implementation helped to ensurecoherence in the sectors activities, and a strong project implementation team was a key contributing factor to projectachievements despite the lack of a singlelead agency. Active participation of key stakeholders at the projectdesign stagecan lead to continued collaboration inproject monitoring. In the case of this project, the unexpecteddevelopment of a Joint Monitoring Team with donorscontributed to greater rigor in data collection and credibilityof theresults generated
P104034 | Power Sector Efficiency Enhancement Project (PROMEF) | Latin America and Caribbean | Honduras | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2009 | 2015 | 2017 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/445621474375622282/text/ICRR-Disclosable-P104034-09-20-2016-1474375612612.txt | http://documents.worldbank.org/curated/en/445621474375622282/pdf/ICRR-Disclosable-P104034-09-20-2016-1474375612612.pdf | IEG draws the following lessons from the experience of thisproject: A critical eye on the feasibilityof projected implementation schedules is essential for evaluating project progress and the need for additional Bankinterventions. The Banks team had an overly optimistic view of project development, even though implementationdelays meant that some outcomes could not be achieved in the time left. As a result, opportunities were missed to make changes thatcould better reflect the projects situation and improve the likelihood ofachievements. Asuccessful implementation of modern consumption monitoring systems isnecessary, but not sufficient, to achieve a reduction in commercial losses. Outcomes, such as reduction in non-technicallosses and CRI, require complementary intensive loss reduction and collection programs that go beyond an investment or technicalassistance that can be provided in a project. They require sustained and continued high level support and commitment by theGovernment and power company management. An adequate project design needs to include baseline data on which tojudge progress towards desired outcomes. The indicators and result framework need to build on what already exists and usehistorical data to assess reasonable targets. Even low quality data prior to implementation would have been more helpful in judginga projects progress than having no baselines and having to withhold critical analysis until reliable indicators to trackprogress became available. Improvements in operational indicators need to be consistent with the activities thatthe project supports. To achieve this end, operational indicators should include only the areas covered by the project,and where the outcome can be reasonably attributed to the projects investment, rather than to a larger set of investmentsoutside the projects control, even when defining indicators by project area is more data intensive and requires the powercompany to have and implement adequate data collection and validation. The overly inclusive nature of outcome indicators in thisproject made them unusable for judging the projects outcomes.
P104041 | DRC Enhancing Governance Capacity | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2008 | 2016 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/461221498488090758/text/ICRR-Disclosable-P104041-06-26-2017-1498488079770.txt | http://documents.worldbank.org/curated/en/461221498488090758/pdf/ICRR-Disclosable-P104041-06-26-2017-1498488079770.pdf | The ICR identified appropriate lessons from the implementation of this project, the most prominent of them highlighting thefollowing aspects: (i) the key role of analytical work to inform project design and implementation, (ii) the importance ofconsensus building capacity and strong relationships with all levels of Government to undertake a governance reform, (iii) the needto design flexible and adaptable projects in order for the project to remain relevant in a context of ever-changing Governmentofficials and priorities, (iv) the contribution of a national communication campaign to build awareness when transformationalstrategies are implemented, and (v) inter-institutional collaboration and civil society participation are key for the successfulimplementation of governance reform programs.IEG draws the following two additional lessons: (i) in a fragile andpost-conflict environment, project performance depends to a high degree on the Banks commitment to providing closesupervision, including a strong and experienced resident team and (ii)the gradual, step-by-step approach paid off,andseems to be an effective modus operandifor theBank in similar contexts.
P104097 | VN - Program 135 Phase 2 Support Credit | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | DPF | 2007 | 2008 | 2013 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/146851474652667130/text/000020051-20140620065749.txt | http://documents.worldbank.org/curated/en/146851474652667130/pdf/000020051-20140620065749.pdf | The establishment of a basic MIS (focusing on outcomes) and implementation manuals prior to the start of the Program is necessary to enhance development effectiveness.To ensure that both men and women share in program benefits, it is important to integrate gender considerations during the design of CDD programs; integrating gender issues during implementation is insufficient. Ownership of the Program objectives and rules by, and strong capacity of, local governments are important to achieve sustained results in CDD interventions.
P104257 | GZ-Village and Neighborhood Development Project | Middle East and North Africa | West Bank and Gaza |  | FCS | Infrastructure | Urban, Resilience and Land | SPF | IPF | 2008 | 2014 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/592571475116747132/text/000012394-20150309080337.txt | http://documents.worldbank.org/curated/en/592571475116747132/pdf/000012394-20150309080337.pdf | The ICR records a number of lessons. Following are two ICR lessons, with some adaptations: CDD type projects should set aside ample time for the community mobilization process, especially in a complex country environment, given its criticality in enabling achievement of development objective. The cyclical nature of the project meant that corrective measures could be implemented during cycle 2, but significant efforts had to be made by the Bank and PMT to turn the project around. As a result of the project process a lot of capacity has been built in the PMT, OCs, and communities, but the learning process would have been less rushed with more time set aside for cycle 1.CDD approach can effectively assure involvement of women and youth in patriarchal traditional societies with strategic community mobilization, endorsement of conditionality and established procedures for monitoring. Program support groups (PSGs) were established in each village and neighborhood with women and youth representation at 27 percent and 41 percent. Results framework provides indicators to measure percentage of women and youth led sub projects.IEG lessonChoice of area development plans over community development plans should be wetted through a pilot before instituting it at the project level to determine the viability of the planned sub-projects to meet the larger scope of municipal investment requirements that will be covered under the ADPs unlike those proposed by CDPs. This is particularly relevant in projects with cyclical nature.
P104265 | MA-Support to ONE (Office National de l'Electricité) | Middle East and North Africa | Morocco | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2008 | 2016 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/617971536175928512/text/Morocco-MA-ONE-Support-Project.txt | http://documents.worldbank.org/curated/en/617971536175928512/pdf/Morocco-MA-ONE-Support-Project.pdf | The following three broadly applicable lessons summarized from the five presented in the ICR with some editing of thesubstance.1. Ensure simplicity in project design. Simplicity of design made project restructuring, asin this project where components and subprojects were dropped and replaced by others with some shifts in the distribution of theprojects funding among categories, easy leading to effective implementation.2. Reliabledevelopment partnerships can drive investment projects to develop infrastructure but also reinforce a policy dialogue to enablepolicy reforms. ONEE and the World Bank maintained a good partnership throughout the project. The World Bank reinforcedits status as a reliable partner to support technical assistance, which enabled important reforms in a sensitive sector. The strongcomplementarity between this operation and an earlier Development Policy Operations was an important aspect of the Bankssupport of a Government program, and could even be considered as a model for a Program for Results series ofoperations.3. A strong engagement with the client on social safeguardsfacilitates project implementation. Throughout supervision, the Bank team demonstrated a strong ability to mobilizeONEEs teams for social safeguards monitoring, by properly identifying and compensating all the impacted communities andprivate landowners. A dedicated social safeguards monitoring tool was jointly developed by the World Bank and ONEE and meritsreplication for similar projects in the future.
P104266 | ENERGY EFFICIENCY | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2009 | 2016 | 2017 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Highly Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/217091493305186770/text/ICRR-Disclosable-P104266-04-27-2017-1493305176036.txt | http://documents.worldbank.org/curated/en/217091493305186770/pdf/ICRR-Disclosable-P104266-04-27-2017-1493305176036.pdf | The following first three except the last one were drawn from the lessons learned from the ICR.1. TA isindispensable to the success of EE projects and the indispensable activity for theprojects success should not be included in a separate project. The projectoverestimated the EE stakeholders capacity. The TA from a separate project did not materialize. According to ANME and thePFIs, the provision of TA would have facilitated and accelerated the implementation of the project, such as support to the PFIs(credit appraisals and technical due diligence, risk assessment, EE marketing, monitoring, and so on) and investors (feasibilitystudies, capacity building, operational training, and so on) to lift off some of the knowledge capacity barriers more efficientlyand faster.2. Energy tariff rebalancing and other reform measures can induce energy efficiencyinvestment. In 2013 and 2014, the GoT increased the energy prices, which helped increase the investors interest incogeneration. This trend might continue in the future if the Government maintains its commitment to a gradual but sustainedincrease in energy prices. There are also barriers and regulatory impediments to be removed in the electricity sector to encouragethe development of cogeneration, including an attractive purchase tariff of excess electricity, power connection to the grid, andso on.3. Robust readiness criteria for PFI selection and bankable pipeline development can help avoid slowimplementation. The selection criteria used were more skewed toward ensuring compliance with prudential rules andregulations and good financial performance and much less on those relating specifically to PFIs EE experience and appetite,which misled their EE readiness. A two-stage approach could be employed: preselect banks that meet the prudential/financialrequirements and then drill further into EE readiness to select the right candidates (management team in place, pipeline ofprojects, management commitment to EE investments, resources available for support, and so on, as illustrated by the case of BH insection 8.a. above ).4. Small non-productive EE activities with high transactions would require strengthening ofthe capacity for the PFIs appraise and handle them. This project was able to finance only relatively larger co-generationenergy efficiency but could not finance the originally planned other smaller EE projects due to the lack of capacity of PFIs tohandle to appraise, their high transaction costs (e.g., review of applications, credit worthiness assessment, follow-up, etc.), andlimited creditworthiness of these investors.
P104301 | Expanding Microfinance Outreach and Improving Sustainability | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2008 | 2012 | 2014 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/137591474629205267/text/000020051-20140626075415.txt | http://documents.worldbank.org/curated/en/137591474629205267/pdf/000020051-20140626075415.pdf | As noted in the Borrower feedback, the failures of the project provides valuable lessons. The ICR highlights a number of useful and well considered lessons with broader application to fragile states, including: (i) avoiding over-reliance on a single institution and stricter assessment of eligibility, with periodic reassessments; (ii) using caution when rolling-out programs in less secure areas; (iii) providing the Apex institution with sufficient means to perform its oversight functions, including through outsourced independent experts; (iv) being careful about assuming that a model that works in one country will be full portable elsewhere; and (v) MFIs need a strong governance structure.Four additional complementary lessons are associated with the present review: (a) a different more cautious project design may help identify emerging problems sooner -- for instance by tranching the line of credit to the Apex institution, with each replenishment triggered by a reassessment of the premise upon which the project initially proceeded; (b) attention should be paid to the project logic and relationship between objectives, activities and results sought; the M (c) all participating financial intermediaries should be subject to an annual external audit undertaken on the basis of prevailing international standards; and (d) the use of emergency procedures imply trade-offs in terms of project readiness and documentation, and consideration should be given not to use such procedures for a project that takes almost two years to prepare.Further lessons may be learnt through an assessment of both microfinance projects overseen by the Bank. Such an exercise is not recommended at this time because of its significant overlap with the recently completed IEG CPE.
P104340 | TP-FTI Program 2009 | East Asia and Pacific | Timor-Leste | Blend | FCS | Human Development | Education | RETF | IPF | 2009 | 2011 | 2012 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/270531474633090567/text/000020051-20140625061854.txt | http://documents.worldbank.org/curated/en/270531474633090567/pdf/000020051-20140625061854.pdf | The ICR offers the following lessons:Core capacity should be in place prior to implementation, as there are risks in moving from preparation to implementation without the requisite capacity in the implementation agency. The analysis of the core capacity should also serve as a basis for building additional capacity during implementation.The M&E framework should include provisions for tracking outcomes for the project's target groups so that the project's impact can be properly assessed.In a context of low public sector capacity and a short project time frame, international consultants can be utilized for effective implementation. However, they should be paired with national staff at all levels in order to contribute to strengthening national capacity.Participation of local communities in school management activities can increase a project's credibility with target groups.
P104357 | Yogyakarta and Central Java Earthquake Roof Structure Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2007 | 2008 | 2009 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/557101475095088092/text/000020051-20140619090708.txt | http://documents.worldbank.org/curated/en/557101475095088092/pdf/000020051-20140619090708.pdf | 1. Close coordination between the World Bank and the implementing agencies both in their respective field offices and head offices permits early detection and appropriate solutions to issues as they arise. In this case, this close relationship resulted in the improvement of targeting, the expansion of the program into UPP villages and an appropriate downscaling of the project before too much wastage occurred.2. Transitional Shelter delivery is better when carried out by local people with their existing social networks/capacity. The capacity of the local communities to band together to form community work teams was well utilized by the project permitting minimal paid work in the construction phase of the project and ensuring value-for-money.3. The Transitional Shelter approach will only be an appropriate approach if it does not have to compete with the government permanent housing program. Both the Bank, as the trustee of the grants, and the implementing agencies have to be equipped with project preparation procedures that are tailored to rapid relief requirements and mechanisms.
P104403 | Lesotho New Hospital PPP | Eastern and Southern Africa | Lesotho | IDA | Non-FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2008 | 2013 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/930501474898421713/text/000020051-20140626121435.txt | http://documents.worldbank.org/curated/en/930501474898421713/pdf/000020051-20140626121435.pdf | These lessons are derived from the ICR (pp. 19-21):Especially in a complex implementation environment, the relationships between all key players and financiers must be clarified from the outset. In this case, it appears that there may have been some initial confusion regarding the relationship between the GPOBA project and the main PPP hospital project., and that confusion is reflected in the statement of the GPOBA project's objective.While it is prudent to restrict proprietary information under a PPP agreement, effective collaboration of the various parties involved in the execution of a PPP project demands measures to handle such information without prejudicing the interests of the main parties. In this case, some of this initial confusion could have been avoided if the relevant part of the PPP agreement had been disclosed to the GPOBA project team (under a comprehensive disclosure agreement).Strong project design (technical and institutional arrangements), careful risk assessment, close supervision, and good M&E design, implementation, and use can mitigate risk and maximize opportunities for learning. There are multiple opportunities for learning from the challenges and achievements experienced by this complex, innovative project.
P104405 | Pre-paid Health Scheme Pilot in Nigeria | Western and Central Africa | Nigeria | Blend | Non-FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2009 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/205971468189272640/text/ICRR14743-P104405-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/205971468189272640/pdf/ICRR14743-P104405-Box393191B-PUBLIC.pdf | The ICR (p. 24) identifies several valuable lessons, including:In order to ensure government ownership and financial sustainability, coordination with different government levels during project preparation and implementation is critical. In this project, the Lagos State Government and the National Health Insurance Scheme were not sufficiently consulted during the project design and implementation phases which would have been important for future engagement and the sustainability of the project. Conducting an in-depth target population study can be useful to inform project design. Even though a target population study was conducted, its scope was too limited and did not include sufficient information on setting the premium and what type of services to include in the benefit package. A more extensive target population survey could have indicated that a second increase of the co-payment rate would be unaffordable for poor enrollees. Contracting expensive private health care providers for the implementation of a community health scheme poses a risk to its sustainability. In this project, two expensive hospitals decided to quit the scheme since they experienced financial losses.
P104456 | CM-Energy Sector Development SIL (FY08) | Western and Central Africa | Cameroon | Blend | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2008 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/129831525961045843/text/Cameroon-CM-Energy-Sector-Development-SIL-FY08.txt | http://documents.worldbank.org/curated/en/129831525961045843/pdf/Cameroon-CM-Energy-Sector-Development-SIL-FY08.pdf | The ICR presentsa numberlessons. Some of them, such as the need for standard bidding documents for procurementrelated to rural electrification projects, have been learnedmany times in the past. While not denigrating the relevanceand importance of old lessons, the following lessons from the ICR stood out as interesting and relevant to the current focus onenhanced infrastructure development in Sub-Saharan Africa. Relying on private sectorparticipation for electricity grid extension without the provision of an adequate regulatory and enabling infrastructure,aswell asadequate end-use tariffs to cover costs and provide a return on investment, is unrealistic. This was the casein this project and consequently the assumption that the private sector wouldtake advantage of the availability ofsubstantial financial resources toextend electricity grids in rural areas was largely unsuccessful (ICR,paragraph55). Conducting feasibility studies for innovative infrastructure development in orderto provide informationto potential privatesector entrepreneurs interested in contracting for such investments can laythe groundwork for efficient procurement ofinfrastructure constructionThe lack offeasibilitystudies for contracts in this project at the time of procurement of the three grid extensioncontracts tookup to 18 months for many reasons including the absence of standard bidding documents and the need to changetechnicalspecifications. This led to delays in signing contract agreements and hence delays in implementation. Whiletwogrid extension projectswere eventually completed,the third grid extension project had to be cancelled as the contractorwas underperforming and the planned activities could not be completed by the projects final closing date. Thiscancellation resulted in thelack of electricity connections for approximately 10,000 new customers in 42 localities in theNorth-West region (ICR, paragraphs 25, 56, 57 and 120). Ascertaining the likely risksand constraints to project implementation are a necessaryaspect of project design at project appraisal. For example,the lengthyand complex process in Cameroon for compensating landholders for the use of their land for ensuring right of wayfor transmission lines and similar reasons in this project involvednational and local institutions but this not an identifiedrisk during preparation norin the course of the projects majorrestructuring. During the projectsimplementationthe compensation process tookover two years tocompletewhich delayed the implementation of theproject considerably. Had thisrisk been identified during preparation, it could have been addressed and eithermitigated by the Bank working with the Government to streamline and simplify its processes or factored into the projectstimetable (ICR, paragraphs 57, 64, 113, 116 and 125).
P104467 | Health System Modernization Project (APL2) in Support of the Second Phase of the Health Sector Reform Program | Europe and Central Asia | Armenia | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2007 | 2016 | 2017 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/786891495645916703/text/ICRR-Disclosable-P104467-05-24-2017-1495645903876.txt | http://documents.worldbank.org/curated/en/786891495645916703/pdf/ICRR-Disclosable-P104467-05-24-2017-1495645903876.pdf | The ICR (pp. 23-25) provides insightful lessons, some of which are reformulated here:Political commitment isthe key prerequisite to health sector reform in the post-socialist context. In this case, government support at thehighest levelsfor politically sensitive hospital rationalization remained consistent, enabling gains in sector efficiencythrough consolidation of hospitals and prioritization of primary care.The APL is a valuable instrument insituations of long-term commitment to reform. In Armenia, reform of the health sector has spanned three Bankprojects and two decades. This instrument enabled the Bank to sequence activities and refine targets as progress was madetoward long-term goals.Infrastructure is not enough. For health system modernization, it isimportant to invest in modernization of hospitals and clinics, but training, capacity building, and modernization of rules forprovider payment and other key resource flows are also essential.Accurate political economy analysis is aprerequisite for health sector reform. In this case, there was potential for significant stakeholder opposition tohospital rationalization, but the government and Bank teams anticipated that opposition and effectively managed expectations andinterests.
P104467 | Health System Modernization Project (APL2) in Support of the Second Phase of the Health Sector Reform Program | Europe and Central Asia | Armenia | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2007 | 2016 | 2019 | PPAR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/725551557425652702/text/Armenia-Achievements-and-Challenges-in-Improving-Health-Care-Utilization-A-Multiproject-Evaluation-of-the-World-Bank-Support-to-the-Health-System-Modernization-2004-2016.txt | http://documents.worldbank.org/curated/en/725551557425652702/pdf/Armenia-Achievements-and-Challenges-in-Improving-Health-Care-Utilization-A-Multiproject-Evaluation-of-the-World-Bank-Support-to-the-Health-System-Modernization-2004-2016.pdf | 5. Lessons 5.1 The APL program shows that an approach that exploits synergies and lessons from other World Bank engagements in the health sector is important for undertaking complex reforms and helping the government stay the course of reform. Complementarities across lending and knowledge instruments allowed the World Bank to engage in a range of health policy areas, including health financing, governance and stewardship of health authorities, and service delivery. 5.2 Macro and micro health policies need to be combined in a manner that the unintended consequences of policy changes are not overlooked. For example, recurrent adaptations of the Basic Benefit Packageâ€”changes in services covered, entitled population groups, and the pricing system supported by policy-based lendingâ€”created uncertainty for patients about the boundaries of the benefit package, increasing the risk of informal payments and potentially undermining health care use. Similarly, the introduction of health financing policy changes, such as the global budgeting mechanism, while improving efficiency and cost containment from a macro perspective, may have had deleterious effects on some dimensions of quality (notably through the creation of waiting lists). 5.3 A shortened period between the approval dates of successive phases of an APL can limit the opportunity to incorporate lessons from previous phases into the design of new ones. The second phase of the operation was advanced to only two and a half years after the approval of the first phase. While this allowed the program team to seize the political momentum to implement hospital optimization plans in the marzes, it also limited the time to incorporate lessons from the first phase into the design of the second phase and introduce course corrections in the implementation of the family medicine model. By the end of APL, I, it was clear that such a model was less suitable in urban areas because of the availability of specialists within the same facility. Yet, because of the limited time, the second phase did not include design components supporting private PHC practices in cities. 5.4 In country contexts with strong social and cultural factors affecting uptake of health care services, supply-side and systemwide policy reforms need to be combined with demand-side interventions addressing the health-seeking behavior of patients. Increased use of PHC services, especially by the vulnerable, depends on the extent to which services are accessible and affordable, have a minimum level of perceived quality, and on cultural factors that affect health-seeking behaviors. While the APL program addressed the accessibility and quality of health care services, attention to patient perceptions and preferences was not explicit, and a considerable share of patients continues to self-refer to specialists due to the preconception that those specialists are more capable of treating certain conditions than generalists are, illustrating that social and cultural preferences take longer to change. 5.5 While investments in infrastructure are not enough for health system modernization, they can help ensure acceptance of the proposed organizational changes involving strong stakeholders in the hospital sector. The enthusiasm of regional health authorities to pursue hospital mergers was strongly associated with the promise of major investments in the marz hospital networks. In fact, the implementation of the program was particularly successful in those regions where it was followed up with major infrastructure investments in those networks.
P104497 | DRC Emergency Urban and Social Rehabilitation Project | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2013 | 2015 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/134211475115526404/text/000180307-20141203042217.txt | http://documents.worldbank.org/curated/en/134211475115526404/pdf/000180307-20141203042217.pdf | IEG draws the following key lesson from the experience of this project: Additional Financing (AF) may not be an appropriate tool for addressing emergency needs. In this case, AF was approved for an emergency project more than four years after the event that triggered the initial emergency response took place. Many observers, in line with the Bank's prior ERC policy, would reckon that emergency responses in projects cannot last for more than 2-3 years lest they become part of the regular, yet still chronic conditions of the sector or country receiving assistance. An emergency sustained for a longer period would point, among other things, to the failure of the initial urgent response. Two other important lessons adapted from the ICR include:The settlement of unpaid domestic debt arising from conflict can be effective and timely in achieving the objectives of an emergency operation. This project used a quick disbursing settlement of with creditors who, while accepting a significant discount, reported that they were satisfied with the payments made. While most of them remain in business, their survival can only be attributed to the project if more is known about the counter-factual, namely the number of creditors likely to have gone out of business without the settlement. Financing operating costs of schools in a transparent manner offers a good chance to increase enrollment rates and educational outcomes for children from poorer families. Moreover, this type of operation helps reduce the financial contributions by parents and is likely to contribute to boosting girlsâ€™ attendance. For the funding to be effective in achieving these results, compliance with local financing and auditing requirements, transparency in the posting of amounts and use of funds, targeted awareness-raising, decentralized decision-making and involvement of parents are critical.
P104523 | AFCC2/RI-IGAD Regional HIV/AIDS Partnership Program (IRAPP) Support Project | Other | Africa |  |  | Human Development | Health, Nutrition & Population | RETF | IPF | 2007 | 2015 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/299951467151669466/text/ICRR-Disclosable-P104523-06-28-2016-1467151645212.txt | http://documents.worldbank.org/curated/en/299951467151669466/pdf/ICRR-Disclosable-P104523-06-28-2016-1467151645212.pdf | The ICR (pp. 35-37) highlights a number of useful lessons, including:Complex regional projects require a heightenedlevel of support and scrutiny to ensure quality at entry and implementation success. The political economy of member stateswas not adequately considered during the design of this project, and adequate and consistent supervision and course correction werenot provided prior to mid-term.Careful reporting of baselines, definition of targets, and measurement of achievement iscritical to determining progress and success. In this case, baselines were inappropriate or missing, the definition andmonitoring of targets was too weak to permit identification of early implementation challenges, and reliance on behavioralsurveillance data (difficult and expensive to collect) to monitor outcomes made it difficult to assess projectimpact.Service delivery institutions cannot be effective if they are not located in proximity to target populations.In this case, the health centers and clinics supported under the project were often far away from border crossings, limiting accessof CBMPs to services. While HIV testing centers were constructed near border crossings, they were in many cases prohibitivelyremote from follow-up treatment services. These shortcomings can be addressed, as the project demonstrated in some cases,through innovative solutions related to outreach, patient referral, and patient monitoring.
P104525 | Cameroon Health Sector Support Investment (SWAP) | Western and Central Africa | Cameroon | Blend | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2008 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/872841543854039739/text/Cameroon-CM-Health-Sector-Supp-SWAP-SIL-FY08.txt | http://documents.worldbank.org/curated/en/872841543854039739/pdf/Cameroon-CM-Health-Sector-Supp-SWAP-SIL-FY08.pdf | The ICR (pp. 35-36) and Borrowers ICR (pp. 93-97) offered numerous useful lessons and recommendations,including:Uninterrupted payment of performance-based financing subsidies is key to motivating healthpersonnel and improving health facilities operating environments. In this case, although PBF revolutionized theway business is done in Cameroons health sector, arrears in payment of subsidies led to lengthy delays in payments,negatively impacting efficiency.Strong monitoring and evaluation systems, supported by competent andadequate staff, are essential for effective tracking of implementation and results. In this case, although reporting wasaccurate and complete at the facility level, there were shortcomings with data collection and consolidation at the national level,complicating assessment of achievement.Involving higher levels of government at the outset of discussionsof performance-based financing implementation holds the potential for significant policy development impact. Through adevelopment policy operation, PBF has now been institutionalized in the national budget with a budget line item.
P104566 | Water Services and Institutional Support Project | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2008 | 2016 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/500821474561753629/text/ICRR-Disclosable-P104566-09-22-2016-1474561739557.txt | http://documents.worldbank.org/curated/en/500821474561753629/pdf/ICRR-Disclosable-P104566-09-22-2016-1474561739557.pdf | Lessons drawn from the ICR, adapted by IEG: For projects that create new institutions, the project time frameshould allow adequate time for enacting legislation and establishingcapacity for initial launch. Once thegovernment issues the necessary decrees to establish a new institution, staffing, facilities and budget need to beprovided,followed by developingcapacity to handledonor procedures. There needs to be a balancebetween expanding the customer base and ensuring quality of service. Theproject objective and results framework wereless explicitly focused on the latter and therefore maintaining quality remains a critical issue. Formalizing commitmentfrom donors through written agreements is critical if project implementation relies on this funding. In the case of thisproject, shortfalls indonor financial contributions led to reshuffling of project arrangements and the need to secure otherdonor funding. Sound procurement strategies can greatlyfacilitate implementation. In the case of thisproject, the procurement plan included the use of design-build contracts, structuring of contracts into manageable sizes to accountfor incidents of non-performance, and bulk procurement to create economies of scale.
P104567 | Second Rural Productive Partnerships Project | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2008 | 2015 | 2016 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/706221468018572664/text/ICRR-Disclosable-P104567-06-10-2016-1465595238692.txt | http://documents.worldbank.org/curated/en/706221468018572664/pdf/ICRR-Disclosable-P104567-06-10-2016-1465595238692.pdf | There are four main lessons drawn largely from the ICR with adjusted language. A productive partnershipsapproach can not only be a cost-effective way to increase productivity, improve competitiveness, and link farmers to markets but itcan work for disadvantaged farmers groups as well or better than established, less poor, farmers groups. Inthis project there wasnotable and demonstrated success with the disadvantaged groups both in terms of numbers of groupssupported which was well above the target and in terms of the quality of their achievement. Sustaining supportfor producer groups over an extended period, until they reach maturity, isimportant for ensuring long-term success.In this case, the ICR records that the support was provided over a relatively short 18 to 24 months from the launching ofpartnerships. Since the project still offers somewhat limited length of experience on sustainability and exit milestones forsupport services,the two-year graduation period mentioned in the ICR seems likely to be a bare minimum and quite dependent oncountry and farmer capacities. Strong internal communication of project achievements to influential governmentstakeholders, particularly those contributing to sector strategies and budgets, is important for demonstrating success andinfluencing scaling up. In this case, some of the sometimes weak government support can be attributed to insufficientinternal selling of the project achievements to those with influence. The Consultative Group forInternational Agricultural Research (CGIAR) can be a valuable source of knowledge and capacity in support of farmer-orientedproject design and implementation. In this case, CIAT (the International Center for Tropical Agriculture) was able toprovide insights that led to important lessons for the evaluation of the project and for the design of future similar operations.CIAT evidence was central inmaking the case that productive partnerships can serve disadvantaged groups within the populationandthat they may perform as well as, or better than, the less disadvantaged groups.
P104595 | CAR - Emergency Urban Infrastructure Rehabilitation & Maintenance | Western and Central Africa | Central African Republic | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/186061504634919529/text/ICRR-Disclosable-P104595-09-05-2017-1504634907138.txt | http://documents.worldbank.org/curated/en/186061504634919529/pdf/ICRR-Disclosable-P104595-09-05-2017-1504634907138.pdf | The following are the main lessons taken from the ICR but with some adaptation: Flexible design andadaptive implementation in a fragile and conflict-affected environment is even more important than for a project in a stableenvironmentbecause the inherent uncertainties and newly emerging diagnoses of the needs are more likely to call forreallocation of resources. In this project,such flexibilitywas feasibledue to the multi-sector nature ofthe project and the targeting of several neighborhoods within the same city. This was achievedwithout significantlyincreasing the level of project complexity. Finding a well-performing contract management agencyisparticularly importantin a conflict-affected environment to mitigate capacity constraints. In this case, themanagement agency arrangementwas coupled with flexibility on the Banks side to accommodate the evolving contextandto addresscapacity rebuildingfollowing the crisis situation.The agencywas able to continue at aminimum operational level following the 2013 crisis due to the Banks flexibility to pay a managementadvance. Designing outreach and communication activities in a conflict or post-conflict environment marked by lowlevels of social capital is an important element in assuring ownership by stakeholders. In this case, the communityconsultations on the household water connections were successful due to the presence of SODECA agents in the field andsimilarlydue tothe presence of an NGO for the drainage activities.
P104670 | TIEN SHAN ECOSYSTEM DEVELOPMENT PROJECT | Europe and Central Asia | Central Asia |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2010 | 2011 | 2013 | ICRR | Less than 10 million |  | Unsatisfactory |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/180781474905439685/text/000020051-20140625065516.txt | http://documents.worldbank.org/curated/en/180781474905439685/pdf/000020051-20140625065516.pdf | The NCO offers two general lessons:Regional project design should be based on a shared understanding of objectives and outcomes by all involved countries. Project objectives and outcomes should be equally important to all countries involved; and implementation arrangements should be clearly accepted by all countries before Board approval. Necessary legislative changes/reforms should be undertaken prior to Board approval and not be made effectiveness conditions. Amending existing laws or policies is a complicated process that requires extensive time and effort. Project design should take into consideration timing requirements if launching of project activities rely on policy and legal changes.
P104687 | Mainstreaming Sustainable Cattle Ranching | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | GEF | IPF | 2010 | 2020 | 2021 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/459191623978067561/text/Colombia-CO-Mainstreaming-Sust-Cattle-Ranching.txt | http://documents.worldbank.org/curated/en/459191623978067561/pdf/Colombia-CO-Mainstreaming-Sust-Cattle-Ranching.pdf | The ICR presents tenlessons which are based on project implementation experience and supporting evidence, considering bothpositive and mixed performance (ICR, para. 87).While the content is relevant, this ICRR consolidates andhighlights the most relevant four lessons which also have broader application beyond this project. These four lessons aresummarized below.(1) Approaches to Promoting Farmer Adoption of SPS Technologies: Scaling-up SPS/iSPSfarmer adoption depends on implementing effective approaches to convincing cattle producers of the financial returns of suchinvestments. Cattle ranchers (CRs) were persuaded through a delivery model that focused on 7 complementaryelements, which are relevant for other countries: (a) screening beneficiaries to help maximize economic benefits; (b) soundknowledge-sharing to influence behavioral adoption changes of cattle farmers; (c) adequate and replicable financial incentives forbeneficiary farmers to invest in SPS/iSPS, including the role of appropriate Payment for Environmental Service (PES) schemes;(d) appropriate upfront support, in the form of inputs and sound technical advice; (e) careful consideration on the timingand likely weather conditions when farmers establish SPS/iSPS; (f) selecting appropriate SPS demonstration sites; and (g) ensuringthe component parts are well-organized, well timed and reliably available, and key public/private institutions work closelytogether;(2) Importance of Effective Partnerships and Key Elements for Scaling-Up:Successful adoption and scaling-up of SPS/iSPS technologies among wide range of cattle farmers requires effectivepartnerships between private sector and farmer-driven organizations, which represent the interests of the farmers,and the public sector, which provide important public goods, in the form of targeted subsidies andtechnical advice to participating beneficiaries;(3) A combination of on-farm SPS and ISPS technologies is likely todeliver the best productive and conservation benefits and enhance beneficiary profitability. Higherenvironmental and productive benefits and profitability can be achieved by planting a combination of SPS and iSPStechnologies. While non-intensive SPS such as dispersed trees can deliver important carbon sequestration benefitsonce established, their impacts on farm productivity are more limited. Intensive SPS, however, tends to deliver higher productivitybenefits and contribute to diversity; and(4) Realistic design and cost-effectiveness are key considerations whendesigning monitoring SPS systems for land use changes at farm level. An integrated approach tomonitoring SPS system was fundamental for providing sound information to structure a clear business case for CRs and other privateand public actors, on the socioeconomic and environmental benefits associated with the different land uses promoted by SPSsystems. Sound ME also enhances the national visibility of SPS technologies, and therefore, its scalability. Accordingly, itis important to work out appropriate and cost-effective approaches for monitoring on-farm land use changes. Also, good practiceintegrated monitoring systems of SPS production and environmental improvements build confidence in generating strongoutcomes and scaling-up SPS technologies.
P104690 | Haiti Catastrophe Insurance | Latin America and Caribbean | Haiti | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2011 | 2012 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/968571475098053739/text/000020051-20140624203502.txt | http://documents.worldbank.org/curated/en/968571475098053739/pdf/000020051-20140624203502.pdf | The ICR offers a number of lessons of which the following are the most important (with some reformulation of language):1. In designing a project supporting disaster insurance there needs to be clarity about the linkage between the objectives and how the project design will meet those objectives. If the objective is to reduce financial vulnerability then the design needs to address both means and scale. In this case, the project was supply-driven in the sense that the insurance solution was the modality on offer when the PDO seemed to invite a broader demand-driven approach.2. Risk pooling through disaster insurance can be effective In reducing individual country financial risk, However, reducing costs and sustaining financial strength, calls for an optimum balance between reserves and reinsurance.3. In the establishment of a catastrophe insurance facility, extensive communication with participants is important to ensure that the costs and benefits of its products are well understood.4. The use of parametric insurance ( insurance based on immediately measurable physical parameters) is particularly important in catastrophe insurance to ensure rapid cash injection through quick payout. However, this injection of funds can only be effective for the impacted country if the country itself has, and can sustain, an effective post-disaster budget execution system.5. Even with a measure of insurance coverage, countries must continue to invest in risk reduction. Catastrophe insurance can only be a part of a broad risk management strategy. The cost of full financial protection would be prohibitive without proactive policy measures and physical investments to address the causes of risks and to mitigate vulnerabilities.
P104694 | Higher Education Development Policy Program - First Operation | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Education | IDA | DPF | 2009 | 2010 | 2016 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/115001468185394084/text/ICRR14827-P104694-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/115001468185394084/pdf/ICRR14827-P104694-Box394823B-PUBLIC.pdf | The series highlights the difference between changes in the legal framework and changes on the ground. It supported an ambitious package of reforms for all three operations. However, the reform's impact was perhaps less than could have been expected. One clear lesson is that the Bank has to look beyond the legal framework and take into account political considerations and the challenge of pushing a reform forward. The series showed how a DPO and an investment credit can support one another. The investment credit supported a great deal of the logistics necessary to monitor the reform. It also supported efforts to implement the steps required to turn the approved policies (prior actions) into reality. The overall reform benefits from this dual channeling of reform. The ICR's discussion of lessons (pages 27-28) also mentions these points. In addition, it introduces several other lessons, including: In Vietnam, consensus building takes time, and Bank support should reflect this. Likewise, the Bank's support can show flexibility in identifying prior actions for the next step of a DPO series. Identifying realistic outcomes is important, and too often DPO series focus more on developing prior actions and triggers. The selection of outcomes needs to take into account the time necessary for the policy to have impact. This was not the case for this DPO series, particularly for HEDPO I and HEDPO II.
P104716 | LR-Agriculture & Infrastructure Development Project | Western and Central Africa | Liberia | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2008 | 2016 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/681141467989892577/text/ICRR-Disclosable-P104716-07-08-2016-1467989879715.txt | http://documents.worldbank.org/curated/en/681141467989892577/pdf/ICRR-Disclosable-P104716-07-08-2016-1467989879715.pdf | The ICR draws the following main lessons from implementing this project. Government commitment for reformssecured early (that is, during the conceptualization of the project) may be critical for successful implementation of institutionalreforms. In the case of this project, the reforms carried out in the port sector was successful in transforming the Monroviato a landlord port model, however there is lack of commitment to reforms in the other sectors supported by theproject. A higher standard of due diligence is required in the procurement of suppliers in weak operatingenvironments to ensure selection of qualified suppliers who are most likely to perform satisfactorily.Under thisproject,it was assumed that the IITA, being present on the ground, could easily be sole sourced for the implementation of theagriculture component for Tree Crops; however this could not materialize and had to be abandoned and replaced by contracts with WFPand AFRICARE.
P104743 | Maldives - Pension and Social Protection Administration | South Asia | Maldives | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2009 | 2015 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/679691467993833844/text/ICRR-Disclosable-P104743-07-08-2016-1467993815811.txt | http://documents.worldbank.org/curated/en/679691467993833844/pdf/ICRR-Disclosable-P104743-07-08-2016-1467993815811.pdf | The ICR (pp. 24-26)lists five lessons or insights that emerge from the experiences of this project. Two ofthese are echoed here, and a third is added. Support for complex policy reform, when carefullyprepared, canensure thatcounterparts are on board once projects become effective. In this case, in-depth prior analytical work andtechnical assistance helped the Bank team prepare a solid project and hit the ground running. Disbursement linkedindicators may be useful to advance specific regulations, but they provide insufficient leverage to tilt the balance on majorpolicy decisions. Given reversals of pension reforms, the Bankwouldgain from investmentsin itsunderstanding of the frequency of pension policy reform reversals and the factors driving them.
P104749 | Justice Sector Support Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2010 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory |  |  | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/363541498855696409/text/ICRR-Disclosable-P104749-06-30-2017-1498855685033.txt | http://documents.worldbank.org/curated/en/363541498855696409/pdf/ICRR-Disclosable-P104749-06-30-2017-1498855685033.pdf | IEG draws the following lessons, adapted from those in the ICR: Operations with narrowobjectives focused on capacity-building and judicial operational efficiency (through support for skills development, physicalfacilities, and information systems) are better suited to the judicial sector than reform-leading instruments emphasizingstructural independence, particularly in transition countries. Successful implementation of an integrated casemanagement system can make a significant contribution to legal sector efficiency, particularly in transitioncountries.Soft investments in areas such as change management activities areimportant and often vital to the success of hard investments often preferred by the Borrowers. MidtermReviews are a vital opportunity to properly restructure a project, renew political commitment, and focus on critical changemanagement activities.
P104749 | Justice Sector Support Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2010 | 2016 | 2021 | PPAR | >=10 million & <25 million | Moderately Satisfactory |  |  | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/786741595517900211/text/Croatia-Justice-Sector-Support-Project.txt | http://documents.worldbank.org/curated/en/786741595517900211/pdf/Croatia-Justice-Sector-Support-Project.pdf | 3. Lessons 3.1 This assessment offers the following lessons that incorporate some of those identified in the Implementation Completion and Results Report and Implementation Completion and Results Report Review\. â€¢ At the design stage, a diagnostic assessment of the main contributors to court backlogs and consultations with major stakeholders could have informed the project design to address other important constraints to achieving the PDO. Outmoded or ineffective laws and legal processes can also cause court backlogs and delays. In Croatia, property transactions and company registration must go through the court system, adding tens of thousands of court cases annually. Removing property transactions from the courts and revising legislation associated with establishing companies so that they can take place online would greatly reduce the burden on the courts. These issues could have been attenuated through more inclusive consultations with potential users. â€¢ When infrastructure works need to be ready for implementation at project startup, it is important to verify that this is the case in advance. During implementation of the JSSP, it was found that the documents and drawings needed for the rehabilitation of courts were not as complete as had originally been thought, leading to significant delays in implementation. â€¢ Delays in critical reviews during project implementation can compromise midterm corrections. In the case of this project, a Mid-Term Review could have meaningfully informed the restructuring of the project. â€¢ When elections are in the near future, continuity risks can be attenuated by briefing key opposition politicians on the rationale for a project. In Croatia, when the new government came to office at the end of 2011, it had little knowledge of the JSSP and viewed it as an initiative of the previous government. To prevent cancellation, substantial effort had to be expended in briefings to demonstrate the project's worth, which resulted in delays.
P104752 | Paraíba Second Rural Poverty Reduction | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2009 | 2014 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/780211468001188441/text/ICRR14898-P104752-Box394888B-PUBLIC.txt | http://documents.worldbank.org/curated/en/780211468001188441/pdf/ICRR14898-P104752-Box394888B-PUBLIC.pdf | The following lessons arise from the project's experience (all are derived from or are adaptations from the ICR):1. A prolonged delay between Appraisal and Effectiveness may need restructuring of project implementation targets, modalities and financing.The time between appraisal and Effectiveness was nearly three years, and implementation was in effect delayed another year as a new State Government was installed. Resultantly, cost estimates became outdated due to inflation, the intended investment program was no longer possible, experienced staff left Cooperarar, and field staff needed re-training. It would have been better to have re-appraised and restructured the project early in implementation, focusing on realistic physical objectives and time frame, any additional Bank/Government funds required, and an intensified training program. 2. M&E should be institutionalized as part of a projectâ€™s organizational structure, implementation framework and work program. Although M&E activities were articulated at appraisal, Cooperar, under pressure to deliver a large work program with minimal time, neglected what was implicitly considered a non-operational activity that could be largely ignored without affecting the projectâ€™s main thrusts. The M&E program was susceptible to such neglect as it was designed more as an â€œadd-onâ€ to the project rather than as an integral part of the project, with internalized management, and implementation targets, and progress and work program included in the regular management meetings for the overall project (but with independent reporting), and in Bank supervision. 3 Income generation under community driven projects is more effective if attention is paid to the whole marketing or agribusiness chain.The Bank was quite effective in promoting the productive sub-projects beyond â€œfarm gateâ€ or local market. This needed training and facilitation in identification of market opportunities, contacting buyers and agri-businesses, and access to information.4. For community investment in rural water infrastructure, institutional development is a particularly important partner to the physical investment.The need to develop a community associationâ€™s capacity in O&M, tariff setting, and community organization was found to be particularly important for rural water supply sub-projects.
P104760 | PE Sierra Irrigation Subsector | Latin America and Caribbean | Peru | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2011 | 2017 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/595941505485032273/text/Peru-Sierra-Water-final-2017.txt | http://documents.worldbank.org/curated/en/595941505485032273/pdf/Peru-Sierra-Water-final-2017.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.(1) Combiningcapacity building activities for WUOsandfarmer groupssmall improvements in infrastructure/equipment can be useful in increasing the performanceof these institutions. In the case of this project, activities focused mainly on capacity building of WUOs and farmersgroups. In combination with small improvements in infrastructure/equipment and capacity building contributed to projectperformance.(2) Implementing activities associated with a gender dimension can be useful forencouraging women participation. In this project, women participation was improved through disaggregating by genderthe results of the project.(3) An adequate co-financing mechanism from the irrigation investment beneficiariesneeds to be specified at appraisal. For this purpose, a socio-economic study of the project areas and its beneficiariesbefore approval is required to properly target the co-financing mechanisms.In the case of this project, delays infunding from beneficiaries contributed to delays, although this was eventually resolved through the governmentproviding morethan planned by way of counterpart funding.
P104774 | LB-EMERGENCY POWER SECTOR REFORM CAPACITY REINFORCEMENT | Middle East and North Africa | Lebanon | IBRD | Non-FCS | Infrastructure | Energy & Extractives | SPF | IPF | 2007 | 2013 | 2014 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/210641475080500130/text/000180307-20141202110817.txt | http://documents.worldbank.org/curated/en/210641475080500130/pdf/000180307-20141202110817.pdf | The following lessons have been taken with some adjustment in language from the ICR:A pragmatic and focused project development objective that is consistent with the level of resources involved is essential to provide a realistic assessment of a projectâ€™s likely impact. In this case, the expectation that this small financial grant would be adequate to bring about significant restructuring of EdL was unrealistic and diluted the effectiveness of resources spent.Transparency in the objectives of the energy sector reform process, and an ex-ante buy-in from major stakeholders is essential for the success of an energy sector restructuring. In this project, there was a significant divergence between EdLâ€™s and MOEWâ€™s vision of how to proceed. The first EdL restructuring study was led almost exclusively by the HCP, and the second EdL restructuring study was led almost exclusively by the MOEW. Neither agency appear to have had established a significant buy-in from other important agencies and players. It is essential to understand who the winners and losers are in any significant power sector reform, so as to create a pro-reform coalition that can help foster the process. Otherwise, narrow interests are likely to overshadow national level interests.
P104786 | SD - Support to Agriculture and Forestry Development Project (ERL) | Eastern and Southern Africa | South Sudan | IDA | FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2008 | 2013 | 2014 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/576791474502761298/text/000020051-20140626111207.txt | http://documents.worldbank.org/curated/en/576791474502761298/pdf/000020051-20140626111207.pdf | Lessons derived from the South Sudan are applicable to many of the Fragile and Conflict Affected States supported by the World Bank Group. Lessons are derived from learning that has occurred since project close- as reflected in the ICR, and World Development Report 2011 on Conflict and Security. Â· In post-conflict environments, international development assistance should help to build capacity for medium-to-long term service delivery functions while tending to imminent development needs. NGOs can play a supportive role in service delivery, but during transition, priority should be placed on enabling local governments to gradually take responsibility for development programs in their jurisdiction. In South Sudan, local governments have depended on NGOs for their operating expenses. Very little attention was paid to the role of Local Governments during the transition, with regard to their assumption of responsibility or with regard to their role of providing local oversight of private service delivery functions. Â· Development assistance in fragile environments should ensure that expertise and capacity remains in program areas to continue assisting beneficiary communities. Facilitation teams trained by projects to provide technical assistance, whether in the agriculture, forestry or other development sectors, should be institutionalized to allow a continuation of these services after project close. (South Sudan ICR). Â· In a post conflict environment the ability to be flexible with regard to choice of service providers is a factor for project success. In South Sudan, ex-ante selection of institutions to provide certain services/inputs, and conditioning this to project effectiveness created delays in project implementation.
P104794 | Health Sector Strategic Plan Support Project | East Asia and Pacific | Timor-Leste | Blend | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2008 | 2015 | 2017 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/990811468619839697/text/ICRR-Disclosable-P104794-07-15-2016-1468619824315.txt | http://documents.worldbank.org/curated/en/990811468619839697/pdf/ICRR-Disclosable-P104794-07-15-2016-1468619824315.pdf | The ICR (pp. 30-31) contains several insightful lessons, including:Political and institutional instability can impedeprogress if not taken into account during project design. In this case, an ambitious SWAp and long list of potentialactivities proved too much for weak capacity that could not be fully rectified due to staff shortages and governmentturnover. Institutional reform is time-consuming, and a projects structure and level of ambition should take this intoaccount.There is a tradeoff between breadth and depth of project support. In this case, the focus on asector-wideapproach overshadowed the need for clarity on exactly what outcomes the project would specifically support (andfor which outcomes the project should be held accountable).While experienced, consistent, in-country Bank supportcanhelp strengthenimplementation capacity even in low-capacity environments, in this case, that support did not appearuntil the time of the first restructuring.
P104806 | Mekong Integrated Water Resources Management | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2012 | 2022 | 2023 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099040423120539829/text/P10480606e15460f10963a0cd7608b23c9b.txt | http://documents.worldbank.org/curated/en/099040423120539829/pdf/P10480606e15460f10963a0cd7608b23c9b.pdf | (Reference ICR paras. 96 to 99).The ICR (paras. 96 to 99) lists a number of lessons and recommendations derivedfrom the Projects experience. From these, IEG derives the following lessons relevant for similar projects carried out incomparable environments.Coordination of transboundary agendas iscritical for the sustainable developmentof a region.The regional agenda is critical for the Lao PDR as it sits almost entirely in the LMB andcontributes the largest flow to the lower stages of the Mekong River. Through the Mekong Program and activities within each membercountry, the combination of basin-related dialogue processes, underpinned by analytical work, enabled the member countries toengage in a collaborative manner, leading to the preparation of joint action plans.Regional outcomes in IWRM,along with a robust outcomes-based Results Framework, are challenging to develop. The Project faced the challenge ofsetting outcome-based indicators with results that would be directly attributable to project activities. Also, the achievement ofsome outcomes takes time to complete after project completion, such as the ongoing implementation of Fisheries Management Plans andRiver Basin Management Plans in the Lao PDR. Adequate attention should be given in future projects to designing methodologies toaddress these issues.
P104848 | Ho Chi Minh City Investment Fund for Urban Development Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2007 | 2013 | 2014 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/220661475113697003/text/000180307-20141202140152.txt | http://documents.worldbank.org/curated/en/220661475113697003/pdf/000180307-20141202140152.pdf | The following lessons are included in the ICR and elaborated by IEG:Where private sector participation is needed it is important to ensure full involvement of the private sector in the design of the Project, including training in Bank project requirements, In this case, the private sector was challenged by the Bank's fiduciary and safeguard policies. Understanding the local legal framework and agreement between the Bank and the Government on the main changes needed is a pre-requisite to implementing policy improvements to attain project objectives. In this case, the lack of Government guidelines on competitive selection of private sector partners was a disincentive for private sector participation. IEG also draws the following lesson:Compatibility between a Country Partnership Strategy and the Project objective and design improves the chances of project success while clarifying the Bankâ€™s role in the sector. This objective and design of this project project, while working in priority sectors, was not clearly linked in its outcome to the CPS objectives.
P104881 | Competitiveness and Integrated Growth Opportunity Project (CIGOP) | Western and Central Africa | Benin | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2008 | 2018 | 2019 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/373021545141938570/text/Benin-Compet-Integrated-Growth-Opportunity.txt | http://documents.worldbank.org/curated/en/373021545141938570/pdf/Benin-Compet-Integrated-Growth-Opportunity.pdf | The ICR presents several useful lessons, including: Project design should be simple andaligned with government priorities. In particular, it should reflect local capacity and should ensure that all stakeholderarrangements and roles should be clearly defined. IEG adds that overly ambitious or unclear design was a serious weakness in thisproject. Sustained government commitment and ownership are the keys to successful implementation ofprojects. It is especially important in the early stages of projects. The World Bank has thecapacity to turn around poorly performing projects, including redesigning the project and ensuring that the TTL providesstrong leadership that obtains strong government commitment, energizes stakeholders and gains the commitment of the projectteam. IEG adds an additional lesson. The project demonstrates the need for closemanagement attention., Early intervention may be called for, in cases where ISRs continually rate progress assatisfactory, yet where disbursements as a proportion of the total project amount are small.
P104931 | Second Development Policy Grant | South Asia | Bhutan | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2007 | 2008 | 2009 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/557281474904491003/text/000020051-20140619103728.txt | http://documents.worldbank.org/curated/en/557281474904491003/pdf/000020051-20140619103728.pdf | There are a number of useful lessons to be drawn from this ICR.In challenging conditions, such as during the political transition situation in Bhutan, cross sectoral development policy lending is appropriate because it can promote continuity in the government's reform program.In countries with weak technical capacity, institution and capacity building efforts are essential for success.Close alignment of up-front actions with the country's own development program helps ensure ownership and success.An improvement in basic data would allow for more effective and better targeted interventions and more accurate measures of success.
P104937 | Solid Waste Sector DPL | Middle East and North Africa | Morocco | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2009 | 2010 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/561341474628273003/text/000020051-20140625220252.txt | http://documents.worldbank.org/curated/en/561341474628273003/pdf/000020051-20140625220252.pdf | The following lessons are taken from the ICR with some adaptation of language:(i) Sector-wise DPLs can be feasible and successful. While the Bank has used extensively DPLs to support structural reforms mainly to strengthen the management of public resources, this operation illustrates that this kind of lending can be used effectively to promote change is line ministries involved in the supply of public goods.(ii) Ownership by the government is key to making progress in a new and difficult area of reforms, especially when using DPL operations. Sustained coordination among state entities is central to producing results. When the Government is in the driverâ€™s seat, the Bank can easily integrate in its country strategy government-initiated reforms and donors can support a transformative reform agenda.(iii) Launching an operation aimed at delivering services to citizens at central and regional levels can lead the government to scale up coordination and lay the foundations for improved financial management for local governments, and better handling of the relationship with private sector service providers. (iv) Sustainability in any sector requires strong investment in building internal technical capacity. Performance of this operation relied on the training program in new areas initiated by the Government, and supported by the donor community.
P104937 | Solid Waste Sector DPL | Middle East and North Africa | Morocco | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2009 | 2010 | 2022 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/328331642545458656/text/Morocco-Municipal-Solid-Waste-Sector-Development-Policy-Loans-1-4.txt | http://documents.worldbank.org/curated/en/328331642545458656/pdf/Morocco-Municipal-Solid-Waste-Sector-Development-Policy-Loans-1-4.pdf | 3. Lessons 3.1 A policy loan can be a viable instrument to start reforms in the MSWM sector, cover multiple aspects, and obtain the governmentâ€™s sustained attention and commitment for a nationwide program. However, because of the sectorâ€™s complexity, with many actors involved at the national and local levels, these reforms require long- term engagement using various instruments. Policy lending instruments could be the first phase, followed by projects that address multiple aspects of the sector. In Morocco, an ongoing local government support Program-for-Results project and the Casablanca Municipal Program-for-Results Project are focusing on transversal systems development and supporting the municipalitiesâ€™ financial and technical capacity issues that could not be addressed fully under the DPL series. 3.2 Continued attention to strengthening municipalities, both financially and institutionally, is key to enabling them to fulfill their service provision mandate on SWM sustainably. The DPL series achieved improvements in increasing revenues and decreasing arrears, but municipality revenues remain low compared with their potential. Moreover, municipalities do not have the financial autonomy to determine the rate and base on which to levy local taxes. The stagnant level of municipal investments in the MSWM sector after the DPL series closed was caused mainly by limited financial resources, and weak institutional capacities to deliver services and oversee delegated management and concession contracts. Thus, strengthening these financial and institutional capacities is key to completing the remaining investments and improving sustainable service delivery soon. Some specific solutions to improve the sustainability of MSWM efforts are strengthening state support for promoting public-private partnerships for construction and operations and maintenance of facilities, applying the principle of extended producer responsibility and polluter pays principles, and promoting environmental taxation. 19 3.3 Behavioral change and leveraging technology are critically needed to establish separation at source and promote waste reduction, reuse, and recycling, promoting the evolution into a circular economy and ensuring environmental sustainability. Recycling at the disposal stage through sorting centers that are set up in the landfills is insufficient to improve recycling rates. Urgent steps include involving households and other waste producers by organizing awareness-raising campaigns in collaboration with nongovernmental organizations to implement waste separation at source, and implementing the extended producer responsibility principle for actual valorization of various recycling value chains and green growth. An adequate communication and awareness campaign is also key. 3.4 Integrated upstream interventions, including policy reforms and incentives and investments for circular economy (along with a focus on collection and disposal), are needed to achieve sustainable solid waste management systems. Working on collection and disposal without sufficient traction on upstream waste reduction, separation at source, recycling, and recovery will not address MSWM needs. This is evident from the fact that the direct landfilling of about 90 percent of municipal waste without recovery, particularly of organic matter, considerably increases the problems related to leachate production. This also leads to landfills reaching their designed life span earlier than planned, requiring expansion or new landfill construction. The ongoing efforts led by Ministry of Industry in collaboration with Ministry of Interior and Ministry of Environment to develop a strategic vision to promote circular economy are important steps and will be very beneficial for the MSWM efforts and the sustainability of the outcomes achieved under the DPL series. 3.5 Scaling up the formalization of waste pickers requires broader enabling policy changes and capacity building and incentives at the local government level. The experience in Morocco with sorting centers at the Oum Azza (Rabat) and Meknes landfills was successful. Replicating this model in other cities will require enabling legislation to support the formalization of those workers through means such as creating a simple registration system through dedicated cooperatives and associations or directly at the recycling plants. Such cooperatives and associations would need to be equipped to train registered waste pickers and provide them with at least basic equipment to ensure the safety and efficiency of their work. 1According to estimates by the Heinrich BÃ¶ll Stiftung Foundation in 2020, based on a calculation of the quantities recovered in the informal sector, there may be as many as 34,000 waste pickers in Morocco. 20 2DPL series 1 and 2 provided $289.19 million, and DPL series 3 and 4 provided $245.9 million, totaling $535.07 million. 21
P104945 | Mozambique Water Private Sector Contracts - OBA for coverage expansion | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Sustainable Development | Water | RETF | IPF | 2007 | 2014 | 2015 | ICRR | Less than 10 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/794001467991004427/text/ICRR14716-P104945-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/794001467991004427/pdf/ICRR14716-P104945-Box393183B-PUBLIC.pdf | A number of lessons were selected by IEG from a longer list identified by the ICR: Output based programs need to assess ability of the recipient to pre-finance investments and consider pre-financing support mechanisms. In Maputo, the existing operator was under severe cash constraints for a variety of reasons, and struggled to pay for the initial investments in connections. Investment pre-financing can be a significant implementation challenge, which can be addressed through a financial assessment during preparation and the incorporation of support mechanism, where appropriate (e.g pre-financing advances or â€˜line of creditâ€™ utilized under the Bankâ€™s Program- for- Results (PforR) financing instrument).Output based payments do not inherently provide incentives for a change in behavior or investment. This project subsidized low-income households to connect to the water system, but it was not designed to incentivize the operator to pursue those connections. Under the arrangements for new connections at the time of project design and initial implementation, an OBA payment was at a disadvantage compared to â€œregularâ€ connections. In the case of this project, an exogenous factor (change in pricing policy) helped it to be more attractive.All the costs of program implementation accruing to the operator should be factored into the OBA payments. Under this project, the operator believes that it incurred significant costs related to the implementation of the program that were not factored into the OBA payments. These included staffing and time costs related to program outreach, financing costs related to costs that intended beneficiaries were not able to pay, and pre-financing costs for materials.There needs to be a strong understanding of the characteristics of the intended beneficiaries. The target beneficiaries generally faced significant challenges in providing US$17 application/connection fee and meeting the bureaucratic requirements of applying for a connection. In order to implement the program, the operator had to develop capacity to support households with low levels of literacy and record keeping.
P104946 | Yemen Safe Motherhood Voucher Program | Middle East and North Africa | Yemen, Republic of | IDA | FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2008 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/212351468190450598/text/ICRR14749-P104946-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/212351468190450598/pdf/ICRR14749-P104946-Box393191B-PUBLIC.pdf | Lessons drawn from the ICR, adapted by IEG:Strong project preparation includes clear and effective communication with the implementation parties, particularly if it is an innovative project approach. In the case of this project, there was a lack of clear understanding by the two hospitals about the overall project concept, the output-based disbursement approach, and the handling of complicated obstetric cases, all of which contributed to significant shortcomings in implementation.Government engagement is critical for achieving an objective that aims to have a demonstration effect for future public-private approaches. In the case of this project, the government was not a formal participant, and minimal efforts to engage the government, Ministry of Health, or Ministry of Finance prevented a greater impact on public policy. However, post-project workshops included the participation of the government, and there are indication of increased government buy-in to the performance-based approach using public-private partnerships.
P104960 | JO-AMMAN SOLID WASTE MANAGEMENT AND CARBON FINANCE | Middle East and North Africa | Jordan | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2009 | 2015 | 2015 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/731481467986321106/text/ICRR14727-P104960-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/731481467986321106/pdf/ICRR14727-P104960-Box393183B-PUBLIC.pdf | The ICR (p. 19) identifies several valuable lessons including the following:Innovative project designs are often linked to higher risks. Therefore, it is critical to have conservative target values and flexibility to make adjustments during project implementation through restructuring.Carbon finance is a results based instrument that is volatile to changes in the carbon market and any delays in project implementation. Extensive risk analysis and identification of mitigation measures, as well as robust efficiency analyses are required if regular investment operations include carbon finance.The success of the design-build-operate of the LFG-to-electricity contract depends on alignment of incentives of all parties and a realistic level of complexity. Under this project, the qualification criteria should have been lower and had a better fit with the buyerâ€™s technical capacity, including capacity to assure full conformity of technical specifications and site conditions.It is critical to continuously track and use M&E data for informed decision making. M&E data and analysis of the full results chain help guide restructuring decisions.Decisions regarding location of solid waste infrastructure in urban areas are highly controversial and socially sensitive. Proper public consultations including all stakeholders should be carried out and decisions on the location made during project preparation.
P104990 | Fourth Poverty Reduction Strategy Grant | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2009 | 2019 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/899921541176155707/text/129569-PPAR-P104990-P106083-P113241-P117495-PUBLIC.txt | http://documents.worldbank.org/curated/en/899921541176155707/pdf/129569-PPAR-P104990-P106083-P113241-P117495-PUBLIC.pdf | 6. Lessons 6.1 The following lessons emerge from the design and implementation experience of the PRSF 4â€“7 series\. â€¢ Programmatic DPF can be an effective form of support for a well-defined, country-owned reform program. In Rwanda, the PRSF 4â€“7 series backed a wellarticulated and sound development strategy with strong implementation arrangements, the 2008â€“12 EDPRS. Arguably, however, value-added of the series stemmed more from the predictable financing that it provided for the overall program and its encouragement to reforms through regular, institutionalized monitoring of progress, than from advancing the achievement of specific objectives and outcomes. â€¢ It is difficult to be definitive about the efficacy of a DPF series unless the results framework is tight-knit, the reforms supported have the requisite depth, and there is a strong and direct causal link between these reforms and the outcomes sought. Under the PRSF 4â€“7 series, progress was made in several cases toward the objectives and desired outcomes. However, the role of the policy actions that the series supported in bringing about that progress versus other contributory factors was not always clear. â€¢ A commitment to providing regular, predictable financing in the form of (multisector) general budget support operations implies that the World Bank needs to be prepared to accommodate dilution or deferral of reform content relative to what is foreseen at the outset. This underscores the importance of entering into such a commitment only in instances in which the World Bank has confidence in the government's long-term intent to see reforms through in good faith despite delays and temporary reversals rooted in technical or political economy factors. In Rwanda, there were several delays and setbacks; for example, the implementation of a revised tariff structure for electricity was continually deferred and diluted. However, all triggers specified in the operations under the PRSF 4â€“7 series (or their equivalent in terms of the substance of the policy actions) were eventually achieved, though in some cases with several years' delay, suggesting that the World Bank's confidence was well placed. â€¢ The World Bank can face a hard choice between adhering to a CPAF in a multisector budget support series and fulfilling the good-practice prescriptions in its operational policy for DPF. In Rwanda, confining prior actions and outcome indicators in the PRSF 4â€“7 series to those found in the CPAF offered clear advantages, such as institutionalized M&E and lower transactions costs, particularly for country authorities. However, CPAF design shortfalls and selectivity in its coverage spilled over into the series, leading to inconsistencies with good practices prescribed under the World Bank's operational policy for DPF. It was often difficult in the PRSF 4â€“7 series to trace the causal links between prior actions (many of which lacked depth) and outcomes sought. Moreover, certain objectives the series sought originally, such as fiscal decentralization, were pursued later through insufficiently focused measures and outcome indicators that were constrained to align with those in the CPAF. â€¢ Successful deployment of an IFMIS can be facilitated by high-level commitment and performance monitoring, sustained external support, and system ownership. In Rwanda, top-level attention to imihigo (performance contract) monitoring included a focus on successive phases of IFMIS rollout, which also received steady technical and financial support from the World Bank (through parallel DPF and investment project financing, and later Performance for Results financing) and from other partners (notably through a Public Financial Management Basket Fund supported by the European Union and the U.K. Department for International Development). In addition, Rwandan authorities believed that the IFMIS's in-house development gave the system's users a greater stake in its successful deployment. 1The World Bank later prepared an analysis of why the reduction in poverty during this period was limited. See World Bank 2013a. 2The precise estimates of poverty, and especially their comparability over time, have been a source of contention in the past. However, the figures cited here have been widely referenced in World Bank operational documents and are taken to be good enough. 3Rwanda's fiscal year was changed in July 2009 from calendar year to July to June to align with East African Community norms. 4There is, in fact, some ambiguity as to whether Poverty Reduction Support Grant 5 or PRSG-6 was the first operation to be aligned entirely with the Common Performance Assessment Framework. PRSG-5 was sometimes labeled a transition operation from the standpoint of being aligned with the Common Performance Assessment Framework (see, for instance, annex 2 of the program document for Poverty Reduction Support Financing 7 (World Bank 2011), but elsewhere (for example, paragraph 53 of the program document for PRSF-7), it was asserted, The PRSG-5 operation was the first operation that aligned the series with the . 5This Project Performance Assessment Report uses the term policy actions to refer to the entirety of measures recorded in the policy matrix and results framework as implemented before the approval of a given operation. By contrast, the term prior actions refers to the subset of measures (usually depicted in bold type in the policy matrix and results framework) that was formally identified as necessary for the approval of the operation. 6 The limitations of an ex post logical framework where objectives evolved over the four-year lifespan of the series can be illustrated with reference to prior action (i) under the program development objective of enhancing the skills of the population. At first, it is unclear how an assessment of the basic education system contributes to the intermediate objective of revamping the strategic and institutional framework for postâ€“basic education, although it arguably speaks to the ultimate objective of enhancing the skills of the population. The answer is that the initial focus in PRSG-4 had been on reducing the pupil-teacher ratio in the nine-year basic education program, but it shifted (exclusively) to postâ€“basic education from PRSG-5 onward. 7 The concept of (structural) depth was originally developed and used in IMF (2007). 8The SMART criteria require indicators to be specific to the objectives toward which progress was to be measured; measurable; achievable; relevant in the sense of appropriate to measure progress toward the objectives; and time-bound. 9 The East African Community fiscal year runs from July to June, in contrast to Rwanda's prior fiscal year, which followed the calendar year. Predictable provision of financing for well-performing countries was a key premise of the Poverty Reduction Support variant of programmatic development policy financing. 11The 2011 and 2015 figures are from the Rwanda Ministry of Education's 2015 Education Statistical Yearbook, which reports the transition rate to upper secondary â€”that is, from senior 3 to senior 4 (GoR 2016, 40). (http\.//mineduc.gov.rw/fileadmin/user_upload/Amatangazo/2015%20Education%20Staiatical%20 YearbookF.pdf). 12Some related (more disaggregated) indicators were tracked during the implementation period of the FY11 Skills Development Project, but this was after the PRSF series' closure. 13As indicated previously, the Skills Development Project was implemented after the PRSF series' closure. 14In addition, the National Institute of Statistics of Rwanda's 2015 Integrated Business Enterprise Survey indicates that almost 80 percent of respondents viewed the availability of skilled or technical labor as no problem (and another 13 percent viewed it as a minor problem). 15The law governing community-based health insurance is Law No. 62/2007 of December 30, 2007. Submission of the law to Parliament was a PRSG-4 prior action. 16For useful background on the evolution of community-based health insurance in Rwanda, see, for example, Kalisa et al. (2015). 17Details of the performance-based financing system implementation and its results are discussed in Basinga et al. (2010). The paper reports on data produced from a prospective quasiexperimental evaluation design that was nested in the pay-for-performance program rollout and compared facilities in a treatment group with those in a control group that continued to receive input-based financing for a two-year period for prenatal care and child preventive care. The study found that significant increases in the provision of some services, such as in-facility deliveries by pregnant women, were associated with pay-for-performance. The results suggest that financial incentives are significant and have a larger impact for services in which providers have more control, such as prenatal care quality. The study also suggested that for services that depend more on patient behavior, such as the decision to seek prenatal care, the program could consider providing financial incentives directly to the patient rather than the provider. 18See the figures for the percentage of children under age five using insecticide-treated bed nets under World Development Indicators (https\.//data.worldbank.org/data/source/worlddevelopment-indicators). 19In fact, implementation of a revised tariff structure was later envisioned (in PRSF-8, approved in November 2011) as one of the triggers for PRSF-9â€”which, given the demise of general budget support in 2012, never materialized. 20The bulk of the increase in access over the PRSF 4â€“7 series' life span appears to have taken place in 2009. This likely reflected a significant increase in generation capacity in that year. 21The number of households and enterprises with access to electricity increased from 91,332 in 2006 to 159,516 in FY10 (compared with a target of 139,000) and to 308,326 in 2011â€“12 (compared with a target of 270,000). Generation capacity increased from 60 megawatts in 2006 to 84 megawatts in FY10 (compared with a target of 80 megawatts) and to 157 megawatts in FY12 (compared with a target of 130 megawatts). 22A subsistence level of electricity (30 kilowatt-hours per month) would be unaffordable for more than three-quarters of the unelectrified population. In recent years, fiscal transfers to the energy sector have declined from 2.5 percent of gross domestic product in FY14â€“15 to 1.4 percent in FY16â€“17. 24In addition, some of the measures lacked depthâ€”for example, completion of a tariff study and validation by Rwanda Utilities Regulatory Authority and the Ministry of Infrastructure. Others, such as the removal of the import duty and value-added tax on liquefied petroleum gas to promote its use and reduce dependence on charcoal, had no direct relation to the electricity outcomes targeted, although they arguably contributed to improving cost effectiveness (and environment-friendliness) in the broader energy sector. 25These investment project financing operations were the FY05 Urgent Electricity Rehabilitation Project and the FY10 Electricity Access Scale-up and Sectorwide Approach Development Project. 26 Implementation Completion and Results Report, page 66. 27 Implementation Completion and Results Report Review, section 4. 28See NISR (2016). Note that the standard for measuring urban access is 200 meters or less from the source and rural access is 500 meters or less. 29 The target for 2011/12 was later revised downward to 37 percent under PRSF-8. 30 The World Bank was Co-chair of the Rural Sector Working Group at the time. 31The 2011/12 figure is from the Implementation Completion and Results Report Review (efficacy section, objective 3), and was slightly under, but close to, the target for that year (PRSG-6 program document, page 44). 32Lack of prior consultation with development partners and other stakeholders (for example, though the Agriculture and Rural Development Sectoral Working Group) meant that alternative solutions to fraud concerns, such as the use of electronic wallets, could not be debated. 33 See also Implementation Completion and Results Report, page 40. 34 See Implementation Completion and Results Report Review, section 4 (objective 3). 35In particular, there are discrepancies in the land area subject to radical terracing between the National Institute of Statistics of Rwanda's seasonal agricultural surveys and figures reported in Implementation Status and Results Reports for the Transformation of Agriculture Sector Program-for-Results operation. 36 Law no. 40/2008 of August 26, 2008, established the organization of microfinance activities. 37 The 2008 figure is from Kantengwa (2010). The later figures are from AMIR (2015). The 13.9 percent of gross domestic product target for 2012 is from the PRSG-6 program document (table 9, page 41). 39Savings and credit cooperatives now account for an important segment of the microfinance institution sector (AMIR 2015). 40According to the website of the Financial Sector Reform and Strengthening Initiative\. The FIRST initiative is a multidonor grant facility that provides short to medium-term technical assistance to promote sounder, more efficient, and inclusive financial systems. Since its inception in 2002, FIRST has funded over 600 projects in about 120 countries, with commitments over $135 million. For more information, visit the website at https\.//www.firstinitiative.org/. 41Several districtand sector-level officials gave the mission demonstrations of the SmartFMIS' capabilities. 42Despite changes in Public Expenditure and Financial Accountability methodology between the 2007 and 2010 PEFAs and the 2017 PEFA, the constituents of this score are unchanged, so the scores are comparable. 43The latest figure is taken from the Implementation Status and Results Report for the Public Sector Governance Program-for-Results operation. 44The Implementation Completion and Results Report (page 47) provides details concerning the substance of the amendments. For instance, they were designed to bring the provisions of the law in line with (i) the revised mandate of the Rwanda Public Procurement Agency, resulting from the full devolution of the procurement function to the procuring entities; and (ii) the Common Market for Eastern and Southern Africa (free trade area) procurement framework (which Rwanda joined in 2004). 45 Separate independent review panels also operate at the district level. 46The Implementation Completion and Results Report Review for the PRSF 4â€“7 series reported that the share had increased very modestly to 75 percent by 2012, missing the target of 87 percent by the series' end. However, the 2010 Public Expenditure and Financial Accountability appears to contradict this because it affirms that 86.6 percent of all contracts above the threshold were awarded by open competition. This is also more consistent with the 2015 Crown Agents findings (Crown Agents 2015). 47See Crown Agents findings (Crown Agents 2015). Similarly, the Rwanda Public Procurement Agency's Annual Activity Report for 2015â€“16 (dated January 2017) affirms, based on its procurement audits, that more than 88 percent of public procurement by value took the form of open bidding. However, it is notable that the Rwanda Public Procurement Agency's reach does not encompass all aspects of a broader concept of public procurement. For instance, as discussed in the section on electricity, many power purchase agreements that the Rwanda Energy Group entered into with independent power producers were negotiated bilaterally rather than tendered competitively. 48Three aspects were scored under procurement in the 2010 Public Expenditure and Financial Accountabilityâ€”the previous methodology\. evidence on the use of open competition for contract award, extent of justification for use of less competitive procurement methods, and existence and operation of a procurement complaints mechanism. All received an A score, despite the subsequent strengthening of the independent complaints mechanism (assessed according to six distinct criteria under the new methodology followed in the 2017 PEFA). 49For example, citizen report cards for 2014â€“16 show citizens' overall net satisfaction with local government services as increasing from 60 percent in 2014 to 75.9 percent in 2016. Trends for many individual service categories (health, for example) are similar. For more detail, see World Bank 2018b. 50For further details, see the discussion in the Implementation Completion and Results Report for the PRSF 4â€“7 series (World Bank 2012, 49â€“50). 51A 2010 census of public sector workers (including workers at the local government â€”province, district, and sector-level, and in-service delivery units such as educational institutions, hospitals, and health centers) showed that approximately 46 percent of workers had been in their current position less than three years and 62 percent had been in their current position less than five years. However, no subsequent census of public sector workers has been made available that would allow comparisons over time.
P104993 | Emergency Services Support Program Multi-donor Trust Fund | Middle East and North Africa | West Bank and Gaza |  | FCS | Human Development | Social Protection & Jobs | RETF | IPF | 2007 | 2011 | 2013 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/705051474905510646/text/000020051-20140625080740.txt | http://documents.worldbank.org/curated/en/705051474905510646/pdf/000020051-20140625080740.pdf | Even with the emergency nature of a project, implementation can still be closely monitored through clear output and outcome indicators. In the case of this project, indicators were eventually clarified and provided a stronger basis for assessing project achievements.In addition, according to the ICR (page 22):Field-based task team leadership, with intensive supervision and adaptability, enables responsiveness of a project to emergency situations. In this project, the implementing units had easy access to the Bank team and project issues were identified early.Spot check audits conducted by an external auditor can be useful for monitoring implementation progress and proper use of project funds. In this project, the spot checks were critical monitoring tools in the absence of mid-term reviews or more formal assessments.
P104994 | Bishkek and Osh Urban Infrastructure Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2008 | 2016 | 2017 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/876501487372330927/text/ICRR-Disclosable-P104994-02-17-2017-1487372310737.txt | http://documents.worldbank.org/curated/en/876501487372330927/pdf/ICRR-Disclosable-P104994-02-17-2017-1487372310737.pdf | The following lessons are selected from those presented in the ICR (p30-32), with some modification oflanguage:1.To enhance the capacities of the local industry, it would be beneficial to offer structured trainings in the early stagesof project implementation. Trainings to strengthen the capacity of the private engineering and construction industryfocusing on planning, design, implementation and supervision of urban works and procedural requirements for procurement in WorldBank financed projects offered in the latter stages of this project generated significant interest among the local industry andparticipants requested follow-up trainings on various topics such as design techniques, approaches during construction andinstallation, on-site verification and controls, energy efficiency measures, etc., indicating strong demand for knowledgetransfer.2. When the country and sector context are less conducive to reforms, simple, straightforward projectswith achievable objectives are more likely to close with satisfactory results. Although Bank supported programs should becognizant of the need for deepening the institutional and policy dialogue over time, it is important to first ensure a minimumlevel of basic services for the population, while in parallel exploring opportunities for further reforms.3.Demand-side measures like reduction of water waste and changes to consumption norms are necessary to reduce water waste andimprove the commercial operation of the water utilities. Water consumption norms across the Central Asia region areextraordinary high, a legacy from the Soviet period, resulting in excessive water use and wastage.
P104995 | Santos Municipality | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2010 | 2015 | 2017 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/755261496238016227/text/ICRR-Disclosable-P104995-05-31-2017-1496237998195.txt | http://documents.worldbank.org/curated/en/755261496238016227/pdf/ICRR-Disclosable-P104995-05-31-2017-1496237998195.pdf | The ICR included five lessons of which following three have broad applicability:1. Strongerefforts are required to ensure that the Feasibility Study Report and Preliminary Engineering Designs (PED) are as accurate aspossible. Preliminary engineering designs only provide approximate cost estimates. Trust funds are often used for PED,because of perceptions of conflict of interest in appraising the detailed engineering designs (DED). Furthermore, the client maynot have the procurement, technical, supervision and management capacity to properly assess the detailed engineering design andsupervise the work. Therefore, a project could fund an independent well-qualified engineer under the loan, housed in the projectimplementing agency.2. Concentrating many consultancy activities in one single contract holder maycreate a risk of implementation problems. The hiring of one consulting firm to perform the three functions of: (i)engineering design, (ii) supervision of the civil works, and (iii) project and contract management support to the UGP createdimplementation problems.It is a common practice to combine the design and supervision of construction tasks under the sameconsultant firm. However, adding the function of overall project management within the same contract does not allow for thedimension of an independent project supervision.This lack of an independent supervisor is a missed opportunity to mitigatethe risks of incompetence and / or fraud within the civil works contract(s). A project could ensure that the implementing agencieshave adequate capacity for all phases of the project, with an experienced independent owners engineer to supportimplementation.3. Bidding processes whereby only one bidder submits should be reviewedvery carefully and possibly re-launched with a different approach if appropriate.Thirty-nine firms bought thebidding documents for the project drainage works, but only one contractor composed of two firms submitted a bid, which was of amuch higher cost than the design engineering estimate, i.e. 50 percent higher.
P105002 | ID National Program for Community Empowerment in Rural Areas | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2008 | 2012 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/406681474628258754/text/000020051-20140625220720.txt | http://documents.worldbank.org/curated/en/406681474628258754/pdf/000020051-20140625220720.pdf | The following lessons are taken from the ICR with some adaptation of language:Well evaluated projects can attract bilateral donors through linked trust funds, such as the PNPM Support Facility to support innovative initiatives, pilot programs, implementation support and program evaluation.Rapid and large scaling up of a programâ€™s operation can exceed institutional capacity, which, in turn, can cause serious problems with data collection and the management and capacity of the MIS. Such challenges should be anticipated and addressed in project design.Several system problem areas common to community-driven operations, such as shortcomings in the mobilization and training of a sufficient number of qualified consultants/ facilitators, delayed and incompliant procurement, and weak financial management including issues of corruption, even if correctly identified, may be difficult to address ex-post. With regard to procurement, simpler and faster procurement procedures, which are reportedly being used in the PNPM-Rural 4 Project, may be more appropriate.Well-conceived and targeted evaluations can provide solid evidence of what works and what doesnâ€™t work in the implementation of a program such as PNPM and provide policy recommendations to improve implementation and the design of successor operations.
P105024 | Social Protection Project | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2008 | 2018 | 2019 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/748541550015210353/text/Jamaica-JM-Social-Protection.txt | http://documents.worldbank.org/curated/en/748541550015210353/pdf/Jamaica-JM-Social-Protection.pdf | The following lessons are drawn from the ICR:Political support and ownership on abroad scale are essential to successful social protection reforms. Project success reflected strong overallGovernment support for objectives, a central forum for social protection in the form of the PIOJ, MLSS role as manager ofimplementation, and the commitment of the Ministry of Finance to pension reform. This created the right environment toimplement the project and secure longer-term sustainability.Human capital development requiresdemand and supply-side interventions. For conditional cash transfers to be effective, they requireappropriate working arrangements between stakeholders, notably the support of education and health sectors at national andsub-national levels to provide timely and quality services, and on the demand side the relaxing of financial and informationbarriers that keep the poor from utilizing services.
P105029 | Third Programmatic Business Product and Efficiency Development Policy Loan | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2008 | 2011 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/812301474569050872/text/000020051-20140625074152.txt | http://documents.worldbank.org/curated/en/812301474569050872/pdf/000020051-20140625074152.pdf | IEG concurs with the ICR on the lessons learned emphasizing in particular the importance of government commitment to ensuring success of the program, attention to political economy of reform, and the importance of close collaboration with other partners active in the country. The lessons concerning importance of flexibility provided by the programmatic approach is also well taken although in this case, it appears that the Bank did not fully make use of that flexibility by resetting the program targets in light of the implementation experience.
P105029 | Third Programmatic Business Product and Efficiency Development Policy Loan | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2008 | 2011 | 2018 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/385471500561415074/text/110740-PPAR-P094301-P095213-P105029-PUBLIC.txt | http://documents.worldbank.org/curated/en/385471500561415074/pdf/110740-PPAR-P094301-P095213-P105029-PUBLIC.pdf | 6. Lessons 6.1 The experience of this DPL program suggests, once again, that in-depth knowledge and government buy-in were essential in Colombia for designing reform programs with substance. In general, the prior actions of this program reflect well what the World Bank knew about Colombia. For example, in the financial sector, the reforms selected exemplify the World Bank's deep understanding of the problems that had to be solved to strengthen the financial system. The impact of the reforms is beginning to be felt even if the results indicators were inadequate for assessing properly the program's contribution. On the other hand, lack of political commitment to tackle the fundamental problems in Colombia's foreign trade sectorâ€”weak institutions and entrenched protectionismâ€”meant that the reform actions supported under this program addressed secondary issues. Consequently, the impact of the actions pursued was limited. 6.2 Staggering interventions by policy areas presented trade-offs between the breadth and depth of the program. While the approach appeared attractive by allowing the World Bank to tackle a larger number of issues while staying focused at each given moment, it also meant limited attention to some issues and one-off support in some areas. The design of the program could have paid more attention to assessing the implications of such trade-offs for achieving the program's objectives, especially the risks to development outcomes in the long run. The experience with this DPL program suggests that staggering interventions to cover more ground is likely to produce programs of modest relevance and shallow impact.
P105036 | Second Education Reform for the Knowledge Economy | Middle East and North Africa | Jordan | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2009 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | High | http://documents.worldbank.org/curated/en/839441512574393630/text/ICRR-Disclosable-P105036-12-06-2017-1512574379277.txt | http://documents.worldbank.org/curated/en/839441512574393630/pdf/ICRR-Disclosable-P105036-12-06-2017-1512574379277.pdf | The ICR (pp. 14-15) offers several useful lessons, including the following lessons adapted byIEG:A bottom-up change built around the school community is more effective than top-down change. The projectshowed that the sustainability of a national school-based development system relies on the systems development at the locallevel, rather than on a series of isolated interventions. When donors supported local players and built their capacity,rather than substituting for them, sustainability was enhanced. Local community engagement, such as having parents involvedin the school development improvement plan, countersigning school expenditures, and meeting regularly with school staff, resultedin a sense of ownership that contributed to sustainability. Close and earlyattention to costing inputs during the design process reduce the risks of financial shortfalls. Under the project,unbalanced estimates for infrastructure resulted in the curtailment of the number of schools that were constructed. When priorities are clearly established within a national policy framework, aprogrammatic approach that brings donors together to cooperate on a single platform is more effective than separateinterventions. This was demonstrated under the project through harmonization and cooperation among the donors,facilitated by the Banks effective convening role in a multi-donor partnership.
P105075 | Third Pakistan Poverty Alleviation Fund Project | South Asia | Pakistan | Blend | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2016 | 2018 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/681981514756464566/text/Pakistan-PAF-Agriculture-2018-Final.txt | http://documents.worldbank.org/curated/en/681981514756464566/pdf/Pakistan-PAF-Agriculture-2018-Final.pdf | The project has provided a number of lessons (ICR pp. 33-35), including the following lessons adapted byIEG: Effective inclusion of women in a development project is facilitated by making gender an integrated part ofproject design, and proactive engagement during project implementation.Once started (after project approval),WID became a joint priority for both PPAF and the Bank, with adaptations in project design, staff training, adjusted implementationprocesses, and staff engagement. These concerted actions stimulated high womens participation, leadership andbenefits. 2. An appropriate range of specialist skillscan criticallyaffectproject implementation, adaptation and outcomes of a project.This was well illustrated in the PPAF IIIteam. This complex project required a wide range of specializations, and most such needs were covered by relevant Bank staff andconsultants. But during project preparation there were no specialists in education and health, and boththe education andhealth programsonly commenced towards the end of implementation. 3.Innovative approaches can help reach the poor and remote villages.PPAF trained young members in thecommunity to become Community Resource Persons, acting as motivators and providing basic extensionmessages. 4. Success with community driven development can be facilitated byan integrated project design, and proactive support during project implementation.In addition toPPAF-IIIs social mobilization component, much of the other two operational components (livelihoods and microfinance) was technical assistance to the communities. The emphasis on social mobilization improved technical capacity and was the primary driver ofthe projects largely successful community development achievements. 5.Performance monitoring using a defined scoring system can help targeting assistance.A MaturityIndex was used to identify performance of all participating communities. (Financial viability, social cohesion andgovernance were amongst the criteria used). This helped monitor overall project performance and identify where additionalassistance was needed.6. Significant change and economic development can befacilitated by a long-term commitment.PPAF was created in 1999, with funding and support from the Bank. PPAF-III,closing in January 2015, thus completed 14 years. Even under PPAF-III the PPAF program was still developing, and in a number ofrespects, bringing in further innovations and large changes such as in micro-finance.
P105092 | Nutrition and Malaria Control for Child Survival | Western and Central Africa | Ghana | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2008 | 2013 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/452921474569507373/text/000020051-20140626124207.txt | http://documents.worldbank.org/curated/en/452921474569507373/pdf/000020051-20140626124207.pdf | The ICR lists four lessons learned, and among them:1. An innovative approach that mixes a SIL (whose aim is to direct finance to neglected topics and areas) and a SWAP (whose aim is to bring donors around a common plan) can be effective in achieving nutrition and malaria prevention at community level; 2. The importance of local ownership to the achievement of community-based health and nutrition objectives should not be under-estimated.IEG added the following lessons:3. Nutrition project leadership is often a contentious issue among ministries/governmental agencies. Unless institutional roles, responsibilities and accountability for nutrition are well defined by Government, it will be difficult for project implementation arrangements to be both efficient and successful;4. It is risky to share project leadership among ministries/governmental agencies. A less risky option worth considering is the organization of the project into two (or more) sub-projects, and the assignment of one lead agency for each sub-project.
P105101 | The AO-Local Development Project | Eastern and Southern Africa | Angola | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2010 | 2022 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099050723192512505/text/P105101-8e3e8e3d-b832-4827-b761-1422e188a963.txt | https://documents.worldbank.org/curated/en/099050723192512505/pdf/P105101-8e3e8e3d-b832-4827-b761-1422e188a963.pdf | The ICR (p. 43-44) included several lessons learned, including the following ones that were adapted byIEG: Involving entities at the local level requires strong technical and fiduciary support.This project envisioned that municipalities were to implement activities such as the construction of local infrastructure.However, the project did not provide technical assistance to the municipalities to be able to provide strong quality control andoversight. The ICR (p. 43) recommended the following useful actions for future projects in this area: i) provide routine fundingfor independent technical audits of infrastructure; ii) rotate local FAS staff across provinces on a regular basis; and iii)conduct continuous audits of provincial audits. Building strong links between national ministries and localentities is key for sustainability and long-term development. In this project, collaborating and coordinating between theministry and municipalities helped to stimulate local development since municipalities were empowered to identify and prioritizetheir development needs. Constructing sub-projects such as schools, water points, feeder roads, and healthcenters requires close coordination with relevant line ministries to ensure that they comply with national norms and standards andare being operated according to national procedures. While this project exceeded its targets for education, health,nutrition and population services, the 2019 technical audit identified shortcomings in terms of norms and standards. Theseshortcomings included appropriate size of schools and classroom as well as width and curvatures of feeder roads etc.
P105116 | Social Protection Development | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2008 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/412121469200617579/text/ICRR-Disclosable-P105116-07-22-2016-1469200598283.txt | http://documents.worldbank.org/curated/en/412121469200617579/pdf/ICRR-Disclosable-P105116-07-22-2016-1469200598283.pdf | IEG draws three lessons from the experience of preparing and implementing this project: Thorough andbroadly-based consultations at the appraisal stage can help to establish government ownership and avoid the inclusion in theproject of activitiesthat do not enjoy a sufficient degree of political consensus. As a result of acceding too quickly to theMinistry of Finances request to include a pension reform component, client ownership was undermined, and the Bank had tospend several years trying to push forward the pension agenda when there was no desire on the part of the Borrower to doso. More careful attention during supervision missions can lead to the early identification and rectification ofprocurement issues. In this case, the issues were not identified until a procurement post review mission took place in April 2013,four years after effectiveness. Focusing attention on existing institutions and on building their capacity has the doubleadvantage of helping to ensure sustainability and reducing the complexity of project implementation. In this case, the creation ofnew institutions and major reorganization of existing ones were deliberately avoided. Similarly, the choice of relativelystraightforward IT applications, rather than complicated and sophisticated technologies, facilitated the absorption and beneficialuse of the technology by the Borrowers entities.
P105122 | Rural Economic Development Initiative | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2010 | 2018 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/221301526663518404/text/Jamaica-JM-Rural-Economic-Development-Initiative.txt | http://documents.worldbank.org/curated/en/221301526663518404/pdf/Jamaica-JM-Rural-Economic-Development-Initiative.pdf | The following is a summary of keylessons from the ICR that this Review considered were highly relevant to this and similaroperations: Technical assistance, implementation support of sub-projects, facilitation of contractualarrangements are critical elements for linking enterprises to markets. Enterprises that received only limitedcapacity building, particularly at the beginning of project implementation, tended to have a lower success rate. JSIF contractedthe service of specialized technical assistance providers which systematically resulted in stronger enterprises, with a clearvision and sustainability plans, and strong contractual arrangements with wholesale buyers. Leadership needs todelegate responsibilities among core managers to ensure continuity, in case leadership needs tobe replaced.Leadership and judicious delegation were found to be important in organizing groups forsub-project development and implementation in this project. Often leadership is concentrated in a single person, with few othersknowing or understanding the business and being able to step in. In this project, when a leader of one of the rural enterprisespassed away and another relocated to a different country, the groups and the sub-projects collapsed or performed well below thelevel achieved under long standing leaders because those leaders had not engaged others through delegation.
P105122 | Rural Economic Development Initiative | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2010 | 2018 | 2021 | PPAR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/308901615827130167/text/Jamaica-Rural-Economic-Development-Initiative.txt | http://documents.worldbank.org/curated/en/308901615827130167/pdf/Jamaica-Rural-Economic-Development-Initiative.pdf | 3. Lessons 3.1 For complex productive alliance projects involving the selection of multiple rural subprojects and the introduction of new private sector market concepts to rural communities, substantial investment to ensure project implementation readiness during preparation can contribute to a faster and more effective project start. REDI was based on implementing multiple subprojects and introducing new private sector market concepts to subsistence farmers and informal tourism providers. In this case, the project would have benefited from better project preparation in terms of identifying an initial set of potential candidates for subprojects (from existing cooperatives, benevolent societies); developing a simple, expeditious subproject selection process; and ensuring the availability of technical assistance needed for launching subprojects (for example, registration, business management practices) at project start. As it happened, the project started without a suitable list of potential subprojects to develop. It was burdened with a subproject selection process that had to be streamlined during implementation. 3.2 For productive alliance projects introducing modern technologies and new business management practices into rural populations, ensuring adequate skills and 9The aide-memoire (World Bank 2015a, 3) indicated that for the previous four years the Food and Agriculture Organization had been providing support to JSIF staff for the gathering and analysis of financial information to measure the impact of the project. JSIF's efforts had suffered considerable delays, leaving both the World Bank and JSIF unable to show evidence that the subprojects were having the intended impacts. The World Bank team also explained to JSIF management that with the current level of information provided to the World Bank, the project would most likely be rated moderately unsatisfactory at the time of evaluation. capacity in the implementing agencies will enhance the achievement of results. The REDI project aimed to introduce modern agricultural technologies and new business management practices and systems into Jamaica's poor, rural, largely subsistence farming sector. The implementing agency, in this case, had an agricultural specialist to address the former but lacked a business planning specialist for the latter. Similarly, the project set out to strengthen the business management practices and market outreach of the informal community tourism providers. The implementing agency, however, lacked both the business management expertise and community tourism capacity to assist the subprojects in these areas. It acquired specialists in these areas only after several years of project implementation. Ensuring adequate project capacity from the outset would have strengthened project implementation from the start. 3.3 Technical assistance supporting private sector market approaches can be critical for linking rural agricultural and tourism operations to new and evolving markets. The REDI project demonstrated that small-scale operators that received only limited capacity building, particularly at the beginning of project implementation, tended to have a lower success rate accessing new markets than those benefiting from technical assistance focused on private sector business practices. It was for this reason that the implementing agency contracted the services of specialized technical assistance providers to assist subprojects through the process. The result was stronger operators, with a clearer vision, more sustainable business plans, and stronger contractual arrangements with wholesale markets.
P105124 | Himachal Pradesh Development Policy Loan 1 | South Asia | India | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2008 | 2010 | 2011 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/871231475069801377/text/India-Himachal-Pradesh-Development-Policy-Loan-1.txt | http://documents.worldbank.org/curated/en/871231475069801377/pdf/000020051-20140624165139.pdf | The ICR included lessons but they were weak since most of the material was about project activities and outcomes and not about broad lessons . From the perspective of this Review three lessons emerged from this ReviewComprehensiveness vs Focus: It is tempting to embark on complex DPL's that cover all or a large part of a Government development program. While the hydropower and environmental components were closely related, as a group they were not tightly related to the project's fiscal and governance objectives and therefore not absolutely necessary for the other components in the DPL. On the other hand they increased implementation complexity to the DPL. The lesson is that a separate DPL specifically for set of important and substantial sectoral development issues is more likely to lead to focused attention on those issues than when they are included in an omnibus program.Monitoring and Evaluation: All projects/programs need an adequate M&E system. In this project the M&E system was an aggregate of individual systems for each stakeholder (mainly GoHP departments) without any coordination of M&E design, standards or processes. The lesson is that to achieve adequate M&E arrangements in programs it is necessary to have an institution, however small, responsible for ensuring consistent design and standards for M&E. The Challenge of Numerous Studies: An important cause for delay in completing studies is the understandable difficulty in reaching agreement on terms of reference. For only one of the studies (Environmental Master Plan) did the first tranche conditions require the completion of the terms of reference although the study was still not completed on time. The lesson is that to achieve the implementation of studies within the short time span of a DPL, their terms of reference should be agreed with the Government at negotiations and included in the PD.
P105135 | Madagascar Fifth Poverty Reduction Strategy Credit | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2010 | 2013 | ICRR | >=50 million & <100 million | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/586191475084021997/text/000020051-20140625220452.txt | http://documents.worldbank.org/curated/en/586191475084021997/pdf/000020051-20140625220452.pdf | IEG supports several of the lessons identified by the ICR (with some modifications), including:The ICR correctly notes that the decision to suspend budget support series can serve a strong signal in countries undergoing governance crises. At the same time, it raises important questions about the readiness of countries to sustain DPL series over the long term (or their demonstrate their readiness to revive a DPL-supported program). It is important for various donor partners to be clear about the benchmarks for withdrawing or reviving support.DPLs that support governance reforms should be based on rigorous political economy analysis, including a review of larger dynamics that threaten political stability. There is also need for much greater clarity on what constitutes feasible governance reforms and monitorable indicators of progress (for instance, measurement of actual levels of corruption are nearly impossible to determine with accuracy and precision, whereas assessments of opportunities to exercise discretion are doable).The provision of supplemental financing in parallel to the withdrawal of PRSC support can send mixed signals and should be thought through carefully.In capacity weak settings, there is often a needed to complement a DPL series with a more extensive capacity building and technical assistance program in parallel.
P105143 | Albania MD Capacity Building & Support to Implement the Integrated Planning System | Europe and Central Asia | Albania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2008 | 2012 | 2013 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/866861474637032762/text/000020051-20140625192636.txt | http://documents.worldbank.org/curated/en/866861474637032762/pdf/000020051-20140625192636.pdf | The main lessons that the ICR and IEG identified are as follows:Complex design in a low capacity environment should be avoided at all costs. While it is tempting to combine many components into a single operation for possible economies of scale in preparation and supervision, the reality is that the pace of implementation can suffer, and the savings in preparation are often translated into more intensive supervision and a subsequent re-design of the project.Projects covering a short time span should avoid complex but under-designed components. Major IT investments such as the AFMIS are more likely to succeed if planned in sufficient detail before the implementation.Lack of competition in contract award can have a negative impact on efficiency or efficacy, and should be avoided for large contracts or important project components.An excessive number of donors in a multi-donor trust fund established to support a specific project can add unnecessary complexity to the project itself. When PIUs are staffed by civil servants, there should be sufficient numbers of staff with the required skills, and sufficient time freed up from other responsibilities to be able to effectively carry out project management functions.The Bankâ€™s design, supervision, monitoring and reporting on trust funded projects needs to improve.
P105164 | Second Student Loan Support Project, APL Phase I | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2008 | 2013 | 2014 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/747201474630715215/text/000020051-20140626123219.txt | http://documents.worldbank.org/curated/en/747201474630715215/pdf/000020051-20140626123219.pdf | The following lessons are adapted from the ICR (p. 19):Student loans can reduce dropout rates, especially among disadvantaged populations. Agreements with institutions of higher educations, in this case, permitted the introduction of a more results-oriented culture.It should not be assumed that funds diversification through private capital markets will be successful. In this case, raising funds from capital markets has been less successful than leveraging ICETEX resources with funds from other sources (due, at last in part, to the impact of the global financial crisis), including municipalities and universities and through Sustainability Funds.It is possible, through incremental changes to formulas used to allocate student loans, to improve targeting of disadvantaged students and make that targeting compatible with risk reduction.
P105176 | Second Rural Sector Support | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2008 | 2013 | 2014 | ICRR | >=25 million & <50 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/362651474637299956/text/000020051-20140626110359.txt | http://documents.worldbank.org/curated/en/362651474637299956/pdf/000020051-20140626110359.pdf | The ICR offers a number of lessons of which the following are the most important (with some reformulation of language):Â· A marshland investment model including: investment in irrigation networks in marshlands and associated hillsides; adoption of sustainable agricultural practices; improvement in agricultural value chains; and, access to markets and supporting farmer organizations offers a potentially valuable framework for replication. This Rwanda case is a useful model. It has become the basis for similar work by other development partners and is laying the foundation for a national irrigation roll-out and further agricultural intensification in Rwanda and elsewhere.Â· Approaches that enhance farmersâ€™ business skills, promote value chains, and link farmers to financial institutions provide sustainable benefits. It is vital to strengthen farmersâ€™ business skills and knowledge through relevant and practical approaches, such as participatory and market-responsive value chain approaches, farmer-based extension, and training for large numbers of lead farmers. Additionally, linking farmer groups and cooperatives to savings and financial institutions, can ensure the sustainability of project investments. Â· A programmatic approach to a financing mechanism enabling several phases is advantageous for consolidating, scaling up, and sustaining project benefits while ensuring clear criteria, direction and initiatives for new interventions. This is important for long term rural sector investments and reforms. Â· Water User Associations should be established and strengthened at the start of irrigation works. This approach instills ownership and understanding of the irrigation schemes, of how they function and of the roles and responsibilities of all water users. The approach also reinforces the need to operate and maintain the infrastructure (a public good) properly and to separate that responsibility from the cooperative, which essentially engages in private productive and entrepreneurial activities.
P105229 | Mainstreaming Climate Change Adaptation in Irrigated Agriculture Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | GEF | IPF | 2008 | 2012 | 2015 | PPAR | Less than 10 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/174251468188651098/text/97052-PPAR-P152174-P152176-P152177-P084742-P105229-P075035-Box391501B-OUO-9-SecM2015-0216.txt | http://documents.worldbank.org/curated/en/174251468188651098/pdf/97052-PPAR-P152174-P152176-P152177-P084742-P105229-P075035-Box391501B-OUO-9-SecM2015-0216.pdf | 4. Lessons on Three Themes 4.1 This chapter reviews three cross-cutting aspects of the projects\. (i) promoting sustainable management of water and agriculture; (ii) climate change adaptation, and (iii) learning through lending. It discusses what worked well, what could have been improved, and lessons for the future. It concludes with a summary of lessons. PROMOTING SUSTAINABLE MANAGEMENT OF WATER AND AGRICULTURE Challenges 4.2 China faces tremendous challenges in sustainably managing water and agriculture. Precipitation in the north is decreasing and will probably become more variable, so water supply is declining. At the same time, there is increasing demand for food â€“ and therefore for water, since agriculture is the main user. Many rivers are running dry to the sea and groundwater is being unsustainably drawn down. Overuse of fertilizer and pesticides poses downstream environmental hazards, including eutrophication and red tides and Industrial and domestic pollution exacerbate these problems. 4.3 This situation raises the difficult institutional challenge of managing finite water resources within a river basin â€“ a problem which requires understanding and dealing with trade-offs among water uses and users. There were three severe obstacles to solving this problem. First, river basin boundaries do not coincide with the established provincial and county level governments. Moreover, efforts to establish river basin commissions in most of the other major river basins in China had run up against the classic difficulty of limited recognition of the commission as an authoritative body.45 Second the environmental and 45 For instance, comments such as this\. Although China has established basin commissions for major rivers and lakes to promote integrated basin management, these water authorities had overlapping and inconsistent mandates, and yet did not coordinate with one another. Third, there was a lack of integrated knowledge of water use and water quality, and a lack of understanding on how different scenarios would affect water flows and economic conditions Interventions 4.4 To confront these challenges, the three projects introduced a set of complementary innovations. IAIL3 fixed dilapidated irrigation canals, introduced productivity-enhancing and water-saving agricultural practices, and supported farmer organizations to better manage water and to boost profitability. It also supported integrated pest management and reduced fertilizer application. MCCA reinforced IAIL3 by emphasizing activities that not only saved water, but were more resilient to temperature changes and extreme events such as drought and floods to changes in precipitation timing. 4.5 In contrast to the farm and community-level interventions of IAIL3/MCCA, the Hai Basin IWEMP addressed the institutional coordination issues at the county, province, and basin level. The project's contribution was in finding a pragmatic way to operate effectively within the government structure and to bring the key agencies involved with water together to work jointly on comprehensive water management. It also introduced technical tools for planning and for monitoring actual consumptive water use. What worked well 4.6 The IAIL3 interventions succeeded in boosting physical yield, water productivity, crop value/kg, and irrigation efficiency, with the result that farmer incomes increased substantially without significantly boosting total water demand. There was success in implementing purely technical improvements, such as irrigation repair and land-leveling, as well as changes in farm practice and community organization, such as WUA management of water (via rationing or fees) and farmer association/cooperative efforts to commercialized agriculture. MCCA smoothly integrated a number of climate change adaptation practices, including greater resilience to floods and droughts. 4.7 At the institutional level, HBP succeeded in introducing meaningful, technically rigorous and integrated planning, informed by consultation. These were not mere paper plans, but documents that informed policy and implementation. A key element of this success was the initiation of cooperation and data-sharing between environmental and water authorities. The Hai Basin Commission's capacity was improved with respect to modeling and data collection and management. basin commissions have limited power to allocate water resource, coordinate water resource exploitation and conservation, and enforce water resource planning at the basin level. (Yong Jiang, April 2009. China's Water Scarcity. In Journal of Environmental Management). 76 4.8 Together the projects succeeded in introducing a new paradigm for thinking about water management. It focuses managers' attention on actual, rather than apparent water consumption, and on the need to restrict total consumption to sustainable levels. This paradigm is an essential tool for water-scarce regions such as the 3H Basin. Areas for further attention 4.9 To achieve sustainability of land and water use, it is necessary to combine the field-level interventions of IAIL3/MCCA with the watershed level interventions of HBP. Most of the water savings from irrigation efficiency under IAIL3 were used to support increased output, so that absolute water savings may have been small. On the other hand, the IWEMPs developed under the HBP were often predicated on the kinds of actions undertaken by IAIL3, so further coordination is desirable. 4.10 At the watershed level, there remain obstacles to cooperation among administrative units and between ministries. While data-sharing between MEP and MWR has been institutionalized within pilot counties, it does not always occur smoothly elsewhere. ET data is not always transmitted to counties. Downstream counties and provinces may not have easy access to data from upstream neighbors. It may be useful to explore ways of boosting incentives for wider data sharing at the Hai Basin Commission, MEP and MWR. 4.11 The technical success in timely and accurate measurements of ET is noteworthy. Operational application of these measurements is less evident. Partly this is due to the complexity of the task. In many ways the application of ET measurement in the ongoing Xinjiang Turpan project is easier because of the simpler hydrology. In Turpan, there is essentially no precipitation, with water coming from runoff from distant mountains, and fields are larger and thus more easily monitorable. In the Hai Basin, in contrast, it is much more difficult to separate the signal of ET management from the noise of changing weather conditions. In these conditions it may not be realistic to aim for operational use of ET for monitoring water use at the WUA or plot level. 4.12 ET measurement could play a critical role however at larger scales. One of the important lessons of this evaluation is that, if reasonable shadow prices are applied to water savings, the benefit/cost ratio of successfully executed water conservation projects could be astronomical. Existing monitoring techniques are not adequate to provide comprehensive, reliable measures of net water savings. Better ET measurement, combined with ground-based data, could solve this problem. 4.13 The challenges are compounded when data are not freely shared. The joint World Bank-Government of China report, China 2030, emphasizes the value of public disclosure of environmental information. Wider distribution of ET and other monitoring data would be consistent with the 'bottom-up' planning orientation of the HBP and would complement the strong technical capabilities of Chinese academics and researchers. Further research could help to resolve the inconsistencies between reportedly strong reductions in groundwater exploitation (or rises in groundwater level) with weak reductions in ET or water use. CLIMATE CHANGE ADAPTATION Challenges 4.14 Climate change adaptation presents challenges. First is promoting awareness of climate change and motivating action. Second is determining what actions, in fact, are indicated. While the broad direction of climate change is clear, the precise evolution of climate at any locality is subject to uncertainty. The third is mainstreaming. If adaptive actions are already beneficial or 'win-win', why are they not already part of practice? If they promote long-term resilience but are currently costly, why should farmers adopt them? Awareness 4.15 China had gone through a conceptual journey before espousing a climate change adaptation program. Until the 2000's, interest in climate change adaptation was primarily in China's research community rather than in the political domain. At the time of approval of IAIL3 in October 2005, Government's climate change concerns were not prominent. 4.16 Interest in climate change adaptation gradually increased in the early to mid- 2000s, with several policy papers likely to have helped stimulate this. Interest mounted as a series of poor harvests drew attention to the need to mitigate the effects of climatic extremes\. droughts, floods, and high temperatures. In 2007, Government issued a National Plan for Coping with Climate Change, which included an emphasis on developing capability in measuring and dealing with climate change, with increased scientific research to support this. By mid-term Review of IAIL3 (September 2008) the adjustment to include a targeted climate change adaptation agenda through the addition of MCCA (approved in September 2008), was made. The Chinese Academy of Agricultural Science, and World Bank sponsored specialists, were brought in to help conceptualize and design a climate change adaptation agenda. This was important to MCCA's subsequent success as the project was the first comprehensive agricultural climate change adaptation project in China, requiring a high level of expertise in its formulation. 4.17 A particular effort, however, had to be put in to familiarize civil society, the extension staff themselves, and farmers with the concept of climate change and the adaptations feasible to counter such changes. And even before that, Government decision makers and senior and middle-level extension staff from the various agencies involved with the project needed themselves to understand and embrace the climate change agenda.46 47 Planning 46 For instance, as commented in the MCCA PAD (page 34) The need for climate change adaptation has been widely recognized only recently. 47 As advised to IEG, climate change adaptation had not received much policy attention before the early 2000s, and it was not surprising, therefore, that IAIL3 did not contain a specific climate change focus at its conception. 4.18 The project supported sophisticated climate modeling efforts. These were important for boosting Chinese capacity to model and understand climate processes. However, these efforts tended to yield only generic implications for specific, localized agronomic interventions. This experience is common to such exercises48 and reflects fundamental scientific uncertainties. First, there is no consensus on the degree to which higher CO2 levels in the atmosphere will fertilize plant growth, counteracting negative impacts from temperature rise. Chinese grain yields could go up or down, depending on the strength of this effect. Second, while climate models yield confident projections of temperature change, they are much less consistent on precipitation trends for smaller geographic areas, and on quantifying flood and drought trends. Third, it is very plausible that pests will increase with temperature, but it is difficult to project their impact. 4.19 For this reason, scientists and policy analysts are increasingly skeptical of a 'predict and prescribe' approach to adaptation (Schindler and Hilborn 2015).49 Given the uncertainties, they advocate designing policies that are robust to a wide range of possible futures. This would apply also to further on-the-ground adaptation activities under the National Comprehensive Agriculture Development Program. Mainstreaming 4.20 MCCA mostly supported interventions that already made sense under current conditions of climate vulnerability, and would be resilient to further changes. These include, for instance, the development and diffusion of drought and flood resistant seeds, and techniques for water conservation. Some â€“ for instance, tree shelter belts were already being practiced under IAIL3 but were expanded. Many of the climate change technologies were familiar, in practice or in concept, to agriculture and irrigation extension staff. Technical feasibility was, thus, not a major constraint. Nor, after initial concern as to whether it would work, were farmers' incentives. Nearly all IAIL3/MCCA's climate change adaptation measures increased farm yields as well as reduced climatic risks, and farmers, once they understood the climate change agenda, and witnessed demonstrations, adopted most of the practices enthusiastically. LEARNING\. KNOWLEDGE CREATION AND DISSEMINATION 4.21 Both IAIL3/MCCA and the Hai Basin Project brought in substantial innovation, as described earlier in this chapter. In both projects, policy makers, implementers and householders had much to learn in order to implement the projects. In turn, these participants would potentially become resources for possible replication of project approaches, although the degree of such outreach varied. Accomplishments 4.22 In terms of knowledge creation, HBP was exemplary in boosting the global stateof-the-art in remote sensing of evapotranspiration and the national state-of-the-art in 48 See IEG's Climate Adaptation Evaluation (2012) for a review. 49 Schindler, Daniel E., and Ray Hilborn. Prediction, precaution, and policy under global change. Science 347, no. 6225 (2015)\. 953-954. 79 integrated economic-hydrological modeling of water resources. As noted above, MCCA supported advances in climate modeling and in development of climate-resilient agricultural technologies. 4.23 Under both IAIL3/MCCA and HBP, the training programs and related activities such as demonstrations and study tours were large. IAIL3/MCCA undertook 37,000 person months of training for extension staff, 74,000 months for farmers, 158 demonstration sites, 145 international and 3,600 domestic study tours, and 330 extension or public outreach publications. HBP included 9 international and 155 domestic training sessions, and 43 domestic and 14 international study tours. For both projects, Joint Expert Groups were also formed at all institutional levels, to provide higher level advice. 4.24 Particularly for the MCCA climate change adaptation program and, though probably to a lesser extent, HBP, public outreach is reported to have been a major effort. Public outreach was part of the mainstreaming climate change adaptation objective of MCCA, and appears to have been significant â€“ some 330 outreach media (booklets, webpages, newspapers, and TV presentations) were undertaken under the MCCA, and, while no numbers are available, HBP staff advised IEG that they had also had a significant outreach effort. 4.25 Dissemination of project results grew in the last years of the projects as project impacts began to be apparent, attracting increasing interest. The projects responded in various ways including distribution of brochures, some workshops at local and national levels, farmer events, and organizing field visits for Government officials. Study visits from other provinces have also been facilitated. SOCAD has also advised that informal visits of technicians from neighboring counties was another form of dissemination. Presentations at conferences, and international exchanges, provided a forum for international contact. 4.26 One of the most noteworthy aspects of the projects is the way in which Bank staff and local experts have supported the diffusion of ET as a concept and as a monitoring technology. There are follow-on Bank projects in China and the Middle East. Study tours from Morocco and from Latin America have further disseminated the approach. What worked â€“ the role of innovators 4.27 World Bank Task Team Leaders and other Bank specialist staff were key catalysts of innovation during project preparation and implementation, according to government staff. They were critical to the introduction of the new paradigm of focusing on ET. There were three commonly shared qualities of these TTLs. First, all had extensive experience in Bank operations and were able to take on a Bank team leadership role. Second, they had expertise in innovations related to the projects, in particular for the HBP which introduced several state-of-the-art technologies. Third, they combined expertise with a passionate championship of new ideas. During preparation, HBP involved multiple missions by an experienced and relevantly specialized Task Team Leader, and was then supervised by a locally based Task Team leader, also highly experienced and qualified. The first TTL continued to be involved with the project as a technical specialist during project implementation. IAIL3/MCCA was both appraised and supervised, with hands-on involvement, from a Task Team Leader with extensive field experience who brought in consultants to bring particular expertise for specific needs. 4.28 There is substantial consistency between these observations and the findings of a survey about the Bank undertaken in 2011-2012 in preparation for the 2013-2016 Country Partnership Strategy.50 The CPS comments that Respondents indicated that the Bank's greatest value to China was in bringing new concepts and innovation, transferring international best practices, and piloting innovations to be scaled up. and\. The Bank must offer innovative knowledge products. 4.29 The second group of innovators were academics and consultants. They were engaged in research and training and were a significant factor in the projects' performance. They ranged in expertise from the National Academy of Sciences and China's top universities and specialist international consultants advising on new technologies, to more junior consultants to extend staff capacities in specific implementation areas. 4.30 In IAIL3, academics were used extensively by the counties, provinces, and at the center. The academics' roles were diverse ranging from advice or actual implementation of the new activities that the projects were taking on; to training; and even to staff type roles to provide extra persons in standard project implementation. Academics hired by counties were mostly from local universities or research institutes.51 At province level, local institutions were also used but higher level specialists, such as from China's elite Chinese Academy of Agricultural Science, were also engaged. International consultants were also hired in some specialized areas, although hiring of academics and consultants at this level was more often at central level â€“ SOCAD itself. 4.31 Whether at county, province or central levels, persons interviewed by the IEG mission were unanimously positive on the value that the academics and consultants had brought to the operations. Hiring experts had greatly enhanced the ability to take on new technologies; they helped a lot; and they were needed ... to show us how to do the new activities, were typical remarks. 4.32 Part of the reason why the three projects had largely successful experiences with academics was that a common practice was to integrate them within the work programs and staffing. Many became, in effect, staff, visiting frequently, and had ready access to data and the field. Thus, trust and teamwork made the consultants skills' more effective. 50 Survey of Ministries, local governments, local project management officers, academics, the media, and NGOs. 51 For instance, in Sihhong and Huaiyuan counties in Anhui, the IAIL3 project team had hired professors from the County Agricultural Institute and Anhui Agricultural University, and had also been visited by a more specialized consultant hired by Anhui Province. The generally positive views from the counties on training and academia also show in decision making since the project. Thus, the level of training in both counties has increased since project closure, and government funding of the training budgets has also continued. 4.33 Notwithstanding the mostly positive appreciation of the help that had been provided by the academic community, there were some weaknesses in how well the highest-level academics and international consultants were able to relate to local conditions. A complaint to IEG was that some of these needed better familiarization with local agricultural conditions and governance practices. Advice was sometimes generic â€“ one size fits all â€“ and insufficiently adapted to China's quite variable socio-agricultural conditions. Similar comments were made about some consultants and academics hired directly by the Bank. 4.34 Nevertheless, the overall benefit from the academics has been high, and, based on IEG's observations, it is likely that, without the academics, the projects would have been significantly less successful in the rapid transformation of the technologies that they all promoted. 4.35 Innovation was facilitated by a receptive culture. In the course of the projects, national participants showed an appreciation of potential new technologies, and the capacity and propensity to rapidly disseminate and implement such knowledge if seen to be successful. Perseverance is also evident. Project preparation of the HBP, for example, was a detailed and lengthy process in unknown terrain for activities such as ET, the institutional structure, and the knowledge management system. The IEG mission was informed that there was some frustration with the length of the process, but the Chinese preparation team and policy makers persevered, with no indication that the innovations would succeed. Government was also prepared to rapidly mainstream the projects' approaches, as evidenced by the integration of the IAIL3/MCCA into the national Comprehensive Agricultural Development program, and use of the HBP as a model for successor water resources management projects. 4.36 However, resistance to change was present in some quarters. For instance, HBP's holistic water resources management approach was initially resisted by the engineering community, who were used to construction of irrigation infrastructure, and considerable effort was needed to change this mind-set. Indeed, according to some involved senior staff from the Ministries of Water and Environmental Management, achieving the change in culture was possibly the project's most difficult achievement. Areas for further attention 4.37 IAIL3 missed an opportunity to contribute to better learning about how to improve land and water productivity. The project introduced a diverse range of approaches and technologies in engineering, agronomy and management. It would be desirable to understand which worked best under which conditions. This is especially true for actions with water conservation benefits, given the potential size of those benefits. While the project did gather voluminous data and produce reports at province and county levels, rigorous impact evaluation was not undertaken. The cost of doing so would have been relatively small, and this could have provided guidance that would increase the effectiveness of efforts to replicate and scale-up IAIL3. 4.38 The Bank has been more of a transmitter of knowledge than itself a significant learner. As noted above, involved staff have played a proactive role in disseminating the concept of ET-based water management, including through follow-on Bank projects. However, this has been driven largely by the individuals involved, rather than being institutionalized in strategy or approach to water-scarce regions. 5. Summary of main observations and lessons 5.1 Concluding this report, following are some lessons and observations which may be of general relevance in China and beyond\. Â· The concept of evapotranspiration management can underpin sustainable water management. Three simple but powerful ideas that water is only used up by evapotranspiration, that allowable evapotranspiration has to be capped at a sustainable level, and that the goal is to minimize non-beneficial evapotranspiration can transform the way water is managed. Â· Water-saving agricultural projects could in principle provide immense economic benefits. In water-scarce regions such as north China, there is a substantial economic value to water savings. Savings on the scale envisioned by the projects, if evaluated at conservation shadow prices, would imply extraordinary economic returns to investment. In these projects, unfortunately, data are not adequate to verify whether there was net water saving. Â· It is possible to simultaneously boost water productivity and land productivity. Usually, more productivity requires more water. Here, intensive agricultural extension, community management of irrigation, environmental improvements, and promotion of higher value crops and commercialization managed to conserve water while boosting crop quantity and quality. This was done in significant part by reducing non beneficial evapotranspiration. Â· Multi-agency, technically based, integrated water management is possible. Under the HBP, environment and water authorities worked together, in consultation with stakeholders to develop plans. The plans were informed by hydrological models that helped prioritize ways to meet water quality and quantity goals. They were incorporated in operational county investment plans. Â· Field-level and basin level approaches are complementary. Holistic management at the basin level depended on the ability to deploy field level techniques for increasing water efficiency. But promoting irrigation efficiency can lead to continued groundwater depletion unless total consumption is capped. Â· Sharing of data is a key to success. Progress was made when the Environment and Water ministries pooled information from their formerly separate monitoring stations and worked together to solve problems, and when Basin authorities shared information with counties. Coordination was hindered when counties found it hard to share information with upstream or downstream neighbors, and when information flows from the center diminished. Globally, there is a growing realization among public agencies that by making data open â€“ freely accessible, machine readable, and unrestricted in use â€“ both public and private sectors are able to make better and more informed decisions. Â· Climate adaptation interventions are easily assimilated when they bring immediate benefits under current climate conditions and variability. Measures introduced were resilient to future conditions, but already made good farming sense given current risks. Substantial outreach to farmers and policymakers helped with adoption, as did incorporation of the innovations in a larger project. Â· Climate modeling is best used to test adaptation policies for robustness against different scenarios, rather than to predict 'what will be'. There are limits to the ability of climate models to predict future cropping conditions, because of fundamental uncertainties about the effect of-more carbon dioxide on crop growth, and inability of the models to accurately predict precipitation. Â· The Bank can be a driving force for technology transfer. Innovations in integrated water management, and the ET paradigm, were introduced by a Bank TTL who combined state of the art, agriculture with irrigation expertise with persuasive leadership, supported by international and local experts, and by dynamic successor TTLs.
P105255 | Poverty Reduction Support Operations 4 | Europe and Central Asia | Georgia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2009 | 2011 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/262521474897841677/text/000020051-20140620075944.txt | http://documents.worldbank.org/curated/en/262521474897841677/pdf/000020051-20140620075944.pdf | IEG broadly concurs with the lessons outlined in the ICR. In particular, the lessons about the importance of strong Government ownership of the reform program, good donor coordination, and the focus by the government on results are unexceptionable. Using the flexibility available under the programmatic lending to adapt the programs to the actual implementation experience is also sound advice for the Bank TTLs.
P105256 | Agricultural Development Programme Support Project SIL (FY08) | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2008 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/439491517267879328/text/Malawi-MW-Agric-Dev-Prog-Support-Project.txt | http://documents.worldbank.org/curated/en/439491517267879328/pdf/Malawi-MW-Agric-Dev-Prog-Support-Project.pdf | The ICR included five lessons. The following are emphasized with some adaptation of language: Complexprojects in countries with limitedimplementation capacity need a dedicated project implementation unit (PIU) with qualifiedstaff to ensure timely implementation of project activities. Theuse of Government systems andstructures promoted ownership, but limited capacityand Government bureaucracies resulted in implementationdelays.The complexity ofa project warrants the establishment of adedicated PIU with key qualified staff. Further,for projects thatfeature national coverage, the regional offices need to be considered for proper project backstopping,including on fiduciary matters. Basket funding modalities (like MDTF) promoted coherence among donors inadvancing reforms, policy positions, as well as flexibility and fast decision making. The setup of the multidonor trust fund ensured that all donors mutually agreed to reforms and policy positions advanced with Government unlike in thepast when there was discrete fragmented implementation. In turn, this reduces transaction costs towards decision making, andincreases ownership and accountabilityof decisions.
P105256 | Agricultural Development Programme Support Project SIL (FY08) | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2008 | 2017 | 2021 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/515771612377662563/text/Malawi-Irrigation-Rural-Livelihoods-and-Agricultural-Development-Project-and-Agricultural-Development-Program-Support-Project.txt | http://documents.worldbank.org/curated/en/515771612377662563/pdf/Malawi-Irrigation-Rural-Livelihoods-and-Agricultural-Development-Project-and-Agricultural-Development-Program-Support-Project.pdf | 3. Lessons 3.1 An integrated and participatory approach to agricultural development can initiate sustainable growth in productivity among SHFs. In the context of a SHFdominated agricultural sector and low productivity, traditional support measures of input supply are needed to close agronomic yield gaps. However, the adoption of such support measures will not be profitable for SHFs unless complementary training and agricultural extension on proper input and land management are provided. The projects, therefore, promoted the synergistic benefits of the simultaneous adoption of hardware (mainly agricultural inputs and irrigation) with software (mainly agronomic knowledge and capacity building). Many irrigation management and extension activities were demand-driven and bottom-up. This approach, therefore, contributed to local capacity, ownership, and community involvement. 3.2 Agricultural projects with a supply-side focus on productivity growth that ignore market linkages are unlikely to provide the right agribusiness mind-set or incentives for farmers to sustainably invest in longer-term agricultural productivity. The projects' integrated approach boosted staple-crop productivity, but continuous increases in agricultural productivity require a change in mind-set toward farming as a business. Without being introduced to or trained to acquire an agribusiness mind-set, it can be difficult for SHFs to think beyond the semisubsistence of food production. To achieve sustainable productivity increases, the right economic incentives must be put in place by explicitly considering the demand side of agricultural production. Higher-value markets offer higher prices (even in rural areas), but if beneficiaries are not integrated into these markets beyond establishing physical access, SHFs have few economic incentives to intensify agricultural production once the projects have ended. Without access to highervalue markets, many of the productivity gains achieved by supply-side efforts will not generate the returns on investments necessary to sustain the profitable intensification of agricultural production. 3.3 Intensive and demand-driven approaches to service delivery in agriculture are innovative but are unlikely to be maintained or expanded when support systems for agricultural sector development lack the capacity and resources to continue providing them. In this case, the IRLADP introduced WUAs to support the capacity building and institutionalization of irrigation management. Both projects provided extension services and organized activities in participation with local communities. Because demanddriven support is intensive and requires continuous follow-up, it is likely to fail when a government's service providers lack the capacity and resources to provide agricultural services to SHFs. 3.4 Introducing sustainable land and water management practices requires a more comprehensive focus beyond irrigation or demonstration plots. As discussed in chapter 2, paragraph 1.28, hotspot prioritization, selective site rehabilitation, and conservation agriculture can result in pockets of success, but a full return to the adoption of small-scale approaches depends on what happens in upstream or surrounding parts of the agricultural landscape. Hence, a more comprehensive catchment or landscape approach to irrigation development is needed to achieve higher-level sustainability. The projects could have considered institutional solutions related to how to transfer uninsured risks in agriculture out of the sector, such as through weather-based insurance mechanisms. As long as agricultural production is highly susceptible to climate shocks and the underlying causes of risks and vulnerability are not addressed, supply-side productivity increases are not likely to be sustained over time. 3.5 There is evidence that the World Bank has learned from these experiences. Two current agricultural projects in Malawi (the Malawi Agricultural Commercialization Project and the Lower Shire Valley Landscape Project) promote agricultural commercialization and adopt a landscape approach in the development of large-scale irrigation schemes. A project preparing an Agriculture Sector-Wide Approach that will assess its effectiveness based only on production outcomes lacks the granularity to understand which project activities are driving observed changes. Moreover, the use of production estimates at the national level without a proper counterfactual does not allow for the attribution of changes to the project. By design, projects that prepare the implementation of an Agriculture Sector-Wide Approach implement a variety of activities at different levels of support. The ADPSP, however, tracked only national production estimates and some service delivery outputs. Even if the ADPSP had been successful in achieving sustainable increases in productivity, the results framework and M&E system would not allow an explanation of the increases. As a consequence, the project missed the opportunity to learn from design issues and revisit the effectiveness of various project activities.
P105269 | Judicial Performance Improvement | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2013 | 2022 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099630011102234549/text/P1052690b2d5ac0d408c56046ec1cc9ccf0.txt | http://documents.worldbank.org/curated/en/099630011102234549/pdf/P1052690b2d5ac0d408c56046ec1cc9ccf0.pdf | IEG concurs with the lessons set out in the ICR. The project offers some lessons specific to Kenya and others that may beapplicable more generally. Below, the most pertinent lessons are extracted:The Value in Leveraging Partnershipswith World Bank Units. The project team sought assistance from DIME in the design of data systems, especially for the datacollection system, which helped the Judiciary in transforming its data collection mechanisms for performance contracts, budgeting,training, and infrastructure.The broader justice community plays a crucial role in the local reformprocess. The rich experiences from the justice community, as well as other task teams in other judiciary projects, canhelp inform a projects implementation, including providing guidance on best-fit options that a project can pursue to addressemerging challenges.Institutionalizing change management champions within the judiciary can help drive the reformprocess forward. Change management champions are essential to ensure that reform activities continue being implemented,despite changes in the leadership body of the judiciary. For example, key reforms implemented as part of this project suchas the development of a governance and anti-corruption strategy, and conducting an organization review assessment and acourt-annexed mediation pilot continued despite changes in the judiciarys leadership body.IEG adds thefollowing:The quality of judicial performance cannot be determined solely by numbers of cases resolved.Numerical case resolution targets must be coupled with other qualitative factors to determine judicial performanceand avoid potential adverse effects associated with the application of numerical case resolution targets alone (such as judgmentsbeing processed too quickly, or summarily being dismissed). In this context, quality surveys are essential, and establishing acontinuous process for court user surveys and reporting on court performance is essential to ensure that quality standards aremaintained. Court reports on performance ought to be conducted on a regular basis (for example, on an annual basis) to enablecross-comparisons on a year-to-year basis. In the interests of transparency and improving public trust and confidence in courts,the reports should be made available publicly.In the justice sector, outcome indicators chosen ought to measureimproved quality in usage of courts. While reducing the distance to courthouses is essential, outcome indicators ideallyshould also capture how extensively courthouses are used, where and by which intended project beneficiaries. Rigorousmonitoring and evaluation systems are required to determine improvements in usage, and thus correct continuing deficits.
P105279 | Senegal Energy Sector Recovery Development Policy Financing | Western and Central Africa | Senegal | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | DPF | 2008 | 2011 | 2013 | ICRR | >=50 million & <100 million | Unsatisfactory |  |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/326941475082176267/text/000020051-20140625060706.txt | http://documents.worldbank.org/curated/en/326941475082176267/pdf/000020051-20140625060706.pdf | The following lessons were derived (with adaptation) from the ICR:Rapidly changing circumstances of the sector require an intensive and continuous dialogue with the Government, and close coordination with donors and partners, which could be greatly facilitated by the follow-up of a Bank team based in the country office. Lending instruments need to be chosen and designed wisely. While a DPO can be a useful instrument for pursuing reforms, having just two tranches, a large number of conditions, and a short implementation period, can lead to inflexibility and non-compliance with agreed actions. This can be exacerbated by the back-loading of conditions, with the most difficult ones reserved for the second tranche. A series of DPLs with limited objectives and financing may bring more flexibility and may be more suited to country and sector circumstances than a single complex operation.Some key conditions that are formulated as specific quantitative targets could create an excessive focus on monitoring of financial indicators rather than on the underlying causes for poor financial performance. There may be scope for focusing more on the underlying causes and designing simple and feasible solutions to address them.Supporting investments could precede and may have a facilitating role for the eventual reform program, which could be more modest and focused on the achievement of selected pre-conditions. For instance, an investment operation could help diversify the energy mix to decrease generation costs, which in turn would contribute to achieving the programâ€™s financial sustainability objectives.In light of country and sector circumstances, realism in the pace of reform and the management of expectations are essential, given the frequent pressures to do many things as fast as possible.
P105279 | Senegal Energy Sector Recovery Development Policy Financing | Western and Central Africa | Senegal | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | DPF | 2008 | 2011 | 2014 | PPAR | >=50 million & <100 million | Unsatisfactory |  |  | Unsatisfactory |  | http://documents.worldbank.org/curated/en/263261468334914418/text/812430PPAR0Sen00PUBLIC00Box379839B0.txt | http://documents.worldbank.org/curated/en/263261468334914418/pdf/812430PPAR0Sen00PUBLIC00Box379839B0.pdf | 5. Lessons Learned 5.1 The following lessons can be derived from the Bank's experience in the power sector of Senegal. 5.2 Proper sequencing of sector policy dialogue and investment support is important for success when the two are closely connected. The viability and sustainability of the investment commitments for SENELEC strongly depended on the sector policy and strategy as well as the financial restructuring of the utility. The absence of a sound policy framework was a factor in the failure of the Electricity Sector Efficiency Enhancement project. When the Bank finally addressed key policy issues under a heavily front-loaded DPC in 2008, it was too accommodating and complacent in its implementation follow up. The most recent Sector Investment Loan, approved in 2012, is similarly light on institutional and policy content while the energy policy content of the recently-approved Governance and Growth DPC appears to neglect certain urgently needed reforms, including on the tariff front. 5.3 The Bank has an important role in ensuring that investment decisions are made based on technical, financial, and economic merits. This is particularly true for generation investments in a country like Senegal, which has limited options given its small system size and the absence of sizeable domestic energy resources. The Bank risks credibility if it takes, or is perceived to take, a dogmatic position against coal-based power where it is the least-cost option (after accounting for environmental externalities), at least in the medium-term, and a potentially critical way to significantly reduce generation costs and turn around sector finances. 5.4 Realistic policy requirements and consistent messages are important to borrowers. Over the past decade, the Bank's stance has fluctuated between a sometimes overly demanding agenda (like in the letter of the 2008 Energy DPC) and an excessively accommodating position when it came to the government delivering on its key commitments (such as on tariffs), all in the context of unwavering and growing financial support. As a consequence, it may have been seen by counterparts as sending mixed messages on the importance and urgency of actual sector reform. 5.5 Where a country's political timetable is liable to bring significant shifts in policy, a keen appreciation of political economy is necessary. Twice, the Bank did not sufficiently appreciate the likely implications of scheduled (democratic) changes in government, first in 2000 and more recently in 2012. In the first instance, the new government hardened its position on SENELEC's privatization, possibly contributing to its failure; and in the second instance, the new government appears to have taken a different approach to investment planning and tariff policy, revisiting key tenets of the Takkal Plan. 5.6 The Bank has much to gain from locating key operational staff in the field, particularly where a continuous and intense dialogue is required, such as Senegal's energy sector. But field location will only yield benefits if human and budget resources are made available; otherwise the teams will become overloaded and key areas requiring specialized expertise (like the hydrocarbon subsector in Senegal) will end up unattended. 5.7 In addition, several lessons specific to the two projects assessed in this report arise. 5.8 Project implementation requires suitable institutional arrangements. In the first project, the institutional arrangements and the location of the PIU were not designed in accordance with the roles and responsibilities of the respective entities\. MEM should have played the role of coordinating entity (except for the few activities directly pertaining to it) and not that of an implementing unit, when most of the project activities required the involvement of SENELEC for their execution. This lesson has been reflected in the design of the latest Sector Investment Loan to Senegal (the Electricity Sector Support project approved in 2012). 5.9 A comprehensive and realistic analysis of sector finances is the best foundation for financial covenants that will be met. The analysis should reflect realistic assumptions regarding the timing and scope of future reform steps regarding tariff changes, financial restructuring, as well as realistic scenarios for future increases in international oil prices, particularly for a system so dependent on liquid fuel imports like Senegal's. Because it was not done in the first project, the financial covenants were essentially meaningless and bound not to be complied with. 5.10 Project success is handicapped at the start if it is not ready for implementation by credit effectiveness. In the first project, the preparation of key components was not fully completed until much later in the project's life, leading to delays in bidding and serious implementation delays, and resulting in the ultimate cancellation of a large part of the credit. In fact, the Project Implementation Manual was not even finalized until more than a year after the project was started. Compounding the problem was the fact that procurement training of key SENELEC staff was insufficient, leading to procurement inefficiencies. 5.11 The outcome of IPP projects cannot be viewed in isolation of broader sector outcomes. While the generally satisfactory completion of the Kounoune project provided needed additional capacity to the system at least-cost and served as a demonstration of the feasibility and benefits of IPP arrangements in Senegal, its outcome is being jeopardized by the recurrent financial difficulties in the sector\. the technical problems that marred the plant in the first two years were partly caused by poor fuel quality, itself the result of SENELEC's strained cash situation. The latter also led to delays in energy payments to Kounoune. More broadly, the dire financial situation of the sector is a disincentive to private investors investing on a large scale in future IPP projects. 5.12 Inattention to the good practice principles for the application of conditionality can result in policy-based operations that are unbalanced and lack focus. In the second project, most of the substantive conditions were back-loaded to the second tranche whereas the first tranche accounted for 70 percent of the credit. Furthermore, the credit included an excessive number of conditions, some of which were vague and/or largely formalistic, whereas others were disconnected from the core objectives of the project. 5.13 In designing policy-based operations, a realistic sense of the pace of reform will take account of political economy considerations. The DPC was clearly too ambitious regarding the expected timeline for key reform steps, including the enactment of needed tariff increases and the elimination of budgetary transfers to the sector. It attempted to achieve too many things at the same time instead of focusing on key actions required to address the core roots of the sector crisis â€“ and following up on their actual implementation.
P105282 | Liberia Health Systems Reconstruction | Western and Central Africa | Liberia | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2007 | 2012 | 2013 | ICRR | Less than 10 million | Moderately Satisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/400401474564126059/text/000020051-20140625190519.txt | http://documents.worldbank.org/curated/en/400401474564126059/pdf/000020051-20140625190519.pdf | The following lessons from the ICR (page 25) are broadly applicable to other emergency projects. 1) Capacity-building in critical areas of project management should be front-loaded when the capacity of implementers is low. At the start of the project, front-loaded capacity building activities (in areas such as procurement, disbursement, financial management, and M&E) should be planned and budgeted, and implemented strategically, along with carefully planned follow-up activities.2) The results framework should include indicators that are directly linked to the project, within the purview of the implementing agency, and measurable. In this case, there were indicators affected by a range of factors outside the scope of the project. As a result, it is difficult to draw a results chain directly from the projectâ€™s activities to its outcomes and impact measured by the projectâ€™s formal indicators. 3) Innovations in design, particularly as they related to capacity constraints, should be encouraged in fragile, post-conflict countries. Successful project implementation in countries with high security problems and no experience with Bank operations is dependent on having strong technical assistance provided by experienced specialists. Innovative approaches to addressing this problem are needed.
P105287 | Vietnam Poverty Reduction Support Credit 7 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2008 | 2009 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/469551474895234248/text/000020051-20140626112326.txt | http://documents.worldbank.org/curated/en/469551474895234248/pdf/000020051-20140626112326.pdf | Lessons from the ICR are supported, in particular that donor coordination can strengthen the policy dialogue and deliver benefits to the client. A PRSC series can serve as an effective framework for policy dialogue and interactions between the government and donors. The benefits can be fundamental and manifold, as supported by a number of outside evaluations. PRSCs can be the â€œone-stop shopâ€ of the policy dialogue, supplemented by sector/thematic DPLs as reform dialogue deepens, and hence raised to a more senior level of government attention than any individual sector effort would have. The role of co-financiers under the PRSC can evolve over time from providers of financing to partners engaged in the preparation of the operations and the policy dialogue with the government. Information flows from the government will expand as trust with the Bank and other partners deepens. This coordination also greatly reduces the transaction costs for the government ministries and agencies (ICR, p. 34).Another lesson is that an incomplete causal chain can lead to difficulty in evaluating the effectiveness of an operation or series in achieving its objectives. When prior actions and targets are directly linked to target outcomes from a PRSC series, there will be a clearer link between the series and the achievement of objectives.Other lessons include the importance of continuity in task team leader (TTL) -- PRSCs 7-10 had the same TTL, and the value of combining policy operations with parallel technical assistance to allow for necessary capacity building. When a government has a sound medium term framework and the program supported by a policy operation is ambitious and broad, a longer series may offer the opportunity to achieve results sought and the flexibility to redirect actions based on experience. In addition, countries facing particularly difficult sectoral challenges should consider a sectoral policy operation to supplement a broader policy operation, allowing more extensive consideration and support to the most difficult issues.
P105287 | Vietnam Poverty Reduction Support Credit 7 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2008 | 2009 | 2015 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/721331467986245693/text/96203-PPAR-REVISED-PUBLIC-VIETNAM-PPAR-FINAL.txt | http://documents.worldbank.org/curated/en/721331467986245693/pdf/96203-PPAR-REVISED-PUBLIC-VIETNAM-PPAR-FINAL.pdf | 6. Conclusions and Lessons Learnt Conclusions 6.1 This review presented an overview of Vietnam's economic and social performance. It assessed the extent to which World Bank DPOs during 2007-12 contributed to its achievements and their sustainability. The main conclusion that emerges from the historical overview is that the country's growth performance during the 1990s and until the mid-2000s was very strong. Effective poverty alleviation also took place during that period, and has been sustained since. This was thanks to transformative measures (especially land reform, enterprise reform and WTO accession) that were taken by Government during the first half of the 2000s (in turn building on earlier reforms) with substantial development partner advice and support, which was generally led by the Bank. 6.2 However, during the period under review (2006-2013) the next generation of transformative reforms (notably as highlighted in the 2007 and 2009 VDRs) were either postponed or diluted, and were thus less effective. Areas such as SOE and financial sector reform, more efficient public investments, anti-corruption, and more effective environmental policies, received insufficient attention. Over the same period, Vietnam departed from the prudent macro-fiscal stance that characterized it in the 1990s early 2000s. 6.3 Past reforms continue to drive strong FDI and buoyant exports. Vietnam can build on these strengths to avoid further loss of growth momentum. This could be based on the implementation select transformative reforms aimed at strengthening the role of the private sector, facilitating the emergence of mediumto large domestic enterprises, and sustainably expanding infrastructure in an efficient manner. The progressive elimination of the stock of contingent liabilities and reducing other risks to the sustainability of fiscal policy would create a more stable macroeconomic environment. One of Vietnam's strengths lies in its social compact, the main elements of which should be maintained, while progressively evolving towards a less paternalistic approach based on stakeholder empowerment. 6.4 The Bank and other development partners can help the country address these priorities through more selective budget support instruments. This is indeed envisaged in the Country Partnership Strategy (2012-16). The 2016-2020 SEDP also provides an opportunity to generate political consensus around these issues in the context of an increasingly complex economy. 6.5 The Bank should be more willing to cease supporting programs should they become so weakened as to make it likely that key objectives would not be achieved. Technical and policy dialogue would be maintained. In this context, high caliber knowledge products will need to continue being prepared, and the relationship of trust that supports frank dialogue with Government needs to be reinforced. Harmonization with all key stakeholders, external and internal, will be important. Strong commitment to deeper reforms would help to sustain Vietnam's economic performance while addressing the challenges of an increasingly complex, middle-income economy, and deepening global integration. Lessons from the Bank's macroeconomic engagement through DPOs. 6.6 The model of the Bank's engagement in macroeconomic and fiscal policies through DPOs in Vietnam since 2007 has not been effective. An important finding emerging from this PPAR is that, while diagnosis of macroeconomic risks was adequate, this was not reflected in program design, despite a highly volatile environment exacerbated by sub-optimal policy choices. This situation was, moreover, aggravated by the lack of an IMF program and the relative weakness of macroeconomic policy dialogue between the Government and the Bretton Woods Institutions. The Bank may have been exposed to reputational risks if its policy lending had been seen as a de-facto endorsement of controversial macro policies. DPOs following those reviewed in this PPAR are still not underpinned by relevant macro policy content, although macroeconomic risks persist. This indicates that the lessons learned during the 2007-2013 period do not appear to have been fully learned. 6.7 Macroeconomic dialogue could advantageously be consolidated in a presence of multiple parallel DPOs. The fragmentation of policy lending into multiple DPOs implemented in parallel in Vietnam during the period of increased macro risks might have weakened Bank's focus on macro framework and even resulted in inconsistencies in policy dialogue. The Bank should have avoided situations when preparation of one operation is held back for concerns over the macro-framework while a parallel DPO is approved and disbursed in the same macro environment. To avoid the repetition of such a situation, there should be a unique and consistent approach towards assessing the adequacy of macroeconomic underpinning of DPOs. When substantial risks are present, policies underpinning the most suitable, in terms of scope and objectives, budget support operation should be reoriented to alleviate them. 6.8 Combining the objectives of external financing for crisis response and promotion of long-standing institutional reforms may not be effective in cases where risks to nonimplementation of reforms are high. The Bank's experience with the Vietnam PIR series indicates that, when financing needs are urgent, it will find itself under pressure to go ahead with disbursements even if the reform implementation is not satisfactory. Crisis response operations should first of all focus on ensuring the sustainability of macro and fiscal framework, and should be underpinned by critical macro, fiscal and structural actions, especially in cases when the IMF is not present operationally. Lessons Learnt â€“ Results and M&E Framework 6.9 Wide-ranging DPOs need to be based on stronger and better quality actions. The importance of each individual prior action increases in multi-sectoral operations with many policy areas because of the implicit limit on the number of total prior actions for operational purposes. If in a series of five operations, for example, each policy area can have a maximum of two or three prior actions in the course of five to six years it is important to ensure that those prior actions have sufficient institutional depth, relevance and criticality. Related to this, in multi-sectoral complex operations there might be no substitutability between the prior actions of unrelated policy areas, which means that weaknesses of prior actions in one sector cannot be offset by relevant and critical prior actions in another sector. 6.10 Lack of focus on and delays in implement essential triggers can weaken the program. In terms of indicative triggers, the Bank has flexibility and discretion in its treatment of the triggers. The transition from Bank's former conditionality framework to the model applied in the series reviewed in this PPAR puts a high premium on sequencing the reforms and ensuring continuity, thus giving considerable significance to the role of triggers for the operations and the overall reform program. Dropping a trigger should be considered as an exceptional event, rather than a regular occurrence, permissible only if the risks to nonimplementation of reforms are duly addressed. 6.11 Partially met triggers require greater attention. Sometimes partially met triggers become prior actions even though they may be less relevant and critical than the originally proposed action. The dilution of content may be to such an extent that these actions would probably not have been considered as prior actions if proposed at the outset. The Bank should pay special attention to possible risks in adopting partially met triggers as prior actions, especially when there is not any realistic expectation that the full original reform will not implemented in a reasonable timetable thereafter. 6.12 It is crucial to have a strong knowledge base for upstream design of reforms and parallel technical assistance to support their implementation. Development partners were willing to put significant resources in these areas, in order to complement Bank financing and dialogue (Vietnam, prefers not to borrow, even on concessional terms, for TA). Selectivity is therefore needed to ensure that the most pressing needs are addressed. Should unmet demand remain, this may be tackled through complementary Bank TA operations, for instance in support of reform teams.151 However, these operations need to be carefully designed in order to match the timing and sequencing needs of DPOs (an issue that arose in the case of P135), and to ensure that the bulk of resources is allocated to meet specific implementation requirements, as opposed to general capacity building (such as purchase of vehicles and equipment, and training). Furthermore, this approach calls for outsourcing knowledge generation and advice to an appropriate mix of experts, both national and international, who can accompany the reforms in medium-term.152 6.13 The design and implementation of M&E for DPOs remains a challenge, and needs to be reconsidered each time a new operation is considered within a series. The PD.153 for the second PIR mentions a lesson learnt elsewhere, whereby an effective M&E mechanism should not just be based on administrative reporting. However, both the PIR and the PRSC suffer from this issue as M&E is not used as a mechanism for feedback and readjustment of activities to improve impact. The P135 is more successful in this area 151 FIAS 2008\. Reform Teams How the Most Successful Reformers Organized Themselves Reform teams consist of a small group of national experts who together with world-class expertise help Governments implement ambitious reforms. 152 In order to achieve such continuity, the experts' contracts may be based on a retainer model. Sorter procurement may also be achieved through framework contracts, whereby a short-list of competitively prequalified consortia/firms expected activities are called upon to provide experts within short delays of 2-4 weeks. The EU has successfully implemented this approach. 153 para. 71 124 because the mid-term review provided a venue for reassessing the implementation of the program. Even there, the change in PRSC indicators took place only for the last operation, although it had become clear much earlier that the relaxation of policy actions required an adjustment in indicators and goals. In both the PRSC and the PIR series there is a disconnect between development objectives, actions and indicators. In the case of the PRSC, there was a logical chain between objectives and indicators, but it is hard to see how some of the reforms would lead to the intended results (the attribution issue). The issue with the PIR is that while there is strong relationship between the reforms and results, their logical link to the development objectives is weak, especially after key reforms were dropped. Lessons Learnt â€“ Bank Approach 6.14 There is a need to reexamine how the Bank approaches sectoral DPOs and how this instrument is differentiated from investment lending. In Vietnam, the distinction between DPOs and investment loans has become blurred, especially with the practice of earmarking funding for the sector the programs support. It can be argued that the four sectoral DPOs might have been best supported by SWAPs and investment lending. The advantage of DPOs is that they disburse rapidly, support to the consolidate budget, and in practice promotes the use of national fiduciary and safeguards systems. However, this approach limits Bank inputs (say on a key study) on the ultimate use of the resources and their underlying processes. To avoid sharp trade-offs that may discourage the use of the most appropriate lending instrument, it seems that in the case of investment lending, it may be desirable to experiment, at least on pilot basis, with further harmonization/convergence between Bank fiduciary and safeguard procedures and national ones. 6.15 The Bank and other development partners should be willing to walk away from an unproductive policy dialogue and withdraw their support of low impact reforms. The delays in P135 (second operation), the second PIR operation and PRSC 10 appear to have been caused by concerns with the quality of the program. In the case of P135, the mid-term review largely addressed the main concerns. However, the last operations in both PIR and PRSC series cannot be readily justified by the contribution to objectives of the weak reform they supported. 6.16 The Bank's recent guideline that suggest to limit the number of operations in a series to three constitutes an appropriate measure. Long-term DPO series need to be kept relevant by maintaining a high level of ambition with respect to the reforms they support. As evidenced by the second PRSC series, a longer-term approach may be hard to sustain. 6.17 Knowledge generated and/or embodied in Bank operations should be properly documented and made public. Bank disclosure policy call for documents it produces being made public, unless classified as confidential. Furthermore, to the extent possible, documents on which policies are based should be easily identifiable and retrieved. In order to preserve knowledge and improve transparency, PDs should properly refer to studies (in some cases the title cited was incorrect) and provide URL links. There is also a question whether disclosure policy is strictly respected (e.g., some energy studies do not appear to have been made public). 125 6.18 It is difficult to evaluate the performance of DPOs in Vietnam without the benefit of a clear reference on what constitutes the norm. This review identifies strengths and weaknesses in the Vietnam DPOs by referencing their own internal logic. However, it is unable to systematically address questions such as how did the Vietnam second PRSC series compared to other PRSCs in terms of ambition, design, results etc. This may result in inconsistency in ratings across countries and projects (ratings contain a subjective element based on the skills, experience and perception of the evaluation team, as well other factors). This issue seems to argue in favor of a new meta-evaluation154 of completed PPARs on similar DPOs, with lessons learnt and recommendations on a more consistent cross-country approach to be reflected in future individual operation evaluations and/or PPARs. Specific Lessons Learnt from P135 6.19 Budget support may not be the best instrument for financing a sector investment program. While a budgetary support operation for a CDD-type program turned out to be moderately satisfactory in the case of Vietnam, the Bank and other development partners had taken a considerable risk. For most countries, it would be highly advisable that the training, at least of the critical personnel (which in a highly decentralized program means a very large number of people), would be done in advance and that an M&E system were in place at the start of the program. There was much retro-fitting under the P135 series that could have been avoided. 6.20 The state of decentralization needs to be fully factored into the design and implementation of targeted poverty programs. Decentralization of government institutions and introducing greater participation at the commune and village levels was an objective of the program as a tool to empower the targeted communities. Various monitoring indicators were used to measure progress on this front. But they did not provide an idea of what would have been good practice in terms of an optimal level of decentralization and participation given the stage of development. An alternative approach could have been to select a control group of provinces that had been decentralizing on their own and could serve as a comparison group for the provinces attempting to develop decentralized structures under P135. That could have enabled the selection of a group of indicators to be used for measuring success before the start of the operation 6.21 Production support to poor communities needs to be tailor-made and well thought through. Much was made of expanding the production component of the program. But the targeted communities were seriously underdeveloped for good reasons. They were remote, mostly mountainous, often forested, and inhabited by people who have eked out livings in these places for centuries. Such places are notoriously difficult to develop and there are few success stories around the world to give guidance. Packages that had worked in other parts of Vietnam (typically used in the more hospitable lowlands) were not likely to be relevant, and subsidies are not sustainable in the long run. This portion of the program could have been better thought through and explored through a series of pilot projects rather than being a part of a budget support operation. See IEG 2010 for an evaluation of PRSCs based on operations completed and evaluated by 2008. 6.22 Good analytical work, economic and other, contributes to success. Populous countries with large externally financed programs, such as Vietnam, are likely to benefit from an amount and variety of analytical work, typically using standard economic tools. Smaller countries with more modest analytical programs can probably learn useful things from a selective reading of the analytical work performed in more abundantly staffed countries. But Vietnam also profits from relevant non-economic analytical work that illuminates the likely behavior of the people involved both at the highest levels as well as at the village level in a way that informs the design of the programs. This sort of work is important but by its nature country specific.155 6.23 Well-designed impact evaluations are a valuable dimension of M&E. The impact evaluation turned out to be very important in assessing the impact of P135, not only regarding poverty but also non-income components of welfare, participation, decentralization and empowerment. This has direct relevance to other National Targeted Programs in Vietnam and elsewhere. It is important that funding of such activities be included in the original project design as their late inclusion may lead to implementation difficulties. 6.24 Vietnam's social compact was instrumental in supporting certain achievements, but may not be readily replicable elsewhere. Vietnam's reforms have relied on a top-down approach, which nevertheless draws in various stakeholders into the program and strengthens their ownership and voice. This is notably the case for targeted programs such as P135. While the country's history and social compact are quite specific, there are generic elements, such as effective engagement of local political authorities and communities that may be useful elsewhere. An example was Martin Rama's Making Difficult Choices\. Vietnam in Transition (2008). For behavioral implications at the village level the best example would be Edwin Shanks et al CDD in Vietnam (2003).
P105288 | AR Buenos Aires Infra Sustainable Investment Dev Proj Phase II | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2007 | 2014 | 2015 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/801401467998763873/text/ICRR14667-P105288-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/801401467998763873/pdf/ICRR14667-P105288-Box393183B-PUBLIC.pdf | IEG agrees with two lessons identified by the ICR from this operation as follows: (i) Good selection of project implementation arrangements can strategically foster institutional strengthening: As a result of the APL, the PBA consolidated a unit dedicated to implementing projects with credit from international organizations that had sufficient capacity to coordinate other ministries and institutions within the Province (such as the MI). In the ten years since the launch of the APL Program, the SCEOCI has become integrated in the operating structure of the GoPBA, going from unit status to agency status to becoming a sub-secretariat. The establishment of a sub-secretariat with significant experience implementing projects with foreign credit has had a multiplier effect, facilitating the GoPBAâ€™s capture of international credit from other organizations(ii) Working at the provincial level facilitates implementation. The APL Program benefited fromdirectly engaging the PBA to design and implement the Programâ€™s activities. This design decisionhelped provide a direct channel and build provincial capacity to work with international organizations,build a close working relationship with the counterpart
P105311 | IN West Bengal Accelerated Development of Minor Irrigation | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2012 | 2020 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/435001617151301756/text/India-IN-WB-Minor-Irrigation-Project.txt | http://documents.worldbank.org/curated/en/435001617151301756/pdf/India-IN-WB-Minor-Irrigation-Project.pdf | The ICR included five lessons. The following three are emphasized with some adaptation of language:1. To ensurea successful outcome for an irrigated agriculture project, an integrated design of structural measures (irrigation infrastructure),and nonstructural measures (management institution development and agricultural support) is essential.While theproject invested in infrastructure to improve water availability, agricultural support services and institution building werecornerstones of the project outcomes. These soft components were absent in state-supported ID programs andconstituted major value added for ADMIP. Finding the right incentive mechanisms for WUAs through both agricultural service supportand performance monitoring was a key nonstructural innovation. Such mechanisms that require multidisciplinary teams are showingresults on the ground and can contribute to sustainability.2.Complex projects that include many sub-projectsscattered over large areas require active learning and adaptive change management with innovations. The first phases ofproject implementation allowed stakeholders to accumulate knowledge which proved crucial during successive phases. The experienceenabled adjustments which contributed to the turnaround of the project. Owing to flexible approaches, the project capitalized oninnovations such as MIS integrated into the GIS, the introduction of a cluster-based approach, and the adoption of an integratedlandscape management model. Also, the project adopted a flexible approach by involving communities to express concerns and derivesuitable solutions.This approach boosted beneficiary satisfaction and improved povertytargeting.3.Developing and implementing a sound human resources development strategy is a cornerstone ofsuccessful project implementation. While an adequate capacity assessment is a crucial step in project preparation,human resources development strategy should also include risks to appropriate staffing level and skills, staff retention, andbureaucratic hurdles. Adopting the right type of incentives to ensure staff motivation can substantially reduce detrimental andfrequent turnover. In hindsight, a full-fledged strategy developed with key stakeholders and accounting for the constraints andrisks could have limited the impact of human resources challenges that the project faced.
P105329 | GMS Power Trade (Cambodia) Project | East Asia and Pacific | Cambodia | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2007 | 2012 | 2013 | ICRR | Less than 10 million |  | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/362921474502413035/text/000020051-20140625194217.txt | http://documents.worldbank.org/curated/en/362921474502413035/pdf/000020051-20140625194217.pdf | Important lessons derived from the ICR are:Regional energy projects involving multiple countries and implementing agencies should be backed by a comprehensive study of power supply and demand trends as a basis for addressing likely scenarios. This project involved three countries and at least three different agencies, all of which had different operating conditions and environments. To minimize risks and challenges in such a complex situation, the project should have developed a comprehensive study of power supply and demand to plan alternative and back-up scenarios for (i) the energy mix and cost of generation needed for power dispatching countries; (ii) options for power-dispatching countries in case of unexpected surges in domestic power demand; (iii) structuring cross-border power tariff in ways to allow the participating countries to adjust and for relevant parties to willingly trade power. A sound Bank-client country relationship is crucial for moving a complex project forward. In this project, despite the Bank's intention to help the client in â€œlearning by doingâ€ to develop modalities for cross-border power trade, following the communication (June 2011) to the client that their restructuring request could not be accepted due to the Bankâ€™s decision to hold back on Board Presentations for Cambodia, the Government requested full cancellation of the Grant.
P105331 | GMS Power Trade (Laos) Project | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2007 | 2015 | 2016 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/478791468185967771/text/ICRR14879-P105331-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/478791468185967771/pdf/ICRR14879-P105331-Box394823B-PUBLIC.pdf | The ICR (page 21-23) draws the following main lessons from this project.(1) Given that regional energy projects involve multiple countries and implementing agencies with different operating conditions and environments, it is important to ensure the commitment and ownership of participating countries through strong political consensus. Further, it is important to adapt to technological developments through regular reviews and updating of implementation plans.(2) Development of cross-border transmission lines, require firm commitment by electricity suppliers and buyers in the form of binding provisions in Power Purchase Agreements (PPA's).(3). While long term cross border transactions have taken place in GMS region, despite the absence of a regional power exchange market, the bilateral transaction-by transaction approach may be feasible only when there are limited cross border transactions within the region. As regional inter connections grow it may be useful to work for a regional power exchange market in the context of a region wide network.
P105403 | Second Land Administration Project (LAP-2) | Middle East and North Africa | West Bank and Gaza |  | FCS | Infrastructure | Urban, Resilience and Land | SPF | IPF | 2012 | 2016 | 2017 | ICRR | Less than 10 million | Highly Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/501051498140357266/text/ICRR-Disclosable-P105403-06-22-2017-1498140343735.txt | http://documents.worldbank.org/curated/en/501051498140357266/pdf/ICRR-Disclosable-P105403-06-22-2017-1498140343735.pdf | The ICR presents the following lessons (slightly edited) based on the operation (ICR, paragraphs 75-86): Formallyrestructuring a project remains an option when reaching the original development goals cannot be reasonably expected. However,political commitment and government ownership cannot be overemphasized. Having clear mandates, regulations, and processes in placeto strengthen the institutional framework firms up project design. When starting at a low capacity, analyseshelp informtarget setting,and identify risk-mitigating efforts to sustain outcomes. Partnering with municipalities is a usefulstrategy to implement a nationwide systematic land registration effort. This could include piloting municipality-specific,on-demand registration, coupled with waiving initial registration fees to create a critical mass of registered properties. At thesame time, fostering an enabling environment to boost the capacity of the private sector to partner with municipalitiesindelivering land administration services could facilitate project implementation. A strategy of wide stakeholder communityparticipation can help improve project efficiency and governance.This strategy may also be useful when using non-judicialland dispute resolution measures to expedite systematic land registration.
P105404 | GZ-SOUTHERN WEST BANK SOLID WASTE MANAGEMENT | Middle East and North Africa | West Bank and Gaza |  | FCS | Infrastructure | Urban, Resilience and Land | SPF | IPF | 2009 | 2016 | 2017 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/747301495472862962/text/ICRR-Disclosable-P105404-05-22-2017-1495472842008.txt | http://documents.worldbank.org/curated/en/747301495472862962/pdf/ICRR-Disclosable-P105404-05-22-2017-1495472842008.pdf | The project has provided a number of lessons (ICR, pp. 27-28), and the following are drawn from theICR: Public Private partnerships can be designed as temporary arrangements to increasecapacity and efficiency. Under the project, the partnership was specifically designed to grow the technical capacitythrough on-the-job training of Joint Services Council staff by working side by side with the privateoperator. Large infrastructure investments in fragile contexts require an incrementalapproach. The project focused on specific and critical aspects of the solid waste management system, namelysecondary collection and final disposal, complemented by institutional building, and public awareness raising. The newsanitary landfill created the necessary momentum to attract additional investments for the sector, which further strengthened wastecollection services at the municipality level. Overall, while a comprehensive sector reform may not always be feasible in a fragilecontext, an incremental, and sometimes opportunistic, investment approach can lead to substantial improvements across the sector,as long as investments are clearly linked to the theory of change. Social safeguardsrequirements can be leveraged to create significant social and economic benefits. The project created sustainablelivelihood alternatives for former waste pickers who were at risk of losing their livelihood when dumpsites were closed.Instead of only offering compensation for monetary loss, a livelihood assessment was conducted and a livelihood schemedesigned for waste pickers and implemented by specialized NGOs.
P105602 | GOVERNMENT`S CENTRAL PUBLIC ADMINISTRATION REFORM (CPAR) | Europe and Central Asia | Moldova | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2007 | 2014 | 2015 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/666861474940710495/text/000012394-20150310074902.txt | http://documents.worldbank.org/curated/en/666861474940710495/pdf/000012394-20150310074902.pdf | The lessons in the ICR are all supported, including the importance of strong Government ownership, staff capacity, long-term commitment, linking policies and budgets, selectively drawing on international advice, donor coordination, transparency and flexibility. Institutional reform is a long-term effort that needs to be supported by sufficient commitment, capacity and funding going beyond the current electoral cycle.In addition, there are well-known benefits of an MDTF both to donors and to the Government: Donors with small field presence and/or lacking technically specialist staff can gain from leveraging on the Bankâ€™s staff and experience in working with government on public administration reform issues. Donors may be more confident when the assistance is channeled through the Bankâ€™s technical and fiduciary controls.
P105651 | Ethiopia Electricity Access Rural Expansion Project, Phase II - GPOBA | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2009 | 2013 | 2015 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/175271475115141411/text/000020051-20150113004647.txt | http://documents.worldbank.org/curated/en/175271475115141411/pdf/000020051-20150113004647.pdf | The ICR Review selected the following main lessons from the project:(1) A proper assessment of the utility's technical and safety standards is needed to avoid a high rate of connection rectification after verification.(2) Output based aid projects need to be flexible to make adjustments to the design during implementation to achieve the project development objective in a changing sector or country specific environment.(3) To support the crafting of incentives to reach low income households, it is important to address all major barriers to electricity access.
P105669 | Mauritius - Economic Transition (TA) Project | Eastern and Southern Africa | Mauritius | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | IPF | 2009 | 2013 | 2014 | ICRR | Less than 10 million |  | Moderately Satisfactory |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/635691474593598739/text/000020051-20140626113043.txt | http://documents.worldbank.org/curated/en/635691474593598739/pdf/000020051-20140626113043.pdf | The NCO draws some familiar lessons: A strong and sustainable commitment to the reforms is essential; knowledge and lending services need to be packaged appropriately for middle income clients; political economy considerations must be factored in; and implementation arrangements and capacity building are critical.
P105683 | Community Empowerment II | Western and Central Africa | Liberia | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2007 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/546581475116949518/text/000180307-20141203060721.txt | http://documents.worldbank.org/curated/en/546581475116949518/pdf/000180307-20141203060721.pdf | The following lessons are derived from the ICR (pp. 23-24):Stakeholder and donor coordination is essential in a post-conflict context, especially during the transition from the post-conflict to the development phase where priorities need to be clearly identified and sequenced. In this case, the Bank and EU collaborated effectively, and LACE further brought together representatives from key government ministries, civil society, and other donor partners.Careful attention to fiduciary and project management skills is essential in a low capacity, post-conflict setting. The Bankâ€™s support in these areas was critical to the success of this project in meeting targets and overcoming implementation delays. Bank fiduciary staff were based in the country office and paid particular attention to the project.Transparency in payment processes to project participants is an important component of strong administration in a low capacity environment. In this case, the project established bank accounts for all project management committees and facilitated direct payments through a commercial bank to all temporary work program beneficiaries.
P105710 | First Competitiveness and Public Financial Management DPL | Latin America and Caribbean | Panama | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2008 | 2008 | 2010 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/447711475087990953/text/Panama-First-Competitiveness-And-Public-Financial-Management-Dpl.txt | http://documents.worldbank.org/curated/en/447711475087990953/pdf/Panama-First-Competitiveness-And-Public-Financial-Management-Dpl.pdf | The ICR offers thoughtful lessons with which IEG is in agreement. (1) Strategic plans need to be translated into clear action plans, which include monitorable output indicators to track progress. Without these, there is a lack of coordination and prioritization which leads to inefficiencies and slows down implementation. Beyond this ICR lesson, however, IEG suggests that not only output but also impact indicators are important, since this are important in identifying any needed mid-course corrections. (2) A good M&E framework can be important in developing a case for maintaining a program in shifting political conditions. (3) Adequate Bank Budget resources are important in sustaining a fruitful dialogue with the government.
P105711 | Africa Stockpiles Programme - P1 Ethiopia | Other | Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2007 | 2013 | 2015 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/791641475093216296/text/000012394-20150409082241.txt | http://documents.worldbank.org/curated/en/791641475093216296/pdf/000012394-20150409082241.pdf | The following lesson is drawn by IEG:Multi-regional, multi-country Adaptable Program Lending operations present considerable implementation challenges which are unlikely to be successfully addressed unless the anticipated synergies, economies of scale or other advantages of the project design are clearly shown to be concrete and readily achievable. Complex regional, multi-country operations like the present one necessarily carry higher risks/barriers to effective implementation than individual country-based projects. The cumulative weight of these risks can severely impede project implementation at both the regional and national levels. For this reason, a thorough evaluation of the anticipated benefits of a regional project design and the likelihood of their achievement should be undertaken before project design decisions are made. In this case, individual country operations would likely have achieved, or even exceeded, the results actually obtained, and at a lower cost in resources.The following lessons are drawn from the ICR with some adaptation of language:The Bank is not presently well equipped to handle multi-regional and multi-country programs. The Bank's internal systems are not geared for administering an umbrella program with multiple sub-projects in more than one region. Bank support for similar approaches in the future should weigh transaction costs and efficiency constraints in designing regional programs. Furthermore, the Bank's internal processing arrangements for regional/multi-national programs should be made sufficiently flexible to accommodate their characteristics and needs rather than applying coding and budget systems that hinder successful implementation.For multi-donor projects, clearly defined roles and responsibilities for all partners and their collaboration need to be agreed and operationalized prior to project effectiveness. The ASP was a complex program, which depended on close collaboration and cooperation among several partners, drawing upon their comparative expertise in pesticide management, project design, implementation, communications, and monitoring and evaluation. To ensure clarity for all partners, each entityâ€™s roles and responsibilities, together with guidance on how the partnership should function, should be defined and agreed on during project preparation. Concise time-bound and budget-related terms of reference for all partners, as well as clearly defined oversight and coordination responsibilities, would greatly improve project design and help to ensure smooth implementation.The dimensions of the task need to be carefully determined and sufficiently well-prepared before implementation. Project activities, such as a national obsolete pesticides inventory and a CESA, are lengthy processes but crucial for determining the dimensions of the disposal task ahead. Ideally, these activities should not be conducted during implementation as was done in this case; they should either be conducted during preparation or during a first implementation phase, followed by a second that comprises adequately timed and budgeted disposal activities. This could include an approach under which the inventory and the CESA are prepared simultaneously.
P105711 | Africa Stockpiles Programme - P1 Ethiopia | Other | Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2007 | 2013 | 2017 | PPAR | Less than 10 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/168841477341223021/text/108524-PPAR-PUBLIC.txt | http://documents.worldbank.org/curated/en/168841477341223021/pdf/Ethiopia-Mali-Morocco-South-Africa-Tanzania-Tunisia-Africa-Stockpiles-Program-Project.pdf | 7. Lessons The ASP-P1 offers a number of lessons that may be instructive for similar environmental cleanup projects, as well as for broader environmental management operations. These include the following. Lessons for environmental operations\. Â· Investments in highly technical environmental cleanup operations often face significant unknowns with respect to the nature and extent of the pollution problem and the available options for remedial actions. They can require a rigorous preparation process to fully determine the scope of the operation. Shortcomings in preparation of the ASP-P1, which took more than four years, did not lead to an adequate determination of the scope and budget of the operation's interventions. Preparation of the ASP-P1 failed to fully determine the scope of the obsolete pesticide problem, and thus grossly underestimated both the amount of obsolete pesticides and associated wastes and the funds necessary to deal with them properly. Â· In environmental operations involving pollution cleanup, the design needs to ensure a careful balance between immediate remedial actions to address threats to human health and the environment and longer-term preventive measures to ensure that similar pollution problems do not recur. Project design should account for the fact that prevention is a long-term process and is likely to extend well beyond the timeframe of the remediation activities. Pollution cleanup activities dominated the project design and budget in the ASP-1 relative to important activities to prevent future environmental pollution. Certainly, the ASP-P1 activities aimed at eliminating the existing pesticide stocks and associated waste were important, but in order to break the cycle of re-accumulation and future risks, it would also be necessary to take appropriate measures, such as controlling imports and limiting the purchase/acquisition of pesticides from abroad to meeting specified needs, to prevent future accumulations and their environmental risks. In the end, as noted in the text, total project financing in most of the ASP-P1 countries was not sufficient to address both cleanup and prevention adequately. Â· In complex environmental cleanup operations, it may be more effective to employ existing environmentally sound technologies outside the country than to create new capacity for this purpose in-country. In the ASP-P1, the governments of the four countries that disposed of their pesticide stocks decided to dispose of them in high-technology incinerators abroad rather than install such capacity for a limited waste stream in-country. 28 Lessons for project design\. Â· A horizontal APL may not add efficiencies in preparation or synergies in implementation if country circumstances are significantly different and if there is little opportunity for intercountry cooperation and coordination. In its original conception, the APL should have provided the six countries in the initial phase of the ASP-P1 with greater efficiencies in project preparation and opportunities for increased cross-country cooperation in implementation, as well as prospects for follow-on investments in a subsequent phase. In the ASP-P1, however, the uniform approach to project preparation, with its standard template for project design, complicated rather than facilitated efficient project preparation. And the desired synergies among the countries in project implementation were never realized because of significant differences in country context. In the end, the subsequent phase was never realized because of the poor performance in the initial phase of the ASP-P1. Â· Complex international partnership arrangements, such as those in the ASPP1, can result in conflicts in defining roles and responsibilities, challenges in effective coordination, and confusion in project interventions. The partnership arrangements designed for the ASP-P1 ended up imposing a burden on project implementation rather than delivering the synergies and benefits originally intended. Within the Bank itself, the cross-regional design of the ASP-P1 created significant challenges for Bank supervision, monitoring, and evaluation. Â· During project design, calculating the benefits of reducing pollution risks to human health and the environment can pose a challenge, but should be undertaken to support cost-benefit and efficiency calculations. There were no financial or economic analyses performed for the ASP-P1 at appraisal, although there are simple methods and tools for approaching the valuation of economic and environmental benefits for environmental projects. The DALY tool developed by WHO is one example of an approach that can be used to measure reduced overall disease burden, as expressed in the number of years lost due to ill-health, disability, or early death. Lessons for institutional capacity\. Â· In terms of institutional capacity for project management, the drivers of success may not be readily identifiable in the implementing agency, but they should be nurtured and sustained to promote successful project implementation. The three countries the IEG mission visited had roughly similar levels of institutional capacity for implementing the project, but while Tanzania had a project champion and dedicated staff that drove project success, Morocco and South Africa never found similar leadership. Â· Programs run risks if they are designed relying on coordination and management functions executed by institutions that do not have sufficient capacity to perform these functions. In the ASP-P1, the PCU was designed to perform overall program coordination and management functions from its position within the institutional structure of NEPAD, but in the end, NEPAD did not have adequate capacity to carry out these functions. Â· Complex regional programs with multiple country projects can impose significant demands on Bank capacity and require focused and sustained supervision by Bank staff. The lack of sustained commitment to the ASP-P1 at the program level and rapid turnover of task team leaders managing supervision of country projects contributed to the highly mixed project outcomes and resulted in widely disparate treatment of the various participating countries.
P105860 | Poverty Alleviation Fund II | South Asia | Nepal | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2008 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/983311578337738603/text/Nepal-NP-PAF-II.txt | http://documents.worldbank.org/curated/en/983311578337738603/pdf/Nepal-NP-PAF-II.pdf | The ICR included 8 lessons. The following three are emphasized with some adaptation of language: Inchanging socio-political environments, project design and implementation need to adapt over time in order to maintain consistencyand relevance to the evolving development challenges. Projects need to be designed and implemented with more flexibilityin mind, which will allow the project to better adapt to the evolving environment. Having more frequent high-level meetings todiscuss the relevance of the design in light of socio-political changes could help projects progress in line with the newinstitutional demands. The post completion sustainability of community level institutions needs a clear plan tobe in place at entry.The project experience showed that funding from development partners may not continue over thelong-term. This calls for a consolidation strategy to be built into the design, and a future vision addressing how beneficiariescould graduate from the project and maintain sustainability. A demand driven approach combined with directfunding is an effective toolin keeping target communities at the forefront and reaching out to the intendedbeneficiaries. The project encouraged communities to take initiatives to improve their livelihoods, particularly inorganizing themselves into community organizations. The project also provided resources directly to the poor, thereby bringing inefficiency and transparency to the activities and ensuring community ownership. Using local knowledge and expertise enhanced theprojects targeting strategy- animportant issue givenNepals diverse ethnicity and languages.
P105872 | Integrated Forestry Development Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2011 | 2017 | 2018 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/873801512769773616/text/ICRR-Disclosable-P105872-12-08-2017-1512769767123.txt | http://documents.worldbank.org/curated/en/873801512769773616/pdf/ICRR-Disclosable-P105872-12-08-2017-1512769767123.pdf | Lessons emerging from the ICR (paragraph 107)include: Early intensive guidance of project staff combinedwith demonstrations facilitate effective implementation. For example, in this project, site demonstrationsproved to bean effective way to persuade farmers to transfer from conventional monoculture silviculture to multiple use, mixed species forestmanagement. Also, farmerswere more willing to adopt multifunction, mixed species afforestation with environmentalbenefits when short rotation crops with early cash-generating potential were included in the planting mix. Forest landscaperestoration with a combination of strategies that include both ecological environmental conservation and landowner economicbenefits proved to be effective in maintaining farmer interest. Bottom-up approaches like the participation of farmersand ethnic minorities in the project planning process to includeactivities which respond to their needs,strengthenownership and interest in a project, and enhance its prospects for sustainability. Projects that are firmly anchored innational policy frameworks and local development strategies, accompanied by strong political support, have a better chanceofsuccess. This was the casein this project since the central PMO, based in the State ForestAdministration,wasresponsible for the national level policy, andthe project was well aligned with the provincialforest strategies. Output-based disbursement used for plantation activitiesconducted by communities is an effectivetool to ensure that the required quality standards are achieved in the field. Output based disbursement also simplified thedisbursement process which could be useful for broad rural community development projects.
P105881 | Sustainable Management of Fish Resources | Western and Central Africa | Senegal | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2012 | 2015 | ICRR | Less than 10 million | Highly Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/103451468178155124/text/ICRR14623-P105881-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/103451468178155124/pdf/ICRR14623-P105881-Box393183B-PUBLIC.pdf | Please see the detailed PPAR evaluation carried out by IEG in parallel for more information.
P105881 | Sustainable Management of Fish Resources | Western and Central Africa | Senegal | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2012 | 2015 | PPAR | Less than 10 million | Highly Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/941991468332415762/text/953150PPAR0P080Official0Use0Only090.txt | http://documents.worldbank.org/curated/en/941991468332415762/pdf/953150PPAR0P080Official0Use0Only090.pdf | 4. Lessons 4.1 The experience of the two projects yields the following lessons\. Â· Reforming the fisheries sector is politically sensitive and a long term pursuit, best suited to a phased programmatic approach in which sustained support is ensured over a series of operations. The timeframe for each stage needs to be set taking into account the capacity of the implementing agencies and the complexity of activities financed. In this case, the Bank maintained continuity in support across several operations but this was not designed upfront. Consequently, implementation was disrupted in the transfer of activities from one project to the next, as activities were put on hold while the restructuring process was carried out. Â· Operationalizing Co-management requires actions at both local and national level, lack of synchronization between the two can disrupt implementation and the motivation of key actors. In both cases implementation progress at the local level was bottlenecked by slow clearances at the central level, as well as delays for centrally procured materials and in processing contracts for experts to support critical activities. This slowed momentum and has frustrated local level actors. The lack of synchronization can be particularly disruptive to seasonal activities. Â· Supporting Alternative Revenue Generating Activities can potentially reduce the poverty-conservation tradeoff by making up for lost income or subsistence opportunities that stem from reduced resource access caused by project activities. But realizing this potential requires more rigorous feasibility studies to ensure that the proposed activity has the potential to generate profits that are equal to revenues forgone and that adequate budgets are provided to cover the full investment costs of the alternative activity. A sustainable system to support alternative revenue generating activities beyond the project timeframe is also needed.
P105897 | READ PNG | East Asia and Pacific | Papua New Guinea | Blend | Non-FCS | Human Development | Education | RETF | IPF | 2011 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/769041485364977908/text/ICRR-Disclosable-P105897-01-25-2017-1485364962431.txt | http://documents.worldbank.org/curated/en/769041485364977908/pdf/ICRR-Disclosable-P105897-01-25-2017-1485364962431.pdf | The ICR identifies the following lessons (ICR, p. 23): EGRA education projects with strong linksbetween objectives and activities can measure learning outcomes with strong evaluation processes.Strong results frameworks,including EGRA surveys, can be used to demonstrate learning outcomes. EGRA activities can have a substantial impact oninforming education policy. The EGRA pilot program results were used to inform the new standards-based curriculum and createrelevant teacher training activities. EGRA surveys are useful in measuring impact. The EGRA survey in thiscasedemonstrated specific reading outcomes for students. Specifically, the baseline and endline surveys revealed that girlsand boys had significant improvement in phonemic awareness, letter sound identification, and familiar word reading in two pilotprovinces as a result of the project. Education procurement processes need established and proven capacity in order toensure on-time delivery of materials. Procurement staff must be familiar with World Bank Group policies and procedures, and theBankmust allocate staff to build capacity on basic procedures like international competitive bidding in order ensure timelydelivery of materials.
P105990 | West Bengal PRI | South Asia | India | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2010 | 2016 | 2017 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/902221498153551934/text/ICRR-Disclosable-P105990-06-22-2017-1498153534961.txt | http://documents.worldbank.org/curated/en/902221498153551934/pdf/ICRR-Disclosable-P105990-06-22-2017-1498153534961.pdf | The ICR included seven lessons. The following are emphasized with some adaptation oflanguage: Political will and Borrower ownership are key to the success of local governance improvementprograms. There was a strong demand and commitment from the Government of West Bengal (GoWB) to implement the project. Theprojects objective was well aligned with GoWBs plans to deepen the devolution of powers and functions to rural localgovernments. The project was prepared at a time when various decentralization processes had already been underway in thestate. Although with the change in government at the state level at the beginning phase of the project, it did not affect theimplementation of the project. During the project, the national and panchayat-level elections also happened but did notaffecteither the PDO or project implementation. Separation of the executing and evaluatingagencies helped ensure the objectivity and integrity of performance assessment. Maintaining the integrity of theperformance evaluation system was key to the success of the project. The use of consulting firms for the external audit of theannual performance assessments managed by the implementing agency rather than the executing agency ensuredobjectivity. Effectivecommunication and gooddocumentation are critical tools forimproving transparency and citizen participation. The impact evaluation of the project showed that providinginformation to community members resulted in their increased and active participation in various GP meetings. Dissemination ofproject information to GP residents through various channels, such as GP Information Booklets, TV commercials, radio spots, noticeboards, hoardings and wall writings, ensured that community members were well informed and could participate effectively in the GPplatforms. Financial incentives such as performance-based block grants combined with capacity buildingactivitiesare an effective and efficient approach in improving the performance of local governments. The projectexperience demonstrated that that performance-based grants complemented with capacity building activitiesenabled GPstoimprove their performance on institutional aspects, especially on timely preparation of annual plans and budgets, execution ofsub-projects, citizen engagement, accounting, and monitoring and reporting. However information is lacking on whether training inthe absence of block grants achieves some effect, since this was not monitored in the project.
P106038 | BR Sao Paulo Trains and Signalling | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2008 | 2015 | 2016 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/916271468215357212/text/ICRR-Disclosable-P106038-06-10-2016-1465565501379.txt | http://documents.worldbank.org/curated/en/916271468215357212/pdf/ICRR-Disclosable-P106038-06-10-2016-1465565501379.pdf | The ICR draws the following main lessons from implementing this project. A longer implementationperiod may need to be considered while implementing brownfield rail projects (that is, while trains are operating on thelines). This project included upgrading of the signaling systems and civil works forrailway lines. As these lines were carrying more than a million passengers daily, an interruption in operations was not feasible,and work had to be conducted only during a small time window, generally from 1 a.m to 4 a.m. The experience of this project showedthat it may be useful to consider a realistic time frame indesigning a railway project while the trains areoperational and there is only a small time window for construction work. Designing payment schedules that provideincentives for successful installation may be useful for minimizing the risks associated with incomplete deliveries.In the case of this project, the systems contract specified large payments for delivering equipment, sincethisequipment had a large weight in the financial proposal. However, in terms of complexity of the activities involved,installation can be a critical part. Since providers in the case of this project were paid a large percentage of the contractvalue when the components were delivered, the contractors had lessincentive for installation of such equipment, and thiscontributed to delays during the implementation phase. It would be useful to have Indicators of reliability andsafety in the results framework in projects of this kind. This project incorporated upgrading permanent ways andsignaling, and these can be expected to improve the delivery ofrail services. Pertinent indicators such as servicestoppages (in units/months or hours/months) and punctuality (in percentage of on time trips) can better indicate progress towardsproject development outcomes.
P106063 | West Africa Regional Fisheries Program | Western and Central Africa | Western and Central Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2010 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/274981509978681209/text/ICRR-Disclosable-P106063-11-06-2017-1509978657440.txt | http://documents.worldbank.org/curated/en/274981509978681209/pdf/ICRR-Disclosable-P106063-11-06-2017-1509978657440.pdf | The ICR included six lessons. The following are emphasized with some adaptation oflanguage: Multi-country/regional projects require sufficient Bank staff and budget toensure adequate implementation support in each of the participating countries. The country-TTL system wasappreciated by the counterparts as it facilitated communication between them and the World Bank and allowed timely feedback to allfour countries. On the other hand, safeguards supervision was restricted by ashortage of specializedstaff. Reforming the fisheries sector to generate lasting benefits requires anincremental approach and commitment over time. As experience from the project showed, carrying outsectoral reforms and affecting behavior changes to control resource use and reduce illegal actions in a context of limitedgovernment budgets and capacities requires considerable allocations of time and capacity building actions and gradual advancementof reform measures. In such cases, APL/Series of Projects is a useful instrument as it allows a phased and flexible order ofinterventions, as well as the addition of more countries as they become ready to join theprocess. Community-led fisheries management is an effective mechanism for reducingfishing effort in the artisanal segment that requires substantial time and know-how to succeed. CommunityManagement Associations (CMAs) with legal access rights proved to be an effective mechanism for introducing new harvesting rules,local surveillance, stock enhancement measures (such as immersed artificial reefs) and local site monitoring, which together helpedrecover fish stocks in the co-managed fishing areas. Co-management structures also proved an important instrument for enhancingcommunities internal cohesion, however the allocation of fishing zones to communities could result in conflicts betweencommunitieswhom were granted and thosewhom were not grantedsuch access.
P106083 | Fifth Poverty Reduction Support Grant | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2019 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/899921541176155707/text/129569-PPAR-P104990-P106083-P113241-P117495-PUBLIC.txt | http://documents.worldbank.org/curated/en/899921541176155707/pdf/129569-PPAR-P104990-P106083-P113241-P117495-PUBLIC.pdf | 6. Lessons 6.1 The following lessons emerge from the design and implementation experience of the PRSF 4â€“7 series\. â€¢ Programmatic DPF can be an effective form of support for a well-defined, country-owned reform program. In Rwanda, the PRSF 4â€“7 series backed a wellarticulated and sound development strategy with strong implementation arrangements, the 2008â€“12 EDPRS. Arguably, however, value-added of the series stemmed more from the predictable financing that it provided for the overall program and its encouragement to reforms through regular, institutionalized monitoring of progress, than from advancing the achievement of specific objectives and outcomes. â€¢ It is difficult to be definitive about the efficacy of a DPF series unless the results framework is tight-knit, the reforms supported have the requisite depth, and there is a strong and direct causal link between these reforms and the outcomes sought. Under the PRSF 4â€“7 series, progress was made in several cases toward the objectives and desired outcomes. However, the role of the policy actions that the series supported in bringing about that progress versus other contributory factors was not always clear. â€¢ A commitment to providing regular, predictable financing in the form of (multisector) general budget support operations implies that the World Bank needs to be prepared to accommodate dilution or deferral of reform content relative to what is foreseen at the outset. This underscores the importance of entering into such a commitment only in instances in which the World Bank has confidence in the government's long-term intent to see reforms through in good faith despite delays and temporary reversals rooted in technical or political economy factors. In Rwanda, there were several delays and setbacks; for example, the implementation of a revised tariff structure for electricity was continually deferred and diluted. However, all triggers specified in the operations under the PRSF 4â€“7 series (or their equivalent in terms of the substance of the policy actions) were eventually achieved, though in some cases with several years' delay, suggesting that the World Bank's confidence was well placed. â€¢ The World Bank can face a hard choice between adhering to a CPAF in a multisector budget support series and fulfilling the good-practice prescriptions in its operational policy for DPF. In Rwanda, confining prior actions and outcome indicators in the PRSF 4â€“7 series to those found in the CPAF offered clear advantages, such as institutionalized M&E and lower transactions costs, particularly for country authorities. However, CPAF design shortfalls and selectivity in its coverage spilled over into the series, leading to inconsistencies with good practices prescribed under the World Bank's operational policy for DPF. It was often difficult in the PRSF 4â€“7 series to trace the causal links between prior actions (many of which lacked depth) and outcomes sought. Moreover, certain objectives the series sought originally, such as fiscal decentralization, were pursued later through insufficiently focused measures and outcome indicators that were constrained to align with those in the CPAF. â€¢ Successful deployment of an IFMIS can be facilitated by high-level commitment and performance monitoring, sustained external support, and system ownership. In Rwanda, top-level attention to imihigo (performance contract) monitoring included a focus on successive phases of IFMIS rollout, which also received steady technical and financial support from the World Bank (through parallel DPF and investment project financing, and later Performance for Results financing) and from other partners (notably through a Public Financial Management Basket Fund supported by the European Union and the U.K. Department for International Development). In addition, Rwandan authorities believed that the IFMIS's in-house development gave the system's users a greater stake in its successful deployment. 1The World Bank later prepared an analysis of why the reduction in poverty during this period was limited. See World Bank 2013a. 2The precise estimates of poverty, and especially their comparability over time, have been a source of contention in the past. However, the figures cited here have been widely referenced in World Bank operational documents and are taken to be good enough. 3Rwanda's fiscal year was changed in July 2009 from calendar year to July to June to align with East African Community norms. 4There is, in fact, some ambiguity as to whether Poverty Reduction Support Grant 5 or PRSG-6 was the first operation to be aligned entirely with the Common Performance Assessment Framework. PRSG-5 was sometimes labeled a transition operation from the standpoint of being aligned with the Common Performance Assessment Framework (see, for instance, annex 2 of the program document for Poverty Reduction Support Financing 7 (World Bank 2011), but elsewhere (for example, paragraph 53 of the program document for PRSF-7), it was asserted, The PRSG-5 operation was the first operation that aligned the series with the . 5This Project Performance Assessment Report uses the term policy actions to refer to the entirety of measures recorded in the policy matrix and results framework as implemented before the approval of a given operation. By contrast, the term prior actions refers to the subset of measures (usually depicted in bold type in the policy matrix and results framework) that was formally identified as necessary for the approval of the operation. 6 The limitations of an ex post logical framework where objectives evolved over the four-year lifespan of the series can be illustrated with reference to prior action (i) under the program development objective of enhancing the skills of the population. At first, it is unclear how an assessment of the basic education system contributes to the intermediate objective of revamping the strategic and institutional framework for postâ€“basic education, although it arguably speaks to the ultimate objective of enhancing the skills of the population. The answer is that the initial focus in PRSG-4 had been on reducing the pupil-teacher ratio in the nine-year basic education program, but it shifted (exclusively) to postâ€“basic education from PRSG-5 onward. 7 The concept of (structural) depth was originally developed and used in IMF (2007). 8The SMART criteria require indicators to be specific to the objectives toward which progress was to be measured; measurable; achievable; relevant in the sense of appropriate to measure progress toward the objectives; and time-bound. 9 The East African Community fiscal year runs from July to June, in contrast to Rwanda's prior fiscal year, which followed the calendar year. Predictable provision of financing for well-performing countries was a key premise of the Poverty Reduction Support variant of programmatic development policy financing. 11The 2011 and 2015 figures are from the Rwanda Ministry of Education's 2015 Education Statistical Yearbook, which reports the transition rate to upper secondary â€”that is, from senior 3 to senior 4 (GoR 2016, 40). (http\.//mineduc.gov.rw/fileadmin/user_upload/Amatangazo/2015%20Education%20Staiatical%20 YearbookF.pdf). 12Some related (more disaggregated) indicators were tracked during the implementation period of the FY11 Skills Development Project, but this was after the PRSF series' closure. 13As indicated previously, the Skills Development Project was implemented after the PRSF series' closure. 14In addition, the National Institute of Statistics of Rwanda's 2015 Integrated Business Enterprise Survey indicates that almost 80 percent of respondents viewed the availability of skilled or technical labor as no problem (and another 13 percent viewed it as a minor problem). 15The law governing community-based health insurance is Law No. 62/2007 of December 30, 2007. Submission of the law to Parliament was a PRSG-4 prior action. 16For useful background on the evolution of community-based health insurance in Rwanda, see, for example, Kalisa et al. (2015). 17Details of the performance-based financing system implementation and its results are discussed in Basinga et al. (2010). The paper reports on data produced from a prospective quasiexperimental evaluation design that was nested in the pay-for-performance program rollout and compared facilities in a treatment group with those in a control group that continued to receive input-based financing for a two-year period for prenatal care and child preventive care. The study found that significant increases in the provision of some services, such as in-facility deliveries by pregnant women, were associated with pay-for-performance. The results suggest that financial incentives are significant and have a larger impact for services in which providers have more control, such as prenatal care quality. The study also suggested that for services that depend more on patient behavior, such as the decision to seek prenatal care, the program could consider providing financial incentives directly to the patient rather than the provider. 18See the figures for the percentage of children under age five using insecticide-treated bed nets under World Development Indicators (https\.//data.worldbank.org/data/source/worlddevelopment-indicators). 19In fact, implementation of a revised tariff structure was later envisioned (in PRSF-8, approved in November 2011) as one of the triggers for PRSF-9â€”which, given the demise of general budget support in 2012, never materialized. 20The bulk of the increase in access over the PRSF 4â€“7 series' life span appears to have taken place in 2009. This likely reflected a significant increase in generation capacity in that year. 21The number of households and enterprises with access to electricity increased from 91,332 in 2006 to 159,516 in FY10 (compared with a target of 139,000) and to 308,326 in 2011â€“12 (compared with a target of 270,000). Generation capacity increased from 60 megawatts in 2006 to 84 megawatts in FY10 (compared with a target of 80 megawatts) and to 157 megawatts in FY12 (compared with a target of 130 megawatts). 22A subsistence level of electricity (30 kilowatt-hours per month) would be unaffordable for more than three-quarters of the unelectrified population. In recent years, fiscal transfers to the energy sector have declined from 2.5 percent of gross domestic product in FY14â€“15 to 1.4 percent in FY16â€“17. 24In addition, some of the measures lacked depthâ€”for example, completion of a tariff study and validation by Rwanda Utilities Regulatory Authority and the Ministry of Infrastructure. Others, such as the removal of the import duty and value-added tax on liquefied petroleum gas to promote its use and reduce dependence on charcoal, had no direct relation to the electricity outcomes targeted, although they arguably contributed to improving cost effectiveness (and environment-friendliness) in the broader energy sector. 25These investment project financing operations were the FY05 Urgent Electricity Rehabilitation Project and the FY10 Electricity Access Scale-up and Sectorwide Approach Development Project. 26 Implementation Completion and Results Report, page 66. 27 Implementation Completion and Results Report Review, section 4. 28See NISR (2016). Note that the standard for measuring urban access is 200 meters or less from the source and rural access is 500 meters or less. 29 The target for 2011/12 was later revised downward to 37 percent under PRSF-8. 30 The World Bank was Co-chair of the Rural Sector Working Group at the time. 31The 2011/12 figure is from the Implementation Completion and Results Report Review (efficacy section, objective 3), and was slightly under, but close to, the target for that year (PRSG-6 program document, page 44). 32Lack of prior consultation with development partners and other stakeholders (for example, though the Agriculture and Rural Development Sectoral Working Group) meant that alternative solutions to fraud concerns, such as the use of electronic wallets, could not be debated. 33 See also Implementation Completion and Results Report, page 40. 34 See Implementation Completion and Results Report Review, section 4 (objective 3). 35In particular, there are discrepancies in the land area subject to radical terracing between the National Institute of Statistics of Rwanda's seasonal agricultural surveys and figures reported in Implementation Status and Results Reports for the Transformation of Agriculture Sector Program-for-Results operation. 36 Law no. 40/2008 of August 26, 2008, established the organization of microfinance activities. 37 The 2008 figure is from Kantengwa (2010). The later figures are from AMIR (2015). The 13.9 percent of gross domestic product target for 2012 is from the PRSG-6 program document (table 9, page 41). 39Savings and credit cooperatives now account for an important segment of the microfinance institution sector (AMIR 2015). 40According to the website of the Financial Sector Reform and Strengthening Initiative\. The FIRST initiative is a multidonor grant facility that provides short to medium-term technical assistance to promote sounder, more efficient, and inclusive financial systems. Since its inception in 2002, FIRST has funded over 600 projects in about 120 countries, with commitments over $135 million. For more information, visit the website at https\.//www.firstinitiative.org/. 41Several districtand sector-level officials gave the mission demonstrations of the SmartFMIS' capabilities. 42Despite changes in Public Expenditure and Financial Accountability methodology between the 2007 and 2010 PEFAs and the 2017 PEFA, the constituents of this score are unchanged, so the scores are comparable. 43The latest figure is taken from the Implementation Status and Results Report for the Public Sector Governance Program-for-Results operation. 44The Implementation Completion and Results Report (page 47) provides details concerning the substance of the amendments. For instance, they were designed to bring the provisions of the law in line with (i) the revised mandate of the Rwanda Public Procurement Agency, resulting from the full devolution of the procurement function to the procuring entities; and (ii) the Common Market for Eastern and Southern Africa (free trade area) procurement framework (which Rwanda joined in 2004). 45 Separate independent review panels also operate at the district level. 46The Implementation Completion and Results Report Review for the PRSF 4â€“7 series reported that the share had increased very modestly to 75 percent by 2012, missing the target of 87 percent by the series' end. However, the 2010 Public Expenditure and Financial Accountability appears to contradict this because it affirms that 86.6 percent of all contracts above the threshold were awarded by open competition. This is also more consistent with the 2015 Crown Agents findings (Crown Agents 2015). 47See Crown Agents findings (Crown Agents 2015). Similarly, the Rwanda Public Procurement Agency's Annual Activity Report for 2015â€“16 (dated January 2017) affirms, based on its procurement audits, that more than 88 percent of public procurement by value took the form of open bidding. However, it is notable that the Rwanda Public Procurement Agency's reach does not encompass all aspects of a broader concept of public procurement. For instance, as discussed in the section on electricity, many power purchase agreements that the Rwanda Energy Group entered into with independent power producers were negotiated bilaterally rather than tendered competitively. 48Three aspects were scored under procurement in the 2010 Public Expenditure and Financial Accountabilityâ€”the previous methodology\. evidence on the use of open competition for contract award, extent of justification for use of less competitive procurement methods, and existence and operation of a procurement complaints mechanism. All received an A score, despite the subsequent strengthening of the independent complaints mechanism (assessed according to six distinct criteria under the new methodology followed in the 2017 PEFA). 49For example, citizen report cards for 2014â€“16 show citizens' overall net satisfaction with local government services as increasing from 60 percent in 2014 to 75.9 percent in 2016. Trends for many individual service categories (health, for example) are similar. For more detail, see World Bank 2018b. 50For further details, see the discussion in the Implementation Completion and Results Report for the PRSF 4â€“7 series (World Bank 2012, 49â€“50). 51A 2010 census of public sector workers (including workers at the local government â€”province, district, and sector-level, and in-service delivery units such as educational institutions, hospitals, and health centers) showed that approximately 46 percent of workers had been in their current position less than three years and 62 percent had been in their current position less than five years. However, no subsequent census of public sector workers has been made available that would allow comparisons over time.
P106161 | Bangladesh - Secondary Education Quality and Access Improvement | South Asia | Bangladesh | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2009 | 2018 | 2019 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/209381538346963254/text/Bangladesh-BD-Sec-Educ-Qlty-Access-Enhancement.txt | http://documents.worldbank.org/curated/en/209381538346963254/pdf/Bangladesh-BD-Sec-Educ-Qlty-Access-Enhancement.pdf | The ICR (pp. 31-34) offered several useful lessons, including the following lessons restated byIEG:Carefully designed incentive schemes motivate students and teachers to improve theirperformance in learning and teaching. SSC Pass Awards motivated poor students who had fewer prospects of moving upto higher levels of education. Best Student Awards, Institutional Awards and Award Books forthe Reading HabitDevelopmentProgram created a competitive environment where students and schools aspired to be highperformers.Leveraging the capacities of specialized agencies through partnership agreementshelps to overcome capacity constraints of the main implementing agency. Partner agencies contributed to thefollowingproject activities: Agrani Bank disbursed stipends; the Department of Public Health and Engineering implementedwater and sanitation activities at the schools; the Bangladesh Bureau of Education Information and Statistics conducted annualsecondary schools census; and Bishwo Shahitto Kendro managed the reading habits program.Harnessingdigital tools promotes both effectiveness and efficiency in managing transaction-intensive and data-intensiveoperations.The project had to process very high numbers of small transactions in decentralized settings.The Local Government Engineering Department, acting as the projects PMT Administrator, expanded its role and established anintegrated database that supported data collection, verification, and processing of transaction information.
P106165 | Lao PDR Trade Development Facility Project | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | RETF | IPF | 2008 | 2013 | 2015 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/399031475118301233/text/000180307-20150108112428.txt | http://documents.worldbank.org/curated/en/399031475118301233/pdf/000180307-20150108112428.pdf | 1. Projects need to be aligned with government priorities to have the best chance of gaining continued government ownership and support. Also key to this is the adoption by Bank staff of participatory preparation with governments. 2. Staff continuity is extremely important to ensure timely and dynamic changes in response to changing circumstances of implementation. Field based staff with experience in key fields is a boon for easy access to client counterparts.
P106165 | Lao PDR Trade Development Facility Project | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | RETF | IPF | 2008 | 2013 | 2018 | PPAR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/888111532098573251/text/127054-PPAR-P106165-P165356-PUBLIC.txt | http://documents.worldbank.org/curated/en/888111532098573251/pdf/127054-PPAR-P106165-P165356-PUBLIC.pdf | 7. Lessons 89. Early engagement with the government\. Appropriate analytic work can lay the basis for sound project design and enhance commitment of the government. Prior to project approval, the World Bank had engaged with the government on trade-related issues and prepared a DTIS. Following the DTIS report, the government prepared an Action Matrix that outlined priority areas where trade-related technical assistance would be needed. The project was highly relevant to the government's priorities because it was created to help implement the government's DTIS Action Matrix. 90. Attribution issues\. The final outcomes in a results framework need to be specific and attributable to the project. It is difficult to attribute the outcomes of relatively smaller projects to broadly defined outcomes at the country level. Efforts should be made to design project-level outcome indicators so that they are directly relevant to the specific activities of the project. 91. Simple project design\. In the context of low institutional capacity, simple project design with fewer components may enhance the focus of a project and the likelihood of full implementation. In addition to trade facilitation, the project included a component related to export competitiveness and the business environment. Although the project did contribute towards skills development in the garments sector, it did not make any major contributions in other non-resource sectors such as handicraft, wood processing, etc. These components may have been better suited to another project, with broader policy-related components, allowing this project to focus more narrowly on trade facilitation issues. 92. Capacity building\. In a limited capacity environment, a learning-by-doing approach can be effective in building project management capacity. At the time of project approval, the implementing agency, NIU, had limited capacity on procurement and financial management. However, the NIU's confidence grew during the implementation period mainly due to a learning-by-doing approach. This approach was based on\. (i) a fulltime procurement advisor attached to the NIU during the initial period; (ii) a full-time financial management advisor in place throughout the implementation period; (iii) training and advice provided by World Bank procurement and financial management specialists based in Bangkok and Vientiane; (iv) continuity on the part of the World Bank team, with the team lead and trade economist remaining in place from project effectiveness until closing, allowing for key relationships to be developed and institutional memory retained. 93. Political commitment\. Accession to a major regional or global agreement such as WTO can serve as a strong incentive for reforms and ensure political commitment. The project helped implement several reforms that were part of Lao PDR's WTO and ASEAN membership commitments. For example, the Lao Trade Portal helped Lao PDR comply with WTO and ASEAN standards that require member countries to make their trade related regulations publicly available and easily accessible. Similarly, progress on improving the SPS legal and regulatory framework was driven by the need for WTO compliance. Accession and compliance requirements of multilateral agreements provided a strong impetus for many of the reforms that were supported by the project.
P106170 | AF: ARTF-Management Capacity Program | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | RETF | IPF | 2007 | 2012 | 2013 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/803041475098330272/text/000020051-20140625193738.txt | http://documents.worldbank.org/curated/en/803041475098330272/pdf/000020051-20140625193738.pdf | Lessons put forward in the ICR are supported, for example: There is a need to target capacity building on ministries undergoing strategic reforms, and sufficiently large clusters of capacity within ministries to have an impact on improving performance. It is important to provide adequate numbers of skilled middle management and junior professional staff to support senior management capacity.Progress in fragile contexts is bound to be slow, and capacity development needs to be realistically calibrated so as not to raise undue expectations.When moving from a highly centralized government structure, careful planning is required to support the positioning of senior staff in sub national jurisdictions.There is a need for continuity, experience and high quality of task team leaders to ensure capable supervision of complex reforms.
P106172 | Nigeria Electricity and Gas Improvement Project (NEGIP) | Western and Central Africa | Nigeria | Blend | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2009 | 2019 | 2021 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/592701608767564202/text/Nigeria-NG-Electricity-and-Gas-Improvement.txt | http://documents.worldbank.org/curated/en/592701608767564202/pdf/Nigeria-NG-Electricity-and-Gas-Improvement.pdf | If sector reforms are likely to strongly influence the achievement of objectives, multiple scenarios should be developedto facilitate the projects rapid adaptation to the changing reform and operational context. The initial problems inthe Nigerian power sector were inadequate energy supply due to energy losses (technical losses), inefficiencies and insufficientpower plant capacity. The project aimed to address these problems by increasing power supply through the PRGs and installing andretrofitting power transmission and distribution facilities. However, the reform of the power sector changed the situation andredefined the problems as (1) poor revenue collection and payment discipline from the DISCOs, and (2) lack of incentives for theprivatized DISCOs to increase power supply and sales to customers. The projects approach to increasing electricity volume andcapacity was not responsive to the post-sector reform situation. Despite the fact that sector reforms were envisioned from thebeginning, the risks were not adequately addressed and there were no alternatives or scenarios considered in case the sectorreforms had a negative impact on the project. It is essential that projects prepare for multiple scenarios and respond to changeearly in order to respond to the envisioned sector reforms if the sector reforms are expected to have a direct or indirect impacton project outcomes.A parallel Power Purchase Agreement (PPA) should be considered when establishing a guaranteescheme. In the project, the GSA was signed between Accugas Limited and Calabar Generation Company Limited (CGC), but dueto policy changes, the government did not receive the full agreed power supply from Calabar. Although gas supply from Accugas wasstable, CGC was also unable to sell power equivalent to the full capacity of CGC due to constrained demand on its network, leavinghalf of its installed capacity unused. The lack of a PPA to guarantee the purchase of power in parallel could have improved thepower supply environment.Indicators in the Results Framework need careful monitoring and revision when theyinvolve privatization. The project was unable to collect data on key indicators such as technical and commercialdistribution losses, distribution outages, and revenue collection ratio after the privatization of distribution entities. Due tothe lack of data on actual performance vis--vis the indicators, it was not possible to properly assess the achievement ofthe projects objectives and to conduct economic and financial analysis. During privatization, it is important to closelymonitor the availability of data and unless original data can be collected, it is vital to explore other data sources or devisedifferent indicators.
P106208 | PE SWAP Pernambuco Educ Results& Account. (PERA) | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2009 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/960311481130548986/text/1481132362677-0000A8056-ICRR-Disclosable-P106208-12-07-2016-1481132357541.txt | http://documents.worldbank.org/curated/en/960311481130548986/pdf/1481132362677-0000A8056-ICRR-Disclosable-P106208-12-07-2016-1481132357541.pdf | IEG summarizes the lessons presented in the ICR (p. 21) as the following: Adequate institutionalcoordination arrangements for project implementation contribute positively to achievements, capacity building, andsustainability. This operation required coordination among the SEE, SAD, SEPLAG, and its Secretariat for ProgramMonitoring. Since SEPLAG has the responsibility in the State for coordinating and monitoring the Results-Based Managementstrategy, it was well poised to coordinate among all the involved agencies and implement the operation. It was able todevelop strong partnerships among the agencies, which led to smooth flow of information and implementation. This model can beutilized by other projects in the state. Measuring achievement of objectives requires the specification ofappropriate key performance indicators. Indicators should be kept simple and well articulated. When compositeindicators are used, setting realistic targets is difficult. The adoption of state-sponsored educationassessment can positively affect schools and students performance and provide information toparents.It is not the assessment itself, butrather the use of the data that brings aboutimprovement. Whenschool and student performancedata are usedto develop action plans to improveteachers practices, that is when improvementsare noted instudent learning. The dissemination of studentperformance data to parents helped to increase parental participation in the education system in this operation.
P106208 | PE SWAP Pernambuco Educ Results& Account. (PERA) | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2009 | 2016 | 2018 | PPAR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/148271500035141485/text/114046-PPAR-P106208-PUBLIC.txt | http://documents.worldbank.org/curated/en/148271500035141485/pdf/114046-PPAR-P106208-PUBLIC.pdf | 7. Lessons 98. Based on the experience of this project, several lessons can be drawn\. Â· Formidable results (dropout, distortion, student learning) can be achieved, but these results take time and may not be evident within the typical implementation period of a World Bank operation. Because of the extensions (not related to implementation), the World Bank's closure report had more years of data to draw on than the typical five-year operation to demonstrate results. This report had even more data to present. This suggests the importance of country monitoring systems, beyond project-focused ones. It also suggests the long-term vision and support that are needed by governments and the World Bank to register improvements, particularly in relation to student learning. In this case, the government began the initial steps of implementing its vision in 2007 and 10 years later, when the IEG mission occurred, the trend of improvement was clearly evident. Â· The success and sustainability of this operation depends largely on the government's commitment to (and ownership of) its comprehensive sector program, sector policies, and sector management system. Attribution of results in this operation goes beyond the World Bank financing to the broader government program. Notably, there has been continuity in education policies and programs in the state government, despite there being multiple governors. This continuity has stabilized the performance monitoring system so that data served as a feedback loop to the system. The government's management process comprised planning, budgeting, and monitoring; thus, the collection of data (related to performance indicators) was critical to monitor the efficacy of public services. Â· Assessment data were used for multiple purposes (including pedagogical purposes) and among multiple stakeholders. Some of the factors that contributed to the use were quality and usability of data, analysis of test results, open and timely dissemination of data, and political continuity over time. As a result, data were part of the conversation at every level from the governor, SEE, regional coordinators, and school principals and teachers and made available to parents. For the system to further identify weaknesses in student learning, results will need to be disaggregated. Â· Equity objectives require clear definition and measurement and may need additional efforts. In this operation, equity was a stated objective, but the equity concern was not clearly articulated or measured. The operation tracked average school scores, which masked heterogeneity. It also focused on low-performing schools, but a performance gap remained between rural and urban schools. Efforts to improve school averages were insufficient to reduce these inequities. Â· Although the reform began before the World Bank was involved, the World Bank added value through transmission of knowledge from experiences and lessons in Brazil and Pernambuco. The World Bank produced several economic and sector works specific to Brazil, which facilitated policy dialogue within the Pernambuco. It disseminated the results of the study analyzing classroom practices, which reinforced the need to focus attention on what teachers do. International best practices were used to inform the structure of the school bonus program. The World Bank assisted in the evaluation of the early implementation of the school bonus program. The client valued the World Bank's knowledge contribution.
P106216 | Bangladesh - Higher Education Quality Enhancement Project | South Asia | Bangladesh | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2009 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/607671581531622065/text/Bangladesh-BD-Higher-Education-Quality-Enhancement.txt | http://documents.worldbank.org/curated/en/607671581531622065/pdf/Bangladesh-BD-Higher-Education-Quality-Enhancement.pdf | Lessons drawn by IEG: Difficulties in measuring higher education sector outcomes (i.e. improved skills ofuniversity graduates) can be addressed through multiple evaluative sources. In the case of this project, theMEplanemployed student, faculty, and employer satisfaction surveys (three rounds), supplemented by findings from atracerstudy and an impact assessment. Introducing a competitive grant mechanism can be an effective first step to engagingautonomous institutions, prior to attempting more complex sector reforms. In the case of this project, the grants aimedtospur innovation and accountability, while deeper quality assurance mechanisms (drafting of nationalqualificationsframework and creation of quality assurance cells in each participating higher education institution)wereintroduced at a later stage.
P106220 | Timor Leste - Youth Development Project | East Asia and Pacific | Timor-Leste | Blend | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2009 | 2013 | 2015 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/642801475115881503/text/000180307-20150108094241.txt | http://documents.worldbank.org/curated/en/642801475115881503/pdf/000180307-20150108094241.pdf | The ICRR gives rise to the following lesson:Â· Emergencies and priorities. In line with Bank strategy at the time of classifying all Timor Leste projects as Emergency projects under OP/BP 8.00, this project was an Emergency Project. In emergency situations, priorities are bound to change over time, and country support for different project elements, or the project itself, may change. This underlines the importance of selecting interventions that have an immediate impact and can be implemented over relatively short periods of time.Â· Grant size and supervision effort. The ICR indicates that resources for supervision were a function of grant size (ICR, p. 32), and turned out to be insufficient to cope with all the challenges of an emergency environment. Calibrating supervision resources to the challenge rather than the size of the Bank loan or grant may be a more rational approach.The following (edited) lessons are drawn from the ICR: Â· Involving youth in the community. Offering youth opportunities to engage in community activities can reduce tensions and bring about a sense of belonging and shared responsibility for outcomes in their communities,Â· Using technical assistance. Specialized technical assistance for livelihood activities is particularly relevant in contexts such as Timor-Leste, where sub-national level staff is likely to have limited technical expertise. Here, capacity constraints at central levels can serve as a good indicator of such bottlenecks that are particularly important to address when field-level interventions are key for success.Â· Monitoring and evaluation. Adopting an M possibly combined with targeted studies and process evaluations that can generate results early on and inform timely corrective action.
P106228 | Ethiopia Nutrition (FY08) | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2008 | 2014 | 2015 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/711311468190148402/text/ICRR14776-P106228-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/711311468190148402/pdf/ICRR14776-P106228-Box393191B-PUBLIC.pdf | The ICR (pp. 36-37) offers useful lessons, including:A projectâ€™s likelihood of success is enhanced through strong country ownership and integration into a wider multi-sectoral agenda. In this case, the National Nutrition Plan provided crucial engagement of government at all levels and key technical and implementation support. At least in part because of the NNP, the project was able to catalyze funding from other sources, particularly for community-based nutrition activities.Community-level service delivery provides instrumental legitimacy and commitment. Ethiopiaâ€™s unique service delivery model, its Health Extension Program (which employs Health Extension Workers at the health post level), provided a cost-effective existing entry point for nutrition support under this project (ICR, p. 36). This existing institutional structure facilitated cost-effective delivery of nutrition services.
P106228 | Ethiopia Nutrition (FY08) | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2008 | 2014 | 2019 | PPAR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/276231563896790836/text/Ethiopia-Nutrition-Project.txt | http://documents.worldbank.org/curated/en/276231563896790836/pdf/Ethiopia-Nutrition-Project.pdf | 3. Lessons 3.1 The use of interactive approaches at the community level can facilitate behavior change. While maintaining traditional communication modalities, the project also adopted a more interactive approach with community conversations, in which people are encouraged to ask, analyze, and act under what is called the triple-A approach derived from a UNICEF concept to assess the problem, analyze its causes, and take actions. The project prepared HEWs for this role through phased training, including higher counseling skills. Behavior change activities were well planned and linked with community mapping and participatory assessments. Nonhealth aspects of malnutrition were also covered. Many mothers who have seen positive results with their children shared their experience with other mothers, household members, and other influencers in the community, thus further disseminating nutrition knowledge in the community. 3.2 In very poor communities, CBN needs to complement behavior change interventions with income support to achieve the desired goals fully because behavior change also depends on the means to keep or to buy healthful and nutritionally rich food. Mothers can apply food diversity practices as counseled by CBN if they have the means to do so. This would contribute to mothers' participation in CBN and adherence to growth monitoring sessions. Poverty often creates food insecurity that prevents access to sufficient, safe, and nutritious food to meet basic dietary needs, resulting in severe vulnerability to both physical well-being and mental health. 3.3 Favorable institutional conditions, programmatic arrangements, and incentives facilitate the unfolding of multisectoral engagement. The project sought to advance multisectoral collaboration, but substantial engagement was visible only after several years because time was required for the actual buildup of nutrition efforts as an integral part of mainstream responsibilities in various sectors. In this sense, the Ethiopia experience shows that evaluations need sufficient time to pass for a plausible impact to have occurred, as noted in IEG's findings in World Bank (2010). This lesson is also in consonance with USAID's lessons learned 2013â€“15 from the Ethiopia Multisectoral NNP indicating that the multisectoral approach requires patience, time, and continuous engagement, and that it requires incentives related to budget, capacity, and accountability. 3.4 Integration of nutrition operations with an existing and institutionalized service delivery mechanism at the community level facilitates CBN implementation. The project embedded its community interventions and micronutrient supplementation within the existing Health Extension Program, thus promoting its efficiency and community reach. 3.5 External collaboration with development partners, under government leadership, catalyzes international expertise and good practices that benefit and reinforce government policy and its nutrition agenda. Both the project and the national program led by the government benefited from such collaboration, which facilitated sharing lessons learned from international experience. Additionally, joint monitoring missions with the government and development partners provided a platform to maintain ongoing dialogue and collaboration.
P106235 | Da Nang-Quang Ngai Expressway Development Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2011 | 2019 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/103681591985138844/text/Vietnam-VN-EXPRESSWAY-DEVEL-DaNang-QNgai.txt | http://documents.worldbank.org/curated/en/103681591985138844/pdf/Vietnam-VN-EXPRESSWAY-DEVEL-DaNang-QNgai.pdf | The ICR provided seven lessons with the reflection on procurement and contract management, safeguard, institutionalcoordination, ME framework, and co-financing framework, which are all useful for the future project preparation andsupervision of the transport projects. In addition to the ICRs lessons, IEG further expands two specific lessons on theME framework and co-financing framework.1. Complex and multilevel engagements need a more nuanced causaltheory than a linear process. The project was clear enough to ensure the causal mechanisms of the expressway developmentbecause it provided a linear mechanism, which reduced travel time, smoothed the traffic, and improved road safety. On the otherhand, the project was not sufficient to design the causal mechanism for capacity improvement due to the complex interventions andmultiple levels of engagements. A tolling strategy, for instance, involved various stakeholders, including a high-level governmententity and private investors, which required extensive consultations and careful consideration of their interests. The projectneeded a detailed causal framework on how the project intended to engage with different levels of entities and to nudge thesestakeholders.2. A systematic framework and engagement with co-financers are strengthened when considering riskmanagement. The project demonstrated effective coordination with the co-financer (JICA). Such coordination was enabledwith the signed procedure agreement, which detailed the coordination mechanism between the two entities. It established theintegrated project review and monitoring services and served as a mechanism to monitor the progress of the entire section of theroads. While effective overall, the lack of risk assessment undermined the effectiveness of the framework. The framework was notresponsive to the cancellation of the JICAs ITS component. Risks associated with each entity should be identified at anearly stage and should be incorporated into the framework.
P106259 | Afghanistan - Second Education Quality Improvement Program | South Asia | Afghanistan | IDA | FCS | Human Development | Education | IDA | IPF | 2008 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/443501548279719788/text/Afghanistan-AF-Edu-Qlty-Improvement-Program-II.txt | http://documents.worldbank.org/curated/en/443501548279719788/pdf/Afghanistan-AF-Edu-Qlty-Improvement-Program-II.pdf | The ICR (pp. 38-40) presented several insightful lessons, including:Heavy reliance ontechnical assistance with a separate coordination unit does not effectively build institutional capacity. Although the use ofa dedicated project coordination unit was seen as necessary because of the projects emergency nature and weak existingcapacity within MoE, it will be important moving forward to develop a permanent cadre of middle-level managers within MoE (a lessonthat has been incorporated into the design of the follow-on project).Third-party monitoring using localorganizations and NGOs can be effective in conflict areas. In this case, when Bank staff were unable to continue regular sitevisits due to the security situation, third-party monitoring enabled continued reporting on project activities andoutcomes.Strong management and supervision, attention to capacity development, and detailed priorplanningare essential to the success of large construction components in low-capacity, fragile environments. In thiscase, constructionwas initiatedwithout sufficient planning and precaution, resulting in the design of schoolsnot suitable to local conditions, insufficiently detailed school drawings and technical specifications, substantial delays due toprocurement challenges, and poor and/or incomplete construction.Increasing girls enrollment requires abalanced strategy incorporating both supply and demand factors,and especiallycareful, deliberateattention tocultural and security concerns. In this case, infrastructure investments (boundary walls, separate toilets, water supplies)and scholarships for girls to attend teachers training colleges were not sufficient for reaching gender targets.Although the project included innovative social mobilization strategies,girls enrollmentremained suppressed due tofamily pressures for girls not to attend school.
P106261 | MX Sustainable Rural Development | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2009 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/646461558014339626/text/Mexico-MX-Sustainable-Rural-Development.txt | http://documents.worldbank.org/curated/en/646461558014339626/pdf/Mexico-MX-Sustainable-Rural-Development.pdf | The ICR included five lessons. The following three lessons are emphasized with some adaptation oflanguage. To ensure a successful outcome, energy technology innovation projects in the agriculturesector need to factor in both demand and supply issues. Promoting agribusiness buy-in and adoption is just one sideof an equation involving multiple, parallel development streams. Similar projects need to factor in: (a) market development,including appropriate technologies, (b) reliable, competitive local providers, (c) specialized advisory and maintenance services;(d)supportive, flexible project procurement whichwill help to establish technical, price and quality standards; (e) TAand training public and/or private - focused on the installation, operation and long-term sustainability of systems; (f)dissemination of the economic, environmental and social results of technology adoption; (g) a parallel RD agenda to resolveemerging challenges, develop databases and make the case for supporting the model; and, (h)ensure that the characteristicsand needs of targeted beneficiaries are well-understood. To ensure participation ofbeneficiaries,energy innovation initiatives can benefit from flexible targeting that involves a clear mechanisms forselection, support/incentives for investment and expected cost-sharing depending on size, production volume andtechnology. A comprehensive, upstream analysis is needed of the scale, activities, typology andmotivation of potential beneficiaries to participate. Technically, interventions inrenewable energyand energyefficiencycan beequally viable for small or large agribusinesses, but economies of scale matter. Larger bio-digestertechnologies are more cost-effective and efficient, while solar has a greater potential to be modular to be efficient.Incentives also matter. While the incentive driving a large dairy operation to participate is likely to lead toa substantialincrease in profitability, for a micro/small agribusiness, pumped water for cattle powered by a photovoltaic system might representthe difference between viability and failure. To ensure accurate assessment of the projectsimpacts, a well designed impact assessment study needs to be done at the completion of the project. The project designneeds to include adequate funding to carry out an impact assessment study, for example, through the Banks Development ImpactMonitoring and Evaluation unit (DIME). The Bank can help public authorities commit to ME (including by financing it with loanfunds, not grant resources) and understand the benefits - social, political, technical and economic - of a data-driven assessmentof public policy, strategy, plans and programs. Building a sound ME systemin key institutions is as important asexecuting the designed agenda.
P106262 | Bicol Power Restoration Project | East Asia and Pacific | Philippines | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2008 | 2009 | 2010 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/154301475070623897/text/000146597-20140619165509.txt | http://documents.worldbank.org/curated/en/154301475070623897/pdf/000146597-20140619165509.pdf | Based on the project's experience, the main lessons that are pertinent to emergency operations are as follows:(1) Close upstream collaboration is critical in emergency projects, focusing particularly on assessing institutional capacities as well as clear requirements and procedures to follow, in order to enhance fast and problem-free implementation.(2) The Bank needs to exercise flexibility in procurement and disbursement arrangements for emergency operations by applying simplified procedures, such as the application of National Competitive Bidding rather than International Competitive Bidding, imposition of the Approved Budget as the contract ceiling, and other measures. Flexibility, however, would still require due diligence on procurement capabilities and compliance with Bank requirements.(3) While minimizing conditionalities to help accelerate implementation of an emergency project, good project governance still needs to be ensured. This can be achieved early in project processing by ensuring that (a) accountabilities are clear in the projectâ€™s institutional structure, and (b) appropriate financial management controls are in place. (4) Even in emergency situations, resettlement planning cannot be overlooked. The possibility of land acquisition and resettlement issues emerging during implementation can make a project vulnerable to delays and even stoppages. Therefore, it is important early in processing to conduct detailed assessments, identify potential problems, and develop responses and solutions.(5) Even in emergency situations, it is possible to complement longer-haul and broader sector reform processes, as demonstrated by this project, which helped the ongoing privatization process by strengthening investor confidence in the sector's responsiveness to natural disasters as well as the capacities of the institutions managing and operating in the sector.
P106280 | Lagos Eko Secondary Education Project | Western and Central Africa | Nigeria | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2009 | 2017 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/595921498746982152/text/ICRR0020676-REVISED-PUBLIC-P106280-ICRR-20170707.txt | http://documents.worldbank.org/curated/en/595921498746982152/pdf/ICRR0020676-REVISED-PUBLIC-P106280-ICRR-20170707.pdf | The followinglessons are adapted from the ICR: Thorough project preparation, simple and relevantdesign is crucial to ensure achievement of project objectives. Multiple preparatory studies were undertaken incollaboration with other donors and with the government, ensuring relevance and appropriateness of design and implementationarrangements. This facilitated adequate project implementation and results. Allocating resources through acompetitive funding mechanism (where schools receive funds based on results) can be an effective way to provide discretionaryresources. A decentralized, school-based approach may allow schools to assess their own needs and align funding against aset of activities in their school improvement plans. For the model to be successful, regular and accurate analysis of schoolperformance is required, as well as capacity building, to allow schools to actively participate in thisexercise. A strong ME system is critical to guiding school-level and sector-wide improvements. Inaddition to the introduction of standardized tests at each grade level to measure year on year improvement, it is important tostrengthen the local capacity to ensure close monitoring of school-improvement measures, including teacher attendance andparticipation of School Based Management Committees. Ensuring ownership at all levels is crucial in building up a strong andsustainable ME system. Strong Government ownership is required to ensure sustainability of grants.Strong government commitment to continue support is an important aspect in ensuring that project gains are not lost atclosure.
P106283 | NI Rural Water Supply and Sanitation Project (PRASNICA) | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2008 | 2015 | 2016 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/518501468322482832/text/ICRR-Disclosable-P106283-06-16-2016-1466111888190.txt | http://documents.worldbank.org/curated/en/518501468322482832/pdf/ICRR-Disclosable-P106283-06-16-2016-1466111888190.pdf | The Implementation Completion Report offers five lessons of which the following are the most important (with somereformulation of language): Sustainable access depends on not only building infrastructurebut also strengthening capacity of institutions and communities and engaging communities from thebeginning. WSS service sustainability depends on the quality of infrastructure as well as institutionalcapacity to operate and maintain the infrastructure. In the rural context, a tiered sustainability chain that connects smallcommunities with TA is key to the sustainability of local water committees during their transformation from dependent organizationsto fully operative, self-sustaining micro-enterprises. Sufficient time is needed prior to design to ensure that users understandthe pros, cons and maintenance requirements of each system. Building communities capacity to select systems that areadequate for their needs and reflect their capacity to operate and maintain the systems increases the likelihood of sustainability.In addition, including a social commitment fee prior to implementation ensures communities have the capacity to pay for the systemsand builds their commitment to the implementation of theworks. Harmonized approach to donor investments helpssynchronize investments, facilitating implementation and maximizing overall results. When a sector relies heavily on donorfinancing, it is critical that sector agencies have tools to align and guide investments to ensure the investments support theagencies vision for the sector, investments are complementary and synergies are explored. The sector wide implementationmanual developed by the project (MEPAS), coupled with regular donor meetings have been key to streamlining donor investments andensuring a certain degree of quality for all RWSS works. Flexible procurementprocedures that can be adapted to the local context proves important for rural water and sanitation projects that generally involvesmall-scale and decentralized interventions, often implemented in low-developed areas where access to markets therefore contractorsare limited. During the implementation of the project, the local consulting firms contracted for the preparation ofdesigns and social assistance did not have the qualifications to apply and carry out for these type of activity in such remoteareas, and international firms did not express the level of interest expected at design. A similar problem was found in thecontracting of works. Evolving approaches (such as the use of social facilitators hired as individual consultants and increased CDDceiling for works) were key to adapt traditional Bank procedures to the rural Nicaraguancontext.This Review finds that:Monitoring and evaluation ofsustainability of water and sanitation projects necessitates designing and monitoring specific outcome and intermediate outcomeindicators on different aspects of sustainability (institutional, financial and environmental), as well as inclusion of indicatorsto measure quality, adequacy, safety and affordability of the systems. The ME system need to include beneficiarylevel assessments to evaluate and report on the beneficiary level satisfaction, utilization, behavior change andaffordability.
P106284 | Turkey Land Registration and Cadastre Modernization Project | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2008 | 2023 | 2024 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099051724144531054/text/P1062841b1cf8c029193f61686219442bcc.txt | http://documents.worldbank.org/curated/en/099051724144531054/pdf/P1062841b1cf8c029193f61686219442bcc.pdf | The following lessons were derived from the ICR (ICR, pages 28-29):1. The World Bank can takeadvantage of the IPF and AF tools for land sector reforms that take a long time to ensure outcomes and sustained client engagementand dialogue. Land sector reform takes long periods of time to ensure successful outcomes. The reforms implemented by theProject took fifteen years. The success of the Project relied on continued collaboration between TKGM and the World Bank, enabledby a combination of extensions of the closing date of the original loan and the AF. The lifting of the three-year implementationrequirement for AFs was a key factor in the World Banks ability to leverage this operational tool and to strengthenlong-term cooperation on land sector reform, particularly for countries that are transitioning from analogue systems to digitalones.2. Investment project financing (IPF) can be an important tool for continued policy dialogue. IPFscan act as a platform for advocating policy solutions. The Projects property valuation activities were considered novel in2008, but also a means to identify ways to address taxation and registration revenue shortfalls in Trkiye, and discussionsconcerning how to address property valuation challenges in Trkiye may not have occurred without the Projects focus onthis issue. Moreover, the World Banks continuous engagement with TKGM, along with broader stakeholder consultations, helpedto develop the policy options reflected in the draft valuation policy and the establishment of TKGMs Property ValuationDepartment in 2019.3. Private sector participation can provide a strong signal of an advanced public sectorreform. The involvement of the private sector can provide a strong signal that the public sector is capable of contractdevelopment and management, as well as transparency and accountability. Private sector participation was a major success factor forthe overall reform of Trkiyes land administration system. Nearly the entire cadastre modernization process, includingcadastre renovation and digitization, was carried out by the private sector based on clear procedures, as specified in contractsbut with a comprehensive quality assurance program carried out by TKGMa major lesson for many countries. In general,countries that procure services from the private sector for land administration reform tend to reap financial, managerial, andtechnological benefits.4. Continuous learning can provide an opportunity to open a discussion on theneeded changes to the agency mandates. A continuous learning model can provide many examples of howcadastral data can be used and what human and technical capacities are required to maximize the benefits. TKGM recognized that itsstaff had to go through routine training to achieve the agencys vision, mission, and strategic goals. The concept ofcontinuous learning was also instrumental in helping TKGM identify how its cadastral data, once it was fullymodernized, could be utilized by other agencies. This offers a good example for other land agencies that are defining theirstrategic goals and roles in public administration mechanisms.5. The use of career staff with strong technicalcapacities by an implementing agency can be a major factor in the success of a Project. TKGM utilized internal staff tomanage Project activities, resulting in highly reduced costs for Project management. Nearly all of the staff continued to work onthe Project throughout its fifteen-year implementation. This lesson may help the World Bank to consider medium- to longer-termbuilding of in-house capacities of Implementing Agencies that new projects can use.
P106332 | Bangladesh Disability and Children at Risk | South Asia | Bangladesh | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2009 | 2016 | 2019 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/978591538149530707/text/Bangladesh-BD-Disability-and-Children-at-Risk.txt | http://documents.worldbank.org/curated/en/978591538149530707/pdf/Bangladesh-BD-Disability-and-Children-at-Risk.pdf | The ICR (pp. 30-31) offered insightful lessons emerging from the projects experience,including:Investment of adequate time and resources in quality at entry facilitates smooth implementation,especially for projects that are first-of-a-kind, or the first project in a portfolio of a given global practice. In this case,insufficient attention to capacity issues of the implementing agency and political economy analysis led to slow implementation inthe projects early years and ultimately the need for significant restructuring.Complexity of projectdesign is most prudently matched with the capacity of the implementing agency. In this case, initial design was not tailored to thecontext of a very complex challenge in combination with very low-capacity implementing agencies. Subsequent restructurings were allan exercise in simplification and streamlining of the design (ICR, p. 30).Investments in political economyanalysis can pay off. In this case, with an election upcoming just after appraisal, it is possible that signs of changes inthe governments stance on social welfare policy could have been anticipated (ICR, p. 30) and taken into account in projectdesign.
P106355 | Competitiveness and Private Sector Development | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Other | Trade & Competitiveness | IDA | IPF | 2009 | 2016 | 2017 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/745221475172573956/text/ICRR-Disclosable-P106355-09-29-2016-1475172557318.txt | http://documents.worldbank.org/curated/en/745221475172573956/pdf/ICRR-Disclosable-P106355-09-29-2016-1475172557318.pdf | The first three lessons are drawn from the ICR, with some adaptation (ICR, pages 27-28), the next two, from IEG.One, the successful implementation of the matching grant program in Mozambique offers several valuable lessons for future Bankmatching grant programs elsewhere: (a) the first-come-first-served approach to grant making works best over thewindow approach in the late stage of the program when demand exceeds the available funds; (b) vetting a roster ofbusiness development service providers helps ensure that only qualified providers are selected and quality services are provided;(c) having a sufficient number of business advisers enables a program to offer coaching and mentoring services; (d) adequateresources should be allocated for field work and due diligence functions; and, (e) impact surveys are valuable to improve programdesign.Two, harmonizing the Banks fiduciary requirements with a borrowers fiduciary practices will aidproject implementation. Differences between the Banks and the Governments (the Mozambique AdministrativeCourts) legal requirements and operational procedures for the approval of procurement actions, including the clearance ofcontracts, stalled the implementation of the project. The project was burdened with complying with two different setsof procurement rules and procedures.Further analysis showed thatthe same problem plagued other Bank operations inMozambique.Three, actively engaging other development partners and donors yields incremental benefits. Thecontribution of the project to improving the business environment in Mozambique was greater than originally envisioned because ofthe provision by Irish Aid of parallel funding to the project, and by the IFC, of complementary technical assistance to theGovernment. The partnerships helped build the network of One-Stop-Shops, including the electronic One-Stop-Shop (e-BAU), whichoffered a range of services to help entrepreneurs start a business.Four, the beneficiary profile of a project needsto be reviewed at mid-term to ensure consistency with project goals. Firms benefitting from the matching grant program were largelycommercial and service enterprises (59 percent), based in Maputo (67 percent), and male-owned (73 percent). A review of thebeneficiary profile at mid-term may have helped intensify efforts to target firms that were engaged in agro-processing andindustry, located in poorer provinces, and women-owned or women-led.And five, both project design and projectimplementation have to be carefully executed.Works on the demonstration farm for the Nampula Fruits Training Center hadstarted. The site lacked water for irrigation; a new site had to be secured. The Project Implementation Unit paid little attentionto movements in the SDR/USD exchange rate,and did not provide a suffcientallowance between contract commitments andfund balances. The project ended with a financing gap of US$1 million at the closing date. The gap was readily coveredbut, together with the unfinished work in the Inhambane Tourism Training Center and in the Nampula Fruits Training Center, wasanother problem to worry about as theproject closing date approached.
P106369 | Regional Communications Infrastructure Program (Phase 2) - Rwanda Project | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Infrastructure | Transport | IDA | IPF | 2009 | 2016 | 2016 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/106481468005416804/text/ICRR-Disclosable-P106369-06-10-2016-1465564273314.txt | http://documents.worldbank.org/curated/en/106481468005416804/pdf/ICRR-Disclosable-P106369-06-10-2016-1465564273314.pdf | The ICR draws the following main lessons from implementing this project.(1). The standards for key results indicatorsfor the ICT projects needs to be reexamined on a regular basis. Given the rapidly changing nature of the ICT sector, projectteams and implementation units needto closely monitor the achievement of indicators andperiodically check theirvalidity and amend them as necessary to reflect the reality of the ICT sector at the time.(2) When considering theexpansion of Wi-Fi networks for educational and other institutions, it is important to consider the nature of the demand. Itis also important to assess if there is adequate broadband access, including links to the fiber networks, for institutions that areeither equipped with Wi-Fi connections or supported with ICT equipment such as laptops. In the case of this project, certainbeneficiary institutions that received laptops through the projects were not provided with broadband access at projectclosure.
P106384 | Statistical Capacity Building-Change and Reform for the Development of Statistics (STATCAP-CERDAS) | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2011 | 2017 | 2018 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/289711524598851726/text/Indonesia-Strengthening-Indonesian-Statistics.txt | http://documents.worldbank.org/curated/en/289711524598851726/pdf/Indonesia-Strengthening-Indonesian-Statistics.pdf | The following priority lessons have beenidentified and reworded by IEG based on those provided in theICR:Sequencing long-term reform. Recognizing that public sector reform projects are long-term processes,a phased approach might deliver visible incremental results throughout project implementation to sustain reform momentum. A seriesof short-term goals or quick-wins could be included in project design, rather than relying on an approach that produces visibleresults only toward the end of a long reform process. In STATCAP-CERDAS, changes in government and agencyleadershiphampered outcomes and focus on reform.Planning for complex ICT procurement. Prerequisitepreparation requirements and enabling conditions need to be in place before starting the procurement process. ICTtransformation is often a key component of public sector reform projects, but the procurement of complex ICT requires bothspecialized knowledge and competency in procurement. The World Bank team should give greater attention to ensuring technicaland institutional readiness by the project implementing agency. In addition,exploring the possibility of drawing therequired technical and procurement expertise from specialized departments tht understand the national peculiarities of procurementwould have been helpful in this instance.Targeting niche markets. Capacity-building projectsfor specialized agencies, such as NSOs, face common challenges such as weak responses to REOIs and weak consultants, caused byinsufficiently developed markets for specialized technical skills. Implementing agencies should conduct active scans of relevantmarkets to identify the best consultants, individuals, and firms and proactively inform them of business opportunities under theproject. World Bank supervision teams can help by providing information on consultants successfully used in other similar WorldBank projects.
P106390 | Sao Paulo Metro Line 4 (PHASE 2) | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/622791553271770166/text/Brazil-BR-SP-METRO-LINE-4-PHASE-2.txt | http://documents.worldbank.org/curated/en/622791553271770166/pdf/Brazil-BR-SP-METRO-LINE-4-PHASE-2.pdf | The following lessons are taken from the ICR with some modification by ICRreviewer: Tariff integration iskey to successful multimodal integration. Forthis project which supported physical integration between the metro system and buses, tariff integration was already in place. Thismade it possible for the expected demand to materialize. Without integrated tickets, many potential passengers might have beenreluctant to switch to the metro system since they would have had to pay twofares. Insufficiently stringent working capital or financial guarantee requirements may delayproject implementation. The original civil works contractor under this project experienced cash flow limitations, whichcould have been avoided through morerigorous working capital or financial guarantee requirements in the bidding documents.During the rebiddingwhen only small construction companies with limited cash flows were available because of theLava Jato investigations,a condition was added whereby the winning company had to present a strongerfinancial guarantee, with 10 percent of the total contract valueavailablebycontractsigning. Procurement forlarge and complex civil works that is based mainlyonbasic/ prelimnaryengineering designs may cause important implementation delays.The decision to carryout the procurement of the civil works based on the basic engineering designs since the detailed designs were not yet ready,together with the choice of using a unit price model, led to major bottlenecks during project implementation. Thiswas due notonly to thedelay in finalizing of the detailed designs, but also due tocontract modifications, resulting in lengthy andcomplex control and approval processes. Bundling the preparation of the detailed designs with the civil works contract can beabetter alternative, as the contracted construction company has the right incentive to ensure their timely completion.Advanced designs are needed insuch cases.
P106424 | Efficient lighting and appliances | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2011 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/959221472852941772/text/ICRR-Disclosable-P106424-09-02-2016-1472852934950.txt | http://documents.worldbank.org/curated/en/959221472852941772/pdf/ICRR-Disclosable-P106424-09-02-2016-1472852934950.pdf | The ICR (pages 24-26) draws six lessons from implementing this project. The four main lessons are as follows(1)Strong government commitment can considerably improveprospects for achieving the project developmentobjective. In the case of this project, even beforeproject preparation, Mexico had already developed a nationalstrategy which laid the groundwork for implementingenergy efficiency and climate change investment program andhad takenthe essential policy and institutional steps to achieve programgoals.(2) A full package of Bank financinginstruments at design can aid in successful implementation. In the case of this project, the design included acombination of features including financial, institutional and proportional instruments for addressing barriers to adopting energyefficiency measures. The design incorporated incentives to low income households through concessional financing.(3)Promotional campaigns can beeffective in National Energy Efficiency Programs. An active and sustainedpromotional program in building awareness of the importance of energy savings using the national communications media inconjunction with household to household consumer visits by appliance suppliersproved to be effective inbringing about achange in the way Mexicos population consumed energy.(4) Innovativeprocurement strategy can aid inmaking more efficient use of IBRD resources. In the case of this project, the awarded contractor was responsible notonly for supplying CFLs but also for distributing them through major retail stores, collecting and disposing the replacedIBs.This approach allowed bidders to benefit from economies of scale.
P106443 | PH-Support for Basic Ed. Sector Reform | East Asia and Pacific | Philippines | IBRD | Non-FCS | Human Development | Education | RETF | IPF | 2008 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/243691475116675393/text/000012394-20150309143432.txt | http://documents.worldbank.org/curated/en/243691475116675393/pdf/000012394-20150309143432.pdf | Lessons from the ICR: Institutionalization of reforms requires a long-term commitment on the part of government and the donor community to support the reform agenda. (ICR, p. 27)Lack of a fully functioning financial management system can handicap project performance by creating a range of financial reporting and audit problems. As demonstrated by this project, strong financial management systems are critical for ensuring the efficient use and accounting of resources. (ICR, p. 27)Lessons from the ICR, adapted by IEG: As this project demonstrates, implementation can benefit from concurrent analytical work when: (i) the issues for advancing the reform agenda are clearly defined; (ii) the institutional arrangements for discussing the results are agreed on; and (iii) broad participation by the different constituencies legitimizes the decisions reached.Lessons from IEG: Equity is often included in the PDO of basic education projects but is rarely adequately measured. As this project demonstrates, the lack of a specific indicator for PDO 2 (equity in learning outcomes) and the resulting absence of data to measure it were significant weaknesses in implementing and subsequently evaluating the project.
P106443 | PH-Support for Basic Ed. Sector Reform | East Asia and Pacific | Philippines | IBRD | Non-FCS | Human Development | Education | RETF | IPF | 2008 | 2014 | 2018 | PPAR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/764931528917588989/text/117900-PPAR-P163932-P163933-P094063-P106443-PUBLIC.txt | http://documents.worldbank.org/curated/en/764931528917588989/pdf/117900-PPAR-P163932-P163933-P094063-P106443-PUBLIC.pdf | 5. Common Lessons 5.1 Project and overall reform program achievements can be assessed and confirmed only through appropriate and relevant results frameworks. Careful consideration should be given to ensuring that a project's results framework is coherent, its objectives well defined, its theory of change well specified, and its indicators wellconceived to measure achievement of objectives. In this case, the lack of precision around the equity objective complicated assessment of achievement. Use of BESRA indicators may have been supplemented usefully with project-specific output and outcome indicators to flesh out the logic behind attribution. 5.2 Broadly defined interventions like SBM are conceptualized and implemented differently in different contexts, heightening the importance of country-specific analysis to explain the mechanisms at work in each intervention. In-depth evaluation of pilots to understand the level, degree, and types of autonomy and community participation achievable and realized, as well as the specific benefits to social efficiency and accountability and equity-related risks associated with various SBM designs, can illuminate important details and frame their generalizability. 5.3 The World Bank can play an important role in leveraging and implementing funds from development partners, but careful attention to implementation systems is warranted when these partnerships are conceived. In this case, challenges surrounding the harmonization of procurement and financial management systems led to inefficiencies and delays that jeopardized project efficiency. 5.4 A technical assistance project implemented in parallel with a major program supported by the World Bank can achieve important benefits. In this case, SPHERE provided resources to operationalize both NPSBE and BESRA and to fill identified gaps, achieving meaningful synergies.
P106445 | Health Equity and Performance Improvement Project | Latin America and Caribbean | Panama | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2009 | 2015 | 2016 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/201761467986334710/text/ICRR14787-P106445-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/201761467986334710/pdf/ICRR14787-P106445-Box393191B-PUBLIC.pdf | Lessons drawn from the ICR (pp. 23-25) are: Low cost recovery rates can negatively affect provider behavior under capitation. Capitation amounts should undergo regional adjustments based on thorough cost analysis. In this case, the original capitation amount was much too low compared to unit costs, and had to be adjusted twice. Delays in manual reporting jeopardize the payment process and contribute to substantial administrative burdens and to delivery suspension. Verification systems must be lean and efficient and set up before RBF payments are made. Contracting private providers can be a successful strategy to reach rural populations. Private providers contracted by the MOH under this project performed considerably better then public health care providers.Processes, roles and responsibilities should be clearly identified in complex payment and reporting systems. Procedures should be kept simple and use modern management systems to keep administrative costs low.
P106445 | Health Equity and Performance Improvement Project | Latin America and Caribbean | Panama | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2009 | 2015 | 2018 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/340911499270013440/text/110617-PPAR-P098328-P106445-PUBLIC.txt | http://documents.worldbank.org/curated/en/340911499270013440/pdf/110617-PPAR-P098328-P106445-PUBLIC.pdf | 4. Lessons 4.1 Chapters 2 and 3 have documented the implementation of the two projects that supported strategies to stimulate human capital accumulation and expand access to basic health services in rural and indigenous communities through CCT and PBF. A joint look at these two programs reveals lessons that could help improve future World Bank operations. 4.2 Attention to possible synergies across interventions within a World Bankâ€“financed project and across two or more World Bankâ€“financed projects when they are being implemented in the same place at the same time can be beneficial. In this case, achievement of such synergies was plausible, for example, through the integration of the management information systems (MISs) of the RO/Social Protection and HEPI projects. The RO MIS makes available a registry of program beneficiaries that may also serve as the basis for an integrated registry of beneficiaries for social programs across the country. The integration of the RO and EEC MIS could have allowed for updating of the RO beneficiary roster using information on household composition collected by the mobile health teams, and the prioritization of RO expansion in communities where utilization of health services is suboptimal among the poor. However, these synergies did not materialize in Panama, indicating that opportunities for improvements in efficacy and efficiency may have been missed. 4.3 To ensure adequate provision of basic health services, the supporting PHC network, including public clinics and hospitals, needs to be strengthened. Mobile health teams cannot provide the whole range of health services that are critical to reducing maternal and child mortality (Kuruvilla et al. 2014). Thus, as recognized in the original design of the HEPI project, it is necessary to strengthen the entire PHC network, which includes the public clinics and hospitals that serve these vulnerable populations, but this was not accomplished in Panama. 4.4 The use of short-term contracts by private health providers can have negative impacts on turnover. The contractual terms offered to private providers of the basic health package (PAISS and PAISS+N) were for one year (renewable to up to four years). In turn, private providers offered short-term contracts (usually for 6 months) to the doctors, nurses, technicians and drivers comprising the mobile health teams. These short-term contracts led to very high staff turnover, which in turn became an extra burden for the regional governments as they had to provide all the training for newly appointed staff. 4.5 Verification systems need to be lean and efficient and set up before RBF payments are made. Processes, roles, and responsibilities, especially in complex RBF payment and reporting systems, need to be clearly identified upfront and kept at a minimum. Modern management systems and technological solutions should be identified beforehand and used to reduce administration costs and avoid potential delays. Unfortunately, the specific operational aspects of the PBF scheme in the HEPI project, including its payment and verification mechanisms, were not fully defined before starting implementation. In particular, the role of the DRSs in verifying and authorizing payments to mobile health teams created bottlenecks and delays that affected the provision of health services. 4.6 Successful impact evaluations require both technical capacity and commitment from the government side and technical support from the World Bank. The impact evaluations envisaged in the Social Protection and the HEPI programs were complex. They required the collection of primary data using household surveys at baseline and at endpoint, and maintaining a clear distinction between those that received the interventions and those that did not. However, the initial delays in contracting the firms to conduct the impact evaluations and the change in government following the presidential election reduced the buy-in from the counterpart in charge of decisions regarding the expansion of the programs, thus reducing the feasibility and quality of the evaluation.
P106449 | Emergency Recovery and Disaster Management | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2008 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/495551475093273232/text/000012394-20150409083316.txt | http://documents.worldbank.org/curated/en/495551475093273232/pdf/000012394-20150409083316.pdf | The following lessons are selected from the ICR:Infrastructure sub projects could be bundled to optimize project impact. For example, a rural settlement that benefited from bundled project investments (rehabilitated primary school complex, a rebuilt access road, and improved potable water infrastructure) attracted families from nearby farms to send their children to its school, transforming livelihood dynamics in the host settlement. DRM awareness at community level contributes to ownership and sustainability. When beneficiaries participate in crucial decision making and supervisory functions over the projects, they become better informed, more engaged, and likely to demand continued government attention.
P106458 | Economic Management and Governance Reform Grant | Western and Central Africa | Central African Republic | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2009 | 2010 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/151631474483837540/text/000020051-20140620074046.txt | http://documents.worldbank.org/curated/en/151631474483837540/pdf/000020051-20140620074046.pdf | The ICR draws some useful lessons. Salient among them for post-conflict countries is:the importance of sharply focused and well-sequenced DPLs, accompanied with technical assistance, for restoring government effectiveness; and close donor coordination, preferably using the same support instruments, for predicting aid flows and facilitating the administration of donor support.
P106468 | Sao Tome Public and Natural Resource Management Development Policy Grant | Eastern and Southern Africa | Sao Tome and Principe | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2010 | 2012 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/405231475101362080/text/000020051-20140624195540.txt | http://documents.worldbank.org/curated/en/405231475101362080/pdf/000020051-20140624195540.pdf | IEG agrees the ICRR's five lessons from this operation: (a) Parallel technical assistance projects can contribute to improving institutional capacity; (b) Operations in fragile states should incorporate adequate M (c) Complexities of new financial system software should not be underestimated; (d) Need to provide adequate funding for supervision; and (e)Donor coordination should be strengthened.
P106489 | Lebanon Emergency Social Protection Implementation Support Grant | Middle East and North Africa | Lebanon | IBRD |  | Human Development | Social Protection & Jobs | SPF | IPF | 2008 |  | 2013 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/496961474631548739/text/000020051-20140625184649.txt | http://documents.worldbank.org/curated/en/496961474631548739/pdf/000020051-20140625184649.pdf | The following main lessons were drawn from the ICR:Governance issues need to be assessed as potentially significant risk factors . Opposition by the National Social Security Fund board made implementation of the Project difficult, and is now threatening results under a follow-up project. While projects may be providing important, and even desirable, services, outcomes cannot be achieved, or can be achieved only partly and not necessarily satisfactorily, unless potential governance issues are recognized, and the risks to project outcomes determined and appropriately addressed. The complexity of the political environment for decision making should not be underestimated, especially in a post-conflict environment. Simply because a piece of policy reform is in the national interest, does not mean that it will be implemented. In Lebanon, the confessional system of governance (i.e. based on religious affiliation) and the resulting diffusion of political authority make reforms subject to collective action, and such collective action is not easy, especially in an environment that has gone through significant upheaval.
P106502 | POVERTY REDUCTION SUPPORT CREDIT IV | Western and Central Africa | Cabo Verde | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2009 | 2010 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/185691474396389529/text/000146597-20140619165028.txt | http://documents.worldbank.org/curated/en/185691474396389529/pdf/000146597-20140619165028.pdf | The ICR draws useful findings and lessons from PRSC 4's experience. Of special note are: the important role played by the donor budget support group in unifying dialogue with the government and harmonizing aid flows; andthe need to focus on improving M&E implementation and utilization. In addition, IEG notes that time-bound conditionality that relies on the political process for completion is vulnerable to delays.
P106528 | MX Results-based Management and Budgeting | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2009 | 2014 | 2015 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/155281468001178947/text/ICRR14681-P106528-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/155281468001178947/pdf/ICRR14681-P106528-Box393183B-PUBLIC.pdf | Some of the lessons derived by IEG based on the review of the ICR include:The Bank needs to carefully assess the choice of instruments in middle-income countries, which may not need financial support as much as the Bank's technical expertise. The Bank needs to learn from its experience in middle-income countries with more sophisticated demands for expertise and technical assistance and use this experience to inform its operations in other countries in the region. As mentioned by the project team, the Mexican experience is more likely to be seen as relevant by regional countries than experiences from more developed OECD countries like Canada or Switzerland. Project design needs to align and adopt with institutional capacity, particularly when there is a massive reform process at stake that involves multiple government agencies and donors. There is also need for better assessments of needs and risks associated with complex reform projects and projects involving multiple implementing agencies.
P106589 | Information Technology Development | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2009 | 2016 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/254811480469144188/text/1480469142630-0000A8056-ICRR-Disclosable-P106589-11-29-2016-1480469132178.txt | http://documents.worldbank.org/curated/en/254811480469144188/pdf/1480469142630-0000A8056-ICRR-Disclosable-P106589-11-29-2016-1480469132178.pdf | The ICR draws the following main lessons from implementing this project.(1) Mechanisms for strong privatesector involvement throughout the entire project cycle can be very useful ICT projects. In the case of this project,active participation of private sector stakeholders at preparation enabled a comprehensive project design that took into accountindustry needs.Likewise, the project benefited from active involvement of industry chambers, association and academia,particularly during MTR and the first restructuring of the project which resulted in revising the indicators.(2)The IT/ITES sector relies on the availability of a talent pool that is conversant with English language. Inthe case of this project, althoughEnglish skills was not envisaged at project design, it was identified as key for exportingIT services during implementation. This necessitated a component of capacity building for imparting English languageskills.(3) A tailored capacity building for procurementfor stakeholders can alleviate procurement delays,especially if capacity is build at early stages. In the case of this project with a various stakeholders,organizations such as the IT chambers although familiar with Government procurement process had limited knowledgeof Bank procedures and this contributed to delays in the early years of the project
P106596 | ROAD REHABILITATION AND MAINTENANCE PROJECT PHASE II | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2010 | 2016 | 2017 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/133571493655451724/text/ICRR-Disclosable-P106596-05-01-2017-1493655434907.txt | http://documents.worldbank.org/curated/en/133571493655451724/pdf/ICRR-Disclosable-P106596-05-01-2017-1493655434907.pdf | The ICR (pages 25 to 27) draws the following main lessons from implementing this project.(1) Project designneeds to bemore realistic in its strategic objectives, in particular institutional reform and capacities andconsistent with allocated time and project capacity and available capacity.The experience of this project showedthat newly established institutions or agencies require more time than unanticipated for transition.Further, even though theproject aimed atinstitutional strengthening of the implementing agencies, thefinancial support provided by the projectaccounted for only2% of the total project cost, while infrastructure investments accounted for the balance.The lowallocation for the institutional dimension did not provide the necessary support for institutional reforms.(2)Successive, long-term Adaptable Program Loans (APLs) may not always be a practical instrument to deliver a program with a largecivil works component. In the case of this project, theRoad Sector Rehabilitation and Maintenance Project (RRMP)wasdesigned to be a ten year APL program to be implemented in three consecutive phases, as long as the required triggers weresatisfied.However, the implementation of phase I of this projecttook 10 years (as compared to the original estimate ofthree years) and phase II was implemented in six and half years as compared to the original estimate of fouryears.Phase III was dropped during the implementation of Phase II. While the long term nature of the APL could bean effective tool for deepening sector reforms, the experience of this project showed that as it took a long time to implement,it may not have been a practical instrument for RRMP II which focused on infrastructure investmentactivities.(3) Successful implementation of a road safety agency needs full politicalcommitment. In recognition of the global concern and growing demand for improved road safety in the road sector,sound road safety policies androad safety action plans tailored to the needs of the country are required and this likely torequire coordination between various ministries (such as, transport, planning, health andeducation), police andimplementation agencies.In the case of this project, although road safety agency was one of the PDOs, it was framed as a small part of the project without providing significant reform measures to fully implement this importantobjective.(4) A robust but clear ME framework that is well aligned with the PDO helps in monitoring andmeasuring the outcomes/outputs of the project activities. Although developing a robust ME framework can be achallenging task for transport projects, given that the project benefits are diverse and realized in different time frames, arobust ME can help in designing the project to respond to its development objectives.
P106603 | Road Asset Management Project | East Asia and Pacific | Cambodia | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2008 | 2015 | 2016 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/340071467989511513/text/ICRR14907-ICRR-PUBLIC-P106603-Box306265B.txt | http://documents.worldbank.org/curated/en/340071467989511513/pdf/ICRR14907-ICRR-PUBLIC-P106603-Box306265B.pdf | Selected lessons from the ICR:Use of temporary, parallel systems does little to create lasting and durable improvements and/or change. The Independent Procurement Agent bypassed MPWT and the national system for carrying out procurement, and thus represents a missed opportunity to build procurement capacity within the Ministry.For M&E frameworks to be useful beyond the project, the framework needs to employ indicators that are not just associated with the achievements associated wit ha particular project but also relevant to decision makers for planning and management decisions.
P106605 | Higher Education Quality and Capacity Improvement Project | East Asia and Pacific | Cambodia | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2011 | 2018 | 2019 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Highly Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/866191534973866726/text/Cambodia-KH-HE-Quality-and-Capacity-Improve-Proj.txt | http://documents.worldbank.org/curated/en/866191534973866726/pdf/Cambodia-KH-HE-Quality-and-Capacity-Improve-Proj.pdf | The ICR lists six lessons (p. 34). Important among these are the following:1. Peer partnershipsand networks are effective in improving the quality of professional performance. The project activities have led to thecreation of the Cambodia Society for Research and Development. This research community, through the practice of peer review, isexpected to contribute to promoting rigor and relevance in the performance of higher educationprofessionals.2. Forging long-term relations withhigher educationinstitutionsoverseas can reduce training and capacity development costs as well as offer sustainable ways ofproviding consistent capacity development opportunities. The project led to increased professional connections andlong-term partnership agreements with universities in Australia that include, among other things, grants to fund Cambodianstudents.3. Research is essential if Cambodia is to achieve success in engaging with globalknowledge networks and training its own postgraduate research students. Engaging with global knowledge networks requiresexchanging research products, and students are better trained through the hands-on experience that research projectsprovide.IEG concurs with these lessons and adds another one:4.Migration of higher education graduates can pose a risk to the development and sustainability of higher education systems in lowerlower-middle-income economies such as Cambodia. A recent Asian Development Bank report noted that brain drain is a sourceof ongoing concern for members of the Association of Southeast Asian Nations. For this reason, strategies that aim to develophigher education systems in such countries should include mitigation measures that include: (i) approaches for minimizing migrationoutflows, and (ii) approaches for using the skills and experience of emigrant academics and high-skilled workers.
P106619 | Health Sector Reform Second Phase APL (PARSS 2) | Latin America and Caribbean | Dominican Republic | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2010 | 2016 | 2017 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | High | http://documents.worldbank.org/curated/en/389491483050118699/text/ICRR-Disclosable-P106619-12-29-2016-1483050105345.txt | http://documents.worldbank.org/curated/en/389491483050118699/pdf/ICRR-Disclosable-P106619-12-29-2016-1483050105345.pdf | The ICR (pp. 29-31) presents lessons learned, including the following (adapted by IEG): Duringproject preparation, the feasibility of financial contributions by the counterpart needs to be carefully evaluated. In thisproject, the government could not make the contribution that was originallypromised, leading to implementation delays untilthe Bank increased its share of project financing. Results Based Financing is a powerful mechanism to improve the qualityof health care service provision. However, it can also create resistance, since the mechanism puts more responsibility on healthstaff. Therefore, communication and availability of information on potential benefits is critical. In this project, resistancetowards the newfinancing mechanismdiminished once the benefits materialized. When using two differentimplementing agencies, it is critical to ensure close coordination and take advantage of synergies to avoid duplication ofactivities and hiring of new staff resulting in higher operational costs. In this project, the PCU faced high operating costs dueto staffing and vehicles used.
P106621 | HT - MEETING TEACHER NEEDS FOR EFA | Latin America and Caribbean | Haiti | IDA | FCS | Human Development | Education | IDA | IPF | 2008 | 2012 | 2014 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/875781474483139121/text/000020051-20140626001219.txt | http://documents.worldbank.org/curated/en/875781474483139121/pdf/000020051-20140626001219.pdf | The ICR (p. 15) provided several lessons, which IEG has synthesized as follows:Accelerated teacher training can be effective when there is an undersupply of teachers. This program was found to be effective because student-teachers were in the classroom one year after pedagogical training. The program required candidates to be high school graduates and pass an examination, but would have been more effective if the training had been coordinated with the academic year. To be able to recruit, maintain, and motivate student-teachers in an accelerated teacher program, stipends were needed. Failure to disburse the stipend demoralized and disillusioned the student-teachers and jeopardized the teaching program. The Bank needs to ensure that timely payments are made. The follow-up project has utilized progressive implementation of stipends (e.g. no stipend in the training year, one-half stipend during the first year of student-teaching, and full stipend during the second year of student-teaching), which partially takes account of the fiscal constraints. The Borrower also provided several lessons, which IEG has synthesized as follows:Time and effort spent on seeking a consensus between the stakeholders is not wasted. In the Haitian education sector, any innovation quickly arouses suspicions and is met with significant resistance. An understanding of the causes of this resistance and the issues faced by the different stakeholders is needed to improve project outcomes. Projects need to be spearheaded by the public sector with the aim of strengthening the country's institutions in the long term. There is a high level of incompetence in the public sector, but this should not lead to the creation of parallel project management structures. The relationship between consultants and civil servants in this project was troubled, due to the fees earned by the consultants in comparison to civil servants' salaries. Bonuses for civil servants involved in projects are being evaluated.
P106622 | Jamaica Second HIV/AIDS Project | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2008 | 2013 | 2014 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/174961474904639674/text/000020051-20140626121744.txt | http://documents.worldbank.org/curated/en/174961474904639674/pdf/000020051-20140626121744.pdf | This project confirmed several lessons already learned from previous Bank-financed HIV/AIDS projects. The ICR (p. 18) highlights five main lessons:Behavior change is difficult to induce. It takes more time than a project's lifetime, particularly in countries like Jamaica with a complex socio-cultural environment, as demonstrated by stigma and discrimination and permanence of false beliefs on HIV transmission.Strong leadership at the highest governmental level is key for the success of a multi-sectoral project.There is a need for a technically sound and adequately funded national HIV/AIDS plan, agreed to by all parties involved and cost-efficiently implemented.The Bankâ€™s fiduciary rules should be adapted to take into account the small size of a country such as Jamaica, because small size makes bidding unattractive.A sustainability plan should be developed early during project implementation.IEG stresses the following three lessons:The most effective prevention intervention against HIV/AIDS is provision of ARVs. However, this is not the most cost-effective measure, because ARVs are still very costly.This means that prevention (education and behavior change) remains the most cost-effective action. However, prevention needs to be targeted to high-risk groups (main conveyors of the HIV virus) and to include comprehensive testing.Financial management and procurement capacity must be addressed during project preparation.
P106623 | Barbados Second HIV/AIDS Project | Latin America and Caribbean | Barbados | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2009 | 2015 | 2016 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/713491468189274927/text/ICRR14795-P106623-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/713491468189274927/pdf/ICRR14795-P106623-Box393191B-PUBLIC.pdf | Lessons from the ICR, adapted by IEG (page 21-22):Cultural constraints can be a barrier in monitoring stigmatized populations. In the case of this project, although the project design relied on civil society organizations to implement activities with key populations at higher risk (men having sex with men and sex workers), there was a lack of broader acceptance to conduct surveillance activities among these populations.When monitoring small population sizes, measuring achievements using actual figures, in addition to or instead of percentages, provides a clearer picture of outcomes. In the case of this project, the targeted population of HIV+pregnant women (denominator) was small, and therefore the failure of just two women to complete treatment significantly affected the overall achievement measured in percentage terms.
P106628 | Consolidation of National Public Management Information Systems | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2010 | 2015 | 2016 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/597941468197979934/text/ICRR14843-P106628-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/597941468197979934/pdf/ICRR14843-P106628-Box394823B-PUBLIC.pdf | The following lessons come from the ICR.Loans do not have to be big to have a big impact. This project shows that projects of high relevance to the government, that have strong implementation arrangements and that apply past lessons from previous operations can produce good results and have a large impact on a governmentâ€™s financial management systems.When the scope of a system with a high proportion of IT investments is unclear, there is a high likelihood that project execution will be delayed and that planned activities have to be redesigned.Thorough and complete risk assessments of a projectâ€™s activities can play a critical role in ensuring that complex activities are carried out successfully.
P106641 | Competitiveness and Public Financial Management DPL 2 | Latin America and Caribbean | Panama | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2009 | 2010 | 2010 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/447711475087990953/text/Panama-First-Competitiveness-And-Public-Financial-Management-Dpl.txt | http://documents.worldbank.org/curated/en/447711475087990953/pdf/Panama-First-Competitiveness-And-Public-Financial-Management-Dpl.pdf | The ICR offers thoughtful lessons with which IEG is in agreement. (1) Strategic plans need to be translated into clear action plans, which include monitorable output indicators to track progress. Without these, there is a lack of coordination and prioritization which leads to inefficiencies and slows down implementation. Beyond this ICR lesson, however, IEG suggests that not only output but also impact indicators are important, since this are important in identifying any needed mid-course corrections. (2) A good M&E framework can be important in developing a case for maintaining a program in shifting political conditions. (3) Adequate Bank Budget resources are important in sustaining a fruitful dialogue with the government.
P106650 | Mauritius Second Development Policy Loan (FY08) | Eastern and Southern Africa | Mauritius | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2008 | 2009 | 2013 | ICRR | >=25 million & <50 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | High | http://documents.worldbank.org/curated/en/713521475098269117/text/000020051-20140625192948.txt | http://documents.worldbank.org/curated/en/713521475098269117/pdf/000020051-20140625192948.pdf | IEG concurs with the ICRâ€™s findings that the success of the reform program in Mauritius was largely due to strong government ownership and a participatory approach which involves all key stakeholders in society. Close coordination with key donors in harmonizing conditionality enabled the government to implement a single comprehensive reform program. An important lesson from Mauritiusâ€™s experience is that the ability to respond to new challenges is essential for successful implementation of the reform program. The program was also sharply focused and internally consistent and therefore easier to implement and monitor.
P106654 | ARTF - Kabul-Aybak/Mazar-e-Sharif Power Project | South Asia | Afghanistan | IDA | FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2008 | 2013 | 2015 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/540091475112843297/text/000180307-20141202141140.txt | http://documents.worldbank.org/curated/en/540091475112843297/pdf/000180307-20141202141140.pdf | The ICR provides the following key lessons: Even when a project is conceived as a follow up to an existing operation, it needs to be appraised thoroughly on a stand-alone basis, so that proper attention can be paid to design issues. Building implementation capacity is as important as investments in physical infrastructure. Infrastructure was rehabilitated under the project, but remained at risk of falling into a build-neglect-rebuild cycle on account of lack of capacity created for operations and maintenance.Results indicators need to be built on a clearly defined results chain, linking inputs to attributable outcomes. In countries with a history of conflict and poor capacity, consideration should be given to use of relative or incremental indicators (e.g. number of households connected and metered).Ensuring adequacy of supervision. Given the importance of on site supervision, which - for this operation - was essential for quick identification (and resolution) of implementation problems, the question is how to ensure this in the midst of deteriorating security conditions in the country, which may make frequent field visits difficult in practice. The use of management agents is one option, but did not work out too well in this project. The answer may lie in simpler design that requires minimal supervision.
P106663 | Sao Paulo Feeder Roads Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2015 | 2016 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/513141467035335609/text/ICRR-Disclosable-P106663-06-27-2016-1467035313957.txt | http://documents.worldbank.org/curated/en/513141467035335609/pdf/ICRR-Disclosable-P106663-06-27-2016-1467035313957.pdf | Two lessons from the ICR are highlighted with some adaptation: There is a need for sufficient lead-time andresources for consensus building on introducing new management systems involving complex procedural changes. Duringthe initial years of this project implementation, the internal deliberations on strategies and goals and definitionofspecificationsfor the management systems took significant time, leading to delays and subsequentextension ofthe project closing date. Sustainability of local road assets could be enhanced throughassistingstate-level institutionsin supporting local governments. Whileworking with state-levelgovernment on implementinga program on rehabilitation of thelocal road network, there is an opportunity to be moreproactively engaged at thelocal level to ensure sustainability ofresults.
P106680 | Second Land Administration Project | Latin America and Caribbean | Honduras | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/536961521833750267/text/Honduras-HN-APL2-Land-Administration.txt | http://documents.worldbank.org/curated/en/536961521833750267/pdf/Honduras-HN-APL2-Land-Administration.pdf | following lessons are taken from the ICR with some adaptation of language.Decentralizationof land administration services needs to be adequately assessed beforehand. Decentralization is complex and is also alengthy and expensive process. An accurate assessment of the Governments capacityis neededto determine theappropriate level of institutional and technical support and assess what progress can be achieved regarding the decentralization ofland services. A series of incremental institutional and technical support activities may be the most appropriate approach. It waslearned that serious consideration should be given to strategically identifying the activities, efforts and timeframe to build thedesired decentralized capacity along with strengthening government institutions and local governments.Setting unrealisticmilestones that depend on measures independent from the project coordinating unit will also place the project atrisk.In order to decrease the waiting time for users to register their land titles, the varyinglevels of institutional capacities (human and technical) in selected municipalities need to be taken into account. Thecapacity ofone municipalitycan beconsiderably different thananothermunicipalityand thecompatibility and additional time it takes to make transactions compatible from one system to another should be taken into account.In this project, some municipalities already had a cadaster that needed to be made compatible with the national cadaster that theproject was establishing at national level with the use of SURE. So some municipalities had significantly more work to do toregister the land titles and the implementing agency had no control over that.A weak implementinginstitution can put the project at risk and place undue responsibility onto the project coordinating unit that, in principle,corresponds to their own mandate. Experience from this project shows that a PCU working with a certain degree of autonomyfrom the land institution is not necessarily beneficial, as it may compromise the government ownership and may affect thesustainability of land projects
P106684 | AR PROSAP2 - Second Provincial Agricultural Development | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2009 | 2017 | 2018 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/957061516292814141/text/ICRR-Disclosable-P106684-01-18-2018-1516292791420.txt | http://documents.worldbank.org/curated/en/957061516292814141/pdf/ICRR-Disclosable-P106684-01-18-2018-1516292791420.pdf | The ICR included six lessons. The following three Lessons are emphasized with some adaptation oflanguage: Operations mixing different scales and levels of intervention need clear justification andconceptualization, realistic estimates of costs and benefits including their distribution, and special attention to the Theory ofChange and Results Framework. Establishing ME systems and practices starts at effectiveness and requires close Banksupervision and collaboration with the coordination unit. Early, high quality baseline development is of paramount importance.Formal restructuring of an unsuitable RF should not necessarily wait for the Mid-term Review. The chain of objectives, theactivities capturing those goals and precisely which farmers are being targeted need to be embedded in a comprehensive set ofappropriate, measurable indicators. Large infrastructure investments need an individual Theory of Change connected to the masterResults Framework (RF). Classes of indicators are needed to measure technology transfer and institutional strengthening as afunction of a systems global efficiency. To ensure proper targeting, the identity andcharacteristics of intended beneficiaries and the distribution of benefits should be analyzed, understood and documented in thePAD. Even in demand-driven projects, it is essential that the targeted beneficiaries be defined, quantified and describedbased on official, current household and geographic data, and that targeting be carefully designed and operationalized. Wherenational or regional databases are thin/non-existent or outdated, projects should consider financing their preparation. Also,projects can generate attractive rates of return, but the distribution of benefits needs close scrutiny. Future operations need toconsider putting a cap on per beneficiary investment cost across investment instruments (which was done for the ANR), withvariations based on the definition/segmentation of the targeted population of producers. Institutionalcapacity building at sub-national levels needs customization to the unique institutional, legal and administrative situations ineach case. This implies significant ex ante analysis and decisions about project expectationsand design rooted in a realistic assessment of the legal and administrative context and incentives. Projects should avoidoverly-standardized training and technical assistance of uneven relevance/utility, adopt both demand and supply-driven approachesand aim for durable change. Also, the constitution of water user consortia is not always appropriate or desirable and should not bean absolute requirement. Project design should not confuse institutional frameworks as fixed by law, and design decisions aboutinstitution-strengthening; the states legal and customary role needs to be understood.
P106685 | AR Socio-Economic Inclusion In Rural Areas | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2015 | 2023 | 2024 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099021324130051938/text/P1066851db18690031b08a15b117e4bac81.txt | http://documents.worldbank.org/curated/en/099021324130051938/pdf/P1066851db18690031b08a15b117e4bac81.pdf | The following lessons are derived from the ICR with some modification of language.Even when targeting ofvulnerable groups is explicitly included in the objectives and the results framework, the desired outcomes may not be achieved ifthose priorities are not mainstreamed in decision making processes at all levels. Many community organizations requestedcapacity strengthening for women and youth and opportunities for them to develop subprojects. The project organized training forthem but left the rest to the provinces, where local priorities ruled. A specific gender sub-indicator included in the frameworkwas not achieved. The seemingly simple step of including representatives of indigenous persons in the provincial evaluationcommittees helped in reaching their targeted share.If the result framework is designed primarily to monitorproject execution and an impact study is depended on for information on outcomes and to link them to outputs, the prospects for acompleted evaluation can be improved if an independent evaluation with a baseline study is commissioned at the beginning of theproject. When project implementation is pushed to the closing date with tightening financial and capacity constraints,doing an evaluation becomes the last priority. The Banks efforts to have a study done were notsuccessful.Wherever provision of technical assistance to individuals or groups of beneficiaries is criticalto a project activity, the prospects of delivering relevant assistance and maintaining it beyond project life may be improved byengaging technical and development organizations that already work with beneficiaries, rather than build the capabilities inproject implementation units. When budgetary limitations were faced, the activities to strengthen beneficiariestechnical capacities were the first to be cut, or delegated to provincial implementing units, which also lacked the requiredtechnical knowledge. Outsourcing technical assistance and training to technical organization (INTA and SAFCI) made it possible toclose the knowledge gap, although the opportunity was missed to engage more local organizations with a presence in the territoryand with contact with local producers. Such linkages could have increased technical support to ensure the development of strongsubprojects and their sustainability after project closing.This review adds another lesson:Where thereare considerable doubts about whether a onetime project support to individuals or groups is adequate to achieve the projectobjective, the chances of success can be improved by considering options to deliver support and monitor outcomes beyond the life ofthe project. Success of this project depends on continued functioning of community organizations, the viability ofwhatever enterprises they are engaged in, and maintained alliances to deliver the project outcomes. Closing the project before theoutcomes are achieved jeopardizes the outcomes as well as the learning.
P106686 | Basic Education Quality Improvement Project | Latin America and Caribbean | Panama | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2009 | 2015 | 2011 | ICRR | Less than 10 million |  | Moderately Unsatisfactory |  | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/718371474854706558/text/000020051-20140624161145.txt | http://documents.worldbank.org/curated/en/718371474854706558/pdf/000020051-20140624161145.pdf | Intercultural bilingual education: Support to intercultural bilingual education in the country has significantly varied across different administrations. Given its importance to ensure that children whose mother tongues are different from the language taught at school can learn as much as others, there is a need for continuous dialogue on its importance and for sharing international experiences on successful programs.Need for more guidance for task teams: In a complex situation, as is the case of a Government transition, there is a need for Bank management involvement at early stages, particularly when decisions and solutions are more political than technical in nature. Monitoring systems included in project design: A monitoring system needs to be simple enough so that it does not become an objective in itself, but rather informs implementing agencies and TTLs about implementation progress. In the case of this project, the idea of including the monitoring and evaluation system into project design was a good one, but its complexity made the design and coordination between different agencies unnecessarily difficult.
P106699 | Haiti - Urban Community Driven Development Project / PRODEPUR | Latin America and Caribbean | Haiti | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2008 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/646821522442473626/text/Haiti-HT-Urban-CDD-PRODEPUR.txt | http://documents.worldbank.org/curated/en/646821522442473626/pdf/Haiti-HT-Urban-CDD-PRODEPUR.pdf | The following lessons were synthesized based on the lessons reported in the ICR (p.31-33) and IEGs ownassessment: Productive subprojects supported by CDD require feasibility studies related to human andfinancial capital, business know-how, including financial literacy,and a conducive enabling environment, includingtechnical assistance. In this project, only 12% of the 131 productive subprojects were still operating after six months,mostly due to inappropriate design and lack of human and financial resources. A main risk to the socio-economic infrastructure thatwas developed by PRODEPUR is sustainability, due to limited ownership of local authorities and lack of human and financialresources for operations and maintenance. Post-disaster housing support must beflexible enough to support the diverse needs of IDPs, who may be renters or property owners, and who have varying degrees ofattachment to their original neighborhoods. The project initially called for reconstruction and rehabilitation support,which is only appropriate for property owners. This had to be completely redesigned once it was realized that 80% of potentialbeneficiaries were renters. Polling also revealed that potential beneficiaries were more willing to move elsewhere than the projecthad originally assumed. Post-disaster investments in public neighborhoodinfrastructure can incentivize private investment in reconstruction. Project experience demonstrated that investments inpublic infrastructure were more effective to stimulate private reconstruction than reconstruction grants. The project wasrestructured to reflect this finding (though concrete evidence was not provided). CDDprojects can set a strong foundation for disaster response efforts. The original CDD activities conducted under PRODEPURallowed communities to rapidly mobilize human and financial resources to respond to the post-earthquake emergency.
P106700 | Agricultural Innovation and Services | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2012 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/833561516650241482/text/ICRR-Disclosable-P106700-01-22-2018-1516650227693.txt | http://documents.worldbank.org/curated/en/833561516650241482/pdf/ICRR-Disclosable-P106700-01-22-2018-1516650227693.pdf | The ICR points to eight lessons learned based on the evidence from project implementation. This Review considered the followinglessons were the most important because of their relevance beyond this project: The World Bank instrumentselected for this project, the Investment Project Financing (IPF)was not the best instrument for promoting the strengtheningof institutions although at the time of appraisal it was the only instrument available. Recent instruments like theDevelopment Policy Framework or Program for Results (P for R)may be better suited because of their focus on buildingcapacities in institutions. Participatory Approaches. Introducing a participatory and bottom up approachto foster innovation in research management requires time, adequate outreach strategy, and clear vision on how to leverageresources through novel alliances. Thesemay cause delays in project implementation and project teams are best served byrecognizing crucial bottlenecksthat could be addressed by heightened capacity building early in theproject. Decentralization of Research. Contracting research to external partners as part of adecentralized approach to engage NGOs and private firms and other non-traditional partners in research activities was potentiallyuseful but required a framework that would allowgovernment to easily transfer funds to non governmentalorganizations. Staffing Challenges. Research institutions (such as the INIAF Institute) whichsupportinnovation systems (like the SNIAF system)depend on retaining highly qualified staff. This objective is bestserved by an autonomous institution (such as the INIAF Institute) that can manage its human resourcesindependently ofpolitical influence.
P106702 | Integrated Solid Waste Management and Carbon Finance Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2011 | 2016 | 2017 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest |  |  | Lessons were selected from the ICR with some adaptation of the language: Aligning incentives andoperational objectives is critical in the development of an operation. Under this project, CAIXAs maininterest in partnering with the Bank on this operation was to have access to World Bank knowledge and technical assistance fordeveloping its CF capacity. A relatively small credit line of IBRD resources, particularly given the extent of CAIXAs ownfinancing resources in the sector, was not in itself a major incentive. Project readiness for implementationis critical. Having a well-defined pipeline of eligible subprojects is essential to allow implementation to beginonce the project is approved. Long delays at the onset of the project while the viability of a pipeline of subprojects is beingevaluated may result in a loss of momentum that may negatively impact the delivery of results. Processoriented intermediate indicators are useful to capture institutional changes and identify bottlenecksin implementation. Indicators reflecting progress (or lack of progress) on critical upstream reforms may send clearersignals to the implementing agency on internal bottlenecks needed to be addressed. Well-coordinated,blended IBRD-CF projects can successfully leverage and complement solid waste management operations. The integrated workof the solid waste and CF teams was one of the most positive design aspects of the operation. Presenting a joint approach toproject implementation underscores the technical and financial advantages of integrating emissions reduction equipment andtechnology from the onset of the project, and allows the inflow of resources early during implementation. Payments for emissionsreductions credits become a critical incentive to accelerate implementation and to more effectively operate landfills in accordanceto CDM technical procedures, as they are proxies for well-managed operations.
P106702 | Integrated Solid Waste Management and Carbon Finance Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2011 | 2016 | 2018 | PPAR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/395271521557013485/text/123798-PPAR-P106702-P124663-P164310-PUBLIC.txt | http://documents.worldbank.org/curated/en/395271521557013485/pdf/123798-PPAR-P106702-P124663-P164310-PUBLIC.pdf | 7. Lessons 7.1 A project with sector-wide objectives must provide for engagement with the government at the policy level to lay a strong basis for achieving development outcomes. This project had a sector-wide focus for solid waste management covering physical investments, institutional strengthening, and encouraging private sector participation. However, engaging primarily with a financial intermediary as the borrower and implementing agency was not sufficient to stimulate interest among municipalities and the private sector, which faced regulatory and institutional issues that need attention at policy-making levels. 7.2 For an operation involving a financial intermediary, a minimum number of sub-projects must be committed at project effectiveness, to demonstrate quick successes and to develop further momentum during implementation. While a list of possible sub-projects had been pre-identified, only the Santa Rosa landfill in Rio de Janeiro was ready for financing, and the others had no specific project designs at project preparation. 7.3 In an upper middle-income country with broad-based financial and institutional resources, the World Bank's interventions in a sector should focus on functional areas with a clear need and demand for external support and expertise. Brazil had significant resources for investing in solid waste management infrastructure. The main needs were capacity building in the implementing municipal governments, and attracting private sector participation, which should have been the focus of World Bank intervention. 7.4 In seeking to attract private sector investment and expertise to public service provision, the major barriers to entry must be clearly recognized and addressed. Incentives at the margin are unlikely to generate wide or sustained interest. The sole privately owned landfill supported to completion by this project (Santa Rosa facility for Rio de Janeiro city) was driven largely by its high public profile. This success could not be replicated in other situations largely because supportive regulation and appropriate incentives (remunerative contracts, tipping fees, and payment guarantees, etc.) are not yet in place for the sector, and carbon finance for landfill gas capture and flaring did not prove to be a significant determining factor.
P106703 | BR Sao Paulo Water Recovery Project - REAGUA | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2010 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/133881517346543350/text/ICRR-Disclosable-P106703-01-30-2018-1517346533127.txt | http://documents.worldbank.org/curated/en/133881517346543350/pdf/ICRR-Disclosable-P106703-01-30-2018-1517346533127.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some modification oflanguage.(1)Results based Schemesmight requiresubstantial effort during preparation.Thisproject demonstrated that suchfinancing schemescould entaillegal aspects (such as the ProjectPerformance Agreements with the service providers in this project)whichrequire along and complex judicialapproval process. Therefore, suchprojectsrequirecompletedevelopment of the set of legal frameworks at thepreparation stage.The delaysin the initial years in completing these legislative requirements essentially underminedthe realization of outcomes during implementation.(2) Project time frame, particularly in the case ofcapital-intensive projectsincorporating designs such as a results-based approach, needs to be realistic.Thisis particularly so with respect to activities such as constructingcapital-intensive Waste Water Treatment Plants whichrequire compliance with environmental legislation. The experience with this project showed that while the approach was relativelysuccessful in financing non-intensive capital investment activities (such as control of water losses and rational water use), itwas less so with respect tosupporting capital-intensive activities (such as construction of waste water treatmentfacilities).(3) Results based approach needs verification capacity and technical assistance to potentialorganizational beneficiaries. The experience of this project showed that the implementation of a results based operationrequires the support of a technical assistance component to assist the providers in preparing proposals.
P106708 | CO DPL on Promoting an Inclusive, Equitable and Efficient Social Protection System | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2010 | 2011 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/415701475110226449/text/000020051-20140625060426.txt | http://documents.worldbank.org/curated/en/415701475110226449/pdf/000020051-20140625060426.pdf | The following lessons come from the ICR (first bullet) and from the review (second bullet):Reform is a continuous process, and long-term engagement yields more profound results than ambitious operations trying to reform the system at once;Information is fundamental to monitor the evolution of a social protection system. The experience of this loan shows that paying insufficient attention to defining good outcome indicators for the inclusive, equitable, and efficiency objectives and neglecting to test the effectiveness of the instruments used makes it difficult to know what works well, depriving the Bank of knowledge that could be deployed to further reform in Colombia and other countries as well.
P106720 | Third Programmatic Fiscal Management & Comp. DPL | Latin America and Caribbean | Peru | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2013 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/208431474588004209/text/000020051-20140625224545.txt | http://documents.worldbank.org/curated/en/208431474588004209/pdf/000020051-20140625224545.pdf | The following lessons were identified by IEG's review and the ICR:Sweeping and sustained reforms (such as Peru's) require strong borrower ownership, a well-defined strategy, a highly consultative approach with country stakeholders, and a response donor consortium. Close coordination with international actors helped the Government to implement its comprehensive reform programs over several years.Sustaining fiscal and related public sector management reforms can be challenging. They place a premium on a 'building blocks' approach (for example, ensure aggregate fiscal policies are in place before undertaking expenditure re-prioritization). At the same time, it is important to be flexible in launching various reform initiatives when public institutions demonstrate a readiness to undertake and internalize institutional changes. An important lesson from Peruâ€™s experience is the need to design flexibility into the program in order to respond to new challenges over the course of reform implementation. Peru was successful in adjusting to the changes in global financial markets while remaining faithful to the objectives of its reform program. The Bank acted as a responsible partner and provided both financial resources and technical advice as needed to enable government to carry on its reform program. The use of the deferred drawdown option (DDO) can be helpful in managing the uncertainties for a volatile global environment. It enables countries to have additional insurance to weather the global financial crisis as the availability of financing from the World Bank increase market confidence and access. It also provides a stamp of approval of good housekeeping.
P106720 | Third Programmatic Fiscal Management & Comp. DPL | Latin America and Caribbean | Peru | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2013 | 2017 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/725661488828202108/text/110742-PPAR-PUBLIC.txt | http://documents.worldbank.org/curated/en/725661488828202108/pdf/110742-PPAR-PUBLIC.pdf | 6. Lessons 6.1 The experience of this DPL series highlights what can be expected from the World Bank's engagement with a well-performing middle-income country. 6.2 A programmatic DPL series is a powerful tool for supporting long-term reforms. When a strong ownership of the client is demonstrated, a programmatic series of operations can offer the World Bank and its client win-win solutions. For the World Bank, a multiyear program of support gives it a chance to pursue an extended and coherent analytical agenda that may not be feasible in multiple one-off operations. To the client, the programmatic series offers a real-time opportunity to engage with the reforms (including both the costs and benefits) and to make adjustments along the way. In the case of Peru, the government was able to advance its investment climate agenda early on and to learn about the need for deeper and longer-term challenges of upgrading the quality its workforce and technologies. The successive rounds of ever deeper reforms on trade and competitiveness, while incomplete and not implemented with maximum efficacy, would have been difficult to accomplish through separate operations, which are invariably interrupted by changes of priorities and political mandates. 6.3 World Bank supervision of the implementation of these operations should cover all aspects of the program to take full advantage of the learning opportunities offered by a programmatic series. It should pay greater attention to not only emerging risks during the period of program implementation, but also factors affecting the sustainability of the achievements in long-term policy reforms. In the case of Peru, supervision of the core program seemingly focused only on a few development objectives and outcomes, and left unattended a complete pillar of reforms. No explanation is given for this in any of the Implementation Status and Results Reports. This may have resulted in issues not being identified and therefore not addressed, in time leading to less progress than expected or reversal of outcomes achieved. It limited the ability of the World Bank and other stakeholders to fully understand and learn from the experience of this DPL series. 6.4 Reforms move to subnational levels, though their implementation may pose a challenge depending on the framework of fiscal decentralization. Despite all the positive steps that the government had taken to enhance efficiency in the allocation of fiscal resources, there remains a pressing need to rationalize the fiduciary and regulatory norms and the multiplicity of control and auditing instances. According to MEF officials interviewed for this evaluation, these have proliferated and seem to be driving a wedge between the central and regional governments' capacity to focus on results rather than procedures, a central objective of results-based budget management. Another area of clear priority is for the government to continue to place strong emphasis at the central and subnational levels on a robust and rigorously appraised public investment program, and enhance its assistance to subnational governments in identifying, designing, and implementing their own programs, particularly in meeting infrastructure deficits (for example, roads, water and sanitation). To do so, the government should consider placing greater emphasis on subnational tax revenue collection and more efficient distribution of fiscal transfers to subnational governments, areas that proved somewhat lagging during the implementation period of this DPL series. 6.5 The application of the DDO in this DPL series illustrated the World Bank's willingness and ability to support Peru at the time of the global financial crisis. It also showed the extent to which the World Bank's new arsenal of financing instruments was able to respond to the needs of middle-income countries where both the volume and the timing of financing are important for risk management purposes. As a tool for risk management, the DDO gives clients access to a large line of credit that is affordable and fast disbursing, which helps maintain the confidence of investors and deter the resolve of speculators. As a debt management tool, the DDO offers the government an insurance policy on its debt-service and priority expenditure commitments without raising the level of external debt in advance. The discretion to call on the World Bank loan in the amount it needs when it needs to allows the government to optimize its debt structure. Moreover, by extending the loan period by up to six years and not requiring the client to draw down the loan, the DDO facilitates World Bank engagement with clients who do not need World Bank financing but value its formal and sustained support for their policy reforms. This is particularly valuable for engaging with well-performing middle-income countries. 6.6 Yet, the present example also illustrates possible tensions between the independent selection of IBRD-financing terms and the monitoring of the World Bank's development effectiveness. In this DPL series, the DDOs were requested and approved for risk management and crisis response purposes, but this important development objective, for which two large loans were granted in record time, was not tracked. Although monitoring of the macroeconomic framework and program implementation continued until closure of the DDOs, the depth of supervision was restricted to verification of preconditions for drawdown, as required for all DDOs, and did not try to capture the effectiveness of the loans for all their development objectives. This raises a question as to whether overall program design or continued periodic supervision should attempt to explicitly include indicators of risk management and crisis containment, to capture overall development impact of the DPL series. As this practice was repeated in multiple DPL series in Peru (and elsewhere), a substantial amount of World Bank resources is at stake. 6.7 A parallel issue is that with its longer drawdown period and its renewal feature, the implementation period of a DPL-DDO extends beyond the program implementation period of a normal DPL, which has consequences on the expected outcomes. This calls for attention especially in situations where the DDO was added to an ongoing DPL series, such as in Peru, which had a set of coherent, noncrisis-related policy objectives and a predetermined program period that did not (and could not) anticipate the additional crisisrelated objective and the extended program implementation period. The World Bank's DDO guidelines only require the monitoring of macroeconomic stability and the continued implementation of the program. Questions can thus be raised on whether there should be any more detailed supervision or scope for review of the overall program at the time of a DDO's approval and renewal or readjustment of the IBRD-financing terms with regard to repayment options as the country's debt management profile may have altered. Notwithstanding, the trade-off relative to the flexibility of the loan instrument is also important. These issues merit further debate.
P106724 | Second Programmatic Reform Implementation Development Policy Loan | Latin America and Caribbean | Uruguay | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2009 | 2012 | 2011 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/610531474906280441/text/000020051-20140624185726.txt | http://documents.worldbank.org/curated/en/610531474906280441/pdf/000020051-20140624185726.pdf | The lessons arising from the overall series are presented in the ICRR for the Second Programmatic Reform Implementation Loan (P106724)
P106735 | Provincial Public Health Insurance Development Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2011 | 2020 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/739371590540694065/text/Argentina-AR-Provincial-Public-Health-Insurance.txt | http://documents.worldbank.org/curated/en/739371590540694065/pdf/Argentina-AR-Provincial-Public-Health-Insurance.pdf | The ICR (pp. 28-29) offered several lessons and recommendations, including the following lessons restated byIEG:The incorporation of new groups of beneficiaries into a public health insurance program can bechallenging and calls for tailored strategies specific to targeted groups to promote enrollment. Under the project,youth required a more welcoming attitude on the part of health care providers. In the case of adult men, overcoming reticence toseek preventive health care was needed. In the case of indigenous persons, interventions were culturally sensitive, and the projectalso sought to enhance awareness about the benefits of indigenous self-identification when receiving healthcare.Universal health coverage is facilitated by a carefully sequenced and incrementalexpansion. In Argentina, Plan Nacer benefited during its early years from a relatively narrow focus on its targetpopulation, consisting of pregnant women and young children with the likelihood of quick and visible gains. By contrast, under thisfollow-on SUMAR project,the target population was expanded to the remaining population groups that were diverse and requiredtailored strategies.The project limited implementation complexities by focusing on cost-efficient preventiveservices.The implementation of results-based financing mechanisms in health programs and relatedorganizational changes are demanding and, as such, they call for substantial technical assistance and adequate staffinglevels.Under the project, the project coordination unit strived, despite its limitations in human and operationalresources, to support the provinces that had uneven institutional and technical capacity, and to promote communication effortsthrough national and regional meetings, field visits, and thematic workshops.Results-based financing incentives in health programs induce behavioral changes amonginstitutional actors and health care providers.Under the project, related incentives promoted provincial buy-in intouniversal health care coverage, prioritization of preventive health care services, and homogenization of clinical and reportingprotocols. Incentives also helped in inducing behavioral changes in providers, such as with timely referral of high-riskpregnancies to facilities equipped to offer the appropriate level of care.
P106747 | NI Development Policy Credit | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2009 | 2009 | 2010 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/807151474560113266/text/000020051-20140620072207.txt | http://documents.worldbank.org/curated/en/807151474560113266/pdf/000020051-20140620072207.pdf | An outcome-driven results framework with well-specified outcome indicators that result from policy actions and specifically measure desired development outcomes is a crucial factor in guiding the design and implementation of a satisfactory Development Policy Operation. Such a framework would be instrumental in overcoming the seeming paradox that appeared in the previous two PRSC series (and, to a lesser extent, in this operation) of all prior actions being met and all targeted indicators being achieved without tangible achievements in poverty reduction. This is precisely why this DPC proposed to focus on strengthening the information basis for monitoring and delivering basic social services. Strengthening the M&E framework remains essential to achieve development objectives.A selective and coordinated approach such as the one adopted in this operation is all the more important as a country's institutional capacity constraint is binding.
P106752 | Unleashing Productive Innovation Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2009 | 2020 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/354161592862518477/text/Argentina-AR-Unleashing-Productive-Innovation.txt | http://documents.worldbank.org/curated/en/354161592862518477/pdf/Argentina-AR-Unleashing-Productive-Innovation.pdf | Several lessonsdocumented in the ICR (para 112-131)reflect the experience of project design and implementation, andthe prominentones are summarized below: Micro-interventions focused on STI can generateresultsina context ofmacro-volatility; on the contrary,market-based instruments may not function aswell.Despite the macro-uncertainty in Argentina, the project supported the creation of technology-based firms,improved firm productivity, created skilled jobs, and commercialized new products, including those which helped increase incomesfor vulnerable communities. However, both the Venture Capital Fund and the Deal Flow Facilitation components were closer to themarket and did not work well,stressing that market-based instruments supporting productive innovation may not function aswell in a context of macro-volatility. Projects focused on supporting knowledge-based companies may considerallowing diverse technology firms to become project beneficiaries: The initial calls for proposals for the innovationgrant program were limited to focus on biotechnology, nanotechnology and ICT.A broader technology focus would have allowedfor faster implementation and a wider response to calls for proposals.The initial low response rate eventually led to theprograms scope being widened to include all technology sub-sectors.Limiting knowledge-based programs to specificsub-sectors mayexclude important innovations from benefitting from project activities. The focus on biotechnology,nanotechnology and ICT was narrow and proposals for the innovation grant program were limited; this low response rate eventuallyled to the programs scope being widened to include all technology sub-sectors; Private sector focusedinterventions need to emphasize thestrengthening of key institutions within the innovation space.The projectsupported key institutions within the national innovation system, including the ANPCyT and the MINCyT.Project financing alsoenabled the creation of FONARSEC, the ANPCyT fund to promote technology-based entrepreneurship and collaborative researchconsortia, andthe National Scientific and Technical Research Council (CONICET Tecnologia), the technology transfer unit underCONICET to support commercialization of new research.Structural institutional support couldaddress long-termfunding constraints for labs and technology centers to allow for better performing operations and maintenance alongside equipmentupgrades. A deeper public-private dialogue and communication is essential to engage the innovationecosystem. Key results arose from a strong and effective public-private dialogue at the activity level. In the bestcase scenario, components requiring private sector participation should incorporate market testing at the design stage to ensureimplementation-ready design and fiduciary requirements.Such a process would have allowed for adjustments in the design priorto the start of implementation, most likely mitigating some of the implementation risks and reducing the associateddifficulties. Beneficiaries of the EMPRETECNO and FSAT programs underscored the signaling value of theirparticipation in these programs, which could be better incorporated into project communications to entice larger-scaleparticipation.Additionally, previous beneficiaries also expressed a commitment to providing mentorship to futurebeneficiaries, which could help ensure long-term support for STI program beneficiaries and increase the valueof participation. Streamlining the projectdesign increases the probability of achieving the identifiedproject objective: Future operations should consider more focused support and simplify the project design toincorporate fewer institutions and implementation agencies, along with simplifying fiduciary requirements to streamlineimplementation. Procurement arrangements which apply to beneficiaries could also be simplified to reduce their associatedburden.Complex Project components should be designed with a focus on the implementation arrangements and the pipelineof beneficiaries with an implementation plan and timeframe, based on clear agreement between the Bank team and governmentcounterparts.Ensuring a good match between Project activities and the specific implementation agency plays a key role insuccess of these activities. A large-scope innovation project requires a strong ME system for a successfulimplementation and assessment:Due to limitations in ME systems and time constraints, the project was unable togather baseline data across all its components, leading to difficulties in documenting the impact of project outcome. This alsohindered institutional credibility for the ANPCyT and MINCyT, along with the overall STI and innovation agenda. Including baselinestudies could have plays a key role in assessing the impact of interventions and measuring the scale of impact.A strongerME system would help document program impacts and allow for more timely adjustments as needed to ensure programeffectiveness.ME design at project preparation would have emphasized the importance of gathering baseline data,especially when accurate statistics were limited.
P106753 | Expanding Opportunities, Enhancing Equity in the State of Pernambuco Development Policy Loan | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | IBRD | DPF | 2012 | 2013 | 2014 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/352881474630689200/text/000020051-20140626122055.txt | http://documents.worldbank.org/curated/en/352881474630689200/pdf/000020051-20140626122055.pdf | Important lessons, taken from the ICR, from this operation include: The capacity and ability of a DPL implementing agency to manage coordination is essential to the delivery of a program of policy actions, A simple and manageable matrix of results indicators is essential for effective implementation, and participation of a core team from the government from the design stage of the project reinforces government ownership and commitment to the program.
P106765 | BR Ceara Inclusive Growth (SWAp II) | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2009 | 2012 | 2013 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/122141474648875628/text/000020051-20140626002254.txt | http://documents.worldbank.org/curated/en/122141474648875628/pdf/000020051-20140626002254.pdf | The lessons captured in the ICR are all well founded and reasonable. What seems to be emerging from the experience with this project is the value of a sustained dialogue with the stakeholders that enables the Bank to serve as an integral partner and trusted advisor. SWAp seems to provide an ideal instrument for such an engagement--a framework that anchors the discussion around medium term outcomes while ensuring periodic monitoring of progress. It also helps to recognize dependencies and potential trade offs among sectors and themes, allowing the operation to have a holistic view of the challenges. Finally, it offers leverage to improve progress of related, but separate operations, through including the performance improvement of those projects as part of the disbursement linked indicators.
P106767 | RIO GRANDE DO SUL FISCAL SUSTAINABILITY | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2009 | 2011 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/398751474633073089/text/000020051-20140625054513.txt | http://documents.worldbank.org/curated/en/398751474633073089/pdf/000020051-20140625054513.pdf | IEG supports the lessons given in the ICR: the importance of debt restructuring to fiscal sustainability, the importance of flexibility by the Bank in meeting the varied needs of state and federal government, and the need to be more realistic in matching the time needed for building support for politically controversial reforms, within the time line of a DPL. More guidance is needed for Bank staff, drawing on the Bank's global experience, of appropriate indicators and time scales for civil service reform that can be adapted to particular contexts.
P106768 | Brazil - Rio de Janeiro Renovating and Strengthening Public Management | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2011 | 2017 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/874671524160551200/text/Brazil-BR-Rio-de-Janeiro-Public-Management.txt | http://documents.worldbank.org/curated/en/874671524160551200/pdf/Brazil-BR-Rio-de-Janeiro-Public-Management.pdf | The following lessons are drawn from the ICR:Flexible Design and Focus on Few Sectors. A primaryreason for project achievements was its focus on management, and flexible design. The loan covered just a few sectors andconcentrated on those areas where the Bank had accumulated experience in the RJS. By including only four areas, both theauthorities and the Bank could devote greater attention to the details of the policies supported under theproject.Linking technical assistance with DPLs. The projects links with the series of DPLswas useful, providing a strong financial incentive for the RJS to follow through on activities supported by the project, as well asan additional platform for high-level dialogue with policymakers. The prior actions in both related DPLs benefitted fromtechnical assistance financed by the project.Strong Supervision and Direct Technical Assistance.The continuous presence of the Bank, with regular supervision missions and technical assistance via monthly video conferences andcalls, played an important role in the implementation of the project, given the political and economic volatility during theimplementation period. The support was possible because of adequate financial resources for supervision. The budget forsupervision, along with available funds from the DPLs and other ongoing investment projects, allowed for more frequent interactionsthan is usual during the implementation phase.
P106794 | CAMEROON WATER AFFERMAGE - OBA for Coverage Expansion | Western and Central Africa | Cameroon | Blend | Non-FCS | Sustainable Development | Water | RETF | IPF | 2008 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/676811467998765788/text/ICRR14688-P106794-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/676811467998765788/pdf/ICRR14688-P106794-Box393183B-PUBLIC.pdf | The main lessons derived from the ICR (pages 19-20) are as follows:1. Effective project preparation and supervision strengthen the foundation for achievement of the PDO. This involves the following steps:a) Enable client ownership.b) Design projects with proper sequencing of activities. c) Include mitigation measures in risk assessment.d) Provide effective supervision of OBA components of larger projects. e) Enable effective monitoring and evaluation.2. For OBA projects, pragmatism and clarity are key for targeting and monitoring. More specifically:a) Incentives are key to performance and operator engagement. b) Pragmatic approaches should be used to target the poor. c) M&E systems and capacity building should be strengthened.d) The subsidy formula should be simple, absolutely clear and well understood by all partners.e) A dedicated PIU could be considered with OBA projects.f) Having the IVA in place could be considered a condition for disbursement in the dated covenants.
P106851 | CG Rep. Health Sector Services Development | Western and Central Africa | Congo, Republic of | Blend | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2008 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/208631468191038449/text/ICRR14726-P106851-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/208631468191038449/pdf/ICRR14726-P106851-Box393183B-PUBLIC.pdf | The ICR (p. 34) identifies several valuable lessons, including:In the case of weak government structures, it is important to conduct an assessment during project preparation to identify challenges in institutional capacity so they can be addressed accordingly and ensure that critical staffing and structures are in place before the project is presented for Board approval. Lack of readiness at entry, weak management capacity, lack of a project coordinator, and high staff turnover led in this case to poor project implementation before project restructuring. It is also important that project design is aligned with institutional capacity, and that capacity strengthening is integrated in project design.Strengthening the Health Management Information System through project activities can lead not only to higher quality data for M&E of the project but also to a positive long-term impact on the health system. In this case, after the restructuring of the results framework, more emphasis was put on M&E and strengthening the health information system by developing annual statistical reports, conducting surveys, and carrying out an impact evaluation of the Performance-Based Financing pilot.
P106855 | General Education Quality Improvement Project - APL 1 (GEQIP) | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2009 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/680161474941361040/text/000012394-20150312070424.txt | http://documents.worldbank.org/curated/en/680161474941361040/pdf/000012394-20150312070424.pdf | The ICR identifies several valuable lessons:The Bank has a comparative advantage due to its expertise as a focal point for development partners. In this case, the Bank's coordination of donor aid helped to avoid fragmentation and bureaucratic burden on the government and ensured alignment with the countryâ€™s objectives.Despite improvements in the quality of education, student assessment scores might not increase. Increases in enrollment rates tend to benefit more socio-economically disadvantaged students into the general student population. This dynamic may decrease assessment scores, as student performance is positively correlated with exogenous factors such as parentsâ€™ level of education and income. There is a need to allocate sufficient budget for supervision and capacity building activities and assign government staff to focus solely on the project. In this project, government accountants were overburdened as they had to fulfill project-related tasks on top of their regular tasks. This led to challenges in financial management. IEG offers this additional lesson:Performance-based financial incentives can decrease high turnover rates in jobs such as teaching in Ethiopia.
P106870 | Improving Community and Family Health Care Services Project | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2011 | 2016 | 2017 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/482241497633180470/text/ICRR-Disclosable-P106870-06-16-2017-1497633164437.txt | http://documents.worldbank.org/curated/en/482241497633180470/pdf/ICRR-Disclosable-P106870-06-16-2017-1497633164437.pdf | The ICR (pp. 24-25) offersseveral lessons derived from the projects experience,including: The development of culturally sensitive interventions, aimed at ensuring utilization ofhealth services by indigenous populations, requires involvement of both the community and health care professionals. A householdsurvey on service satisfaction at the beginning of the project revealed that one of the main reasons for not using health serviceswas the lack of cultural adaptation in service provision. The task team worked closely with community and health practitioners fromindigenous backgrounds to develop materials and documents for training and education on reproductive health that were translated tothe language Miskito.This ICRR adds: Despite the overallpositive experience with capitation payments linked to results,capitation payments cannot overcome all access and quality shortcomings in health service provision. In this case, the governmenthas recognized that some municipalities underperformed due to difficult access in some communities (demand barrier), understaffedhealth units (health system capacities), and mismatch of population data provided by INIDE and the actual population(HMIS). Alignment of results framework indicators with results-based financing performancetargets (associated with capitation payments) is an efficient way to monitor project progress towards objectives,as it usesalready available informationand does not requireadditional effort to collect new data. It simplifies MEactivities appropriately, as long as the performance targets are adequate measures of the projects objectives.
P106872 | Ethiopia-Road Sector Development Program APL4 | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2009 | 2017 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/545381541530038710/text/Ethiopia-ET-RSDP-Stage-IV-APL-FY09.txt | http://documents.worldbank.org/curated/en/545381541530038710/pdf/Ethiopia-ET-RSDP-Stage-IV-APL-FY09.pdf | The ICR (para 49) presented severallessons and recommendations. The main lessons are presented below with some adaptationof the language: The road slope protection by grassing should be done on time to ensure the grasses are wellrooted before contractors demobilize from sites. For instance, in some sections on Mekenajo to Dembidolo road corridor,trees and grass that had been planted were yet to take root in many places even well after the handing over of the project road.Flooding was widely observed in the Mekenajo-Dembidolo road corridor, where several coffee-growing farmers reported losing coffeetrees and other perennial crops (ICR p.77). The involvement of multiple institutionsthatmanage resettlement, land acquisition, and grievances requires early discussions and greatercoordination.Early discussion and consultations with the different agencies, such as Regional Road Authoritiesand lower level government - woredas, and with PAPs, over land acquisitions and resettlement could help to minimizedelay during project implementation.
P106885 | Integrated POPs Management | East Asia and Pacific | Philippines | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2010 | 2018 | 2019 | ICRR | Less than 10 million | Highly Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/935721559580441036/text/Philippines-PH-GEF-Integrated-POPs-Management-Proj.txt | http://documents.worldbank.org/curated/en/935721559580441036/pdf/Philippines-PH-GEF-Integrated-POPs-Management-Proj.pdf | Some lessons adapted from the ICR are below:The importance of setting realisticand relevant targets requires careful study and planning: The procedural and technical process for designing and adoptingregulatory instruments that are critical for project success should be well studied and planned for so that related projectimplementation risks can be mitigated, and delays planned for. For instance, in this project the legal output for an executiveorder for the interagency task force on POPs management involved prior interagency coordination, and a lengthy approval andissuance process with final approval by the Office of the Philippine President. According to the ICR (para 101), this wasunachievable within the project life.A narrow focus on POPs reduction by sector could be betterthan a comprehensive plan covering all emissions sectors, to achieve tangible results: The project had incorporatedseveral distinct POPs areas ((1) POPs pesticides, (2) dioxides and furans produced by industrial processes, (3) PCBs in electricaltransformers, and (4) POPs contaminated sites) resulting in numerous implementing agencies and complex coordination challenges.Some successful POPs projects in other countries focused on a single area, or where there was a substantial direct governmentinvolvement (for example UPOPs from hospital waste and PCBs owned by government utilities in Tunisia - P100478) that allowedgreater control of activities and outputs, and achievable targets.
P106899 | Energy Community of South East Europe APL 3 - Montenegro Project | Europe and Central Asia | Montenegro | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2008 | 2014 | 2015 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/773561468188928263/text/ICRR14653-P106899-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/773561468188928263/pdf/ICRR14653-P106899-Box393183B-PUBLIC.pdf | The ICR identified the following lessons that could help future project design:Realistic cost estimates derived after carrying out the design and technical specifications can avoid needless uncertainties;It is important to design key indicators that are practical, logical and measurable targets;Restructuring opportunities should be utilized to remedy omissions of key indicators.
P106906 | Land Administration and Management Project | Europe and Central Asia | Montenegro | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2009 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/499621495464819885/text/ICRR-Disclosable-P106906-05-22-2017-1495465715249.txt | http://documents.worldbank.org/curated/en/499621495464819885/pdf/ICRR-Disclosable-P106906-05-22-2017-1495465715249.pdf | From ICR ReviewerBreaking World Bank siloson land administration andland useplanning:Integrated projectsaddressing both land administration and land use planninghave thepotential of producing important development impact. Underthe current structure of the Social, Urban, Rural andResilience GP - similarprojects should be easier to staff and manage ensuringseamless project teamscapableof encompassing.Revision of PDO indicatorsrequires the project team to plan aheadwith arevisedapproach to undertakethe economic analysis during the preparation of theICR. Adapting piecemealeconomic analysisupon theclosure of the project does not yield the necessary rigor toestablish with certainty the efficacy of the use of World Bank and counterpart resources.FromICRDesigning robust PDO indicators: The external shock caused by the global financial crisisand thesubsequent dropping of the indicator tracking the real estate transfer tax and property tax receipts exposes an important issue inthe design of indicators. To the extent possible, PDO indicators should be directly affected by project activities or outcomes, andberelatively shielded from market fluctuations. Active implementation support can deliver strong developmentoutcomes: During project implementation, the team responded quickly with appropriate restructurings that reallocated funds,adjusted Project targets, and extended the Project closing date.Innovative approaches may be risky but can pay off:Testing a new approach under a project can be risky as the chances for success or failure are often the same. A full participatoryapproach to planning under this project was one such approach that proved to be challenging from an implementation point ofview.Eventually people started believing in the process and began taking ownership. At the end, the planning process tookmuch more time than anticipated at the design stage. The Project consequently had to be restructured. However, the participatoryapproach to planning under the Project proved successful.
P106909 | Urban Water Sector Project | Western and Central Africa | Burkina Faso | IDA | FCS | Sustainable Development | Water | IDA | IPF | 2009 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/891831624540710271/text/Burkina-Faso-BF-Urban-Water-Sector-Project.txt | http://documents.worldbank.org/curated/en/891831624540710271/pdf/Burkina-Faso-BF-Urban-Water-Sector-Project.pdf | Four lessons were derived from the ICR and the additional information provided by the project team.Acheck-based (verification) approach can contribute to the achievement of the project outcomes in increasing access towater. Upon receiving a request for water connection, ONEA connected a dwelling to the water network after verifying thatthere was someone residing in that dwelling. Such verification process prevented unnecessary connections to vacant dwellings orplots where there was no dwelling. This check-based approach ensured that services were provided in urban and semi-urban areaswhere such services were needed. This contributed to the achievement of a higher number of people with access to water than therevised target value set at additional financing and reduction of inactive connections (Project teams email dated April 21,2021)Delegation of water service provision to private companies in public-private-partnership (PPP) models can bea more efficient and practical solution for increasing access to water in informal settlements where the poor live.Because of the absence of official streets and delimitation of properties, ONEA could not develop a water network and installconnections in informal settlements in Ouagadougou using its usual network planning and development approach. To meet the highdemand, ONEA partnered with local neighborhood operators for the provision of water in informal settlements. According to the PPPcontract, ONEA is responsible for the supply of bulk water to the delegated perimeter, and the private operator is responsible forthe distribution of the water to the beneficiaries. Operators used simplified networks built by using polyethylene high densitypipes and implemented tailored payment plans for customers in line with their revenue streams (ICR, pp.27-28). This approachdirectly benefited 18,900 people living in informal settlements (ICR, p.15).Strengthening the whole sanitationservice chain can improve the sustainability of sanitation services. The project supported the construction ofon-site sanitation facilities at households and schools, the training of the masons in latrines manufacturing and repair, thetraining of the pit emptiers in emptying pits and transporting of fecal sludge to treatment, and the construction of fecal sludgetreatment plants to be operated by ONEA. The absence of any of these sanitation service chain components could adversely affect thesustainability sanitation services. The projects support to the whole sanitation service chain was critical in thedevelopment of sanitation services in Ouagadougou and Bobo-Dioulasso, and the creation of a sanitation market (ICR,pp.19-21)The demand-responsive approach and activities to induce demand for services can be critical in increasingaccess to sanitation services. The project supported the creation of demand for sanitation services through communitymeetings, household visits, and sanitation promotion campaigns. The beneficiaries contributed to the cost of construction oflatrines, which were subsidized by the project. Citizen engagement and availability of options, such as the rehabilitation oftraditional latrines instead of construction of new ones, were critical in latrine take-up by beneficiaries. At project closing,the beneficiaries estimated contribution to the cost of on-site sanitation facilities was US$7.64 million (ICR, p.20).
P106927 | South Sudan MDTF HIV/AIDS Project | Eastern and Southern Africa | South Sudan | IDA | FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2008 | 2013 | 2014 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/486781474492137929/text/000020051-20140626112457.txt | http://documents.worldbank.org/curated/en/486781474492137929/pdf/000020051-20140626112457.pdf | The following lessons are derived from the ICR (pp. 22-23, 42-43):International NGOs can deliver services faster and with more effectiveness in low-capacity countries, but in the long term their participation is not sustainable. Transition arrangements are therefore required. In this case, it will not be financially or managerially sustainable for the government to deliver services at high marginal unit cost via the four contracted lead agencies, and yet the project did not explicitly design an â€œexitâ€ or â€œhandoverâ€ strategy from use of these agencies.Realistic results-based indicators, closely tied to a projectâ€™s development objectives, are essential from the outset. In this case, an adequately designed M&E system was not in place at the start of implementation, and appropriate arrangements were not made to ensure that available information was used strategically for decision making. With key target groups still not adequately identified and mapped, it is impossible to track the most important data on knowledge and behavior change.Undue emphasis on inter-sectoral action on HIV/AIDS should be avoided in low-capacity systems. While it is important to build constituencies across various ministries, complex implementation arrangements that involve various line ministries integrating HIV/AIDS across their programs are unlikely to be successful. Specific action is most important, for example, for peer-based interventions to decrease HIV transmission among risk groups (probably led by NGOs) and for provision of supportive services such as voluntary counseling and testing (probably led by health ministries).
P106956 | Ningbo New Countryside Development Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2010 | 2016 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/331371487005509137/text/ICRR-Disclosable-P106956-02-13-2017-1487005496725.txt | http://documents.worldbank.org/curated/en/331371487005509137/pdf/ICRR-Disclosable-P106956-02-13-2017-1487005496725.pdf | The ICR (p.27-28) includes several useful lessons learned, which have been somewhat reframed byIEG:1 Involving local communities in the project preparation phase canbe beneficial in overcoming challenges related to the construction and Operations Maintenance of rural wastewater facilities.However, sufficient time for this process needs to be planned for. In this project villagers were involved in all stagessuch as the village selection, design, and Operations Maintenance. However, the time required for these consultations wasunderestimated and led to implementation delays.2 A combination of one-time financial subsidies and awarenessraising of wastewater treatment services among communities is critical to connect a high number of individual households to ruralwastewater treatment infrastructure. In this project the costs of indoor connections were covered by the project. Inaddition, raising awareness of the benefits of rural wastewater infrastructure led to a high rate of indoor householdconnections.3 Implementing wastewater tariffs to cover Operations Maintenance costs is challenging.In this project it was estimated that the Operations Maintenance costs of the Chunhu Town wastewater management investmentswould be covered by wastewater tariffs by 2016. However, projections indicate that the time frame was unrealistic and it would takeuntil 2022 to cover for the costs, assuming that the tariff is being increased at a steady rate every three years which seemsunrealistic.4 Technical assistance components also need to be outcome oriented to measure their contributiontowards the projects objective. In this project indicators measured the completion of certain technical assistanceactivities, however, they did not measure the extent to which these activities contributed to the improvement of townshipmanagement.
P106963 | Third Programmatic Development Policy (PDPG3) | Europe and Central Asia | Tajikistan | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2011 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/849911474593042097/text/Tajikistan-Programmatic-Development-Policy-Grant.txt | http://documents.worldbank.org/curated/en/849911474593042097/pdf/Tajikistan-Programmatic-Development-Policy-Grant.pdf | There are several good lessons in the ICR, three of which stand out. First, a good understanding of the political economy of a country is basic for the program design to be realistic and the expected outcomes to be achievable.Second, a focus on results helps in creating government appreciation of and commitment to the program, because it helps direct the focus of the dialogue to a concrete discussion of how to best achieve the desired outcomes.Third, in an environment of low capacity, technical assistance to expedite implementation is essential.
P106975 | Rep. of Congo - Water, Electricity & Urban Development SIL (LEN) | Western and Central Africa | Congo, Republic of | Blend | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2010 | 2021 | 2023 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/099425009022222646/text/P1069750798cd702b0b61a0e076506fa9ab.txt | http://documents.worldbank.org/curated/en/099425009022222646/pdf/P1069750798cd702b0b61a0e076506fa9ab.pdf | IEG derives the following lessons drawn from the ICR:1. When appraising a project cofinanced bycounterpart funding, a review of the Borrowers fiscal outlook and sustainability should be undertaken. Thegoal of such a review would be to ascertain that Government counterpart funding is underpinned by stable tax inflowscollection. In the case of the project in question, the dependence on oil export revenues meant that when oil prices fell theGovernment was unable to provide its share of counterpart funding. The result was that the burden of project funding fellexclusively on the World Banks shoulders, causing a number of activities to be canceled, and the ambition of the project tobe scaled back.2. In designing infrastructure projects, the costing of components and activities needs toclarify the taxation regime of supplied goods and services. For the project in question, the Governmentpreferred that project expenditures on all goods and services supplied using project resources include a value added tax(VAT). This meant that tax payments effectively reduced the resources available to generate targeted outcomes. Atproject closing, taxes paid to the Treasury amounted to about US$14.0 million resources that should have been used to fundproject activities supported expected outcomes.3. When a project is implemented in the context of weakeconomic governance, the World Bank needs to strengthen its fiduciary oversight of project implementation: The starkcontrast between the relatively low level of fiduciary risk assessed at appraisal and the poor level of fiduciary management duringimplementation demonstrates that PCUs implementing Bank-funded projects cannot by themselves transform the governance context inthe Borrowers management systems for public resources. The World Bank team needs to provide TA and exert fiduciaryoversight.
P106982 | DRC-Growth with Governance in the Mineral Sector | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2019 | 2020 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/644241568989029363/text/Congo-Democratic-Republic-of-DRC-Growth-w-Gov-in-Mineral-Sector.txt | http://documents.worldbank.org/curated/en/644241568989029363/pdf/Congo-Democratic-Republic-of-DRC-Growth-w-Gov-in-Mineral-Sector.pdf | IEG derives the following lessons, drawn from the ICR: To pursue sector reforms in the mining sector, aclear understanding of the political economy is needed. The project demonstrated that in DRC, the activities around thereform of the Mining Code, in particular, proved very sensitive. After submission to Parliament in 2015, the draft code was notdiscussed for two years, mainly because of intense lobbying by mining companies. Discussions were initiated in 2017, in partthrough the projects efforts, in the form of a Note on the Mining Code prepared by the World Bank on 2016, and analytical workconducted by the IMF. International organizations can help adjust the mining sector reform debatewhen it becomes politically charged and unbalanced through intensive lobbying.The project illustrates the importantrole that institutionslike the World Bank and IMF can play in supporting sector reform through institutional strengthening,by helping to defuse some of its more politically charged elements. Building up enforcement capacity is critical, and any legalrevision needs to be accompanied by strong capacity-building efforts, both at regulatory and administrative levels, especially forcountries with poor governance, always taking into account that the enforcement of reforms takes time usually more thanplanned. Technical assistance projects in fragile country environments/sectors requireintense supervision and long-term engagement. The experience of the project demonstrates the critical role of supervisionin ensuring satisfactory project performance.During the post-restructuring phase,intensive supervisioncombinedmultiple missions with frequent follow-up video conferences. The costs of such implementation support need to be factored in fromthe outset.
P107050 | RY-Integrated Urban Development Project (IUDP) | Middle East and North Africa | Yemen, Republic of | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2010 | 2015 | 2016 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/448311468141558959/text/ICRR-Disclosable-P107050-06-10-2016-1465564577433.txt | http://documents.worldbank.org/curated/en/448311468141558959/pdf/ICRR-Disclosable-P107050-06-10-2016-1465564577433.pdf | The ICR provided the following main lessons:(1) Identifying stakeholder incentives through a politicaleconomy analysis is critical to generate ownership of project and optimize its design.In the subjectproject, stakeholder consultation would have highlighted Yemens fragility, established the urgency for national dialogue onurban upgrading and allowed for better gauging of appropriateness and Government ownership regarding the matter. The analysisreport would have also clarified the nature of the operating environment and supported the need for a fragility-led projectpreparation and implementation design rather than a low capacity approach.(2) Informed restructuring should beconsidered as a key tool in implementation support rather than as a last resort. The project lagged inprogress partially due to the internal conflict in Yemen and due to weak capacity of the implementing agency. The project underwenttwo restructurings. An informed restructuring could have cancelled non-performing activities, e.g., at the time of the firstrestructuring, rather than during the second restructuring, which was towards project closure. This would have simplified theproject scope and freed up associated financial and human resources.(3) Adapting theBanks operational approach to better fit a Fragility, Conflict andViolence (FCV) context would allow for more flexibility and facilitate proactivity. The Bank used standardmechanisms for implementation support and performance assessment through traditional procedures for the subject project. But,instead it should have considered adjusting its operational approach to a Fragility, Conflict and Violence (FCV) context throughspecific tools that allow for more flexible and proactive project monitoring, supervision, restructuring, and performanceassessment. The task teams should have conducted more regular and frequent supervision through videoconferences, and/or audioconferences rather than project reviews via reverse missions for the subject project. Back-up mechanisms could be specified in theOperational Manual to preempt issues, e.g., by adding provisions to avoid rebidding in cases of large cost increases betweenbidding and contract implementation, and establishing back-up arrangements for reporting and reaching out tobeneficiaries.
P107062 | Second Program 135 Phase 2 Support | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | DPF | 2009 | 2010 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/641111474942570772/text/000180307-20141203060928.txt | http://documents.worldbank.org/curated/en/641111474942570772/pdf/000180307-20141203060928.pdf | A number of useful lessons are highlighted in the ICR. This review also finds that the transfer of resources in challenging areas where poverty proved to be persistent may not be sufficient for poverty reduction if it is not underpinned by long-term and sustained focus on capacity development at the local level. Related to that, the review finds that the Bank needs to consider changing the modality of engagement (moving to investment lending from policy lending) when it is clear that technical assistance will remain a major shortcoming for the project. The review finds that country-wide targeted poverty reduction programs are difficult to implement without being preceded by a pilot program that could help to carefully diagnose the causal chain of resource transfer, capacity building and poverty reduction, and to use the lessons for more successful scaling-up at the national level. Also, the review finds that the Bankâ€™s support for specific government programs should be based on a careful assessment of the design and implementation risks. And lastly, the review finds that in cases where there is a need for more than one ICR for the same series (such as in the case of this series) the final ICR needs to consider covering the series in its entirety.
P107062 | Second Program 135 Phase 2 Support | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | DPF | 2009 | 2010 | 2015 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/721331467986245693/text/96203-PPAR-REVISED-PUBLIC-VIETNAM-PPAR-FINAL.txt | http://documents.worldbank.org/curated/en/721331467986245693/pdf/96203-PPAR-REVISED-PUBLIC-VIETNAM-PPAR-FINAL.pdf | 6. Conclusions and Lessons Learnt Conclusions 6.1 This review presented an overview of Vietnam's economic and social performance. It assessed the extent to which World Bank DPOs during 2007-12 contributed to its achievements and their sustainability. The main conclusion that emerges from the historical overview is that the country's growth performance during the 1990s and until the mid-2000s was very strong. Effective poverty alleviation also took place during that period, and has been sustained since. This was thanks to transformative measures (especially land reform, enterprise reform and WTO accession) that were taken by Government during the first half of the 2000s (in turn building on earlier reforms) with substantial development partner advice and support, which was generally led by the Bank. 6.2 However, during the period under review (2006-2013) the next generation of transformative reforms (notably as highlighted in the 2007 and 2009 VDRs) were either postponed or diluted, and were thus less effective. Areas such as SOE and financial sector reform, more efficient public investments, anti-corruption, and more effective environmental policies, received insufficient attention. Over the same period, Vietnam departed from the prudent macro-fiscal stance that characterized it in the 1990s early 2000s. 6.3 Past reforms continue to drive strong FDI and buoyant exports. Vietnam can build on these strengths to avoid further loss of growth momentum. This could be based on the implementation select transformative reforms aimed at strengthening the role of the private sector, facilitating the emergence of mediumto large domestic enterprises, and sustainably expanding infrastructure in an efficient manner. The progressive elimination of the stock of contingent liabilities and reducing other risks to the sustainability of fiscal policy would create a more stable macroeconomic environment. One of Vietnam's strengths lies in its social compact, the main elements of which should be maintained, while progressively evolving towards a less paternalistic approach based on stakeholder empowerment. 6.4 The Bank and other development partners can help the country address these priorities through more selective budget support instruments. This is indeed envisaged in the Country Partnership Strategy (2012-16). The 2016-2020 SEDP also provides an opportunity to generate political consensus around these issues in the context of an increasingly complex economy. 6.5 The Bank should be more willing to cease supporting programs should they become so weakened as to make it likely that key objectives would not be achieved. Technical and policy dialogue would be maintained. In this context, high caliber knowledge products will need to continue being prepared, and the relationship of trust that supports frank dialogue with Government needs to be reinforced. Harmonization with all key stakeholders, external and internal, will be important. Strong commitment to deeper reforms would help to sustain Vietnam's economic performance while addressing the challenges of an increasingly complex, middle-income economy, and deepening global integration. Lessons from the Bank's macroeconomic engagement through DPOs. 6.6 The model of the Bank's engagement in macroeconomic and fiscal policies through DPOs in Vietnam since 2007 has not been effective. An important finding emerging from this PPAR is that, while diagnosis of macroeconomic risks was adequate, this was not reflected in program design, despite a highly volatile environment exacerbated by sub-optimal policy choices. This situation was, moreover, aggravated by the lack of an IMF program and the relative weakness of macroeconomic policy dialogue between the Government and the Bretton Woods Institutions. The Bank may have been exposed to reputational risks if its policy lending had been seen as a de-facto endorsement of controversial macro policies. DPOs following those reviewed in this PPAR are still not underpinned by relevant macro policy content, although macroeconomic risks persist. This indicates that the lessons learned during the 2007-2013 period do not appear to have been fully learned. 6.7 Macroeconomic dialogue could advantageously be consolidated in a presence of multiple parallel DPOs. The fragmentation of policy lending into multiple DPOs implemented in parallel in Vietnam during the period of increased macro risks might have weakened Bank's focus on macro framework and even resulted in inconsistencies in policy dialogue. The Bank should have avoided situations when preparation of one operation is held back for concerns over the macro-framework while a parallel DPO is approved and disbursed in the same macro environment. To avoid the repetition of such a situation, there should be a unique and consistent approach towards assessing the adequacy of macroeconomic underpinning of DPOs. When substantial risks are present, policies underpinning the most suitable, in terms of scope and objectives, budget support operation should be reoriented to alleviate them. 6.8 Combining the objectives of external financing for crisis response and promotion of long-standing institutional reforms may not be effective in cases where risks to nonimplementation of reforms are high. The Bank's experience with the Vietnam PIR series indicates that, when financing needs are urgent, it will find itself under pressure to go ahead with disbursements even if the reform implementation is not satisfactory. Crisis response operations should first of all focus on ensuring the sustainability of macro and fiscal framework, and should be underpinned by critical macro, fiscal and structural actions, especially in cases when the IMF is not present operationally. Lessons Learnt â€“ Results and M&E Framework 6.9 Wide-ranging DPOs need to be based on stronger and better quality actions. The importance of each individual prior action increases in multi-sectoral operations with many policy areas because of the implicit limit on the number of total prior actions for operational purposes. If in a series of five operations, for example, each policy area can have a maximum of two or three prior actions in the course of five to six years it is important to ensure that those prior actions have sufficient institutional depth, relevance and criticality. Related to this, in multi-sectoral complex operations there might be no substitutability between the prior actions of unrelated policy areas, which means that weaknesses of prior actions in one sector cannot be offset by relevant and critical prior actions in another sector. 6.10 Lack of focus on and delays in implement essential triggers can weaken the program. In terms of indicative triggers, the Bank has flexibility and discretion in its treatment of the triggers. The transition from Bank's former conditionality framework to the model applied in the series reviewed in this PPAR puts a high premium on sequencing the reforms and ensuring continuity, thus giving considerable significance to the role of triggers for the operations and the overall reform program. Dropping a trigger should be considered as an exceptional event, rather than a regular occurrence, permissible only if the risks to nonimplementation of reforms are duly addressed. 6.11 Partially met triggers require greater attention. Sometimes partially met triggers become prior actions even though they may be less relevant and critical than the originally proposed action. The dilution of content may be to such an extent that these actions would probably not have been considered as prior actions if proposed at the outset. The Bank should pay special attention to possible risks in adopting partially met triggers as prior actions, especially when there is not any realistic expectation that the full original reform will not implemented in a reasonable timetable thereafter. 6.12 It is crucial to have a strong knowledge base for upstream design of reforms and parallel technical assistance to support their implementation. Development partners were willing to put significant resources in these areas, in order to complement Bank financing and dialogue (Vietnam, prefers not to borrow, even on concessional terms, for TA). Selectivity is therefore needed to ensure that the most pressing needs are addressed. Should unmet demand remain, this may be tackled through complementary Bank TA operations, for instance in support of reform teams.151 However, these operations need to be carefully designed in order to match the timing and sequencing needs of DPOs (an issue that arose in the case of P135), and to ensure that the bulk of resources is allocated to meet specific implementation requirements, as opposed to general capacity building (such as purchase of vehicles and equipment, and training). Furthermore, this approach calls for outsourcing knowledge generation and advice to an appropriate mix of experts, both national and international, who can accompany the reforms in medium-term.152 6.13 The design and implementation of M&E for DPOs remains a challenge, and needs to be reconsidered each time a new operation is considered within a series. The PD.153 for the second PIR mentions a lesson learnt elsewhere, whereby an effective M&E mechanism should not just be based on administrative reporting. However, both the PIR and the PRSC suffer from this issue as M&E is not used as a mechanism for feedback and readjustment of activities to improve impact. The P135 is more successful in this area 151 FIAS 2008\. Reform Teams How the Most Successful Reformers Organized Themselves Reform teams consist of a small group of national experts who together with world-class expertise help Governments implement ambitious reforms. 152 In order to achieve such continuity, the experts' contracts may be based on a retainer model. Sorter procurement may also be achieved through framework contracts, whereby a short-list of competitively prequalified consortia/firms expected activities are called upon to provide experts within short delays of 2-4 weeks. The EU has successfully implemented this approach. 153 para. 71 124 because the mid-term review provided a venue for reassessing the implementation of the program. Even there, the change in PRSC indicators took place only for the last operation, although it had become clear much earlier that the relaxation of policy actions required an adjustment in indicators and goals. In both the PRSC and the PIR series there is a disconnect between development objectives, actions and indicators. In the case of the PRSC, there was a logical chain between objectives and indicators, but it is hard to see how some of the reforms would lead to the intended results (the attribution issue). The issue with the PIR is that while there is strong relationship between the reforms and results, their logical link to the development objectives is weak, especially after key reforms were dropped. Lessons Learnt â€“ Bank Approach 6.14 There is a need to reexamine how the Bank approaches sectoral DPOs and how this instrument is differentiated from investment lending. In Vietnam, the distinction between DPOs and investment loans has become blurred, especially with the practice of earmarking funding for the sector the programs support. It can be argued that the four sectoral DPOs might have been best supported by SWAPs and investment lending. The advantage of DPOs is that they disburse rapidly, support to the consolidate budget, and in practice promotes the use of national fiduciary and safeguards systems. However, this approach limits Bank inputs (say on a key study) on the ultimate use of the resources and their underlying processes. To avoid sharp trade-offs that may discourage the use of the most appropriate lending instrument, it seems that in the case of investment lending, it may be desirable to experiment, at least on pilot basis, with further harmonization/convergence between Bank fiduciary and safeguard procedures and national ones. 6.15 The Bank and other development partners should be willing to walk away from an unproductive policy dialogue and withdraw their support of low impact reforms. The delays in P135 (second operation), the second PIR operation and PRSC 10 appear to have been caused by concerns with the quality of the program. In the case of P135, the mid-term review largely addressed the main concerns. However, the last operations in both PIR and PRSC series cannot be readily justified by the contribution to objectives of the weak reform they supported. 6.16 The Bank's recent guideline that suggest to limit the number of operations in a series to three constitutes an appropriate measure. Long-term DPO series need to be kept relevant by maintaining a high level of ambition with respect to the reforms they support. As evidenced by the second PRSC series, a longer-term approach may be hard to sustain. 6.17 Knowledge generated and/or embodied in Bank operations should be properly documented and made public. Bank disclosure policy call for documents it produces being made public, unless classified as confidential. Furthermore, to the extent possible, documents on which policies are based should be easily identifiable and retrieved. In order to preserve knowledge and improve transparency, PDs should properly refer to studies (in some cases the title cited was incorrect) and provide URL links. There is also a question whether disclosure policy is strictly respected (e.g., some energy studies do not appear to have been made public). 125 6.18 It is difficult to evaluate the performance of DPOs in Vietnam without the benefit of a clear reference on what constitutes the norm. This review identifies strengths and weaknesses in the Vietnam DPOs by referencing their own internal logic. However, it is unable to systematically address questions such as how did the Vietnam second PRSC series compared to other PRSCs in terms of ambition, design, results etc. This may result in inconsistency in ratings across countries and projects (ratings contain a subjective element based on the skills, experience and perception of the evaluation team, as well other factors). This issue seems to argue in favor of a new meta-evaluation154 of completed PPARs on similar DPOs, with lessons learnt and recommendations on a more consistent cross-country approach to be reflected in future individual operation evaluations and/or PPARs. Specific Lessons Learnt from P135 6.19 Budget support may not be the best instrument for financing a sector investment program. While a budgetary support operation for a CDD-type program turned out to be moderately satisfactory in the case of Vietnam, the Bank and other development partners had taken a considerable risk. For most countries, it would be highly advisable that the training, at least of the critical personnel (which in a highly decentralized program means a very large number of people), would be done in advance and that an M&E system were in place at the start of the program. There was much retro-fitting under the P135 series that could have been avoided. 6.20 The state of decentralization needs to be fully factored into the design and implementation of targeted poverty programs. Decentralization of government institutions and introducing greater participation at the commune and village levels was an objective of the program as a tool to empower the targeted communities. Various monitoring indicators were used to measure progress on this front. But they did not provide an idea of what would have been good practice in terms of an optimal level of decentralization and participation given the stage of development. An alternative approach could have been to select a control group of provinces that had been decentralizing on their own and could serve as a comparison group for the provinces attempting to develop decentralized structures under P135. That could have enabled the selection of a group of indicators to be used for measuring success before the start of the operation 6.21 Production support to poor communities needs to be tailor-made and well thought through. Much was made of expanding the production component of the program. But the targeted communities were seriously underdeveloped for good reasons. They were remote, mostly mountainous, often forested, and inhabited by people who have eked out livings in these places for centuries. Such places are notoriously difficult to develop and there are few success stories around the world to give guidance. Packages that had worked in other parts of Vietnam (typically used in the more hospitable lowlands) were not likely to be relevant, and subsidies are not sustainable in the long run. This portion of the program could have been better thought through and explored through a series of pilot projects rather than being a part of a budget support operation. See IEG 2010 for an evaluation of PRSCs based on operations completed and evaluated by 2008. 6.22 Good analytical work, economic and other, contributes to success. Populous countries with large externally financed programs, such as Vietnam, are likely to benefit from an amount and variety of analytical work, typically using standard economic tools. Smaller countries with more modest analytical programs can probably learn useful things from a selective reading of the analytical work performed in more abundantly staffed countries. But Vietnam also profits from relevant non-economic analytical work that illuminates the likely behavior of the people involved both at the highest levels as well as at the village level in a way that informs the design of the programs. This sort of work is important but by its nature country specific.155 6.23 Well-designed impact evaluations are a valuable dimension of M&E. The impact evaluation turned out to be very important in assessing the impact of P135, not only regarding poverty but also non-income components of welfare, participation, decentralization and empowerment. This has direct relevance to other National Targeted Programs in Vietnam and elsewhere. It is important that funding of such activities be included in the original project design as their late inclusion may lead to implementation difficulties. 6.24 Vietnam's social compact was instrumental in supporting certain achievements, but may not be readily replicable elsewhere. Vietnam's reforms have relied on a top-down approach, which nevertheless draws in various stakeholders into the program and strengthens their ownership and voice. This is notably the case for targeted programs such as P135. While the country's history and social compact are quite specific, there are generic elements, such as effective engagement of local political authorities and communities that may be useful elsewhere. An example was Martin Rama's Making Difficult Choices\. Vietnam in Transition (2008). For behavioral implications at the village level the best example would be Edwin Shanks et al CDD in Vietnam (2003).
P107101 | Kabul Urban Roads Improvement Project | South Asia | Afghanistan | IDA | FCS | Infrastructure | Transport | RETF | IPF | 2009 | 2012 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/570511474750627126/text/000020051-20140625220900.txt | http://documents.worldbank.org/curated/en/570511474750627126/pdf/000020051-20140625220900.pdf | The following lessons are taken from the ICR with some adaptation:(p 12 -13):In the absence of implementation capacity in the implementing agency, it is prudent to ensure the establishment of a strong project management unit well before financing becomes effective. Project Preparation Funds may be used to employ essential staff of the unit before the project is approved.The implementing agencies must be made aware of their obligation to pay their bills on time, when the work has been done in compliance with the contract. This requires training staff to understand the requirements of the contracts and payment procedures, financial management systems, and appropriate delegation of decision authority.Contract packaging should be done to limit the number/size of contracts that can be awarded to a single contractor to an appropriate level. This can mitigate the risk of over-relying on a single contractor and possible poor implementation performance.IEG Lesson: Projects that aim at reduction in traffic congestion should include activities that would establish a traffic management system for the corridors and at key junctions, including introduction of physical barriers between opposite lanes, traffic signs and signaling, with associated regulations, enforcement mechanisms and incentives.
P107137 | BO PICAR Community Investment in Rural Areas | Latin America and Caribbean | Bolivia | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2012 | 2021 | 2022 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/210741636757170860/text/Bolivia-BO-PICAR-Comm-Investment-in-Rural-Areas.txt | http://documents.worldbank.org/curated/en/210741636757170860/pdf/Bolivia-BO-PICAR-Comm-Investment-in-Rural-Areas.pdf | The ICR presents eight lessons arising from this project (ICR, paras. 98 105), including project-specific aspects andaspects applicable to other countries. This ICRR focuses on consolidating key elements of the eight lessons into fourstrategic lessons arising from this project, which focus on aspects which are potentially relevant for other similarCDD-type of projects.(a) Lesson 1: Leveraging the enhanced roles and capacities of key actors toScale-Up and Sustain CDD approaches and Sustainable Results: A lesson from this project is the importance devotingsubstantial financial and technical resources to strengthening the complementary roles of relevant key actors (in this case, threeactors) in the design, implementation and OM of the project/subprojects (ICR, paras. 98, 102 and 101):(i)EMPODERAR (the Government project coordination/management entity), with respect to ensuring: proper application of the subprojectcriteria and fostering strong CDD approaches by the target beneficiary communities; adequate autonomy and accountability; technicalsoundness and stability of management and staff; accordingly, such an entity can play a vital role in scaling-up the CDD approachat national level, while fostering strong coordination and collaboration with other relevant actors;(ii) participatingtargeted communities, which were empowered in specific ways to design, implement and sustain the subprojects, including subprojectcycle management of resources and fiduciary responsibility, based on community participating planning (CPP) strategies andprocesses, and therefore, demonstrate the viability of scaling-up sustainable CDD approaches to development;(ii)gender/women, guided by a gender strategy especially in their roles to prioritize community needs and sound implementation andOM of project-financed subprojects, taking a CDD approach; accordingly, ensuring an active role of women in each participatingcommunity will enhance the prospects of successful scaling-up the CDD approach and investments for povertyreduction.(b) Lesson 2: Strategic Role of Geo-Referenced Management Information System/MIS (ICR, para.99): The lesson in this project is this type of MIS system provided a useful tool for enabling project management toensure: effective project implementation and ME; the generation of a major geo-referenced database of communities, beneficiaryhouseholds, infrastructure and other assets, which was assembled as part of an effective ME system, and thereby providing auseful tool for enhanced project management decision-making and a useful data base for enhancing projectmanagement.(c) Lesson 3: Operationalizing Various Complementary Dimensions to Sustainability of CDDProjects (ICR, para. 103): The project highlighted the lesson of the importance and relevance of operationalizing variouscomplementary dimensions to achieving sustainability, especially for CDD-type of projects, including assigning an active role ofwomen in the CPP cycle. These elements, which comprise positive lessons for similar projects, include:(i) The projectpromoted social sustainability by building on existing local-level institutions and forms of government, laying the groundfor decentralized conflict resolution. Social sustainability is the bedrock on which other forms of sustainabilityrest;(ii) PICAR delivered asset sustainability (infrastructure and services) because communities were sufficientlyempowered and organized, including assigning an active role of women in the beneficiary community organizations/committees, toassume full responsibility for OM, particularly for productive infrastructure and micro-irrigation subprojects;(iii)the project demonstrated the importance of and practical approaches to promoting fiscal and environmental sustainability,which involve additional transfer of responsibilities to beneficiary communities to reinforce long-term management of resources,including OM and assigning an active role of women in the local community committees, within a decentralized approach andpolicy framework to sustainable development.(d) Lesson 4: Importance of Working Out/Agreeing Early AppropriateEvaluation Approach/Tool (ICR, paras. 104 105): Given the strategic importance of a sound evaluationsystem/tools to assess the results of the project on targeted beneficiaries and public policy (e.g., retention of population inrural areas), and therefore the potential role and rationale of scaling up the projects investments to other parts of thecountry, the project demonstrated the project lesson of the importance of working out and agreeing early (preferably during designphase and year 1) on the most appropriate evaluation tools and approach to the project.
P107139 | Sustainable Land Management Project | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2008 | 2014 | 2016 | ICRR | >=10 million & <25 million | Satisfactory |  |  | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/109811468001176696/text/ICRR14656-P107139-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/109811468001176696/pdf/ICRR14656-P107139-Box393183B-PUBLIC.pdf | The ICR draws multiple lessons. The most pertinent are consolidated and adapted below:A programmatic approach establishing and scaling up Sustainable Land Management efforts can generate a number of benefits despite the initial transaction costs associated with convening and aligning financing, experiences and approaches among partners and stakeholders. Technical assistance during preparation is important for ensuring the success of such an approach.For projects with a decentralized implementation structure, high staff turnover of technical staff at the local level as well as changes in key focal points and development agents can be detrimental to the quality and timeliness of implementation. Enhanced recruitment procedures, appropriate incentive mechanism (working conditions, training, etc.) and harmonization of salaries and benefits among district staff working on different projects are important for minimizing such disruptions.Sustainable local institutions are critical for the effective delivery of services required to implement sustainable land management programs and technical assistance for building their capacity should be built into project design. In this case, implementation of project activities were more effective in areas in which local level implementation structures were established and sustained through technical assistance, targeted capacity building and reward and incentive schemes.Area closures can be effective mechanisms for environmental rehabilitation, climate resilience and reclamation of biodiversity but they require strong community engagement and commitment. Community by-laws can be instrumental in bringing this about.
P107139 | Sustainable Land Management Project | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2008 | 2014 | 2021 | PPAR | >=10 million & <25 million | Satisfactory |  |  | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/126731603826296434/text/Ethiopia-Sustainable-Land-Management-Project-I-and-II.txt | http://documents.worldbank.org/curated/en/126731603826296434/pdf/Ethiopia-Sustainable-Land-Management-Project-I-and-II.pdf | 3. Lessons 3.1 The watershed management approach can lead to significant land restoration when appropriate structural and biological measures are introduced to treat the affected landscape with active participation of the local community. Treatment of the upper catchment and the fast-growing gullies with reinforced gabion check-dams and vegetative cover was critical in controlling soil erosion from its source upstream. Demand-driven community participation is key for the uptake and effectiveness of watershed interventions. In some highly erodible catchments (for example, the Dalocha watershed in Gimbichu), the resource-poor communities were willing to contribute labor but required a supply of capital items for treating large gullies. The lesson is that natural resource restoration advanced significantly when the right SLM practices were implemented to arrest and reverse degradation. 3.2 Area closures are relevant for the restoration of degraded lands but require increased investments for alternative supply of forages to convince the local communities to forgo these benefits during the process of natural regeneration. Livestock feed is a very limited resource in many land-scarce and intensively cultivated highlands. Some communities that agreed initially to enforce area closures were highly reluctant or unwilling to implement area closures unless alternative sources of fodder and fuelwood were available (for example, some microwatersheds in Upper Guder, Amhara). Controlled harvesting of livestock feed and beekeeping activities within area closures facilitated compliance. The lesson is that a supply of alternative sources of livestock feed and fuelwood, information about the long-term costs of traditional freegrazing systems, and a shift to a phased approach to area closures, which allows communities to successively put more communal land into conservation, can all enhance the local acceptability and viability of this model for land restoration. 3.3 Farm productivity growth requires arresting both the on-site and off-site soil erosion to prevent degradation of farmlands and to enable investments in modern farm inputs. Given the geospatial interdependence within watershed landscapes, farmland restoration and the use of productivity-enhancing inputs significantly depends on controlling the off-site erosion originating upstream. A good example is the farm productivity growth in the Adikelkel microwatershed (in Enderta, Tigray), where arresting soil erosion and runoff originating from the upper reaches was critical to achieving sustainable intensification and productivity growth on farmlands in the lower valley. The lesson is that farm productivity growth requires arresting both the on-site and off-site soil erosion that leads to degradation of farmlands and therefore lowers incentives to adopt SLM practices and modern inputs. 3.4 Effective demonstration of up-front economic and livelihood benefits is fundamental for smallholder farmers to protect and maintain the SLM practices introduced on their lands through project support. Past soil and water conservation investments promoted through governmentand donor-supported programs were not sustained by farmers mainly because of limited local participation and ownership and the focus on structural measures that do not bring short-term benefits. In Ethiopia, many smallholder farmers are unable to forgo immediate benefits for long-term sustainability gains. The lesson is that the SLMP, under the two phases, was able to overcome this challenge through proactive local participation and the demonstration of up-front economic benefits, such as increased crop and livestock production and other incomegenerating activities, which are critical for continued interest in and maintenance of the soil and water conservation structures. 3.5 In drought-prone areas, small-scale irrigation is the key enabler for translating the benefits of land restoration into reduction in household vulnerability to climate shocks through income diversification and protection against droughts. Small-scale irrigation is the most cherished component of the SLM package in Ethiopia and has become the game changer in creating incentives for improved watershed management. Water harvesting and small-scale irrigation also offered opportunities for income and dietary diversification, allowing households to grow high-value fruits and vegetables throughout the year. This created additional income and employment and reduced the pressure to migrate to the cities or other areas, especially for youth. Small-scale irrigation also provides protection against drought (for example, the Weinalem microwatershed in Raya Azebo, Tigray). The key lesson is that in high-pressure and drought-prone productive landscapes like the Ethiopian Highlands, water harvesting and small-scale irrigation establish strong links among land restoration, resilience, and reduction in human vulnerability. 3.6 Market-oriented agroforestry interventions (for example, Acacia decurrens) that bring sustainable income for smallholders can be vital ingredients in creating incentives for the adoption of biological measures for land restoration and improving resilience to climate shocks. Agroforestry systems, such as Acacia decurrens, that bring additional benefits through nitrogen fixation while also generating cash income are vital win-win options for land restoration, income growth, and asset creation. The lesson is that in the microwatersheds where such market-oriented agroforestry practices have been supported (for example, Akusty in Fagita Lekoma, Amhara), this has induced transformational changes in restoring highly degraded landscapes, creating employment, generating income, and reducing poverty and out-migration. 3.7 Watershed management programs can have differential impacts on the landless, women, and youth, but such trade-offs can be reduced by promoting inclusive livelihood activities and land certification to reallocate communal land. The SLMPs promoted off-farm youth employment and gender-inclusive programs, including the keeping of small ruminant livestock, poultry, and bees. In addition, many communities adopted the sharing of grass and biomass from treated communal lands, actively benefiting the poor and landless. Reallocation of communal land to landless youth has also created incentives for improved management while generating some employment and income benefits, especially when opportunities for youth migration are limited. The lesson is that, although area closures in some locations forced women to travel long distances in search of fuelwood, this challenge was mitigated in some cases through onfarm agroforestry production in conjunction with controlled harvesting of biomass in closed areas. 1Sustainable land management is defined by the Food and Agriculture Organization of the United Nations as the use of land resources, including soils, water, animals, and plants, for the production of goods to meet changing human needs, while simultaneously ensuring the long-term productive potential of these resources and the maintenance of their environmental functions (http\.//www.fao.org/nr/land/ sustainable-land-management/jp/). Typical SLM practices include the following\. physical soil and water conservation; flood control and drainage; water harvesting and runoff management for multiple uses; soil fertility management and biological soil conservation; agroforestry, forage development, and forestry; and gully control. 2 The second-level land certificates use geospatial data to better define a plot's location, size, and boundaries to provide landholding rights. These certificates show all the different parcels managed by farm households and include women as equal landholders. These improvements from the initial first-level certificates are expected to facilitate access to finance (serving as collateral), facilitate land rental and lease transactions, and help resolve land-related disputes. 3 Structured discussions with focus groups and key informants, including communityand woreda-level watershed teams, were held to solicit information on the extent of adoption of SLM practices; changes in the levels of soil erosion, runoff, and vegetation cover; use of improved inputs; crop and biomass yields; and changes since the beginning of the SLMP, separately for farmland and communal lands. As outlined in the protocols (see appendix C), this information was summarized in detail for each case study and was used to provide a performance rating in terms of achievement of the project objectives. The IEG team also assessed the livelihood and vulnerability effects in terms of changes in food security, water security, and outmigration. 4Given the sampling approach, the distribution of ratings in each region does not represent the regional situation. The interpretation is only valid at the aggregate level (across the three regions). This applies across all the tables where similar ratings are presented. 5 The separate performance ratings for Sustainable Land Management Project I and SLMP II shown in appendix C are consistent with the joint performance ratings given for reducing land degradation and improving land productivity. 6These findings are consistent with other evidence showing that the returns on SLM investments are higher in drier areas, where rainfall is a binding constraint to productivity growth and SLM offers moisture conservation benefits that facilitate land regeneration and yield growth (for example, Kassie et al. 2008, 2009). 7 However, the Implementation Completion and Results Report for SLMP II stated that some 9,661 landless youth were issued second-level land certificates or other legal documentation to use communal landholdings in exchange for restoring land. 8The regional coordination units also serve as the coordinators of the watershed management and SLM activities supported by other donors (for example, the International Fund for Agricultural Development, KfW, and the German Agency for International Cooperation).
P107146 | Acre Social and Economic Inclusion and Sustainable Development Project - PROACRE | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2009 | 2022 | 2023 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/099061223192036306/text/P107146028cfc80a1099b00c1442bfb2566.txt | http://documents.worldbank.org/curated/en/099061223192036306/pdf/P107146028cfc80a1099b00c1442bfb2566.pdf | The ICR included eight lessons. The following three lessons are emphasized with some adaptation of language:1.An operation focused on key, well defined issuescan help keep an implementation schedule on track despite shifting governmentpriorities and/or weakened government commitment.This projects experience demonstrated thata broad,poorly defined scope associated with a poorly delineated implementation timeline resulted in an extended implementation period thatlasted 13 years.2.Supporting agricultural development activities in remote areas can benefit from arealistic upstream analysis that serves as the foundation for the overall approach to productive activities and marketing.The main challenges in remote rainforest areas include high transport costs, weather-dependent logistics, and compromised access totechnical assistance and credit. Hence, successful implementation of investments in agricultural production in such remote areasrequires sufficient value addition to render the activities competitive, as well as a well-organized value chain downstream withparticipants that are motivated to work with suppliers and buyers from remote areas because of a unique feature of the products. Inthis project the examples were anticipated to be Brazil nuts and other nuts and fruit, but enduring marketing partnerships were notdeveloped.3.The preparation of an Interim ICR for an original loan constitutes acritical input for the preparation of the final ICR when an AF extends the overall implementation period and/or creates two clearlydistinct implementation phases. Non-observance of this provision can significantly complicate the preparation of the finalICR, in particular when the AFcreates the conditions for two different phases in project implementation, and where theinstitutional memory of the first phase has largely disappeared.
P107159 | MX Urban Transport Transformation Progr | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2019 | 2020 | ICRR | >=50 million & <100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/204701578926572072/text/Mexico-MX-Urban-Transport-Transformation-Progr.txt | http://documents.worldbank.org/curated/en/204701578926572072/pdf/Mexico-MX-Urban-Transport-Transformation-Progr.pdf | The ICR (p. 39 to 41) provided several lessons learned which were adapted by IEG: Ensuring implementationreadiness before project approval is critical for mitigating any potential risks to a successful implementation.This project could have benefitted from conducting a market analysis to confirm more potential borrowers, identifying mitigationmeasures for the risk of low demand for project financing and identifying the opportunity for BONABRAS to on-lend to privatecommercial banks with confirmed demand and capacity for processing loans to private operators. Also, more attention at preparationcould have been given to effective coordination between BANOBRAS and PROTRAM. Flexible technical requirementsbenefit national programs when they can be adapted to the context of local needs. In this project, PROTRAM hadseveral requirements such as all sub-project promoters creating a transport authority, approving an integrated mobility plan, andhaving an appropriate technical, economic, and legal structure and assessment . Low-emissions programs benefitfrom improving public transport. Low-carbon vehicles may be more successfully introduced to private operators when the additionalclimate and environmental benefits are clearly explained. In this project, the introduction of low-carbon vehicletechnology added complexity, higher potential investments costs, and technology risks that negatively impacted projectimplementation and deterred private operators from seeking resources for the purchases of buses.
P107163 | ID-Infrastructure DPL (IDPL) | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2008 | 2008 | 2014 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/835061474576042640/text/000020051-20140625184514.txt | http://documents.worldbank.org/curated/en/835061474576042640/pdf/000020051-20140625184514.pdf | The ICR lists several lessons including the need to link performance indicators to development objectives through a results framework. In addition, there are lessons on how to retaining the focus on the overall objectives: with so many indicators, not all equally important, progress on some inputs and the urgent need to specify "prior actions" for the next loan give an illusion of progress.One additional lesson is the need for a thorough a mid-term review that takes stock of any progress, and alerts senior officials in government on what remains for the objectives to be attained. If an important issue was overlooked initially, or framed poorly (e.g. regressive subsidies instead of how to de-politicize electricity pricing), a mid-term review could have introduced it as a prior action for the loan that followed. A series of programmatic loans require mid-course corrections, and subsequent loans should not proceed on autopilot with perfunctory approvals.
P107218 | Poverty Reduction Support Credit (PRSC1) | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2011 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/629931474633174326/text/000020051-20140626112412.txt | http://documents.worldbank.org/curated/en/629931474633174326/pdf/000020051-20140626112412.pdf | The broad thrust of the lessons in the ICR is supported:Success will be more likely in reform areas which coincide with the Governmentâ€™s own priorities and where the Bank has other instruments to engage outside the budget support frameworkWhile a budget support framework can provide a platform for sustained dialogue, by itself it has limited leverage in influencing Government policy and institutional actions in situations where official development assistance is sharply declining as a share of Government resources. The Bank should be cautious in proceeding with programmatic approaches such as PRSCs when government commitment is uncertain, and donor priorities are shiftingThe Bank should effectively manage transitions within the Bank team to ensure that reform programs stay on track, and relationships are protected between the Bank, Government, and development partners.There is a need to develop more granular, outcome indicators of public sector performance that are achievable within the term of a PRSC series. Sectoral operations are important to carry out alongside PRSCs in supporting energy sector reforms, with energy outcome indicators that address core issues of sustainability. In addition, the Bank should use indicators in policy operations that are forward looking, and not seek targets that have already been achieved prior to the appraisal of such operationsThe Bank should also carefully consider the implication of changes to the basic underpinnings of the macro framework, such as a sharp uptick in the fiscal deficit, during implementation of a PRSC programFinally, a lesson learnt from PRSC3 is that in the face of waning commitment to the original program from Government and donors, closing the series early and moving forward on a new programmatic basis may yield better development outcomes than persisting with the original design.
P107242 | LaoPDR Fourth Poverty Reduction Support Operation | East Asia and Pacific | Lao People's Democratic Republic | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2009 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/662231474634349460/text/000180307-20141201111524.txt | http://documents.worldbank.org/curated/en/662231474634349460/pdf/000180307-20141201111524.pdf | IEG concurs with the lessons derived by the ICR, including the importance of:(1) Complementarity between policy and institutional dialogue through PRSO and existing investment and technical assistance projects is critical for the success of reforms.(2) Adapting to the political economy of reforms, identifying champions in government with a reasonably well-defined reform agenda and engaging with a broader range of actors, and selecting focused sector engagement were PRSO work has a clear comparative advantage.In addition to these lessons from the ICR, IEG notes the importance of selecting performance indicators, ex ante, which can be benchmarked and monitored.
P107254 | Integrated Early Childhood Development Project II | Eastern and Southern Africa | Eritrea | IDA | FCS | Human Development | Education | IDA | IPF | 2008 | 2009 | 2011 | ICRR | Less than 10 million |  | Moderately Unsatisfactory |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/208311474555795757/text/000020051-20140624162635.txt | http://documents.worldbank.org/curated/en/208311474555795757/pdf/000020051-20140624162635.pdf | The NCO offers no lessons. IEG would draw the following.Ensure that all the standard Bank requirements are included in the Financing Agreement Package and that they are explained to the Borrower at negotiations, if required. This project was cancelled due to the Borrower's refusal to sign the Supplemental Letters that were not included in the Financing Agreement Package. The Borrower's view was that they did not need both as the FA was adequate. The Bank should have recognized the problem earlier and implemented a strategy and dialogue to fully understand the Borrower's concerns and assure the Borrower that the Supplemental Letters were an additional requirement for this operation but a standard requirement for all operations.
P107256 | Blue Nile Start-Up Emergency Project | Eastern and Southern Africa | Sudan | IDA | FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2008 | 2012 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/953441468178155417/text/ICRR14628-P107256-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/953441468178155417/pdf/ICRR14628-P107256-Box393183B-PUBLIC.pdf | The ICR provides a useful set of lessons (pages 17-19). Of particular importance is the need for realism in local capacity and in the government's capacity to provide financial support. The lessons also note the importance of adjusting to local context and of developing a good results framework even in a weak environment.
P107288 | SN- DPO-Public Financial Support Credit | Western and Central Africa | Senegal | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2011 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/853831474504975187/text/000020051-20140624195623.txt | http://documents.worldbank.org/curated/en/853831474504975187/pdf/000020051-20140624195623.pdf | The ICR contains a long list of good lessons for designing a well-focused DPO program. Three of these lessons stand out: 1. Field placement of staff greatly enhancing the Bank's capacity to quickly and appropriately respond to country needs in a rapidly changing environment. 2. Key PFM reforms can be supported by DPOs in an effective manner, but often need to be complemented by technical assistance operations to follow through and better implant reforms in government ministries. 3. Policies governing Bank support for public agency reforms should be carefully evaluated, since in Senegal, and perhaps a range of other countries, improved public sector management appears to be a more appropriate course of action, at least through the medium term, than privatization and liquidation.
P107300 | Pakistan: Sindh Education Ssector Project (SEP) | South Asia | Pakistan | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2009 | 2012 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/712281475080215412/text/000020051-20140626001130.txt | http://documents.worldbank.org/curated/en/712281475080215412/pdf/000020051-20140626001130.pdf | Several lessons are reported in the ICR (p. 25-26), which IEG has synthesized to the following:Strong political commitment and ownership are critical for successfully steering a sector-wide reform program addressing governance and accountability. This required the Government to challenge vested interests to make changes from patronage-based teacher recruitment. The support by all levels of the Bank was continuous and intensive, which helped keep momentum since it provided needed support at critical points. A realistic assessment of capacity is important to inform the design and sequencing of reform programs for optimal impact. Using an incremental approach to strengthen district education management facilitated effective implementation. Diagnostic assessment of student learning is an initial point, but not sufficient. Capacity improvements are needed in test design, administration, analysis, and wide dissemination of findings to stakeholders and the public. The Reform Steering Committee provided high-level oversight and interdepartmental coordination of the reform, but did not replace the need for consistent oversight at the local level. Such a high-level group could not provide oversight with sufficient regularity and focus on the local level. What may have been effective was more active participation along with working groups at the provincial level to guide and resolve issues, as well as an oversight mechanism at the lower level. District performance remained less than ideal during the project, and so stronger coordination was needed between departments to push forward the reform.
P107303 | MW-PRSC-2 | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2012 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/725301474854089207/text/000020051-20140625083421.txt | http://documents.worldbank.org/curated/en/725301474854089207/pdf/000020051-20140625083421.pdf | The ICR highlighted six key lessons learned from the implementation of the PRSG series that are appropriate, noteworthy, and should inform the preparation of future DPOs. 1. The importance of government ownership. Key institutional reforms in agriculture and social protection were not implemented because of a lack of buy-in across the government. 2. The need to assess the political economy of sensitive reforms. The political economy dimensions of certain key reforms under the PRSG series (i.e., maize marketing, fertilizer subsidy, and social protection) were underestimated. As result, progress in implementation in these areas was slow and policy reversals occurred. 3. There is merit in working within a harmonized framework. CABS provided the authorities and Bank staff with a harmonized framework for the provision of budget support that also enhanced the quality of policy dialogue across donors and provided political leverage for good governance. 4. Flexibility in the program assessment framework should be encouraged. It is difficult to foresee all the relevant issues and internal/external developments at the beginning of a DPO series. 5. A robust and flexible M&E framework is important for tracking progress in PDOs. The MGDS M&E framework did not generate sufficiently comprehensive information for monitoring outcome indicators, particularly regarding tobacco market, fertilizer market, and commercial justice reforms. 6. The bar for policy reform should be set sufficiently high enough to mobilize change while avoiding overly ambitious and complex measures. An important lesson learned from earlier DPOs was that programs should be focused given existing institutional capacity constraints.
P107311 | National Decentralized Planning and Finance Program | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2010 | 2015 | 2016 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/769061467297906396/text/ICRR-Disclosable-P107311-06-30-2016-1467297887807.txt | http://documents.worldbank.org/curated/en/769061467297906396/pdf/ICRR-Disclosable-P107311-06-30-2016-1467297887807.pdf | This ICRR endorses the following lessons (summarized) from the ICR (pp. 26-27):Reviewing andrevising the projects results framework midway through implementation would help ensurethat the indicators being monitored are appropriate in tracking the projectsachievements. Project teams often select indicators without taking into account their ease of tracking and their relevancein revealing the projects achievements. Once they have gained this experience, they should use the opportunity of themid-term review to thoroughly review the relevance of the indicatorsInstitutionalizing community participationrequires commitment by government and an appreciation of its benefits. Community participation is an expensiveundertaking, especially in rural areas, where people must travel great distances to participate in meetings. Such an expense mustbe justified in terms of better decision-making and more satisfied citizens. Teams should consider undertaking citizen satisfactionsurveys periodically to assess how effective the measures promoting participation have been. This information could then be used todesign better approaches.Providing support only for capacity building without linking it to monitoring of thedelivery of infrastructure and services reduces the Banks andpartners influence in ensuring funds for these purposes are used efficiently andeffectively for district development. Because the capacity building and institutional strengthening supported underthisprogram were not aligned more closely with the inter-governmental transfer system nor any other tool to monitor theoutcome of the participatory planning process at district level, the Bank and partners could not review if the districtsfunds for investments were actually spent on citizens priorities.Working through country systems is goodpractice, but key systems should be in place from the outset to avoid implementation delays. The use of Mozambiquesfinancial management and procurement systems was an important design element of the project that contributed to strengtheninggovernment systems. However, the reliance on country systems can also become a bottleneck for implementation. It is thereforeimportant to ensure that key country systems that the project depends on are operationally effective in order to avoid delays inimplementation.Commitment and provision of resources for creation of a user-friendly computer-based performancemonitoring system allows for tracking of project outcomes and outputs across a large number of project entities. Theimplementing agency started to develop the district performance monitoring system under the previous project and maintained itscommitment throughout the project period. As a result, an effective system of tracking and reporting on district performance is inuse by all 128 districts, which is generating a wealth of information on the performance of districts across a range ofindicators.
P107313 | Fifth Poverty Reduction Support Credit (PRSC5) | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2011 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/378051474503650391/text/000020051-20140624160501.txt | http://documents.worldbank.org/curated/en/378051474503650391/pdf/000020051-20140624160501.pdf | IEG broadly concurs with the lessons noted in the ICR, in particular, the lessons pertaining to the importance of government ownership of the reform program and good donor coordination:(i) importance of strong government ownership, taking the time to nurture it, through dialogue and analysis of the political economy of reforms; and (ii) working together with the rest of the donor community through the G-19 is helpful, notwithstanding the difficulties and tensions resulting there from and in particular the rigidity of the PAF.
P107313 | Fifth Poverty Reduction Support Credit (PRSC5) | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2016 | PPAR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/746821469129481595/text/106459-PPAR-P083459-P103277-P107313-Box396277B-OUO-9-mozambique-0716.txt | http://documents.worldbank.org/curated/en/746821469129481595/pdf/106459-PPAR-P083459-P103277-P107313-Box396277B-OUO-9-mozambique-0716.pdf | 11. Lessons The following lessons have been drawn from this PPAR\. Â· Carefully chosen objectives and prior actions for policy development operations can provide the basis for the necessary conditions for better macroeconomic policy, good governance, and sound economic development. In the short term a number of reforms can be achieved either because of or in the wake of prior actions. For example the Central Revenue Authority was established in 2007 (a prior action for PRSC-4). Since then it received support from the Government of Switzerland (a member of the donor group providing general budget support) and performed well, raising tax collection from 15.9 percent of GDP in 2007 to 27.3 percent in 2014. Â· Policy development operations can reduce poverty by increasing growth and improving institutions that have responsibilities for poverty reduction, but that focus was not sufficient for significant poverty reduction in Mozambique. For example, GDP growth was sustained at between 6 and 7 percent per annum, prior actions requiring the Government to allocate at least 65 percent of its annual budget to priority sectors maintained the capacity of ministries that had a responsibility for delivering social services to the poor, and a number of social indicators was well maintained. However, the incidence of money metric poverty was reduced by only 4 percentage points over six years from a high poverty incidence of 56 percent in 2002/2003 to 52 percent in 2008/2009. Â· Development policy operations that use general budget support as the instrument for providing assistance can also be appropriate vehicles for the harmonization of donor strategic assistance. The Performance Assessment Framework agreed between the Government and general budget support development partners, if well crafted, can be the basis for fruitful cooperation among these partners. The downside risk is the possible constraint on the Bank's flexibility with respect to prior actions outside the Performance Assessment Framework. For example, the Bank needed to negotiate with general budget support donors to obtain their agreement to include additional actions on food security in PRSC-5 that were outside the Performance Assessment Framework. Â· The political economy context can have critical impacts on the achievement of policy reform. Understanding the political economy context for reforms in policy is critical to assessing the likelihood that reforms will take place. For example, a National Program for Decentralized Planning and Finance was to have been achieved as a prior action for PRSC-5. However, the political barriers to achieving internal agreement on a national plan for decentralized planning and finance were seriously underestimated and a plan was not approved by the Government during the PRSC 3-5 series.
P107314 | Nairobi Metropolitan Services Improvement Project | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2012 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/297851634305610281/text/Kenya-KE-Nairobi-Metropolitan-Services.txt | http://documents.worldbank.org/curated/en/297851634305610281/pdf/Kenya-KE-Nairobi-Metropolitan-Services.pdf | Adapted from the ICR (pages 25-26). The design of metropolitan development projects requires engagementwith local levels, incentives, and quick wins. The project experience indicated that engagement in metro-levelinfrastructure is not easily recognized or appreciated by local-level (county) governments, and that consistent interest in thecounties on metro level development cannot be assumed. It was the inclusion of the local/urban level infrastructure, an obviouspolitical gain for the counties and their elected leaders, that maintained their interest. Integratedplanning for metropolitan infrastructure and services, while challenging to coordinate, is necessary to establish a backbone foreffective metropolitan growth. Urban planning in areas that have already experienced human settlement and development ischallenging. This project, for the first time assisted in the preparation of the strategic and integrated development plans of themetropolitan sub-areas. These plans integrated land use, transport, environment, economic activities and social services. Theexistence of these plans ensures that the metropolitan emphasis on the development of the region ismaintained. Market rehabilitations can helpaddress the core needs of the urban poor; however,they are difficult to implement particularly where different levels of government need to coordinate. The projectexperience illustrated the processrequired identification of feasible relocation sites, first moving of the traders, thenmoving them back after the markets are completed takes time. Intensive engagement with the traders was carried out throughout theimplementation period.
P107335 | Governance Reform and Growth Grant - 3 | Western and Central Africa | Sierra Leone | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2011 | 2013 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/866571474631897892/text/000020051-20140625155055.txt | http://documents.worldbank.org/curated/en/866571474631897892/pdf/000020051-20140625155055.pdf | The following lessons are drawn from the ICR and considered especially important by IEG:1. Embedding policy reforms in the Governmentâ€™s reform agenda instills greater government ownership of the program, diminishing the risk of delays or shortcomings in achieving objectives.2. In a country short of management capacity, a detailed M&E framework is not likely to be sustainable without intensive donor inputs and supervision.3. The consistency in team leadership of supervision (as was the case in all three GRG operations) from appraisal of the initial operation and though completion can have a strong positive role in program performance.
P107343 | BI - Agro-Pastoral Productivity and Markets Development Project | Eastern and Southern Africa | Burundi | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2010 | 2020 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/897671613587675227/text/Burundi-Bi-Ag-Past-Product-Market-Devel.txt | http://documents.worldbank.org/curated/en/897671613587675227/pdf/Burundi-Bi-Ag-Past-Product-Market-Devel.pdf | The ICR presents 6 soundlessons (ICR, paras. 80-85). Thelessons that have broader application than this project havebeen summarized below, with some sharpening of thetext.(a)A communitydriven development (CDD) design can be successfully implemented in an FCV environment (para 80): This projectsuccessfully combined support to agriculture production, infrastructure development, and access to markets in a participatoryapproach at the grassroots, It was well suited as a model for other development operations in an FCV contextprovidingtargeted support to smallholders and rural entrepreneurs for increasing agriculture productivity, infrastructuredevelopment, access to market and capacity development of strategic actors, at various levels.(b)Innovations Require Adequate Time and Support to Implement and Become Sustainable (para. 81): Given theprojects introduction ofimproved technologyinvolving processing and sophisticated equipment in a low incomecountry like Burundi, the lessonis that the relevant project activities, especially if innovationsinvolvesophisticated equipment, should be carried out with a sufficient lead time, so that the project-funded equipment canbe tested and made functional, and to enable the operators to be trained, prior to projectclosing.(c) Importance of Integrating Crop and Animal Husbandry Support for EnhancedProductivity (para. 82): Most subprojects provided this type of integrated crops/livestock approach, since mostsmallholders cultivated crops and raised different types of livestock. Therefore, the project provided an important lessonregarding the rationale of the project supporting increased productivity of both smallholder crops andlivestockactivities, which contributed to symbiotic production increases, for the kinds of production conditions prevailing in the projectarea, or similar contexts. This point was also reinforced by the projects Impact Evaluation Study (2020) and by theBanks TTL to the IEG evaluator during the interview with the project team (note, January 27,2021).(d) Approaches to promoting a successful solidarity chain with widercommunity benefits will impart benefits to other beneficiaries (para 83): The producers benefiting from project-suppliedanimals (cows) had the obligation as part of their sub-projects to ensure that one of the offspring from the heifer would be givenfree of charge to another member of the Producer Organization (PO) under strict social control, thereby generating wider benefitsfor the community. These initial producer recipientsalso received specific training for enhancing their productivity. The ICRcorrectly recognized two factors, which are also lessons, which could apply to other countries with similar cultural conditions.The two emerging lessons from this projects solidarity chain are: (i) to ensurethe existence of appropriatepreconditions for this solidarity approach, where this process of a solidarity chain is particularly well attuned tothe existing local social fabric of Burundis/or another countrys rural areas, where population is dense, and strictcommunity rules and norms apply; and (ii) to includein the projects appropriate follow-up actions to ensure provision oftraining for the second-round beneficiaries to further enhance their benefits, and also to ensure viable approachestoscaling-up and sustainability of this mechanism to the next round of beneficiaries.(e) Sound MarketAnalysis is an ImportantNecessary Condition for any Project that Generates increased Production (para. 84): Theproject experience highlights the lesson, that a project which generates production surpluses, especially by smallholders, theimportance of carrying out sound ex-ante market analysis, including assessing: market potential and the competitiveness of thetargeted value chains; and realistic domestic and export market outlets.(f) Legislation to EmpowerProducer Organizations (POs) needs to be Timely to have a Sustainable Impact(para. 85): The project highlights thevital role of Water User Associations (WUA) to enable beneficiaries organizedinto POs tomanage and maintaincommunity-based infrastructure provided by the project, in this case, marshland irrigation infrastructure. Accordingly, theICR highlighted the importance and need for the project to overhaul the entire regulatory framework of WUAs to create and organizeindependent WUAs, which are essential to maximize project impact and improve sustainability, including collection of water fees andmanagement of the funds by WUAs. The projects specific lesson is to ensure that the project addresses relevantlegislative requirements early during project implementation to ensure adequate time for completion of legislation prior to project closure, to the extent feasible, or at least, to ensure clear follow-up arrangements so that legislation is completed within areasonable period of time.
P107350 | Water Resources Development | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2012 | 2020 | 2022 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/180331635980934684/text/Mozambique-MZ-Water-Resources-Dev-I-SIL.txt | http://documents.worldbank.org/curated/en/180331635980934684/pdf/Mozambique-MZ-Water-Resources-Dev-I-SIL.pdf | The ICR included six lessons, the following two are emphasized with some adaptation of language:1. To ensuresuccessful implementation of activities, the Bank and the Borrower need toinclude in the project design adequateimplementation support measuresthattakeinto account any capacity constraints. While the realities on theground did not allow the implementing arrangements to materialize as envisioned, the Bank and Borrower could have ensured adequatestaffing in light of the National Directorate for Water Resources Management growing portfolio. The Borrower must also ensure keypositions are filled with capable staff. While a program of technical assistance could potentially bolster implementation capacity,the provider should ideally be familiar with country and sector context in order to ensure advice is readilyapplied.2. To closea project with pending activities, afirm and tangible government commitment isneeded to finance and complete each of the remaining activities. This is particularly important for sensitive activitieswith potentially high risks, including reputational risks to the Bank, such as resettlement compensation and dam safety. Short ofproject extension, the Bank could devise a special instrument/vehicle to continue providing minimal financing mainly for softactivities that would enable the Bank to support clients in fulfilling its obligations and mitigating risks to both the client andthe Bank.The following additional lesson is emphasized by IEG:To ensure successful and timelyimplementation of projects that involve dams and related works,dam design and hydrological studies need to be ready at theonset of implementation. The project experience demonstrated that deferring the dam related designs to a later time duringimplementation not only caused significant delays, but also resulted in an unanticipated change in design. Dam design andhydrological studies need be conducted by reputable sources to ensure qualityand avoid costly changes duringimplementation.
P107355 | Governance and Institutional Dev. | Western and Central Africa | Cote d'Ivoire | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2008 | 2017 | 2018 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/489291525726412541/text/Cote-dIvoire-CI-Governance-and-Institutional-Dev.txt | http://documents.worldbank.org/curated/en/489291525726412541/pdf/Cote-dIvoire-CI-Governance-and-Institutional-Dev.pdf | The ICR (pp. 26-28) offers a number of insightful and broadly applicable lessons, including:Whencommitment from all parties is secured, assistance to conflict-affected communities can be effective. In this case, the Bankcommitted to continuous engagement even in a high-risk environment, taking advantage of opportunity and actively managing risksrather than avoiding risk and disengaging.Commitment and communications capacity is important at alllevels, including beneficiary institutions. In this case, beneficiary ministries were not adequately staffed and did not buyin at all stages of reform, forcing the PCU to assume the implementation role in the early stages of projectimplementation.Gender inclusion requires adequate analysis up front and targeted action in line with theresults of that analysis. In this case, the AFstarget for outreach tofemale beneficiaries in the cocoasector was based on an inaccurate estimate (whose source appears to be unknown) of women participating in cocoa cooperatives.Regardless of the realism of the target, reaching it would have required deliberate effort to include and support women, whichappears not to have been the case.
P107365 | Development Policy Lending 3 (DPL 3) | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2009 | 2009 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/908861474574723237/text/000020051-20140625061447.txt | http://documents.worldbank.org/curated/en/908861474574723237/pdf/000020051-20140625061447.pdf | The ICR has appropriate lessons.First, while the flexibility in DPLs allows adjustments when domestic political circumstances or external events compel these adjustments, it may be preferable for the Bank to focus on more narrowly defined and specific reforms with a different lending instrument in order to have impact and success. Second, joint action with other donors is at times imperative to obtain the desired result such as, in this case, procurement reform. Third, a good M&E system should ensure that the necessary information to monitor progress is readily available.
P107372 | Afghanistan Judicial Reform Project | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2008 | 2012 | 2013 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/369861475110764588/text/000020051-20140625220540.txt | http://documents.worldbank.org/curated/en/369861475110764588/pdf/000020051-20140625220540.pdf | Lessons include the following, drawing on the findings and lessons in the ICR: Multi-donor funding mechanisms can improve donor coordination, but coordination among government bodies may remain problematic;Thorough project preparation is essential, even in emergency situations;Designs should take into account implementation challenges such as inexperience of implementing institutions in working with Government financial and procurement systems, the time needed to recruit and train qualified specialists, and the varying levels of commitment to different reform objectives by key stakeholders within Government and implementing institutions;Human resources reforms should be integrated into overall civil service reform programs, and be properly sequenced, with pay reform held back as an incentive for adopting other crucial measures;More support than was available in this case is needed to build robust MGreat care is needed in judicious use of international expertise, taking into account the difficulties and expense of recruiting them in risky environments, and the risks of communication and cultural misunderstandings.
P107375 | Lesotho HIV and AIDS Technical Assistance Project | Eastern and Southern Africa | Lesotho | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2010 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/120101497633221851/text/ICRR-Disclosable-P107375-06-16-2017-1497633212723.txt | http://documents.worldbank.org/curated/en/120101497633221851/pdf/ICRR-Disclosable-P107375-06-16-2017-1497633212723.pdf | The ICR (pp. 37-38) cites a number of insightful lessons:In countries with high HIV prevalence,a national coordinating mechanism/platform to facilitate cross-sectoral collaboration is essential. In this case,when the NAC was closed, the resulting leadership vacuum negatively impacted this project and the overall nationalresponse.Line ministries are generally not suited for leadership of multisectoralefforts. In this case, after the closure of the NAC, coordination responsibility was housed with the healthministry. This led to challenges securing coordinating with other entities, particularly theMOLGC.When a project is significantly restructured, its intended outcomes may no longer match theoriginal project development objectives. In this case, even the original project design was not well matched withits stated objective of an effort to contain and reverse the epidemic.
P107398 | Budget Support | Western and Central Africa | Gambia, The | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2011 | ICRR | Less than 10 million | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/368681474851245770/text/000020051-20140624183701.txt | http://documents.worldbank.org/curated/en/368681474851245770/pdf/000020051-20140624183701.pdf | Performances1. Fiscal management objectives may conflict with achievement of other objectives. In the PSRGG, fiscal performance suffered partly due to increases in the wage bill; yet an increased wage bill may be needed to implement a more generous compensation policy that attracts needed professional staff to the civil service.2. Project performance indicators should measure the achievement of intended outcomes. In the PSRGG, the outcome indicators for civil service capacity (share of local training in training budget and coverage of the payroll by the IFMIS) are barely, if at all, indicative of the government's ability to recruit and retain qualified staff. 3. There is a significant risk that M&E arrangements that rely on existing institutions without adequate incentives in place will fail to deliver desired M&E outputs. After the release of the single tranche, it appears that the Government had little incentive to deliver M & E outputs, as reflected for example in the lack of some output indicators and the absence of any of the intended annual reviews.
P107407 | JM Education Transformation Capacity Building | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2010 | 2015 | 2016 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/663231468039545501/text/ICRR-Disclosable-P107407-04-20-2016-1461189957004.txt | http://documents.worldbank.org/curated/en/663231468039545501/pdf/ICRR-Disclosable-P107407-04-20-2016-1461189957004.pdf | Among the lessons identified by the ICR (page 22), two important lessons are noted: Even with delays in adoptinglegal frameworks, new agencies can be rendered functional and accomplish much in support of sector results. Indeed, the experienceacquired during the initial years ofnew agenciesfunctioning under this projecthas served to enhance dialogueand consensus among stakeholders and inform the fine-tuning of legislation, enabling their optimalperformance. Synergistic action of a range of institutions around the goal of school effectiveness and the quality ofteaching and learning can be achieved if prerequisite factors are in place: an evidence-based design; strong national consensus andshared vision, precipitated by extensive stakeholder involvement; clarity and complementarity of roles and responsibilities forachieving a common goal; strong capacity and effectiveness of each institution; public recognition and reward of good performance;and strong leadership and a change management approach that accommodates learning-by-doing.In addition,IEGidentifies two lessons: A countrys legislative environment will strongly govern the pace of introduction ofnew institutional processes and frameworks. Taking advantage of learning-by-doing asan operation evolves, andapplying appropriate solutions, can positively affect project outcomes.
P107456 | CV-SME Capacity Building and Economic Governance | Western and Central Africa | Cabo Verde | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2010 | 2015 | 2016 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/961351468227111784/text/ICRR-Disclosable-P107456-06-22-2016-1466626254406.txt | http://documents.worldbank.org/curated/en/961351468227111784/pdf/ICRR-Disclosable-P107456-06-22-2016-1466626254406.pdf | The ICR offers three technical and one operational lesson. The lessons point, inter alia,to the need for ensuring thepresence of a functioning project management unit early on and for providing adequate technical assistance.Inaddition to these, IEG offers the following lessons: Matching grants for SMEs represent a challenge thatrequire special skills in planning and execution. This project encountered significant capacity issues in operating thegrants, providing the necessary services, controlling the risks of abuse and assessing the results. It isessential to invest the time and resources to design and develop an adequate monitoring and evaluation system early on. Amongother things, the ME system can help determine the validity and feasibility of the results framework. This project didnot develop or implement a functioning ME system. It did not address the issue of missing or unreliable data until muchtoo late. It kept an outcome target that did not have any linkages to project activities until the last year ofoperation.
P107473 | Montenegro Institutional Development and Agriculture Strengthening (MIDAS) | Europe and Central Asia | Montenegro | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2009 | 2020 | 2020 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/267501592257082067/text/Montenegro-INSTIT-DEV-AGR-STRENGTH.txt | http://documents.worldbank.org/curated/en/267501592257082067/pdf/Montenegro-INSTIT-DEV-AGR-STRENGTH.pdf | The following lessons are drawn from the ICR with some adjustments in language:A prioritized and phasedapproach of measures allows for successful implementation of complex policy changes. The piloting and incrementalapproach adopted by MIDAS for implementing rural development grants in line with EU IPARD procedures helped stakeholders tostrengthen their capacities, identify and address bottlenecks in implementation, and gain practical experience before expanding tomore complex further measures. The considerable absorption rate of IPARD funds towards the end of the project demonstrated thesuccess of this gradual approach.Coordination of complementary strengths provide the basis for effectivecollaboration and the creation of synergies during project implementation. The case of MIDAS demonstrates that a strategiccollaboration and continuous communication between national and donor agencies can generate synergies in the design and supervisionof investments. MIDAS sector investments and institutional strengthening activities were complemented by EU technicalassistance, with the joint goal of moving the country closer to EU accession. This collaborative environment also allowed fortesting innovative approaches, such as over-contracting in MIDAS which was adopted in the IPARD program in Montenegro (ICR, para89).Structural sector weaknesses are not overcome by successful pilot projects and will usually need to beaddressed separately to make best use of the pilot results. While MIDAS successfully prepared its beneficiary agriculturalproducers and MSMEs for IPARD support, this process also highlighted the larger underlying structural issue of limited access torural finance to scale up producers capacity to pre/co-finance sector investments (like IPARD). Addressing such issuesrequires separate targeted action.
P107473 | Montenegro Institutional Development and Agriculture Strengthening (MIDAS) | Europe and Central Asia | Montenegro | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2009 | 2020 | 2022 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/895831642545683565/text/Montenegro-Institutional-Development-and-Agriculture-Strengthening-Project-MIDAS.txt | http://documents.worldbank.org/curated/en/895831642545683565/pdf/Montenegro-Institutional-Development-and-Agriculture-Strengthening-Project-MIDAS.pdf | 3. Lessons 3.1 A clear articulation of the expected transformation of the agriculture sector, and a logically associated and well-defined path to follow at the institutional and production level, is crucial in justifying reforms and achieving desired outcomes. The MIDAS case showed that aiming for change, such as for EU accession, can facilitate project implementation progress through strong government ownership of the project activities. It also helps to justify the essential reform processes (such as the establishment of the 2015 Law on Food Safety) and adjustments or restructuring of project activities (such as expansion to agroprocessors) where the link to reaching the overall goal is evident. 21 3.2 A practical â€œlearning by doingâ€ pilot approach can help identify and address bottlenecks and prepare the sector for new practices and procedures. In this case, the piloting and incremental approach adopted by MIDAS for implementing rural development grants in line with EU-IPARD procedures helped the sectorâ€™s different stakeholders at institutional and production levels to strengthen their capacities, identify and address bottlenecks in implementation, and gain practical experience before expanding to the more complex actual IPARD measures. Utilizing project funds to confirm that stakeholders can meet required procedures for future funding is an excellent way to ensure the sustainability of project outcomes. 3.3 Sector weaknesses need to be addressed in a holistic manner at institutional, administrative, regulatory, and production levels to comprehensively foster a countryâ€™s agriculture sector competitiveness. MIDAS addressed interlinked systematic weaknesses through a complementary and holistic approach involving a diverse group of sector agents. It further coordinated its efforts with other donors and actors in the sector to create synergies and avoid duplication. Such complementary efforts at different levels in the agriculture sector allowed agricultural producers and institutions to prepare for EU preaccession process requirements and modernize agricultural production. 3.4 Projects supporting compliance with market standards can help beneficiaries meet necessary conditions for market participation, but they do not guarantee market inclusion or expansion without connection support for new market linkages. MIDAS focused on enabling agricultural producer and agroprocessors to upgrade their standards but did not support them in fostering new market linkages. This opportunity could have provided further benefits in terms of stable offtake market sales and building business relationships. The transition to commercial viability of producers requires additional steps that ensure market access. 3.5 Access to finance for agricultural producers should be assessed at appraisal to test the extent to which limited credit is an overarching constraint to broader sector development. Although MIDAS successfully prepared agricultural producers and agroprocessors for focused IPARD support, its implementation also highlighted the larger underlying structural issue of limited access to rural finance that would increase producersâ€™ capacity to prefinance sector investments. Addressing this issue would require separate targeted actions that would need to be embedded in the project design or in complementary projects by the World Bank or other donors within a larger overall program. 22 1A referendum led to the foundation of Montenegro and its independence from the former Yugoslavia in 2006. 2The acquis communautaire, also referred to as the European Union (EU) acquis, comprises all of the founding rights and obligations of the EU, and its adoption is a condition of EU accession. 3Former president Milo Djukanovic, who was in power with the Democratic Party of Socialists for nearly 30 years, lost in the parliamentary elections in August 2020, and a new coalition government was formed in December 2020 under prime minister Zdravko Krivokapic. 4The Instrument for Pre-Accession Assistance for Rural Development (IPARD) is part of the EUâ€™s assistance supporting the transformation of the agriculture sector in EU candidacy countries. IPARD funds are managed by the candidate countryâ€™s own institutions. 5 Despite Montenegroâ€™s small size, the agroclimate and landscape vary significantly from the north to the south and coastal areas, allowing for diverse agricultural production: olive and citrus fruit production dominate on the coast, vegetable production and vineyards dominate in the center and near the agglomerations of NikÅ¡iÄ‡ and Podgorica, and livestock production dominates in the north. 6The Montenegro Institutional Development and Agriculture Strengthening (MIDAS) project underwent five restructurings and received two additional financings, leading to a total implementation period of 10 years. In December 2015, the first additional financing with â‚¬4.72 million from EU grants through a World Bankâ€“administered trust fund was approved and the project development objective revised, expanding the original project development objective by two elements to more granularly specify the intended objectives: â€œ(i) to improve delivery of government assistance for sustainable agriculture and rural development in a manner consistent with the EUâ€™s pre-accession requirements; (ii) to increase the experience of Montenegrin authorities in administering rural development grants in accordance with EU-IPARD core rules, and (iii) to support a selected number of agricultural holdings and food establishments in upgrading towards EU standardsâ€(World Bank 2020a). 7During MIDAS implementation, the name of the Ministry of Agriculture, Forestry and Water Management (MAFWM) was changed to the Ministry of Agriculture and Rural Development. At the time of this assessment, the ministry name had changed back to MAFWM. 8A matching grant is a one-off, non-reimbursable transfer to project beneficiaries for a specific purpose, on the condition that the recipient contributes a matching amount for the same purpose such as technical assistance, asset investment, or financing of working capital (IFAD 2012). 9The Integrated Administration and Control System (IACS) is an obligatory system used by EU Member States for the management and control of payments made to farmers under the Common Agricultural Policy. The IACS uses advanced techniques to check parcels by aerial or satellite photography and to cross-check farmersâ€™ claims with computer databases. It also ensures that payment irregularities are revealed and queries are followed up. 10 The IPARD program for each preaccession country is based on different measures set at the European level. IPARD measures focus on different aspects of agriculture and rural 23 development. Each country presents its program of IPARD measures to the European Commission for approval. When approved, IPARD measures are managed by countriesâ€™ national institutions and IPARD agencies. Montenegro has been accredited for three measures piloted in MIDAS: Measure 101, â€œInvestments in agricultural holdings to restructure and upgrade to the EU standards,â€ Measure 103, â€œInvestments in processing and marketing of agriculture and fishery products to restructure and upgrade to the EU standards,â€ and Measure 302, â€œDevelopment and diversification of rural economy.â€ 11 EUfarmers receive support in the form of direct payments on the condition that they comply with strict rules on human and animal health and welfare, plant health, and the environment. Additional payments are available, for example for farming methods that go beyond basic environmental protection or for farmers working in areas with natural constraints. 12More information on the IACS and related processes can be found at https://ec.europa.eu/info/food-farming-fisheries/key-policies/common-agricultural- policy/financing-cap/financial-assurance/managing-payments_en. 13 Twinning is an EU instrument for institutional cooperation among the public administrations of EU Member States and beneficiary or partner countries. Twinning projects bring together public sector expertise from EU Member States and beneficiary countries to provide support for the transposition, implementation, and enforcement of the EU legislation, building up the capacities of beneficiary countriesâ€™ public administration throughout the accession process. In Montenegro, two twinning projects took place during the MIDAS project implementation: the IPA 2008 twinning project from 2010 to 2012 and the IPA 2011 from 2013 to 2015. 14 There are three categories of food establishments in Montenegro, as per Article 122 of the 2015 Law on Food Safety. Category 1: food establishment is compliant with EU food safety standards and issued with an approval for operations; Category 2: noncompliance detected during inspection, and food establishment has six months to eliminate it as a condition of obtaining approval for operations; and Category 3: noncompliance has not been eliminated, and food establishment has 180 days to eliminate it as a condition of obtaining approval for operations. The Law on Food Safety applies to all stages of the production and distribution of food and feed, but does not apply to the primary production of food or feed for private domestic consumption, the preparation, handling, or storage of food for private domestic consumption, or feed used for feeding food-producing animals for private domestic consumption (MEK 2015). 15According to the International Organization for Standardization, ISO/IEC 17020:2012 specifies requirements for the competence of bodies performing inspection and for the impartiality and consistency of their inspection activities. 16Hazard Analysis Critical Control Point is a management system in which food safety is addressed through the analysis and control of biological, chemical, and physical hazards from raw material production, procurement, and handling, to manufacturing, distribution, and consumption of the finished product. 24 17The EU legislation (â€œThe Hygiene Packageâ€) includes provisions for flexible application of hygiene requirements in small and medium enterprises, which was also adopted by MAFWM during MIDAS implementation to raise the quality and safety of local products and traceability. 18 Of the 1,573 surveyed agricultural holdings, 711 were IPARD-like grant recipients, or successful applicants, 655 were farmers who had applied but not received an IPARD-like grant, or unsuccessful applicants, and 207 were control group farmers who had not applied for IPARD- like grants. 19 The socioeconomic assessment interviewed 182 agricultural producers and agroprocessors, of which 85 had applied for IPARD-like funds and 97 were the control group (MAFWM 2019b). 20 EachEU candidate country presents its program of IPARD measures to the European Commission for approval. When approved, IPARD measures are managed by the countriesâ€™ national institutions and IPARD agencies. 25
P107493 | Economic Governance Reform Project | Western and Central Africa | Guinea-Bissau | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2013 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/812781474508225175/text/000020051-20140625082751.txt | http://documents.worldbank.org/curated/en/812781474508225175/pdf/000020051-20140625082751.pdf | There are three main lessons that can be drawn from the experience of this project:Even in a difficult environment characterized by political instability and weak capacity, progress can be achieved by focusing policy lending on a few actions that are in line with the countryâ€™s own priority, politically feasible and technically ready thanks to a sufficient body of knowledge built through analytical work and technical assistance.Monitoring and evaluation should rely on predictable funding, possibly from the Bank through parallel operations or the use of trust funds. The M&E performance was negatively affected by the design choice of not creating new M&E systems and relying on the existing PRSP process or studies like the PEFA updates funded by other donors. In practice, the principle of avoiding duplication of efforts should be accompanied by an assessment on whether the need improvements or funding is likely to materialize within the program timeframe and by the preparation alternative measures in case either or both would fail to materialize.Not all risks can be managed by the Bank, in particular those concerning political instability. It is nevertheless clear that any progress will depend on the ability of the donor community to properly address the dominance of the military in the countryâ€™s history since independence and the infiltration of drug cartels in the countryâ€™s economic and political life. Without addressing the root causes of political instability, any progress achieved could remain essentially fragile.
P107498 | Fifth Poverty Reduction Support Grant-PRSC 5 | Western and Central Africa | Benin | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2013 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/344761474558359159/text/000020051-20140625225901.txt | http://documents.worldbank.org/curated/en/344761474558359159/pdf/000020051-20140625225901.pdf | The ICR draws a number of important and appropriate conclusions about defining realistic objectives and selecting results indicators that can be attributed to actions supported by the operation; and pursuing narrower, but deeper reforms, with more coherence across policy areas. (p. 52)Two lessons from this review are first, that linking the various triggers and prior actions more tightly to AAA, and to Benin's development challenges, explicitly defining objectives and expectations, and ensuring that accompanying measures would be undertaken could have improved outcomes, or at least strengthened the dialogue and monitoring.Second, while oversight during preparation of the various operations flagged potential problems, more explicit guidance from best practice findings would have been beneficial, for instance keeping the focus on a single sector in infrastructure, or maintaining a consistent dialogue in education and civil service reform throughout the series.
P107559 | Guiyang Guangzhou Railway | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2009 | 2017 | 2018 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/689171506351132832/text/ICRR-Disclosable-P107559-09-25-2017-1506351121957.txt | http://documents.worldbank.org/curated/en/689171506351132832/pdf/ICRR-Disclosable-P107559-09-25-2017-1506351121957.pdf | The following lessons are taken from the ICR, with some adaptation of language.(1) Unified control over railwayprogram development, project design, financing and implementation can help in achieving overall success.In the caseof this project,the China Railway Corporation (CRC) was solely responsible for planning, financing and implementingindividualprojects and creating delivery mechanisms. The unified control over the project enabled timely completion ofactivities.(2) Although agglomeration benefits have been recognized in theory with railway projects, there are fewquantitative data to assess the results. This may be due to the longer time span required for reaping such benefits. An expost analysis after five or ten years after the railways have been in operation could be undertaken to assess the quantitativebenefits.(3) The choice of a multi-project engagement can help the Bank in engaging in a broader policy dialogueand to support effective institutional change, even when the Bank financing is limited. Although Bank financing waslimited to a small percentage of project cost, this approach enabled the Bank to support a much wider and unified program ofrailway projects, to provide holistic support through policy dialogue with the Ministry of Railways and China Railway Corporationon sector reforms, and to ensure the application of Bank safeguard policies.(4) Good preliminary design, strictcontrol over compliance with standards and specifications can help in implementation of large and linear infrastructureprojects. In the case of this project an early and good preliminary project design was the basis for the feasibilityreport and initial cost estimates. The subsequent detailed design did not deviate significantly from the preliminary design.In addition, applicable standards and technical specifications for railway construction and material inputs were formulated andadhered to strictly. These factors helped in the timely implementation of a large project.
P107598 | MZ PROIRRI Sustainable Irrigation Development | Eastern and Southern Africa | Mozambique | IDA | FCS | Sustainable Development | Water | IDA | IPF | 2011 | 2019 | 2019 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/198091558718942398/text/Mozambique-MZ-PROIRRI-Sustainable-Irrigation-Devt.txt | http://documents.worldbank.org/curated/en/198091558718942398/pdf/Mozambique-MZ-PROIRRI-Sustainable-Irrigation-Devt.pdf | The ICR offered the following four lessons from the operations that may benefit future similar projects(paragraph 72):1. Forming fully functional and self-sustaining WUAs requires time.Project design with short time frames for intervention are unlikely to result in effective institutions. For example, inIndia, IEG observed that continued financial, technical, and institutional support for the WUAs over a period of three years wouldlead to an acceptable level of self-sustainability to be followed by continuous support to WUAs. The INIR capacity has to bestrengthened to monitor, support, and train WUAs as needed. This lesson informed the design of the follow-on IRRIGAproject2. The overall economic viability of investments inirrigation requires a suitable cropmix and acceptable utilization rate of irrigated land. Irrigated lands with a mix of high-value and staple crops ensurereturns on investment in irrigation. High-value crops are more profitable than staples such as rice. The EIRRs at projectclosing would depend on the diversity ofthe cropping pattern. The rate of use of arable areas with irrigation and drainageservices has a direct correlation with the profitability of irrigation infrastructure.3. TechnicalAssistance (TA) for nascent organizations combined with adequate skill sets of staff are critical for project delivery.For example, in the case of this project, strategic service providers came late. But hands-on TA made a difference inimproving the implementation capacity. The project also had initial delays and cost escalations due to a lack of technicalcompetence to review engineering design and compliance with safeguard issues. Technical reviews and approval of engineering designswere not thoroughly done and resulted in cost escalation for scheme construction.4. Investments inmarket-driven irrigation could facilitate the commercialization of smallholder farmer organizations. Investments inirrigation infrastructure need to recognize market driven opportunities. When the market signaled that the high cropping intensityamong horticulture and out-growers production systems led to better integration of the producers with inputs and outputs marketscompared to rice producers, small farmers switched from growing rice to these horticultural products.
P107608 | National Road Rehabilitation (Osh-Batken-Isfana) | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2010 | 2015 | 2016 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/377111468185395314/text/ICRR14864-P107608-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/377111468185395314/pdf/ICRR14864-P107608-Box394823B-PUBLIC.pdf | The following lessons are adapted from the ICR: A road corridor design approach is advisable in preparation and implementation of similar road projects. This could also help the government leverage financing from other donors.Development of new software systems should be well coordinated between all donors present in the countryâ€™s sector. Donors have their own road asset management systems which they offer to the client. Under this project, a simplified RAMS version was built on the previous efforts of JICA and ADB. Achieving inter-agency coordination and ownership requires time. Building all the stakeholders' ownership of road safety activities aligned with best international practices was not reached within this project's time-frame.
P107612 | NATIONAL WATER SUPPLY & SANITATION PROGRAM | Europe and Central Asia | Moldova | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2008 | 2014 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/632621467987835924/text/ICRR14797-P107612-Box393228B-PUBLIC.txt | http://documents.worldbank.org/curated/en/632621467987835924/pdf/ICRR14797-P107612-Box393228B-PUBLIC.pdf | The ICR derived a number of lessons from the project experience: The project was a second generation project following an earlier project which did not carry out adequate background analysis and was therefore too ambitious in scope regarding the require an increase in tariffs, which were not sustainable due to the weak sector level policy dialogue and political climate. A well-functioning PIU, in terms of structure, staffing, internal organization, reporting lines, decision authority, and performance incentives, was essential in improving implementation.Even though the project was originally intended to rapidly assist with the aftermath of the 2007 drought, the infrastructure investments should have been accompanied by assistance for management and maintenance, and other sustainability support.
P107617 | Water Users Association Development Support Project | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2011 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/334681553217268370/text/Azerbaijan-WUAP.txt | http://documents.worldbank.org/curated/en/334681553217268370/pdf/Azerbaijan-WUAP.pdf | The ICR offered five lessons from the project. This review selected three that had broad relevance beyond this project, they arepresented below with some editorial changes. Long-term support for Water Users Associations and the sectorfosters sustainable service delivery models. This project benefited from a sequence of four World Bank projects beginningin 1997, each building on the outcome of the previous ones. These projects provided the building blocks in the sector whichfacilitated the outcome of this project - from establishing the legal framework to cumulative institutional support. Governmentwillingness to partner in the reform of the sector is also crucial. The Government is implementing an ambitious water resourcedevelopment program adding storage and several large irrigation canals. A secondary irrigation and drainage infrastructure will bedeveloped but will depend on the Government priorities for irrigated agriculture in rural areas and response to the question of howeconomic benefits generated from water use in agriculture compare to those generated by other sectors. The National Water ResourceStrategy of Azerbaijan sets a long-term goal, focusing on sustainability and efficiency of water supplies to respectivesectors, meeting environmental requirements while maximizing economic benefits. If the irrigation and drainage programs wereimplemented as planned, secure water supply could be met by addressing both the secondary system level and the entire watermanagement systems. Adjustments may include optimization of reservoir management, more efficient water conveyance and distribution,a shift toward adoption of advanced irrigation technology. Azerbaijan Water Users Associations are now well-establishedinstitutions and could expand their responsibilities to make them a preferred partner for local water resource management.The Azerbaijan model may be one that other countries could consider emulating. Virtuous improvement cycles couldbe built on well-defined selection criteria for participation. The project developed a set of well-defined criteria,including performance of the WUAs. The associations participated in the design stage to identify priority needs. They alsoparticipated in the rehabilitation works to foster ownership. The associations also better appreciated the importance ofmaintenance of the on-farm system through training. The project approach combining investments with technical assistance showed theassociations that rehabilitating the irrigation and drainage system improved the delivery of water supply, facilitated an increasein agricultural productivity, and enabled association members to pay their service fees. Increased collection rates of service feesled to improved financing of the operations and maintenance needs of the on-farm system. A participatory approach by all keystakeholders reflecting their commitment supported a virtuous circle and provided the incentives for the associations to improvetheir performance. Sound construction control facilitates the management of large, decentralized investmentprograms. The project demonstrated that complex multiple site construction works can be managed without major delays bycloselyinvolving end users. Continued involvement by WUA chairmen facilitated timely resolution of issues. This enabled WUAsto improve irrigation service delivery to their members, who in turn acknowledged the improved services by making timely paymentsof irrigation service fees.
P107648 | National Dairy Support Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2012 | 2020 | 2021 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/766871613087488778/text/India-National-Dairy-Support-Project.txt | http://documents.worldbank.org/curated/en/766871613087488778/pdf/India-National-Dairy-Support-Project.pdf | The ICR included sevenlessons. The following three are emphasized with some adaptation oflanguage:1.Data collection and analytics are critical elements needed to successfully drive projectimplementation, anchor needed course correction and allow transparent and objective assessment of impact.TheInformation Network for Animal Productivity and Health (INAPH), with its multi-million data records, is now at national scaleand officially mainstreamed. This system permittedthe calculation of Estimated Breeding Values (EBVs) and estimation ofgenetic progress. Milk recording and production costs captured in INAPH on 2.85 million milch animals supported the business casefor optimal nutrition management as a least-cost, productivity-enhancing approach. The National Dairy Development Boards(NDDB)use of INAPH data in scheduled regional review meetings with End Implementing Agencies (EIAs) allowed objectiveassessment of implementation progress and the formulation of action plans to prevent and recoup delays.2. Improvedanimal nutrition plays a critical rolein the efforts to modernize smallholder dairying.The benefits of rationbalancing program (RBP) and Fodder Development transferred to a receptive clientele cannot be overstated and they areconfirmedby the results in milk productivity and quality. Tangible, measurable gains emerged rapidly when the RBP regime wascorrectly delivered, adopted and practiced. The resulting boostin producer incomes motivated further growth in DCS/DPCmembership and producers commitment to the wellbeing of their animals and to milk quality. A major co-benefit of RBP wasreduced GHG emissions and water footprint, a message which needs constant reiteration. The instruments for delivering suchservices/messages must be both financially and technically sustainable.3. Ensuring access toorganizedmarkets is a critical initial requirement to sustain increasesin productivity. Unless a producer sees increaseddirect remuneration from selling more and higher quality milk, there is little incentive to invest in productivity-enhancingtechnologies. The Village-based Milk Procurement System (VBMPS) unequivocally provided this incentive. That said, the enablingconditions for the VBMPS as designed may not be easily replicated outside India, as they depend on a well-established system ofcooperatives, village and matrix organizations, a technically and operationally advanced and well-connected lead institution, ITconnectivity and economies of scale. Careful consideration is needed to determine whether such system can be used/adapted to otherconditions and contexts.
P107649 | Second Karnataka State Highway Improvement | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2011 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/763491577727591555/text/India-IN-Karnataka-State-Highway-Improv-Pro-II.txt | http://documents.worldbank.org/curated/en/763491577727591555/pdf/India-IN-Karnataka-State-Highway-Improv-Pro-II.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage. 1. Adequate resources and time are required for planning and preparing innovative and complexinitiatives on civil works for institutional strengthening. The experience of this project demonstrated that the designunderestimated the time required for preparing bid documents and terms of reference by institutions who were not familiar with theDBFOMTapproach. These factors contributed to delays in implementation. 2. There can be several benefitsfrom new contracting structures andincentive systems. The new contracting structure (modified annuity andco-financing projects) in this project resulted in a substantial reduction and elimination of time and cost overruns as compared tothe prevailing predominant contracting mode (that is, item rate contracts).The long-term concessions provided for goodoperation and maintenance of the road assets in the post-construction period. 3.Physical/engineeringimprovements are necessary but may not be enoughfor addressing road safety issues.The experience of thisproject demonstrated that engineering improvements at the network level, need to be complemented by robust programs forenforcement, education and awareness, with coordinated efforts from all stakeholder departments to address road safetyissues. 4. Environmental management can be facilitated when it is integrated as part of the constructioncontracts. The experience of this project demonstrated that implementation of environmental measures during constructionis likely to be more effective if integrated as part of the construction contracts.
P107661 | BOS Knowledge Improvement for Transparency and Accountability | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2009 | 2013 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/137851474501298275/text/000020051-20140626114751.txt | http://documents.worldbank.org/curated/en/137851474501298275/pdf/000020051-20140626114751.pdf | The ICR (pp. 25-26) provides a number of recommendations, synthesized by IEG as the following:Good and reliable data at preparation are essential for monitoring and evaluating new approaches in the delivery of education services. In this case, independent monitoring and survey data monitored the process, but their value was decreased as there were no baseline data at preparation. Establishing and maintaining a continuous funding mechanism is a prerequisite condition for schools to have efficient and timely grant disbursements. During this project, there were substantial delays when the funding mechanism was changed. This resulted from staff members who were poorly suited for their responsibilities, conflicting regulations, and schools that were not prepared to develop detailed annual budgets. Maintaining stability in the funding mechanism is preferred, but if changes are made, advanced capacity building for all entities is needed.
P107666 | PE Water Resources Management Modernization | Latin America and Caribbean | Peru | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2010 | 2016 | 2017 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/673451491524624481/text/ICRR-Disclosable-P107666-04-06-2017-1491524612539.txt | http://documents.worldbank.org/curated/en/673451491524624481/pdf/ICRR-Disclosable-P107666-04-06-2017-1491524612539.pdf | The following lessons are selected, with some modification of language, from ten lessons formulated by the ICR (p.23-24): Piloting river basins to implement a new institutional and legal framework before expanding it in the restof the country is useful. In this project it provided the opportunity to revise guidelines based on the implementation experienceand generate interest among stakeholders in other river basins. In order to develop sufficient participation bystakeholders it is important to identify potential stakeholders and support the election of representatives of each group. In thisproject such a process allowed for a balanced representation of views and interests. Promoting an education program suchas water culture is critical for strengthening institutional capacity and communication with the public. In thisproject the water culture program was critical for sharing project results and improving ANAs communicationwith the public.
P107698 | Strengthening Emergency Health Response in Northern Iraq | Middle East and North Africa | Iraq | IBRD | FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2008 | 2012 | 2013 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/920901475089465952/text/000020051-20140626000517.txt | http://documents.worldbank.org/curated/en/920901475089465952/pdf/000020051-20140626000517.pdf | Lessons drawn from the ICR (pages 18-19) and adapted by IEG:The sustainability of a project may be at risk when there are no clear plans for project transition in the design stage. In the case of this project, longer-term aspects of capacity building (such as establishment of an institutional framework, coordination arrangements within the government, and a strategy for long-term operations and maintenance) were not considered in the project design, and therefore the risk to development outcomes is considered significant.Lessons from IEG:Even in a post-conflict environment with the need for rapid response, technical aspects of the project design should be carefully assessed. In the case of this project, although the scope of project activities was narrowly focused on emergency medical services (as opposed to the entire health sector), the technical requirements for the communications system needed to be re-assessed, which led to implementation delays and higher project costs.
P107722 | Development of a National Statistical System for Tanzania | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | IDA | IPF | 2011 | 2018 | 2020 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/540301571671512011/text/Tanzania-TZ-NEAS-STATCAP.txt | http://documents.worldbank.org/curated/en/540301571671512011/pdf/Tanzania-TZ-NEAS-STATCAP.pdf | The following lessons are drawn from the ICR:Statistical capacity building is a long-termprocess. Statistical capacity building encompasses institutional and human capacity building as well as datadevelopment and dissemination. The project sought to address this by creating an enabling environment encompassing all theseelements over a period of five years. This proved to be too ambitious: effective development policy making requires carefulmonitoring of processes to correctly adapt policy to circumstances in the environment. In Tanzania, an ambitious plan hasbeen put into place to develop a solid data base for policy making, but this requires time and patience.The project had to berestructured as a result of a too ambitious agenda for implementation of the countrys statisticalplan.Absence of a legislative framework can be an important factor in advancing or retarding reform. Thereadiness of a statistics law can crucially influence the pace and scope ofimplementation of statistics reform. Thelawiscentral to anyorganizational, institutional and human resource changes that are being sought. InTanzania, the passage of the law, and its ultimate formulation, was a long process that would involve many stakeholders, makingpassage even slower.IEG adds the following lesson:Significant changes in outcome indicators and targetsduring implementation can reduce (or increase) the relevance of those indicators to the originally formulated project developmentobjectives. When this occurs, as in this case, greater coherence would be obtained through appropriate modificationof the statement of objectives.
P107772 | Second Education Quality and Relevance (APL 2) | Europe and Central Asia | Armenia | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2009 | 2016 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/472571468008134971/text/ICRR-Disclosable-P107772-06-09-2016-1465499604466.txt | http://documents.worldbank.org/curated/en/472571468008134971/pdf/ICRR-Disclosable-P107772-06-09-2016-1465499604466.pdf | The project provided a number of lessons (ICR, p. 22), and the following lessons are drawn from the ICR and adapted byIEG: The Banks long-term engagement in the education sector provides a robust platform for broader dialogue,and constitutes acatalyst for key sector reforms (IEG Note: The long-term engagement under two APLs hasfacilitatedbroad reform involving all sub-sectors of education). Teacher professional development can significantlybenefit from acquiring best practices through collaborative settings and international partnerships (IEG Note: This lessonwas demonstrated by the effective twinning arrangement betweenthe Armenia State Pedagogical Universityand OuluUniversity in Finland).
P107782 | PG: Rural Communications Project | East Asia and Pacific | Papua New Guinea | Blend | FCS | Digital | Digital Development | IDA | IPF | 2011 | 2019 | 2019 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/755011561640955544/text/Papua-New-Guinea-PG-Rural-Communications-Project.txt | http://documents.worldbank.org/curated/en/755011561640955544/pdf/Papua-New-Guinea-PG-Rural-Communications-Project.pdf | The ICR identified a number of lessons, which arerephrased and summarized below: Weaknesses ininstitutional capacity should be addressed early to ensuresmooth implementation of the project. The projectsexperience shows that the weak capacity of the PIU in procurement and financial management and thelimitedinstitutionalcapacityin the management of the UAS fund caused significant delays in the project launching. NICTA hadtohire dedicated consultants/staff and an independent verification agency to support the projectimplementation. Improvement in rural connectivity can benefit fromtargetedpartnershipbetween theprivate sector and the UAS demonstrationprojects. Despite the challenges experienced during implementation, the project teamwas successful in improving theconnectivity for rural peopleand the rural economy through working with the private sector in upgrading and modernizing theexisting telecommunications infrastructure and supporting the supportingtelecenters. Financialsustainability of rural communication infrastructure is uncertain, andmay require subsidies or tower sharing to properlymanage the infrastructure. The operation and maintenance costsof rural communication arehigherincomparison tocommunication sites in urban areas. This is primarily due to the poor accessconditionsof the sites. For communications infrastructure structure to achieve desiredimpacts in rural areas, enabling services andfair market competitionis needed.To realize the communications potential,reliable electricity service is a prerequisite. Given the low purchasingpower in rural areas, the subscribers need to havethe purchasing powerto buy phones. Moreover,there is a need topromote healthy competition in the market to ensure users benefit fromlower costs and betterservices.
P107797 | Bangladesh Power Sector Development Policy Credit | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | DPF | 2008 | 2009 | 2010 | ICRR | >=100 million | Unsatisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/893201475093841541/text/000020051-20140620071326.txt | http://documents.worldbank.org/curated/en/893201475093841541/pdf/000020051-20140620071326.pdf | Reform programs agreed with caretaker governments are likely to face implementation problems when the reforms impose substantial political costs on the incoming government in charge of implementing them. As a result, the expected outcomes do not materialize and the Bank may have to start the policy dialogue from a low base to reach consensus on what is important and achievable for the new government. While for the Bank it might be reasonable to seize an opportunity for reform when a caretaker government is in power, the Bank should sharpen its analysis to identify what it is more likely to be continued and what has the highest risk of stalling once a new administration is in office.
P107797 | Bangladesh Power Sector Development Policy Credit | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | DPF | 2008 | 2009 | 2014 | PPAR | >=100 million | Unsatisfactory |  |  | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/669251468212073331/text/885460PPAR0P070C0disclosed060240140.txt | http://documents.worldbank.org/curated/en/669251468212073331/pdf/885460PPAR0P070C0disclosed060240140.pdf | 5. Lessons The following lessons are drawn from the experience with the three operations that have been assessed in this report. A. Off-grid household electrification can accelerate the benefits of lighting in a cost-effective manner, to populations that face uncertain waiting periods for grid-based electricity, or are unlikely to obtain grid-based electricity due to remote or inaccessible locations. The RERED project experience shows that potential beneficiaries can respond well to ownership-based Solar Household System schemes, and factor in the likelihood of gaining access to grid-based electricity at a later stage. B. A public-private partnership model can efficiently deliver large-scale and dispersed off-grid electricity services, by deploying public funding through private sector stakeholders. Flexibility to adapt to market conditions and signals are the hallmarks of this model, while quality assurance and after-sales and maintenance service mechanisms are a necessity for acceptance by beneficiaries. C. One-off technical assistance or credit support operations should be highly strategic, selective and practical in supporting policy and institutional issues of a complex nature. The PSD Technical assistance project took on an ambitious agenda covering power sector policies, regulation, industry structure and private sector participation, and struggled to get traction on any of these matters. D. Similarly to Lesson C, One-off Credit operations cannot be expected to make headway on multiple policy fronts in a sector, especially if these issues have some commonalities with other sectors. The Power Sector Development Policy Credit single-tranche operation covered complex issues of governance and financial sustainability, which were difficult to resolve to any significant extent in a program of short duration. E. Achieving broader social and economic outcomes from electricity access provision will primarily depend upon the pursuit of a least cost path for grid expansion backed by appropriate sector policies, complemented by off-grid electricity in the interim or permanently as needed. While Bangladesh has demonstrated impressive growth in Solar Home Systems and continues to pursue this path for improving access to electricity, it needs to keep in mind that off-grid electrification can inherently provide only a limited range of services to beneficiaries compared to grid-based electricity. Achieving broader social and economic outcomes from electricity provision will primarily depend upon the pursuit of a least cost path for grid expansion for which persisting policy and regulatory bottlenecks have to be resolved.
P107833 | SECONDARY AND LOCAL ROADS | Europe and Central Asia | Albania | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2008 | 2013 | 2014 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/928331474586742869/text/000020051-20140626122954.txt | http://documents.worldbank.org/curated/en/928331474586742869/pdf/000020051-20140626122954.pdf | The ICR (page 23) reports that there were three main lessons from this project:(1) Strong political support is required to avoid delays both during project preparation and during the implementation period. This is particularly important when coordination is required between the different actors (such as the national government, local government units, the local community and multiple donors funding different components of a program).(2) Closely related to the above, a strong implementing agency with proven experience of dealing with the local governments and the local community can significantly improve implementation.(3) Strong supervision in the initial years of the project is important for reinforcing the implementing agency in areas where its experience may be lacking In this case, although the implementing agency had experience in dealing with the local government, they did not have sufficient background in road construction and supervision. Backing by an international consultant with relevant experience in road supervision was therefore highly productive.
P107833 | SECONDARY AND LOCAL ROADS | Europe and Central Asia | Albania | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2008 | 2013 | 2019 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/705171550180046590/text/132552-PPAR-P107833-P167750-PUBLIC.txt | http://documents.worldbank.org/curated/en/705171550180046590/pdf/132552-PPAR-P107833-P167750-PUBLIC.pdf | Lessons Implementing a successful multidonor programmatic approach to sector development requires the combination of government commitment with credible planning and common rules of engagement. This project was embedded in a larger SLRIP, which the government was demonstrably committed to. The World Bank supported the government in developing a common set of requirements for technical design, procurement, and fiduciary management, which gave other donors the confidence to participate in and strengthen the various component projects of the larger SLRIP. Concentrating competencies within one agency may frustrate future decentralization of responsibilities. Shortly after project completion, the government undertook a territorial reform that reorganized LGUs and transferred to them the responsibility for managing the secondary and local roads under their jurisdiction. This sudden development left most LGUs underprepared for their new duties. Further capacity building for LGUs is needed so that they can adequately perform this function. In the absence of need-based and credible linkages to resource allocation, a road asset management system may not get sufficient traction. Following project completion, the Road Maintenance Planning System software has not been used to any significant extent for its intended purpose of prioritizing, planning, and apportioning funds for road management activities. This can be attributed at least partly to the perception that the data were unlikely to be used as a basis for resource allocation.
P107840 | Regional and Local Roads Program Support Project | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2008 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/506271495226045949/text/ICRR0020321-REVISED-PUBLIC-P107840.txt | http://documents.worldbank.org/curated/en/506271495226045949/pdf/ICRR0020321-REVISED-PUBLIC-P107840.pdf | The ICR presentedfour lessons but most were either not noteworthy or narrowly focused on this project. The one thathad some broader application is, with some adaption, presented below.Flexibility in the scope of institutionalsupportshould be balancedagainst relevant risk mitigation. In this project the scope of institutionaldevelopment activities was kept flexible to allow for adjustment based on the needs of relevant agencies and the sector at large,considering that the role of the initial implementing agency FNRR (PESRs predecessor) was still evolving and its needs forcapacity building were not fully known. This arrangement facilitates a more targeted support fora sector that is undergoingmajor reforms. A caveat is that there are risks that as a result of too much flexibility some important activities, such ascapacity building for road safety enhancements in this project,mayend up not being included in the component designs.Appropriate measures should be adopted to ensure that such risks are addressed.
P107840 | Regional and Local Roads Program Support Project | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2008 | 2016 | 2019 | PPAR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/100771550588248016/text/132581-PPAR-P107840-P167751-PUBLIC.txt | http://documents.worldbank.org/curated/en/100771550588248016/pdf/132581-PPAR-P107840-P167751-PUBLIC.pdf | 7. Lessons 7.1 Objective criteria developed and applied in a participatory manner can support a transparent framework to allocate investments and maintenance funds in the roads sector. This project developed a multicriteria framework (including length of the road segments, number of registered vehicles, fuel consumption, surface size, and population) and applied it in partnership with municipalities and local communities. The framework was later adapted into a law to distribute the central budget for road works among municipalities. 7.2 The decentralization of responsibilities to local governments needs to be accompanied by the availability of commensurate resources and capacity building. The responsibility of managing and maintaining local road networks was devolved to municipalities through territorial reforms in North Macedonia beginning in the early 2000s. However, with limited funds and limited capacity, municipalities continue to face challenges carrying out their mandate. 7.3 Road safety and road design elements need to be jointly integrated into the project design and monitoring framework to mitigate risks to the effectiveness of road projects. Under this project, road safety aspects were not consistently followed initially but were introduced only after project restructuring. A better approach is to include road safety elements in the project development objective and then integrate them into the project design and monitoring framework. 7.4 Road project appraisal requires sufficient time and technical due diligence to ensure effective and timely project implementation. The shortcomings experienced in quality at entry relating to the lack of detailed designs at project commencement, and inadequate provision of capacity building for municipalities, might have been overcome if greater time and technical due diligence had been committed to these matters at project appraisal.
P107841 | Integrated Ecosystems Management in Niger (APL phase 2) | Western and Central Africa | Niger | IDA | FCS | Sustainable Development | Agriculture and Food | GEF | IPF | 2009 | 2020 | 2021 | PPAR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/247381611169237800/text/Niger-Community-Action-Program-and-Community-Based-Integrated-Ecosystem-Management-Project-Phase-I-and-II.txt | http://documents.worldbank.org/curated/en/247381611169237800/pdf/Niger-Community-Action-Program-and-Community-Based-Integrated-Ecosystem-Management-Project-Phase-I-and-II.pdf | 4. Lessons 4.1 Land and resource restoration projects should supportâ€”and make evident how they are supportingâ€”existing customary flexible tenure arrangements to ensure distributional benefits among resource users and to mitigate conflict risks. Traditional land use arrangements in Niger between farmers, agropastoral, and transhumant populations are negotiated in ways that provided mutual land use benefits. However, as the CAP shows, increasing the value of openor pooled-access degraded land without clear, enforceable land use agreements can lead to predation by elites and farmer encroachment. This occurred in the first CAP-supported site, where restored parcels were sold outside of the community. It also occurred in areas that supported intercropping (crop agriculture alongside tree planting)\. Although land restoration activities took place on communal land, the introduction of intercropping facilitated individualized claims on community land. Such projects should be designed with an understanding of the customary flexible tenure arrangements and the coping strategies of vulnerable resource users who access communal lands as a social safety net. The composition of land management committees also requires attention to ensure that they represent different resource user rights and to mitigate the risks of predation. 4.2 The success of natural resource restoration depends on the extent to which private or communal resource users are compensated over reasonable, short-term time frames for abstaining from using those resources until the long-term public benefits of resource restoration are achieved. The assessment of CAP-1 and CAP-2 found that when compensation is too small or takes too long to materialize, it discourages resource users from abstaining from using the resources, which undermines restoration of the resource base. For example, carbon credits were distributed to CAP beneficiaries eventually, but after the sequestration of 152,583 tons CO2 equivalent was verified, the process was severely delayed and caused a significant level of consternation. 4.3 Projects that support land and resource restoration can ensure that women benefit by addressing participation barriers linked to social and cultural norms. In CAP-1 and CAP-2, women benefited less from project activities for multiple reasons. The cash-for-work programs did not include female-only tasks in geographic areas where women could be separated from men. Additionally, these programs did not provide women with alternate options for childcare and other domestic responsibilities during the hours and in the areas where these programs were implemented. Women did benefit from specific natural resource management programs, especially from banquettes that protected their vegetable gardens from soil erosion and flooding. However, wider extension services provided to male farmers (that included the distribution of advice, fertilizer, seed, and tools) were not provided systematically to women, who often farm less-lucrative crops (for example, peanuts) in plots next to their husbands' land. 4.4 Socioeconomic and anthropological analyses, conducted before project elaboration, can support the gender aspects of production and marketing better. In Niger, a very large number of women must fend for themselves and their families because their husbands migrated to other West African countries, such as Cote d'Ivoire, Nigeria, and Senegal, to look for work. However, compared with other Sahelian countries, there were few socioeconomic and anthropological studies conducted during the CAP period that focused on gender issues. The evaluation and research show that direct involvement of women in selling livestock in markets is generally frowned upon in Nigerien society, and though it may differ among the Hausa, women-owned livestock receive lower prices than those owned by men do.
P107843 | Federal District Multisector Management | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2009 | 2013 | 2014 | ICRR | >=25 million & <50 million | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/193811474895301572/text/000020051-20140626112627.txt | http://documents.worldbank.org/curated/en/193811474895301572/pdf/000020051-20140626112627.pdf | The ICR (p. 17) offers valuable lessons:Results-based operations with SWAp agreements require strong Government commitment, including high-quality staff. Safeguards could help to quickly adjust to changes in Government and commitment. M&E is a cornerstone in results-based operations. In this case, the missing M&E framework severely affected validity of data and of indicators used for disbursement. Bank procurement rules in a SWAP can remain challenging and require special attention, even though country fiduciary systems are used. In this case, the Bank's procurement rules requested contracts to comply with anti-fraud and anti-corruption clauses, which was not a requirement in the country procurement system.
P107845 | Second Basic Education | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2009 | 2014 | 2015 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/697331475117120787/text/000012394-20150312112805.txt | http://documents.worldbank.org/curated/en/697331475117120787/pdf/000012394-20150312112805.pdf | Lessons drawn from the ICR (pages 19-20):Sustainable institutional arrangements should be built into project design for key innovations that are introduced by the project. In the case of this project, there was insufficient attention given to ensuring that the student-centered teacher training and the learning assessments would be owned and sustained by the government after project closing. Project activities such as an analysis of existing systems and their shortcomings, and identification of institutional and financial requirements for scaling up, could have been included to ensure sustainability.A properly designed results framework is essential for project evaluation. In the case of this project, the project indicators were not clearly linked to the project interventions, nor were assessments properly aligned with the implementation schedule.
P107847 | PROVINCIAL ROADS | South Asia | Sri Lanka | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2010 | 2015 | 2016 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/388881468335433608/text/ICRR-Disclosable-P107847-06-10-2016-1465565907253.txt | http://documents.worldbank.org/curated/en/388881468335433608/pdf/ICRR-Disclosable-P107847-06-10-2016-1465565907253.pdf | The ICR draws the following main lessons from the experience of implementing this project.(1) Itis critical that good quality detailed engineering designs, bidding documents, and environmental and social safeguards documentsare prepared at the preparation stage. Project experience underlines the importance of ensuring that Bill of Quantitiesare based on detailed engineering designs, bids are received by appraisal, and project cost estimates are based on actual bidprices. Pre-construction activities also need to be completed to help ensure efficient implementation.(2)The environmental assessment at appraisal should address the vulnerability of roads to landslides. In the case ofthis project, this was not done for Uva province and no corrective measures were put in place during implementation. Learningfrom the experience of landslide stabilization in Pakistan, Nepal, Bhutan and India, cost-effective soil bioengineeringandbiotechnical measures for remedying slope instability could have been applied.(3) A thorough assessment of theconstruction industrys capacity during pre- and post-qualification evaluation is required to prevent delays. Inthe case of this project, the local contractors capacity was overstretched due to the increased amount of funding beingchanneled for large infrastructure projects. As a result, most of the contractors failed to keep to the work program andreported delays.
P107851 | Burundi - Financial & Private Sector Development | Eastern and Southern Africa | Burundi | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2010 | 2018 | 2018 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/422981530232845541/text/Burundi-BI-Finance-Private-Sector-Development.txt | http://documents.worldbank.org/curated/en/422981530232845541/pdf/Burundi-BI-Finance-Private-Sector-Development.pdf | The lessons learned presented in the ICR were derived from the experience of the project design and implementation, and aresummarized and rephrased hereunder:(i) Simplicity and moderate optimism should guide the design ofprojects in fragile environments: In a fragile context, it iskey to be simpleandselectivein identifying priority objectives and activities. In hindsight,the project wasverycomplex and wide in scope,and this reduced the pace of implementation andled to repeated restructuring. The design ofoperationsshould be based on careful consideration of potential risks.The volatility of the political andeconomic environment in a fragile state need to be considered at the project design stage through the inclusion of mitigationmechanisms to manage adverse circumstances under a number of potential scenarios.An appropriate risk analysis, taking intoaccount possible adverse scenarios, should accompany the design of operations in fragile country contexts. The possibility for ascale down of theproject should be considered during the design stage, with mechanisms to be triggered if adversescenarios materialize.(ii)A reduced project scope might mitigate the fiduciaryweaknesses on the ground.Asimplified design mayhelp to address potential fiduciaryissues at their source.A reduction in the number of project components reduces the complexity and increases transparency inimplementation andthe risks of potential leakages.As fiduciary issues aredifficult to address when they occur,significant efforts are required to monitor the early stages of project implementation to prevent these issues fromemerging.(ii) Continuity and field presence of TTLsare central to generating results infragile environments:The rotationin project responsibilitiesdisrupts projectimplementation,entails a steep learning curve, andshould be limited and properly planned. In this case,the second TTL was assigned responsibilities on top of his existing commitments, resulting in poorer supervision outcomes.Following theFebruary 2014 restructuring,a resident co-TTLwas appointed and was alsoresponsible for the implementation of anIFC technical assistance project. In the future, pairing up an IPF operation with a complementary technical assistance activitycould enhance the effectiveness of implementation and build the capacities of the client.(iii) Fora project with highly technical components, it isessential to(a) secure the experts very early,(b) associate themsince inception andduring supervision, and (c) provide the required management oversight: The involvement ofexperts at the preparation stage is a cost-effective investment, and may facilitate quicker project implementation at later stagesand help to avoid restructuring. In this case, therewas no payment system specialist at design,and a fulltimepayment system expert joined the team onlylater in 2014. Moreover,effective supervision requires significant technicalexpertise, andthe project team should identify the necessary resources to leverage experts during project implementation fromthe project side and from the WBG side. Finally,the successful implementation of IT solutions depends in equal measureon the technical competence of the providers and the quality of project management, and thelatter needs to be factored intothe project design.(iv) More efforts should be invested in the preparation ofeconomicanalysis atinception to determine whether the project represented the expected least-cost solution to attainidentified and measurable benefits. The WBG has had enough experience in implementing payment systems reforms in both Middle andLow Income (including fragile states) Countries by setting up payment system infrastructures to benchmark the cost per unit peroutput .
P107921 | Afg Strengthening Institutions DPG | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2009 | 2011 | 2012 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/150861474511651065/text/000020051-20140624212606.txt | http://documents.worldbank.org/curated/en/150861474511651065/pdf/000020051-20140624212606.pdf | The lessons cited in the ICR --- that DPGs can work well in a high risk environment, strong government ownership is crucial to progress and sustainability, Bank budget support can leverage larger amounts of budget support from other donors, the importance of a focal point in the host institution for institutional knowledge, presence on the ground by the Bank, and donor harmonization -- are all supported. IEG also recognizes the importance of technical assistance, but sees this as a risk since development partners could scale back levels of technical assistance as they scale back their military forces, and local counterparts may not be capable of taking over the more difficult functions. An additional lesson, as also pointed out in WDR 2011, is that it is crucial to empower local leaders to determine and direct PFM and other institutional processes that make sense locally and that can promote broad-based consensus inclusive of all ethnic groups while being sufficiently robust to deal with rapid social and economic change. The WDR gave examples of some societies and states that have succeeded in managing these stresses without persistent recourse to violence, while others have not -- and finds the essential difference to be the ability of a societyâ€™s institutions to mediate conflict. It is not yet clear whether Afghanistan is on track to succeed. As in other settings, it will take a generation or more of persistent effort to turn ineffective institutions into â€˜legitimateâ€™ entities which are capable, inclusive and accountable. Among the challenges of doing this is that creating local and national institutions capable of resolving conflicts peacefully and providing the stability and predictability needed for sustained economic growth is deeply affected by commercial, diplomatic and security decisions taken beyond the country concerned. The DPG has has had moderate success in meeting its objectives to date by walking a thin line between moving towards international standards of PFM, procurement and accountability on the one hand, and maintaining local ownership and an Afghan face to the reforms on the the other. The context is extraordinarily difficult and risky, with violence increasing and no end in sight. It is impressive that the Bank and Government working together have achieved as much as they have.
P107921 | Afg Strengthening Institutions DPG | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2009 | 2011 | 2013 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/870751468197964841/text/Afghanistan-First-Second-and-Third-Programmatic-Support-for-Institution-Building-Project-and-Strengthening-Institutions-Development-Policy-Grant-Project.txt | http://documents.worldbank.org/curated/en/870751468197964841/pdf/Afghanistan-First-Second-and-Third-Programmatic-Support-for-Institution-Building-Project-and-Strengthening-Institutions-Development-Policy-Grant-Project.pdf | 4. Lessons Although Afghanistan's history and challenges are somewhat unusual, given the enormous impact of international actors since 1979 and the high profile of the international terrorist threat over the last decade, the experience over the period of these operations offers a few important lessons relevant to other fragile and conflict-affected states\. * Development Policy Operations can achieve important public administration and financial management reforms in high-risk environments with strong government ownership and flexible implementation. Bank investment lending, analytic and advisory services, and Bank-managed multi-donor trust funds, together with close coordination with the initiatives of other donors, can substantially increase the probability of success of development policy operations. Continuity, experience, and quality of Bank staff are necessary conditions for program effectiveness; with location in-country an added advantage. * Emergency consultant support in the shortand medium-term can usefully supplement the skill base in Governments where progress in institution and capacity building is bound to be a slow and time-consuming process. These skilled personnel can help adopt structures, processes, systems, and regulations to enable reforms in, inter alia, pay and grading, administrative reform oversight, human resources monitoring, tax administration, financial management, procurement, and audit. However, ensuring the transition to a more normal administrative structure is crucial for sustainability. * It is crucial to empower senior officials from Government to determine and direct administrative reform, public financial management and other institutional processes that make sense locally and that can promote broadbased consensus inclusive of key political groups, while being sufficiently robust to deal with rapid social and economic change. This PPAR has demonstrated that when such officials are supported by extensive analytical work and parallel technical assistance operations, development policy operations can emerge that succeed in facilitating limited but important progress taking place in a volatile setting. World Bank (2011 a) gives examples of some societies and states that have succeeded in managing these stresses without persistent recourse to violence, while others have not and finds the essential difference to be the ability of a society's institutions to mediate conflict. It is not yet clear whether Afghanistan is on track to succeed. As in other settings, it will take a generation or more of persistent effort to turn ineffective institutions into 'legitimate' entities which are capable, inclusive and accountable. This will be challenging. Creating local and national institutions capable of resolving conflicts peacefully and providing the stability and predictability needed for sustained economic growth are deeply affected by commercial, diplomatic, and security decisions taken beyond the country concerned. Development policy lending can have substantial success in meeting their objectives by walking a thin line between moving towards international standards of public administration, financial management, procurement, and accountability on the one hand, and maintaining local ownership and local face to the reforms on the other.
P107981 | Maldives Mobile Phone Banking Project | South Asia | Maldives | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2008 | 2014 | 2015 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/549531475115572396/text/000012394-20150310074326.txt | http://documents.worldbank.org/curated/en/549531475115572396/pdf/000012394-20150310074326.pdf | The following lessons were selected and adapted from the ICR as the most important: Government commitment is often critical to project success. In addition, it is important to ensure commitment on the part of key stakeholders, whose participation is important to the success of the project. As these commitments can change over time, depending on changes in the political economy, project design should include mitigation measures to deal with this risk.For a pilot project, it is important to keep the design simple and in keeping with the quality of the countryâ€™s implementation capacity.It is important to link the results framework closely to project development objectives, to ensure accurate measurement of progress towards achievement of project goals.
P107992 | ENERGY EFFICIENCY | Europe and Central Asia | Montenegro | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2009 | 2018 | 2019 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/456181548970493167/text/Montenegro-ENERGY-EFFICIENCY-IN-PUBLIC-BUILDINGS.txt | http://documents.worldbank.org/curated/en/456181548970493167/pdf/Montenegro-ENERGY-EFFICIENCY-IN-PUBLIC-BUILDINGS.pdf | Following are lessons from the ICR with somemodifications.1. Alignment withgovernment policy and regulatory objectives is important to the achievement of the PDO. The project benefitted from beingapproved just a year after Montenegro signed the energy community treaty. The objective of the project and that of thegovernment were aligned. The project enabled the government to demonstrate progress towards meeting its energy community treatyobligations. Policy and regulations were developed and implemented during the course of the project. Other IFIs working in thesector had the similar strategic objectives, which ensured the alignment with the Paris Declaration on Aid Effectiveness and theAccra Agenda for Action.2. Budgetingenergy efficiency investment costs may need to allow a portion for non-energy efficiency measures. During theimplementation of the original project, the government realized that ancillary measures (e.g., painting, rewiring, replacinggutters, etc.) were necessary to complete building renovations. This was important for two reasons: (i) improving facades ofthe buildings enabled the government to gain political support for the project; (ii) some of the investments needed non-energyefficiency investments (e.g., better toilets, structural support, etc.) to bring the buildings up to comfortable norms. As aresult, the additional finance allowed up to 10 percent of each subprojects investment cost to carry out non- energyefficiency works.3. Proactive capacitybuilding for stakeholders is necessary for timely implementation. The project was extended four times to finish works, andUS$350,000 (280,000) was canceled from the original project because bidders had failed to meet technical requirements. Thesechallenges could be traced to the limited capacity of the TSU at the beginning, and the service providers limited capacityto work with international financing institutions. Proactive capacity building would have trained both the TSU and serviceproviders early in the process to avoid the delays. While workshops were held, the counterparts needed on-the-job training as well,which helped speed up the project implementation.
P107998 | Second Solid Waste Management | Europe and Central Asia | Bosnia and Herzegovina | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2009 | 2018 | 2018 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/999991529599446683/text/Bosnia-and-Herzegovina-SOLID-WASTE-MGT-2.txt | http://documents.worldbank.org/curated/en/999991529599446683/pdf/Bosnia-and-Herzegovina-SOLID-WASTE-MGT-2.pdf | IEG selected three lessons from the ICR, with some adaptation:Sustainability of the SWM sectorinvestments may be at riskif a tailored institutional and capacity building program is not implemented.Thiswas a second-generation project in SWM that focused on infrastructure development that however did not include substantial policydialogue and institutional strengthening, and lackedsustained public awareness initiatives.Implementation of thereformagenda in SWM requires significant human and financial resources, public awareness initiatives as well ascapacitybuilding in managerial and technical areas such as landfill optimization, revenue collection and management.In order to ensure long-term sustainability of a certain sector, it is critical to bring sector financing to the top of thepolicy dialogue agenda and identify reasonable responsibilities of entities at different levels. In this project,while the central government expects the municipalities to finance the extension of coverage, maintain equipment, andadvance the sector to meet the Waste Directive by the European Union, the municipalities already face financial constraints. Goingforward it will be critical to identify realistic responsibilities by the municipalities and the central government to ensure thesustainability of the sector. When designing a results framework it is critical that the selected indicatorscapture the whole picture of the progress that is being made. In this project, PDO indicator 2 measured the numberof sites being environmentally compliant by measuring leachate quality. However, the indicator did not take into account that onelandfill was responsible for 40% of the countrys solid waste. Defining the indicator by volume rather than number ofsites would have provided more accurate information.
P108005 | CORRIDOR X HIGHWAY PROJECT | Europe and Central Asia | Serbia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/546951602190836089/text/Serbia-CORRIDOR-X-HIGHWAY-PROJECT.txt | http://documents.worldbank.org/curated/en/546951602190836089/pdf/Serbia-CORRIDOR-X-HIGHWAY-PROJECT.pdf | The following four lessons in the ICR stood out as important and relevant to other projects in the road sector and are presentedhere with some editing.To maximize the impact of a large-scale transport project, it can be designed in thecontext of Integrated Territorial Development (ITD), including multi-sector regional and urban programs. The ITD is a toolsuggested by the EU to implement multi-sectoral territorial strategies in an integrated manner. It allows governments to implementoperational programs in a cross-cutting manner drawing funding from several priority axes of multiple operational programs based onan integrated strategy for a specific territory, such as South-eastern region of Serbia in this case. It is essential to develop across-sectoral integrated development strategy that addresses the development needs of the region at the planning stage, as well asdesign to build synergies produced by coordinated implementation.When different sections of a highway constructionproject are funded by multiple IFIs via parallel financing, consolidating the supervision arrangement under one InternationalFinancing Organization (such as the World Bank) may have positive impacts on implementation. The project experience showedthat such a supervision arrangement can make a significant impact on the quality, schedule and cost control aspects. It can alsomake a positive impact on overall coordination of the whole project. Enabling the supervision engineer to compare and examinecross-learning cases to come up with optimal solutions in similar technical situations. This is especially important in countriesthat have low contract management capacity.Adequate design quality and planning can help minimize time and costoverrun risks; project timelines should be planned more generously for complex transport projects. It is important toensure thorough geotechnical investigations, particularly for mountainous road works. In addition, the duration of implementationshould be realistic considering the local conditions and availability of resources. Works should be strategically packaged in lotstaking into account the markets and likely efficiency of works implementation. The cost estimate should reflect a realistic cost ofthe local conditions and markets without overly relying on the standard schedule of rates.The environmental andsocial (ES) management requirements under works contracts should be standardized and clarified in the bidding documents andrequirements. Whereas the ES safeguards of construction works have been a priority for a long time, cost allocationis often underestimated. ES management should be an integral aspect of contract award criteria. The cost of Environmental andSocial Management Plans (ESMPs) implementation should be specifically budgeted. The new World Bank guidelines of ContractorsESMP requirementsand introduction of ES Performance Security should be standardized to ensure the ES aspects to befully costed for proper management.
P108023 | Energy Efficiency Project | Europe and Central Asia | Belarus | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2009 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/180081543250739020/text/Belarus-Energy-Efficiency-Project.txt | http://documents.worldbank.org/curated/en/180081543250739020/pdf/Belarus-Energy-Efficiency-Project.pdf | The following main lessons were derived from the projects implementation experience, as paraphrased fromthe ICR (pages 31-32):Strong government support is key to catalyzing energy efficiencyinvestments. Borrower commitment and the support of implementing agencies are critical to fulfilling energy efficiencyobjectives. High proactivity by implementing agencies is important in overcoming implementation challenges. Open dialogue with theborrower on sector structural reforms can stimulate more energy efficiency endeavors and help attract new players, such as newdonors and partners in the sector.A thorough market assessment during project preparation can helpdevelop an appropriate procurement approach. The unsuccessful tendering early in the project caused delays inimplementation. International procurement of supply and installation services for package sizes of US$20 million and above wasunusual at that time, as international firms were not used to investing large amounts in Belarus. Many Belarusian constructionfirms would not qualify if the procurement guidelines were applied and if state-owned enterprises were set aside from participatingin the tenders. The prequalification process failed to anticipate the uncertainty of the international market response and did notgather adequate information on the capacity of local bidders. A rigorous market assessment needs to be conducted before theprocurement process so that solutions to these issues can be developed before the tenderingcommences.Good operation and maintenance practices need to be established in order to sustainproject results and development impacts. The projectapplied good practices on OM training for state-of-the-arttechnology. First, all plants upgraded through the project included onsite OM training provided by the supplier as part of itscontract. Second, although site owners of the smaller sites conducted the daily operation tasks, theymobilized biyearlycontracts with certified companies to mitigate their insufficient capacity and human resources. In the larger sites, theenergo operators were required to pass formal OM training to operate any of their district heating plants in thecountry. The borrower and implementing agencies need to maintain strict OM training and, continue the inspection andmaintenance contracts particularly for smaller plants, while building local capacities and know-how.
P108058 | Caribbean Catastrophe Risk Insurance Facility | Latin America and Caribbean | Caribbean |  |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2007 | 2012 | 2013 | ICRR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/901861475092273503/text/000020051-20140626080209.txt | http://documents.worldbank.org/curated/en/901861475092273503/pdf/000020051-20140626080209.pdf | The ICR (para. 91) provides a list of lessons learnt. Most are generic, such as: the importance of consultations with stakeholders on an ongoing basis; the essential role of donor support/funding; the vital role of private sector expertise; the significance of implementing good governance practices within CCRIF and ensuring its service delivery at a low cost. Another important point concerns the need for flexible Bank oversight of innovative projects, which should be based on experimentation and feedback of results into implementation. Additional lessons from the review herein are as follows;The project provides a good example of successful outcomes based on a focused approach and simple, yet sophisticated design underpinning an innovative concept. The availability of substantial resources for preparation seems quite critical to achieve success. Care should be taken when designing the M&E system to better capture project results, notably outcome, and build-in stakeholder assessments. Should the initial design be found insufficient, project restructuring provides and entry point for retrofitting the M&E framework with improved indicators and/or other assessments.The IBTF is not an adequate project appraisal document. For larger grants funded by Trust Funds, a more elaborate document similar to a PAD is now required . However, in the absence of such a document for older projects, the ICR should inform itself of all relevant documents produced during project preparation.
P108069 | Integrated Public Financial Management Reform | Western and Central Africa | Sierra Leone | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2009 | 2015 | 2016 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/349461467993515001/text/ICRR14894-P108069-PUBLIC-Box394874B.txt | http://documents.worldbank.org/curated/en/349461467993515001/pdf/ICRR14894-P108069-PUBLIC-Box394874B.pdf | Lessons in the ICR are supported. In addition, IEG adds the following:1. Strategies for sustainability can be part of the project design from the very beginning. Strategies for mainstreaming PFM consultants into the permanent civil service are best designed and agreed upon from the very beginning. Extensive use of capacity substitution and supplementation as in Sierra Leon to short-circuit capacity constraints while providing an opportunity to move forward on the reform agenda, poses clear challenges to longer-term sustainability.2. Monitoring and evaluation arrangements are most helpful when designed from the outset so as to ensure usefulness not only for reporting on project performance but also for learning and adjusting implementation as needed across all project stakeholders.In addition: 3. Achieving long-term sustainable institutional capacity building outcomes such as the one pursued by PFM reforms and in a post-conflict context of low capacity requires a programmatic, step-by-step approach built in a long-term vision but focused on a reasonable number of building block priorities at a time and aligned with actual capacity. Simplicity, prioritization and sequencing should be given much more attention from the very beginning and during implementation.4. Capacity building requires much more than training and equipment. Capacity building project design, especially in the political sensitive area of PFM and in a post-conflict context, needs to be carefully coordinated with related cross-cutting institutional reforms such as civil service and other governance reforms from the onset. A successful PFM capacity building project canâ€™t be implemented in isolation from the broader country political economy and institutional context and requires high level buy-in at senior political and technical levels across government. A right balance of supply and demand side interventions in PFM capacity building projects may help in achieving sustainable results as there may be more appetite for PFM reforms outside of the executive; an opportunity to build a coalition for reform. The project found good traction with measures targeted to non-governmental stakeholders and the Parliament, which have improved their capacity to oversee public finance.
P108069 | Integrated Public Financial Management Reform | Western and Central Africa | Sierra Leone | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2009 | 2015 | 2018 | PPAR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/648961523885856500/text/124660-PPAR-P164951-P108069-PUBLIC.txt | http://documents.worldbank.org/curated/en/648961523885856500/pdf/124660-PPAR-P164951-P108069-PUBLIC.pdf | 7. Lessons The World Bank's support for PFM reforms in Sierra Leone through the implementation of this project provides potentially useful lessons for the design of similar operations in other fragility, conflict, and violenceâ€“affected countries, especially in the Africa Region. â€¢ In the absence of a conducive PFM policy environment, there are clear limits to what can be achieved through investment project financing alone. In this case, while most of the project's targeted outputs materialized, its development objectives were largely unachieved. The investment project financing design did not, and perhaps could not be expected to, address the binding policy constraints to achieving the outcomes. In the absence of PFM policy reforms to address constraints, the link between supported activities and intended outcomes was weak. The project could have achieved better results if the policy constraints to enhanced credibility, control, and transparency of fiscal and budget management had been addressed in a parallel manner, including with World Bank support through other lending and nonlending instruments (for example, development policy financing), supported and preceded by Advisory Services and Analytics. â€¢ Effective support for improving the demand for good governance can benefit from broadening support beyond civil society organizations to include academia, the media, and the private sector. This project included only civil society organizations. Although it had good outreach with communities, the communities lacked the necessary capacity to analyze economic issues and budget documents. â€¢ In the context of low Internet density, effective public dissemination of state documents calls for combining online publication with alternative means of diffusion. Where there is very low Internet density, as in Sierra Leone, online dissemination is unlikely to reach more than a small part of the population. Alternative methods of dissemination would have been more productive in attaining the goal of greater transparency. In this case, the problem was exacerbated by the lack of publicity on the availability of documents on the web, thereby limiting outreach even to those with Internet access. â€¢ Effective and sustainable World Bank leadership of multi-donor support to PFM reforms requires a continuous effort by staff to consult with external partners. In this case, this effort appears insufficient. DFID and the EU were reportedly disappointed that the reform strategy was tailored almost exclusively to address World Bank priorities. Little room was left for other development partners to contribute, which led them to withdraw funding from the follow-on project. A more partnership-oriented approach could have secured their continued participation. â€¢ Effective World Bank support for designing and installing information technology systems requires tailoring solutions to address borrower capacity limitations. For example, it is crucial to ensure all equipment critical to achieving project outcomes is in place and that staff can operate it. Where the installation and implementation of a management information system involves a consultancy, it is desirable to avoid the high costs and dependency frequently associated with timebased contracts. Rather, contracts should be structured around system implementation and allow for building the client's capacity on a sustainable basis.
P108078 | Maldives Environmental Management Project | South Asia | Maldives | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2008 | 2016 | 2017 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/787991498832548594/text/ICRR-Disclosable-P108078-06-30-2017-1498832534354.txt | http://documents.worldbank.org/curated/en/787991498832548594/pdf/ICRR-Disclosable-P108078-06-30-2017-1498832534354.pdf | The ICR (pp. 28-29) identified a number of lessons, of which the most important are listed below withsomeadaptation:1. There is a need for right balance funding, implementation period and design. In acountry with such unique geographical context as Maldives Islands, there is a need of sufficient time for successful implementationand analysis.2. Given projects complex environmental, technical and financial settings, careful analysis ofgeographical, technical and local challenges is required to maximize the results of priority investments. Projectpreparation timeline would allow conducting adequate assessment of complexities and local challenges.3. In orderto achieve objectives, the projects framework should be coherent with clear articulation between activities andoutcomes. It was conceptually desirable to integrate infrastructure focused interventions such as the RWMF withdemand-side interventions (awareness raising and behavior change) and management practices (introducing new technologies and wastemanagement practices).4. Strengthen client capacity is a key for successful sustainability. New andtechnical challenging sectors (establishing private-public partnerships) should be prioritized particularly if these are criticalfor long-term sustainability of the investment.
P108080 | Kosovo Financial Sector Strengthening & Market Infrastructure Project | Europe and Central Asia | Kosovo | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2008 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/477731516400344845/text/ICRR-Disclosable-P108080-01-19-2018-1516400337704.txt | http://documents.worldbank.org/curated/en/477731516400344845/pdf/ICRR-Disclosable-P108080-01-19-2018-1516400337704.pdf | The ICR (page 38) notes several lessons: It is important toassess the capacity of theimplementing agency and its ability to undertake the project as a vital component of project design. There is aneedfor a dedicated Project Implementation Unit in circumstances where local capacity is limited and there is unfamiliarity with WorldBank processes and procedures. Complexity can lead to delays --by designing a project where there were numeroussmall procurement processes --which could beovercome by consolidatingthe small-scale activitiesInIEGasinto a larger procurement package.In IEGs assessment, the ICR could have gone furtherin some areas: An important issue is that providing assistance in negotiating complicated procurement processesshould have been foreseen at the outset of the project. Conversations with the TTL revealed that even towards the end of theproject, Kosovo counterparts did not fully comprehend the need to use World Bank procurement rules rather than local procurementrules. A specific assessment of supervision requirements at the outset of the project and as part of the restructuring in2011 could have led to more cost efficient supervisory processes, with perhaps a recommendation that the TTL should have beenresident in Kosovo for at least part of the project.
P108143 | Water Sector Improvement APL Phase II: Metolong Dam and Water Supply | Eastern and Southern Africa | Lesotho | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2009 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/335021580309888003/text/Lesotho-LS-Water-Sector-Imp-Proj-Second-Phase.txt | http://documents.worldbank.org/curated/en/335021580309888003/pdf/Lesotho-LS-Water-Sector-Imp-Proj-Second-Phase.pdf | IEG derives the following lesson, drawn from the ICR:Complex projects require strong implementationarrangements: The project was of moderate size (US$50 million at completion), but included four components and more thantwo dozen sub-activities ranging from infrastructure development to preparation studies to training and institutionalstrengthening to modeling. Implementation was managed by several different government agencies, which called for a high degree ofcoordination. Such a highly integrated approach offered some advantages, but it also raises the issue of whether the resultantcomplexity which made management of the project much more difficult called in practice for far more rigorous andwell-planned implementation arrangements than were anticipated. In general, projects need to minimize complexity in thedesign phase, or, if unavoidable, to ensure that coordination and implementation arrangements are adequate and wellthought-out.A focus on hiring local labor can help mitigate potential social issues: The Government had astrong policy of trying to utilize local labor for construction of infrastructure and project-related tasks as much as possible,which incorporated in the approach to the project. The community councils were utilized to actively promote local recruitment, andthe local government provided facilities to minimize the need to construct temporary housing. There was no influx of externallabor, as a result of which associated social risks were greatly reduced.
P108144 | Sustainable Land Management Project | Western and Central Africa | Senegal | IDA | Non-FCS | Sustainable Development | Agriculture and Food | GEF | IPF | 2010 | 2013 | 2014 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/560331475113735303/text/000180307-20141202140812.txt | http://documents.worldbank.org/curated/en/560331475113735303/pdf/000180307-20141202140812.pdf | Some of the lessons identified by the ICR with some rewording is as follows:Community demand driven approaches can greatly improve the ownership, success and sustainability of development projects. This project demonstrated that use of producer organizations in managing sub-projects improves accountability , transparency and ownership of projects which leads to successful implementation and sustainability of efforts. However producer organizations may often need capacity building efforts for project management. Inclusion of multiple institutions in project implementation can be successful if coordination is well designed. IEG also finds that:Pilot interventions focusing on sustainable management of land need to not only test technologies and processes but to utilize the lessons to plan for the next steps in scaling up. In this case, there seems to have been limited focus on preparing for the next steps.
P108178 | Second Land and Real Estate Registration Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2009 | 2014 | 2015 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/894351475118501183/text/000012394-20150310074817.txt | http://documents.worldbank.org/curated/en/894351475118501183/pdf/000012394-20150310074817.pdf | The ICR listed a number of lessons, but some of them were more like findings or conclusions than lessons. The main lessons (with some reformulation of language) were as follows:Robust M&E framework based on objective indicators and tracked consistently throughout the project is key to adequately monitor project outputs and outcomes. This allows for greater focus on what is important for PDO achievement and course correction, when necessary.A necessary condition for a vibrant land market is the existence of an efficient land and real estate registration system and a self-financed sustainable registration institution. These are particularly important especially in the face of political instability. Project support enabled the successful roll out of the IT system and the creation of the self-financed GIS Center, which has reduced the registration servicesâ€™ reliance on the state budget and will allow for future investments without straining the government budget.Keeping digital archives for land and real estate registry systems is important especially in politically volatile countries. Over the course of this project, separate digital archives were maintained and updated regularly. This was extremely valuable as records could easily be replaced when paper records were lost. The ability to issue certificates based on these records helped stabilize the country in the aftermath of the violence in the South. Partnership arrangements and coordination efforts with other donors with specialized skills are helpful for achieving effective implementation of projects. For example Bank-FAO partnership under this project was very effective in delivering technical advice to the Gosregister/DCR and the LROs on a range of topics, including surveying and mapping, valuation, IT, legal and associated matters. Likewise, technical support from SIDA was highly useful in aiding Gosregister/DCR and the LROs to develop and fully exploit the Bank funds to improve technology, skills and procedures. This Review adds another lesson, namely the importance of a project's implementation to address all aspects of a project's objectives, and that an ICR should draw attention such shortcomings.
P108253 | Niger Reform Management and TA | Western and Central Africa | Niger | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2010 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/743341519247994534/text/Niger-Niger-Reform-Management-and-TA.txt | http://documents.worldbank.org/curated/en/743341519247994534/pdf/Niger-Niger-Reform-Management-and-TA.pdf | The first two of the following lessons are taken from the ICR, with some adaptation of language, and the third is drawn byIEG. Capacity building on an institutional level demands ongoing support and cannot be viewed as a one-offintervention. In an environment where there are frequent institutional changes in government and a high rate ofturnover, it is necessary to provide capacity development support on an on-going basis. Exogenous risks that canjeopardize sustainability of project results need to be carefully assessed during appraisal. Whenplanning project activities and targets in the results framework, these risks need to be considered. Unforeseenchanges to a projects activities may trigger safeguards and hence require a reclassification. When a projectchanges to include unforeseen civil works that are likely to have an impact on the environment and on people, proactiveintervention during implementation, involving the requisite expertise, and restructuring the project to reflect the new safeguardscategory, is essential to ensure compliance with Bank safeguard policies.
P108258 | e-delivery of Public Services | South Asia | India | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2011 | 2012 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/180071474487832317/text/000020051-20140626105108.txt | http://documents.worldbank.org/curated/en/180071474487832317/pdf/000020051-20140626105108.pdf | The ICR includes useful lessons, particularly regarding the need for creative instruments and approaches to support the Government of India. This is relevant for efforts to support electronic governance as they involve long-term engagement to help institutional strengthening and short-term actions to establish inter-sectoral policy frameworks. The new lending instrument, Program-for-Results, might be able to address some of the challenges, but this review agrees with the ICR that an innovative and creative approach is needed for engaging with a sophisticated client on issues that are as complex as e-governance.
P108368 | Central African Backbone - APL1A | Western and Central Africa | Western and Central Africa |  |  | Infrastructure | Transport | IDA | IPF | 2010 | 2016 | 2017 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/135451493052490925/text/Western-Africa-AFR-Central-African-Backbone-APL1A.txt | http://documents.worldbank.org/curated/en/135451493052490925/pdf/Western-Africa-AFR-Central-African-Backbone-APL1A.pdf | Of the seven lessons provided in the ICR (page 40-42), the following four lessons are deemed to be the most importantfromthe experience of implementing this project and have broader application beyond this project ..(1) Projectsshould not move forward to Board approval if the project team and client countries are not truly committed and ready to implementthe project. In the case of this project, a deadline for IDA commitments was used as the justification for moving toproject approval.This led to the splitting the project activities in two phases - with the second phase focusing on theregional PPP dimension.Theproject countries perceived the regional PPP option as a top down option imposed by the Bankand considered this as an infringement on theirsovereignty. Consequently they took actionsin direct contradiction withthe regional PPP proposed for the second phase. This eventually resulted in cancellation of activities associated with thiscomponent.(2). A thorough political assessment of high-level national commitmentto regional commitmentcoupled with communication campaign is required for regional projects. While support from the heads of stateof a regional body such as CEMAC can provide important political backing for a regional project, general political economychallenges at the national level such as the interest of incumbent operators need to be addressed before designing a regionalproject. For regional projects such as this,a communications strategy and implementing agencies is necessary to ensure thatall stakeholders understand the objectives and desired results of the project.(3) For some difficult reforms inthe ICT sector such as awarding a new license, privatization of an incumbent operator, passing a PPP law, a Development PolicyOperations(DPO)may be a viable option. A DPO or series of DPOs at thenational or regional level undertaken in partnership and agreement with the country or countries that include these reforms asconditions or triggered may be a more appropriate instrument to use, in combination with Adaptable Program Loans(APLs).(4) This project demonstrated how a regional projects performance can be monitored at thecountry level since all results indicators were country-focused. Incorporation of country-based ME in regionalprojects can be helpful in identifying the best performing and less performing countries within a regional project in order tobetter target project issues.This can also help in streamlining regional projects into country programs.
P108368 | Central African Backbone - APL1A | Western and Central Africa | Western and Central Africa |  |  | Infrastructure | Transport | IDA | IPF | 2010 | 2016 | 2018 | PPAR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/668111530296585544/text/126034-PPAR-P108368-P117652-P165413-P165415-PUBLIC.txt | http://documents.worldbank.org/curated/en/668111530296585544/pdf/126034-PPAR-P108368-P117652-P165413-P165415-PUBLIC.pdf | 4. Lessons 4.1 A thorough political economy assessment and high-level national and regional commitment are key ingredients for complex regional ICT projects. The experience from CAB APL 1A illustrates that ICT reforms are politically difficult to implement due to the resistance and influence of incumbent operators. A thorough analysis of the political economy in all countries appears to be a critical tool to use during project preparation. It is essential that the political economy assessment identify high-level national champions (at senior positions close to the level of the President or Prime Minister) who can overcome political economy challenges. Commitment to the necessary reforms should be confirmed with official agreements. In addition, a communication campaign on planned reforms during project preparation and implementation, to sensitize stakeholders and get their continuous buy-in, is essential. 4.2 The experience from the Central Africa Backbone APL 1 and 2 project shows that public private partnership arrangements are difficult to implement in multiple countries, particularly when countries have asymmetrical needs and incentives with respect to increasing competition for the provision of international and national capacity. In CAB 1B, Cameroon perceived the regional PPP as an option imposed by the World Bank from above, considering it as an infringement on their sovereignty; consequently, they rejected the approach. This was also partially because Cameroon had less incentive to take part in the regional PPP, because it already had access to submarine cables and most of its national backbone was already built. Therefore, Cameroon withdrew its participation in the second phase of the project. Chad followed Cameroon and proceeded to have its national backbone built under a separate contract, creating a separate company in early 2012 to manage its fiber optic network in direct contradiction to the regional PPP envisaged under the project. On the other hand, in CAB APL 2, the existence of an upstream regional multi-country project (the Africa Coast to Europe-ACE) connecting up to 23 countries, facilitated the effective connection and implementation of public private partnership arrangement in Sao Tome and Principe. This was achieved as the implementation happened separately within each country jurisdiction based on regionally agreed parameters. 4.3 Technical assistance for the preparation of legislation and sector strategies is only the first step to creating an enabling environment for the ICT sector. The technical assistance can be effective if projects include sufficient resources to adopt legislations and strategies. In CAB APL 1A, there was a need for additional funds to implement the result of the studies developed by the project technical assistance. In Cameroon, for example, the regulatory agencies had to look for additional resources to implement some of the study recommendations. 4.4 Assessing and funding the capacity needs of Regional Economic Communities is important for project coordination and implementation, so that they can carry out their functions effectively. Regional institutions perform important roles, such as convening countries, securing their political commitment; helping them take collective decisions; playing an advocacy role; and performing M&E functions at the regional level. The project experience showed that CEMAC was effective during project design and negotiations but lacked capacity during implementation, particularly on M&E. The World Bank could have supported its needs through better use of its own influencing and coordinating power. 4.5 In weak capacity environments, it is beneficial that the projects build the needed institutional capacity for the Borrower to further/implement the crucial reforms and to ensure the sustainability of the investments in the country. For example, in APL2, the prepared regulations and ICT strategy were not adopted after the project was closed. In addition, although the project connected schools to the internet through last mile investments with planned O&M activities, lack of institutional capacity for monitoring and follow up made the results unsustainable.
P108373 | Third Emergency Services Support Project (ESSP III) | Middle East and North Africa | West Bank and Gaza |  | FCS | Human Development | Social Protection & Jobs | SPF | IPF | 2008 | 2013 | 2014 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/481231475111867351/text/000020051-20140626115012.txt | http://documents.worldbank.org/curated/en/481231475111867351/pdf/000020051-20140626115012.pdf | Lessons from the ICR (pp. 20-21), with adaption by IEG:Field-based task team staff are highly beneficial in an emergency context. In the case of this project, implementing agency staff had quick and easy access to the Bank team, there was close monitoring of implementation progress, and there was quick responsiveness to government requests.M&E can still be carried out effectively in an emergency context with low capacity in the line ministries. In the case of this project, the project team was still able to collect basic data on the functioning of education, health and social services to inform project implementation progress. Enabling factors likely included the fact that this project was the third in a series of identical projects that utilized the same indicators, and the intensive supervision (quarterly progress reports from line ministries, regular spot checks by an independent auditor, and quarterly supervision missions by the field-based task team).
P108440 | Mali Energy Support Project | Western and Central Africa | Mali | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2009 | 2018 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/929901588777501123/text/Mali-Mali-Energy-Support-Project-SIL-FY09.txt | http://documents.worldbank.org/curated/en/929901588777501123/pdf/Mali-Mali-Energy-Support-Project-SIL-FY09.pdf | The ICR provided the following key lessons (with some adaptation in wording):A focused project design producesbetter results than a complex project with multiple objectives. The projects positive achievements can be traced tohaving allocated most of the projects resources to reinforcing the transmission and distribution networks (90 percent ofproject funds). The remaining funds were assigned to supporting energy efficiency activities, capacity building, and institutionalstrengthening. The PDO was also formulated such that the desired results focused on increasing electricity access and efficiency.The Bank team also gave consistent emphases to electricity infrastructure on the ground, which in turn also helped achieveefficiency gains. More diverse and lower achievement levels may have been obtained if the project had been expanded to includepower utility reform or the expansion of rural electrification.The World Bank can achieve results in fragileenvironments, if it can move more quickly toward a systematic approach containing a set of dedicated procedures and guidance forprojects in fragile countries. The 2012 security crisis in Mali was overwhelming and initially pointed towards theBanks closing up its operations until security was fully restored. The new World Bank arrangements that allow operations infragile environments can be effective if they are timely and rapidly implemented. The preparation of an Interim Strategy Note (ISN)based on a sustained dialogue with the key stakeholders in Mali and in the donor community, the overhaul of the countrysportfolio, and the restructuring of the project all contributed to the success of this project. Past experiences from operationscompleted in Mali and elsewhere should be fully captured to ensure that new procedures tailored to theFCV context are adoptedand become effective.For activities to successfully contribute to the project objective, they should be highlyconsistent with the borrowers immediate needs and priorities. This projects performance in building thetransmission and distribution infrastructure was satisfactory because that activity was in line with the Governments plan toexpand energy access. Despite political instability and changes in the power utility management, all resources devoted to thisactivity were used to deliver the expected output. Activities supporting the energy efficiency and innovation (loss reduction andsolar-powered energy) were less successful, because they were not on the priority plate of the borrower. Activities to be supportedby a World Bank project should be carefully researched and tested for close strategic alignment with the Governments keypriorities before their selection as project components.Inadequate readiness impedes the timely launching ofproject implementation. Implementation readiness means that the project implementing agency must have (i) all stakeholderson board at approval, and (ii) the required expertise (including fiduciary management and safeguards) by the time the projectreaches effectiveness. In the case of this project, all stakeholders were not ready for implementation, as EDM-SA becameeffectively operational after the creation of an implementation unit three years after effectiveness (2002). Procurement expertiseand technical experts were also lacking until the recruitment of a private firm and competitive staff to assist EDM-SA to procureand install transmission and distribution equipment.
P108443 | Sao Paulo Sustainable Rural Development and Access to Markets | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2010 | 2019 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/338911561728559557/text/Brazil-BR-SP-Sust-Rural-Dev-Access-to-Markets.txt | http://documents.worldbank.org/curated/en/338911561728559557/pdf/Brazil-BR-SP-Sust-Rural-Dev-Access-to-Markets.pdf | 1. In designing an agricultural marketing project, inclusion of measures to increase agricultural yields couldsubstantially increase the projects impact.The project included some, but very limited, agriculturalextension, relying on the general agricultural extension services of the state extension agency. Yet with more targetedagricultural support services, crop yields would likely have increased further, substantially enhancing the overall impact of theproject on productivity by increasing crop yields as well as market valueadded.2. Specialist marketing and business experience are required todevelop and implement an agriculturalmarket development project. The preparation and supervision teams had abroad array of disciplines including in agribusiness, and staff had some general exposure to marketing in the course of their work,but this was mostly in a generalist capacity. More specialist inputs would have been desirable. (For instance, specialist skills inmarket chains, business development, commercial relations, assessing commercial opportunities and diversifying marketoptions.)3. Opportunities to boost participation of women should be sought forin a rural development/marketing project.The project, unlike its predecessor, the Land Management III Project, whichhad a proactive and well-regarded gender focus, had no specific program or features supporting participation of women, nor even anydata collected regarding gender participation. A rural development and marketing project involving community organizations is wellsituated for actions and processes that can foster greater social inclusion, and a gender participation program to that effectwould have been desirable.4. If a projects main institutional features andmain component(s) are not ready for implementation from Effectiveness or earlier, with core needs such as procurement alreadystaffed and trained, there is a risk of implementation delay. The project, while ultimately successful, required anextension of the originally planned 5 years by a further 3 years. The primary reason was the unreadiness of theimplementing agencies, both in their institutional linkages and in staff skills and experience, and there was a complete lack ofexperience amongst the farmer organizations. Procurement procedures and other operational capabilities were also lacking, and theagencies and farmer organizations had little experience in marketing. An initial two yearsintegrated in project design tobuildimplementation capabilities would have been more responsive.
P108444 | MZ-Energy Development and Access Project (APL-2) | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2010 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/157701526683577615/text/Mozambique-MZ-Energy-Dev-Access-Project-APL-2.txt | http://documents.worldbank.org/curated/en/157701526683577615/pdf/Mozambique-MZ-Energy-Dev-Access-Project-APL-2.pdf | Three lessons are derived from the ICR by IEG.Project objectives which are not clearly definedcan be overlooked during project implementation. The project objective to increase access to modern energyservices was not defined in the PAD or the ICR. The projects focus shifted on increasing electricity access and movedaway from the distribution of woodfuel stoves, which is the other component of modern energy services, according to the definitionby the International Energy Agency. At the first project restructuring, while the project activities related to the woodfuel stoveswere substantially decreased, the project development objective was not revised nor the ME design was changed to monitor theachievement of project objective to increase modern energy services.A lack of understanding ofgovernments large-contract clearance procedures can adversely affect projectimplementation. As explained in Section 10.b. Fiduciary Compliance, advance payments to some contractors could notbe made on time because of the lengthy approval process of large contracts by the Commission for External Economic Relations, whichis chaired by the prime minister. As the ICR (p.38) states, assessment of such clearance procedures at appraisal would help designmore realistic procurement plans and implementation schedules.Establishment of designated accountsfor project implementing agencies, especially for those which have state-owned economic enterprise status, can facilitate anefficient flow-of-funds and disbursement system. The use of government accounts and systems required EdM to pay theinvoices first and to be reimbursed by the MIREME later. This caused delays in project implementation until a designated accountwas established for EdM at the first restructuring.
P108489 | India First Statistical Strengthening Project | South Asia | India | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2010 | 2012 | 2012 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/854131474854179550/text/000020051-20140625111607.txt | http://documents.worldbank.org/curated/en/854131474854179550/pdf/000020051-20140625111607.pdf | This assessment agrees with the lesson drawn in the ICR that a short-lived instrument such as a stand-alone DPL is inadequate for a program of reforms that is likely to take years and that needs more attention to intermediate outcomes. The better alternative that comes to mind is a program of DPLs (with a first set of loans focusing on intermediate results and latter loans focusing on final development outcomes), as originally suggested by the project's QER in 2008 and requested by the ROC. Or perhaps a project loan with disbursements focused at the federal level could have been better tailored to progress in implementation.This assessment also agrees with other ICR lessons pointing to the usefulness of knowledge transfer through supervision missions, the criticallity of mature country systems to ensure good quality strategies and implementation, and the benefits of technical assistance and capacity building efforts in implementing reforms at the state level.
P108525 | Capacity Building for Economic Management Grant | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2009 | 2014 | 2016 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/608221467998175911/text/ICRR14812-P108525-Box393228B-PUBLIC.txt | http://documents.worldbank.org/curated/en/608221467998175911/pdf/ICRR14812-P108525-Box393228B-PUBLIC.pdf | The IEG review draws the following lessons:Projects aiming to improve the effectiveness of government institutions will benefit from an initial assessment of the gaps or pitfalls in targeted institutions. As the ICR points out, capacity constraints could have been assessed early to address them in time for project implementation. Similarly, project objectives could have been articulated more precisely with good knowledge of capacity constraints.Monitoring and Evaluation needs precise objectives that are amenable to measurement. The projects imprecise objectives made it difficult to assess progress, all the more so as the objectives targeted complex institutional performance issues.Sustained capacity building achievements will require that the public sector is enabled to hire and retain adequate staff. Otherwise, the Government will not be ready to absorb and maintain capacity building efforts. There is a risk that the projectâ€™s capacity building achievements will suffer from the public sectorâ€™s high turnover rates.
P108583 | 3A W/C Africa Air Transport Phase II-B | Western and Central Africa | Western and Central Africa |  |  | Infrastructure | Transport | IDA | IPF | 2009 | 2013 | 2014 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/868041474510169097/text/000180307-20141201110500.txt | http://documents.worldbank.org/curated/en/868041474510169097/pdf/000180307-20141201110500.pdf | The following three lessons are the most important ones drawn from the longer list presented in the ICR (with some adaptation of language):Numerous and demanding effectiveness conditions are likely to delay implementation. Minimizing, and if possible eliminating, such conditions would be facilitated by transferring them to the pre-negotiation or pre-Board presentation stage.Ensuring timeliness of externally conducted technical audits, and their coordination with project activities, is important for measuring progress when the audits are meant to play a determinant role in evaluating outcomes. The limited window of opportunity to have ICAO audits confirm compliance with international standards led to reliance on self-evaluation by the implementing agencies.Including two countries with wide disparities in technical capacity and requirements in the same project can lead to discrepancies in performance which make evaluation of the project as a whole difficult.
P108592 | GEF Huai River Basin Marine Pollution Reduction Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2012 | 2016 | 2017 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/840911479715891826/text/1478095732062-0000A8056-ICRR-Disclosable-P108592-11-02-2016-1478095720121.txt | http://documents.worldbank.org/curated/en/840911479715891826/pdf/1478095732062-0000A8056-ICRR-Disclosable-P108592-11-02-2016-1478095720121.pdf | Among the principal lessons highlighted by the ICR (pp. 33-34) are the by now generally well-understood needs for strong andpersisting government commitment to project objectives and design and for localassociations, such as the FEPAs, to be basedon firmbeneficiary ownership. It also pointed to the needs for appropriate institutional arrangements -- in thepresent case to permit adequate cross-sectoral coordination -- an adequate implementation period, and for the restructuring ofpoorly implementing andoverly complex projects in relation to borrower institutional capacity.To theselessonsshould be addedthe needs: (i)to ensure that key projectoutcome indicators are fully and clearlyaligned with project development objectives; and (ii) for the economic analysis methodology applied at appraisal to be appropriate,in the present case cost-effectiveness rather than cost-benefit analysis.
P108627 | Nanning Urban Environment | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2010 | 2016 | 2018 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/834191504716444207/text/ICRR-Disclosable-P108627-09-06-2017-1504716432254.txt | http://documents.worldbank.org/curated/en/834191504716444207/pdf/ICRR-Disclosable-P108627-09-06-2017-1504716432254.pdf | Following lessons emerged from the project(ICR pages22-23): Timely restructuring is goodpractice in project implementation. Restructuring should be carried out as soon as the need materializes in order toenable the proper accounting of project activities and an assessment of project performance that is based on accurate and adequateevidence. Project implementing entities need to be trained as early as possible in fiduciary and safeguardsrequirements in order to improve the efficiency of project implementation. Ideally before project effectiveness, theBank should share the rules for handling variation orders with the client, and the client should report to the Bank the planning,design and other changes that are necessitating those variation orders. Project implementation staff need to be trained wellin resettlement and land acquisition and resettlement aspects, to ensure the proactive handling of any issues and adequatecoordination with other agencies. The planning and optimization of municipal infrastructure is needed in order toyield savings in capital and OM costs. For example, the design and size of WWTPs can be optimized by carefullyaligning the design parameters with influent water characteristics and the existing facilities in the services areas (e.g., whetherthese have septic tanks or combined sewer systems). It is also important to have a balance between infrastructure investments andinstitutional or regulatory capacity-building. Assigning sole responsibility to a single utility can effectivelyenhance technical competencies, financial sustainability, and project management efficiency. Under the project,GNWC, which was made responsible for the Jiangnan and five smaller WWTPs, proved highly competent in management and OM, and ingenerating enough revenue to cover operation costs. IRBMs innovative management mechanism for dealing withmunicipal water environment and pollution control provides a good example for other cities in China. It takes acomprehensive approach that includes modification and enforcement of laws, and capacity building of local governments. Moreover, itaddresses uncoordinated and fragmented activities by defining the roles and responsibilities of various agencies.
P108654 | Brazil Pernambuco Sustainable Water | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2010 | 2020 | 2022 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/981611635980989090/text/Brazil-Brazil-Pernambuco-Sustainable-Water.txt | http://documents.worldbank.org/curated/en/981611635980989090/pdf/Brazil-Brazil-Pernambuco-Sustainable-Water.pdf | IEG derives the following lessons drawn from the ICR:Project implementation should focus on ensuring thatsewerage household connections are installed in parallel to the construction of the wastewater treatment plants. Theinstallation of wastewater household connections was designed to start after the construction of the wastewater treatment plantswas complete. Connections should take place during the construction of the sewerage network to ensure that treatment plants receivesufficient wastewater flows.Innovative approaches to design and build WSS systems efficiently should beincentivized to accelerate project implementation, ensuring that set outcomes are met. The Bank and COMPESA foundinnovative solutions for the construction of water supply and wastewater systems which were time and cost effective, includingthrough design-build-operate contracts and performance-based contracts. The design-build-operate contracting approach was testedwith the Santa Cruz do Capibaribe sewerage system. This allowed COMPESA to complete the project in a timely manner, with fewercontract amendments than through the traditional approach of bidding for works with basic engineering designs. COMPESA plans are toadopt the design-build-operate approach for a number of upcoming water supply and sewerage works packages. Similarly, theperformance-based contracting approach used for the first time with the Olinda NRW reduction program is now being replicated andexpanded to other municipalities under COMPESAs management.Vulnerabilities to climate change and othernon-climatic stresses and shocks should be incorporated into project design and implementation support plans for water andsanitation investments. The identification of the vulnerability of water systems to climate and other non-climaticuncertainties during project design should be accompanied by appropriate planning and project management mechanisms to enhancepreparedness and response, but also to set realistic targets for project objectives, particularly in areas known to suffer fromnatural disasters such as droughts and floods. Techniques for assessing the vulnerability of water systems to climate change andother non-climatic uncertainties should be integrated into implementation support tools to inform in a timely manner the need forrestructuring and for adjusting targets as well as infrastructure component designs. In addition, taking into account thehydrological risk associated with recurrent droughts into the design of infrastructure could for example lead to more flexible,robust, progressive and resilient approaches to planning and building water and wastewater systems, thus minimizing the impacts ofreduced water or wastewater flows on their operation and on the costs (both capital and operating expenses) associated with theseassets.
P108759 | Public Expenditure Development Policy Loan | Europe and Central Asia | Serbia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2011 | 2016 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/829331473934079095/text/ICRR14947-P108759-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/829331473934079095/pdf/ICRR14947-P108759-Box396299B-PUBLIC.pdf | The ICR draws some important lessons (1 through 3), which IEG re-interpreted and summarized as follows. Lessons no. 4-5 have been added by IEG.1. Reforms lacking the support of effective champions may fail to show progress. In the education sector where there was no effective champion little progress was made.2. Mixing short-term fiscal objectives with medium-term structural reforms of public expenditures can lead to contradictions and obstacles to the achievement of one or the other of these objectives. And linking them can lead to the entire program (and the associated external financing prospects) going astray, on account of shortcomings in only one dimension of the program.3. Indicators and targets that consider alternative possible scenarios may improve the usefulness of M&E, especially when achievements of outcomes can be strongly affected by unforeseen external macro-economic developments (e.g. as in the case of the wage and pension bills defined as shares of GDP), and of future data availability (e.g., as in the case of PEFA indicators). 4. In crisis situations, the Bankâ€™s exposure limits may reduce its role in shaping a DPL program. If the World Bank could have lifted, at least temporarily, its exposure limits to allow an even larger financial assistance package, it would have provided the Bank a stronger role in shaping the overall fiscal consolidation program, which instead was driven almost solely by the IMF, and more leverage over the scope and pace of the structural reforms it supported.Crisis situations, when it is necessary to minimize cuts in social spending, may be good opportunities to make social assistance programs more effective (e.g. improving their targeting) This was indeed the case for Serbia in 2009-2011.
P108768 | Mongolia Mining Sector Technical Assistance Project | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2008 | 2016 | 2018 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/715971513954323042/text/ICRR-Disclosable-P108768-12-22-2017-1513954316170.txt | http://documents.worldbank.org/curated/en/715971513954323042/pdf/ICRR-Disclosable-P108768-12-22-2017-1513954316170.pdf | Two lessons are derived from the ICR.Technical assistance projects with the objective ofreforming one of the major economic sectors of a country can be adversely affected by the changes in the politicallandscape. Especially after the government change in Mongolia in 2012, some of the project activities could not beimplemented due to the governments decision to review the Mining Law which resulted in a moratorium on mineral licensing(ICR, p.17). Furthermore, the governments decision to increase its control over the state equity holding company of Erdenesforced a Level 1 restructuring of the project development objective (ICR, p.18).Availability offunds from global capital markets to finance government investments and expenditures can reduce acountrys reliance on donor financing, which in return might reduce thegovernments appetite for sectoral reforms exclusively through technical assistanceprojects (ICR, p.17). This can also result in a restrictive foreign investment regime which would further diminish theneed for reform (ICR, p.17). Therefore, although a countrys easy access to funds is not a bad thing, per se, yet, in orderto keep the countrys interest and commitment to sectoral reforms through technical assistance, such projects may besupported by other financing instruments, such as Program for Results (ICR, p.38).
P108776 | MONGOLIA: EDUCATION FOR ALL FAST TRACK INITIATIVE (EFA-FTI) CATALYTIC TRUST FUND | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Human Development | Education | RETF | IPF | 2007 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/625071475873281399/text/000012394-20150312065529.txt | http://documents.worldbank.org/curated/en/625071475873281399/pdf/000012394-20150312065529.pdf | The ICR (pp. 17-18) offers the following useful lessons:Low-income countries operating under severe financial constraints can benefit greatly from â€œbridge fundingâ€ that funds capital expenditure and other development expenses until they can begin to cover such expenditures on their own. This lesson may ring particularly true for countries, like Mongolia, undergoing economic transition.Even when financed through an instrument whose guidelines require use of broad, global objectives and indicators, projects should be careful to supplement those requirements with project-specific indicators so that attribution of results can be plausibly established. In particular, the indicators should fit the scale of the intervention. A wide variety of constraints and variables, including institutional capacity, weather, and construction costs, can impact construction efforts. Projects need to anticipate such variables and supervise closely, retaining a civil works engineer as part of supervision teams where appropriate.
P108787 | Public Finance Management Strengthening Program MDTF | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2008 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/714251468186253286/text/ICRR14652-P108787-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/714251468186253286/pdf/ICRR14652-P108787-Box393183B-PUBLIC.pdf | The ICR contains a number of lessons from this project. IEG broadly supports several of these suggestions, many of which have been commonly brought up in the course of evaluations of this kind of project. This includes the importance of an effective project steering committee, and an operational manual that adequately reflects local implementation capabilities. IEG believes that the following lesson taken from the ICR (with some adaptation of language) is particularly important and needs to be highlighted: Accurate assessment of the Recipientâ€™s capacity and, more generally, of the project-related institutional environment is crucial for designing a capacity-building project. In a low capacity environment the institutional arrangements are generally fragile and simple re-use of institutional solutions, which functioned well for the earlier projects, would not guarantee a continuous success. Undertaking a project-specific capacity needs assessment could be a useful tool of risk mitigation. In addition, IEG supports the following lesson: In cases when there has been a long-standing issue with project governance arrangements and lack of the recipientâ€™s cooperation to resolve the problem, the Bank needs to be prepared to be more proactive in pushing for a satisfactory resolution, including downgrading the implementation rating and indicating to the authorities readiness to cancel the project. Any project extension in such situations should be made conditional on the recipientâ€™s performance in line with the agreements made.
P108791 | International Institute for Water and Environmental Engineering (2ie) | Western and Central Africa | Burkina Faso | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2008 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/313151479137007236/text/ICRR-Disclosable-P108791-11-14-2016-1479136991096.txt | http://documents.worldbank.org/curated/en/313151479137007236/pdf/ICRR-Disclosable-P108791-11-14-2016-1479136991096.pdf | Lessons drawn from the ICR, adapted by IEG: A robust business plan addressing the financial and operationalsustainability of an institution can be a strong driver of collective actionfrom donors and partnership institutions.In the case of this project, the plan attracted additional investment, raised political commitment, and allowed partners toidentify areas of comparative advantage. Effective donor collaboration in ME and procurement can help facilitateproject implementation. In the case of this project, agreement among donors and partner institutions to harmonize ME andto consolidate procurement approvals through one agency helped to ensure that ME arrangements were carried out as planned andthat procurement could go smoothly after initial delays.
P108879 | AFCC2/RI-Nyika Transfrontier Conservation Area Project | Other | Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2011 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/826391523281313531/text/Africa-Nyika-Transfrontier-Conserv.txt | http://documents.worldbank.org/curated/en/826391523281313531/pdf/Africa-Nyika-Transfrontier-Conserv.pdf | The ICR has five main lessons. They are useful but arguably not new for projects of this type. They are given here with someadjustment of language and someexpansion ofsubstance. In a transfrontier conservationinitiative, high-level commitment within the participating governments is crucial because of the need for collaborationnotjust on thetechnical and management issues but also on the political issues. In this case, it was particularlyimportant to get the relationship formalized in a treaty signed at the highest level. It was also useful that there were alreadyshared historical and cultural values between the two countries and that there was already a good working relationship betweenresponsible departments at the technical level. Conservation efforts cannot be dissociated from stronginvestments in communities surrounding national parks and reserves but this requires a thorough understanding of any parallelprograms aimed at livelihoods and careful planning to accommodate the phasing and sources of this support and to forecast theresidual need for project investments. In this case, the project did not handle the design and the phasing for this issueas well as it might have. Initially the livelihoods activities were to besupported by other interventions. However, theseturned out to be insufficient for the full project period and adjustments had to be made. Robust design andtimely implementation of ME is particularly important for a transboundary conservation initiative calling for coordinationbetween two countries. In this case, there were weaknesses in design that led to weaknesses in implementationpartlydueto staffing and skills issues. There was also weakness in an insufficient ex ante analysis at appraisal of thechallenges and costs of counting wildlife and interpreting findings. There could have been more attention at appraisalto theexploration ofother efficacy and efficiency indicators such as: at intermediate outcome levels - numbers and type ofinteractions betweenagencies or unitsat field level; trends in poaching encounters and apprehensions; changes incommunity reporting of localillegal activities; changes in community earningsfrom tourism and wildlife; community,wildlife guide, wildlife professional, and lodge/tour operatoropinion surveys; and, at higher outcomelevels,possiblycontingent valuation analyses.
P108885 | VN - Agriculture Competitiveness Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2014 | 2015 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/613891467998481010/text/ICRR14698-P108885-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/613891467998481010/pdf/ICRR14698-P108885-Box393183B-PUBLIC.pdf | The ICR includes eleven lessons and four of these are selected below with some adaptation of language:Projects promoting a â€˜demand-drivenâ€™ approach may give rise to scattered â€˜islandsâ€™ of activity not able to reach a critical scale or have notable impact in any major value chain. The possibility of more transformative impacts is increased if technology, partnership and infrastructure interventions are more strategic and geographically clustered.Facilitating increased private service provision, contract farming, and more multi-dimensional public-private collaborative initiatives in agriculture requires a set of â€˜soft skillsâ€™ which may not be readily available at the level of provincial agricultural departments. If applying a decentralized approach and seeking to rely upon public systems to facilitate these institutional changes or innovations, then considerable early and sustained attention needs to be given to training and technical support. Also, other modalities (i.e. using NGOs; private management companies; industry associations) should also be considered. Incentives may be weak in relation to smallholder agriculture, where there is little â€˜willingness to payâ€™ for stand-alone advisory servicesâ€”for example, in relation to â€˜good agricultural practicesâ€™. Incentives for private entities to provide technology demonstration and advisory services may be strong whenever the company has something to sellâ€” inputs, equipmentâ€”or wants to buy a commodity with distinctive characteristics. In the case of smallholders, service providers may need to be specially contracted to provide such services. Promoting complex relationships between farmer organizations (FOs) and established agribusiness companies is better done in stages. Newly formed groups without any history of collective action will be regarded as unattractive partners by companies. For new or weak FOs, to the initial focus should be on developing core management skills and effective governance arrangements and undertaking a few basic functions. Incremental steps in collective action (i.e. â€˜partnerships among farmersâ€™) should precede efforts to link them directly with specific downstream buyers, and even then, several steps may be needed to build trust and confidence before any significant multiple commitments are made.
P108932 | Pastoral Community Development Project II | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2008 | 2014 | 2016 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/239031468190450033/text/ICRR14742-P108932-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/239031468190450033/pdf/ICRR14742-P108932-Box393191B-PUBLIC.pdf | The ICR drew five lessons from the project. In brief they were (a) Communities gain confidence in their ability to solve their own problems when they receive appropriate training to support decision-making. (b) Community empowerment can be achieved by consultation early in the process on their priorities for use of scarce project funds. (c) An SOE-driven approach to CIF replenishments is too unwieldy and creates implementation delays. A more practical needs to be found for all such projects.(d) Rural savings and loan cooperatives work well in promoting income generating activities that communities are very familiar with, but less so on promoting new income generating activities. (e) Small-scale irrigation interventions, crop yield improvements are almost automatic in terms of implementation, but crop diversification is not because it was found that farmers require more time, along with support services, to diversify crops to such things as onions and tomatoes. This Review concluded that there were five broad lessons from the project:(a) Care needs to be taken in ensuring that a CDD model of development is fully participatory and integrated into local development planning processes, since without this, the ownership and sustainability of community driven development planning will be weak and the process and its effects (pro-poor participation in local development planning, increased relevance and resilience of community demanded assets, better targeted distribution of assets etc) will diminish after project close. (b) Projects that seek to reduce vulnerability of project affected persons require a clear method for assessing and measuring vulnerability and the project attributable impacts, especially in an environment with several donor and government funded initiatives seeking to secure the same effect. (c) Implementing CDD within transhumant societies requires a differentiated design for the agro-pastoralists that are largely sedentarized and the migrating population and their relatives residing in associated hamlets. There are many lesson to learn from this project about how to design and implement a CDD program that takes these differences into account, especially in a fast changing social and economic environment that were not presented in the ICR. Facilitation, for example, will require a different skills set and some assets will need to be mobile. Decision-making processes will vary and will need to be designed in a manner that takes into account the needs of pastoralists who may not be present in decision-making forums.(d) Care also needs to be taken to understand the role of the pastoral projects as a function of the wider political-economy, especially with regard to the role of the project as function of programmatic goals designed to sedentarize pastoral communities. (e) Pastoral Development projects are often implemented in environments that are characterized by a certain level of land and asset contestation. While this project had a grievance mechanism, the effectiveness of this mechanism was not reported in the ICR. Donors should apply a conflict filter in such cases to determine whether interventions in contested areas may help or hurt a fragile environment, and adjust design accordingly. In the case of the PCDP, the project indicated it would avoid areas affected by conflict, or the risk of conflict. However a strong justification is required to ensure that the redirection of aid in these areas will not exacerbate grievances or potentially contribute to pockets of increased poverty and insecurity. The approach needs to weighed against multiple factors.
P108932 | Pastoral Community Development Project II | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2008 | 2014 | 2016 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/842511468195564739/text/104210-PPAR-P075915-P108932-P156317-P156319-SecM2016-0132-Box394878B-OUO-9.txt | http://documents.worldbank.org/curated/en/842511468195564739/pdf/104210-PPAR-P075915-P108932-P156317-P156319-SecM2016-0132-Box394878B-OUO-9.pdf | 5. Lessons High-level lessons on program strategy and sequencing 10 IEG interview with State Minister of MoFA. 11 IEG interview with the Pastoral Affairs Standing Committee. 12 PPAR mission interviews. Programmatic approaches that involve multiple projects over a long period of time are more effective when, in addition to assessing project outputs, they measure the extent to which overall programmatic objectives are being met. There is a need to have a results framework that specifies not only the short-term objectives of each of the projects in the series but also how these link to the overall program objectives. M&E systems should track not only individual project accomplishments but should also be designed to assess the programmatic objectives, even if these can only be achieved over time. Triggers for moving forward with successive phases of an adaptable program are more effective when they take stock of the extent to which the project is meeting its overall program aims. This stock-taking should promote mid-course correction based on lessons. A rigorous independent impact assessment conducted after each phase can provide the more accurate information needed to ensure that the program is well phased. The Bank can use the body of knowledge gained through its successive project interventions to help governments develop an informed sector strategy, especially in difficult and uncertain areas such as pastoral development. While the Bank may choose to proceed with project support, it is critical that in the absence of a clear approach, Bank experience be used to support the development of such a strategy through dialogue and continued engagement. Project-specific lessons Support for household or small rural income generating activities is more effective when based on needs and capacity assessments and supported by business planning, training, legal and technical assistance, and the supply of affordable finance. Group-executed activities are complex, because they require strong trust and cooperation among members who, if the group is formed by the project, require time to build trust. The decision to support individual versus group economic activity should be based on an understanding of existing social norms and economic relationships. Rural savings and credit groups can be successful when there is a strong sense of cohesion in the community, when they have a predominant focus on women, and when they are supported with adequate and sustained capacity-building support. Seed capital, and clear rules of the game, were also found to be key ingredients in helping to ensure the success of the rural savings and lending groups in Ethiopia. When dealing with mobile pastoral communities, consideration should be given to different service provision approaches such as mobile schools and health to supplement the classic participatory local development model, which is better suited to sedentary populations.
P108974 | Nicaragua Hurricane Felix Emergency Recovery Project | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2008 | 2015 | 2016 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/194261468000290735/text/ICRR14810-P108974-Box393228B-PUBLIC.txt | http://documents.worldbank.org/curated/en/194261468000290735/pdf/ICRR14810-P108974-Box393228B-PUBLIC.pdf | The following main lessons are drawn from the project experience and the ICR: 1. The design of emergency recovery projects should be focused on sustainable short-term activities directly related to the recovery which can be implemented rapidly.HFERP was a hybrid between short-term emergency related actions, and longer-term investments in institutions and infrastructure, which diverted attention and resulted in a longer implementation period.2. Implementation arrangements for emergency operations should be straightforward and pragmatic rather than supportive of more complex long-term institutional goals.Using the project to support Governmentâ€™s strategy to decentralize and mainstream national administration severely impaired project implementation capability.3. Make component design simple and able to take off fast.It was unlikely that creating a revolving credit fund, and (later) switching management to a new, inexperienced bank would take off quickly. Other options could have been considered. For instance, providing direct grants to fishermen through an existing agency would likely have enabled a much faster response in the short term, with a more mainstreamed credit system to be built later. 4. Provision of livelihood activities should have follow-on technical assistance to beneficiaries rather than disengaging once the activity is launched.Under the fisheries program, beneficiaries received technical assistance when credit was initiated, but longer-term follow-up was not provided, even though some technologies â€“ such as operation of new boat engines - were new to the fisher-folk (breakages were frequent).
P109024 | Aceh Economic Development Financing Facility | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2009 | 2013 | 2015 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/872091475116336281/text/000180307-20150108103239.txt | http://documents.worldbank.org/curated/en/872091475116336281/pdf/000180307-20150108103239.pdf | The ICR identifies several important lessons emerging from the project, including :Collaboration between governments and NGOs can be a valuable tool to foster development but requires careful preparation (e.g., pre-identification of potential partners) and an adequate time frame; andIn a complex set up, it would be better to start with one/two pilot projects to develop know-how in the selected SIEs and in the government agency overseeing them and to test solutions before scaling up and replicating.
P109078 | EFA/FTI: Education Sector Development Program | Western and Central Africa | Mauritania | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2008 | 2012 | 2013 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/197471474633592143/text/000020051-20140625231648.txt | http://documents.worldbank.org/curated/en/197471474633592143/pdf/000020051-20140625231648.pdf | The ICR presented a number of lessons (pgs 20-21): Special agreements with United Nations Agencies and other donors should be cleared early in the appraisal process. This refers to the World Food Program activity which was delayed for a year as there were no standard contracts that could be cleared by the Bank.Community participation for school construction can enable low cost school construction and local ownership. Communities using this approach need to be trained in school maintenance and construction should be complete, including privacy fences and latrines.Project preparation should include a quality review regardless of institutional requirements This lesson draws attention to the lack of quality oversight in the development of the project, although it is clear that not all projects can have a full quality review process. This should be discussed further with the Fast Track Initiative management.In addition, IEG found two further lessons:Tightening activities and objectives at mid term would have led to a more monitorable project.Projects cannot be considered Satisfactory in Implementation Status Reports if they are not progressing towards overall project development impact. A reasonable disbursement profile does not give the whole picture of project progress towards development goals.As noted in comments from the Region, the Bank needs to ensure that when working as an implementing agency for a third party organization, the criteria for project design are compatible with those standard for the Bank in order to ensure quality and the ability to measure results..
P109126 | Rural Enterprise Support Project Phase II | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2008 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/163191512745196672/text/ICRR-Disclosable-P109126-12-08-2017-1512745187552.txt | http://documents.worldbank.org/curated/en/163191512745196672/pdf/ICRR-Disclosable-P109126-12-08-2017-1512745187552.pdf | The ICR provided three lessons, based on which, and with some adaptation, this Review identified the following mainlesson:1. A combination of training of financial institutions on lending appraisal and risk management withtraining of farmers and rural enterprises on business planning and use of technology is key to increasing lending to theagricultural sector. The project provided training to staff in participating financial institutions on project appraisal,risk assessment, and monitoring to reduce risk aversion of the commercial banks. At the same time, the project trained farmers andagro-processors on preparation of high quality business plans and on adoption of good/ sustainable agricultural practices toincrease profitability of investments. These were key to increasing the lending portfolio of the participating financialinstitutions (PFIs) in the agricultural sector (ICR, paras 73, 85 and 87). By project completion, 57 percent of the PFIs hadincreased their agricultural portfolio by at least 10 percent per year during the project implementation period, exceeding thetarget stipulated in the project appraisal document by 42.5 percent (ICR, Data Sheet).In addition, this Review suggeststhat the following lesson was alsolearned:2. Rural enterprise finance projects should ensure that data onprofitability of sub-projects are collected adequately at projectcompletion.Underthe project, creditfunds were provided to the PFIs for a period of 20 years. All data on sub-projects were kept at these PFIs. The projectimplementing agency (RRA) for the ICR received data on the profitability of only 14 sub-projects, representing only 2 percent ofthe total number of enterprises the projects credit funds supported. PFIs refused to give profitability data for moresub-projects on the ground that it was too soon to see the profitability results at the project completion. In addition, it wasunknown whether the 14 sub-projects were selected on a random basis. This resulted in a significant gap in evidence on the projectefficacy.
P109126 | Rural Enterprise Support Project Phase II | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2008 | 2017 | 2019 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/673121555683514715/text/Uzbekistan-Irrigation-and-Drainage-Interventions-to-Support-the-Agriculture-Sector.txt | http://documents.worldbank.org/curated/en/673121555683514715/pdf/Uzbekistan-Irrigation-and-Drainage-Interventions-to-Support-the-Agriculture-Sector.pdf | 5. Common Lessons 5.1 IEG's assessment of FVWRMPâ€I and RESPâ€II generates the following common lessons\. 5.2 Expanding the uptake of waterâ€efficient agricultural technologies requires policies that provide a strong incentive to adopt those technologies. Both projects included activities to promote farmers' application of waterâ€saving technologies. However, such use was limited in FVWRMPâ€I. Despite generally better technology adoption in RESPâ€II at project completion, the sustainability of those practices is at risk given the current policy environment. An improved incentive structure would include policies encouraging adequate water pricing and/or quotas to avoid water overuse by farmers, promoting less waterâ€intensive crop cultivation, and enhancing land tenure security and access to rural finance. 5.3 Water consumer associations can deliver efficient irrigation services when backed by a legal framework that clearly specifies their responsibility and accountability within the entire irrigation service delivery institutional system. The assessment of WCAs in the FVWRMPâ€I and RESPâ€II projects revealed deficiencies because of the lack of specific regulation and accountability measures for WCAs in Uzbekistan. Such regulations are crucial to warrant the effective execution of contractual relationships between WCAs and local irrigation and drainage system authorities, and between WCAs and member farmers. 5.4 Water consumer associations can deliver efficient irrigation services when they have access to continuous and sufficient financial resources. WCAs under FVWRMPâ€I and RESPâ€II suffered from persistently low service fees and insufficient collection rates. One reason for this was their inability to provide the services in delivering irrigation water and maintaining irrigation canals under their responsibilities, as in FVWRMPâ€I (disincentivizing farmers to pay for services not received). However, WCAs that execute their services often face challenges in collecting service fees owed by all of their member farmers. The lack of sufficient financial resources has led WCAs to accumulate significant debt and develop an inability to pay and retain staff, as evidenced under both projects. 5.5 Coordination and consistent approaches across World Bank projects in the same sector are crucial to ensure broad and harmonized institutional capacity building. Both FVWRMPâ€I and RESPâ€II aimed at improving the capacity of WCAs and farmers, but they differed in their design and approach partially because of the availability of parallel donor grant financing and engagement under RESP II. Although training issues were similar in both projects, RESPâ€II also provided WCAs with smallâ€scale equipment to enable them to execute their operational and maintenance needs. Field demonstrations and farmer field schools under RESPâ€ II were designed better than those under FVWRMPâ€I because they were based on regular needs assessments of farmers and close monitoring, leading to a higher uptake of improved and sustainable practices.
P109195 | Emergency Senior Executive Service Project (ESESP) | Western and Central Africa | Liberia | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | SPF | IPF | 2008 | 2011 | 2013 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/808671474633887267/text/000020051-20140625082246.txt | http://documents.worldbank.org/curated/en/808671474633887267/pdf/000020051-20140625082246.pdf | The main lessons that can be drawn from the experience of this project and the ICR review are:Simple projects with focused short-term objectives are lower risk and can deliver higher impact results in low capacity, fragile settings. The SES operation was simple with two straightforward components and a small budget. In principle, it should serve as a building block for more sophisticated institution building measures.A project aimed at providing quick-surge capacity from expatriates or the private sector should pay early attention to issues of sustainability, knowledge transfer, and the factors needed to deliver longer term improvements in institutional performance. The still unproven sustainability of the SES is part of a more general problem with diaspora projects as emphasized by a 2011 study by the African Development Bank (AfDB, The Use of Diasporas in Government Functions in Post-Conflict and Fragile Situations, available here). This risk entails â€œlittle knowledge transfer....as a result of deploying only a few experts from the Diaspora to their countries of origin.â€ Strong M&E systems are necessary, particularly in pilot initiatives relating to capacity development and institution building. These should be designed properly and the results of the final assessment should always be included in the ICR or their exclusion explained.The reputation of programs should be monitored and claims made should receive adequate follow-up, even if they are made on-line rather than through more traditional channels.A number of other lessons are mentioned in the ICR. These could be pared down and focused on a key point that emerges from the SES program experience -- institution building at the center of government, especially in post-conflict settings, offer a rare opportunity for the Bank to advice on and help implement a vision for the role and structure of the state that is fiscally sustainable and politically durable.
P109224 | Agricultural Technology and Agrribusiness Advisory Services | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2010 | 2018 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/350081565625926192/text/Uganda-UG-ATAAS.txt | http://documents.worldbank.org/curated/en/350081565625926192/pdf/Uganda-UG-ATAAS.pdf | The ICR provided some important lessons; the most relevant ones follow with some modification of language.Indynamic, short-term political environments, large-scale, flagship projects can minimize their exposure to policy risk by reducingthe concentration of key large size activities under one implementing agency. This was a large financial scale projectwith national coverage. However, nearly 50 percent of the total project cost was allocated to Component 3, 75 percent of which wasto be financed by the government to be allocated to NAADS. This design feature left the project highly exposed to a risk of policyand institutional shifts, especially in a political environment in which the role of NAADS came under high public scrutiny duringpreparation and immediately after the projects Board approval. In retrospect, the project could have reduced theconcentration of big-ticket and politically visible activities of technology promotion, beneficiary selection for uptake grants,and matching grants for commercialization under one implementing agency, to reduce the risk of disruptive institutionalchange.In countries where parliamentary approval is required, project effectiveness can be accelerated by bringingparliamentarians on board during the preparation stage. In Uganda, parliamentary approval is a condition foreffectiveness. Under the project the effectiveness date was delayed by 12 months owing to a lengthy parliamentary ratificationprocess. An early communications outreach to key policy makers like the Uganda Parliamentary Agriculture Committee could haveaccelerated the ratification process.The establishment of a single PCU can enhance coordination and administrativeefficiency of complex projects with a multiplicity of implementation actors. At appraisal, NARO and NAADS were jointlyresponsible for Component 2 and RE interfaces and partnership arrangements were planned at the national, zonal, and districtlevels. However, an explicit coordination unit was not created within the MAAIF, to which both Secretariats would have reportedindependently. This oversight resulted in the slow mobilization of Component 2 activities such as joint strategic planning,ME, and SLM until restructuring, when corrective action was taken and a PCU was established within the MAAIF that considerablyimproved implementation of activities. It is good that the Bank seeks to improve government capacity, but effective PCUs can oftenstill play this role in addition to more effective coordination and oversight. Careful assessment of the need for a PCU must happenearly in the design process.
P109333 | Support of ETSIP 1 DPL 2 | Eastern and Southern Africa | Namibia | IBRD | Non-FCS | Human Development | Education | IBRD | DPF | 2009 | 2011 | 2013 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/426731474896990532/text/000020051-20140626103821.txt | http://documents.worldbank.org/curated/en/426731474896990532/pdf/000020051-20140626103821.pdf | IEG concurs with the ICR (pp. 26-27) on the following lessons, which are particularly relevant for other countries with little or no prior experience with the Bank:Less complex design and activities should be planned for a country with little or no prior experience with the Bank. This loan was ambitious, covering all subsectors in education, and put a strain on the Ministry's implementation capacity. It would have been more prudent to begin with a less complex operation, establishing a successful foundation that subsequent efforts could build upon.More time should be allocated to preparation/appraisal when a country has little or no experience with the Bank. This would permit the gathering of stakeholder understanding and agreement and also permit the Bank to establish a greater presence in the country and foster a relationship that can minimize misunderstandings. This also would allow for greater assessment of government implementation capacity prior to project execution. More support must be provided by Bank staff in countries with little or no experience with the Bank.
P109575 | Jamaica Hurricane Dean ERL | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2008 | 2012 | 2013 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/117261475074019384/text/000020051-20140626104310.txt | http://documents.worldbank.org/curated/en/117261475074019384/pdf/000020051-20140626104310.pdf | The following lessons have been taken from the ICR with some adaptation:Effective maintenance of infrastructure and a focus on prevention can reduce a countryâ€™s vulnerability to natural disasters, and can cost less than post-disaster relief and reconstruction efforts. In Jamaica, as in many countries, maintenance does not receive the priority it merits, and post-disaster expenditures are therefore frequently higher than they would otherwise be.Efforts to increase sustainability through community-based efforts and approaches to maintenance of facilities should generally be encouraged, but Jamaicaâ€™s experience shows that they are not a substitute for the important shift in national priorities regarding infrastructure maintenance that is also needed.Emergency operations have higher chances of success if they remain focused and avoid over-ambitious development objectives and targets. If project design is burdened with such targets, successful implementation would likely be undermined. In this case, objectives were kept narrow and simple.In emergency operations, donor coordination is particularly important in delivering a rapid response to the Borrowerâ€™s needs. In this case, inadequate coordination led to a year-long hiatus in negotiating the Tropical Storm Gustav legal agreement, resulted in a period of constrained implementation. A clear prior understanding of the requirements of each external partner, and consequent consideration of alternative financing sources, would reduce such delays.
P109575 | Jamaica Hurricane Dean ERL | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2008 | 2012 | 2021 | PPAR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/697821608139799755/text/Jamaica-Hurricane-Dean-Emergency-Recovery-Loan.txt | http://documents.worldbank.org/curated/en/697821608139799755/pdf/Jamaica-Hurricane-Dean-Emergency-Recovery-Loan.pdf | 7. Lessons 7.1 Using existing agencies with a proven track record can be an effective approach for implementing emergency response projects. Given the urgency for expedient and effective implementation inherent in emergency recovery loans, to the extent possible, emergency recovery projects can capitalize on the comparative advantage of using counterpart institutions with proven implementation capacities and ability to work well with other institutions. For the HDERL, JSIF was particularly well suited to undertake implementation of the project, having had extensive experience with similar community infrastructure operations and firsthand knowledge of World Bank requirements for procurement, financial management, and M&E functions. 7.2 When designing rehabilitation works, close consultation with users can ensure the provision of better services. The inclusion of key stakeholders in the planning process and the incorporation of their suggestions, needs, and general inputs has proved useful in many subprojects. In the case of the HDERL, the facilities that improved the most were those for which suggestions from users were incorporated. 7.3 Expectations need to be managed as there are limits to how much progress can be made on disaster risk reduction or emergency preparedness under an emergency operation. In many contexts, the occurrence of a natural disaster provides a window of opportunity and political support to undertake efforts to improve disaster risk reduction. In the case of the HDERL, the project objective included support for improving government response capacity, but this came late in the design process, and the activities for supporting government response capacity and risk reduction were relatively minor and not at a scale necessary to achieve significant impact.
P109588 | Environmental and Social Capacity Building for the Energy Sector | Western and Central Africa | Cameroon | Blend | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2008 | 2013 | 2015 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/820641475118523746/text/000012394-20150109154710.txt | http://documents.worldbank.org/curated/en/820641475118523746/pdf/000012394-20150109154710.pdf | (i) The trade offs between better portfolio performance and a premature closing of a Bank project needs to be considered carefully. Slow starts for TA projects are not uncommon. In the case of this project, the mid-term review could have provided an appropriate forum to strengthen the implementation arrangements that, in turn, could have ensured greater development effectiveness of the project. The 15-month delay between the decision to cancel and actual closing also attest to the bureaucratic obstacles in prematurely closing the project.(ii) To overcome the complexity of multiagency projects, strong leadership and simple project design can play critical roles. A balance needs to be established to strengthen, on the one hand, multi-agency coordination inherent for the management of social and environmental safeguard issues and promote country ownership, while ensuring, on the other hand, a limited complex institutional arrangement to allow adequate support andmonitoring by the PIU and the WB task team.
P109607 | ACGF - Madagascar Financial Services Project | Eastern and Southern Africa | Madagascar | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2008 | 2017 | 2019 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/833761544713493505/text/Madagascar-MG-ACGF-Financial-Services-FY08.txt | http://documents.worldbank.org/curated/en/833761544713493505/pdf/Madagascar-MG-ACGF-Financial-Services-FY08.pdf | The ICR identified a number of lessons, two ofwhich arerephrased below (i and ii), and athirdlesson (iii) wasformulated by IEG: (i) In country circumstances offragility and crisis, flexibility and selectivity in managing the Banks portfolio and focusingonsupporttothe private sectorcan facilitate the Banks reengagement.Unlike other projects in the Banksportfoliofor Madagascar, the team kept this project open, proactively restructuredit several times in responsetocircumstances on the ground, and shifted theproject focus to private sector activities. This flexible projectmanagementduring the period of political instability allowed for the World Banks immediate reengagement after the OP/BP7.30 was lifted. This approach proved to be the right decision in the context of this project.(ii)Thisset-up of a successful Partial Portfolio Credit Guaranteeoffers elements ofa best practice and could bereplicated in other Banks operations.Key factors that contributed to the PPCG success included the following:(i)the Governments initial contribution and the targeted TA to support financial institutions in making proper lendingdecisionslimited adverse selection; (ii) a local fund managed by a local fund manager; (iii) an automatic guarantee thatprecludes the PPCG from redoing the credit analysis performed by the PFI; (iv) a silent guarantee that does not provide anyincentives for borrowers to default;and (v) the mobilization ofthe private capital of banks and MFIs, not that ofgovernment. Furthermore, the PPCG complied with all the WB 16 Principles for Public Credit Guarantee Schemes forSMEs.(iii) A committed World Bank team working closely withthe Borrowersinstitutionscarefully selected for their effectivenesscan bekey factors leading tostrong projectperformance, evenin fragile environments. This is another aspect of the first lesson. With the crisis thathitMadagascar during the period of project implementation,odds were high for this project to unravel or to beclosed. It tooka committed World Bank teammaking the right decision tokeep the project alive andtoundertake the needed restructurings. It took the presence of a strong PIU and a competent coordinator, under the oversightofa Banking Commission lodged in the Central Bank,to maintain the momentum of reforms despite the uncertainties in thepolitical sphere.
P109648 | Cambodia Trade Development Support Program (RETF093573) | East Asia and Pacific | Cambodia | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2009 | 2017 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/963411507667888722/text/ICRR-Disclosable-P109648-10-10-2017-1507667876933.txt | http://documents.worldbank.org/curated/en/963411507667888722/pdf/ICRR-Disclosable-P109648-10-10-2017-1507667876933.pdf | The following lessons are drawn from three cited in the ICR (pages 27-28), with some adaptation.Sector-Wide Approaches (SWAps) are an integrative way to bring governments, donors, and stakeholders together to helpdevelop a sector. But, the lesson of this operation is that the operating principles of SWAps must be highly developed androbust enough to be effective at helping broaden dialogue, formulate policies, generate expenditure programs, and coordinatefunding. It is also essential for a SWAp to establish adequate monitoring arrangements. Cambodias Trade SWAp was anascent program and did not have a clear results framework in 2008, which made it difficult for the TDSP to determine the first setof high-impact activities thatwould support the first and third pillars of the Trade SWAp.Theprogrammatic approach must strike a difficult balance between giving government implementing agencies the responsibility and thediscretion to select projects for funding versus determining early on the projects that are best able to advance the projectobjectives. It cannot be said that each of the 29 activities supported by the TDSP contributed equally to the objectivesof the project. Considering this fundamental tension in the programmatic approach, the lesson isthat clear principles mustset for the identification and development of projects and strong mechanisms must be designed for their appraisal and selection.Combining activities that offer immediate payoffs and those that yield long-run benefits are an optimal way toimprove the trade sector and the business environment in a country. The automation of trade business processes and thefacilitation of trade activities had rapid payoffs under the TDSP. But, it was equally important for the TDSP to focus on thelonger-term efforts to build institutional capacity in trade policy formulation and implementation, including through Governmentstaff training, business and economic research, and public-private sector policy dialogue.Because the project implementingagencieswere unlikely to be ready at project effectiveness, itwas essential for the project to pursuecapacitybuilding and staff training activities, with a focus on knowledge transfer and staff retention. The lesson is that both near-termrapid-payoff activities and long-term institution-building activities are necessary for project success.
P109683 | Kenya Agricultural Productivity and Agribusiness Project | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2016 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/421741483122428763/text/1483122427221-0000A8056-ICRR-Disclosable-P109683-12-30-2016-1483122417764.txt | http://documents.worldbank.org/curated/en/421741483122428763/pdf/1483122427221-0000A8056-ICRR-Disclosable-P109683-12-30-2016-1483122417764.pdf | The ICR included five lessons. The following are emphasized as lessons with general applicability-with some adaptation oflanguage: ME systems should be developed early in the process for effective guidance toproject managers. The projects ME at the national level was designed late during projectimplementation and largely focused on project processes and less on outcomes. First, ME systems should be designed duringproject preparation and adequately funded. Second, there should be an attempt at leveraging technology in data collection,transmission, and distribution. Third, periodically during the course of project implementation, there should be workshops andforums that discuss ME performance with a view to taking corrective action and sharing good practices among projectparticipants. Fourth, MTR exercises should critically review ME inadequacies early in project implementation and proposeactions to remedy these shortcomings. It is critical to haveefficient financial monitoringmechanisms for community-based projects to ensure financial management. The projectexperienceddifficulties accounting for money spent on project activities, partly because of inadequate documentation to backup expenses, especially those at the community level. The project design should have internal audit mechanisms that constantlyfollow up, instead of only relying on annual audits. Project implementation support teams should be proactive in preventing theiroccurrence and addressing them early on. To retain high-caliber service providers,schedulingtheir payments shouldbe calibrated to correspond with theirassigned workloads. Asdesigned under the project, payments to private service providers were scheduled in rather arbitrary tranches of 10%, 20%, 30%, and40%. Yet, work that is much more significant takes place early on, including farmer mobilization and training. This caused an unduefinancial burden on service providers and caused difficulties in retaining high-caliber service providers. Thefollowing lesson is emphasized by IEG: Ensuring good quality at entry is a critical element to achieve asuccessful outcome. The projects experience demonstrated that shortcomings at Quality at Entry couldsignificantlyundermine the projects implementation and derail its progress. In particular, it is important to identifyrisks and include relevant risk mitigation measures.
P109683 | Kenya Agricultural Productivity and Agribusiness Project | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2016 | 2019 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/656601553621618378/text/Kenya-Agricultural-Productivity-Program-KAPP-I-and-II.txt | http://documents.worldbank.org/curated/en/656601553621618378/pdf/Kenya-Agricultural-Productivity-Program-KAPP-I-and-II.pdf | Lessons The following lessons are drawn from the experience of the KAPP program. Sustained government ownership and commitment are key to achieve complex and sectorwide institutional reforms. KAPP sought to improve sector performance by undertaking complex policy and institutional reforms in research and extension along with changes in the underlying legal and regulatory frameworks. KAPP was a pioneer in the effort to revitalize the largely ineffective and public-sector-dominated research and extension systems through reforms to introduce demand-driven and pluralistic approaches. Despite the challenges of sectorwide coordination and fundamental changes in sector governance, sustained government ownership and commitment to improving the efficiency of the agricultural sector can result in substantive reforms in the national agricultural research and extension systems. Effectiveness of institutional reforms and project outcomes requires sustained effort through continuous realignment with the changing context. KAPP supported significant policy and institutional reforms, but it faced challenges in sustaining the implementation of these reforms through the devolution of power and resources to county administrations. The devolution provided significant powers and responsibilities for the agricultural sector to the counties and enhanced local ownership, but the lack of local capacity, unclear priorities for agriculture, and weak coordination and alignment with the new setting affected implementation and effectiveness of the extension reforms, including the sustainability of the cooperatives and farmer common interest groups. The long-term effectiveness of institutional reforms depends on sustained effort, capacity building, and continuous realignment to new conditions. Participatory and client-driven approaches with strong priority setting and regular evaluation are critical to stimulate and transform the agricultural research system. A conclusion from this project is that considerable effort is needed to make agricultural research more responsive, demand-driven, inclusive, and effective in developing technologies and stimulating uptake by its clients. KAPP resources were used to support a wide range of core and new research initiatives but it led to fragmentation of effort and the proliferation of small-scale activities. Agricultural research can benefit from a mechanism that clearly articulates priorities from the demand side, as a basis for research planning, and from effective instruments that connect research with extension. Provision of agricultural extension services to poor small-scale farmers as a public good requires a sustainable financing mechanism. The public good characteristics of agricultural research and extension in Kenya continue to offer the rationale for public sector participation in both. KAPP's approach was to introduce pluralism into the extension system by supporting public funding of a private sector fee-for-service delivery model. The public sector played a leading role when the private sector lacked an incentive to provide extension services to poor farmers unable to pay for such services. Although this model worked well when project financing was available it was not sustained after the project closed. Public funding complemented by cost-sharing with farmers tied to marketing of surplus produceâ€”through cooperatives or farmer groupsâ€”may contribute to bolstering funding arrangements for agricultural extension to poor small-scale farmers. Public sector funding for extension services can be decoupled from public provision to strengthen complementarities and create space for private sector participation and improved service delivery. KAPP piloted the contracting of private providers using farmer grants and demonstrated that the public sector can engage and deliver extension services using private providers. This is more justified in areas where the private sector lacks the motivation to deliver such paid services without public support. Public funding can be decoupled from public provision to provide contracted services to smallscale farmers, which creates space for a more efficient delivery of services using the private sector and contributes to strengthening complementarities between the public and private extension systems. Scaling up the contracted service delivery model using the privatized extension system requires development of new public regulatory and quality control systems. The KAPP experience shows that contracted extension service delivery by private feefor-service extension is viable for market-oriented, high-value products (such as dairy) where farmers' net benefits are higher than the cost of accessing such services. However, it was not possible to scale up this model without the development of new public regulatory systems that ensure high-quality technical content of private fee-for-service extension. 1During the same period, about 64 percent of the total population was in rural areas. The survey further revealed extreme poverty, with 3.9 million peopleâ€”of which 3.2 million were in rural areasâ€” who struggled to live in conditions of abject poverty and were unable to afford the minimum required food consumption basket. Overall poverty refers to households and individuals whose monthly adult equivalent total consumption expenditure per person is less than K Sh 3,252 in rural and periurban areas, and less than K Sh 5,995 in core urban areas. Extreme poverty refers to households and individuals whose monthly adult equivalent total food and nonfood consumption expenditure per person is less than K Sh 1,954 in rural and periurban areas, and less than K Sh 2,551 in core urban areas (KNBS 2018). 2The core agriculture sector encompasses crops, livestock, and fisheries-related economic activities. More broadly the sector also includes institutions involved in land and water management, cooperatives, environment, forestry, and regional development, including development of arid and semiarid lands. 3 There is a wide literature on agricultural extension and reforms, including contracted extension services (see Umali 1997; Davis and Place 2003; Feder, Birner, and Anderson 2011; and Kidane and Haggblade 2016). The evaluation benefited from review of the existing literature. 4 The Ministry of Agriculture, Livestock and Fisheries was formed through Executive Order No. 2/2013 of May 20, 2013. It comprises three state departments, namely Agriculture; Livestock, and Fisheries which had been separate line ministries since 2008. In 2015, the Department of Irrigation Technology and Infrastructure under the State Department of Agriculture was transferred to the newly established Ministry of Water and Irrigation, but later returned as a separate State Department for Irrigation under the Ministry of Agriculture, Livestock, Fisheries and Irrigation. In 2013, by act of parliament, KARI merged with the Coffee Research Foundation, the Tea Research Foundation, and the Kenya Sugar Research Foundation to form the Kenya Agricultural and Livestock Research Organization. Overseeing 16 research institutes, KALRO is the premier national institution bringing together research programs in food crops, horticultural and industrial crops, livestock and range management, land and water management, and socioeconomics. 5 World Bank management agreed to a reallocation of the IDA credit and IDA grant funds on June 6, 2008. The project was provided a 12-month extension based on the midterm review to make up for the delays in implementation progress, inadequate flow of funds, and inadequate counterpart government funds in the first year. 6The agriculture line ministries had overall responsibility for project oversight through the ICC. While KARI retained the ultimate fiduciary responsibility for KAPP I, some fiduciary responsibility was passed on to the KAPP Secretariat at the central level, and to the DSUs at the district/local level as they develop some capacity. 7The membership of the KAPP Steering Committee in phase I was composed of the directors of KARI, National Environmental Management Authority, Veterinary Services, Livestock and Agriculture, Fisheries, representatives of Kenya National Federation of Agricultural Producers, and representatives of the Ministries of Cooperative Development, Ministry of Natural Resources and Wildlife Management, Ministry of Finance, civil society, NGOs and community-based organizations. 8The ASPSC comprised 13 nominees of the ministries represented in the ICC, representatives from Ministries of Finance, Trade, Energy, Industrialization and Roads, the director of KARI, and senior officials representing the private sector, universities, and NGOs. 9The ASPSC was responsible for approving (i) work program proposals for applied research, extension and empowerment, agribusiness and investment projects, including the oversight of microprojects planned and implemented at the regional level; (ii) the annual work plans and budgets of investment projects (such as KAPAP), before recommending their endorsement by the ICC; (iii) monitoring of the implementation progress of investment projects; and (iv) reviewing and making recommendations on proposed policy changes to the ICC. 10The KAPP Secretariat was staffed by professionals, selected through an open and competitive process and seconded from the line ministries for the duration of the project. Staff performance was evaluated at midterm. Confirmation of appointment of all technical staff was subject to review and approval by the World Bank. 11This later expanded to four entities when the Ministry of Fisheries Development and Ministry of Livestock Development became separate entities in 2008. Presidential Circular No. 1 (2008) elevated the department to a Ministry of Fisheries Development and placed the Kenya Marine and Fisheries Research Institute in the new ministry. 12Although KARI retained the ultimate responsibility for project financial management and procurement for the duration of KAPP I, it gradually built financial and procurement capacity within the KAPP Secretariat and other implementing institutions and gradually devolved responsibility to them by the end of phase I. Initially, disbursements were made on the basis of statements of expenditures, direct payment, and special commitments, while the transition to report-based disbursements and financial management reporting was progressively introduced and became effective by the end of phase I. The KAPP Secretariat was also responsible for managing the consultative processes, and coordinating the information, monitoring, evaluation, and analytical input into those processes, information communication and public relations associated with KAPP and KAPAP. Except for specific activities that will be undertaken by other implementing agencies (for example, policy studies), the secretariat was responsible for facilitating and coordinating the implementation of the project with the other implementing agencies. 13Each DSU was staffed with at least two professionals, a district coordinator, a monitoring and evaluation specialist, and a supporting accountant, secretary, and driver. 14 These were the Ministries of Agriculture, Livestock Development, Fisheries Development, Cooperative Development and Marketing, KARI, and KENFAP. Although the KAPP Secretariat formally held responsibility for implementation of the NARS component, KARI/KALRO retained responsibility for the KARI/KALRO subcomponent. The fiduciary responsibility for KAPAP was vested initially with the Ministry of Agriculture, which later in 2013 became the Ministry of Agriculture, Livestock and Fisheries. 15Triggers for moving from the first into the second phase include (i) a national extension policy and related institutional and implementation framework approved by the government; (ii) two cycles of project monitoring and evaluation completed, with at least 85 percent of the district intervention impacts evaluated; and (iii) at least 60 percent of the Kenya Agricultural Research Institute component implemented and evaluated as satisfactory. 16The PAD further elaborates the means to include the following\. (a) reforms in extension to increase pluralism, responsiveness to clients and participation by private providers; (b) an evolutionary change in the existing system of agricultural research to improve accountability and impact; and (c) increased empowerment of producer organizations to influence the planning, design, implementation, funding and monitoring and evaluation of research, extension, training and capacity building activities. The project was extended for 12 months following the midterm review to make up for the delays in implementation progress and inadequate flow of funds and inadequate counterpart funds in the first year. 17Among these were (i) incorporation of the National Agricultural Research Project, Phase II's competitive grants under a new KAPP I research grant facility; (ii) the requirement that Agricultural Technology and Information Response Initiative collaborate in local farmers' forums to ensure the responsiveness of research proposals to farmers' demands; (iii) the requirement that all new research proposals include a dissemination strategy; and (iv) following the experience of the Arid Lands Resource Management Project in Kenya, steps to mainstream the activities of KAPP I's newly created DSUs by linking them to existing district bodies. 18 The KAPP I KPIs included\. (i) NARS action plan adopted in year two and implementation initiated by year three; (ii) collaborative activities occupy 50 percent of project financing to non-KARI research institutes; (iii) inventory of KARI technologies and institutional capabilities carried out and database developed by end of year one, and updated annually thereafter; (iv) progressive devolution of KARI resource allocation and accountability for adaptive research programs to centers and center research advisory committees; (v) six extension approaches tested and proven cost effective; (vi) 20 client forums created and functioning at district and divisional levels; and (vii) 40 producer organizations investing in technology multiplication. 19This follows from the Sector Social and Environmental Assessment which was conducted during the design stage to lay out the steps for mainstreaming environmental and social issues into the three phases of the KAPP. 20High financial management risks were identified owing to a weak control and low capacity environment of the existing government system, to potential delay in allocation of counterpart funds, government delay in submission of audited accounts, and lack of KAPP Secretariat experience handling World Bankâ€“financed projects. To address these concerns, a number of project-specific risk mitigation arrangements were proposed in the project design. These include the creation of an Inter-Ministerial Steering Committee to be responsible for overall project implementation supervision, monitoring and reporting, institutional arrangements to place all fiduciary responsibility with KARI, and the subcontracting of an independent annual audit to a private firm of auditors who will report to the Controller and Auditor General ( CAG). 21These included a plan for a stand-alone accounting system, including hiring of a consulting firm to do capacity building for KARI and the project secretariat; streamlining of disbursements to district units and research centers; and strengthening of oversight and internal audit functions by the project steering committee. The lessons learned have been incorporated in the second phase of the APL. 22 The IEG mission and field visits to selected counties indicate that the initial activity under KAPP I was the piloting of selected approaches for delivering pluralistic extension services which were piloted in four locations in each district. After the piloting of the extension models, four value chains were selected in each county initially through a participatory approach that enabled farmers in each location to select their priority enterprises (commodity value chains). KAPP I then supported the establishment of three CIGs for each of the selected value chains to facilitate access to demand-driven extension services, new technologies, and agribusiness services using contracted service providers and empowerment of producer organizations. This was undertaken in tandem with the macro level policy and institutional reforms in research and extension systems. 23 Under industrial and horticulture crops alone the research covered\. vegetables (tomatoes, French beans, African leafy vegetables, herbs and spices, medicinal plants); aromatic plants (aloe, vanilla, moringa); fruits (bananas, passion fruits, avocado, papaya, mangoes, citrus); flowers (lilies, gladiolus, tulip, moby dick, anthurium); nuts (macadamia, cashew, groundnuts); industrial crops (pyrethrum, cotton); and oil crops (sunflower, soya beans, safflower, castor, jatropha, oil palms). The program developed partnerships with other stakeholders such as international universities, private institutions, international agricultural research centers, NGOs and community-based organizations through memoranda of understanding (MoUs) and letters of agreement (World Bank 2010a, 26). 24The ICR indicated that only two KARI centers (Molo and Perkerra) and a subcenter (Matuga) were included in the ATIRI activities (World Bank 2009a, para 18). 25 Under KAPP, it was expected that ATIRI would be modified to be the main means for planning, implementing, monitoring and evaluation of farmer demand-driven activities. ATIRI was also expected to contribute to capacity building and empowerment of farmer groups. The anticipated ATIRI operational modalities were, however, not effected during phase I. Under phase II, ATIRI was devolved into an outreach and partnership program (World Bank 2009a). 26 The ICR-KAPP I (World Bank 2009a, 22) reported that farmers in the North Eastern province who are largely pastoralists favored a multidisciplinary pastoralist approach. In the Coast province, the farming systems approach for technology and development and transfer which allows farmer-to-farmer learning was more popular. 27The three indicators were (i) increased uptake of technologies and practices; (ii) integrated research and extension policy and institutional framework in place by 2007; and (iii) pilot activities in 20 districts testing pluralistic extension approaches and supporting client empowerment. The second and third indicators are formulated more as outputs and do not directly capture the outcomes in terms of effects or behavior changes that follow from policy and institutional reforms. Since KAPP was implemented in two phases, the long-term impacts of KAPP I also form part of the impacts of KAPAP. For farmers who benefited from the two phases, the impacts are difficult to isolate, and the project's M&E framework was not designed to capture the contribution of the first phase to the total impacts of KAPP. 28KAPP I intended to support KARI in reducing this dependence and set up the Agricultural Research Investment Services as a subsidiary private company for internal income generation. Although the draft legal instruments and business plan for ARIS were developed, they were not finalized and approved. However, KARI initiated some ARIS pilot activities in some KARI centers (such as commercializing KARI's surplus farm resources, laboratory and analytical services) but ARIS could not be established without the legal mechanism. 29The sample size was drastically reduced to 800 households but maintained the original distribution into target and control groups. The well-designed baseline survey implemented by the Tegemeo Institute covered 15 out of the 20 pilot districts stratified into 8 agro-regional zones and was carried out from July to September 2006. The baseline collected data from 2,027 households, 60 percent (1,202) in target areas and 40 percent (825) in control areas within the same districts. Given the wide geographical area and sectorwide interventions of KAPP I, this is likely to reduce the level of precision in estimating the adoption effects of the project despite the substantive baseline data collected which remained largely underutilized. 30Difference-in-difference is a useful technique to use when randomization on the individual level is not possible. The method requires data from preand post-intervention, such as cohort or panel data (individual-level data over time) or repeated cross-sectional data (individual or group level). The approach removes biases in post-intervention period comparisons between the treatment and control group that could be the result from permanent differences between those groups, as well as biases from comparisons over time in the treatment group that could be the result of trends owing to other causes of the outcome (Wooldridge 2013). 31This indicates that even if adoption in the target areas increased only by 3.3 percent, the net increase considering the decline in adoption by the same percentage in the control areas, the overall effect of the project is higher than the change in the target areas (also showing the value of a control comparison group). 32For better accountability, it would be useful for project design to consider as part of its PDO and outcome indicators the real changes that could be directly attributed to the intervention. 33The EDPs were introduced in two cycles in the 20 districts and 80 divisions targeted by KAPP I. The EDPs included fish farming, vegetables, intensive dairy, and snow peas. The EDPs introduced new activities that were considered to be economically and financially viable. 34This was also to allow for sufficient time to develop and release the research product, and the time taken by the farmers to progressively adopt the new technology. The analysis used farm models, which were fed with average price, input, output, and adoption rate data from the rural household baseline survey (2006) and the technology adoption survey (2008). Yields for previous years (2005â€“07) were calculated by interpolation techniques or linear regressions. 35 Quantifiable benefits included (i) increased yields owing to the uptake by farmers of KARI's new technologies; (ii) improved adoption of chemical fertilizer on maize; (iii) improved agricultural practices; (iv) enhancement of agricultural research and development of extension services; and (v) other factors, such as the participation of farmers in formal markets. Nonquantified benefits included (i) increased nonmonetary benefits at the household level; (ii) benefits in terms of rural income and purchasing power; (iii) social benefits in terms of food security and nutrition at the household scale; (iv) environmental protection from soil, water, and environment conservation technologies; and (v) economic externalities (World Bank 2010a, annex 3). 36ICR reported 4.6 percent adoption of improved seeds for maize and potato, 3.1 percent improved seeds for mango, 9.4 percent improved dairy cattle breed, compared to the PAD estimated target adoption rate after 20 years of 15 percent, 30 percent, 30 percent, and 10 percent, respectively (World Bank 2010a). 37Although careful domestication and continual adjustments are needed to make NASEP better aligned with the devolved structure, several of the institutional changes (such as contracted service delivery and rural cooperatives) and the development outcomes initiated through the project face high risks of not being maintained or sustained (see the section on KAPAP for details). 38As the ICR notes, KARI only had limited experience at the time in managing a multisectoral research and development project with community involvement which required setting up of local-level implementation structures (World Bank 2009a, 5). 39Both major and minor crops as well as new and nontraditional crops were allocated scarce resources, thereby thinly spreading the effort and making it hard to address the critical challenges that limit productivity growth and improve food security in line with the SRA. 40Recognizing the gap in the quality of the M&E system, the project team modified the results framework in August 2006 to clarify targets and improve measurability although these indicators remained focused on outputs. The amendment was not formally approved by the World Bank and thus was not used for project assessment (World Bank 2009a). 41The 2006 baseline covered 15 of the 20 pilot project districts and sampled a total of 2,027 households. In the 2009 technology adoption survey, number of both districts and households was substantially scaled down to 800 households in 9 districts. 42 Based on satisfactory progress made under two triggers and moderately satisfactory progress under one trigger, the Kenya Agricultural Productivity and Agribusiness Project (KAPAP â€”phase II of the APL) was approved by the Executive Directors on June 11, 2009. 43 Triggers for moving from the second to third phase included (i) the government approved Agricultural Sector Development Strategy 2010â€“2020 by year 1, prepared an ASDS implementation framework and investment plan in year 2, and its implementation started by the midterm review in year 3 of KAPAP; (ii) the government rolled out the implementation of the National Agricultural Sector Extension Policy and set out the institutional framework for regulation and financing of commercial extension/advisory services by the midterm review in year 3; and (iii) the institutional mechanisms for the implementation of the National Agricultural Research System policy were in place by year 2 and the restructuring of the Kenya Agricultural and Livestock Research Organization was completed by the midterm review in year 3 of KAPAP. 44The Vision 2030 aimed to boost growth in this sector through enhancing agricultural productivity, extending land use for agricultural production especially in Arid and Semi-Arid Lands (ASALs), strengthening market supply chains, and increasing value addition of agricultural produce (Government of Kenya 2007). 45Furthermore, the PDO is in line with the Comprehensive Africa Agricultural Development Program developed by the New Partnership for Africa's Development of the African Union. 46As laid out in the PAD, KAPAP intended to support\. (i) improvement of research and extension systems and their linkages to sector priorities through the implementation of ASDS, NASEP, and NARS policies, including improved planning, coordination, funding, and implementation of public agricultural programs aimed at sector transformation, growth, and reduced risk; (ii) empowerment of farmer organizations and other stakeholders to influence planning, design, funding, implementation, and monitoring and evaluation of agricultural research, extension services, training, and capacity building activities; (iii) development of agribusiness along commodity chains aimed at improved value addition and marketing; and (iv) integration and mainstreaming of gender and other crosscutting issues (HIV/AIDS, youth, and environment) throughout the project area and along the value chains. 47There were strong links with the Global Environment Facilityâ€“supported Kenya Agricultural Productivity and Sustainable Land Management Project (KAPSLMP-P088660). 48KAPAP KPIs are set as percentage increase in\. (i) average yields of selected agricultural products in smallholder farming systems in the project area; (ii) earnings of men and women from smallholder agricultural activities in the project area; (iii) public investments in the agricultural sector; and (iv) participating men and women smallholder farmers who are satisfied with extension, empowerment, and agribusiness services. 49This was needed to clearly capture the target values and the achievements and to include the core indicator and its targets, as well as to standardize the unit of measurement for the relevant indicators to avoid double counting of the beneficiaries. 50Each RSU had a mandate to undertake the delegated functions of the KAPP Secretariat\. (i) to coordinate, in consultation with the District Development Committees (DDCs), all consultative, planning, and implementation processes at the district and division levels, including micro-projects implemented at the local level; and (ii) to assume monitoring and evaluation, financial management, procurement, and public relations functions. 51The RSUs and the Regional Agricultural Sector Steering Committees (RASSSCs) were renamed, respectively, to County Service Units and County Agricultural Sector Steering Committees, in line with the county government structure. 52The midterm review mission observed the persisting concern in delays of disbursement with the remaining 41.7 percent of the total credit amount yet to be disbursed for 18 months to the original closing date of December 31, 2014. 53In the past year, the number of beneficiaries has increased by 67 percent to over 220,000, significant increases in yields and incomes were recorded among the project beneficiaries, the number of CIGs has almost doubled to more than 4,800, and a total of 85 cooperatives and five companies with a membership of close to 120,000 were registered. The collaborative research supported under the project also made good progress with promising results, which the various industry players have started to adopt, and the KARI research program continued to register good progress, with a total of 185 technologies/varieties/innovations released for use. 54Some of the remaining activities included collaborative research activities, expansion of community interventions to include more areas in each county, capacity building for the newly formed cooperatives and other marketing groups, consolidation of farmer empowerment and organization, engagement with the targeted 20 county governments in the operational areas, and ensuring that supported community groups implement and account for the various grants. 55Environmental issues identified in KAPAP include (i) loss of natural habitat, (ii) use of inappropriate farming practices, (iii) agriculture/wildlife conflicts, (iv) agro-processing pollution, (v) misuse of pesticides, and (vi) proneness to climatic fluctuations (especially drought). Social issues identified include (i) inability of resource-poor farmers to access extension services and inputs, (ii) inappropriate technology and thus poor adoption, (iii) inadequate access and control of production functions for women, (iv) impact of HIV/AIDS on production systems and livelihoods, and (v) KAPAP activities were envisaged to have longerterm impacts on indigenous peoples indirectly affected by project activities (for example, through change in diet and livestock-related activities). 56These frameworks were developed to fully comply with environmental legislations and procedures in Kenya and with the World Bank's environmental and social safeguard policies. Subprojects and community micro-projects were screened according to KAPAP-specific ESMF, IPMF, and IPPF to assess the potential negative impacts that would require attention prior to their implementation in order to adequately address the World Bank's safeguard standards. 57The KAPAP-IPPF built upon the IPPF developed under the World Bankâ€“supported Kenya Agricultural Productivity and Sustainable Land Management Project. It was based on free, prior, and informed consultations with indigenous peoples undertaken in five phases for the KAPSLMP and made customized proposals for further free and informed consultants with the indigenous peoples in the KAPAP project (Government of Kenya 2009c). Measures were put in place to (i) avoid potentially adverse effects on the indigenous peoples' communities; or (ii) when avoidance is not feasible, minimize, mitigate, or compensate for such effects; and (iii) ensure that the indigenous peoples receive social and economic benefits that are culturally appropriate and genderas well as intergenerationally inclusive. 58In Nakuru, the indigenous people were engaged in honey production; in West Pokot, they were al
P109691 | Micro, Small and Medium Enterprise Development | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2008 | 2015 | 2016 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/576451468186847775/text/ICRR14904-ICRR-PUBLIC-P109691-Box396265B.txt | http://documents.worldbank.org/curated/en/576451468186847775/pdf/ICRR14904-ICRR-PUBLIC-P109691-Box396265B.pdf | The ICR drew seven lessons, the most important of which (with editing) is: Success in implementation of matching grants programs, especially for Micro, Small and Medium Enterprises, calls for significant hand-holding at the application stage. Grant applicants need assistance to identify relevant and practicable training appropriate to their business needs. After grants are awarded, close monitoring of the implementation of such programs, including on-site visits to beneficiary firms, is essential to enable early detection of problems and their mitigation.
P109710 | Livelihood Recovery for DI Yogyakarta and Central Java | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2009 | 2012 | 2013 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/175901474486169148/text/000020051-20140625191000.txt | http://documents.worldbank.org/curated/en/175901474486169148/pdf/000020051-20140625191000.pdf | Key lessons from the ICR and IEG's review are:Given the complex features and characteristics of financial intermediary projects, they should not be considered under emergency conditions. Combining both the short term (recovery and reconstruction goals) and long term and sustainable financial sector operations in a single operation is challenging. Designing an exit strategy at the inception allows all the stakeholders to provide their input early on and then continuously through implementation. Equally important is the need to continuous engagement and feedback during implementation.
P109722 | Emergency Public Service Delivery | Western and Central Africa | Guinea-Bissau | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2008 | 2009 | 2010 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/569911475093920815/text/000020051-20140620081015.txt | http://documents.worldbank.org/curated/en/569911475093920815/pdf/000020051-20140620081015.pdf | The preparation and implementation of this operation suggests the following lessons:Â· Project preparation should include a thorough investigation of the data base to identify possible overestimations of the wage bill and payments to â€œghostâ€ civil servants, especially in countries where official data is notably unreliable and where there are governance issues.Â· All relevant stakeholders should be consulted and involved as much as possible in preparation, negotiation and implementation.Â· Key performance indicators should be carefully selected with respect to the realism of their attainment, their relevance to the PDO, their usefulness as a measure ot progress towards PDO achievement, and their flexibility in the face of changing circumstances..Â· For rapidly-disbursing emergency operations, it is preferable to avoid, wherever possible, a change in task team leadership between preparation and implementation (the depth and breadth of consultation are likely to be enhanced if the TTL knows that she/he will need to address personally the consequences of project design).
P109736 | TA for Capacity Development in Hydropower and Mining Sector | East Asia and Pacific | Lao People's Democratic Republic | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2010 | 2021 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/954701631031450397/text/Lao-Peoples-Democratic-Republic-LA-TA-for-Hydropower-and-Mining-sectors.txt | http://documents.worldbank.org/curated/en/954701631031450397/pdf/Lao-Peoples-Democratic-Republic-LA-TA-for-Hydropower-and-Mining-sectors.pdf | The ICR (paras. 104 to 109) lists a number of lessons which are relevant for technical assistance projects undertaken in similarenvironments. Based thereon, IEG derives the following lessons:A long-term program of support that builds step bystep, taking past success and failures and new challenges into account, and is positioned to help bring keyagreedrecommendations into actual implementation, is appropriate for facilitating beneficial transformation of these sectors.The experience under the project showed that, in sector environments which arefragmented, with many decision-makersand stakeholders, capacity-building and institutional oversight improvement take time. The HMTA was able to achieve good results inpart because it was able to extend over 10 years in a period of substantial evolution of the sectors and was seen as being able tocontribute significantly to needed sector reform.Grant support from development partners can significantlyleverage the financing available for technical assistance and thereby expand the scope and coverage of technicalassistancebeyond that can be supported by the state budget.The HMTA served as a catalyst for donor contributions that allowedthe use of a varied international pool of experts. This was helpful in ensuring the transparency and in avoiding conflicts ofinterest.Development of capacity for ensuring compliance with dam safety regulations iscritically important for ensuring resilient and sustainable hydropower development. The LPDRs experience has shownthat ensuring IPPs compliance with dam safety provisions can be a significant challenge given limited technicaland staffcapacity. The LEPTS and the new Dam Safety Guidelines would pose additional demands regarding institutional oversight. Thecapacity-related improvements made under the HMTA would help in this context.If the PDO indicators do notcapture all relevant outcomes of the project, there is a risk that positive and solid project results may not be measured,demonstrated, and reported on. In this project, despite the additional indicators that were added during restructuring,there was a lack of relevant indicators to sufficiently measure and demonstrate project outcomes. This made it difficult for theproject to demonstrate and report on the full aspect of the projects results.
P109737 | Nigeria Scaling Up Sustainable Land Management Practice, Knowledge, and Coordination | Western and Central Africa | Nigeria | Blend | Non-FCS | Sustainable Development | Agriculture and Food | GEF | IPF | 2011 | 2014 | 2015 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/269591475116144585/text/000020051-20150113011420.txt | http://documents.worldbank.org/curated/en/269591475116144585/pdf/000020051-20150113011420.pdf | Lessons are derived from the ICR and from IEG's evaluations of other related agricultural projects. Projects designed to transfer knowledge and skills and to strengthen capacity should be designed with indicators that measure the relevance and quality of the desired learning, its uptake, and its impact. "Small investment projects" implemented over a short time period (3-4 years) require very strategic design and realistic results chains. Projects designed to support capacity building, training and the dissemination of information require intense monitoring and adaptive learning. Bifurcating this aim - by financing an investment program (small grants) alongside capacity building and training -- risks diluting attention to one or both aspects of project implementation. A Trainer-of-Trainers approach to agricultural extension requires an intense investment in monitoring the quality of information being transmitted. There is an abundance of literature available on the opportunities and pitfalls associated with trainers-of-trainers approaches in the agricultural sector, including DEC's research on the quality of information transmission in farmer field schools. The Impact Evaluation of the Training and Visit System (in part conducted by IEG, then OED - see the case of Kenya) also offers relevant lessons in this respect. Gender reporting in projects must extend beyond the "number of women reached" to qualitative monitoring and reporting on the quality of their participation, voice, perceived and actual benefits in World Bank programming.
P109804 | Access to Finance and Capacity Building of Earthquake-Affected MSEs in Yogyakarta and Central Java | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2009 | 2011 | 2013 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/166781475083968976/text/000020051-20140625190913.txt | http://documents.worldbank.org/curated/en/166781475083968976/pdf/000020051-20140625190913.pdf | Following are lessons from the ICR summarized:Ensure government involvement throughout the entire project life-cycle and allocate staffing and funding resources for the same. Leverage existing capacities and resources of the target groups to create ownership and to cost-effective project implementation.Establish a robust information management, monitoring, evaluation and reporting system.Start early on project continuation planning and sustainability to design a viable project exit strategy and continuation plan agreeable to all stakeholders. A well-functioning implementation agency is essential for a successful implementation of a multi-component and complex project.In addition, IEG draws the following lessons: During the design phase, the Bank needs to carefully assess the capacity and willingness of all the key implementing agencies and identify any related risk with respect to each one of them and propose appropriate and workable mitigating strategies.Appropriate restructuring options should be considered when any major components are cancelled.Major changes and restructuring should be reflected in the M&E
P109925 | KH--EDUCATION FOR ALL FAST TRACK INITIATIVE CATALYTIC TRUST FUND | East Asia and Pacific | Cambodia | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2008 | 2013 | 2014 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/113491474564368918/text/000020051-20140626111509.txt | http://documents.worldbank.org/curated/en/113491474564368918/pdf/000020051-20140626111509.pdf | The ICR offers 6 lessons (pp. 22-23). The three most important are highlighted below, with additional observations by IEG:Â· â€œAn appropriate and thorough institutional capacity and readiness assessment during the preparation stage is strongly recommended to improve the implementation readiness conditions for complex initiatives being piloted for the first time.â€ IEG concurs with the ICR assessment that â€œimplementation issues may have been mitigated by a more thorough capacity assessmentâ€ and â€œa capacity assessment of the construction department could have helped set more realistic civil works targetsâ€ (p. 23). Such assessments would be an important first but insufficient step in avoiding the starting delays and other implementation challenges encountered by the project. Efforts to proactively plan ways to mitigate weaknesses revealed by those assessments are also required. Â· â€œA well-conceived â€˜results-chainâ€™ demonstrates connectivity between the stated PDOs and the agreed â€˜observable and measurableâ€™ outcome indicators, and the attribution is limited to the scope of the project.â€ The project lacked such a results chain, and what monitoring system it did have deviated from the PDOs. Management should have taken the opportunity of one of the three project restructurings to harmonize the discord between the PDOs and the Results Framework. The ICR also makes the useful point that â€œcandid and internally consistent ISRs should serve as a critical tool for management to encourage proactivityâ€ (p. 23).Â· â€œTargeting students with high academic potentialâ€”while ensuring that the poorest students are among that setâ€”may be an approach that maximizes both the equity and effectiveness objectives of demand-side incentive programs.â€ Where the first two lessons treat issues of project management and implementation, this lesson is a critical design finding from a well-executed rigorous impact evaluation that should inform the design of future demand-side incentive programs both in Cambodia and elsewhere. The ICR also calls for further research into whether this lesson â€œhold[s] in other settings (e.g. where there is greater heterogeneity in student poverty levels)â€ (p. 23).
P109932 | DO Emergency Recovery & Disaster Mgmt | Latin America and Caribbean | Dominican Republic | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2008 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/539131505394879951/text/ICRR-Disclosable-P109932-09-14-2017-1505394863980.txt | http://documents.worldbank.org/curated/en/539131505394879951/pdf/ICRR-Disclosable-P109932-09-14-2017-1505394863980.pdf | The ICRpresented seven lessons learned from the project. The two that are most noteworthy and have broaderapplicationare, with some adaption,summarizedbelow:Bundling small, geographically dispersedcivil works of moderate technical complexity into packages for international bidding has disadvantages as well as potentialadvantages that need to be carefully weighed. If successful, this approach can reduce the number of procurement processesand enhance the quality of bids to be received. However, such packages of works may not be attractive to international civil workscompanies and eventually may have to be unbundled for national bidding. This process can cause significant implementation delay, asthe bundling and unbundling processes can take a lot time. The project spent about a year to bundle a number of small works relatedto repair of conveyance canals and other infrastructure into three packages but no international companies expressed interest inbidding. This required a reversion to national bidding, causing some further delays (ICR, Section 2.2.4).Aflexible design approach should be balanced with relevant risk mitigation to ensure that important activities for sufficient,notmerely necessary,achievement will not be omitted. Due to its emergency response nature, the project keptits target on institutional capacity building open and allowed it to be set after the projects effectiveness. Thisarrangement facilitated the projects short preparation process and a rapid emergency response. A caveat is that there arerisks that as a result of too much flexibility some important activities may end up not being included in the component designs.Appropriate measures should be adopted to ensure that such risks are addressed. In this project, the target for institutionalcapacity building was eventually set as the establishment and operation of an effective disaster risk early warning system. As theICR states, while such a system was necessary, it was not sufficient to prevent or mitigate the impact of disasters. The DominicanRepublic also needs to strengthen its integrated water resource management at watershed level and its capacity to plan, establishand manage protective civil works to reduce vulnerability and mitigate impact (page 24).
P109961 | Second National Water Supply and Sanitation Project | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2008 | 2019 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/589301592605530421/text/Azerbaijan-NATL-WATER-SUPPLY-SAN-II.txt | http://documents.worldbank.org/curated/en/589301592605530421/pdf/Azerbaijan-NATL-WATER-SUPPLY-SAN-II.pdf | This review has drawn three lessons based on the ICR incorporating material on lessons listed on page 30 of theICR.Insufficient project preparation can critically affect project outcomes and implementation of safeguardpolicies. This is a rather generic lesson, but the experience from this project needs to be shared. The project budget wasestimated without the completion of detailed feasibility studies, and the project area was determined as 21 rayons. When thefeasibility studies were completed after project implementation started, it was found that the project cost was massivelyunderestimated, and the project funds could only finance investments in eight rayons. This was a significant decrease in thegeographic scope of the project limiting the impact of the intervention. Since detailed work plans were not prepared inadvance either, it was not clear whether there would be any involuntary resettlement or not. It was also found only just before thestart of construction works that some private lands would be affected by the project. Payments to persons affected by the projectcould not be processed before the start of the works. This resulted in delays of between 2 and 5 years. The project team becameaware of this issue only in 2016. The projects non-compliant status with this safeguard policy continued through to projectclosing. Additionally, the project implementation capacity of AzerSu was also inadequately assessed during project preparation.Overwhelmed by a US$2 billion project portfolio, AzerSu could not implement the project; hence, the project implementation entityhad to be changed early in project implementation.Weak institutional capacity and lack of performance control cancritically affect the sustainable delivery of water supply and sanitation services. AzerSu predominantly focuses onexpanding water supply and sewerage networks nationwide. There is no performance control mechanism set or benchmarks establishedfor operational, technical and financial sustainability of the utility. The steady stream of cash from the central governmentthanks to high oil revenues has so far helped AzerSu avoid major financial constraints. The project originally aimed at phasing outgovernment support to AzerSu through the strengthening of AzerSus financial situation, but this could not be achieved.Currently, AzerSu and rayon utilities are in a financially precarious situation. This can adversely impact the availability,quality and reliability of these services should there be shortages in funds transferred from the central government budget.Additionally, AzerSus weak institutional capacity is a concern for the technical sustainability of the wastewater treatmentfacilities.Expanding sewerage network without adequately addressing the households connection issue canhinder the achievement of full development impact while creating potential technical issues for the wastewater treatmentfacilities. The project activities did not include the construction of private connections to households, nor did theutility had any program to incentivize these connections. Therefore, the connection rate to sewerage network at project closing was at 40 percent. Households use septic tanks. These tanks drain wastewater to underground, and the remaining fecal sludge is removedonce a year or less frequently. Therefore, the cost of maintaining septic tanks is very low, whereas laying pipes to connect to thesewerage network is costly for low-income households. However, septic tanks are harmful to environment and poses health risks,because the wastewater drained to underground mixes with underground water that is used for irrigation of lawns and vegetablegardens, and for watering orchards. Additionally, a lower connection rate to the sewerage network would result in a lower amount ofeffluent being treated at wastewater treatments plants, which might force the treatment plants to operate at a much lower capacityand cause technical inefficiencies.
P109964 | Second Multisectoral HIV/AIDS | Eastern and Southern Africa | Burundi | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2008 | 2011 | 2013 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/471731475090896963/text/000020051-20140625075155.txt | http://documents.worldbank.org/curated/en/471731475090896963/pdf/000020051-20140625075155.pdf | Experience in preparing and implementing this project suggests the following lessons drawn from the ICR (p. 17):Harmony between the PAD and the financing agreement is crucial for maintenance of appropriate focus and targeting. In this case, the statement of the projectâ€™s development objective in the PAD cites only prevention activities, while the Financing Agreement adds treatment. Even though treatment is now acknowledged as an important component of prevention, it is important for clarity of project activities and priorities that these statements not contain discrepancies.Coordination between development partners is necessary to avoid duplication and ensure efficiency of allocation of resources. In this case, a lack of harmonization between the Bankâ€™s and the Global Fundâ€™s support resulted in double payments for the same services.Results-based financing arrangements are a promising tool to accelerate and/or strengthen achievement of results, even in a post-conflict environment. In this case, even in the context of weak health systems, RBF contributed to the achievement and exceeding of some indicators over a relatively short time frame.IEG adds the following additional lesson:Even in a generalized HIV/AIDS epidemic in Africa, it is possible to reach high-risk groups with appropriately targeted interventions. However, the political will to do so is difficult to sustain and risks compromising the effectiveness of the program in the general population.
P109986 | Water and Sanitation Millennium Project | Western and Central Africa | Senegal | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2010 | 2015 | 2016 | ICRR | >=50 million & <100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/547871467034515357/text/ICRR-Disclosable-P109986-06-27-2016-1467035413857.txt | http://documents.worldbank.org/curated/en/547871467034515357/pdf/ICRR-Disclosable-P109986-06-27-2016-1467035413857.pdf | The ICR draws the following main lessons from implementing this project.(1)The project confirmed the relevanceand efficacy of social connection programs as the best way of achieving the Water and Sanitation Millennium DevelopmentGoals. The results achieved in the Dakar area regarding urban water supply showed that universal access to safe water throughhouseholds connections is a feasible goal in Sub-Saharan Africa.(2) It is preferable to package rural waterworks contractson a geographical basis rather than on a technical basis. Having a single contractor working on all activities in a givernarea rather than have to coordinate several specialized contractors.
P110018 | Improving Teacher Education | Latin America and Caribbean | Guyana | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2011 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/836911480531397414/text/1480532291262-0000A8056-ICRR-Disclosable-P110018-11-30-2016-1480532278023.txt | http://documents.worldbank.org/curated/en/836911480531397414/pdf/1480532291262-0000A8056-ICRR-Disclosable-P110018-11-30-2016-1480532278023.pdf | Lessons drawn from the ICR (pages 18-19), adapted by IEG: Anarrow and focused project scope canhelpto ensure successful implementation of project activities that have immediate impact but also contribute tobroaderoutcomes. In the case of this project, interventions were narrowly focused on improving the teacher training system whilealso supporting institutional development (curriculum revisions, performance evaluation tools) to ensure continued quality ofteachers intraining. When baseline data are not available but are to be determinedthroughevaluationsdeveloped as part of the project design, it is critical to ensure the original outcome targets arerealistic.In the case of this project, the unrealistic targets and the delayed revisions led toa lower outcomerating.
P110020 | RCI- Emergency Urban Infrastructure (FY08) | Western and Central Africa | Cote d'Ivoire | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2008 | 2014 | 2015 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/252781468191037278/text/ICRR14735-P110020-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/252781468191037278/pdf/ICRR14735-P110020-Box393183B-PUBLIC.pdf | Lessons from the ICR, adapted by IEG:Emergency projects benefit from simple implementation arrangements and having the project team leader in-country. This project engaged existing governmental agencies responsible for water, sewerage, solid waste and roads, without creating new agencies. The project team based in the country for an emergency project is an important element in the achievement of the objective.Keeping cities clean requires continuous efforts and not just a single campaign. Behavior change is a major part of improved solid waste management services and should be supported by a long-term strategy combining awareness-raising and economic incentives.Management of standpipes should be accompanied by awareness-raising campaigns. These include awareness about illegal water sellers and managers. Also, the financial situation of standpipe managers requires continued improvements, e.g., through proper pricing policies and the construction of kiosks for these managers.High costs of sewerage connections need to be addressed. The real costs of such connections are too high for potential poor beneficiaries, and there is a need for subsidies to help poor families to pay for their new sewerage connection. The payment of connections could be deferred over several years.
P110050 | Improving Public Sector Performance | Latin America and Caribbean | Honduras | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2012 | 2016 | 2017 | ICRR | Less than 10 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/754391480538917462/text/ICRR-Disclosable-P110050-11-30-2016-1480538901675.txt | http://documents.worldbank.org/curated/en/754391480538917462/pdf/ICRR-Disclosable-P110050-11-30-2016-1480538901675.pdf | The ICR developed several lessons, excerpted here: Procurement of information technology systemsthrough traditional investment operations takes time, commitment, and flexibility. In this case, none of these prerequisiteswas in place. A challenging country context and weak capacity should appropriatelytemper project ambition.A focus on fewer, or evenjust one, of the projects major planned outputs may haveincreased the probability of success. A lower-level Project Coordination Unit may lack theauthority and capacity toguide multiple entities through complex activities requiring collaboration andcoordination.A higher-level Steering Committee at the outset may have more effectively produced political consensus onpriorities and actions.
P110051 | HARYANA POWER SYSTEM IMPROVEMENT PROJECT | South Asia | India | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2010 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/749121542823671547/text/India-IN-Haryana-Power-System-Improv-Project.txt | http://documents.worldbank.org/curated/en/749121542823671547/pdf/India-IN-Haryana-Power-System-Improv-Project.pdf | The ICR identifies several important lessons. Periodiccampaigns to reinforce the importance of safety are a critically important addition to safety manuals: There were twoaccidents under the project due to lack of attention to safety requirements. To minimize this problem, safety issues have to bereiterated and reinforced in each interaction. Safety manuals are important, but their procedures need to be reinforced throughperiodic campaigns and workshops. Contracting for new technology needs to be handled differently from standardcontracting. The AMI package was a new technology for India for which official standards were not available at the startof the project. In such cases, new strategies need to be agreed upon at all levels during project preparation. The AMI procurementwas treated like a regular supply and installation procurement, whereas it needed a two stage bidding process that would allow theutility to hold one-on-one discussions with qualified bidders, update technical specifications, before asking for finalbids. Taking too legalistic and adversarial approach in the management of contracts is not alwayshelpful. Contractual remedies such as applying liquidated damages and cashing the performance security bonds, need to bedone judiciously to avoid creating additional problems of contractor cash-starvation causing further slowing down of contractimplementation. These risk and cost actions should be undertaken only as the last resort, since almost all such casesend up in arbitration or litigation. Alternative Dispute Resolution mechanisms like Dispute Resolution Boards may be helpful insuch situations.IEG adds the followinglesson: Investment projects in utilities should analysis theutilities financial situation, and where appropriate, identify the reasons why they appearto lack thefunds for implementing infrastructure investments. Such projects should includeactivities that are designed at a minimum to begin to resolve thisproblem. Lack of attention to underlying political andinstitutional problems that lead to the insufficiency ofinvestmentis likely to undermine the sustainability ofproject-supported improvements and does nothing to improve the long-term financial health of the sector.
P110075 | Increased Access to Modern Energy | Western and Central Africa | Benin | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2009 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/685641588341096276/text/Benin-BJ-Increased-Access-to-Energy-SIL.txt | http://documents.worldbank.org/curated/en/685641588341096276/pdf/Benin-BJ-Increased-Access-to-Energy-SIL.pdf | Two lessons were taken from the ICR with some adaptation of language.Differences between World Bank procurementrequirements and those at the national level can result in lengthy project implementation delays and higher workload for theproject implementation unit (PIU). This is an issue widely seen in World Bank project, which is also confirmed by thisproject. The DNCMP had a very low threshold for full approval of contracts, which resulted in delays processing numerous small sizeprojects up to four months, which was substantially longer than the stated-timeline of 15 business days. The lower contract sizethreshold for full contract approval also increased the work load of the PIU due to increased paper work.Lack ofinstitutional capacity of project implementation institutions can delay project implementation and jeopardize the achievement ofproject objectives. Like the first lesson, this one, too, is a common issue in World Bank projects. However, it is worthpointing this out here again, since the project implementation and achievement of the project objectives were adversely affected bythe lack of project implementation capacity, especially, at the SBEE and ABARME. The financial management and procurementresponsibilities of these two institutions had to be transferred to the PIU and the project activities related to ruralelectrification had to be cancelled. As a result, the achievement of the objective to increase access to electricity was modest.The project design at appraisal was overly optimistic about the SBEEs institutional capacity and the mitigation methods toimprove ABERMEs capacity were not realistic. This major shortcoming was partially addressed at the second restructuring inOctober 2013, more than four years after project approval.
P110092 | NI Greater Managua Water and Sanitation (PRASMA) | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2009 | 2015 | 2016 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/189821467993753816/text/ICRR14878-P110092-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/189821467993753816/pdf/ICRR14878-P110092-Box394823B-PUBLIC.pdf | The ICR provides the following lessons with which the IEG review concurs.1. The benefit of integrating PCUs in the agency responsible for the sector in terms of institutional development and contribution to the success of the project outweighs the potential costs of a unique compartmentalized PCU dedicated to one Bank Project.2. A simplified project focusing on physical infrastructure and access to beneficiaries is more likely to succeed in achieving its clear objectives especially given a determined government with a clear vision and preference to gradual approach to reform. 3. Emphasis on social inclusion and public participation when targeting low income settlements improves acceptance of the Project and the safeguarding of assets built.
P110099 | Water Sector Capacity Building & Advisory Services Project (WCAP) | South Asia | Pakistan | Blend | Non-FCS | Sustainable Development | Water | IDA | IPF | 2008 | 2021 | 2023 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099255012232263908/text/P11009902b92890a1095b90ae8d8cd760f2.txt | http://documents.worldbank.org/curated/en/099255012232263908/pdf/P11009902b92890a1095b90ae8d8cd760f2.pdf | IEG derives the following lessons drawn from the ICR: To avoid implementation delays, the role of the PSCshould be limited in its terms of reference to providing overall policy guidance and general oversight of Project implementation,and not to making decisions on adjustments to project activities. The PSC was given responsibility to make decisionsregarding changes in project activities, in the expectation that this would be faster and more flexible than seeking governmentapproval for each change. However, the PSC, which comprised representatives of multiple stakeholders, proved difficult to convene,which significantly slowed implementation. Where the results frameworks focus on outputs,supplementary data are required to measure the outcomes of institutional strengthening projects. The outcomes of projectsthat support capacity building and technical assistance are difficult to assess on the basis of outputs alone. Additional data arerequired to monitor the changes that take place as a results of training, upgrading decision support tools, constructing andrehabilitating laboratories, and preparing feasibility studies. These data can be collected through surveys and other datacollection methods. Overcoming capacity gaps requires continuous and tailored support. Theagencies implementing the project had very different capacities for implementation. To build the capacity of the weaker agenciesrequires precise identification of capacity gaps and the provision of expertise from outside of the agencies. Capacitybuilding should also comprise more than just trainings, and include study tours, ad hoc technical assistance, and support insoft skills such as capacity for coordination. More intensive efforts to build the capacity of weaker implementingagencies would help to close the capacity gaps. Project management arrangements need to be maintainedthroughout the project period to ensure smooth implementation. A key reason for the underperformance of the AF was thelack of a full-time dedicated project director and the frequent turnover of staff, and the chronic understaffing of the PMPIU. Thefollowing measures could strengthen management of future projects: (a) use existing government systems and staff as much aspossible to avoid creating parallel systems and build their capacity aimed at fostering a dedicated cadre of experts in the publicsector, (b) encourage implementing agencies to procure experts with compensation commensurate with the market.
P110109 | Fifth Poverty Reduction Support | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2010 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/662231474634349460/text/000180307-20141201111524.txt | http://documents.worldbank.org/curated/en/662231474634349460/pdf/000180307-20141201111524.pdf | IEG concurs with the lessons derived by the ICR, including the importance of:(1) Complementarity between policy and institutional dialogue through PRSO and existing investment and technical assistance projects is critical for the success of reforms.(2) Adapting to the political economy of reforms, identifying champions in government with a reasonably well-defined reform agenda and engaging with a broader range of actors, and selecting focused sector engagement were PRSO work has a clear comparative advantage.In addition to these lessons from the ICR, IEG notes the importance of selecting performance indicators, ex ante, which can be benchmarked and monitored.
P110126 | Regional and Municipal Infrastructure Development Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2009 | 2015 | 2016 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/602831468185395597/text/ICRR14866-P110126-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/602831468185395597/pdf/ICRR14866-P110126-Box394823B-PUBLIC.pdf | Lessons from the ICR, adapted by IEG:Providing credits to creditworthy local self-governments with reasonable credit capacity and grants to small municipalities with no credit capacity helps enhance the credit culture and ensure that small municipalities are also included. Fiscal discipline should be enforced to help municipalities learn how to function in a market borrowing environment.Investments should take place with a strategic vision in place. The adoption of a wastewater management strategy under this project introduced more cost-effective technology options and encouraged donor organizations to commit resources and invest in the sector.A transparent and fair system for housing allocation for conflict affected people may help avoid complaints. Distribution of houses among internally displaced people during a lottery attended by all beneficiaries was a critical aspect of this process under the project, which strengthened beneficiariesâ€™ trust in the system, and allowed a smooth process, with no complaints related to lack of transparency in housing allocations.
P110147 | Ghana Second Agriculture Development Policy Operation | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | DPF | 2010 | 2011 | 2015 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/447151475116261071/text/000180307-20141203062550.txt | http://documents.worldbank.org/curated/en/447151475116261071/pdf/000180307-20141203062550.pdf | The ICR noted three lessons: complementarity of policy agenda with other Bank operations, the need for borrower to internalize monitoring of data and ensure adequate reporting, and the need for overall policy framework that includes complementarity with other donors (in this case CIDA, which provided substantial complementary budget support).Additional lessons that could be considered in future operations:Ensure more concrete development objectives that are easier to link with policy framework, actions, outputs and outcome indicators. The Bank should take into account the size of its interventions relative to the magnitude of the desired objectives as an input into the definition of development objectives. If the size of the loan is very small relative to the size of the economy or sector, then development objectives should be scaled down to what realistically the Bank operation can be expected to influence. Exercise greater selectivity and prioritization in the design of DPOs in terms of the number of policy areas, prior actions, and outcome indicators. Choose prior actions that are less process and documents oriented. Actions that are more geared towards policy implementation that can be quantified and linked more directly with outputs and outcomes have a greater chance of attribution, monitoring, measurement, and impact.Never choose an outcome indicator that depends on a baseline study that is not already available. Each outcome indicator should have an unambiguous, ideally quantitative baseline at the time of DPO design. Also, it should be relatively easy to observe, measure, monitor its updates and rate of change. Indicators that depend on surveys that are yet to be carried out run the risk of becoming irrelevant if a survey is delayed, as is often the case.A macroeconomic framework should include a detailed quantitative assessment of debt sustainability with appropriate sensitivity analysis. It should also indicate whether it is primarily a Bank assessment or joint with the IMF and whether there are any differences in the assessment of the macroeconomic framework and risks.
P110147 | Ghana Second Agriculture Development Policy Operation | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | DPF | 2010 | 2011 | 2017 | PPAR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/707151490035515853/text/112622-PPAR-PUBLIC.txt | http://documents.worldbank.org/curated/en/707151490035515853/pdf/112622-PPAR-PUBLIC.pdf | 4. Lessons 189. The experience of these two programmatic DPO series provides the following lessons. 190. In a sector such as agriculture, in which responsibilities are fragmented across many different directorates and agencies, impact could be heightened by broadening engagement beyond key counterparts in the leading ministry to other directorates charged with delivering program results. In this case, the World Bank's dialogue and engagement was largely through counterparts in the MOFA's PPMED. Although other directorates participated in the selection and identification of prior actions, insufficient efforts were put in to sensitization and capacity building for implementation of reforms. There was a limited understanding of the budget support instrument among many key stakeholders beyond PPMED and lack of ownership in implementation of reforms. Weak coordination within MOFA and the weak leverage that PPMED had over other agencies linked to prior actions hampered PPMED's capacity to track subsequent implementation. 191. Rigorous assessment of government commitment and ownership is needed not only at the design stage but throughout implementation. In Ghana, the government engagement was high with respect to identifying and meeting prior actions but subsequent implementation of reforms was weak. 192. Potential synergies between sector and general budget support operations could be enhanced by more effective coordination and monitoring and feedback between the two. In these two agriculture DPOs, it was assumed at the design stage that the general public financial management reforms supported by PRSCs and economic governance DPOs would also benefit MOFA. However, public financial management reforms did not perform as expected. This illustrates the need for feedback to the sector operation so that measures can be taken to compensate. Additionally, in the agriculture sector, many reforms are needed beyond MOFA's jurisdiction, some of the crossjurisdictional reforms may be best incorporated into national-level budget support. In the second series, MOFA was cautioned by MOFEP to only agree on budget support triggers and targets over which MOFA had direct control. This makes sense from the standpoint of ensuring that targets are met in the short term, but it limits the utility of sector budget support in tackling critical bottlenecks in the sector that are covered by other ministries, directorates, and agencies. The completion reports of both series argue that actions beyond the jurisdictional mandate of the sector ministry would be better managed under MDBS. This too requires greater coordination and ongoing feedback and monitoring between sector and macro level teams. Prior actions that can improve coordination across ministries, directorates, and agencies should be considered. 193. Defining DPO series objectives in concrete and measurable terms and scaling ambition down to what the actions in the operations can realistically be expected to influence can improve the demonstration of impact and enhance attribution. In both of the series reviewed the overly general formulation of objectives made it difficult to connect to the outcomes of the various policy areas to the very ambitious series objectives. The results framework did not establish a clear causal chain between the prior actions and the overall series objectives. The mismatch between the identified outcomes and the prior actions and performance indicators added to the difficulty in establishing the contribution of the series prior actions to the series objectives. Prior actions geared toward policy implementation that can be quantified and linked more directly with outputs and outcomes have a greater chance of attribution, monitoring, measurement and impact.
P110156 | Swaziland Health, HIV/AIDS and TB Project | Eastern and Southern Africa | Eswatini | Blend | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2011 | 2019 | 2019 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/637901559743802849/text/Eswatini-SZ-Health-HIV-AIDS-TB-Project-FY11.txt | http://documents.worldbank.org/curated/en/637901559743802849/pdf/Eswatini-SZ-Health-HIV-AIDS-TB-Project-FY11.pdf | The ICR (pp. 33-34) offered several lessons and recommendations, including the following lessons restated byIEG:Collaboration with other ministries facilitates health sector performance. Underthe project, several challenges were dependent on other ministries, such as the Ministry of Public Service for human resources; theMinistries of Public Works and Economic Planning for infrastructure maintenance; and the Ministry of Finance for stockouts ofessential drugs.The inclusion of critical inputs such as essential drugs in the projectfinancing plan prevents a negative impact onproject services that may be caused by uncertain supply from other financingsources. During project implementation, support to pharmaceuticals and human resources was expected from otherfinancing sources, including from development partners, but such expectations did not materialize resulting in pharmaceuticalshortages.Utilization of comprehensive quality improvement techniques facilitates the monitoring ofservice quality. The quality of health services was a key project area, and the introduction of quality improvementplans for health facilities would have strengthened the monitoring of quality aspects.
P110167 | Transitional Support Credit | South Asia | Bangladesh | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2009 | 2010 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/632371474634910375/text/000020051-20140620081929.txt | http://documents.worldbank.org/curated/en/632371474634910375/pdf/000020051-20140620081929.pdf | The Bank should be fully engaged during transitional governments where there appear to be windows of opportunity for significant reforms. This may well be a rare opportunity to pursue important reforms. However, reforms supported by such operations will be managed by subsequent governments, and so such operations would frequently be high risk operations. Nevertheless, this is an appropriate focus for Bank supported operations.The Bank must continue to maintain a dialogue with political parties, including those in opposition, and with other key opinion makers in a more institutionalized manner to ensure continuous and better assessment of public support for reforms. While the Bank was right to seize the window of opportunity to support wide-ranging reforms by the CTG through a stand-alone operation, far-reaching governance reforms are better supported using a programmatic series of budget support operations. However, given the limited time frame for the CTG, such a series was not possible in this case.
P110191 | Fifth Development Policy Loan | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2009 | 2009 | 2011 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/970071474906299542/text/Indonesia-Fifth-Development-Policy-Loan.txt | http://documents.worldbank.org/curated/en/970071474906299542/pdf/Indonesia-Fifth-Development-Policy-Loan.pdf | The lessons arising from the overall series are presented in the ICRR for the Sixth Development Policy Loan - P113638.
P110207 | Preparedness and Control of Avian Influenza | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2008 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/660961475114036848/text/000012394-20150312110339.txt | http://documents.worldbank.org/curated/en/660961475114036848/pdf/000012394-20150312110339.pdf | The following lessons are emphasized from the ICR with some adaptation of language:Flexible implementation arrangements are more suitable in an emergency operation. There is need for greater pragmatism and flexibility during emergency projects especially if there is a threat of a disease outbreak. Options might range from using the procurement staff of existing/ongoing projects with experienced personnel for the more urgent items, while non-urgent items are procured by the relevant line ministry staff whose capacity might still need some strengthening, to hiring experienced consultants for the duration of the project, to pairing line ministry staff with more experienced short-term consultants for on the- job training. In addition, it is important to constructively use the time before project effectiveness to make progress on procurement (especially where procurement accredited staff in the ministries already exist), instead of waiting for project effectiveness before starting the procurement process.Engagement with parliament during project preparation can facilitate timely approval of projects by parliament. Adequately engaging key parliamentarians about the projectâ€™s broad scope and the varied and persistent nature of the threats addressed under the project could have potentially facilitated an expedited and favorable consideration of the project in Parliament. It is particularly important that relevant parliamentary sectoral committees be closely associated with the project preparation process to ensure timely approval.Working across sectors can be an effective way of addressing zoonotic diseases. With the growing and persistent threat from zoonotic diseases, a culture and effective modi operandi of collaboration between the ministries in charge of health and livestock are critical in ensuring adequate monitoring of, and rapid response to major zoonotic disease outbreaks. Implementation arrangements through Government structures should take into account not only staffâ€™s technical competency but also their actual availability. The Office of the Prime Minister (OPM) tends to be a favored choice for coordinating projects of a multisectoral nature, as was the case in this project. With the growing tendency for multi-sectoral approaches, hence the risk of overwhelming OPMâ€™s capacity, the choice of OPM for project coordination should be weighed against the available capacity to fulfill the function. Alternative implementation arrangements (such as conferring coordination responsibilities to the ministry with the preponderance of project activities) should also be considered.
P110251 | Healthcare support to the poor of the Northern Upland and Central Highlands | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2008 | 2012 | 2013 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/114321474572097918/text/000020051-20140626001857.txt | http://documents.worldbank.org/curated/en/114321474572097918/pdf/000020051-20140626001857.pdf | Lessons drawn from the ICR (pp. 26-27) and adapted by IEG:Outcomes from local-level projects can inform national programs and policies, if this is well-considered in the project design. In the case of this project, experiences gained from the bottom-up planning approach were unlikely to have sustainable capacity impact because the approach was not adopted more broadly by the government.Benefits of a dual supervision arrangement should clearly outweigh the costs. The Bank/EC arrangement brought high levels of technical support and coordination; however, it resulted in two separate reporting systems that led to inefficiencies in project management.
P110267 | Second Rural Water Supply & Sanitation | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2009 | 2015 | 2016 | ICRR | Less than 10 million | Moderately Satisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/817081467987910663/text/ICRR14838-P110267-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/817081467987910663/pdf/ICRR14838-P110267-Box394823B-PUBLIC.pdf | The ICRR provides 12 lessons and the three most important are summarized below: Design of so called â€˜repeaterâ€™ or follow-on operations should involve comprehensive consultations with various key stakeholders to capture any legacy issues and incorporate important lessons on what has and has not worked at different stages of the original project. In the subject project, the implementing agency was inherited from the earlier project without fully diagnosing that its effectiveness was the result of good project management consultants, rather than its own internal capacity. Ensure that expediency does not displace capacity building in government institutions. In this project expediency led to the by-passing of the line agency and outsourcing project management to a NGO, and this approach turned out to be a successful arrangement for getting implementation up to speed and back on track. However, care has to be taken at restructuring that the NGO managers have the skills and capacity to work alongside their government counterparts, transfer knowledge and build capacity. The community- based rural water supply delivery model should fully consider sector maturity and competence, political context, and capacity at the local level. Stakeholders must be informed and prepared for the fact that some community-based drinking water user associations may underperform or fail because of inadequate capacity or financial resources to address issues, and must plan for solutions to assist associations in need.
P110371 | Sustainable Urban Transport Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2018 | 2019 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/270641561147309273/text/India-IN-Sustainable-Urban-Transport-Project.txt | http://documents.worldbank.org/curated/en/270641561147309273/pdf/India-IN-Sustainable-Urban-Transport-Project.pdf | IEGselected three lessons from the ICR, with some adaptation of the language: BRTprojects need to establish comprehensive teamssimilar tometro projects.BRT systemsarecomplex projects that are more than infrastructure design and contracting of civil works. They include operational dimensions suchas bus service plan, design of operating procedures, traffic management, pedestrian access, safety processes, among other. Theyinclude land acquisition and safeguard management processes, communication, and consultation processes. The experienceunderthis projectwas that the BRT office tended to be on a small scale, reliant on units of the mother agencies formuch of the technical support, and with a primary focus on civil works. The non- construction elements (i.e., land acquisition) aswell as operations tended to continue to reside in other departments or agencies. This led to fragmentation in planning anddelivery, gaps in communication and responsibilities, and understaffing in critical areas. BRT projects must be implemented throughnodal entities and should be more substantial and multifunctional so that they have the capability to deal with all the issues inan integrated way. BRT and ITS only realize their true potential when there is theability to utilize them. BRT infrastructure and ITS have great potential, but this potential can only be achieved whenthere is the business/service plan and the organizational capacity to utilize them well. To a large extent, the cities supportedunder this projectonly began to prepare themselves for the operational phase as the works were being completed, while theyneeded to do so several years earlier.The ITSin Mysore provides an excellent model of how it progressively used thedata and functionality of the ITS to adjust its schedules and routes, to tackle a wide range of long-standing operational problems,and gradually incorporated the ITS into its processes throughout the organization. Ridership development requires greater effort.In Pimpri-Chinchwad, the weak capacity of PMPML and deteriorating fleet have led to a declining service on its operational BRTcorridors despite a positive public response to the system. It is better to avoidtwo-stage and temporary resettlement in the land acquisition process.Under this project, the shifting of displacedfamilies to transit housing for 18 months resulted in people living there for about six years due to inordinate delays inconstruction of alternative housing causing hardship to displaced families. Similarly, the three-month temporary displacement ofshopkeepers in Hubli-Dharwad resulted in a 10-month wait for shopkeepers to bring them back to the original site due to delay inconstruction schedules. This suggests avoiding two-stage resettlement or temporary displacement and instead planning for permanentresettlement.
P110407 | AF Rural Enterprise Development Program | South Asia | Afghanistan | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2010 | 2018 | 2020 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/306761563989663854/text/Afghanistan-AF-Rural-Enterprise-Devt-Program.txt | http://documents.worldbank.org/curated/en/306761563989663854/pdf/Afghanistan-AF-Rural-Enterprise-Devt-Program.pdf | The ICR included eight Lessons. The following three are emphasized with some adaptation oflanguage: Advocating womens participation to strengthen the family unit, ensuring women to womenservice delivery, facilitating partnership among women, and developing village-level role model are allcritical elements toensure women participation in culturally conservative environments.Despite the social and cultural context ofAfghanistan, the project successfully mobilized women and promoted their entrepreneurship. Theprojects rural enterprisedevelopment model suited womens mobility, as Enterprise Groups (EGs)tapped into village or district market. The designchange to enable EGs to take loans from SGs was also to womens advantage, as they took smaller loans than men. Thelower profitability among women-owned EGs would have to be addressed in the follow-on project, potentially by supporting women EGsto select profitable sectors, such as dairy/livestock, which would facilitate PA aggregation and supply chain development, and todevelop linkages with district or provincial market by hiring a few men. Bolsteringthe inclusionof marginalized groups requires innovative approaches such as roaming enterprise facilitators. The projectsexperiencedemonstrated that innovation for inclusion is possible in the most fragile of environments. The project pilotedinnovative support for people with disabilities and Kuchies (nomadic tribe) and the use of roaming enterprise facilitators tobolster inclusion. These innovations were very successful and contributed to the achievement of some of the outcomes concerningwomen and people with disabilities. These approaches provide effective cost saving strategies for similar rural livelihoodprojects. Replicating arural enterprise development model in fragile countries requiresestablishing five key elements: group savings and credit, economic mobilization, aggregation of micro enterprises, Small and MediumEnterprise (SME) development, and supply chain development. With few private sector actorsand limitednationalor provincial supply chains in Afghanistan, the SME support was necessary to help village-level micro enterprises tap into thedistrict or provincial market. Theproject focused on Savings Groups (SGs) mobilization and savings to make credit availablefor village-level enterprise development. These small savings by rural men and women improved incomes andemploymentopportunities for EG members in targeted villages. The Project aggregated EGs into Producer Associations tofacilitate linkages with the project-supported SMEs. While there were fluctuations in employment, both EGs and SMEs had an overallincrease in non-EG member (on payroll) and seasonal employment in about five years.
P110446 | Malawi Third Social Action Fund (MASAF 3) APL II (LDF Mechanism) | Eastern and Southern Africa | Malawi | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2008 | 2014 | 2016 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/931491468188937428/text/ICRR14808-P110446-Box393228B-PUBLIC.txt | http://documents.worldbank.org/curated/en/931491468188937428/pdf/ICRR14808-P110446-Box393228B-PUBLIC.pdf | The following are general lessons drawn from the ICR:In order to assist communities in realizing their development needs, efforts such as training and technical backstopping of the Local Authorities are vital and need to be sustained if Local Authorities are to take over the role of development management. Where such efforts have been sustained and the right numbers of key staff supported, it has contributed to the successful implementation of sub-projects and early completions.Information, education, and communication (IEC) can play a catalytic role in mobilizing communities and other stakeholders for community development and ensures transparency and accountability. It can also assist in clarifying project processes and procedures that contribute to smooth project implementation.Successful achievement of policy objectives is dependent on consistent commitment from the respective stakeholders in terms of meeting their share of obligations. In this case, the institutionalization of fiscal devolution has not been fully implemented because government has not yet devolved the development budget and the cooperating partners still insisting on discrete funding and accountability reporting
P110446 | Malawi Third Social Action Fund (MASAF 3) APL II (LDF Mechanism) | Eastern and Southern Africa | Malawi | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2008 | 2014 | 2016 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/931331469129179396/text/106389-PPAR-P157696-Box396277B-OUO-9-malawi-0716.txt | http://documents.worldbank.org/curated/en/931331469129179396/pdf/106389-PPAR-P157696-Box396277B-OUO-9-malawi-0716.pdf | 6. Lessons 6.1 The main lessons to draw from the project are as follows\. Â· CDD can facilitate decentralization, but the right balance must be struck between community priority setting and local development planning. MASAF's participatory planning process â€“ providing facilitation and financing that allowed communities to define their priorities, develop investment proposals, have them financed, and implement them â€“ was mainstreamed into the local planning process, giving LAs the role MASAF had played. In principle, this addresses the main objective of decentralization, i.e. to improve service delivery, and ensure participation. However, in undertaking mainstreaming, care must be exercised that proper balance is found in the participatory process\. while community participation was formally incorporated into the local development process in MASAF 3 APL II, community priority setting seemed to have become secondary to district level planning. While this may be justified in terms of broader and longer term district level planning objectives, it also points to the need for transparency in the setting of district level planning objectives. Â· CDDs that emphasize longer term improvements may not always be the best instruments for addressing shocks. CDDs with their support for expanding access to basic services form part of the social safety net. However, they may not always be well suited to address short-term shocks. In MASAF, this was partly the case â€“ while some of its livelihood components built longer term capacity, only the public works mechanism was one that could easily be expanded and compressed in reaction to economic or climatic shocks hence the introduction of two AFs, providing resources to expand public works; and subsequently the emphasis placed on unconditional cash transfers and public works under MASAF 4. An adaptable safety net should contain both longer-term productive mechanisms, as well as mechanisms that can be adapted to respond to crises. Â· Monitoring and Evaluation can be a critical factor to successful project implementation. The M&E drew on an already-established MIS that was enhanced over time with a well-defined M&E strategy for project processes, information requirements, tools and methodologies for data collection, analysis and reporting. The existence of a comprehensive M&E plan with clear roles and accountabilities as they relate to indicators tracking with respect to data gathering and reporting was also important. Â· Assessing institutional capacity at the design stage, and systematically during implementation, is critical, especially when the project includes a component on capacity building at the local level. The design of the project should take into consideration the institutional capacities available under the project to get a better sense of the limitations on absorptive capacity, the institutional risks and needed capacity to effectively administer and monitor proposed activities. During implementation, the systematic assessment of institutional arrangements and capacity should be integral to project supervision. One of the successes of the project was that the APL II design included systematic assessment of current capacities of LAs and the establishment and use of capacity benchmarks to support LAs in their new tasks. Â· Beneficiary feedback throughout the assessment, provides important evidence of the impact of the operation from the perspective of the beneficiaries. MASAF did well in designing surveys and evaluations that provided information on project process and outcomes. Participatory M&E (through citizen report cards and community score cards) helped to identify service gaps and promote accountability of service providers. This is critical, particularly given the nature of a CDD operation, which supported community-driven infrastructure and extended basic services to the vulnerable poor. Documenting how feedback was used to improve activities, processes and arrangements under the operation is also very important. Â· Sub-project economic and financial costs should take into account affordability of sub-projects in poor communities. In some instances, communities faced difficulties in meeting a 25 percent community contribution towards the cost of educational sub-projects, including in particular when material shortages pushed up unit costs. In other instances, application processes proved too complicated. Increased attention needs to be paid to direct as well as indirect costs in designing sub-projects to ensure their affordability. Â· Linking income generation interventions with asset building opportunities can help build economic resilience. MASAF linked savings-investment opportunities to the public works schemes. This resulted in group savings and revolving funds that allowed participants over time to build a savings and assets base. It is important to consider such opportunities of linking savings-investment schemes to cash transfers as a means of more permanently improving the situation for poor households.
P110462 | Argentina Mining Environmental Restoration Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2009 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/931341521756988585/text/Argentina-AR-Mining-Environmental-Restoration-Proj.txt | http://documents.worldbank.org/curated/en/931341521756988585/pdf/Argentina-AR-Mining-Environmental-Restoration-Proj.pdf | The ICR (p. 33) includes valuable lessons learned: When designing a project, it is important to takeinternal regulations of local entities into account. In this project, a panel of international experts was to behired to provide advice on international best practice in planning and designing remediation efforts. However, the Ministryof Energy and Mines had internal contractual regulations in place which did not allow for the panel to be established asplanned. Local ownership is critical for a successful project implementation. In this project, anew project activity the construction of a public green space was added as a mitigation measure at the legacy siteduring project implementation by the CNEA, the municipality and the Bank. Allowing for this flexibility resulted in a higheracceptance for the remediation activities at Malarge. By engaging in high risk-high return operations, theBank can set an example and create models for future environmental remediation efforts: Even though this project hadsome shortcomings, the Bank, in collaboration with the government, implemented the first and critical uranium site remediation inthe country by bringing international technical expertise, adequate environmental and social standards, and financial resources tothe table.
P110481 | Energy Community of South East Europe APL Program - APL 5 for Albania DAM SAFETY | Europe and Central Asia | Albania | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2008 | 2022 | 2023 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099845101092329398/text/P11048107790ae08409ecb0136db729f7b6.txt | http://documents.worldbank.org/curated/en/099845101092329398/pdf/P11048107790ae08409ecb0136db729f7b6.pdf | The ICR included eight lessons. The following three are emphasized with some adaptation of language:1. Ensuringimplementation readiness for complex infrastructure projects iscritical to avoid future delays during implementation.Early preparation of documents and sites can help avoid unnecessary initial delays. Feasibility studies and technicaldesigns need tobe identified during the preparation stage andconcluded by the time the project goes to the Board.However, often, studies might take longer, and projects need to be prepared fast (depending on whether the bank is ensuring the IDAwindow is met or some regional concessional financing window). In such cases, a vertical Multi Phase Programmatic Approach(MPA)could be utilized wherein the technical studiesrepresent the first phase and some rehabilitation works to correctlyidentify issues and major infrastructure investment could be the second and/or third phases.2. The timing ofsupport and coordination between development partners is important to ensure timely completionof project activities.While the project served as remarkable example of cooperation betweenfinancial development institutions, the timingof support and coordination needed to be planned better. For instance, Vau I Dejes works were originally supposed to be funded bythe World Bank and had been part of the project appraisal, and KfW took over the project at a much later stage. Similarly, EBRD didnot come into the picture before 2011. Proper delineation of tasks during the appraisal stage could have helped bring on EBRD andKfW at an earlier stage to complete the project earlier. Proactive coordination and collaboration between various developmentpartners need tobe improved by proper communication between the World Bank, the Government, and other bilateral andmultilateral partners before or during appraisal.3. Regional adaptive program loans, such as the ECSEE APL, arecomplex operations thatneedsufficient time and resources to conduct technical studies, engage client governments, andtrain implementation agencies to ensure technical correctness, implementation feasibility, and political supportability.The program has shown that regional energy market development is a complex and long-term undertaking and is affected bynational/EU regulations. The main challenges in the implementation of such projects could range from the implementation of aregional action plan for a wholesale market to the integration of transmission lines into a regional network.
P110525 | Multi-Donor Trust Fund to Support Public Financial Modernization in Vietnam | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2009 | 2014 | 2015 | ICRR | Less than 10 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/755701467993502309/text/ICRR14678-P110525-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/755701467993502309/pdf/ICRR14678-P110525-Box393183B-PUBLIC.pdf | The ICR (pp. 22-23) draws the following lessons:Mid-term project adjustment can be triggered by a change in political momentum, which in turn can lead to improved project performance.Projects with a broad and ambitious structure spanning across many departments can benefit from effective delegation and clarity of roles, responsibilities, and accountability. From this project it follows that communication and a PMU with a strong coordination and facilitation role are important complementary factors.Frequent and effective communication between stakeholders is important for implementation. Given this project's complexity, this was particularly important to coordinate among many priorities.There is a trade-off between flexibility and strategic focus of a program. Allowing flexibility in the program meant that the government could react quickly to emerging needs, that were sometimes even outside of the core PFM. This, however, also meant that the operation diluted its strategic focus. After restructuring, the operation become more focused but less flexible.
P110525 | Multi-Donor Trust Fund to Support Public Financial Modernization in Vietnam | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2009 | 2014 | 2016 | PPAR | Less than 10 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/678051469685075659/text/Vietnam-Public-Financial-Management-Reform-Project.txt | http://documents.worldbank.org/curated/en/678051469685075659/pdf/Vietnam-Public-Financial-Management-Reform-Project.pdf | 10. Lessons General 10.1 An evolving project level M&E may be a good substitute for a formal one that is pre-set at appraisal. This can be the case when the iterative, demand-driven nature of the activities does not allow clear measurable objectives to be set from the outset. Also approaches, such as use of social media, may be informative and cost-effective. Finally, standalone studies and assessment provide important complements to results-based M&E. 10.2 Outcomes for PFM operations are difficult to measure at closing. The Vietnamese cases show how ongoing policy actions take time to mature as do systems. In this instance, project outcomes became fully apparent in early 2016. In cases elsewhere, a number of factors including poor governance may undermine the initial results. Even though periodic PEFA assessments are not suitable as M&E for operations because of lags in indicators, they can provide useful information on PFM program progress over time. 10.3 PFM reforms need decades to complete. Vietnam is well into its second decade of reform. Both the government strategy and actions needed to reach the higher level objective of good governance show the need for this effort to be sustained into the 2020s. In this context, continued effective provision of financial and, more importantly, knowledge by development partners, will be needed. Strong donor harmonization and coordination have been enabling factors so far. Coordination has become more important now that some partners are no longer participating in the follow-up to the MDTF under preparation, providing separate support instead. 10.4 The funding of operations may not be commensurate with their impact. Significant results were attained under MDTF II even though the grant amount was small. The supervision resources devoted to the project were large compared to disbursements because they underpinned an important policy and institutional dialogue. The World Bank correctly continued to support project implementation, even at a time were difficulties were experienced. On the government side, capacity built was sustained and, together with substantial ownership, resulted in actions being continued beyond the timeframe of the project. 10.5 TA operations that are initially focused on a single ministry may have a greater chance of success. Clarity in ownership and leadership of the activities by the MOF, which is the leading institution in PFM, was essential and avoided overcomplicated coordination mechanisms in the case of MDTF II. However, future PFM reforms will inevitably have to cover multiple entities and would need to ensure activities are well sequenced and coordinated. FMIS 10.6 Strong and sustained government and MOF commitment is essential. Since these projects can take 7â€“10 years or longer for completion, it is necessary to maintain this commitment over a long period, which can extend beyond an election cycle. This commitment can be achieved better if projects are framed as public expenditure management systems reform, rather than just accounting systems reform. In Vietnam, government support was particularly important to address project-staffing issues, resolve business processes issues, and tackle interorganization issues. 10.7 Comprehensive FMIS implementation as in Vietnam takes about 10 years to complete. These projects are characterized by slow disbursement rates over the initial years, which are spent in systems design, testing and piloting. The disbursement profile needs to be adjusted accordingly. 10.8 Continuity in the project team contributes to success. There was stability on both government and Bank side, and key members of the team that designed the project remaining engaged in its implementation for the first few years ensured an effective transfer of knowhow to field-based and other Staff. 10.9 Systems sequencing is key. The TABMIS implementation in Vietnam illustrates how project implementation for similar systems needs to be phased44 to achieve significant outcomes such as good budgetary control and cash management early in the Project. It is necessary to first implement modules to cater to core budget execution processes and processing of payments and receipts transactions, across government, before going on to other noncore elements, such as fixed assets/inventory management, human resource or fleet management. 10.10 Systems deployment strategies should make sure that a large part of the budget is covered from the outset. A major part of the budgetary resources should be subjected to ex-ante budget and cash control so that meaningful fiscal control and cash management is possible at an early stage in the deployment. A deployment across treasury offices through which these transactions are routed, may be sufficient for this purpose. 10.11 Spending unit access is a challenge in the use of treasury centric systems. The lack of spending unit access inhibits ownership at the line ministry and end-user level. This often leads to line ministries developing independent financial systems for their own management use, as in the case of Vietnam. Avoiding this outcome requires that once the basic treasury system has been implemented and is operating in stable mode, the large spending units be empowered and made responsible for the bulk of transactions. 10.12 Availability of specialized IT expertise within the Bank project team is critically important to assure the quality of design and supervision of the projects that support development of complex IT systems. The Bank team needs to have experienced specialists on board or available to advise the client on important technical issues during the design and implementation phases. These specialists also need to be familiar with procurement practices and procedures for IT related procurements and the World Bank rules under which they will need to be applied. 10.13 Staff in the implementing agencies should recognize the inevitability of change. Resistance often comes from staff responsible for operating the legacy systems as well as those who are used to doing their regular work in a given way and are reluctant to change. MOF management has a major role to play. 10.14 The design of the main consultancy package has proven to be a significant bottleneck for TABMIS implementation. The consultancy package should be designed to ensure that appropriate consulting help is available throughout the various stages of the project. 10.15 Not all needs may be foreseen during the project's preparation and original design. The number of system users of TABMIS increased threefold between design and full rollout and had to be accommodated.
P110535 | Reproductive and Child Health Project - Phase 2 | Western and Central Africa | Sierra Leone | IDA | FCS | Human Development | Health, Nutrition & Population | RETF | IPF | 2011 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/822581525096640753/text/Sierra-Leone-SL-Reprod-Child-Health-II-Proj-FY10.txt | http://documents.worldbank.org/curated/en/822581525096640753/pdf/Sierra-Leone-SL-Reprod-Child-Health-II-Proj-FY10.pdf | The ICR (pp. 40-42) offerslessons from project experience, including the followingrestated by IEG, observing thatsome of these lessons are reasonable propositions, but do not appear to bedirectlyobtained from actual projectexperience: The buy-in and early involvement of key stakeholders in planning medical wastemanagement facilitate adequate implementation. The lack of early engagement of stakeholders in medical wastemanagement planning contributed to low compliance (ICR, p. 41). Phasing theimplementation of large-scale and complex health interventions enhances the likelihood of successful implementation.The project scope exceeded existing capacities, and the PBF required several stakeholders to work together. Hence, the ICRsuggests that capacity and implementation challenges may have been overcome if the project followed an incremental implementationapproach rather thanan all-at-oncenational implementation, and that district capacities would have informed theselection of districts under a phased approach.Note: This proposition makes sense, but it is not directlyobtained from actual project experience. The effectsof the Ebola Viral Diseasecrisis on the health system in Sierra Leone illustrate the importance of strong community-based systems for surveillance, healtheducation, and service delivery. Note: These reasonableassertions are found in the internationalliterature,but they are not directly derived from actual project experience.
P110538 | Ferghana Valley Water Resources Management Phase-I Project | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Sustainable Development | Water | IDA | IPF | 2010 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/792691508186394069/text/ICRR-Disclosable-P110538-10-16-2017-1508186380282.txt | http://documents.worldbank.org/curated/en/792691508186394069/pdf/ICRR-Disclosable-P110538-10-16-2017-1508186380282.pdf | The ICR included five lessons, but most of them were concerned with narrow operational issues faced by this project. Thoselessons with broader application beyond this project are listed below with some editing.For greatereffectiveness of the ME framework for project implementation, the overall ME system needs to be firmly established andtested before project effectiveness or within the first year of the project. In the FVcase, the deficiencies in theME design led to the inconsistency in the methodology for monitoring certain indicators that required restructuring. Theupsides and downsides of outsourcing the ME function may also vary according to localcontextThe administrative complexities in implementation can severely hamper progress (includingexcessive delays in contacting and procurement) and undermine the benefits from restructuring. In the specific case ofthis project, while the mid-term review (MTR) was undertaken in November 2013, the requested formal restructuringto improvethe ME framework could only beeffected in April 2015,quite late in the process for a project that closed in Dec2016, after a five-month extension from its initial plan.Projects that require large-scaleinfrastructure works and importation of heavy equipment or international competitive bidding require careful design of contractingarrangements considering the laws of the country and in close coordination with local authorities for smooth execution.There were serious performance issues in the ICB-2 and ICB-3 contracts which highlighted the need for better contract managementfor increased efficiency and effectiveness and compliance with relevant Bankpolicies. In addition, progress in importingheavy equipment was hampered by the need to get clearance by MFERIT and a long customs clearance which was only resolved after morethan half-a-year delay when the GOU intervened to resolve the matter for importation of the heavy machinery critical for thelarge-scale infrastructure work.Increased awareness and demonstration by itself will notnecessarily enhance introduction of complex technologies which require broad program support. While the DemonstrationPlots (DPs) showed positive results for introduction of drip irrigation, deep ripping, and other innovative demo activities,farmers were cautious to immediately adopt newpractices such as drip irrigation because of the high associated cost and theirinability to diversify production, given other limiting factors (policy and institutional framework such as mandatory state ordersfor some crops). Better policies, technical (e.g. maintenance of drip systems) and financial support (including access to long termlending) can facilitate and enhance uptake.In addition to engineering solutions,development of sustainable water and irrigation management systems for addressing associated land quality and drainage problemswill require better institutional arrangement including establishment and empowermentof local water user associations.This project under its second component aimed to provide support for institutional strengthening of publicinstitutions and private farmers organizations involved in water management and utilization. Institutional issues (includingstructural, legal and organizational) related to the functioning of the Water Users Associations (WUAs) were not however directlyaddressed. The planned technical assistance for drafting a new Water Code and the legislation and regulations related to WUAestablishment and operations, was not financed by the project as this was supported through UNDP. Once the legislation process iscompleted, the proposed Phase II project can benefit from greater attention to the implementation ofthis new code.
P110538 | Ferghana Valley Water Resources Management Phase-I Project | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Sustainable Development | Water | IDA | IPF | 2010 | 2017 | 2019 | PPAR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/673121555683514715/text/Uzbekistan-Irrigation-and-Drainage-Interventions-to-Support-the-Agriculture-Sector.txt | http://documents.worldbank.org/curated/en/673121555683514715/pdf/Uzbekistan-Irrigation-and-Drainage-Interventions-to-Support-the-Agriculture-Sector.pdf | 5. Common Lessons 5.1 IEG's assessment of FVWRMPâ€I and RESPâ€II generates the following common lessons\. 5.2 Expanding the uptake of waterâ€efficient agricultural technologies requires policies that provide a strong incentive to adopt those technologies. Both projects included activities to promote farmers' application of waterâ€saving technologies. However, such use was limited in FVWRMPâ€I. Despite generally better technology adoption in RESPâ€II at project completion, the sustainability of those practices is at risk given the current policy environment. An improved incentive structure would include policies encouraging adequate water pricing and/or quotas to avoid water overuse by farmers, promoting less waterâ€intensive crop cultivation, and enhancing land tenure security and access to rural finance. 5.3 Water consumer associations can deliver efficient irrigation services when backed by a legal framework that clearly specifies their responsibility and accountability within the entire irrigation service delivery institutional system. The assessment of WCAs in the FVWRMPâ€I and RESPâ€II projects revealed deficiencies because of the lack of specific regulation and accountability measures for WCAs in Uzbekistan. Such regulations are crucial to warrant the effective execution of contractual relationships between WCAs and local irrigation and drainage system authorities, and between WCAs and member farmers. 5.4 Water consumer associations can deliver efficient irrigation services when they have access to continuous and sufficient financial resources. WCAs under FVWRMPâ€I and RESPâ€II suffered from persistently low service fees and insufficient collection rates. One reason for this was their inability to provide the services in delivering irrigation water and maintaining irrigation canals under their responsibilities, as in FVWRMPâ€I (disincentivizing farmers to pay for services not received). However, WCAs that execute their services often face challenges in collecting service fees owed by all of their member farmers. The lack of sufficient financial resources has led WCAs to accumulate significant debt and develop an inability to pay and retain staff, as evidenced under both projects. 5.5 Coordination and consistent approaches across World Bank projects in the same sector are crucial to ensure broad and harmonized institutional capacity building. Both FVWRMPâ€I and RESPâ€II aimed at improving the capacity of WCAs and farmers, but they differed in their design and approach partially because of the availability of parallel donor grant financing and engagement under RESP II. Although training issues were similar in both projects, RESPâ€II also provided WCAs with smallâ€scale equipment to enable them to execute their operational and maintenance needs. Field demonstrations and farmer field schools under RESPâ€ II were designed better than those under FVWRMPâ€I because they were based on regular needs assessments of farmers and close monitoring, leading to a higher uptake of improved and sustainable practices.
P110555 | Energy Emergency Project | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2008 | 2013 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/767801475118268660/text/000012394-20150303150649.txt | http://documents.worldbank.org/curated/en/767801475118268660/pdf/000012394-20150303150649.pdf | The main lessons identified in the ICR are the following:For energy management, both supply side and demand side actions are important. The Government needs to bring Energy tariffs progressively to levels that allow for full cost recovery while encouraging greater efficiency in energy consumption.While emergency recovery assistance projects, by their nature, need to have a limited and specific focus to help address priority needs they also prove effective vehicles for helping the concerned authorities to start putting in place essential longer term policy measures.
P110576 | Education For All-Fast Track Initiative Program | Western and Central Africa | Benin | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2007 | 2012 | 2014 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/140451475073086091/text/000020051-20140625234423.txt | http://documents.worldbank.org/curated/en/140451475073086091/pdf/000020051-20140625234423.pdf | The ICR (p. 22-24) provided several lessons, which IEG has synthesized to the following:Realism is required. Capacity challenges were identified, but were not dealt with before project effectiveness, which had obvious implications during the course of implementation. Designs must be simple and achievable, but they must also address the education sector needs, which are often complex and interrelated. Thus, capacity constraints cannot be overlooked in future projects and simplicity of implementation must be sought in the design.It is possible to design M&E within a pooled funding mechanism from many donors and track project interventions and thus attribution and contribution of FTI resources to attainment of the objective. Indicators were developed, which were a subset of the larger SWAP program indicators. This allowed the Bank to commit to pooled funding and still undertake its evaluation obligations. Government ownership of the project fluctuated, which adversely impacted implementation. When the planned management structure did not function, the Ministry of Finance put forth an ad-hoc management team that moved the project forward. Future projects will need to identify the roles and responsibilities and formalize the management unit.Focus on building the capacity of systems, not individuals. Given that civil servants rotate between jobs regularly, ongoing training must be put in place. Putting systems in place that are consistently followed by subsequent staff is the way forward. In this project, FTI procedures were new and took time to learn, but helped to rationalize the execution and accountability in the process.
P110588 | Revitalizing the Sudan Gum Arabic Production and Marketing | Eastern and Southern Africa | Sudan | IDA | FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2010 | 2013 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/538621483415420938/text/ICRR-Disclosable-P110588-01-02-2017-1483415409800.txt | http://documents.worldbank.org/curated/en/538621483415420938/pdf/ICRR-Disclosable-P110588-01-02-2017-1483415409800.pdf | The ICR included six lessons. The following are emphasized with some adaptation oflanguage: Addressing policy reformscombined with interventions targeting production, marketingand finance constraints can generate substantial gains for producers. The projects dual focus on sector reform andinterventions designed to address issues around production, marketing and access to finance created a dynamic that allowedproducers organizations to quickly benefit from market liberalization. While all gum arabic producers benefitted from sectorreform, those with additional access to training in production and harvesting, and productive infrastructure, transport andmicrofinance were able to more quickly take advantage of the improved marketing and priceenvironment. Market information systems are better located with organizations directly controlled bybeneficiaries. Having the market information systems anchored within a line ministry has proved challenging in othercountry contexts and appears to have faced similar challenges under this project. Lessons from other countries have shown marketinformation systems should be hosted and managed by the direct beneficiaries who need information and have interest to shareinformation. The need for information should be determined by producers and private operators and they could create their ownassociation to manage the system. The Ministry of Foreign Trademight not have the same needs and interest to access quick andreliable market information.
P110599 | Essential Public Health Functions Programs II Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2011 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/163921559249644801/text/Argentina-AR-Essential-Public-Health-Functions-II.txt | http://documents.worldbank.org/curated/en/163921559249644801/pdf/Argentina-AR-Essential-Public-Health-Functions-II.pdf | The ICR (pp. 29-30) offered several useful lessons, adaptedhere: Consensus-building and collaboration between national- and provincial-level actors can helparticulate strategies and responsibilities of the various levels. This project supported symposia, joint working sessions,seminars, workshops, and field visits that helped build consensus and coordination within the framework of the countrysfederal structure. Project evaluation methodologies require definition during preparation in order to ensure availabilityof appropriate data. In this case, data challenges limited the relevance and utility of the final impactevaluation.IEG offers one additional lesson: Projects with complex,multiple-part objectives require a matching array of outcome indicators. In this case, the development objectives covered 18functional areas across 24 provinces, and the results framework was inadequate to assess achievement comprehensively.
P110614 | Sergipe State Integrated Project: Rural Poverty | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2009 | 2012 | 2014 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/298331474593106200/text/000020051-20140626003106.txt | http://documents.worldbank.org/curated/en/298331474593106200/pdf/000020051-20140626003106.pdf | The following lessons are selected and edited from the ICR (pp.21-22):1. Fomenting community demand without commensurate capacity or resources to filter, approve and finance the resulting proposals may be counter-productive. Local governments need to have credible information on the likely financing to be available as well as the capacity to design messages tailored to targeted groups on both poverty and capacity grounds, drawing on relevant skills to ensure proper analysis and differentiation of proposals according to social or commercial objectives. In the absence of these prerequisites, communities may not be ready to go along with another government program that promises but does not deliver. 2. The sourcing and quality of technical assistance is as important as its financing and needs attention from the earliest stages of project development. Allocating a portion of project/sub-project cost for technical assistance is not sufficient to resolve the fundamental problem of the scarcity and quality of such services in rural areas or the need to build up those services over time. Studies and direct experience, such as that of the Sergipe State Integrated Rural Poverty Project, consistently show that TA quality and quantity are a top priority for rural development stakeholders in mainly rural, relatively low income jurisdictions.3. The design of the monitoring and evaluation framework for a given project must takeinto account the information expected at end-of-project and how the project will obtain it. Starting with a clear understanding of project objectives and their link to the results framework, fewer large scale studies and more issue-targeted analyses should provide evidence on PDO achievement by closing. If certain indicators are unsuitable or unrealistic, adjustments should be addressed as early as possible. Turnover in the Borrowerâ€™s management team requires an intensive effort to help the new group understand and buy into project objectives, the results framework and project methodology and to keep M&E on track.
P110616 | Nile Basin Initiative Institutional Strengthening Project | Other | Africa |  |  | Sustainable Development | Water | RETF | IPF | 2009 | 2013 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/698801468185393096/text/ICRR14816-P110616-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/698801468185393096/pdf/ICRR14816-P110616-Box394823B-PUBLIC.pdf | The ICR (pp. 36-42) identified a number of overarching lessons applicable to (i) Basin engagement The most important are: Institutional strengthening is part of a continuum and requires a long term commitment. Efforts to support the NBI have been ongoing for 13 years. As a regional Basin organization, NBI is still relatively young when compared with other international Basin organizations.It is essential to maintain a platform for Basin-wide dialogue and to continue activities at a technical level during periods of political instability. The project provided core support to the NBI during a critical period (2008) when a new political framework for cooperation was under discussion and in (2010) when political consensus was weak.If the principles of, and the approach to, financial sustainability are defined and agreed at the outset, subsequent disputes and delays can be minimized. This project introduced the concept of â€˜minimum functionalityâ€™ defined as the minimum level of staff, operations and activities required to maintain the basic functioning of the institution. Donor and member states contributions were defined. Strengthening a regional institution is not a straight forward linear process. It requires flexibility to maximize the value of support to meet needs of the institution, particularly when the institution operates within a complex political context.Bank Supervision capacity and corresponding resources need to account for multiple operational locations in regional projects. ISP implementation support required in country staff (procurement and financial management ) as well as supervision visits to all three Centers to individually assess progress and review issues, followed by a joint meeting of the three Centers together to review findings overall and to agree actions. In addition, to brief the PSC, attendance was required at the NileTAC meetings. This was time and resource intensive.
P110618 | TG-Economic Recovery and Governance Grant | Western and Central Africa | Togo | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2008 | 2009 | 2010 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/893221474512546135/text/000020051-20140620073913.txt | http://documents.worldbank.org/curated/en/893221474512546135/pdf/000020051-20140620073913.pdf | The ICR contains good lessons of which two stand out.The continuation of analytical work in countries under stress gives the Bank the opportunity to resume its assistance quickly and effectively, when country circumstances permit.In fragile country situations, it is imperative to focus on those very few reforms which are likely to succeed and are most critical to restoring economic growth.
P110632 | Sichuan Small Towns Development | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2011 | 2017 | 2018 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/451651512426511859/text/ICRR-Disclosable-P110632-12-04-2017-1512426501486.txt | http://documents.worldbank.org/curated/en/451651512426511859/pdf/ICRR-Disclosable-P110632-12-04-2017-1512426501486.pdf | The lessons are taken from the ICR with some modification of language:1 . Sufficient projectmanagement capacity of the Implementing Agencies in relation to the workload needs to be ensured, and overlap of projectimplementation functions need to be minimized. Even for experienced PMOs it may be difficult to manage more than one Bankproject at any given time thus risking implementation delays. Once the PMOs capacity is found not to be commensurate withtheir work load, the Bank should take proactive measures by addressing appropriate authorities to push for added staffing andcapacity strengthening of the PMO. Also, in the case where a capacity constraint is foreseeable, adjustments to the projectpreparation schedule could be considered to minimize the overlap of project implementation functions under one PMO. 2 . Project implementation may be significantly affected by changes in local master plans, therefore risksshould be identified early with appropriate mitigation measures. While local master plan changes are beyond the control ofboth the Bank and the Implementing Agencies, the risk might be foreseeable in some countries (like China) with frequent master planchanges due to escalating urbanization processes. To mitigate the risk, sub-projects should be selected to avoid civil worksthat are likely to be subject to upcoming master plan changes. 3 . The Results Framework should be designedwith clearly defined end target values and annualized targets for both KPIs and IOIs to enable monitoring of project progress on agradual basis. This would make it possible to use the project indicators as a strong tool to inform management of majorbottlenecks and to facilitate decision-making and proactive actions. 4 . A simplified procurement plan cancontribute to timely implementation and completion of a project. Entering in to large-scale contracts could result infewer number of contracts, efficient competitiveness and potential for loan savings. 5 . When landacquisition or resettlement delays are foreseeable, early and proactive actions should be undertaken well in advance of the projectclosing date. Bank-financed project resettlement schedules need to be coordinated well with local resettlement schemes incases where the Bank supported projects resettlement schedules depend upon the schedules of larger domestic or nationalresettlement programs, to ensure that project resettlements are not delayed due to delays in the local resettlement scheme.
P110635 | Aceh-Nias Livelihoods and Economic Development Program (LEDP) | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2011 | 2013 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/422511475113052201/text/000180307-20150108102812.txt | http://documents.worldbank.org/curated/en/422511475113052201/pdf/000180307-20150108102812.pdf | A lesson noted by the MDF secretariat and the ICR was that capacity building takes time and can conflict with the urgency that a post-disaster response requires. The LEDP two year implementation time limit was determined by the closing date of the MDF and a two-year duration was too tight to assess the project outcomes.A two year implementation period was also too short for a full assessment of the project outcomes, several of which would not be evident by the completion date so soon after project start up.In a fragile post-disaster environment, where there is inadequate local capacity, implementation by outside consultants can ensure a swift roll out of the project. Under the original design LEDP activities should, ideally, have been implemented by the Nias district authorities as part of their mandate of providing agricultural extension services. However, the districts could not have addressed the post-disaster needs in the tight time-line because of their capacity and resource constraints. Despite the low capacity of farmer groups, targeted block grants to them for improving productivity proved to be a successful tool. When properly targeted they responded to the group's needs and could finance capacity building activities that allowed considerable learning by doing. Proposals financed by the grants for composting, using biological pesticides, raising of pigs and hens, and vegetable planting were financially successful. In Nias the grants also helped diversify farmer's livelihood options and improve communities' resilience to future disasters through enhancing food security.
P110643 | PROGRAMMATIC ELECTRICITY SECTOR DEVELOPMENT POLICY LOAN | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2009 | 2010 | 2016 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/466851468185965896/text/ICRR14819-P110643-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/466851468185965896/pdf/ICRR14819-P110643-Box394823B-PUBLIC.pdf | Please see the detailed PPAR evaluation carried out by IEG in parallel for more information.
P110643 | PROGRAMMATIC ELECTRICITY SECTOR DEVELOPMENT POLICY LOAN | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2009 | 2010 | 2016 | PPAR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/833321468189848942/text/99322-PPAR-P110643-P117651-P121651-SecM2015-0300-Box393222B-OUO-9.txt | http://documents.worldbank.org/curated/en/833321468189848942/pdf/99322-PPAR-P110643-P117651-P121651-SecM2015-0300-Box393222B-OUO-9.pdf | 6. Lessons 6.1 The Bank can maximize its development impact by concentrating its strategic engagement including its lending and advisory support in sectors with track records of success. Even in large middle income countries, the Bank can sometimes maximize its impact by engaging in only a few sectors with heavy concentration of support, rather than trying to cover all sectors but being unable to sustain continuous engagement. Turkey chooses to engage with Bank in only a few sectors, based on track records of success in those sectors. The long term engagement of the Bank in the electricity has helped to build a critical mass of operations that allows for significant locally based expertise (multiple sector experts in the Bank's Turkey country office), relationships of trust with key stakeholders, and use of a range of instruments (including investment lending, analytic work, and policy lending) which have relative advantages in supporting particular sub-objectives. 6.2 A well-designed programmatic DPL can be a key instrument in the Bank's long-term engagement. The DPL instrument can leverage the Bank's strengths on technical advice, convening power, and credibility to help support sector reforms that can have substantial impacts. In this DPL series, the electricity sector reforms had a strong design and so were successful in supporting the government's goals of increasing private sector investment in electricity generation. In contrast, the design of the environmental pillar was less well designed and so the DPL provided little additional impact relative to a without-operation counterfactual. 6.3 Prior actions should focus selectively on those reforms that are critical to achieving project objectives but are difficult to undertake because of political or institutional resistance. These are the cases where the DPL's ability to apply some pressure can have an additional impact. In this operation, prior actions on electricity tariff reform, cost-based electricity pricing, and distribution company privatization important effects. 6.4 Prior actions should also ensure that they are additional to what would occur in the absence of the DPL operation. A DPL is unlikely to lead to implementation of major government policies that would not have otherwise occurred, especially in large middleincome countries; effective policy changes require a high degree of government ownership. But a DPL can help governments to increase the pace of reforms and their technical quality if the existence of a prior action or trigger is a significant motivating factor. In this operation, many of the environmental policy reforms were motivated primarily by engagement with the EU rather than the Bank and by a desire for EU harmonization to support potential accession, and so the existence of Bank DPL triggers had little additional impact. If a DPL is used primarily to establish a policy dialog rather than to achieve substantial development results through the prior actions then it may have little impact. 6.5 DPLs can achieve good outcomes when they serve as the culmination of a process of engagement, as in the electricity sector in Turkey. With sufficient background work, DPLs can have significant heavy policy actions from the first operation. This increases the impact, and reduces the risk of failing to achieve positive results should the planned programmatic series not be completed. DPLs may not work as well if used as the initial point of engagement for a sector, as in the environmental aspects of this operation. Hopes that policy dialog through a DPL will then lead to a pipeline of follow-up projects may not eventuate. 6.6 A comprehensive yet well integrated set of market reforms can provide credible signals and incentives to private investors. A wide set of market reforms can provide credible signal to investors; combined program of price reforms, market development, incentives for RE, privatization encourage large scale investment. The order of reforms can be important in determining successful\. privatization can be more effective if investors are confident that there will be clear market demand. 6.7 Changing laws and regulations may not have much impact on environmental outcomes when environmental management agencies are weak and lack implementation and enforcement capacity. In these cases a DPL may not be the most effective instrument for achieving environmental goals. 6.8 A Bank DPL may have little additional impact if the design does not fully incorporate the existing political and institutional motivations. In this case, the primary motivation of the government for many environmental reforms was on EU harmonization, and the Bank's DPL added relatively little to this effort. The Bank may have had more impact if it had covered environmental issues not already covered by the EU harmonization process.
P110644 | Afghanistan Financial Sector Strengthening Project | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2009 | 2014 | 2015 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/857671467992460565/text/ICRR14780-P110644-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/857671467992460565/pdf/ICRR14780-P110644-Box393191B-PUBLIC.pdf | The ICR (p. 22) identifies several valuable lessons, including:In conflict-countries with a fragile security situation, collaboration between the Bankâ€™s task team and other Bank teams working on the country, learning about project implementation challenges can have a positive impact on project outcomes. At the time of appraisal the Bank was implementing twelve different projects in Afghanistan of which seven had zero disbursement after two years of implementation. This could have been an important indication that a wide range of robust mitigation measures were necessary before project implementation even started.A poor security situation can have a negative impact on project implementation if mitigation measures have not been identified in advance. This project experienced significant difficulties in hiring international consultants for capacity building within the DAB due to security concerns. However, the project design did not include any alternatives.A lesson added by IEG:Candid performance reporting allows the Bank to take timely corrective actions. In this project, implementation progress was rated Moderately Satisfactory between February 2011 and June 2013, even though the project experienced significant challenges and had only disbursed 20% of its grant proceeds.
P110661 | Sustainable Management and Biodiversity Conservation of the Lake Aibi Basin | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2011 | 2016 | 2017 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/809151483124789344/text/ICRR-Disclosable-P110661-12-30-2016-1483124770563.txt | http://documents.worldbank.org/curated/en/809151483124789344/pdf/ICRR-Disclosable-P110661-12-30-2016-1483124770563.pdf | Among the lessons drawn by the ICR, the following are of more general relevance:. The directparticipation of local government officials in support of projectobjectives and activitiesis likely to improve itseffectiveness.In the presentcase the drafting of key decrees and regulations needed local ownership to beacceptable. Strong beneficiary participation is also a key to project success. As an example, the ICR(para. 109, pg. 24) refers to the initial actions of the Ethnic Minorities Development Plan and Process Framework which providedtraining and follow-up consultations to local officials, farmers, and herders that were reportedly essential to ensure adequateimplementation of this plan. Where local institutional capacity is poor, ensureup-front training of localmanagement staff with regards to Bank requirements and procedures for procurement and financial management, etc.issufficient to address significant weaknesses and/or lack of prior familiarity. In some cases, there should be follow-up with morehands-onassistance by the Bankto guaranteeadequate learning bydoing and to helpavoid unnecessary implementation delays.An important lesson for this type ofoperation should also behighlighted:4. Protected area projects should be appraised within the larger environmental context. Asthe main threats (e.g., uncontrolled grazing and water use upstream) to the ecological integrity and biodiversity of theproject wetland came from areas outside the protected area (in this casea Natural Wetland Reserve) itself, it is important todirectly identify and address these problems by takinga broader landscape management approach rather than focusingexclusively on improved management of the protected area per se
P110679 | ARP/II-Integrated Solid Waste Management | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2008 | 2019 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/979951558014277395/text/Azerbaijan-ARP-II-INTEGRATD-SOLID-WASTE-MGT.txt | http://documents.worldbank.org/curated/en/979951558014277395/pdf/Azerbaijan-ARP-II-INTEGRATD-SOLID-WASTE-MGT.pdf | IEG selected three lessons from the ICR, with some adaptation of thelanguage:(1)Broadening solid waste management dialogue beyond environmentalissuesto financial sustainability allows forholistic sector engagement. This project was initiallydriven by environmental issues. However, by broadening the dialogue over time to include financial sustainability, the Bank teamwas able to support the Government in thinking beyond the waste sector technically. The dialogue and technical support on financialsustainability led to a more holistic engagement in terms of policy, planning and strategy, institutional aspects, technicaldesign, environmental and socialaspects.(2) Working with waste pickers beyond resettlementand compensation can lead to safer and secure livelihoods. In addition to physical resettlement and compensation through aspecial state agency, the project developed a comprehensive livelihood restoration plan which included options for the wastepickers and families residing by the site. The options included apartments in Baku for those being relocated from the Balakhanisite and full-time employment with benefits at the materials recovery facility for those affected, in addition to trainings andsafer, more secure conditions at the Balakhani Landfill.(3) Revamping of the solid waste managementsector takes time. With the Government strong commitment and support, the approved national solid waste managementstrategy, capacity building and infrastructure investments, the experience of this project shows that it takes time to develop andsustain the solid waste management sector.
P110679 | ARP/II-Integrated Solid Waste Management | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2008 | 2019 | 2022 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/873271633364626952/text/Azerbaijan-ARP-II-Integrated-Solid-Waste-Management-Project.txt | http://documents.worldbank.org/curated/en/873271633364626952/pdf/Azerbaijan-ARP-II-Integrated-Solid-Waste-Management-Project.pdf | 3. Lessons 3.1 Significant spending on modern waste facilities alone is not sufficient to ensure an effective MSW disposal system. Nearly 50 percent of the waste collected in Greater Baku fails to reach the authorized treatment and disposal facilities (the Balakhani sanitary landfill, upgraded under the World Bank project) and the materials recovery and waste-to-energy facilities (built by the government outside the project scope). Despite the success in improving waste collection under the project, a significant proportion of the collected waste is dumped informally. Continued illegal dumping in Greater Baku undermines the efficiency for a large share of waste to be processed, treated, or recycled. The treatment and disposal facilities are operating at half capacity and entail high capital and operating costs. Lack of appropriate financial and institutional incentives to deliver waste to treatment and disposal, ineffective enforcement, and weak accountability can undermine the effectiveness of the entire chain, from waste collection and transportation to final disposal. Solutions to integrate the interrelated processes in the SWM chain are critical. 3.2 Closing illegal dumps is likely to be ineffective without complementary measures to strengthen institutional accountability and achieve behavior change. Cleaning up dump sites requires a holistic approach that involves addressing both causes that created dump sites in the first place and promoting behavioral change. Closing illegal dump sites did not eliminate the practice of waste dumping by many communities, and uncontrolled disposal continues in the peri-urban areas of Baku. These unsustainable practices generate continuous contamination of water, soil, and air and pose health risks to residents. The government still needs to find ways to provide incentives for transporting waste to the authorized treatment and disposal facilities. International experience also highlights the importance of public awareness and outreach in proper waste disposal to help eradicate illegal dumping. 3.3 It is important to think through the sequencing of sector interventions in unreformed sectors to prioritize interventions that ensure a minimum threshold of viability and reforms that may enable meaningful progress. When this investment project started, it correctly prioritized the sector diagnostics and carried out basic critical investments to address the most immediate environmental concerns. That was highly positive. Beyond that, however, it would have been important to focus further efforts and political leverage on key policy and institutional reforms to enable the sector to improve its performance in a sustainable way, most of them already highlighted by the initial diagnostics. Instead, and although still useful, the additional financing of the project focused on physical works related to the modernization of the landfill, missing the opportunity to raise the ambition and tackle those needed reforms to deal with the sector's binding constraints in the Baku metropolitan area. As seen across regions and countries, investment projects tend to be much more effective in delivering the expected results when the sector, at an earlier stage, has gone through a minimum threshold of reforms, which creates an enabling environment to absorb investments with favorable and sustainable development results. Notes 1Municipal solid waste is generated mainly by residential and commercial sources in the country and is classfied in two main categories\. biodegradable and nonbiodegradable. Biodegradable waste is food waste, paper, plants, and wooden fractions, and nonbiodegradable waste is plastics, glass, and metal. Note that construction and demolition waste is not managed within the municipal waste in Azerbaijan. 2The Baku City Executive Authority collected waste fees of $4,711,294 from 1,013,200 residential subscribers (population, not number of households) and 24,600 other customers in 2018. Baku City's population was 2,262,600 in 2018, and 44.8 percent of fee collection was achieved by the Baku Executive Authority. 3 The local executive authorities (LEAs) govern regions, cities, and city districts (rayons). The LEA is an extension of executive power headed by the president. LEAs do not have common representation. The president appoints each head of LEA, who is subordinated to the president through the presidential administration. The Provision on Local Executive Authority, adopted on 16 June 1999, determines the legal status of local state administration in Azerbaijan. In June 2012, the president approved the new regulation that granted additional powers to the LEAs, strengthening their dominant position in Azerbaijan's local affairs. LEAs coordinate the activities of municipalities and territorial divisions of state administration, among other responsibilities. LEAs can be referred to as a local tier of government only nominally because they do not have independence and simply implement the central government's decisions. For more information, visit https\.//portal.cor.europa.eu/divisionpowers/Pages/Azerbaijan.aspx. 4 Municipalities in Azerbaijan were created by law in 1999 and started to operate in 2000 with elected mayors and city councils. The actual transfer of responsibilities and financing has been lagging, however, and the role of municipalities is limited. The municipalities do not yet have adequate authorization under the Law on Industrial and Domestic Wastes or the capacity to participate significantly in the solid waste sector. The current framework leaves municipalities little discretion over a significant portion of the responsibilities granted to them by the Law on the Status of Municipalities in 1999. Funding from state budgets goes directly to the LEAs, which are responsible for submitting proposals to the state rather than municipalities. Municipalities are de facto subordinated to the LEA. No substantial public administration reforms have taken place since Azerbaijan gained its independence in 1991. Neither municipalities nor LEAs can make decisions independently. Because of the lack of finances and political and administrative powers, municipalities cannot decide on local issues. The LEAs cannot make decisions independently and usually consult the central government before making decisions. See https\.//portal.cor.europa.eu/divisionpowers/Pages/Azerbaijan.aspx for more information.5 Currently, there is only one investment project, financed by the European Bank for Reconstruction and Development, to improve solid waste collection services in the city of Ganja, Azerbaijan. The project entails buying new collection vehicles and bins, implementing a smart collection system, and improving maintenance bays and the dump site area. The project's total cost is estimated at up to 10 million euros, to be funded by EBRD on a sovereign loan basis. Ganja is the first city in Azerbaijan to join the EBRD Green Cities Program. As part of this program, EBRD collaborates with cities to identify, prioritize, and implement vital sustainable infrastructure projects.
P110693 | Vietnam New Model University Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2010 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | High | http://documents.worldbank.org/curated/en/099345003162235611/text/Vietnam000VN0New0Model0University.txt | http://documents.worldbank.org/curated/en/099345003162235611/pdf/Vietnam000VN0New0Model0University.pdf | Lessons from the ICR (page 36-37), adapted by IEG: Developing a transnational university model --involving two very different countries -- can require extra time and attention to the issue of differing cultural practices inoperating a higher education institution.In the case of this project, there were complexities given that the Germanand Vietnamesesystems involved different practices with regard to governance, teaching, and research. Although the projectdesign and mitigation measures recognized the complexities of this type of institutional development, it took more time thananticipated to blend the two systems. Bringing inexperienced technical assistance from the very start canhelp tofacilitate smooth implementation ofa complex project.This project, which aimed to createanew state-of-the-art university from scratch,was highly dependenton the involvement of experienced civil engineers,construction managers, and specialists with technical knowledge of research equipment. The VGU staff had limited experience inpurchasing research equipment, and asa result,staff and researchers depended on visiting scholars from Germanuniversities to support the development of technical specifications and capacity development.However, these visits wereshort, whichoften delayed the completion of technical specifications and led to further delays in the procurement ofequipment. Investment in one university institution as a demonstration model can be a successful approach toimpacting the sector, as long as learning and dissemination are embedded in the project design and resultsframework.In the case of this project, key planned outputs included workshops and training sessions with Ministryand higher education officials, and the results framework included an indicator on dissemination activities.
P110752 | Justice Services Improvement Project II | Latin America and Caribbean | Peru | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2011 | 2016 | 2018 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/878751504791067217/text/ICRR-Disclosable-P110752-09-07-2017-1504791028097.txt | http://documents.worldbank.org/curated/en/878751504791067217/pdf/ICRR-Disclosable-P110752-09-07-2017-1504791028097.pdf | This review finds the following lessons from the ICR of key importance, with some rephrasing: There is a need tobalance trade-offs between holistic and more focused approaches to reform. In the case of this project, pilot interventions wereuseful for delivering faster results, but they were not scaled up or communicated to the point where they could influence userperceptions of judicial quality. Complex and evolving judicial reforms need dynamic ME frameworks that are revisedas conditions change. In the case of this project, the restructurings could have provided opportunities to update targets and addnew indicators to better measure achievements. Capacity building may have a limited impact where anticipated reforms arepostponed. In the case of this project the payoff of capacity building will be dependent on future NCPC implementation. Astrong coordination mechanism bringing together key stakeholders can help to maintain policy priorities. In the case of thisproject, the Steering Committee continued and expanded from the previous project, and helped to keep up momentum despite changes inkey leadership positions.
P110762 | Nepal: Peace Support Project | South Asia | Nepal | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2008 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/761201467998769447/text/ICRR14718-P110762-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/761201467998769447/pdf/ICRR14718-P110762-Box393183B-PUBLIC.pdf | The ICR (pp. 17-18) presents a number of lessons as follows: In a high risk and politically sensitive situation, it is critical to be proactive to adjust to the changing environment. Hence the restructuring immediately following Board approval;Conservative planning in terms of outputs is necessary when preparing emergency operations. In this case, overly ambitious objectives with regard to the capacity of a new ministry became an issue.In addition, IEG notes the following lesson:A field-based TTL and project team that are able to closely monitor implementation and communicate with the client in fragile and post-conflict environments can be critical to project outcomes. In the case of Nepal, the Bank's teams based in New Delhi and Kathmandu worked hard to build consensus with both key government representatives and donor staff on the first project restructuring; more frequent visits by the TTL and close coordination continued to be essential in improving project performance as the project moved forward.
P110803 | Post Primary Education and Training Program | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2009 | 2015 | 2015 | ICRR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/439831468187454335/text/ICRR14737-P110803-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/439831468187454335/pdf/ICRR14737-P110803-Box393183B-PUBLIC.pdf | The ICR highlights the following lessons with which IEG agrees:Proper institutional and capacity assessments during preparation and inclusion of a strong capacity development component are essential for projects that mainstream implementation in a decentralized system. This was the first IDA education project to mainstream implementation responsibility into the line agency (MoES) in Uganda and to decentralize certain responsibilities to schools. However, project design failed to include adequate capacity development activities to help ensure relevant MoES departments and school level officials have the capacity to implement the project. Technical assistance strategically integrated with an agency responsible for program implementation can significantly help enhance capacity. Under this project, the lower secondary curriculum review process led by the National Curriculum Development Centre (NCDC) was supported by an international expert team that was fully integrated into the management structure and day to day operations of the NCDC, resulting in strong national ownership of the reform processand enabling effective capacity development. Similarly, the project recruited 4 engineers who were integrated in the Construction Management Unit (CMU) and worked along with the 3 Government engineers to oversee school based civil works; under the overall supervision of the head of the CMU. Their involvement, albeit late during the project implementation cycle significantly helped improve implementation of civil works during the latter part of the project. Ensuring a project is ready for implementation and defining an appropriate implementation time frame are important to ensure effective implementation and achievement of results. Half of the originally approved project duration time was spent completing project preparation resulting in important delays and unnecessary implementation stumbling blocks which got the project off to a bad start. A focus on resolving implementation bottlenecks is important, but should not distract from focus on achievement of outcomes and objectives. Given design shortfalls, the Bank and counterparts had to focus on addressing implementation bottlenecks. However, the focus on these led to a focus on outputs, without timely attention to progress on achievement of outcomes.
P110836 | Tanzania Poverty Reduction Support Credit 10 | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2013 | 2014 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial |  |  | The ICR brings the following lessons, with which the IEG review agrees. A series ofdevelopment policy operations that focuses on a limited, well-researched, jointly designed and monitored reform agenda, is likelytohave more traction than those with broad and dispersed focus. The PRSC 9-11 series focused on two pillars and fivepolicy areas, in contrast to the two preceding it, which encompassed four pillars and a wide range of reform areas. A smaller andsharper focus made it easier to implement and monitor the program and adjust it in a timely manner as the circumstances demandedit, which was instrumental in achieving the outcomes. The move from broad business environment reforms to streamlining processes inselected areas has yielded better outcomes. Narrowing the focus facilitatedconcentrating efforts in fewer areas, but made the program prone to unreachable targets during the duration of the program.The outcome indicator should be achievable both because of the program and as a measure of realism. While theoutcome indicators of the PRSC 9-11 program were clear and well-defined, some of the program targets were set too high (share ofMKUKUTA to reach 100%), or number of signed PPP project at 4). A key reason for over-ambition was drawing the targets from thegovernments long-term development plans and strategies to align them with the governments objectives, but thesetargets were somewhat inappropriate for a short-term program more oriented to the budget cycle.IEGadds the following lesson:The experience of the program shows that inadequate indicators andoutcome targets can affect the assessment of a programs actual development outcome. This suggests that closemonitoring of program results during implementation is as important for program success as monitoring the implementation of theprograms prior actions and triggers.
P110841 | Energy Community of South East Europe APL6 Project - Turkey | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2011 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/534741488328680047/text/ICRR-Disclosable-P110841-02-28-2017-1488328672288.txt | http://documents.worldbank.org/curated/en/534741488328680047/pdf/ICRR-Disclosable-P110841-02-28-2017-1488328672288.pdf | Political commitment and sustained dialogue are critical for market and institutional reform. During theimplementation of the APL 2 and APL 3 projects, concern had emerged that the institutional setup of TEIAS might not be sustainablein the medium to long term.The dialogue at the time of project preparation established a broad agreement about the diagnosisof TEIASs constraints and the need to consider options for increasing TEIASs operational capacity and financialstrength. A program of measures, reflecting relevant international best practices suitably adapted to local conditions, was agreedupon and formed the basis of Government support for the project.Continuity and consistency of the implementationarrangements and the policy dialogue are crucial for the successful execution of the World Banks safeguards policies.The Banks team experienced frequent changes of social safeguards team members and revisions of reportingrequirements. It would have been useful if these issues had been resolved during the appraisal process, or at least implemented bya more unified safeguards team, since these changes required successiveadjustment periods as well as some confusion anddifficulties in the timely collection and reporting of the relevant information.
P110845 | Disaster Risk Mitigation and Adaptation Project | Europe and Central Asia | Albania | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2008 | 2013 | 2015 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/542891474942841249/text/000180307-20150112091944.txt | http://documents.worldbank.org/curated/en/542891474942841249/pdf/000180307-20150112091944.pdf | The following three lessons have been selected from those presented in the ICR, with some adaptation of language, as being of particular importance:If a project is presented to the Board for approval before it is ready for implementation, significant delays are likely to result. In this case, the lack of adequate implementation arrangements, technical specifications and terms of reference for key studies and consultancy services were not in place at the time of Board approval. Such shortcomings have a particularly negative impact when approaches new to the country are introduced, requiring considerable education and buy-in from government officials and other key stakeholders. Dealing with a large number of government ministries and agencies, each with the ability to act autonomously, can lead to serious coordination problems and consequent implementation delays. Such was the case here. Even if all agencies are on board with respect to the projectâ€™s objectives and the activities agreed for their specific component, minor departures from established bureaucratic procedures can still cause major delays. The design of the implementation arrangements led to a demand for strong coordination that proved beyond the capacity of the Borrower. A cautious approach at the beginning of a potentially large and complex program can reduce the risk of failure, while allowing progress at the Borrowerâ€™s chosen pace towards meeting the conditions necessary for larger-scale support in the form of either investment projects or Development Policy Loans. In this case, the project, which was the initial one supporting the program, focused on needed capacity building and reforms to the policy and legal framework. An APL can be an appropriate tool for such an approach.IEG adds the following two lessons: Lack of consistency among key indicator targets presented in the different project documents can make the task of both the implementation and evaluation teams more difficult. In this case, there was inconsistency concerning the key outcome targets between the Financing Agreement and the PAD, and even within the PAD itself (with stronger targets contained in an Annex than those in the main text). The ICR was consequently confused as to whether the January 2012 restructuring had brought about a significant change in the key outcome targets or not.Where other external partners play an important role in ensuring the achievement of at least some of the projectâ€™s objectives, it is important that this role be fully discussed in the appraisal documents and its implications for attribution considered in the ICR. In this case, the PAD does not assess the role of other partners â€“ such as the Italian Civil Protection, the UN International Strategy for Disaster Reduction and World Meteorological Organization -- involved in disaster risk management in Albania. The ICR fully acknowledges their role, especially in helping to sustain the implementation of the DRMAP when the Bank project ran into difficulties. However, the attribution dimension would have benefited from a fuller discussion.
P110849 | Mexico - Climate Change Development Policy Loan | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2008 | 2012 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/888491474586454684/text/000020051-20140625072258.txt | http://documents.worldbank.org/curated/en/888491474586454684/pdf/000020051-20140625072258.pdf | The first two lessons have been adapted from the ICR with some modification. The third is from IEG.1. A Memorandum of Understanding can provide an integrated and flexible approach for the provision of analytical support, technical assistance and training to complement climate change Development Policy Loans.2. Recognizing that many actions, especially with respect to adaptation to climate change in a large and diverse country, are best addressed at the sub-national level, a national government can establish a broad framework and incentives to engage sub-national governments as well as mechanisms to strengthen the capacity of weaker ones.3. A Development Policy Loan requires clearly defined objectives and a logical results framework. In particular the main intended outcome â€“ in this case â€œmainstreamingâ€ -- should be clearly defined and measurable. All outcomes and outputs should be relevant to the Program Objective and have operational definitions with stated baselines and targets, so that achievement can be objectively assessed. Any indicator that can be stated in quantitative terms should have its baseline, target and achievement expressed in those terms.
P110862 | IRAQ: Public Financial Mgmt Reform | Middle East and North Africa | Iraq | IBRD | FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2009 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/830901475115948554/text/000012394-20150309080111.txt | http://documents.worldbank.org/curated/en/830901475115948554/pdf/000012394-20150309080111.pdf | IEG concurs with the following reworded lessons from the ICR: (i) Ownership of the reforms is the prerequisite of any progress in the execution and oversight of any public financial reform program. If you don't have key reformers in the government and an identified constituency supporting the reform agenda throughout the implementation process, there is a risk that PFM reforms will not be initiated and achieved;(ii) Meticulous design concentrated on a few priority and manageable reforms and focus on identifying champions and appropriate constituency are the requirements in the context of a post-conflict country. In the case of this project, the above described approach was not followed and there was late redirection of the project, resulting in limited progress; (iii) Speed, sequencing and phasing of PFM reforms in a post-conflict environment needs to be thought through up-front. This has to be tailored to the context of each country, and requires a deep political economy analysis; (iv) Strategic direction for any specific reform and effective working relationship between international consultant(s) with broad experience and the local consultants who are attuned to the realities on the ground can be an anchor for successful PFM reforms;(v) Finally, in recognition of experimental nature of this type of technical assistance project, there should be adequate time provided for implementation combined with proactive supervision and redirection of the project as needed on the basis of a timely mid-term review.
P110910 | South East Europe and Caucasus Catastrophe Risk Insurance Facility (Serbia and Macedonia) | Europe and Central Asia | Western Balkans |  |  | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2011 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/794641491601577771/text/ICRR-Disclosable-P110910-04-07-2017-1491601563342.txt | http://documents.worldbank.org/curated/en/794641491601577771/pdf/ICRR-Disclosable-P110910-04-07-2017-1491601563342.pdf | The ICR presents the following lessons (slightly edited) based on the operation (ICR, paragraphs 123-127): Awell-functioning catastrophe insurance market in a disaster-prone region is an important tool to mitigate the financial impact ofdisasters. A professionally managed, independent reinsurance company like Europa Reinsurance Facility Limited(Europa RE) enhances trust in a new, innovative, and transformational program and signals freedom from political pressures orinterests. Government policies that make mandatory the use of catastrophe insurance products bolsters demand for theinsurance products Alternative, market-based solutions, like those introduced by Europa RE in the face of reluctance tomake catastrophe insurance mandatory could be a desirable strategy in other region wide programs. For example, based on having alarge farming base (as in FYR Macedonia and Serbia) a reinsurer could develop an Agriculture Yield Index Insurance. Another exampleisdeveloping alternative distribution channels such as mobile telecom service providers for bundled micro insuranceproducts.
P110943 | TG-Community Dev. Project ERL (FY08) | Western and Central Africa | Togo | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2008 | 2014 | 2015 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Moderately Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/416571475116927708/text/000180307-20141203061146.txt | http://documents.worldbank.org/curated/en/416571475116927708/pdf/000180307-20141203061146.pdf | Lesson drawn from the ICRR process:Â· Sustainability of investments may be an inherent risk in community infrastructure projects. While it may not be possible to insure against it, it can be reduced through strong capacity building at community and local authority levels and careful monitoring of the quality of that capacity building. A longer-term programmatic engagement including through a community development fund may be a way to build sustainability. Lessons drawn from the ICR (abridged):Â· Although the rationale for including a cereals production activity was persuasive, its development impact was limited. Benefits might have been greater had this activity been integrated into an ongoing support program to agriculture.
P110978 | Rural Electrification Phase II Project of the Rural Electrification (APL) Program | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2010 | 2015 | 2017 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/206601481320527372/text/ICRR-Disclosable-P110978-12-09-2016-1481320515433.txt | http://documents.worldbank.org/curated/en/206601481320527372/pdf/ICRR-Disclosable-P110978-12-09-2016-1481320515433.pdf | The lessons derived from the implementation experience of this project are consistent with the findings of the WorldBanks 2011 study Lao PDR Power to the People: Twenty Years of National Electrification, which reviewed thehigher-level lessons and the factors underlying the significant progress that was achieved during that period. The main lessonsfrom this project, which update and reinforce those earlier lessons, are as follows (as paraphrased from theICR): The timely, efficient, and effective achievement of electricity access requires prior clarity in plans,targets, institutional framework, financing, and monitoring mechanisms. A workable balance must be achieved between(i) state subsidies, tariffs, and financing policies and (ii) maintaining the commercial viability of the power sector withcost-recovery tariffs. The projects Power to the Poor Program demonstrated that providing low-cost financing andtargeting households without electricity access (in villages that had been previously electrified) can be a simple and effectivemeans to provide grid connections, while also providing significant benefits in terms of social inclusion (especially for women andchildren), health, and income generation. The key success factor in increasing electricity access was the broad-based andlong-term national commitment to electrification, the establishment of the necessary technical codes, and the introduction ofup-to-date technical innovations to lower the cost and accelerate the electrification program. Data on private sectorinvestments need to be updated regularly in order to coordinate grid extension with off-grid electrification and thereby avoidstranded off-grid assets in the event that grid connections arrive earlier than expected. Carefulconsideration is warranted before including financial indicators as PDO outcome indicators or covenants, given (i) thesociopolitical risks associated with the reforms necessary to meet them, especially when tariff adjustments are involved, and (ii)the time required to bring about financial improvement, which often may exceed the life of one project.
P111017 | Bangladesh Padma Multipurpose Bridge Project | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2011 | 2012 | 2014 | ICRR | >=10 million & <25 million |  | Highly Satisfactory | Moderately Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/344871474666143742/text/000020051-20140626120120.txt | http://documents.worldbank.org/curated/en/344871474666143742/pdf/000020051-20140626120120.pdf | The Padma Bridge project showed that for the Bank to remain engaged where poverty is pervasive, it must encourage new ways to minimize risks and promote change in an ingrained culture of corruption. The Bank has since developed an action plan to enhance safeguards to reduce fraud and corruption risks in the Bank-wide program, which intends to redouble efforts to build country systems to manage these risks, and to achieve greater transparency through access to information and greater citizensâ€™ engagement. Long-term strengthening of country systems and capacities is the most sustainable means of managing risks, improving governance and fighting corruption. While most of the Bankâ€™s activities in Bangladesh support both systems and capacity development, the Bankâ€™s post-Padma Action Plan calls for greater effort at strengthening government performance in budget formulation and management as well as public procurement, oversight by parliament and supreme audit institutions, strengthening of banking supervision and payment systems, and decentralized local government systems.It is important that the Bank works more closely with other co-financiers not only in the preparation and implementation of projects, but also in the formulation of its remedies and corrective actions in corruption cases.The use of External Expert Panel to assist the Anti-Corruption Commission introduced a new tool in the Bankâ€™s toolkit to find ways of working with country authorities to tackle fraud and corruption when it is uncovered. Although in this case the outcome of the panelâ€™s work did not lead to a successful resolution to continue with IDA financing, the new mechanism is intended to assist in ensuring a free and fair process that can provide independent expert advice and an outside perspective.
P111034 | Jakarta Urgent Flood Mitigation Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2012 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/645041582041426391/text/Indonesia-Jakarta-Urgent-Flood-Mitigation-Project.txt | http://documents.worldbank.org/curated/en/645041582041426391/pdf/Indonesia-Jakarta-Urgent-Flood-Mitigation-Project.pdf | The ICR presented 7 lessons drawn from this project. Most of them were focused on specific characteristics of this floodmitigation project. Based on these lessons one broad lesson is presented below: Establishing relevant PDOindicators with reliable baselines at project appraisal providethe basis for sound project management as wellasrigorous monitoring and evaluation of project resultsIn this flood mitigation project, the originalPDO indicators were (a) water level of inundated areas; (b) the number of hours of water logging in inundated areas; and (c) theextent of inundated areas. These indicators were acknowledged at appraisal to be vague The PAD stated that Performanceindicators are expected to be reviewedand adjusted as necessary during Mid-Term Review (Annex 1, page 20). Therewere no reliable baselinesbecause they could not be accurately mapped to neighborhood units, and most importantly they wereten years out of date because land subsidence in the project area during those ten years had been far more rapid than anticipatedwith serious consequences for the veracity of old baselines.These shortcomings made the original PDO indicators problematicbecause they provided no measurable or substantive challenge. Indeed it was not until the Mid Term Review that the PDOindicators were amended to: (a) average flood depth; (b) average length of inundation; (c) and number of neighborhoods affected byfloods, which could be attributed to the project and measurable. Nevertheless the challenges of obtaining accurate baselinedata continued. As this review noted There was a lack of well distributed measurements of indicators such as flooddepth and duration.Even with in-stream gauges and water level readings in some areas, data were not properly recorded.Asingle actual observation value was used for multiple kelurahans that had different characteristics (Section9b).The general lesson is that sound appraisal and ME methodology needs, amongother things, tocreate timely and measurable PDO indicators with accurate baselines thatwould contribute to generating reliable data to guideimplementing agencies to track the progress of implementation. The specific lesson from this project is that an investment ingenerating accurate baseline data at the time of appraisal would have improved implementation and MEperformance.
P111061 | Southern Sudan - Water Supply and Sanitation Project | Eastern and Southern Africa | South Sudan | IDA | FCS | Sustainable Development | Water | RETF | IPF | 2010 | 2013 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/592421474940447198/text/000180307-20141203053838.txt | http://documents.worldbank.org/curated/en/592421474940447198/pdf/000180307-20141203053838.pdf | The ICR highlighted a number of lessons, including Political and technical considerations must be closely managed during project design and implementation, and expectations on what a project can realistically deliver clearly accessed and communicated to all stakeholder constituenciesâ€™ right from the outset. Projects in fragile and post-conflict environments are sometimes developed and appraised with limited or incomplete information, and other dynamic conditions, which may create risks to implementation and outcomes. Trade-offs between quality and timeliness of delivering services should be carefully balanced, and project design should be cognizant of the fact that sustainable water and sanitation service delivery requires adequate time to do well, especially in regard to the need for strengthening institutional capacity at the national, state, community, and civil society levels, and elements that require behavioral change such as community-led total sanitation (CLTS). Structures established to operate and maintain facilities to ensure continued service delivery at the local or community level should be provided with ongoing support during the post construction stage, to ensure sustainability.
P111064 | Togo - Financial Sector and Governance Project | Western and Central Africa | Togo | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2009 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/307621498832658516/text/ICRR-Disclosable-P111064-06-30-2017-1498832650583.txt | http://documents.worldbank.org/curated/en/307621498832658516/pdf/ICRR-Disclosable-P111064-06-30-2017-1498832650583.pdf | The ICR (page 40) notes several lessons: Political commitment is key in driving reform. In Togo, the politicalbuy in was strong in the Ministry of Finance but weak in other parts of Government. In addition, there were strong vested interestsopposed to reform of the publically owned banks and reforms in the microfinance sector. The political landscape was alsocomplicated by elections and by social unrest. This project illustrates strongly the need for comprehensive analysis of thepolitical economy of the country when designing the project. The World Bank had very few close relationships with key counterparts.This is a point that the ICR could have emphasized more strongly in the body of the text. Togo remains a difficultenvironment in which to implement reform and more account could have been taken in design and implementation of the fact that thecountry was emerging from a long period of political and economic instability. A similar point was made in the ICRR of the TogoPrivate Sector Development Support project (P122326). The ICR states that the Bank worked closely with the Government toensure a simple design and implementation of reforms. This statement is not borne out, however, by subsequent statements in thelessons learned section of the ICR, where the conclusion is that the scope of the project was overly ambitious and that the PDO wasnot simple nor straightforward. Simplicity of project design with a limited number of objectives would have better suitedthe realities of the limited institutional capacity in Togo. The ICR suggests that the focus should have been on 1 or2 institutions. The ICR could have gone further and suggested that in the difficult political and capacity circumstances, wheregoals are nevertheless ambitious (and urgent given the financial sector fragility), there could perhaps have been a series ofprojects, with subsequent ones depending on the success of the initial ones. While not noted in the ICR, the projectillustrates the need for close attention at the outset to minimize delays in getting the project started. The ICRR of the TogoPrivate Sector Development Support project (P122326), noted similar issues in Togo, where long delays occurred in getting theproject off the ground.
P111074 | IQ: Integrated National Energy Strategy Technical Assistance | Middle East and North Africa | Iraq | IBRD | FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2010 | 2013 | 2015 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/477581475117040924/text/000180307-20141203060306.txt | http://documents.worldbank.org/curated/en/477581475117040924/pdf/000180307-20141203060306.pdf | The lessons cited in the ICR are by and large appropriate and include both generic and specific points: (i) need for a pragmatic approach; (ii) importance of a simple and flexible project design in post conflict countries; (iii) policy dialogue being an integral part of project design and implementation; (iv) success depends on commitment, ownership and quality delivery, including on the consultant side; (v) the importance of pursuing a strategic process which bring together all key stakeholders based on strong coordination mechanisms; and (vi) on the Bank side, recognition that implementation in post-conflict environments can be costly.A complementary lesson emerging from this review is that consolidating procurement into a single lot, as opposed to segmentation of tasks, may result in attracting better quality expertise and also transfer certain risks to the consultant. However, risk of capture due to consolidated procurement needs to be recognized up-front and mitigated throughout implementation.
P111078 | WBG Support for Fiscal Sustainability and Public Financial Management | Middle East and North Africa | West Bank and Gaza |  | FCS | Equitable Growth, Finance and Institutions | Governance | SPF | DPF | 2008 | 2009 | 2010 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/191491474397888349/text/000146597-20140619165631.txt | http://documents.worldbank.org/curated/en/191491474397888349/pdf/000146597-20140619165631.pdf | Four lessons, well covered in the ICR, follow from the evaluation. First, strong borrower ownership at the political and administrative levels are of critical importance. In the case of WB&G, the absence of a functional legislative body facilitated in some sense the implementation of the reform program by a motivated technocratic government. On the other hand, extensive consultations with various stakeholders ensured strong buy-in from all parties. Second, in conflict-affected borrowers heavily dependent on budget support, such as WB&G, progress in institution and capacity building is bound to be a slow and time-consuming process. Objectives need to be realistic, focussed on few critical priorities on the path toward longer-term development goals. Third, World Bank budget support can be critical in leveraging other donors budget support. Fourth, field based task management contributes to improving the quality and effectiveness of Bank support.In addition, complementarity between the DPL program and other Bank lending and AAA, together with close coordination with other donors interventions, substantially increase the probability of success.
P111153 | Tanzania Strategic Cities Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2010 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/594221634919490583/text/Tanzania-TZ-Strategic-Cities-Project.txt | http://documents.worldbank.org/curated/en/594221634919490583/pdf/Tanzania-TZ-Strategic-Cities-Project.pdf | The following lessons are adapted from the ICR:Long-term transformative impact and sustainability of urbandevelopment projects in rapidly growing cities relies on the governments ability to plan and enforce land use regulationsand to secure public land for future infrastructure. Interventions such as demarcation of infrastructure rights of way,identification and protection of environmentally sensitive and hazardous lands, assembly of land would be needed for futureinfrastructure and services (through acquisition or land readjustment), and drastically increasing coverage of neighborhood-levelland use plans may be complicated from a political or social safeguards management point of view.Enhancing ownsource revenue (OSR) collection in local governments requires a deep and robust understanding of the policy environment, currentpractices, and incentive structures surrounding Local Government Authority (LGA) OSR generation. System development andupgrading is an important entry point that can achieve immediately impressive results, as was the case for Local Government RevenueCollection Information System (LGRCIS), but anchoring system improvements in a comprehensive institutional strengthening programthat includes development and operationalization of revenue enhancement strategies through training, hands on support for datacollection, continual ME, and ongoing technical assistance is necessary for cementing and deepening systembenefits.To ensure sustainability of project investments, business plans and operation and maintenance (OM)arrangements of economic infrastructure needs to be prepared upfront. The project experience shows that while mostinfrastructure became operational right after completion, some economic infrastructure such as the two lorry terminals were not putinto operation due to the absence of business plans and associated OM arrangements.
P111155 | Zanzibar Urban Services Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2021 | 2022 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099422104262230225/text/P11115500ae8df0fa084b30ca559a46bc12.txt | http://documents.worldbank.org/curated/en/099422104262230225/pdf/P11115500ae8df0fa084b30ca559a46bc12.pdf | The ICR listed five lessons based on the operations and are slightly edited here for consideration by other teams who maydesigning similar projects in the future: Effective institutional arrangements may require engaging key lineministries atahigh-level steering committee.Early implementing capacity weaknesseswerestrengthened by additional capacity building throughtraining. In this project, the implementing agency was under the Ministryof Finance and Planning (MOFP) and reported directly to itsPrincipal Secretary.Representatives from key line ministriesand municipal councilswere appointed including the Zanzibar Urban Municipal Council, three Pemba Town Councils, Stone TownConservation and Development Authority,and the Department of Urban and Rural Planning. These appointmentsmeantproactive engagement and establishedownership by relevant sectors/agencies.Technical expertise fromthedifferent Ministries, Departments and Agencies (MDAs) and other key stakeholders gave a platformto address technicalchallenges,provided oversight, and regular guidance.The Project Coordination Committee (PCC) was established at thebeginning of the project and was functional throughout implementation.The PCC conducted regular site visits, monitoredquality, and decided on changes to achieve the PDO. Involving representatives from these agencies was proven to be veryuseful for decision making, capacity building, and ownership of the project. Challenges to complyingwith environmental and social safeguards are best met with timely responses. In this project,the drainage works werelocated in densely populated urban areas.Occupational and public safety risks were high. Involuntary resettlement wasunavoidable. Complex working environments and weak safeguards monitoring by the project team early on led to work sites safetyissueshatwere later resolved with effective preventive and corrective actions. For example, the seawall was no morethan 10 meters from the Sultans Palace, an iconic heritage building of Zanzibar.Vibration at the work site coulddamage the building. The contractorsuse of small hand drills instead of large drilling machines to prevent any potentialdamages was strictly enforced. STCDA and other authorities handled three chance archaeologicalfindseffectively. Creditproceeds may be used to meet unforeseen increasingresettlement costs. In this project, IDA proceeds was allowed to be used to meet rising resettlement costsbecauseappraisal estimateswere not informed by detailed design or feasibility studies. The lack of government fundingto finance the compensation for project affected persons, was met by using proceeds of the credit, not normally usedinBank-financed projects. Supervision was strengthened with extra oversight andinstitutional arrangements for RAPimplementation.Detailed designs and feasibility studies at project preparation may best inform RAP costs.Experience inthe region suggests that when detailed RAP costs are established during project preparation, it is often possible to reduce coststhrough design reviews during implementation. Effective stakeholder engagement processes mayhelpaddressOM needs of infrastructure assets. In this project,an OM plan was preparedand discussed together with all stakeholders including the ZUMC, MOFP, and community representatives before the landfill wasconstructed to properly and sustainablyoperatethe Kibele landfill. Adopting anurban designmay help create and avoid encroachment of public space.In this project, an urban design approachwas adopted to prevent the encroachment of and informal uses of public rights-of-way. After the drainage system investment wascompleted, an urban design approach with public space enhancement was proposed and implemented. In the Mizingani seawall project,after the contractors camp took over an area previously used for unorganized street parking, the space was securedandtransformed to serve as a small public park around a historic tree, linked to the seawall, andprevented the returnand encroachment of an informal car park.
P111163 | Xinjiang Turfan Water Conservation Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2010 | 2017 | 2018 | ICRR | >=100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/503161511361496851/text/ICRR-Disclosable-P111163-11-22-2017-1511361483560.txt | http://documents.worldbank.org/curated/en/503161511361496851/pdf/ICRR-Disclosable-P111163-11-22-2017-1511361483560.pdf | The ICR (p. 27-29) provides several useful lessons learned including the following:1 . Addressing the supplyand demand side of water management is critical for achieving a sustainable outcome: In this project activities includedconstructing upstream reservoirs for water storage and introducing consumption caps, water allocations, and ET monitoringdown-stream but at the same time also extending services for farmers to increase incomes. This allowed for saving water withoutnegative impact on farmers income. Also, this project showed that a combination of strict caps on water consumption incombination modern irrigation technologies can result in water savings. In addition, changing the legal definitions of water rightsto be based on permitted water-consumption instead of the traditional withdrawal-based water rights, was critical for achieving theproject outcomes.2 . Implementing the knowledge management system during project implementation allows for bettertesting the system and training staff: In this project the office system, which was to be used in the water bureausdaily activities, only became operational at the end of project closing. This did not allow for starting to use the system slowlyand identify any questions by staff, while technical assistance for the project is still ongoing. Also, project disseminationmaterial, which was produced to share lessons learned about the project, was only produced at the end of the project, not allowingclose guidance by Bank experts.3. Aligning the PDO with local development objectives is critical for receivingpolitical support: This project benefitted from high level support by local and provincial governments. For example, whenit was clear that modern irrigation technology alone would not be sufficient to save much water and that the total irrigation areamust be reduced, the party secretary supported these efforts. This support was critical since much of the land was owned bystate-owned enterprises.4. Implementing remote sensing (RS) technology is a sustainable approach to monitoringwater consumption and combating water scarcity. This project showed that the use of RS technology allowed fordetailed monitoring and water accounting at the river basin level at a relatively low cost. The RS technology measured the actualuse of water in irrigated agriculture, providing local water managers with data to control water use via water rights, water userassociations, and penalty fees for overuse.5. Integrating the ET approach and practices intodifferent levels of water institutions is critical for ensuring the sustainability of project outcomes. In this project,ET management concepts and practices such as the Office Application and Information System was implemented in the offices of theTurpan Municipal Water Bureau. This system integrated basin-level water accounting, dynamic irrigation planning tools, and ETmonitoring databases allowing to monitor water consumption, manage land reclamation, close wells, review water rights permits, andmake basin-level decisions more effectively.
P111164 | Vietnam Poverty Reduction Support Credit 8 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2009 | 2010 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/469551474895234248/text/000020051-20140626112326.txt | http://documents.worldbank.org/curated/en/469551474895234248/pdf/000020051-20140626112326.pdf | Lessons from the ICR are supported, in particular that donor coordination can strengthen the policy dialogue and deliver benefits to the client. A PRSC series can serve as an effective framework for policy dialogue and interactions between the government and donors. The benefits can be fundamental and manifold, as supported by a number of outside evaluations. PRSCs can be the â€œone-stop shopâ€ of the policy dialogue, supplemented by sector/thematic DPLs as reform dialogue deepens, and hence raised to a more senior level of government attention than any individual sector effort would have. The role of co-financiers under the PRSC can evolve over time from providers of financing to partners engaged in the preparation of the operations and the policy dialogue with the government. Information flows from the government will expand as trust with the Bank and other partners deepens. This coordination also greatly reduces the transaction costs for the government ministries and agencies (ICR, p. 34).Another lesson is that an incomplete causal chain can lead to difficulty in evaluating the effectiveness of an operation or series in achieving its objectives. When prior actions and targets are directly linked to target outcomes from a PRSC series, there will be a clearer link between the series and the achievement of objectives.Other lessons include the importance of continuity in task team leader (TTL) -- PRSCs 7-10 had the same TTL, and the value of combining policy operations with parallel technical assistance to allow for necessary capacity building. When a government has a sound medium term framework and the program supported by a policy operation is ambitious and broad, a longer series may offer the opportunity to achieve results sought and the flexibility to redirect actions based on experience. In addition, countries facing particularly difficult sectoral challenges should consider a sectoral policy operation to supplement a broader policy operation, allowing more extensive consideration and support to the most difficult issues.
P111164 | Vietnam Poverty Reduction Support Credit 8 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2009 | 2010 | 2015 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/721331467986245693/text/96203-PPAR-REVISED-PUBLIC-VIETNAM-PPAR-FINAL.txt | http://documents.worldbank.org/curated/en/721331467986245693/pdf/96203-PPAR-REVISED-PUBLIC-VIETNAM-PPAR-FINAL.pdf | 6. Conclusions and Lessons Learnt Conclusions 6.1 This review presented an overview of Vietnam's economic and social performance. It assessed the extent to which World Bank DPOs during 2007-12 contributed to its achievements and their sustainability. The main conclusion that emerges from the historical overview is that the country's growth performance during the 1990s and until the mid-2000s was very strong. Effective poverty alleviation also took place during that period, and has been sustained since. This was thanks to transformative measures (especially land reform, enterprise reform and WTO accession) that were taken by Government during the first half of the 2000s (in turn building on earlier reforms) with substantial development partner advice and support, which was generally led by the Bank. 6.2 However, during the period under review (2006-2013) the next generation of transformative reforms (notably as highlighted in the 2007 and 2009 VDRs) were either postponed or diluted, and were thus less effective. Areas such as SOE and financial sector reform, more efficient public investments, anti-corruption, and more effective environmental policies, received insufficient attention. Over the same period, Vietnam departed from the prudent macro-fiscal stance that characterized it in the 1990s early 2000s. 6.3 Past reforms continue to drive strong FDI and buoyant exports. Vietnam can build on these strengths to avoid further loss of growth momentum. This could be based on the implementation select transformative reforms aimed at strengthening the role of the private sector, facilitating the emergence of mediumto large domestic enterprises, and sustainably expanding infrastructure in an efficient manner. The progressive elimination of the stock of contingent liabilities and reducing other risks to the sustainability of fiscal policy would create a more stable macroeconomic environment. One of Vietnam's strengths lies in its social compact, the main elements of which should be maintained, while progressively evolving towards a less paternalistic approach based on stakeholder empowerment. 6.4 The Bank and other development partners can help the country address these priorities through more selective budget support instruments. This is indeed envisaged in the Country Partnership Strategy (2012-16). The 2016-2020 SEDP also provides an opportunity to generate political consensus around these issues in the context of an increasingly complex economy. 6.5 The Bank should be more willing to cease supporting programs should they become so weakened as to make it likely that key objectives would not be achieved. Technical and policy dialogue would be maintained. In this context, high caliber knowledge products will need to continue being prepared, and the relationship of trust that supports frank dialogue with Government needs to be reinforced. Harmonization with all key stakeholders, external and internal, will be important. Strong commitment to deeper reforms would help to sustain Vietnam's economic performance while addressing the challenges of an increasingly complex, middle-income economy, and deepening global integration. Lessons from the Bank's macroeconomic engagement through DPOs. 6.6 The model of the Bank's engagement in macroeconomic and fiscal policies through DPOs in Vietnam since 2007 has not been effective. An important finding emerging from this PPAR is that, while diagnosis of macroeconomic risks was adequate, this was not reflected in program design, despite a highly volatile environment exacerbated by sub-optimal policy choices. This situation was, moreover, aggravated by the lack of an IMF program and the relative weakness of macroeconomic policy dialogue between the Government and the Bretton Woods Institutions. The Bank may have been exposed to reputational risks if its policy lending had been seen as a de-facto endorsement of controversial macro policies. DPOs following those reviewed in this PPAR are still not underpinned by relevant macro policy content, although macroeconomic risks persist. This indicates that the lessons learned during the 2007-2013 period do not appear to have been fully learned. 6.7 Macroeconomic dialogue could advantageously be consolidated in a presence of multiple parallel DPOs. The fragmentation of policy lending into multiple DPOs implemented in parallel in Vietnam during the period of increased macro risks might have weakened Bank's focus on macro framework and even resulted in inconsistencies in policy dialogue. The Bank should have avoided situations when preparation of one operation is held back for concerns over the macro-framework while a parallel DPO is approved and disbursed in the same macro environment. To avoid the repetition of such a situation, there should be a unique and consistent approach towards assessing the adequacy of macroeconomic underpinning of DPOs. When substantial risks are present, policies underpinning the most suitable, in terms of scope and objectives, budget support operation should be reoriented to alleviate them. 6.8 Combining the objectives of external financing for crisis response and promotion of long-standing institutional reforms may not be effective in cases where risks to nonimplementation of reforms are high. The Bank's experience with the Vietnam PIR series indicates that, when financing needs are urgent, it will find itself under pressure to go ahead with disbursements even if the reform implementation is not satisfactory. Crisis response operations should first of all focus on ensuring the sustainability of macro and fiscal framework, and should be underpinned by critical macro, fiscal and structural actions, especially in cases when the IMF is not present operationally. Lessons Learnt â€“ Results and M&E Framework 6.9 Wide-ranging DPOs need to be based on stronger and better quality actions. The importance of each individual prior action increases in multi-sectoral operations with many policy areas because of the implicit limit on the number of total prior actions for operational purposes. If in a series of five operations, for example, each policy area can have a maximum of two or three prior actions in the course of five to six years it is important to ensure that those prior actions have sufficient institutional depth, relevance and criticality. Related to this, in multi-sectoral complex operations there might be no substitutability between the prior actions of unrelated policy areas, which means that weaknesses of prior actions in one sector cannot be offset by relevant and critical prior actions in another sector. 6.10 Lack of focus on and delays in implement essential triggers can weaken the program. In terms of indicative triggers, the Bank has flexibility and discretion in its treatment of the triggers. The transition from Bank's former conditionality framework to the model applied in the series reviewed in this PPAR puts a high premium on sequencing the reforms and ensuring continuity, thus giving considerable significance to the role of triggers for the operations and the overall reform program. Dropping a trigger should be considered as an exceptional event, rather than a regular occurrence, permissible only if the risks to nonimplementation of reforms are duly addressed. 6.11 Partially met triggers require greater attention. Sometimes partially met triggers become prior actions even though they may be less relevant and critical than the originally proposed action. The dilution of content may be to such an extent that these actions would probably not have been considered as prior actions if proposed at the outset. The Bank should pay special attention to possible risks in adopting partially met triggers as prior actions, especially when there is not any realistic expectation that the full original reform will not implemented in a reasonable timetable thereafter. 6.12 It is crucial to have a strong knowledge base for upstream design of reforms and parallel technical assistance to support their implementation. Development partners were willing to put significant resources in these areas, in order to complement Bank financing and dialogue (Vietnam, prefers not to borrow, even on concessional terms, for TA). Selectivity is therefore needed to ensure that the most pressing needs are addressed. Should unmet demand remain, this may be tackled through complementary Bank TA operations, for instance in support of reform teams.151 However, these operations need to be carefully designed in order to match the timing and sequencing needs of DPOs (an issue that arose in the case of P135), and to ensure that the bulk of resources is allocated to meet specific implementation requirements, as opposed to general capacity building (such as purchase of vehicles and equipment, and training). Furthermore, this approach calls for outsourcing knowledge generation and advice to an appropriate mix of experts, both national and international, who can accompany the reforms in medium-term.152 6.13 The design and implementation of M&E for DPOs remains a challenge, and needs to be reconsidered each time a new operation is considered within a series. The PD.153 for the second PIR mentions a lesson learnt elsewhere, whereby an effective M&E mechanism should not just be based on administrative reporting. However, both the PIR and the PRSC suffer from this issue as M&E is not used as a mechanism for feedback and readjustment of activities to improve impact. The P135 is more successful in this area 151 FIAS 2008\. Reform Teams How the Most Successful Reformers Organized Themselves Reform teams consist of a small group of national experts who together with world-class expertise help Governments implement ambitious reforms. 152 In order to achieve such continuity, the experts' contracts may be based on a retainer model. Sorter procurement may also be achieved through framework contracts, whereby a short-list of competitively prequalified consortia/firms expected activities are called upon to provide experts within short delays of 2-4 weeks. The EU has successfully implemented this approach. 153 para. 71 124 because the mid-term review provided a venue for reassessing the implementation of the program. Even there, the change in PRSC indicators took place only for the last operation, although it had become clear much earlier that the relaxation of policy actions required an adjustment in indicators and goals. In both the PRSC and the PIR series there is a disconnect between development objectives, actions and indicators. In the case of the PRSC, there was a logical chain between objectives and indicators, but it is hard to see how some of the reforms would lead to the intended results (the attribution issue). The issue with the PIR is that while there is strong relationship between the reforms and results, their logical link to the development objectives is weak, especially after key reforms were dropped. Lessons Learnt â€“ Bank Approach 6.14 There is a need to reexamine how the Bank approaches sectoral DPOs and how this instrument is differentiated from investment lending. In Vietnam, the distinction between DPOs and investment loans has become blurred, especially with the practice of earmarking funding for the sector the programs support. It can be argued that the four sectoral DPOs might have been best supported by SWAPs and investment lending. The advantage of DPOs is that they disburse rapidly, support to the consolidate budget, and in practice promotes the use of national fiduciary and safeguards systems. However, this approach limits Bank inputs (say on a key study) on the ultimate use of the resources and their underlying processes. To avoid sharp trade-offs that may discourage the use of the most appropriate lending instrument, it seems that in the case of investment lending, it may be desirable to experiment, at least on pilot basis, with further harmonization/convergence between Bank fiduciary and safeguard procedures and national ones. 6.15 The Bank and other development partners should be willing to walk away from an unproductive policy dialogue and withdraw their support of low impact reforms. The delays in P135 (second operation), the second PIR operation and PRSC 10 appear to have been caused by concerns with the quality of the program. In the case of P135, the mid-term review largely addressed the main concerns. However, the last operations in both PIR and PRSC series cannot be readily justified by the contribution to objectives of the weak reform they supported. 6.16 The Bank's recent guideline that suggest to limit the number of operations in a series to three constitutes an appropriate measure. Long-term DPO series need to be kept relevant by maintaining a high level of ambition with respect to the reforms they support. As evidenced by the second PRSC series, a longer-term approach may be hard to sustain. 6.17 Knowledge generated and/or embodied in Bank operations should be properly documented and made public. Bank disclosure policy call for documents it produces being made public, unless classified as confidential. Furthermore, to the extent possible, documents on which policies are based should be easily identifiable and retrieved. In order to preserve knowledge and improve transparency, PDs should properly refer to studies (in some cases the title cited was incorrect) and provide URL links. There is also a question whether disclosure policy is strictly respected (e.g., some energy studies do not appear to have been made public). 125 6.18 It is difficult to evaluate the performance of DPOs in Vietnam without the benefit of a clear reference on what constitutes the norm. This review identifies strengths and weaknesses in the Vietnam DPOs by referencing their own internal logic. However, it is unable to systematically address questions such as how did the Vietnam second PRSC series compared to other PRSCs in terms of ambition, design, results etc. This may result in inconsistency in ratings across countries and projects (ratings contain a subjective element based on the skills, experience and perception of the evaluation team, as well other factors). This issue seems to argue in favor of a new meta-evaluation154 of completed PPARs on similar DPOs, with lessons learnt and recommendations on a more consistent cross-country approach to be reflected in future individual operation evaluations and/or PPARs. Specific Lessons Learnt from P135 6.19 Budget support may not be the best instrument for financing a sector investment program. While a budgetary support operation for a CDD-type program turned out to be moderately satisfactory in the case of Vietnam, the Bank and other development partners had taken a considerable risk. For most countries, it would be highly advisable that the training, at least of the critical personnel (which in a highly decentralized program means a very large number of people), would be done in advance and that an M&E system were in place at the start of the program. There was much retro-fitting under the P135 series that could have been avoided. 6.20 The state of decentralization needs to be fully factored into the design and implementation of targeted poverty programs. Decentralization of government institutions and introducing greater participation at the commune and village levels was an objective of the program as a tool to empower the targeted communities. Various monitoring indicators were used to measure progress on this front. But they did not provide an idea of what would have been good practice in terms of an optimal level of decentralization and participation given the stage of development. An alternative approach could have been to select a control group of provinces that had been decentralizing on their own and could serve as a comparison group for the provinces attempting to develop decentralized structures under P135. That could have enabled the selection of a group of indicators to be used for measuring success before the start of the operation 6.21 Production support to poor communities needs to be tailor-made and well thought through. Much was made of expanding the production component of the program. But the targeted communities were seriously underdeveloped for good reasons. They were remote, mostly mountainous, often forested, and inhabited by people who have eked out livings in these places for centuries. Such places are notoriously difficult to develop and there are few success stories around the world to give guidance. Packages that had worked in other parts of Vietnam (typically used in the more hospitable lowlands) were not likely to be relevant, and subsidies are not sustainable in the long run. This portion of the program could have been better thought through and explored through a series of pilot projects rather than being a part of a budget support operation. See IEG 2010 for an evaluation of PRSCs based on operations completed and evaluated by 2008. 6.22 Good analytical work, economic and other, contributes to success. Populous countries with large externally financed programs, such as Vietnam, are likely to benefit from an amount and variety of analytical work, typically using standard economic tools. Smaller countries with more modest analytical programs can probably learn useful things from a selective reading of the analytical work performed in more abundantly staffed countries. But Vietnam also profits from relevant non-economic analytical work that illuminates the likely behavior of the people involved both at the highest levels as well as at the village level in a way that informs the design of the programs. This sort of work is important but by its nature country specific.155 6.23 Well-designed impact evaluations are a valuable dimension of M&E. The impact evaluation turned out to be very important in assessing the impact of P135, not only regarding poverty but also non-income components of welfare, participation, decentralization and empowerment. This has direct relevance to other National Targeted Programs in Vietnam and elsewhere. It is important that funding of such activities be included in the original project design as their late inclusion may lead to implementation difficulties. 6.24 Vietnam's social compact was instrumental in supporting certain achievements, but may not be readily replicable elsewhere. Vietnam's reforms have relied on a top-down approach, which nevertheless draws in various stakeholders into the program and strengthens their ownership and voice. This is notably the case for targeted programs such as P135. While the country's history and social compact are quite specific, there are generic elements, such as effective engagement of local political authorities and communities that may be useful elsewhere. An example was Martin Rama's Making Difficult Choices\. Vietnam in Transition (2008). For behavioral implications at the village level the best example would be Edwin Shanks et al CDD in Vietnam (2003).
P111182 | Vietnam Poverty Reduction Support Credit 9 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2010 | 2012 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/469551474895234248/text/000020051-20140626112326.txt | http://documents.worldbank.org/curated/en/469551474895234248/pdf/000020051-20140626112326.pdf | Lessons from the ICR are supported, in particular that donor coordination can strengthen the policy dialogue and deliver benefits to the client. A PRSC series can serve as an effective framework for policy dialogue and interactions between the government and donors. The benefits can be fundamental and manifold, as supported by a number of outside evaluations. PRSCs can be the â€œone-stop shopâ€ of the policy dialogue, supplemented by sector/thematic DPLs as reform dialogue deepens, and hence raised to a more senior level of government attention than any individual sector effort would have. The role of co-financiers under the PRSC can evolve over time from providers of financing to partners engaged in the preparation of the operations and the policy dialogue with the government. Information flows from the government will expand as trust with the Bank and other partners deepens. This coordination also greatly reduces the transaction costs for the government ministries and agencies (ICR, p. 34).Another lesson is that an incomplete causal chain can lead to difficulty in evaluating the effectiveness of an operation or series in achieving its objectives. When prior actions and targets are directly linked to target outcomes from a PRSC series, there will be a clearer link between the series and the achievement of objectives.Other lessons include the importance of continuity in task team leader (TTL) -- PRSCs 7-10 had the same TTL, and the value of combining policy operations with parallel technical assistance to allow for necessary capacity building. When a government has a sound medium term framework and the program supported by a policy operation is ambitious and broad, a longer series may offer the opportunity to achieve results sought and the flexibility to redirect actions based on experience. In addition, countries facing particularly difficult sectoral challenges should consider a sectoral policy operation to supplement a broader policy operation, allowing more extensive consideration and support to the most difficult issues.
P111182 | Vietnam Poverty Reduction Support Credit 9 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2010 | 2012 | 2015 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/721331467986245693/text/96203-PPAR-REVISED-PUBLIC-VIETNAM-PPAR-FINAL.txt | http://documents.worldbank.org/curated/en/721331467986245693/pdf/96203-PPAR-REVISED-PUBLIC-VIETNAM-PPAR-FINAL.pdf | 6. Conclusions and Lessons Learnt Conclusions 6.1 This review presented an overview of Vietnam's economic and social performance. It assessed the extent to which World Bank DPOs during 2007-12 contributed to its achievements and their sustainability. The main conclusion that emerges from the historical overview is that the country's growth performance during the 1990s and until the mid-2000s was very strong. Effective poverty alleviation also took place during that period, and has been sustained since. This was thanks to transformative measures (especially land reform, enterprise reform and WTO accession) that were taken by Government during the first half of the 2000s (in turn building on earlier reforms) with substantial development partner advice and support, which was generally led by the Bank. 6.2 However, during the period under review (2006-2013) the next generation of transformative reforms (notably as highlighted in the 2007 and 2009 VDRs) were either postponed or diluted, and were thus less effective. Areas such as SOE and financial sector reform, more efficient public investments, anti-corruption, and more effective environmental policies, received insufficient attention. Over the same period, Vietnam departed from the prudent macro-fiscal stance that characterized it in the 1990s early 2000s. 6.3 Past reforms continue to drive strong FDI and buoyant exports. Vietnam can build on these strengths to avoid further loss of growth momentum. This could be based on the implementation select transformative reforms aimed at strengthening the role of the private sector, facilitating the emergence of mediumto large domestic enterprises, and sustainably expanding infrastructure in an efficient manner. The progressive elimination of the stock of contingent liabilities and reducing other risks to the sustainability of fiscal policy would create a more stable macroeconomic environment. One of Vietnam's strengths lies in its social compact, the main elements of which should be maintained, while progressively evolving towards a less paternalistic approach based on stakeholder empowerment. 6.4 The Bank and other development partners can help the country address these priorities through more selective budget support instruments. This is indeed envisaged in the Country Partnership Strategy (2012-16). The 2016-2020 SEDP also provides an opportunity to generate political consensus around these issues in the context of an increasingly complex economy. 6.5 The Bank should be more willing to cease supporting programs should they become so weakened as to make it likely that key objectives would not be achieved. Technical and policy dialogue would be maintained. In this context, high caliber knowledge products will need to continue being prepared, and the relationship of trust that supports frank dialogue with Government needs to be reinforced. Harmonization with all key stakeholders, external and internal, will be important. Strong commitment to deeper reforms would help to sustain Vietnam's economic performance while addressing the challenges of an increasingly complex, middle-income economy, and deepening global integration. Lessons from the Bank's macroeconomic engagement through DPOs. 6.6 The model of the Bank's engagement in macroeconomic and fiscal policies through DPOs in Vietnam since 2007 has not been effective. An important finding emerging from this PPAR is that, while diagnosis of macroeconomic risks was adequate, this was not reflected in program design, despite a highly volatile environment exacerbated by sub-optimal policy choices. This situation was, moreover, aggravated by the lack of an IMF program and the relative weakness of macroeconomic policy dialogue between the Government and the Bretton Woods Institutions. The Bank may have been exposed to reputational risks if its policy lending had been seen as a de-facto endorsement of controversial macro policies. DPOs following those reviewed in this PPAR are still not underpinned by relevant macro policy content, although macroeconomic risks persist. This indicates that the lessons learned during the 2007-2013 period do not appear to have been fully learned. 6.7 Macroeconomic dialogue could advantageously be consolidated in a presence of multiple parallel DPOs. The fragmentation of policy lending into multiple DPOs implemented in parallel in Vietnam during the period of increased macro risks might have weakened Bank's focus on macro framework and even resulted in inconsistencies in policy dialogue. The Bank should have avoided situations when preparation of one operation is held back for concerns over the macro-framework while a parallel DPO is approved and disbursed in the same macro environment. To avoid the repetition of such a situation, there should be a unique and consistent approach towards assessing the adequacy of macroeconomic underpinning of DPOs. When substantial risks are present, policies underpinning the most suitable, in terms of scope and objectives, budget support operation should be reoriented to alleviate them. 6.8 Combining the objectives of external financing for crisis response and promotion of long-standing institutional reforms may not be effective in cases where risks to nonimplementation of reforms are high. The Bank's experience with the Vietnam PIR series indicates that, when financing needs are urgent, it will find itself under pressure to go ahead with disbursements even if the reform implementation is not satisfactory. Crisis response operations should first of all focus on ensuring the sustainability of macro and fiscal framework, and should be underpinned by critical macro, fiscal and structural actions, especially in cases when the IMF is not present operationally. Lessons Learnt â€“ Results and M&E Framework 6.9 Wide-ranging DPOs need to be based on stronger and better quality actions. The importance of each individual prior action increases in multi-sectoral operations with many policy areas because of the implicit limit on the number of total prior actions for operational purposes. If in a series of five operations, for example, each policy area can have a maximum of two or three prior actions in the course of five to six years it is important to ensure that those prior actions have sufficient institutional depth, relevance and criticality. Related to this, in multi-sectoral complex operations there might be no substitutability between the prior actions of unrelated policy areas, which means that weaknesses of prior actions in one sector cannot be offset by relevant and critical prior actions in another sector. 6.10 Lack of focus on and delays in implement essential triggers can weaken the program. In terms of indicative triggers, the Bank has flexibility and discretion in its treatment of the triggers. The transition from Bank's former conditionality framework to the model applied in the series reviewed in this PPAR puts a high premium on sequencing the reforms and ensuring continuity, thus giving considerable significance to the role of triggers for the operations and the overall reform program. Dropping a trigger should be considered as an exceptional event, rather than a regular occurrence, permissible only if the risks to nonimplementation of reforms are duly addressed. 6.11 Partially met triggers require greater attention. Sometimes partially met triggers become prior actions even though they may be less relevant and critical than the originally proposed action. The dilution of content may be to such an extent that these actions would probably not have been considered as prior actions if proposed at the outset. The Bank should pay special attention to possible risks in adopting partially met triggers as prior actions, especially when there is not any realistic expectation that the full original reform will not implemented in a reasonable timetable thereafter. 6.12 It is crucial to have a strong knowledge base for upstream design of reforms and parallel technical assistance to support their implementation. Development partners were willing to put significant resources in these areas, in order to complement Bank financing and dialogue (Vietnam, prefers not to borrow, even on concessional terms, for TA). Selectivity is therefore needed to ensure that the most pressing needs are addressed. Should unmet demand remain, this may be tackled through complementary Bank TA operations, for instance in support of reform teams.151 However, these operations need to be carefully designed in order to match the timing and sequencing needs of DPOs (an issue that arose in the case of P135), and to ensure that the bulk of resources is allocated to meet specific implementation requirements, as opposed to general capacity building (such as purchase of vehicles and equipment, and training). Furthermore, this approach calls for outsourcing knowledge generation and advice to an appropriate mix of experts, both national and international, who can accompany the reforms in medium-term.152 6.13 The design and implementation of M&E for DPOs remains a challenge, and needs to be reconsidered each time a new operation is considered within a series. The PD.153 for the second PIR mentions a lesson learnt elsewhere, whereby an effective M&E mechanism should not just be based on administrative reporting. However, both the PIR and the PRSC suffer from this issue as M&E is not used as a mechanism for feedback and readjustment of activities to improve impact. The P135 is more successful in this area 151 FIAS 2008\. Reform Teams How the Most Successful Reformers Organized Themselves Reform teams consist of a small group of national experts who together with world-class expertise help Governments implement ambitious reforms. 152 In order to achieve such continuity, the experts' contracts may be based on a retainer model. Sorter procurement may also be achieved through framework contracts, whereby a short-list of competitively prequalified consortia/firms expected activities are called upon to provide experts within short delays of 2-4 weeks. The EU has successfully implemented this approach. 153 para. 71 124 because the mid-term review provided a venue for reassessing the implementation of the program. Even there, the change in PRSC indicators took place only for the last operation, although it had become clear much earlier that the relaxation of policy actions required an adjustment in indicators and goals. In both the PRSC and the PIR series there is a disconnect between development objectives, actions and indicators. In the case of the PRSC, there was a logical chain between objectives and indicators, but it is hard to see how some of the reforms would lead to the intended results (the attribution issue). The issue with the PIR is that while there is strong relationship between the reforms and results, their logical link to the development objectives is weak, especially after key reforms were dropped. Lessons Learnt â€“ Bank Approach 6.14 There is a need to reexamine how the Bank approaches sectoral DPOs and how this instrument is differentiated from investment lending. In Vietnam, the distinction between DPOs and investment loans has become blurred, especially with the practice of earmarking funding for the sector the programs support. It can be argued that the four sectoral DPOs might have been best supported by SWAPs and investment lending. The advantage of DPOs is that they disburse rapidly, support to the consolidate budget, and in practice promotes the use of national fiduciary and safeguards systems. However, this approach limits Bank inputs (say on a key study) on the ultimate use of the resources and their underlying processes. To avoid sharp trade-offs that may discourage the use of the most appropriate lending instrument, it seems that in the case of investment lending, it may be desirable to experiment, at least on pilot basis, with further harmonization/convergence between Bank fiduciary and safeguard procedures and national ones. 6.15 The Bank and other development partners should be willing to walk away from an unproductive policy dialogue and withdraw their support of low impact reforms. The delays in P135 (second operation), the second PIR operation and PRSC 10 appear to have been caused by concerns with the quality of the program. In the case of P135, the mid-term review largely addressed the main concerns. However, the last operations in both PIR and PRSC series cannot be readily justified by the contribution to objectives of the weak reform they supported. 6.16 The Bank's recent guideline that suggest to limit the number of operations in a series to three constitutes an appropriate measure. Long-term DPO series need to be kept relevant by maintaining a high level of ambition with respect to the reforms they support. As evidenced by the second PRSC series, a longer-term approach may be hard to sustain. 6.17 Knowledge generated and/or embodied in Bank operations should be properly documented and made public. Bank disclosure policy call for documents it produces being made public, unless classified as confidential. Furthermore, to the extent possible, documents on which policies are based should be easily identifiable and retrieved. In order to preserve knowledge and improve transparency, PDs should properly refer to studies (in some cases the title cited was incorrect) and provide URL links. There is also a question whether disclosure policy is strictly respected (e.g., some energy studies do not appear to have been made public). 125 6.18 It is difficult to evaluate the performance of DPOs in Vietnam without the benefit of a clear reference on what constitutes the norm. This review identifies strengths and weaknesses in the Vietnam DPOs by referencing their own internal logic. However, it is unable to systematically address questions such as how did the Vietnam second PRSC series compared to other PRSCs in terms of ambition, design, results etc. This may result in inconsistency in ratings across countries and projects (ratings contain a subjective element based on the skills, experience and perception of the evaluation team, as well other factors). This issue seems to argue in favor of a new meta-evaluation154 of completed PPARs on similar DPOs, with lessons learnt and recommendations on a more consistent cross-country approach to be reflected in future individual operation evaluations and/or PPARs. Specific Lessons Learnt from P135 6.19 Budget support may not be the best instrument for financing a sector investment program. While a budgetary support operation for a CDD-type program turned out to be moderately satisfactory in the case of Vietnam, the Bank and other development partners had taken a considerable risk. For most countries, it would be highly advisable that the training, at least of the critical personnel (which in a highly decentralized program means a very large number of people), would be done in advance and that an M&E system were in place at the start of the program. There was much retro-fitting under the P135 series that could have been avoided. 6.20 The state of decentralization needs to be fully factored into the design and implementation of targeted poverty programs. Decentralization of government institutions and introducing greater participation at the commune and village levels was an objective of the program as a tool to empower the targeted communities. Various monitoring indicators were used to measure progress on this front. But they did not provide an idea of what would have been good practice in terms of an optimal level of decentralization and participation given the stage of development. An alternative approach could have been to select a control group of provinces that had been decentralizing on their own and could serve as a comparison group for the provinces attempting to develop decentralized structures under P135. That could have enabled the selection of a group of indicators to be used for measuring success before the start of the operation 6.21 Production support to poor communities needs to be tailor-made and well thought through. Much was made of expanding the production component of the program. But the targeted communities were seriously underdeveloped for good reasons. They were remote, mostly mountainous, often forested, and inhabited by people who have eked out livings in these places for centuries. Such places are notoriously difficult to develop and there are few success stories around the world to give guidance. Packages that had worked in other parts of Vietnam (typically used in the more hospitable lowlands) were not likely to be relevant, and subsidies are not sustainable in the long run. This portion of the program could have been better thought through and explored through a series of pilot projects rather than being a part of a budget support operation. See IEG 2010 for an evaluation of PRSCs based on operations completed and evaluated by 2008. 6.22 Good analytical work, economic and other, contributes to success. Populous countries with large externally financed programs, such as Vietnam, are likely to benefit from an amount and variety of analytical work, typically using standard economic tools. Smaller countries with more modest analytical programs can probably learn useful things from a selective reading of the analytical work performed in more abundantly staffed countries. But Vietnam also profits from relevant non-economic analytical work that illuminates the likely behavior of the people involved both at the highest levels as well as at the village level in a way that informs the design of the programs. This sort of work is important but by its nature country specific.155 6.23 Well-designed impact evaluations are a valuable dimension of M&E. The impact evaluation turned out to be very important in assessing the impact of P135, not only regarding poverty but also non-income components of welfare, participation, decentralization and empowerment. This has direct relevance to other National Targeted Programs in Vietnam and elsewhere. It is important that funding of such activities be included in the original project design as their late inclusion may lead to implementation difficulties. 6.24 Vietnam's social compact was instrumental in supporting certain achievements, but may not be readily replicable elsewhere. Vietnam's reforms have relied on a top-down approach, which nevertheless draws in various stakeholders into the program and strengthens their ownership and voice. This is notably the case for targeted programs such as P135. While the country's history and social compact are quite specific, there are generic elements, such as effective engagement of local political authorities and communities that may be useful elsewhere. An example was Martin Rama's Making Difficult Choices\. Vietnam in Transition (2008). For behavioral implications at the village level the best example would be Edwin Shanks et al CDD in Vietnam (2003).
P111183 | Vietnam Poverty Reduction Support Credit 10 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2012 | 2013 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/469551474895234248/text/000020051-20140626112326.txt | http://documents.worldbank.org/curated/en/469551474895234248/pdf/000020051-20140626112326.pdf | Lessons from the ICR are supported, in particular that donor coordination can strengthen the policy dialogue and deliver benefits to the client. A PRSC series can serve as an effective framework for policy dialogue and interactions between the government and donors. The benefits can be fundamental and manifold, as supported by a number of outside evaluations. PRSCs can be the â€œone-stop shopâ€ of the policy dialogue, supplemented by sector/thematic DPLs as reform dialogue deepens, and hence raised to a more senior level of government attention than any individual sector effort would have. The role of co-financiers under the PRSC can evolve over time from providers of financing to partners engaged in the preparation of the operations and the policy dialogue with the government. Information flows from the government will expand as trust with the Bank and other partners deepens. This coordination also greatly reduces the transaction costs for the government ministries and agencies (ICR, p. 34).Another lesson is that an incomplete causal chain can lead to difficulty in evaluating the effectiveness of an operation or series in achieving its objectives. When prior actions and targets are directly linked to target outcomes from a PRSC series, there will be a clearer link between the series and the achievement of objectives.Other lessons include the importance of continuity in task team leader (TTL) -- PRSCs 7-10 had the same TTL, and the value of combining policy operations with parallel technical assistance to allow for necessary capacity building. When a government has a sound medium term framework and the program supported by a policy operation is ambitious and broad, a longer series may offer the opportunity to achieve results sought and the flexibility to redirect actions based on experience. In addition, countries facing particularly difficult sectoral challenges should consider a sectoral policy operation to supplement a broader policy operation, allowing more extensive consideration and support to the most difficult issues.
P111183 | Vietnam Poverty Reduction Support Credit 10 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2012 | 2013 | 2015 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/721331467986245693/text/96203-PPAR-REVISED-PUBLIC-VIETNAM-PPAR-FINAL.txt | http://documents.worldbank.org/curated/en/721331467986245693/pdf/96203-PPAR-REVISED-PUBLIC-VIETNAM-PPAR-FINAL.pdf | 6. Conclusions and Lessons Learnt Conclusions 6.1 This review presented an overview of Vietnam's economic and social performance. It assessed the extent to which World Bank DPOs during 2007-12 contributed to its achievements and their sustainability. The main conclusion that emerges from the historical overview is that the country's growth performance during the 1990s and until the mid-2000s was very strong. Effective poverty alleviation also took place during that period, and has been sustained since. This was thanks to transformative measures (especially land reform, enterprise reform and WTO accession) that were taken by Government during the first half of the 2000s (in turn building on earlier reforms) with substantial development partner advice and support, which was generally led by the Bank. 6.2 However, during the period under review (2006-2013) the next generation of transformative reforms (notably as highlighted in the 2007 and 2009 VDRs) were either postponed or diluted, and were thus less effective. Areas such as SOE and financial sector reform, more efficient public investments, anti-corruption, and more effective environmental policies, received insufficient attention. Over the same period, Vietnam departed from the prudent macro-fiscal stance that characterized it in the 1990s early 2000s. 6.3 Past reforms continue to drive strong FDI and buoyant exports. Vietnam can build on these strengths to avoid further loss of growth momentum. This could be based on the implementation select transformative reforms aimed at strengthening the role of the private sector, facilitating the emergence of mediumto large domestic enterprises, and sustainably expanding infrastructure in an efficient manner. The progressive elimination of the stock of contingent liabilities and reducing other risks to the sustainability of fiscal policy would create a more stable macroeconomic environment. One of Vietnam's strengths lies in its social compact, the main elements of which should be maintained, while progressively evolving towards a less paternalistic approach based on stakeholder empowerment. 6.4 The Bank and other development partners can help the country address these priorities through more selective budget support instruments. This is indeed envisaged in the Country Partnership Strategy (2012-16). The 2016-2020 SEDP also provides an opportunity to generate political consensus around these issues in the context of an increasingly complex economy. 6.5 The Bank should be more willing to cease supporting programs should they become so weakened as to make it likely that key objectives would not be achieved. Technical and policy dialogue would be maintained. In this context, high caliber knowledge products will need to continue being prepared, and the relationship of trust that supports frank dialogue with Government needs to be reinforced. Harmonization with all key stakeholders, external and internal, will be important. Strong commitment to deeper reforms would help to sustain Vietnam's economic performance while addressing the challenges of an increasingly complex, middle-income economy, and deepening global integration. Lessons from the Bank's macroeconomic engagement through DPOs. 6.6 The model of the Bank's engagement in macroeconomic and fiscal policies through DPOs in Vietnam since 2007 has not been effective. An important finding emerging from this PPAR is that, while diagnosis of macroeconomic risks was adequate, this was not reflected in program design, despite a highly volatile environment exacerbated by sub-optimal policy choices. This situation was, moreover, aggravated by the lack of an IMF program and the relative weakness of macroeconomic policy dialogue between the Government and the Bretton Woods Institutions. The Bank may have been exposed to reputational risks if its policy lending had been seen as a de-facto endorsement of controversial macro policies. DPOs following those reviewed in this PPAR are still not underpinned by relevant macro policy content, although macroeconomic risks persist. This indicates that the lessons learned during the 2007-2013 period do not appear to have been fully learned. 6.7 Macroeconomic dialogue could advantageously be consolidated in a presence of multiple parallel DPOs. The fragmentation of policy lending into multiple DPOs implemented in parallel in Vietnam during the period of increased macro risks might have weakened Bank's focus on macro framework and even resulted in inconsistencies in policy dialogue. The Bank should have avoided situations when preparation of one operation is held back for concerns over the macro-framework while a parallel DPO is approved and disbursed in the same macro environment. To avoid the repetition of such a situation, there should be a unique and consistent approach towards assessing the adequacy of macroeconomic underpinning of DPOs. When substantial risks are present, policies underpinning the most suitable, in terms of scope and objectives, budget support operation should be reoriented to alleviate them. 6.8 Combining the objectives of external financing for crisis response and promotion of long-standing institutional reforms may not be effective in cases where risks to nonimplementation of reforms are high. The Bank's experience with the Vietnam PIR series indicates that, when financing needs are urgent, it will find itself under pressure to go ahead with disbursements even if the reform implementation is not satisfactory. Crisis response operations should first of all focus on ensuring the sustainability of macro and fiscal framework, and should be underpinned by critical macro, fiscal and structural actions, especially in cases when the IMF is not present operationally. Lessons Learnt â€“ Results and M&E Framework 6.9 Wide-ranging DPOs need to be based on stronger and better quality actions. The importance of each individual prior action increases in multi-sectoral operations with many policy areas because of the implicit limit on the number of total prior actions for operational purposes. If in a series of five operations, for example, each policy area can have a maximum of two or three prior actions in the course of five to six years it is important to ensure that those prior actions have sufficient institutional depth, relevance and criticality. Related to this, in multi-sectoral complex operations there might be no substitutability between the prior actions of unrelated policy areas, which means that weaknesses of prior actions in one sector cannot be offset by relevant and critical prior actions in another sector. 6.10 Lack of focus on and delays in implement essential triggers can weaken the program. In terms of indicative triggers, the Bank has flexibility and discretion in its treatment of the triggers. The transition from Bank's former conditionality framework to the model applied in the series reviewed in this PPAR puts a high premium on sequencing the reforms and ensuring continuity, thus giving considerable significance to the role of triggers for the operations and the overall reform program. Dropping a trigger should be considered as an exceptional event, rather than a regular occurrence, permissible only if the risks to nonimplementation of reforms are duly addressed. 6.11 Partially met triggers require greater attention. Sometimes partially met triggers become prior actions even though they may be less relevant and critical than the originally proposed action. The dilution of content may be to such an extent that these actions would probably not have been considered as prior actions if proposed at the outset. The Bank should pay special attention to possible risks in adopting partially met triggers as prior actions, especially when there is not any realistic expectation that the full original reform will not implemented in a reasonable timetable thereafter. 6.12 It is crucial to have a strong knowledge base for upstream design of reforms and parallel technical assistance to support their implementation. Development partners were willing to put significant resources in these areas, in order to complement Bank financing and dialogue (Vietnam, prefers not to borrow, even on concessional terms, for TA). Selectivity is therefore needed to ensure that the most pressing needs are addressed. Should unmet demand remain, this may be tackled through complementary Bank TA operations, for instance in support of reform teams.151 However, these operations need to be carefully designed in order to match the timing and sequencing needs of DPOs (an issue that arose in the case of P135), and to ensure that the bulk of resources is allocated to meet specific implementation requirements, as opposed to general capacity building (such as purchase of vehicles and equipment, and training). Furthermore, this approach calls for outsourcing knowledge generation and advice to an appropriate mix of experts, both national and international, who can accompany the reforms in medium-term.152 6.13 The design and implementation of M&E for DPOs remains a challenge, and needs to be reconsidered each time a new operation is considered within a series. The PD.153 for the second PIR mentions a lesson learnt elsewhere, whereby an effective M&E mechanism should not just be based on administrative reporting. However, both the PIR and the PRSC suffer from this issue as M&E is not used as a mechanism for feedback and readjustment of activities to improve impact. The P135 is more successful in this area 151 FIAS 2008\. Reform Teams How the Most Successful Reformers Organized Themselves Reform teams consist of a small group of national experts who together with world-class expertise help Governments implement ambitious reforms. 152 In order to achieve such continuity, the experts' contracts may be based on a retainer model. Sorter procurement may also be achieved through framework contracts, whereby a short-list of competitively prequalified consortia/firms expected activities are called upon to provide experts within short delays of 2-4 weeks. The EU has successfully implemented this approach. 153 para. 71 124 because the mid-term review provided a venue for reassessing the implementation of the program. Even there, the change in PRSC indicators took place only for the last operation, although it had become clear much earlier that the relaxation of policy actions required an adjustment in indicators and goals. In both the PRSC and the PIR series there is a disconnect between development objectives, actions and indicators. In the case of the PRSC, there was a logical chain between objectives and indicators, but it is hard to see how some of the reforms would lead to the intended results (the attribution issue). The issue with the PIR is that while there is strong relationship between the reforms and results, their logical link to the development objectives is weak, especially after key reforms were dropped. Lessons Learnt â€“ Bank Approach 6.14 There is a need to reexamine how the Bank approaches sectoral DPOs and how this instrument is differentiated from investment lending. In Vietnam, the distinction between DPOs and investment loans has become blurred, especially with the practice of earmarking funding for the sector the programs support. It can be argued that the four sectoral DPOs might have been best supported by SWAPs and investment lending. The advantage of DPOs is that they disburse rapidly, support to the consolidate budget, and in practice promotes the use of national fiduciary and safeguards systems. However, this approach limits Bank inputs (say on a key study) on the ultimate use of the resources and their underlying processes. To avoid sharp trade-offs that may discourage the use of the most appropriate lending instrument, it seems that in the case of investment lending, it may be desirable to experiment, at least on pilot basis, with further harmonization/convergence between Bank fiduciary and safeguard procedures and national ones. 6.15 The Bank and other development partners should be willing to walk away from an unproductive policy dialogue and withdraw their support of low impact reforms. The delays in P135 (second operation), the second PIR operation and PRSC 10 appear to have been caused by concerns with the quality of the program. In the case of P135, the mid-term review largely addressed the main concerns. However, the last operations in both PIR and PRSC series cannot be readily justified by the contribution to objectives of the weak reform they supported. 6.16 The Bank's recent guideline that suggest to limit the number of operations in a series to three constitutes an appropriate measure. Long-term DPO series need to be kept relevant by maintaining a high level of ambition with respect to the reforms they support. As evidenced by the second PRSC series, a longer-term approach may be hard to sustain. 6.17 Knowledge generated and/or embodied in Bank operations should be properly documented and made public. Bank disclosure policy call for documents it produces being made public, unless classified as confidential. Furthermore, to the extent possible, documents on which policies are based should be easily identifiable and retrieved. In order to preserve knowledge and improve transparency, PDs should properly refer to studies (in some cases the title cited was incorrect) and provide URL links. There is also a question whether disclosure policy is strictly respected (e.g., some energy studies do not appear to have been made public). 125 6.18 It is difficult to evaluate the performance of DPOs in Vietnam without the benefit of a clear reference on what constitutes the norm. This review identifies strengths and weaknesses in the Vietnam DPOs by referencing their own internal logic. However, it is unable to systematically address questions such as how did the Vietnam second PRSC series compared to other PRSCs in terms of ambition, design, results etc. This may result in inconsistency in ratings across countries and projects (ratings contain a subjective element based on the skills, experience and perception of the evaluation team, as well other factors). This issue seems to argue in favor of a new meta-evaluation154 of completed PPARs on similar DPOs, with lessons learnt and recommendations on a more consistent cross-country approach to be reflected in future individual operation evaluations and/or PPARs. Specific Lessons Learnt from P135 6.19 Budget support may not be the best instrument for financing a sector investment program. While a budgetary support operation for a CDD-type program turned out to be moderately satisfactory in the case of Vietnam, the Bank and other development partners had taken a considerable risk. For most countries, it would be highly advisable that the training, at least of the critical personnel (which in a highly decentralized program means a very large number of people), would be done in advance and that an M&E system were in place at the start of the program. There was much retro-fitting under the P135 series that could have been avoided. 6.20 The state of decentralization needs to be fully factored into the design and implementation of targeted poverty programs. Decentralization of government institutions and introducing greater participation at the commune and village levels was an objective of the program as a tool to empower the targeted communities. Various monitoring indicators were used to measure progress on this front. But they did not provide an idea of what would have been good practice in terms of an optimal level of decentralization and participation given the stage of development. An alternative approach could have been to select a control group of provinces that had been decentralizing on their own and could serve as a comparison group for the provinces attempting to develop decentralized structures under P135. That could have enabled the selection of a group of indicators to be used for measuring success before the start of the operation 6.21 Production support to poor communities needs to be tailor-made and well thought through. Much was made of expanding the production component of the program. But the targeted communities were seriously underdeveloped for good reasons. They were remote, mostly mountainous, often forested, and inhabited by people who have eked out livings in these places for centuries. Such places are notoriously difficult to develop and there are few success stories around the world to give guidance. Packages that had worked in other parts of Vietnam (typically used in the more hospitable lowlands) were not likely to be relevant, and subsidies are not sustainable in the long run. This portion of the program could have been better thought through and explored through a series of pilot projects rather than being a part of a budget support operation. See IEG 2010 for an evaluation of PRSCs based on operations completed and evaluated by 2008. 6.22 Good analytical work, economic and other, contributes to success. Populous countries with large externally financed programs, such as Vietnam, are likely to benefit from an amount and variety of analytical work, typically using standard economic tools. Smaller countries with more modest analytical programs can probably learn useful things from a selective reading of the analytical work performed in more abundantly staffed countries. But Vietnam also profits from relevant non-economic analytical work that illuminates the likely behavior of the people involved both at the highest levels as well as at the village level in a way that informs the design of the programs. This sort of work is important but by its nature country specific.155 6.23 Well-designed impact evaluations are a valuable dimension of M&E. The impact evaluation turned out to be very important in assessing the impact of P135, not only regarding poverty but also non-income components of welfare, participation, decentralization and empowerment. This has direct relevance to other National Targeted Programs in Vietnam and elsewhere. It is important that funding of such activities be included in the original project design as their late inclusion may lead to implementation difficulties. 6.24 Vietnam's social compact was instrumental in supporting certain achievements, but may not be readily replicable elsewhere. Vietnam's reforms have relied on a top-down approach, which nevertheless draws in various stakeholders into the program and strengthens their ownership and voice. This is notably the case for targeted programs such as P135. While the country's history and social compact are quite specific, there are generic elements, such as effective engagement of local political authorities and communities that may be useful elsewhere. An example was Martin Rama's Making Difficult Choices\. Vietnam in Transition (2008). For behavioral implications at the village level the best example would be Edwin Shanks et al CDD in Vietnam (2003).
P111205 | EU Natura 2000 Integration Project | Europe and Central Asia | Croatia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2011 | 2017 | 2018 | ICRR | >=25 million & <50 million | Satisfactory |  |  | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/748101515624205935/text/Croatia-EU-NATURA-2000.txt | http://documents.worldbank.org/curated/en/748101515624205935/pdf/Croatia-EU-NATURA-2000.pdf | IEG abstracted the following two lessons arise from this project:1 . Bridge Financial Resourcesare essential for countries joining the EU to comply with new regulations. This project provided important access tofinancial resources to a country that was about to join the EU. Without the investment that Croatia made on its natural and natureparks through this project, it is highly unlikely that Croatia would have been able to effectively report on the Natura 2000objectives in 2019. The contributions of this project also ensured that Croatia was able to access quickly EU mechanisms to helpsupport and fund conservation efforts.2 . Conservation projects can lead to improved Inter-Sectoraland Inter-Ministerial Cooperation. Much of the land that needs to be protected as part of the Natura 2000 objectives wereprivately owned. Therefore, there was a need in this project to work across sectors, across ministries, and with diversestakeholders. At the beginning of the project, cooperation between different inter-sectoral and inter-ministerial agencies was poorand a significant challenge (ICR, para 56). In fact, the responsibility line in the Ministry changed several times in the project.That said, the project also brought a concrete reason and provided incentives for different groups across sectors and ministries tocooperate and work together. For example, the Ministry of Environment and Energy reported better collaboration and understandingwith key partners as a result of this project, according to the Borrowers statement (ICR, para. 126). Another example, is thatalmost all departments in the Nature Protection Directorate were involved with the implementation and contributed to the project(ICR para 136).The following two lessons come from the IRC:3.Wide stakeholder involvement is crucial for effectively managing projected areas. The project built the capacityof a wide range of stakeholders who use and manage the protected areas. It was important to clarify roles, raise awareness, andhelp incentivize improvement in protected areas environment.4. Experienced and motivatedPIU, and project implementation readiness help Project hit the ground running. Members of the PIU hadhigh capacity and had previous Bank project experience. Embedding the PIU within the Ministry of Environment and Energy enabledcooperation with ministry, park staff, and community organizations. Extensive project preparation enabled the team to hit theground running. This included pre-screening over 100 potential ecological network investments at the beginning of the project. Someof these projects were funded by the loan, others served as a pipeline to apply for EU funding.
P111222 | Bhutan Development Policy Grant/Credit for Institutional Strengthening | South Asia | Bhutan | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2011 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/470801474511395983/text/000020051-20140624185424.txt | http://documents.worldbank.org/curated/en/470801474511395983/pdf/000020051-20140624185424.pdf | 1. DPLs, especially in countries facing capacity constraints, can be useful to promote government structures to formulate and implement policy reforms. In this case, the Department of Public Accounts was strengthened by the role it played in convening and working with other government ministries and agencies to implement the DPFIS. 2. Leveraging DPLs with technical assistance and investment operations can be important in promoting key reforms. This was evident under the DPFIS as it was coordinated with investment and technical assistance operations in private sector development, ICT, public financial management, and other areas. 3. The Bank needs to carefully assess the prospects for impact in sectors where other donors play much larger roles than those envisaged by the Bank. In this case, another donor was very active in the power sector, limiting the impact which could be expected from Bank assistance. Any future involvement in the power sector in Bhutan should bee preceded by a careful assessment of likely impact.
P111272 | Emergency 2007 Cyclone Recovery and Restoration Project | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2009 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/533751552058833403/text/Bangladesh-BD-Emergency-2007-Cyclone-Recovery-Rest.txt | http://documents.worldbank.org/curated/en/533751552058833403/pdf/Bangladesh-BD-Emergency-2007-Cyclone-Recovery-Rest.pdf | The ICR draws the following main lessons with some adaptation of language.(1)Carefulplanning is required for multi-sectoral projects requiring multi-sectoral coordination andimplementation arrangements. This project had six implementation agencies, each under a different ministry, responsiblefor implementing the various components. The experience of this project demonstrated the importance of capacity building of theCoordination and Monitoring Unit to support the line ministries and clear delineation of roles between the coordination unit andamong the different actors involved.(2) Land acquisition procedures need to be strengthened foremergency situations. To balance the need for urgent infrastructure works and following due process, the Bank could eithersupport country-level reforms in the land acquisition process or agree with the government to allow accelerated procedures foremergency works.(3) Well defined Results and ME frameworks for emergency projectsis needed for enhancing achievement of outcomes. Given that teams find it challenging to establish a robust MEframework, it would be useful to develop standardized guidelines to help bring about a more nuanced and fine-tuned MEframework for disaster recovery projects. Also given that emergency projects are to be prepared quickly, baseline studies need tobe conducted either before or just after project approval to capture the pre-project status required in order to measure the impactof the project.(4) Regular community consultations throughout the project can be useful forgenerating practical improvements to increase impact. In livelihood recovery activities, constantbeneficiary feedback can help in continuous improvements in design and implementation.
P111290 | Ivory Coast Protected Area Project | Western and Central Africa | Cote d'Ivoire | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2009 | 2015 | 2016 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/767461468197947133/text/ICRR14847-P111290-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/767461468197947133/pdf/ICRR14847-P111290-Box394823B-PUBLIC.pdf | The project's experience yields the following lessons of wider applicability (lessons 1 to 3 are from the ICR): 1. Dependence on a separate funding source for financing a key activity presents risks. For example, in the case of PARCâ€™s sub-component for developing community micro-projects to improve livelihoods and enhance incentives for park protection, financing was to be provided by another Bank project.. This project was terminated due to bad performance, leaving the micro-projects without a funding source. Financing as a component within PARC would have provided a safer source of funds for the micro-projects.2. The success of community engagement was enabled through a multi-faceted approach. The project involved multiple ways to engage communities in changing damaging practices to proactive management of the park. These included: awareness raising, co-opting local authorities such as local politicians and traditional village leaders, and contracting villagers for park maintenance and surveillance; and, in the original design, village livelihoods micro-projects. Sufficient ownership was achieved to influence a radical reduction in cattle grazing and significantly reduce poaching. Further, this multifaceted program to engage communities in park management and maintenance was still able to succeed without the livelihoods micro-projects, a standard element of many park management projects. 3. In a post-conflict situation, to the extent feasible within the time pressures present, a detailed situational and risk analysis, and extensive consultation with stakeholders are important bases for project preparation. The five-month preparation period left little time for more than rapid assessments and limited consultation. A lengthier preparation period would have provided more opportunity for consultations with communities and donors, assessing baselines and targets for monitorable indicators, learning from past project experience, and tailoring the design for more expeditious project implementation.4. Collecting funds through a dedicated non-Governmental Foundation can be a successful way of generating funds for the management of parks or similar environmental projects.. The Foundation for Parks and Reserves of Cote dâ€™Ivoire (FPRCI), a private foundation dedicated to collecting funds for maintaining the Parks, attracted far greater financing than anticipated â€“ well over the needs of Comoe Park.5. A projectâ€™s logical framework, design, monitorable indicators and M&E need close linkage.There were some gaps in the linkages, until the Mid-Term-Review which revised about a third of the Indicators, and part of the M&E program.
P111330 | Eastern Nile Watershed Management Project | Other | Africa |  |  | Sustainable Development | Water | GEF | IPF | 2009 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/141341485192193778/text/ICRR-Disclosable-P111330-01-23-2017-1485192177638.txt | http://documents.worldbank.org/curated/en/141341485192193778/pdf/ICRR-Disclosable-P111330-01-23-2017-1485192177638.pdf | The ICR provides 3 important lessons from this operation, summarized below: (ICR, paragraphs86-89) Successful inter-country cooperation will continue to be a challenge in the region for some timeeven if starting out with committed parties. Flexibility and recognizing opportunities for cooperation are important considerationsto move a project forward. Successful adoption of new watershed management practices require engaging stakeholders andsupporting their continued participation. Effective communications are key to ensure that expectations from the project remainrealistic. Independent, third party institutions like academic and research facilities are useful avenues to sustainableknowledge and skills development. Following project close, the Nile Basin Initiative will continue to support academic partnershipsand internships that benefit all countries of the Nile Basin (ICR, para 89).IEG suggests anotherlesson. Incorporating lessons learned from prior operations into subsequent project design (as indicated in the PADwas done for this project)may not necessarily be replicable during similar implementation. In this project, watershedmanagement technologies borrowed from other projects were deemed not to be replicable. The lesson is that the transferof technologies is potentially beneficial but their replicability needs to be carefully researched in advance.
P111394 | Teacher Education Improvement Project | Middle East and North Africa | West Bank and Gaza |  | FCS | Human Development | Education | SPF | IPF | 2010 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/232061585594408185/text/West-Bank-and-Gaza-GZ-Teacher-Education-Improvement-Project.txt | http://documents.worldbank.org/curated/en/232061585594408185/pdf/West-Bank-and-Gaza-GZ-Teacher-Education-Improvement-Project.pdf | Lessons drawn from the ICR (pages 28-29) and adapted by IEG: The presence of a committedleaderatthe Deputy Minister level can counter any negative impact from multiple changes in Ministers of Education due to geo-politicaltransitions. In the case of this project, the Deputy Minister served along tenure during the lengthy project period, despitefive changes of Minister of Education, championed the project concept, and governed over the various implementing entities,supported by an effective project coordination unit. A teacher accreditation framework/process can serve toharmonize the work of different stakeholders in the teacher education sector.In the case of this project, the accreditationprocess included establishing formal relationshipsamong teacher education institutions,mentor schools, and menteeschools, as well ascoordinating the work of different units within the Ministry of Education.
P111421 | China: Anhui Medium Cities Urban Transport Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2018 | 2019 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/607681556639186550/text/China-CN-Anhui-Medium-Cities-Urban-Transport.txt | http://documents.worldbank.org/curated/en/607681556639186550/pdf/China-CN-Anhui-Medium-Cities-Urban-Transport.pdf | First two lessons are adopted from the ICR while the last lesson is from IEGs perspective of theproject.1 . The Realization of an integrated urban transport system hinges on system integrationand institutional coordination. Since a city is organic anddynamic in nature, static planning can hinder optimumurban development. In the Anhui project, the location of the High-Speed Rail Station was moved, which impacted the traffic flows.The project adaptively changed the design of the Huxin Road in Anqing, to meet a new traffic demand. Conversely, the project washindered when the process for the new construction of the Anning intercity rail and viaduct commenced. Coordination with the railowners was not successful and led to the cancellation of some project activities. Both engineering and institutional stakeholdercoordination in respect of planning were critical to establishing an integrated urban transport system.2. Prototyping a new concept gradually raises the level of acceptance. Before the project, the municipalitiescarried out road construction without coordinating with other relevant departments. With the introduction of the integratedcorridor development, the institutions were required to validate the plans and designs across agencies. Such a change process oftengenerates resistance by the implementing agencies and concerned stakeholders. For this project, it piloted the new concept at theinitial stage, which incrementally increased the level of acceptance of the concept.3 . Harnessingan innovative concept can benefit from mobilizing evidence of performance, geared to foster engagement. The project was amove towards changing the fragmentation of the urban transport system through an innovative pilot project corridor developmentconcept which is the planning and implementation of the integrated urban transport system: the improvement of traffic managementsystem (signal, channelization and singing), street lighting system, underground utilities and bus stop facilities. However,evidence was not well mobilized. Monitoring the corridor level data did not generate new evidence on the effectiveness of theintegrated corridor development concept, hindering its scalability and institutional engagement. A comparison between the projectand the conventional approach, which could have been embedded in the results framework, could be instrumental in fosteringengagement by various stakeholders.
P111432 | AFCC2/RI-RCIP3 - Regional Communications Infrastructure Program - Phase 3 | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Infrastructure | Transport | IDA | IPF | 2009 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/437831542041042691/text/Africa-RCIP-Phase-3.txt | http://documents.worldbank.org/curated/en/437831542041042691/pdf/Africa-RCIP-Phase-3.pdf | The ICR identified a number of lessons and recommendations that are rephrased and summarizedbelow:(i) Efficacy ofWBGs regional programs andprojectsrequires well-devised implementation arrangements: Whilethere was value added fortheRCIPto promotea coherent actionon ICT investment in the sub-region,implementingthreedifferent projects under one World Bank codewas constrained bylack of operational flexibility, and aninsufficientbudget for their preparation,supervision and reporting. In order to minimizethe above drawbacks whilemaintaining the advantages of a regional approach, it isadvisable to developa customizable regional umbrella programfor digital development in a specific region butensure thateach countrys project isimplemented as astand-alone operation.(ii) Because of rapid change in the ICTsector,asequentialapproachmight resultin a betterproject design. A multi-phased approach allows more flexibility in adapting theprojects design to changing circumstances in the ICT sector andin the countrys context. Therefore,a clearsequencing of activities at the preparation stage, using a multi-phase approachenables smoother implementation andstrengthens the projects relevance throughout its course.The identification of this sequencing already at thepreparation stage might havefacilitateda more efficient and organizedimplementation.(iii) As specific eGovernment applicationstendbecome obsoletequickly, the Bank should aim to support activities to thefoundations of digital government:The Bank might want to consider focusing its investments in building thefoundations of digital government (interoperability modules and Application Programming Interfaces (APIs), cloud technology,cybersecurity ordata warehouses) instead of developing eGovernment applications, because the latter might becomeobsoletevery quickly. Moreover,developing eGovernment applications requires strong coordination between differentbranches of government, thus involvingsignificant coordination risks beyond what theBank is preparedfor.(iv) When designed appropriately, PPP arrangements areeffective modelstosupport ICT projects and programs: The positive outcomes from the RCIP3suggest thatthe PPP models are both effective in delivering results, and efficient in their cost structure and organization, and could beadopted in future connectivity operations.In Malawi and Mozambique, theacquisition of wholesale bandwidth by thegovernment created the incentives and reduced investment risk for private operators to build out new backbone infrastructure whichcould serve both government and the private market. In Tanzania, the reverse subsidy auction model adopted for rural mobileconnectivity ensured the highest value for money and maximum leveraging of private financing through the competitive awardprocess while shifting all financial and operational risk for the mobile sites and services offerings to the private sectoroperators.
P111470 | Education For All-Fast Track Initiative Program | Western and Central Africa | Guinea | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2009 | 2015 | 2016 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/261861468256457653/text/ICRR-Disclosable-P111470-06-02-2016-1464899175643.txt | http://documents.worldbank.org/curated/en/261861468256457653/pdf/ICRR-Disclosable-P111470-06-02-2016-1464899175643.pdf | The ICR provides the following key lessons (summarized and paraphrased) based on project experience (pp. 31-32) that will beuseful for future projects:Project designs benefit from taking into consideration the fragility ofthe economic and political environment. The FC-PSE was designed in a politically, socially and institutionally fragilesetting. The Pooled Fund approach to supporting the Government in achieving its sector objectives was appropriate in light of the2005 Paris Declaration and efforts to promote sustainability of investments in the sector. The complex design of the FC-PSE, whichsupported activities across the sector, was reliant on strong institutional capacity and inter-ministerial coordination. Though theproject was significantly reduced in terms of scope and implementation needs in response to reduced funding in 2011 and 2012, itmay have been useful at either of these times to reduce the scope even further in order to better ensure the timely and effectiveimplementation of project-supported activities and effective ME.Pooled funding can be aneffective mechanism for providing support to achievement of the Governments strategicobjectives in the education sector. This projects strong alignment with Government strategies and support fromother DPs active in the sector including AFD, KfW and UNICEF promoted harmonization of efforts, reduced duplication of activities,and promoted continued support to the education sector during a period in which the Bank was only able to provide informaltechnical supportto the Government.The Banks swiftengagement following periods of crisis can be instrumental in ensuring that governments have the necessary financial and technicalsupport to continue to implement their sector strategies and to provide services at a time when their own resources and capacityare more limited. The timely reengagement of the Bank under this Project was possible, in large part, due to theproactivity demonstrated by the Project team in maintaining technical dialogue with the government (?) and with the DPs that wereactive on the ground throughout the period following the coupdtat.The establishment of a robust ME system isinstrumental in ensuring that the outputs and outcomes of an operation are properly documented. Through the MEsystem established and used in the context of the Project required input from various decentralized levels, the informationprovided by this system was critical for undertaking joint annual sector reviews and for adequately documenting and reporting onachievements under this operation.
P111479 | CO Rio Bogota Environmental Recuperation and Flood Control Project | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2011 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099112223123541021/text/P1114790d2918d0950b89e0b4e4cfe7a495.txt | http://documents.worldbank.org/curated/en/099112223123541021/pdf/P1114790d2918d0950b89e0b4e4cfe7a495.pdf | IEG derives the following lessons drawn from the ICR: Inadequate time in the implementation schedule fordesign-build contracts to allow for preparation of detailed designs, carrying out procurement processes, and engaging highlyqualified advisory services supporting the client during procurement and contract management can result in delays in projectimplementation. Thoroughly preparing design and procurement documents will allow for smooth implementation. In addition,the reference design used in the bidding process should include at least 20 percent of the preliminary engineering with technicalspecifications, including key equipment. In addition, the advisory services during implementation should serve as projectmanagement consultancy with the capacity and ability to make decisions that help optimize the plants design as constructionproceeds. Strong interinstitutional coordination mechanisms, close accompaniment and supportthroughout the design and implementation phase can help in working across the water resources management and water supply andsanitation subsectors in a single project. Entering into a legally-binding agreementthe Convenio 171betweenCAR and the utility that specified the roles and responsibilities of each was critical in ensuring good coordination between theseinstitutions throughout project preparation and implementation. The convenios strategic importance was such that anyamendment, suspension, abrogation, repeal, or waiver that would have materially and adversely impacted, in the Banksopinion, the borrowers ability to perform any of its obligations under the Banks legal agreement, would have beenconsidered grounds for suspension of the legal agreement between the Bank and theborrower. Meaningful, deep, and continuous engagement with communities directly affected byconstruction works may help build support for projects and may prevent delays due to social opposition. The Banksand CAR teams efforts to engage communities throughout project preparation and implementation helped to ensure thatresidents broadly supported the project, preventing potential delays that would arise with social opposition. That at least 40percent of the labor force (both skilled and unskilled workers) for constructing the WWTP came from the local community also helpedin generating support for the project.
P111545 | Kenya Cash Transfer for Orphans and Vulnerable Children | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2009 | 2019 | 2020 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/467731578682407225/text/Kenya-KE-Cash-Transfer-for-OVC-FY09.txt | http://documents.worldbank.org/curated/en/467731578682407225/pdf/Kenya-KE-Cash-Transfer-for-OVC-FY09.pdf | The ICR (pp. 32-35) included several valuable lessons, adapted here by IEG: Adequate targeting mechanismsand regular recertification are critical for a conditional cash transfer program in order to ensure that the money goes where itshould. In this project, there were reports that households continued the program despite the OVC turning 18 years, orthat households claimed benefits even though there was no OVC living in the household. In order to address these issues, thegovernment has rolled out a new payment mechanismthat requires proof of life and IDs for registration and is updating datainputs into the targeting tool as well as the recertification strategy. Finding a sustainable, streamlined, andsystematic process for ensuring timely payments to beneficiaries is critical for the success of a program. In 2016, thisproject conducted an analysis of the steps required to complete a payment cycle, findingthat 24 internal steps had to betakenover a total of 90 days. The government addressed this lengthy process through streamlining and was able todecreasethe timelineto 54 days, resulting inthe government meeting the performance standard for timely paymentsfor three consecutive payment cycles. However, this performance was not sustainable when the National Treasury did not prioritizeSDSP disbursements. Therefore, in order to increase the likelihood of a timely process, the National Treasury agreed to includeallCTs on the recurrent budget instead of the development budget. Allowing sufficient time in theprojects design for the introduction of new delivery systems is important to ensure benefits in the long run. In2015, the project introduceda new two-factor authentication payment mechanism, resultingin the disruption of projectimplementationdue to challenges with collecting biometric data. However, evidence from field visits also indicated thatbeneficiaries have benefited from choosing providers in much closer proximity than before, reducing the cost and time to access thepay point.
P111546 | Kenya Youth Empowerment Project | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2010 | 2016 | 2017 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | High | http://documents.worldbank.org/curated/en/341501487967487230/text/ICRR-Disclosable-P111546-02-24-2017-1487967476844.txt | http://documents.worldbank.org/curated/en/341501487967487230/pdf/ICRR-Disclosable-P111546-02-24-2017-1487967476844.pdf | The ICR (pp. 27-28) contains several bulleted lessons, most of which describe aspects of what went well in thisproject and should be repeated in similar projects in Kenya and elsewhere (the Borrowers ICR also containsvaluable and somewhat differently worded lessons). These lessons can be regarded as good practices; theyare hardly new and should not surprise anyone familiar with employment and vocational training, yet they deserve to be recapped andsummarized here briefly: Public-private partnership is important for employment and trainingprograms. In this case, itproved useful to engage the private sector for project management andas training andinternship providers. It also proved useful to solicit feedback on skills needs from potential employers. Paying closeattention to details of implementationis essential. Issues around targeting, transparency in selection of trainees, tacklingof gender barriers, amounts paid in stipends, and the delivery of life skills were all identified and addressed during projectimplementation. Implementation capacity is essential, and running projects of this type is labor intensive. Adequate andsufficient skills for running the ME system are needed. Linking interns or former interns to business developmentservices may help increase impact by supporting trained youth to become entrepreneurs. (These services were not offered by thisproject, and it is unclear if there are actual experiences from this project of the benefits of adding such support, or if thislesson is a bit speculative.)IEG adds the following lesson: Offeringinternships in rural areas is infeasible in some settings. Aplanned expansion of this project torural areas wasdropped because of difficulty identifying employers willing to offer internships.
P111548 | VIETNAM: Haiphong Urban Transport Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2011 | 2020 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/281681617973397356/text/Vietnam-VN-Haiphong-Urban-Transport-Project.txt | http://documents.worldbank.org/curated/en/281681617973397356/pdf/Vietnam-VN-Haiphong-Urban-Transport-Project.pdf | Following lessons are taken from the ICR with some modification of the language:1. Appropriate measures need tobe incorporated at design to ensure compliance with environmental andsocial safeguards. Thisproject facedsignificant delays during implementation,due the difficulties associated withcounterpart funding for land acquisitionand resettlement activities.The lesson from this is that future projects need to raise the visibilityofsituationswhere land acquisition and resettlement activities are involved,and intensify additional supervisionefforts towards resolving these issues. This is especially so for projects classified as Category A (full assessment)projects.2. ME framework need to be comprehensive and incorporate all features of projectactivities. Given that project activityonthe construction of a new urban arterial road wasin areas ofurban agglomeration with heavy pedestrian traffic, the ME framework could formally have incorporated akey outcomeindicator for monitoring road safety incidents. Further, where theME framework at design had shortcomings (unclearmethodology) as in this project, they could have been identified and addressed during project implementation.3.Urban transport components need to include a more robust set of measures to amplify the demonstrative effect ofinterventions. This project provided technical inputs for supporting the creation of a Public Transport Unit (PTU) withinthe Department of Transport. The efforts to improve the fleet, operations and infrastructure could have been articulated as part ofa broader public transport strategy. This aspect of design is particularly important given growing urbanization in many countriesin Africa and Asia.
P111556 | AFR RI-East Africa Public Health Laboratory Networking Project | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Human Development | Health, Nutrition & Population | IDA | IPF | 2010 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | High | http://documents.worldbank.org/curated/en/099930001142240777/text/Eastern0Africa0h0Laborat0Net00FY100.txt | http://documents.worldbank.org/curated/en/099930001142240777/pdf/Eastern0Africa0h0Laborat0Net00FY100.pdf | The ICR (p. 35) offered several important lessons and recommendations, including the following lessons re-stated byIEG:In regional projects, the effectiveness of the regional coordination role is enhanced when itisalso focusedon facilitating country roles. Under the project, this was well demonstrated by the East,Central and Southern Africa Health Community through its attention to supporting countries with weaker capacities, and by creatingplatforms for knowledge sharing.Regional projects can leverage country expertise and encourage each country totake a technical lead in specific thematic areas to enhance the skills and motivation of regional teams in advancing transformativechanges in the region. Under the project, leadership in key technical areas was reached by consensus and allowed Tanzania,Kenya, Uganda, and Rwanda to serve as centers of excellence on selected topics.Projects with complextechnical interventionsbenefit from the early involvement of partner agencies that have a comparative advantage in thoseareas. Under the project, the engagement of the Task Team with the U.S. Centers for Disease Control and Prevention, theWorld Health Organization, and the African Society for Laboratory Management brought added value to laboratory strengthening and tothe stepwise laboratory quality improvement process towards accreditation.The introduction of new proprietarytechnologies to development projects can be challenging, as considerable time is required to provide justifications for singlesource procurement, as was encountered under the project with GeneXpert for TB testing,
P111567 | Rwanda Electricity Access Scale-up and Sector Wide Approach (SWAp) Development Project | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2010 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/102241553114033231/text/Rwanda-Rwanda-Electricity-Access-Scale-up-Proj.txt | http://documents.worldbank.org/curated/en/102241553114033231/pdf/Rwanda-Rwanda-Electricity-Access-Scale-up-Proj.pdf | IEG selectedthreelessons fromthe ICR, with somemodification: A combination of grid and off-grid solutions based on geographicinformation system mapping techniqueshelps accelerate electricity access expansion. Rwanda was one of the firstcountries to prepare and implement a nationwide electrification program combining grid and off-grid means, based on a systematicand least-cost plan aided by geographic information system mapping techniques that combine technical, economic, demographic, anddemand and supply data. The objective of this prioritization was to ensure that the program maximizes benefits of electrification,while minimizing program costs. The prioritization took advantage of Rwanda being a small country with high population density,making potential rollout faster than larger low densely populated countries. StrongGovernment ownership of projects, and projects that are aligned with national priorities are in a strong position to succeed fromthe onset. When governments own the access agenda and incorporate it in their growth strategies, the access expansionagenda is most likely to be successful. The GoR participated in the design and preparation of the national program and geospatialplan, drew up clear results frameworks, and established ME accountability under the overall institutionalsetup. Well coordinated donor support can greatly enhanceresults from aninclusive sector effort, and is of particular value in a post-conflict situation. This energy sectorproject isan example of how development partners can come together in a constructive manner in a post-conflict country. TheSWApstructure in Rwanda was built upon existing institutions and assigns clear responsibilities to the different parties inthe sector working group, including government institutions, development partners, private sector, and other energy sectorstakeholders.
P111577 | Local Government and Decentralization Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2010 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/847271535087192794/text/Indonesia-ID-Local-Government-and-Decentralization.txt | http://documents.worldbank.org/curated/en/847271535087192794/pdf/Indonesia-ID-Local-Government-and-Decentralization.pdf | The lessons are drawn from the ICR with some modification of language: Design that enhances a countrys ownsystems improves a projects ability to adapt to policy changes that may be introduced during project implementation. Forexample, in this case, the project enhanced the capacity of an existing independent auditor, the BPKP, to independently verify thecompleteness and compliance with agreed upon indicators of DAK financed activitiesusingthe WBRS. Even when DAK policychanged during implementation such as introducing different DAK allocation categories, or modifying the applicable incentivesystem, participant LGs continued to use theWBRS and BPKP continued to carry out its independent verification of DAK financedactivities. In addition, the use of an existing agency, the BPKP,to independentlyverify LG completed DAK activities notonly strengthened the internal auditors capacity but also saved the Government,that was co-financing this activity,considerable resources. The cost of using BPKP was less than hiring an external consultantfor the samefunction. Scaling up a project requires a careful assessment of financial and human resource needs; the project team mayneed toidentify alternative funding sources and secure commitments.In the case of this project, scaling up meantincluding a range of LGs with diverseinitial implementation capacity and over a wide area, requiring field visit assessments.The need for the resultingadditional financial resourcesput considerable pressure onthe Borroweras the solesource for the co-financing ofthe capacity building component. In this case, even with the mitigating measures identified atappraisal, the high risk that the Government may notbe able to meet theircommitment became increasingly evident duringimplementation.The budgetary shortfall limited the implementation of capacity building activitiesneeded for theadditional participating LGsto be trainedtomeet project eligibility requirements. A more realistic implementationtimeline could have identified choke points, such as the funding shortfall, to trigger previously appraised alternative fundingsources, such as components of the loan itself. In the event, the Bank teamfound resources from the Global Partnership forOutput-Based Aid (GPOBA) for ME training. Resource needs to sustain the adoption of project-introduced reform withinan existingGovernment system after project closing need to be identified as early as possible. In this case, the Governmentaccepted that independent verification of projects financed by fiscal transfers improved DAK accountability. But after projectclose, the MOF only requests BPKP on an ad hoc basis to continue to independently verify DAK financed projects. The Governmentconfirmed that they neededmore resources to build the capacity of other agencies in this area. Project design should includethe identification of how improvementsintroduced under the project could be sustained throughan institutional componentand propose policy changes that the Government may consider so that reformscan besustained after projectcompletion. A robust ME framework, with the responsible entities clearly identified, is particularly important wherenew modalities of funding are being applied. In this case, output verification and analysis of performance by various LGs couldhave been used by responsible government agencies in informing the design and implementation of futurefunding mechanisms, notjust to build compliance capacities. In this project, for example, each government agency enhanced its capacity for direct trainingneeds of LGs based on capacity gaps from an analysis of the ME reports. However, an analysis of the outcome of thefiscaltransfer system could have benefited from a design review to inform the best uses of such transfers in line with Governmentpriorities.
P111592 | Higher Education Science and Technology | Eastern and Southern Africa | Mozambique | IDA | FCS | Human Development | Education | IDA | IPF | 2010 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/910791590156399460/text/Mozambique-MZ-Higher-Educ-Science-Techn-FY10.txt | http://documents.worldbank.org/curated/en/910791590156399460/pdf/Mozambique-MZ-Higher-Educ-Science-Techn-FY10.pdf | The ICR(paras 77 to 81) offeredseveral usefullessons, including the following adapted byIEG:1. Establishing a National Qualification Framework requires strong commitment and ownership from allstakeholders. An inter-ministerial governmental structure can ensure commitment, framework ownership, and synchronizationof qualifications of tertiary education institutions and TVET. In this case, the incorporation of TVET as part of the MCTESTP,along with the participation of area-specific experts from HEIs, helped ease the transition of students from TVET institutions toHEIs as both systems became synchronized.2. Effective accreditation mechanisms are essential to ensuring qualityof higher education programs and institutions. In the case of the CNAQ, the use of digital platforms to support datamanagement introduced more flexibility to the accreditation process for courses and programs. External evaluation of the CNAQsperformance helped the government gain insight on how to improve HEIs own processes and procedures.3.Anticipating the capacity needs for an accreditation body to meet a potential post-project increase in the demand for HEIaccreditation enables newly created bodies, such as the CNAQ, to solidify after closure.This was a key point in thecase of the HSET, as compulsory accreditation and a pre-accreditation for all new HEI programs became a requirement. The HEST didnot take this factor into account, and consequently the QNAC faced challenges in its ability to meet increased demand for itsaccreditation services, putting the sustainability of the outcome at risk.4. The following considerations cansupport the enhancement of research capacity and its relevance: Early development of guidelines with clearselection and award criteria are key for research grants implementation. Training on proposal writing and presentation aswell as feedback to researchers can accelerate readiness and quality of research proposals. Site visits to researchgroups by area-specific specialists, followed by capacity building in fiduciary matters, can help ensure compliance with researchfund procedures. Partnerships and knowledge networks with international institutions can enhance research projectfunding, harmonization of methodologies for data collection, and strengthening of higher education quality assurancemechanisms.5. Scholarships for equity and competitiveness programs can benefit from: ME processes with beneficiaries and students involved can improve the quality and relevance ofinformation. Clear eligibility and selection criteria of scholarship candidates help achieve objectives. Ashift from a demand-driven model to integrated supply-side scholarship management iseased when clear planning and monitoringmechanisms and procedures are applied to scholarship holders. Similarly, the shift is facilitated when the rights and duties ofscholarship holders, host institutions, and scholarship granting institutions are clearly defined in the scholarshipshandbook.
P111598 | Tanzania - Backbone Transmission Investment Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/803101527781014187/text/Tanzania-TZ-Backbone-Transmission-Investm-FY11.txt | http://documents.worldbank.org/curated/en/803101527781014187/pdf/Tanzania-TZ-Backbone-Transmission-Investm-FY11.pdf | Two lessons are derived from the ICR by IEG.Absence of mechanisms for the coordination ofprocurement decisions in a multi-donor-financed project can result in delays in project implementation. The need for closecoordination among donors during project implementation to ensure efficient procurement and project implementation was noted atappraisal (PAD, p.12). However, the lack of mechanisms to coordinate procurement decisions among donors, especially when there weredisagreements, resulted in a 30-month delay until the first major contracts could be signed.Thequality of the owners engineer hired to support theimplementingagency(IA) in project implementation can not only result in an on-time and successful completion of theproject activities, but also help the IA strengthen its weak institutional capacity to be utilized in future projects.Despite the initial long delay in signing the major contracts for the transmission line, the support from a highly experienced andreputable owners engineer ensured the successful completion of the project activities. At the project closing date, anadditional extension was not needed becausethere were nodelays in construction works at that point. The sameowners engineer was also instrumental in strengthening TANESCOs institutional capacityin projectimplementation, including safeguard policies.
P111598 | Tanzania - Backbone Transmission Investment Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2017 | 2024 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099705407112450505/text/SECBOS-cec6d743-ebfd-4c5a-a156-948d3e2476b7.txt | https://documents.worldbank.org/curated/en/099705407112450505/pdf/SECBOS-cec6d743-ebfd-4c5a-a156-948d3e2476b7.pdf | All factors central to a projectâ€™s outcome should be either internalized in the design of the project or addressed through measures outside the project. In this project, the objective of improving the availability, reliability, and quality of power supply was dependent on the adequacy of generation and the robustness of the distribution network, neither of which were realized as planned. Hence, the transmission line is underused. â€¢ Organizing the financing of large infrastructure projects implemented in phases in a programmatic manner can be critical in avoiding implementation delays for subsequent phases. Although the economic analysis favored a phased approach for the construction and upgrading of the BTL, a programmatic financing approach could have appropriately linked the second phase to demand conditions and provided the financing up front, which would have prevented delays in the upgrading of the substations. Expanding distribution networks to the villages beyond the immediate transmission project areas can increase the development impact of such projects on access to electricity. Some villages that were not covered by the electrification program under the project remained unserved even though they are located a short distance from the electrified villages. A significant potential exists for expanding electricity access to these villages by addressing both demand-side (cost barriers and awareness of the potential benefits of access to electricity) and supply-side (technical standards) constraints. â€¢ Large transmission projects can be ineffective in facilitating the development of variable renewable energy without an adequate policy framework and enabling environment to attract private sector investors. The BTL provides a robust transmission capacity for the integration of intermittent electricity supply from wind and solar sources, but attempts to develop renewable energy projects under a power purchase agreement failed because of the investorsâ€™ high perceived investment and operation risks. The stalled sector reform is a barrier to attract private sector investments in generation, including renewable energy.Funding from multiple donors is both necessary and desirable for large infrastructure investment projects, but inadequate coordination among donors can adversely affect project implementation, resulting in delays and risking the achievement of the project objectives. Five international donors that financed the project had their own procurement procedures with which TANESCO had to comply. This complicated the coordination of procurement reviews and approvals and resulted in delayed awards of four important contracts by 30 months. â€¢ Without technical assistance support for productive uses of electricity, electrification of rural settlements with subsistence-level economies can have limited positive impact on the socioeconomic welfare of the inhabitants, especially women. The households with subsistence-level economic activity either did not connect to electricity or used it only for lighting. The main benefit of access to electricity for women was a reduction in time required to fetch water or grind grains, but women did not receive any support on how to use the time saved from those activities to generate income for their households with or without the use of electricity. The impact of electricity on their socioeconomic welfare, hence, was limited.
P111602 | Lebanon Emergency Fiscal Management Reform Implementation Grant | Middle East and North Africa | Lebanon | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | SPF | IPF | 2009 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/933781475115848169/text/000012394-20150309080359.txt | http://documents.worldbank.org/curated/en/933781475115848169/pdf/000012394-20150309080359.pdf | The ICR offers some judicious lessons: matching project design to purpose and duration, including baselines and targets in results framework, and creating working groups with international and local experts and line staff.IEG emphasizes these lessons in particular:The Project objective and outcome targets have to be consistent with the planned project time frame. This emergency operation was to be implemented over 2.5 years. Strong collaboration between the Bank team and implementing agency staff can move a project forward even if the country is going through political upheaval and top decision makers are not able or willing to remain committed to the project objective.An excessively detailed results framework is not consistent with a technical assistance project where learning acquired during early implementation will be used to adjust areas of focus and/or activities later.
P111633 | Second Northern Uganda Social Action Fund Project (NUSAF2) | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2009 | 2016 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/139511483114872829/text/ICRR-Disclosable-P111633-12-30-2016-1483114852836.txt | http://documents.worldbank.org/curated/en/139511483114872829/pdf/ICRR-Disclosable-P111633-12-30-2016-1483114852836.pdf | Lessons are drawn from the ICR:Strengthening institutional capacity. Anticorruption measures inaproject can become models for broader social accountability. To ensure good governance and accountability for funds under thisproject, measures were taken to institutionalize the Transparency, Accountability and Anti-Corruption program at the communitylevel. Establishing systems for immediate reporting of grievances were vital in minimizing misuse of subproject resources and alsosparked demand for accountability in other social programs.Project implementation at the local level. Theuse of participatory approaches to identify beneficiaries and community priorities empowers local people to articulate and sharetheir own opinions, needs, problems, and abilities.In this project, participatory approaches enabledbeneficiaries toinfluence decision-making processesfor formulating and implementing subprojects to satisfy their needs. The close workingrelationship between the local government and the project technical support team and between the communities and the localgovernments improved the quality of infrastructure outputs at the local level. The mainstreaming of the project within localgovernment strengthened the delivery of the project at the local level and provided space for communities and local authorities towork jointly in the delivery of the project at the community level.Savings and investmentarrangements. Where community groups are linked to savings and investment opportunities, they can develop intosustainable savings groups, further enhancing their access to financial services at the local level. Some community groups underthe project are developing into village savings and loan associations and cooperatives. The benefits accruing to the individualmembers are motivating more people to join.A number ofadditional impacts were recorded that also provide usefullessons: Banking services and financial inclusion. Social protection payment mechanisms can enhancefinancial inclusion by linking program beneficiaries to mainstream financial service providers and by increasing the development offinancial infrastructure in previously underserved areas. Increasing the incomes of local households through regular socialprotection transfers can encourage the development of financial infrastructure. Broader service deliveryaccountability. As a result ofspecific social accountability mechanisms ina project, broader awareness aboutrights and responsibilitiescan enhanced. While this was intended to be related toproject-specific accountability andgovernance mechanisms, communities, beneficiaries, non-beneficiaries, and implementers began using similar structures andprinciples to lodge complaints about broader government and nongovernmental organization service deliveryprojects. Well designed projects can leverage additional resources and innovation at the local communitylevel. Besides leveraging DfID funds, the project also drew other funds. Anecdotal evidence indicates additionalresources being mobilized at the individual/community level. Insome areas, where communities selected heifers asassets, other stakeholders such as Heifer International provided add-on services such as technical advice and guidance on how tomaximize the productivity of the animals
P111661 | Tertiary Education Finance for Results Project III | Latin America and Caribbean | Chile | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2012 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/856491509641827518/text/ICRR-Disclosable-P111661-11-02-2017-1509641819229.txt | http://documents.worldbank.org/curated/en/856491509641827518/pdf/ICRR-Disclosable-P111661-11-02-2017-1509641819229.pdf | Lack of arobust results chain with clear links between project activities and intended outcomes(achievable and measurable within the project time frame)can createsignificant challenges in assessing projectachievements. In the case of this project, the results chain was not well established at the beginning of the project;numerous indicators had to be dropped/revised/added during project restructuring due to lack of relevance andmeasurability. Studies intended to inform sector policyhave limitedimpact if notbacked bythe relevant oversight authority(adapted from ICR, page 31). In the case of this project, theprojects policy support activities were not executed in a timely manner due to lack of direct high-level oversight, and therewas no evidence of impact on ongoing reforms.
P111665 | Rio de Janeiro Municipality Fiscal Consolidation for Efficiency and Growth DPL | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2011 | 2013 | 2015 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/261131475112926884/text/000012394-20150109154749.txt | http://documents.worldbank.org/curated/en/261131475112926884/pdf/000012394-20150109154749.pdf | This ICR Review concurs with the lessons identified in the ICR (pg. 27). The simultaneous policy/financial engagement at different government levels in countries where the allocation of responsibilities for policy design and implementation is decentralized would seem to be an effective approach to garner stronger policy commitments, coordination, and implementation.Clearly, more country cases are necessary to form a more definite view. Sometimes the long-term impact of structural reforms (e.g., parametric changes to pension funds) might not be fully/properly appreciated by those involved, particularly when faced with strong reluctance to move away from the status quo even thought it might be unsustainable. The Bank could by putting forward strong analytical evidence early on during policy discussions advance the formation of a political consensus in support of such reforms.
P111667 | AVIAN INFLUENZA CONTROL AND HUMAN INFLUENZA EMERGENCY PREPARDNESS AND CONTROL | Latin America and Caribbean | Haiti | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2012 | 2014 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/313581474574397793/text/000020051-20140626002035.txt | http://documents.worldbank.org/curated/en/313581474574397793/pdf/000020051-20140626002035.pdf | The ICR identifies a number of lessons, including: Close coordination and cooperation between animal health and human health are key to successful implementation of investments. Involvement of all concerned partners from the government with sound inputs from technical international agencies and vision from the donorsâ€™ community led initially to the design of a comprehensive plan, which prioritized activities, avoided overlaps and major gaps in the activities. The establishment of a medium to long-term prevention and control program is required. Transition from emergency response to medium-term system strengthening was envisaged in the design of the National Plan and interventions also need to focus on systemic improvements and basic capacity building which are sustainable in the medium to long term.Mitigation measures to close a financing gap should be part of appraisal. Potential sources of funding should be identified during preparation. Institutional strengthening in project management is the pillar to success in fragile contexts, in particular for emergency operations. Assessment of institutional needs (personnel, training, facilities, logistics and equipment), including the fiduciary agency, needs to be thoroughly carried out during project preparation to identify the most efficient implementation arrangements, and to provide for the strengthening of project management throughout the life of the Project.
P111669 | Sao Tome - Adaptation to Climate Change | Eastern and Southern Africa | Sao Tome and Principe | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2011 | 2018 | 2019 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/547331544713425900/text/Sao-Tome-and-Principe-ST-Adaptation-to-Climate-Change-LDC.txt | http://documents.worldbank.org/curated/en/547331544713425900/pdf/Sao-Tome-and-Principe-ST-Adaptation-to-Climate-Change-LDC.pdf | The ICR presented six lessons, based on which this Review highlights the following, which is well supported bythe project experience and has more potential for being useful beyond this project:1. Flexibilityin the scope of coastal adaptation projects should be balanced against relevant risk mitigation. In this project, thescope of the project components was kept flexible to allow for adjustment based on the needs of local coastal communities andfishermen in the implementation process. This took into consideration the complexity of the challenges faced by these communitiesand the multiple dimensions of solutions available for addressing them. This design facilitated a more tailored support needed fora complex project like this one. A caveat is that there are risks that as a result of too much flexibility, some importantactivities, such as identification of basic safety at sea equipment and the OM arrangements in this project, may end up notbeing carried out timely or even not included in the project design at all. Appropriate measures should be adopted to ensure thatsuch risks are addressed.This Review also notes the following additionallesson.2. Coastal adaptation projects can produce significant other development outcomes.The adaptation works in pilot communities under the project were designed to reduce flooding. After completion, these works werefound to have contributed to improved access to clean water by local residents. In addition, the preparation of a safety expansionzone as part of the adaption works resulted in construction of a new school and was expected to improve local access to electricity(ICR, para 66). According to the efficiency analysis in the ICR, the benefits from these induced non-project development outcomeswere about twice the benefits from reduced flooding.
P111741 | Municipal Development Program | Middle East and North Africa | West Bank and Gaza |  | FCS | Infrastructure | Urban, Resilience and Land | SPF | IPF | 2010 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/229201475788679001/text/000180307-20150409084538.txt | http://documents.worldbank.org/curated/en/229201475788679001/pdf/000180307-20150409084538.pdf | The following lessons are taken from the ICR with some adaptation of language: Improvements in service delivery should be conceived as a long-term process in well-defined phases. The first phase should focus on improvements to the underlying institutional and municipal management aspects of the municipalities and local governments as well as monitoring of results.A performance based grant system linking the size of investment grants to performance can incentivize municipalities to improve financial management and planning procedures and to increase transparency. The benchmarking of performance in itself can drive municipalities to strive for better rankings compared to their peers.Improved donor coordination is a rewarding albeit lengthy process, which can be successfully facilitated when all agree to make use of single set of procedure. In this project, all Funding Partners agrees to use the Bank's procurement and safeguards procedures. Under the project, the joint donor approach was successfully expanded to include joint development of the project, use of single procurement, financial management (FM), and monitoring systems, based on Bank procedures, and joint supervision missions.
P111741 | Municipal Development Program | Middle East and North Africa | West Bank and Gaza |  | FCS | Infrastructure | Urban, Resilience and Land | SPF | IPF | 2010 | 2014 | 2015 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/103331468188676148/text/97405-PPAR-P111741-Box391504B-OUO-9.txt | http://documents.worldbank.org/curated/en/103331468188676148/pdf/97405-PPAR-P111741-Box391504B-OUO-9.pdf | 4. Lessons 4.1 Since MDP I closed, the Bank and the funding partners provided additional financing for a follow-up project\. the Municipal Development Project II. The experience under MDP I encouraged the funding partners and the recipient to utilize MDP I's modes of implementation through the MDLF. The performance indicators have been tightened, and municipalities have to perform even better. This is intentional in order to reach higher objectives of the program for municipal sector reform that were agreed on between the Palestinian Authority and international donors. MDP I by design has provided valuable lessons to the follow-up projects and for the overall local government reform program in the Palestinian territories. The main lessons are\. Ã˜ A common donor approach to project design and implementation can yield positive results by utilizing and strengthening the same implementing agency, using a consistent results framework, aligning fiduciary and safeguards requirements, using similar criteria in selecting and implementing projects, and conducting joint supervision missions. In the case of MDP I, this approach avoided duplication of the efforts of the implementing agency and provided a common platform through a sector steering committee to agree on reform and next steps. Working through multiple institutional players can enhance policy and operational outcomes, but requires upfront that mechanisms are developed to formalize institutional partnerships with clearly defined common targets and timetables. Ã˜ The programmatic approach used in the Municipal Development Program allows for the evolution of effective reform solutions through identifying needs in road management, designing and implementing capacity building efforts, and learning from experience. The design and implementation of MDP I was adjusted based on lessons learned from the EMSRP II, and the results, measured through indicators, were improved. Ã˜ The inability to combine resources of the many financing partners can adversely affect the size of projects and the composition of the sub-projects. In the case of MDP I, this led to a concentration of funds in the roads sector, where investments could be modular, but conversely this led to the funding of projects that were not necessarily the first priority to the communities. Numerous small projects tend to strain the capacities of the Municipal Development and Lending Fund and its staff. On the other hand, smaller funds and stricter access may deter the larger municipalities from seeking further funding. Ã˜ Use of local codes, materials, and experiences in building roads instead of internationally accepted technical standards lowers costs, but can also compromise quality. The lack of standard materials in the case of Gaza led to local innovation in use of local material; rubble was made into brick like shapes (interloctyles). However, the life of these materials is unknown. The Technical Audit and Usability Assessment prepared under MDP I highlighted the reasons for the low costs for roads construction, including reliance on experience rather than technical specifications and codes, as well as using lower standards.
P111760 | Syrdarya Water Supply Project | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Sustainable Development | Water | IDA | IPF | 2011 | 2019 | 2021 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/527101610149896393/text/Uzbekistan-SYRDARYA-WATER-SUPPLY.txt | http://documents.worldbank.org/curated/en/527101610149896393/pdf/Uzbekistan-SYRDARYA-WATER-SUPPLY.pdf | This review has drawn three lessons incorporating material from the lessons listed on page 33 of theICR.Incomplete project preparation at appraisal can result in significant implementation delays and less focus oncapacity building activities. At appraisal, only the feasibility studies were ready and detailed design and biddingdocuments were to be prepared by the project implementation consultant (PIC) to be hired under the project. The procurement of thePIC took for two years, which had a cascading effect on the procurement of contracts for investment activities. The delay inprocurement, hence in investment activities, resulted in spending more effort to kick-start these activities rather than focusingon institutional capacity building concurrently. The project coordination unit and the Syrdarya SUE, the public utility, lackedinstitutional capacity in project implementation, financial management and safeguards policy. These responsibilities were mostlydelegated to the project implementation consultant. Hence, the project was not successful in strengthening institutionalcapacity.Closing a project with the expectation that pending activities would be financed by saved counterpartfunding can critically affect the achievement of project objectives and also weaken the Banks oversight over the completionof pending activities. Following the extension of the project closing date by 18 months, the Bank management decided notto extend the project closing date again although some investment activities were still ongoing. The decision was part of a watersupply and sanitation (WSS) sector portfolio-wide action planthe Bank had three WSS projects in implementation and a fourthone was under preparationand aimed at closing projects where the government was expected to complete the pending activitiesusing its own funds. As a result, the Banks oversight over the project activities weakened, and the government prioritizedthe expansion of the water supply network rather than connecting households to the system through metered piped connections. At thetime of the writing of the Implementation Completion and Results Report by almost one year after project closure, some transmissionand distribution investment activities were still pending, and the project had failed to achieve most of the outcome leveltargets.Absence of internal plumbing in household units in a basically urban water supply project can adverselyimpact the achievement of project outcomes and economic benefits despite the completion of the backbone of the water production,transmission and distribution network. The projects theory of change did not address the absence of internalplumbing in apartment buildings and houses in villages. The beneficiaries in these households could have access to water frompublic stand posts, which is not convenient. Despite the achievement of a significant infrastructure backbone for water supplyservices in the Syrdarya region where such network did not exist before, the project significantly fell short of achieving thetarget number of metered household connections because of the absence of internal plumbing.
P111780 | Enhancing SME Access to Finance | Europe and Central Asia | Bosnia and Herzegovina | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2010 | 2017 | 2017 | ICRR | >=100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/382871498492119896/text/ICRR-Disclosable-P111780-06-26-2017-1498492106584.txt | http://documents.worldbank.org/curated/en/382871498492119896/pdf/ICRR-Disclosable-P111780-06-26-2017-1498492106584.pdf | The first three lessons are taken from the ICR with some adaptation of language, and the fourth lesson is drawn byIEG:(i) Flexibility helps to keep projects relevant even when the macroeconomic environment changes, but operationalguidelines need to provide stronger guidance to mitigate the risks associated with flexibility, (ii) Credit lines are most relevantfor predominantly locally-owned banks, because foreign-owned banks have to reconcile local demands and the priorities of thecorporate headquarters, (iii) PIUs which have a financial intermediation mandate are preferable partners for credit lines, as theycan add value with their local knowledge of the banking and real sector, build institutional capacity and promote sustainability ofresults, and (iv) assessment of the impact of credit lines is difficult, because it has to distinguish between results accruing toPIUs, the PFI, and the ultimate beneficiaries; attribution also has to be estimated, involving an assessment of the without-projectscenario.
P111795 | NI Public Financial Management Modernization Project | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2011 | 2021 | 2022 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/681411636579222712/text/Nicaragua-NI-PFM-Modernization-TAL.txt | http://documents.worldbank.org/curated/en/681411636579222712/pdf/Nicaragua-NI-PFM-Modernization-TAL.pdf | The design called for procurement of a customized off-the-shelf IFMIS system, its deployment, training of staff, andimplementation of 8 systems within a 5-year-period. This was unrealistically ambitious given the country capacity and not in linewith the Banks PFM modernization experience elsewhere; in fact, the IFMIS diagnostic report from 2010 by an independentinternational expert (referenced in the ICR) concluded that the SIGAF project is the most ambitious IT project ever startedin Nicaragua and, as such, is riskiest due to its complexity, size, and management (Cornelius Hopmann 2010.Alternativas para la Estrategia de Desarrollo y las Modalidades de Contratacin SIGAF p3).IEG supports lessons from the ICR on the need for realistic timelines, reform sequencing, and risk assessments. IEGadapts lessons from the ICR as follows:The results framework and supervision of PFM projects should focus on the systemsand reforms supported by the project. At the design stage, the two PEFA linked PDO indicators were overly aggregated and did nothave baselines or targets. Use of PEFA indicators should be taken only when baseline data exists and when there are adequateassurances that a second assessment will be undertaken at an appropriate time to assess impact.The Bank should focusholistically on PFM reforms needed to achieve intended results, not just systems. ISRs reveal that the Bank team focused primarilyon the execution of the main contract (SIGAF) and did not discuss in much detail progress towards achieving other PFM reformssupported by the project.
P111840 | AO-Municipal Health Service Strengthening (Revitalização) | Eastern and Southern Africa | Angola | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2010 | 2019 | 2019 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/995791561833546459/text/Angola-AO-Municipal-Health-Serv-Strength-FY10.txt | http://documents.worldbank.org/curated/en/995791561833546459/pdf/Angola-AO-Municipal-Health-Serv-Strength-FY10.pdf | The ICR (pp. 33-34) offered several lessons and recommendations, including the following lessons restated byIEG:Strengthening coordination and collaboration between the health sector and other relevant ministriesfacilitates the achievement of intended project objectives. Solving some of the project implementation challenges requiredthe leverage of other ministries, such as the Ministry of Territorial Administration and State Reform for land acquisitions; theMinistry of Social Protection for outreach activities; the Ministry of Finance for local staff payments; and the Ministry of SocialAction, Family, and Women to support institutional rather than traditional deliveries.Bank flexibility and arelationship of trust promote country-Bank partnership.The ICR noted the example of the Banks responsiveness,under the project,to government needs for yellow fever vaccines when the country faced a yellow fever outbreak in 2015, thuspreventing delays in dealing with the outbreak.According to the ICR, trust and flexibility contributed to the enhancement ofthe country-Bank partnership that grew from one project to a larger program that included three projects addressing maternal andchild health, health system strengthening, expansion of child health services, and regional disease surveillance, with three grantsin support of front-line service delivery for deworming, integrated service delivery, and public financialmanagement.The choice of co-financing partners should be weighed and assessed in terms of advantages vs.disadvantages.TEPAs small grant contribution was appreciated, especially in view of significant financialconstraints, but managing the grantwas challenging because of delayed responsiveness, difficult coordination, high burden ofadministrative processing, and delays in accessing fundsthat negatively impacted related aspects in projectimplementation.
P111849 | Second Emergency Social Protection Implementation Support Project | Middle East and North Africa | Lebanon | IBRD | FCS | Human Development | Social Protection & Jobs | SPF | IPF | 2009 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/855201517937069784/text/Lebanon-LB-ESPISP-2.txt | http://documents.worldbank.org/curated/en/855201517937069784/pdf/Lebanon-LB-ESPISP-2.pdf | Lesson drawn by IEG:Afavorable political environment is a prerequisite for effectivereform. A major lesson from the project, and especially the restructuring, is the need to invest only when thepolitical economy in the sector is favorable for reform andfor ensuring national ownership of reforms across all politicalparties. During periods when there is insufficient commitmentto reform in a sector, it may make sense for theBanktofocus insteadon continued policy dialogue with the Government through analytical work andoutreach.Lessons drawn from the ICR (pp. 29-31):Emergency projectsinclude a wide spectrum of responses to crises, but political uncertainty adds to the complexity of emergency assistance.Emergency assistance, as provided for under OP/BP 8.00, is meant to comprise speed, flexibility, and simplicity. Normally, inemergency situations, governments are united in their commitment to the objectives of emergency assistance. An environment ofpolitical uncertainty adds a further dimension to responding to emergency situations and can have a potentially detrimental impacton the components of emergency assistance. This was evident under this project, as the NSSF lost commitment to the reforms it wasto implement.Multi-sectoral projects, with several implementing agencies, are notoriously complex,all the more so in an emergency mode. Detailed procedural manuals and guidelines along with regular training canenhance the efficiency and quality of a projects implementation. Further, having a separate unit to handle fiduciary mattersmay well be the most efficient way of handling aspects that could otherwise stall implementation. While this project wasunconventional in that it had a higher level objective of building a pipeline of subsequenthuman developmentprojects insupport of the Governments Social Action Plan, normally, in emergency situations, it would be preferable to have more simplystructured projects, with fewer implementing agencies and sectors.It is possible, in apost-conflict environment, to achieve concrete institutional reforms. This project was successful in achieving significantinstitutional reforms in health, education, and social protection. Most of these are notable and can be considered difficult evenin more stable environments. Reforming the hospital contracting system, establishing a comprehensive safety net program relying ona single data base of the poor, and objective targeting mechanisms are institutional reforms that many countries struggle toachieve.
P111905 | Second Infrastructure Development Policy Loan | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2009 | 2009 | 2014 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/835061474576042640/text/000020051-20140625184514.txt | http://documents.worldbank.org/curated/en/835061474576042640/pdf/000020051-20140625184514.pdf | The ICR lists several lessons including the need to link performance indicators to development objectives through a results framework. In addition, there are lessons on how to retaining the focus on the overall objectives: with so many indicators, not all equally important, progress on some inputs and the urgent need to specify "prior actions" for the next loan give an illusion of progress.One additional lesson is the need for a thorough a mid-term review that takes stock of any progress, and alerts senior officials in government on what remains for the objectives to be attained. If an important issue was overlooked initially, or framed poorly (e.g. regressive subsidies instead of how to de-politicize electricity pricing), a mid-term review could have introduced it as a prior action for the loan that followed. A series of programmatic loans require mid-course corrections, and subsequent loans should not proceed on autopilot with perfunctory approvals.
P111926 | Costa Rica Catastrophe Deferred Draw Down Option (CAT DDO) | Latin America and Caribbean | Costa Rica | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2009 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/997871549931229147/text/Costa-Rica-CR-CAT-DDO.txt | http://documents.worldbank.org/curated/en/997871549931229147/pdf/Costa-Rica-CR-CAT-DDO.pdf | The following five lessons were drawn from the ICR (paras 106 to 111) with some modification inlanguage: Well-established institutional arrangements and an advanced understanding ofdisaster risk financing instruments together with a close dialogue with the Bank enable the Government to make strategic use of theDPL with a CAT DDO. When this operation became effective, Costa Rica had an advanced understanding of disaster riskfinancing. The National Emergency Fund was already in place. Financial contributions of each ministry for emergencies andreconstruction and the insurance of public assets were mandatory. Being able to use these three disaster risk funding instrumentsin a complementary manner, the Government was able to withdraw the loan proceeds in response to several disasters instead of usingthe entire funds for a singleevent. A DPL with a CAT DDO and the related technical assistance constitute an opportunity to establish and strengthen thedialogue on disaster risk management among government agencies. Before this operation, the Ministry of Finance, the CNE,and MIDEPLAN had only a limited understanding of each others roles in and contributions to disaster risk management.Successful disaster risk management and financing required close collaboration among these institutions, which jointly developed adialogue and a common understanding on the topic. With the support of complementary technical assistance, such as the one todevelop a risk financing strategy, this collaboration was furtherstrengthened. A DPL with aCAT DDO is notonly an instrument to provide quick liquidity after a disaster. Given its flexibility, the DPL with a CAT DDO can also beused to reduce the fiscal impact of disasters in the longer term. In Costa Rica, immediate liquidity after natural disasters wasnot always required since financial resources from the national budget allocated for other purposes were used. However,replenishing these resources is critical to avoid compromising on development goals. The DPL with a CAT DDO offered a flexiblesource of funds to close this funding gap due to its soft trigger, namely the declaration of a state of emergency and a withdrawalrequest. The Government was free to decide if, when, and how much to drawdown. Having in place acarefully planned exit strategy beforea DPL with a CAT DDO closes is critical. Withthe somewhat unexpected closing of this operation because of the deterioration of the macroeconomic framework, Costa Rica lost aflexible and convenient instrument in its overall disaster risk financing strategy before being able to put an alternative inplace. Therefore, when Hurricane Nate hit very shortly after the project closed, the country had to go to the private financialmarket for additional resources, which was time consuming and expensive. An earlier effective dialogue on the implications of aninadequate macroeconomic situation and alternate arrangements before the operation closed could have avoided this problem withhurricane Nate but would not have forestalled the need fora carefully plannedrobust disaster risk management frameworkin place when external support ended. Withdrawal amounts from the DPL with a CAT DDOthat are tailored to the countrys absorptive capacity enable an effective use ofresources. With the first withdrawal of loan funds in response to the Cinchona Earthquake, the Government realized thatthe implementation capacity was limited and that the response activities take time. Learning from this experience, the Governmentadopted a withdrawal strategy that focused on smaller amounts based on both the need for funds and the absorptive capacity of theline ministries.
P111928 | MUNICIPAL DEVELOPMENT | Latin America and Caribbean | Belize | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2011 | 2017 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/316071504636061349/text/ICRR-Disclosable-P111928-09-05-2017-1504636050300.txt | http://documents.worldbank.org/curated/en/316071504636061349/pdf/ICRR-Disclosable-P111928-09-05-2017-1504636050300.pdf | Summary of Lessons from the ICR: There were 5 lessonslisted in the ICR forthis project, but twowere acknowledged in the ICR to be focused on project specific operationalissues.The three with a generalapplication are summarized below Successful re-engagement projects require particular efforts to bring thecounterpart/PIU up to speed on procurement and financial management. Extra time should be dedicated to project preparationand support to the PIU, as was the case with this project. It is important to provide enough resources forproject management and staffin the PIU toavoid capacity challenges. A few implementation challenges emerged inthis project because of a lack of specialized expertise in Belize because it is a small country. It is essentialto develop mechanisms to ensure sustainability and maintenance of works. In this project, enhanced municipal revenue andstrong commitment from mayors to continue capacity building activities were instrumental in mitigatingrisks to theprojects sustained development outcome.Lessons further identified by thisReview: It is necessary to arrange evaluations of training programs financed by projects to measureand understand their impact and added value. In the absence of an evaluation of capacity building activities, it isproblematic to attribute results to project financed training activities as was the case in this project.
P111942 | Armenia Tax Administration Modernization Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/777191578679927121/text/Armenia-Tax-Administration-Modernization-Project.txt | http://documents.worldbank.org/curated/en/777191578679927121/pdf/Armenia-Tax-Administration-Modernization-Project.pdf | Three factors contributed to good design. First, project design was informed by several pieces of analyticalwork.Second, the project built on existing SRC operations and facilities, which ensured that changes were incremental andtherefore manageable. Finally, the project design reflected an integrated approach, includingthetechnicalassistanceon institutional changes and process re-engineering provided by USAID and IT investmentsfinanced by the Bank.The efficiency of an integrated approach may be difficult to assess.In thisproject, the economic and financial analysis exclusively focused on the efficiency of Bank-financed components, including thebenefits of the USAID-financed activities but not their costs.There are key features to developing complexICT systems.The upgrading to a comprehensive and integrated tax management system is usefully accompanied by aseries of key considerations: (i) vision and strong leadership to ensure consistency in IT strategy and priorities; (ii) the rightsequencing of technical assistance and IT investments to help ensure smooth and timely implementation; (iii) realistic timelineswhen choosing between a customized system (the project option) and a commercial off-the-shelf solution; (iv) the local ITmarkets capacity when opting for customized systems;and (iv) the extent of technical assistance needed to supportbusiness process reengineering and change management.
P111943 | Afghanistan Power System Development Project | South Asia | Afghanistan | IDA | FCS | Infrastructure | Energy & Extractives | RETF | IPF | 2009 | 2017 | 2019 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/326571560896959086/text/Afghanistan-AF-ARTF-Power-System-Development.txt | http://documents.worldbank.org/curated/en/326571560896959086/pdf/Afghanistan-AF-ARTF-Power-System-Development.pdf | First lesson is derived from the ICR. The other two are taken from the ICR with some adaptation oflanguage.A poorly designed project is unlikely to produce good results. The originalproject development objective (PDO) was clearly defined and funds were secured from the Afghanistan Reconstruction Trust Fund(ARTF). However, there was a major mismatch between the project activities, expected outputs and outcomes. Some project activities,such as energy efficiency activities and much needed rehabilitation of switchyards in Naghlu and Mahipar, did not directly relateto the PDO. The flaws in theory of change and project design resulted in two PDO revisions making the PDO more of an output levelobjective, rather than an outcome level one. In fragile countries, relying on third party for projectmanagement is necessary; however, if this is not properly designed and managed, it can be costly and ineffective in achievingproject outcomes and strengthening institutional capacity in the country. Because of the weak capacity of the Ministry ofElectricity and Water (MEW) to implement the project, a project management firm was contracted to manage the project activities.Not only did this prove to be very expensive, it also resulted in almost no local capacity strengthening, which is as important asbuilding infrastructure in fragile or post-conflict countries, like Afghanistan. After the transfer of the implementation of theproject activities to the utility, DABS, there was a rapid increase in the quality of delivery, as a result of the intensivetraining given in Dubai to the DABS staff in charge of project implementation. This kind of capacity building gained throughproject implementation would also increase the project implementing agencies ownership of theproject. In fragile or post-conflict countries, where project sites cannot be visited due to securityconcerns, utilization of local engineers or third party monitoring (TPM), different than the project management firm, can improveproject monitoring and evaluation (ME). The project faced serious problems in implementation, supervision and datacollection from the start. The project teams inability to visit project sites after 2014 due to security concerns weakenedproject supervision. However, after the hiring of local engineers by DABS, there was partial improvement in project supervision.Towards the end of the project, data could be collected thanks to TPM funded by ARTF. The projects results were evaluatedagainst the data collected by TPM.
P111996 | Upgrading and Greening the Rio de Janeiro Urban Rail System | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099121223125527914/text/P1119960a1ff450470a7df07a4ff225b60b.txt | http://documents.worldbank.org/curated/en/099121223125527914/pdf/P1119960a1ff450470a7df07a4ff225b60b.pdf | This review has drawn three lessons based on the information in the ICR.If the replacement of an aging trainfleet with newer trains is not supported by other interventions to improve the safety, affordability, and accessibility of theservice, the improvement in the level of service and shift to public transport can be limited. The project successfullyfinanced the acquisition of 106 trains to replace the aging rolling stock of SuperVia and expanded the fleet to above 200 trains.However, the project did not intervene in other aspects of the rail service that would holistically improve the service quality,such as safety measures, fare integration, and non-motorized access to the stations. This resulted in a lower improvement in theservice quality. For example, because safety measures were not implemented, such as barriers installed at the level-crossings, theoperational speed of the trains had to be restricted to avoid accidents. The project could not complete a plan for fare reform thatwould make rail transit more attractive; therefore, when suburban mobility started to bounce back in 2021, passengers preferred bustransport as the bus fare is subsidized. In conclusion, the replacement of the aging rolling stock with new trains is necessary,but for a significant improvement in the service quality and a shift to rail transport, a holistic approach should be adoptedencompassing other aspects of rail transport.Inadequate capacity and interest of the counterpart in technicalassistance activities can critically impact the achievement of project outcomes. The project financed various studies andplans related to suburban rail transit and logistics in the State of Rio de Janeiro and the RMJR, but some important studies couldnot be completed. The main reason was the insufficient in-house technical capacity of the project implementation entities inpreparing the necessary technical and bidding documents. The second reason was insufficient interest from the decision-makingauthorities in implementing these plans and studies and frequent turnover in the political context. Therefore, the project fellshort of achieving its objective to improve the transport management and policy framework in the State of Rio de Janeiro and theRMJR. The high number of projects to be prepared under the project was also a hurdle; however, given the 13-year projectimplementation period, most of the technical assistance activities could have been completed by projectclosing.Numerous project restructurings may not be instrumental in improving the projectsperformance. The project was restructured eight times including an additional financing earlier in project implementation.These restructurings were mostly processed to use significant loan savings and unused funds to finance additional projectactivities, but most of those activities could not be completed and, therefore, cancelled, such as the purchase of seven light-railtrains, rehabilitation of CENTRALs buildings, and the construction of security walls and level-crossings fences to improvesafety. The restructurings were not effective in improving the projects performance, and, eventually, US$80.65 million offunds were cancelled.
P112011 | GT Enhancing MSME Productivity Project | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | IPF | 2011 | 2016 | 2018 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/797731504637345565/text/ICRR-Disclosable-P112011-09-05-2017-1504637333665.txt | http://documents.worldbank.org/curated/en/797731504637345565/pdf/ICRR-Disclosable-P112011-09-05-2017-1504637333665.pdf | Five lessons are drawn from the ICR (pages 20-23), with some adaptation.A project that adopts theprogrammatic approach must consider the institutional capacity of project participants to design, develop, and implement eligiblesub-projects that are aligned with the program objectives. In this case, the project postponed making the basicdecision of which agribusiness value chains to support to the implementation phase of the project, expecting MSMEs and other valuechain members to readily prepare action plans and eligible projects. Many aspects of project design were also left incomplete,including results indicators and targets. Considering the weak institutional capacity in the country, the project could havebenefitted from substantive project preparation work, possibly supported by a technical assistance (TA) grant or loan, to identifyand analyze the potential value chains, draw value chain strategy and action plans, and prepare eligible sub-projects for fundingby the time of project appraisal. The project lending operation could then have concentrated on supporting the implementation ofthe value chain sub-projects.An Operations Manual can serve as a useful tool for the efficient implementationof a project. The project lacked an operations plan that could have settled many of the ensuing confusion about processflows, procedures, and other technical details in the implementation of the project. An institutional plan could have alsoclarified the roles, responsibilities and powers of the bodies created to implement the operation. The execution of the projectsuffered from many implementing entities having ill-defined roles and powers. The Steering Committee turned out to have beenprohibited by law from enacting governmental decisions because it included representatives from the academic community, civilsociety, and other non-governmental bodies. The Advisory Committee could advance recommendations but not make binding decisions.And in this case, the PIU did not have budget executions powers.In view of the variances between Bankprocurement standards and guidelines and a borrowers procurement conventions and practices, it is vital that the Bank and agovernment thoroughly vet and settle differences in procurement policies and methods before project implementation. It isalso vital that the Bank determine that a client government has a full understanding of the project procurement rules. The LoanAgreement (pages 12-14) required adherence to the Banks Procurement Guidelines and Consultant Guidelines. Nonetheless,procurement was a huge challenge for this operation because of policies that conflicted with each other,confusion regarding the application of which policies, and a lack of a thorough understanding of the procurementprocess.Where child labor is a known practice, the Bank and a government need to investigate anddiscuss the issue early on during project preparation. Children work in post-harvest activities in the export vegetablevalue chain in rural Guatemala, a practice common among indigenous communities in Latin America, where the family acts as a laborunit. The issue was raised with the Bank during project implementation. In response, the Bank barred disbursements from the secondcomponent of the project until mitigation measures were developed, an action that delayed implementation of the component by half ayear. Agreement was subsequently reached on a suitable course of action: (a) grant sub-agreements committed the projectbeneficiaries to desist from using child labor; (b) value chain training activities were to include training on child labor issues;(c) value chain social assessments were to cover child labor issues; and, (d) the Government pledged to protect the rights ofchildren to security, education, and recreation.Restructuring exercises need to focus on actions that aregermane to the objectives of the project and not be distracted by unrelated or peripheral proposals, particularly near a projectclosing date. A Government request for the funding of feasibility studies for irrigation projects lay outside the scope ofthe project. Similarly, extraneous to the project were attempts to incorporate activities targeted at the communities affected bythe construction of the Chixoy hydroelectric dam four decades earlier. While providing individual and collective reparations todisplaced communities is a priority for the Guatemalan Government, these proposals would have been better considered as part of anew operation, with adequate time and resources provided for their preparation, rather than being tacked on to an old projectnearing its closing date.
P112017 | DJIBOUTI - Food Crisis Response Development Policy Grant | Middle East and North Africa | Djibouti | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | SPF | DPF | 2008 | 2009 | 2011 | ICRR | Less than 10 million | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/143171474587105499/text/000020051-20140624155439.txt | http://documents.worldbank.org/curated/en/143171474587105499/pdf/000020051-20140624155439.pdf | A program of cash transfers targeted at the poor is preferable to elimination of food taxes. In this development policy operation the government was initially opposed to targeted transfers. Instead it opted for eliminating taxes on basic food items as a quick way to respond to price crises. However this had a high risk that there would be substantial leakage to less-poor groups.Emergency operations are necessarily short-term in focus; their effectiveness can be enhanced if they are supported by follow-up operations designed to strengthen the institutional framework for coping with future crises.There is no justification for burdening small, emergency operations with a costly and sophisticated monitoring and evaluation system; but in order to make mid-course adjustments and to ultimately check project outcome it is essential to have a working M&E system.
P112017 | DJIBOUTI - Food Crisis Response Development Policy Grant | Middle East and North Africa | Djibouti | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | SPF | DPF | 2008 | 2009 | 2012 | PPAR | Less than 10 million | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/107911468243915477/text/671890PPAR0P110ite0Cover0Box369247B.txt | http://documents.worldbank.org/curated/en/107911468243915477/pdf/671890PPAR0P110ite0Cover0Box369247B.pdf | 6. Lessons 6.1 There is a trade-off between speed and targeting accuracy in the preparation of emergency response operations. Although the staples on which taxes were lifted in Djibouti were key components of the food basket of low-income households, there was necessarily a significant leakage to better-off groups. On the other hand, budget support allowed for rapid response and was appropriate to the circumstances of Djibouti. More investment lending was not an option given that Bank commitments had already hit the IDA allocation limit. 6.2 Emergency response can be fruitfully combined with the development of a longer-term program. The raison d'etre of the Bank is to support long-run social and economic development and in responding to emergencies it should keep this mandate in view. The Djibouti operation showcased this approach. Given the small size of the grant the fiscal space created by offsetting tax exoneration was ultimately of less importance than the opportunity to stimulate a dialogue on new approaches to safety nets. This opening was consolidated by the simultaneous deployment of institutional development funds aimed at strengthening the capacity to target social protection to the poor. 6.3 It is not self-evident that reducing taxes on food staples will lower their prices\. if tax reduction is to be used as an instrument there should be sufficient evidence to demonstrate that the proceeds will be passed through to the consumer and that the poor will be targeted. The food market in Djibouti is dominated by a small group of importers, facilitating collusion in the setting of prices. In the event of a tax reduction, pass through to consumers may therefore be less than expected. It would have helped if the Bank had sought more information about market structure and the consumer demand profile before choosing tax reduction as the preferred instrument to support.
P112033 | Uttar Pradesh Sodic Lands Reclamation III Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/472371571762264197/text/India-IN-UP-Sodic-III.txt | http://documents.worldbank.org/curated/en/472371571762264197/pdf/India-IN-UP-Sodic-III.pdf | The ICR included three lessons. These are emphasized below with some adaptation oflanguage: Functional farmer collectives are needed for improving market access. Formation offully functional FPOs is a long and arduous process that is hard to accomplish within typical project timeframes. Even withthe hiring of specialist service providers, to helpthe projectwith the formation and strengthening of FPOs, it was onlyin year 5 of implementation that the initial set of FPOs were deemed ready to undertake their activities and by project closing,many FPOs, (around 38 FPOs were still considered weak and in need of strengthening if they were to serve theirroles. Identification and selection of project targets is critical to ensure timelyimplementation. The largest share of project investments was meant to reclaim sodic land patches identified andselected based on specific technical selection criteria. During implementation, it became evident that patches in the targetdistricts, meeting the criteria were limited. An assessment of the available patches during preparation would have led to morepragmatic identification and selection criteria. Sustainability of outcomes needs carefulconsiderations of Operation and Maintenance arrangements. Infrastructure development in many countries has often followedthe build-neglect-rebuild paradigm mainly because of poor asset maintenance. Project design anticipated challenges with OM and madeprovisions for maintenance of the rehabilitated drains, with clear responsibilities for both government (ID) and beneficiaries.These maintenance arrangements were triggered upon completion of rehabilitation of any drains and by project closing they were still functional and should help sustain project outcomes.
P112052 | Mozambique Education Sector Support Program Fast Track Initiative Catalytic Fund | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2009 | 2011 | 2013 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/828091474893774559/text/000020051-20140625223739.txt | http://documents.worldbank.org/curated/en/828091474893774559/pdf/000020051-20140625223739.pdf | The overarching lessons reported in this ICR are synthesized and restated as the following:Successful execution of decentralized activities requires capable managerial personnel, and capacity building. With this project, supervision of school construction and fiduciary management was done at the provincial and district levels, yet insufficient personnel and training constrained the progress in the civil worksProviding grants to schools can be a way of directly targeting resources. This project found that schools were able to plan and manage the funds. However, while training strengthened school councils further support was needed to facilitate development of school plans, budgeting and financial reporting (ICR, p. 21). Insufficient monitoring and evaluation constrains accountability. This project document contained a brief description of the sector plan and lacked a specific discussion of results chain, indicators, and components/activities, thus making it difficult to track progress. Moreover, during the project implementation, evaluations were not implemented to provide more evidence of effectiveness of interventions.
P112073 | BR Federal Integrated Water - Interaguas | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2012 | 2019 | 2020 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/675681566228793005/text/Brazil-BR-MST-Federal-Integrated-Water-Sector.txt | http://documents.worldbank.org/curated/en/675681566228793005/pdf/Brazil-BR-MST-Federal-Integrated-Water-Sector.pdf | The ICR (p. 25-28) provided several useful lessons learned: Being realistic about the size of a loan fortechnical assistance is important for both the Bank and the Borrower. In this project it the size of the Bank loan wassignificantly too large, especially, since only US$8.04 million was disbursed at the restructuring, already four years into projectimplementation. Also, given the political and economic situation, the risk was High that disbursement would not increasesignificantly. When project implementation includes more than one autonomous ministry or several agencies, it iscritical that that one entity with general authority takes on the responsibility to coordinate among all participating entities.In this project, the MPOG did not take on such responsibility which resulted in implementation challenges due to lack ofleadership and clarity of responsibility for coordinating the program and its daily activities. It isimportant that responsibilities for Financial Management and Procurement are defined during project preparation and capacitybuilding activities are conducted if necessary. One of the reasons for implementation delays in this project was thecomplex and evolving procurement arrangements which were not implemented as defined in the projectsPAD. Study tours can foster cooperation among institutions through learning about different approaches forinstitutions within and across government levels can effectively work together but also to build personal relationships betweenstaff from different implementing agencies. In this project the study tours build stronger personal relationshipsamong key stakeholders and fostered the collective commitment to achieve a shared goal.
P112074 | BR Sergipe Water | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2012 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/201531623417942517/text/Brazil-BR-Sergipe-Water.txt | http://documents.worldbank.org/curated/en/201531623417942517/pdf/Brazil-BR-Sergipe-Water.pdf | The ICR (paras.79 to 89) lists a number of lessons thathave relevance for projects implemented in similarenvironments:1. Client capacity needs to be realistically assessed early on in project design: The experience underthis project has shown that, when designing the project,it is essentialto make a realistic assessment of theclients implementing capacity, particularly when it is a first-time client not adequately familiar with Bank fiduciaryprocedures and requirements. Basic training in procurement, financial management, and safeguards procedures needs to be providedearly on in the implementation process.2. Interventions in irrigation related improvements need to be undertakenat an earlystage of project implementation: Capacity building activities aimed at improved soil management andconservation practices need to be implemented after the new irrigation systems are in place to maximize thedemonstrationeffects and increase ownership. Improved practices are more likely to be accepted and used after thephysicalinvestments are in place.3. Training of rural producers in improved techniques and practices requiresclose and continuing contact: The experience under the project has shown that close and continuing contact and social actionwith the targeted beneficiaries is essential to motivate participants and keep them engaged.4. Projects should bedesigned to have sufficient flexibility to adapt to changing priorities: An important priority that emerged during projectimplementation was the emergency response that was required to address the collapse of a major water supply pipe supplying water tothe city of Aracaju. Project funds had to be re-allocated to address this need.
P112096 | Basic Education Project | Eastern and Southern Africa | Sudan | IDA | FCS | Human Development | Education | RETF | IPF | 2009 | 2013 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/328061474898864162/text/000020051-20140626122237.txt | http://documents.worldbank.org/curated/en/328061474898864162/pdf/000020051-20140626122237.pdf | Lessons from the ICR: Â· Institutional assessment needs to be integral part of the design, taking into account both capacity and incentive to deliver of the proposed implementing agencies. Assigning the implementation responsibility to the agency that has ownership of the project outputs increases the chances of project activities being implemented satisfactorilyLessons from the ICR, adapted by IEG: Â· Because interventions to improve the teaching force involve a range of complex issues (recruitment and remuneration, deployment, professional development, etc.), they require adequate time to be well-structured politically, administratively, and technically. Â· Improved education infrastructure can only occur in the context of other available infrastructure: roads, water, qualified labor; this reduces the likelihood that the most remote areas are the most suited for investment.Lessons from IEG: Bank projects are not implemented in a vacuum, and reference to other ongoing efforts and results by other partners is essential for consideration of the relevance, efficacy, and efficiency of the project.
P112097 | Technical Assistance for Water-sector Capacity Building | South Asia | Afghanistan | IDA | FCS | Sustainable Development | Water | RETF | IPF | 2009 | 2013 | 2015 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/665061467986261989/text/ICRR14635-P112097-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/665061467986261989/pdf/ICRR14635-P112097-Box393183B-PUBLIC.pdf | The following lessons were derived from the ICR (p. 19):Capacity building takes time, particularly in post-conflict areas where the talent base is low. There may be little value in building very specialized analytical capabilities in-house especially when facing the challenges of attracting and retaining talent. On the job training supplemented by short courses over a short implementation period may not suit a pos- conflict scenario. Using technical consultancy as a vehicle to carry out capacity-building requires a clear match of skills, and realistic timelines to attract qualified experts who need to be in place by the time the project starts.When introducing new concepts such as integrated water resource management, project design calls for time and effort to better establish government commitment.
P112107 | Liberia Emergency Food Support for Vulnerable Women and Children | Western and Central Africa | Liberia | IDA | FCS | Infrastructure | Urban, Resilience and Land | SPF | IPF | 2008 | 2011 | 2013 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/869651474587251631/text/000020051-20140625060905.txt | http://documents.worldbank.org/curated/en/869651474587251631/pdf/000020051-20140625060905.pdf | The last three lessons are drawn in part from the ICR, pp. 20-21. 1. If emergency operations are to be assessed by results, project objectives need to be framed accordingly. This also entails a results framework at the outcome or intermediate outcome level, appropriate measurement methods and adequate budgetary resources.2. Emergency projects with simple designs and straightforward objectives are likely to be implemented successfully. A strong commitment from government and partners, including the Bank, is also needed to prepare and implement emergency programs speedily and effectively.3. In fragile countries with weak institutional capacities, reputable international agencies already operating in the country may be good partners for implementing project interventions successfully and rapidly. WFP was firmly on the ground in Liberia and, with its logistical capacity, was ready to get things moving fast. However, for such partnerships to be effective there needs to be a firm understanding along the lines spelled out in the fourth lesson, below.4. When, under the UN Framework Agreement, the Bank turns to a UN agency for implementation, monitoring and reporting will be more timely and useful if there is full agreement at the outset by both parties on performance indicators (both baselines and targets) and the contents and frequencies of monitoring reports, as well as the need to report significant operational events, such as thefts, promptly.
P112131 | Mauritania Road Corridor ACGF | Western and Central Africa | Mauritania | IDA | Non-FCS | Infrastructure | Transport | RETF | IPF | 2011 | 2015 | 2019 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/398451544562670230/text/Mauritania-Mauritania-Road-Corridor-ACGF.txt | http://documents.worldbank.org/curated/en/398451544562670230/pdf/Mauritania-Mauritania-Road-Corridor-ACGF.pdf | The following are the key lessons reported in the ICR with some adaptation oflanguage:While parallelco-financing might be a useful instrument in certain situations, itsbenefitsneed to be carefully weighed againstthe risks. In this case, the parallel co-financing arrangementexposed the Bank to the risk of project delay, and this negatively influenced the project outcome. Therefore, ifparallel co-financing with a common PDO is chosen, thebenefits ofusing this instrument should carefully be laid out inthe project documents andweighed against the risk that theBank isresponsible for the project as awhole.The perceived effect of a split rating might disincentivize task teams to restructure aproject. In this case, the project team decidednot to restructure the project because when it becameclear thatthe project portionof the co-financier would not be completed on time, they felt that a restructuring would not havesubstantially changed the project outcome rating giventhe split rating requirement.Adedicated task team assigned to the project throughout the project cycle enhances the chances of successful projectimplementation. The implementation of this project confirmed a well-known lesson, which is that the continuity of the taskteam throughout the project cycle can contribute to the success of a project. The degree of trust engendered by a long termacquaintance with the countrys institutions enabled the Bank team to defuse an escalating conflict between the Grantee and acontractor that could have foreclosed the project.Sustainability of road projects requiresattention to complementary measures. These include assuring adequate maintenance and effective axle load control fortrucks. The damage caused by overloaded vehicles, especially to roads built on sand, is large and costly to remedy. Engaging theprivate sector in establishing and operating weigh stations may be an option to pursue.
P112157 | EMERGENCY FOOD SECURITY AND SEED IMPORTS PROJECT | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Sustainable Development | Agriculture and Food | SPF | IPF | 2008 | 2013 | 2015 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/868561475093100280/text/000012394-20150409080814.txt | http://documents.worldbank.org/curated/en/868561475093100280/pdf/000012394-20150409080814.pdf | The ICR (p. 20) identified several valuable lessons, including:Emergency situations present a tradeoff challenge between an immediate response and building long-term capacity. The governmentâ€™s wish to hire local NGOs for the project implementation led to delays but it might have also contributed to a longer-term engagement between local NGOs and local communities. This might increase the sustainability of project activities. Depending on the emergency it can be critical for a country to receive additional financing in order to sustain ongoing activities and to implement new activities. In Tajikistan the original financing addressed the food crisis while the additional financing allowed to include additional beneficiaries and address longer-term structural challenges in the agricultural sector. This will make poor rural households less vulnerable to future shocks.Establishing entities such as the Community Production Groups and the Community Seeds Funds in Tajikistan can be beneficial during land reforms. NGOs provide information and enable farmers to exchange information among themselves to make more informed decisions. This can be the first step of producers and farmers association.
P112258 | Private Housing Finance Markets Strengthening Project | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2009 | 2013 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/225411474566628289/text/000020051-20140626115646.txt | http://documents.worldbank.org/curated/en/225411474566628289/pdf/000020051-20140626115646.pdf | The ISR lists six lessons around the following themes: (i) it is difficult to effectively pursue dual objectives, especially when one is short-term in nature, the other long-term; a point also related to the instrument used which while expedient may have contributed to shortcomings in project design; (ii) market stabilization is especially important at a time of crisis; (iii) there should be better links between inputs and results sought; (iv) project design may limit its ability to leverage change; and (v) a good operational relationship may provide a gateway to a strong technical dialogue.A specific lesson emerging from the present review concerns the importance of planning for and undertaking a mid-term review of the project while substantial funds still remain undisbursed.
P112262 | Upper Secondary Education (MUSE) Development Policy Loan | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Human Development | Education | IBRD | DPF | 2010 | 2011 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/935211489413538931/text/Mexico-MX-Upper-Secondary-Education-DPL.txt | http://documents.worldbank.org/curated/en/935211489413538931/pdf/Mexico-MX-Upper-Secondary-Education-DPL.pdf | The following lessons are selected from the ICR:The DPL Programmatic Series was the most suitable Banklending instrument to provide general budgetary support while accompanying a reform program. The DPL Series allowed adjustment tothe pace in which policies were implemented and was also helpful for policy continuity despite changes in the administration andruling party in December 2012.In countries with strong technical capacity such as Mexico, DPLs canusefullyfocus on those elements of the reforms that will benefit most from Bank engagement. In this operation, the Bank triedto respond to the clients technical demands while being selective in choosing in which areas to support the Government basedon team composition and availability of resources.Complementary technical assistance can help to inform theGovernment reform and achieve the DPL Series objectives. In this operation, the technical collaboration between the Bank and theGovernment helped shape the policies introduced by the upper secondary education reforms based on evidence and international bestpractices. The provision of just-in-time technical assistance helped overcome the main obstacles faced during implementation of thereformAligning DPL Program indicators to official indicators helps decrease the ME burden of the Program for theGovernment and allows the team to obtain more reliable and timely information. When the Bank team aligned its indicators to theofficial indicators in DPL 3, ME was greatly improved because the implementing agency had more pressure to periodicallycollect and report data on official indicators.Introducing school accreditation processes requires taking intoaccount schools starting conditions and their ability to improve the education services they provide. Gaining fullaccreditation to enter the upper secondary education system proved to be challenging for most schools in Mexico. In many instances,schools found it difficult to comply with the full accreditation criteria and many lacked the necessary resources to complete theaccreditation process. To tackle these issues, as in the Mexican case, policies might consider allowing schools to gain temporaryaccreditation if they comply with a set of minimum criteria of quality and commit to specific quality improvements over a certainperiod of time.
P112264 | Strengthening the Business Environment for Enhanced Economic Growth DPL | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2011 | 2012 | 2013 | ICRR | >=100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/759541475094036088/text/000020051-20140625230318.txt | http://documents.worldbank.org/curated/en/759541475094036088/pdf/000020051-20140625230318.pdf | The lessons listed in the ICR (section 6) are mostly generic: (a) importance of strong country ownership and commitment; (b) critical relevance of prior analytical work; (c) need to incorporate a solid M&E, including well thought through outcome indicators. Broader lessons from the present review are as follows:When legal reforms are not immediately attainable, the reform agenda may be pursued somewhat successfully through regulatory and administrative measures. Resulting outcomes may help eventually overcome vested interest and political reticence against deeper reforms.In some cases, a "horizontal" programmatic approach may be an appropriate way to tackle issues on multiple fronts through analytical work, investment lending and a stand-alone DPL.As stated in the ICR analysis (not under lessons learnt), the full results of a DPL that is not part of a series may not be adequately measured at project closing.
P112312 | GT Fiscal and Institutional DPL | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2009 | 2010 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/814771474564391608/text/000020051-20140625060805.txt | http://documents.worldbank.org/curated/en/814771474564391608/pdf/000020051-20140625060805.pdf | The ICR points out the limits of short-term actions such as those supported by the series, in supporting politically controversial reforms. Actions requiring legislative approval will be difficult (e.g. tax reform) without a strong impetus of public support (access to information). Reforms that must be sustained over a long time period to achieve success (improved financial sector supervision) need support from multiple operations, while some measures that could be introduced under the authority of the executive (improved tax administration) did deliver short turn results (reduced evasion). Further, the impetus of external economic pressure can add an impetus to reform when both authorities and the Bank can be flexible enough to respond at the right time. Going beyond the ICR, the uneven outcome of PFM and procurement reforms indicates that there are limits to what can be achieved with new laws, formal processes, and electronic systems. Drawing on the WDR2011, future work might explore the functioning of informal flows of resources through patronage networks, and see if there are good practices where these resources support valuable public goods, and opportunities for using such practices to help design more far-reaching reforms of the formal public resource management system.
P112321 | Central African Republic: EFA-FTI Catalytic Fund Preparation | Western and Central Africa | Central African Republic | IDA | FCS | Human Development | Education | RETF | IPF | 2009 | 2015 | 2016 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/964901468224385213/text/ICRR-Disclosable-P112321-06-07-2016-1465335272213.txt | http://documents.worldbank.org/curated/en/964901468224385213/pdf/ICRR-Disclosable-P112321-06-07-2016-1465335272213.pdf | IEG has synthesized the lessons contained in the ICR (pp. 39-40) to the following: Complementing governmentcapacity with external service providers and delegated project management and implementation arrangements can be effective infragile contexts when there is adequate understanding of capacity constraints of all parties. Balancing state capacitybuilding with external service providers can work, but this strategy should be based on a thorough analysis of capacity, which wasnot undertaken at entry. Such an analysis may have pointed to issues that would ariseduring implementation that couldhave been mitigated. These arrangements between government and external service providers can improve operational capacity of allparties when accompanied by strong supervision from the government and development partners. A robust monitoring andevaluation system is essential to track implementation and measure achievement of objectives and allow attribution to projectinvestments. In this case, sector-wide indicators were established, as the common practice within Fast Track Initiativeprojects isto align with country ME systems to facilitate data collection, ownership, and sustainability. While thisselection of indicatorswas done to align with country ME systems, there still is a need to select indicators related toproject-financed activities to measure the specificimpact of the project. To build country capacity, clear protocols need tobe established for indicator monitoring to ensure that data collection and analysis capacity exists or iscreated. In low-capacity and/or fragile contexts, design simplicity and close supervision are essential.Close supervision of civil works activities by the Bank and Implementing Agency is needed in these contexts, particularly whenconstruction occurs in more remote areas. Given low capacity, more support is needed to establish the technical aspects ofcivil works, such as architectural design and water studies. These studies were not done at preparation of thisproject,and the technical audit was conducted late in implementation. As a result, there were cost inefficiencies andproblems with building quality throughout the projects lifetime. Developing prototypes for certain construction elementsas a reference for firms may have helped to improve the quality of both design and execution. There is high value in theWorld Bank remaining engaged with client countries during periods of crisis, including in cases where policies require thesuspension of project disbursements. For this project, the Bank maintained dialogue with the government and coordination withother development partners on supporting the education sector during the crisis. This facilitated the Banksre-engagement when the political and security situation allowed. Maintaining dialogue and financing operations on acase-by-case basis can also help mitigate the negative effects of crisis at the country level, by providing technical advice orfinancing for critical activities to maintain stability in an education sector.
P112334 | Uganda: Energy for Rural Transformation APL-2 | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2009 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/214341510675721822/text/ICRR-Disclosable-P112334-11-14-2017-1510675709492.txt | http://documents.worldbank.org/curated/en/214341510675721822/pdf/ICRR-Disclosable-P112334-11-14-2017-1510675709492.pdf | The following lessons were drawn by IEG from the ICR.Projects can face serious problems inachieving the project objectives if the project design relies on the involvement of the private sector without a thoroughassessment of the latters interest to the project. The project design had assumedthat the private sector finance would be available for financing household connections, which did not materialize. Furthermore, itwas assumed that the private ICT operators would be interested in the ICT investment opportunities under Component 2. Thisassumption also proved to be wrong and no project activity could be implemented to achieve the second objective to increase ICTaccess in rural areas of Northern Uganda.Effectiveness of independent verification agents plays akey role not only in monitoring the progress of the project implementation, but also in achieving the projectobjectives. Independent verification agents (IVAs) hired to monitor the progress of output-based aid (OBA) subsidieshad differing levels of performance. The verification of OBA subsidies by the IVAs helped the project team supervise the projectprogress towards achieving the project goals, but, at times, their poor performance caused the project implementation to slowdown.
P112346 | Affordable Mortgage Finance DPL | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2010 | 2015 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/998221478615065246/text/ICRR-Disclosable-P112346-11-08-2016-1478615044879.txt | http://documents.worldbank.org/curated/en/998221478615065246/pdf/ICRR-Disclosable-P112346-11-08-2016-1478615044879.pdf | Three lessons are drawn from the ICR (pages 34-35), with some adaptation.One, a housing subsidy program hasmuch to learn from the international experience with mortgage-linked subsidies. The Bank drew heavily from global experiencewith mortgage subsidies, including those offered by Mexicos Sociedad Hipotecaria Federal, Malaysias Cagamas,Jordans Interest Buy-Down Subsidy, and Chiles Upfront Grant Subsidy, to help Egypt transition from a supply-sidehousing subsidy program to demand-side mortgage subsidy program. Egypts Affordable Mortgage Program promotes the use ofmarket-based mortgage loans, with subsidies extended to low- and middle-income homebuyers to make the mortgages affordable.Two, a policy reform program requires a heavy dose of technical assistance, particularly when the institutionalcapacity to advance the reform program is vital, but may be lacking. The Bank extended substantive technical assistance to theGovernment and to the Mortgage Finance Fund not only to help formulate policies, draft laws, and write regulations for the mortgagesubsidy program but also to help the MFF with organizational, staffing, and operational issues. More than simply increasing thenumber of market-based mortgages with subsidies, it was vital to have built up a more capable MFF that could advance to affordablemortgage program forward, far beyond the life of the DPL.Three, extensive consultations with stakeholders areessential to initiate and sustain a reform program. The Bank and the Government engaged many stakeholders in housing andhousing finance, including banks, mortgage finance companies, regulatory agencies, and international donors, to design theAffordable Mortgage Finance Program and to advance the program objectives at a time of political and economic uncertainty in Egypt.That the Government involved stakeholders encouraged an informed evaluation of the reform proposals, enhanced the credibility ofthe new subsidy policies, and generated expectations that the program would be sustained.
P112359 | NanGuang Railway Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2009 | 2015 | 2016 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/938851468242670903/text/ICRR-Disclosable-P112359-06-09-2016-1465476833556.txt | http://documents.worldbank.org/curated/en/938851468242670903/pdf/ICRR-Disclosable-P112359-06-09-2016-1465476833556.pdf | The ICR draws the following main lessons from the experience of implementing this project.(1) Unified controlover railway program development, project design, financing and implementation can help in achieving overall success, even when theBank contribution is relatively low.In the case of this project, the China Railway Corporation was solelyresponsible for planning, financing and implementing individual projects and creating delivery mechanisms.The unified controlover the project enabledtimely completion of activities, despite the relatively marginal financial contributions from theBank.(2) Although agglomeration benefitshave been recognized in theory with railway projects, there are fewquantitative datato assess the results. This may partly due to the longer time span required for reaping thebenefits. An ex post analysis after five or ten years after the railways have been in operation can be undertaken to assess thequantitative benefits.(3) Adequate provisions need to be made at the design stage for a Mid TermReview. An assessment through the Mid-Term review can be helpful in adapting the project to the circumstances andmaking changes to the relevant indicators if need be. ---
P112359 | NanGuang Railway Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2009 | 2015 | 2018 | PPAR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/710291532450039202/text/127580-PPAR-P112359-P166862-PUBLIC.txt | http://documents.worldbank.org/curated/en/710291532450039202/pdf/127580-PPAR-P112359-P166862-PUBLIC.pdf | 7. Lessons â€¢ Sound technical design, project preparation, and implementation management, combined with a strong financial capacity, are a recipe for success for a high-speed railway project. The NanGuang Railway Project was completed on time, with high quality, and at a relatively low cost. Evidence from the project shows that its success was attributable to good preliminary design, meticulous planning, strict control over compliance with standards and specifications, and reliable and responsible contractors. China Railway Corporation and Ministry of Railways deserve major credit for these achievements. Their success was also attributable to the smooth coordination of the Ministry of Railways and CRC with local governments on land acquisition and timely provision of counterpart financing. The World Bank contributed to the success through providing guidance and support to ensure the project's preparation and implementation met high standards, especially in technical and environmental specifications and in achieving economic benefits in China's less developed regions. â€¢ Agglomeration effects are an important benefit of high-speed rail development, and should be incorporated in the cost-benefit analysis of such projects. In addition to conventional benefits, such as user time savings, operating cost savings for traffic diverted from the conventional lines, and reductions in environmental externalities, this project has confirmed that a high-speed rail project also has significant agglomeration benefits, coming from more closely connected economic activities and markets, better knowledge sharing, and greater productivity owing to increased competition between spatially closer markets as a result of high-speed rail connections. The magnitude of agglomeration benefits depends on local circumstances, such as industry structure, local conditions, and governance. It is important to identify and quantify agglomeration benefits in feasibility studies to better inform the selection of rail routes and stations. â€¢ Successful reforms in large and complex infrastructure sectors such as railways in China require sustained policy dialogue and engagements. By the time of the project approval, China had pursued reforms in the railway sector for about 10â€“15 years, and had achieved solid progress in core reform areas. The World Bank contributed to this process through its provision of support on capacity building and institutional development in multiple dimensions across the system. To promote further reforms, the government asked the World Bank's advice on relevant international experience in railway development. Using this project and the other five high-speed rail projects as a platform, the World Bank continued its policy engagements with the government, including an introduction to the experience in railway sector governance in eight countries. These engagements played an important role in informing relevant reforms in China's railway sector, especially the 2013 landmark reform, which separated the commercial management of railway services from the railway regulatory function, and established corporations for railway services delivery. â€¢ Good connections of high-speed railway lines with other transport modes and between the rail stations and urban centers are critical to achieving the full benefits of high-speed trains. This project's experience shows that a high-speed railway line often entails a major investment, requiring high traffic density for it to be economically viable. Integration of the railways with other transport modes is important to achieving a high traffic density throughout the system. It is therefore necessary to take measures at the design stage to ensure that rail station cities have concrete plans for a timely buildup of complementary infrastructure and the provision of services necessary for good local transport connections to the railway stations, such as reliable and safe public transport and taxi services.
P112368 | Cote d'Ivoire: Economic Governance & Recovery Grant (EGRG) II | Western and Central Africa | Cote d'Ivoire | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2011 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory |  | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/219241474558525356/text/000020051-20140624170232.txt | http://documents.worldbank.org/curated/en/219241474558525356/pdf/000020051-20140624170232.pdf | The experience of EGRG-2 indicates that while political constraints determine where and how much to reform, they should not prevent exploring the consequences and ultimate outcomes of a program. Not doing so is likely to prevent identifying actions that lead to true outcomes in future programs.
P112369 | Mauritius Third Development Policy Loan | Eastern and Southern Africa | Mauritius | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2009 | 2012 | 2013 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | High | http://documents.worldbank.org/curated/en/713521475098269117/text/000020051-20140625192948.txt | http://documents.worldbank.org/curated/en/713521475098269117/pdf/000020051-20140625192948.pdf | IEG concurs with the ICRâ€™s findings that the success of the reform program in Mauritius was largely due to strong government ownership and a participatory approach which involves all key stakeholders in society. Close coordination with key donors in harmonizing conditionality enabled the government to implement a single comprehensive reform program. An important lesson from Mauritiusâ€™s experience is that the ability to respond to new challenges is essential for successful implementation of the reform program. The program was also sharply focused and internally consistent and therefore easier to implement and monitor.
P112446 | Afghanistan - Strengthening Health Activities for the Rural Poor (SHARP) | South Asia | Afghanistan | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2009 | 2014 | 2014 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/205931474892810388/text/000020051-20140626130657.txt | http://documents.worldbank.org/curated/en/205931474892810388/pdf/000020051-20140626130657.pdf | Lessons drawn from the ICR (pages 24-25), adapted by IEG:The flexibility features of NGO contracts need to consider fiduciary control rules set out by Ministries of Finance. In the case of this project, the NGO contracts were designed to allow NGOs a great deal of flexibility and authority in the use of inputs to deliver services. However, NGOs were not always able to take full advantage of this flexibility because of the detailed reporting requirements by the Ministry of Finance on the use of funds and inputs. Streamlined mechanisms should be put in place for NGO procurement in the case of follow-on projects, in order to avoid implementation delays and service disruption. In the case of this project, all NGO contracts were terminated at the end of the previous project and entirely new procurement processes had to be started under the next project.
P112456 | Regional Trade Facilitation Project II | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2011 | 2015 | 2017 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/188261467920874963/text/ICRR-Disclosable-P112456-07-07-2016-1467920863532.txt | http://documents.worldbank.org/curated/en/188261467920874963/pdf/ICRR-Disclosable-P112456-07-07-2016-1467920863532.pdf | Some of the lessons identified by the ICR were either findings or recommendations. This review concurs with thethreelessons identified in the ICR as rephrased below:(i) Scale of business matters for a regional risk insuranceagency to operate on a sound footing. With only 10 member states and a paid-up capital of less than US$200 million, ATIhad, in 2012, only 13 percent of the estimated market for political and commercial risk insurance in Sub-SaharanAfrica.Expanding country membership to achieve a critical mass was therefore essential for ATI to reduce its vulnerability onthis account, as well as to be able to play a more effective developmental role in the region. Reaching critical mass is alsoimportant for ATI to be able to maintain its A/Stable international credit rating,so as to be perceived by brokers,reinsurers and coinsurers as a trustworthy player in the international insurance market.(ii) When theBank invests in entities operating within a global industry, a regulatory mechanism needs tobe internalized in the governancearrangements or take the form of an external regulator. The mechanism willensure that benchmarks arecontinually reviewed and updated beyond Bank supervision toguarantee that a public sector entity like ATI keeps pacewith its internationally competitive peers, without taking excessive risk.(iii) The Bank should avoid makingshort-lived regional programmatic commitments, but rather invest upfront in securing a critical mass for a singleoperation. Mobilizing country participation in regional projects takes time and capacity building, which should not beunderestimated. RTFP II pursued a programmatic approach designed to allow members to join when ready. However, by the time acritical mass of countries was ready to join (ECOWAS), regional IDA funding was not available due to competingdemands.(iv) Another lesson identified by IEG is that for a regional entity to stay the course of competitivenessin a complex political insurance industry, it has to rely on advice of top-notch institutions, including multilateral banks andfirst-rate management firms.
P112495 | RESTORING EQUITABLE GROWTH AND EMPLOYMENT PROGRAMMATIC DEVELOPMENT POLICY LOAN | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2011 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/960341474905787421/text/000020051-20140625224719.txt | http://documents.worldbank.org/curated/en/960341474905787421/pdf/000020051-20140625224719.pdf | IEG concurs with the ICR that a flexible approach of DPL series can be helpful in supporting reforms and maintaining dialogue over the longer run. However, in countries such as Turkey where the Bank's exposure is significant, a more focused approach may be needed. Going forward, a focused approach will be all the important given the Bank's limited capital -- an issue raised in IEG's recent evaluation of the Bank's crisis response. Great selectivity places a premium on strong analytical work and ongoing country dialogue.IEG also concurs with the CPSCR: both policy dialogue and attention to M&E are essential for DPL series to achieve their objectives. Equally important are political incentives for Governments to sustain reform efforts over the medium-term.This ICR review also notes that the trade-offs between the shorter crisis response and longer term structural reform goals of policy based operations should be made explicit. Attempting to achieve both objectives within a single series (such as the REGE-DPL) can be especially challenging. Furthermore, DPLs that provide short term external financing in the absence of an IMF program should first seek explicit agreement on the macroeconomic framework and the Government's fiscal stance.
P112516 | Botswana - Morupule B Generation and Transmission Project | Eastern and Southern Africa | Botswana | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2010 | 2016 | 2017 | ICRR | >=50 million & <100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/392781485213835961/text/ICRR-Disclosable-P112516-01-23-2017-1485213819609.txt | http://documents.worldbank.org/curated/en/392781485213835961/pdf/ICRR-Disclosable-P112516-01-23-2017-1485213819609.pdf | The following lessons were selected from the ICR: Right balance of expertise in the Bankteam is essential. The Bank team for Morupule B lacked the right expertise in some important areas, advising on the EPCcontract, the technical and engineering details and early detection, mitigation and remedies of any defects, the projectmanagement, project implementation arrangements, safeguards and the level of resources. The Banks added-value in providingsuch expertise is important for its client countries, where technical and managerial skills and experience with complex projectsmay be limited. In-depth expert scrutiny and monitoring from the very early stage ofthe project is essential to avoid or remedy deficiencies. While the ME and Result Framework are focused on theoutcomes and results, scrutiny and monitoring of the quality during design, inputs, and the process of delivering outputs canidentify potential risks and deficiencies and increase the project resilience, preparedness and remedy them before it istoolate. This projects defects were found after commissioning of the plants, which had become extremely difficult andcostly to resolve. Ensuring the capacity of the implementing agency and contractors interms of technical, management and safeguards with the right expertise, and the adequate number of personnel and resourcesareessential. If not sufficient, the additional resources and support need to be provided.
P112523 | EAST-WEST HIGHWAY IMPROVEMENT 3 | Europe and Central Asia | Georgia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/915481498054360756/text/ICRR-Disclosable-P112523-06-21-2017-1498054339686.txt | http://documents.worldbank.org/curated/en/915481498054360756/pdf/ICRR-Disclosable-P112523-06-21-2017-1498054339686.pdf | The ICR (pages 22-23) identified a number of lesson of which three have broad applicability: Toprepare good engineering design, there is a need to ensure that qualified engineers (international or local) are hired by theImplementing Agency during the preparation of road designs. These engineers should supervise the preparation and/or review thedraft designs. There is a need to re-assess risks and put in place adequate mitigation measures to addressproject safeguards management capacity issues. The project experience showed that land acquisition and resettlement procedures tooklonger than expected. Therefore, the safeguards documents need to be periodically revised/updated, approved, disclosed andcorrectly implemented. Since the implementation of road safety requires a number of stakeholders, a clearframework for multi-sectoral coordination needs to be established during project preparation.
P112526 | Agriculture and Rural Development | Europe and Central Asia | Kosovo | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2011 | 2023 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099120623114034439/text/P1125260b5304001509b1c0cddedf1bdc51.txt | http://documents.worldbank.org/curated/en/099120623114034439/pdf/P1125260b5304001509b1c0cddedf1bdc51.pdf | The ICR presents relevant and sound lessons, supported by the projects design and implementation experience and evidence,and which have broader application in Kosovo and beyond this project.Lesson 1:Simple project design and intense implementation support may counter fragility and institutional weaknesses. TheARDP concept and structure were simple and relevant, aiming to match the implementing capacity of the government. For the newclient countries with rather limited experience in the World Bank operations, the lesson is that the Bank project teamsactive proactivity in guiding and advising counterparts from the outset on sound project design and implementation practices willhelp to ensure that they are in accordance with the relevant Bank policies and guidelines, good practices and the countrysdevelopmental requirements.Lesson 2: If a clear definition of the PDO, its indicators andaccurate targets is missing, measuring the project results and impacts effectively may become challenging. The high-leveloriginal PDO, some indicators or the methodology to collect them which were not well defined at project design, and posed achallenge when evaluating the projects impact. The lesson is that Project design teams assurance that PDO andindicator definitions are clear early in the life of the project will help ensure sound RF and basis for design, measurement andassessment. The lesson further highlights the importance of targets being realistic and achievable during the life of theproject. A proactive approach to introduce adjustment as necessary, both in terms of PDO and RF, taken at an early stage of theproject implementation, supported by an effective ME system, will help ensure sound measurement and assessment by the end ofthe project. Also, the project highlights the lesson of the importance of the project: being selective, strategic and simple in thenumber and content of the performance indicators; if these features are not followed, this could result in a ME systembecoming overly complex and ineffective, with limited usefulness.Lesson 3: Participatory monitoring (bybeneficiaries and key government and community actors) may contribute to the success of implementation and sustainability ofinvestments. Introducing participatory monitoring for ARDP irrigation infrastructure rehabilitation works provided severalbenefits, which included the active engagement of the beneficiaries in advance of the investment implementation, provided anopportunity for the beneficiaries to fully understand the feature of the investments, the benefits it will provide and the activerole the beneficiaries can play in ensuring the investments will address their priority needs. This participatory mechanismprovides the implementing agency with the opportunity to promptly respond in case any obstacles or wrongdoing on the side of thecontractor arise during the implementation. Finally, participatory monitoring helps ensure long term sustainability, since theinvestments are owned by the beneficiaries and other key stakeholders; participatory monitoring enabled beneficiaries to become anactive part of the process versus being simply considered the passive recipient of the investments.
P112544 | CATASTROPHE DEVELOPMENT POLICY LOAN DEFERRED DRAW DOWN OPTION (DDO) | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2009 | 2013 | 2015 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/635451475093430177/text/000012394-20150409084028.txt | http://documents.worldbank.org/curated/en/635451475093430177/pdf/000012394-20150409084028.pdf | The ICR offers three categories of lessons:1. CAT-DDOs as instruments can open up new opportunities. For example, a DPL with CAT-DDO can provide liquidity while also introducing broader concepts of Disaster Risk Financing and Insurance (DRFI) for countries. 2. CAT DDOs can serve as instruments of broader engagements, such as providing a platform to bring other sectors and institutions and enhance the DRM policy dialogue with TA. 3. CAT DDO design and implementation can be improved through the following measures:a. Clear guidelines to manage early disbursements of CAT DDO; and incentives in place to monitor the progress of the program even after full disbursement.b. More specific reporting mechanisms in the loan agreements and followed through after disbursementc. More clearly explaining the renewal option of DPLs with CAT DDO to the government .
P112573 | Urgent Electricity Rehabilitation Project | Western and Central Africa | Cote d'Ivoire | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2009 | 2015 | 2017 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/738631471039484328/text/ICRR-Disclosable-P112573-08-12-2016-1471039475381.txt | http://documents.worldbank.org/curated/en/738631471039484328/pdf/ICRR-Disclosable-P112573-08-12-2016-1471039475381.pdf | Lessons 2 and3 of the following lessons are somewhat related but not identical to the ICRs lessons (paragraphs 137and 139, p. 29-30).1. Attention to anticipated consequences are crucial when a project recommendsthe sector reform, because otherwise, a subsequent project may recommend another round of reform, which can result in considerabletransaction costs and time delays. The ICR of the prior Private Sector Energy Project (P001184) noted that following therecommendations of the projects study, the Government abolished the state-owned power utility and created a new sectorstructure comprised of SOGEPE, SOPIE and ANARE. However, following this projects study recommendations, the SOGEPE andSOPIE entities implementing this project were disbanded and a new state company CI-Energies (CIE) succeeded them. Both projectsexperienced these organizational changes during project implementation.2. Sector investment projectfinancings (IPFs) and DPOs can be complementary to achieve common objectives but the outcome may not be fullyattributable to IPF alone and may not be achievable if the target value is set too ambitious. The Government of CotedIvoire rejected a tariff studys recommendations of the previous Private Sector Energy Project (PSEP) (P001184;1995-2004). With the complementary impacts of this project and PRSCs, the Government adopted part of the recommendations of thecurrent projects tariff study. Yet, the project could not achieve the targets for zero subsidy, the tariff reform andindependency of ANARE. These targets were ambitious and might not be fully attributable to a project that focused mainly onthe technical side of policy support at the sector level. PRSCs had a more conservative subsidy reduction target than this project.The Bank has been supporting subsidy reform, often under crisis conditions, with a range of instruments since 1988. Rapidachievement of ambitious targets may not be realistic.3. Even with a rather simple andstraightforward design as in the current project, the collection and use of the most recent data can save costs and timelater. The engineering studies for this projects distribution network upgrade were prepared based on outdated data.This led to inaccuracies in the technical specifications and difficulties in implementing the actual works. New solutions and costestimates for the rehabilitation of the network had to be prepared, which resulted in delays in implementation and costoverruns.
P112578 | Private Sector Renewable Energy and Energy Efficiency Project | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2009 | 2017 | 2018 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/670411510945091527/text/ICRR-Disclosable-P112578-11-17-2017-1510945078195.txt | http://documents.worldbank.org/curated/en/670411510945091527/pdf/ICRR-Disclosable-P112578-11-17-2017-1510945078195.pdf | The ICR provides a number of lessons for projects of similar design, i.e. involving the provision of credit lines to one or morefinancial intermediary institution(s). The following lessons are drawn from those presented: Policy andregulatory support is essential for credit lines to have a transformational and sustainable impact. While the Projectsuccessfully addressed the key constraint of a lack of availability of long-term finance, conducive policies on the part of theGovernment such as the Feed-In Tariff (FiT) regime and purchase guarantees were essential to create demand among projectsub-sponsors for investment in RE and EE. Similarly, the development of solar capacity was supported by an amendment in 2013 ofTurkeys Unlicensed Generation Regulation, exempting small solar power generation (capacity of up to 1MW) from licensingobligations, and making them FiT eligible. More specific policy and regulatory support (e.g. through a streamlining of permits licensing) under the Project would have helped further improve the impact of the credit line by helping to remove barriersfor less prevalent technologies, which in turn could have helped attract more commercial financing. Credit lines canbe made more effective with technical assistance (TA). Especially to enable project participants meet safeguards requirements.Since financial intermediary institutions in a Project are likely to have different levels of capacity, TA provided in parallelwith the participation of other donors can usefully complement the Banks own capacity building activities,e.g. in thecarrying out of energy audits and feasibility studies. TA provided to the private sector and Government can be useful instimulating a broader interest in project activities (e.g. in energy efficiency), and in disseminating results, which wouldencourage the participation of other commercial lending institutions. If, as in the case of this Project, TA is financed inparallel by other donors, continued coordination with these donors will be needed to ensure that the TA actually provided iscomplementary to the Banks own capacity building activities. Specific guidance (in the PAD and the Operations Manual)is needed for ME, in order to ensure that there is consistency across FIs involved. If multiple FIs are involved in aproject, specific guidance should be provided on ME in the Operations Manual, to describe methodologies and assumptions, toensure consistency in utilization of results indicators.
P112600 | AFCC2-RI-Association for Strengthening Agricultural Research in Eastern and Central Africa (ASARECA) Trust Fund | Other | Africa |  |  | Sustainable Development | Agriculture and Food | RETF | IPF | 2009 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/532411589647661337/text/Africa-Association-for-Strengthening-Agricultural-Research-in-Eastern-and-Central-Africa.txt | http://documents.worldbank.org/curated/en/532411589647661337/pdf/Africa-Association-for-Strengthening-Agricultural-Research-in-Eastern-and-Central-Africa.pdf | The ICR proposed 12 useful lessons from the project. Two presented below, with some modifications in language, wereconsidered by IEG as the most important. The third lesson below is an additional lesson that IEG drew from theproject.1. Regional projects require tailored and tightoversight of fiduciary andprocurementactivities.The fiduciary crisis and suspension of disbursements in the first year of this project is illustrative ofthe consequences of mis-procurement, not only in the general unacceptability of such malfeasance, but alsoin itsoperational consequences - severe negative impacts on project implementation. Fiduciary oversight was particularly difficultwithmultiple countries involved.The typical checks and balances of a project in one country alone - such as auditing asstandard practice, andoversight by the countrys financial agencies - were not applied for the small country programs.Practical means to provide the necessary fiduciary and procurement guidance and monitoring is required, with variability by countryto reflectdifferent institutional structures. The first lesson is that for a regional project involving multiple countries,intensive training, special auditingarrangements, and other measures are necessaryto avoid fiduciarymismanagement.The second lesson is that an appropriate levelof funding forBank staffing to provideoversight of procurement and financial management also needs to be considered.2. Design for the resourcesavailable, not the resources desired.The Bank team planned for project financing assumingthat donors would, asin the past with OP-I, provide significant additional funding to augment the Banks US$30 million contribution. But donors didnot contribute the funds expected. This caused a financing crisis and a major downsizing of the project, only months after projectapproval. The lesson is that no project should be declared effective until all funds required for the efficient implementation ofthe project have been confirmed.3. A full restructuring rather than an informal adjustment of a projectsimplementation plan is preferable when a projects implementationenvironment (particularly its funding) has significantlychanged.When disbursements for OP-II were suspended, this might have put into question the type ofprojectneeded in the new financing environment. Rather than formally restructure, the project was adjusted to finance theprojects software aspects - in essence, a scaled-down OP-II without the TIMPs.However, with the core of theproject effectively closed down, the type and scale of software activities, and many other features of the project neededchange.The lesson is that aformal restructuring of theproject, provides greater opportunity for consideringrevised objectives, components, institutional arrangements and funding in order to complete implementation efficiently than ad hocadministrative adjustments.
P112611 | Increasing Resilience to Climate Change and Natural Hazards Project | East Asia and Pacific | Vanuatu | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2013 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/815971590784586738/text/Vanuatu-Increasing-Resilience-to-Climate-Change.txt | http://documents.worldbank.org/curated/en/815971590784586738/pdf/Vanuatu-Increasing-Resilience-to-Climate-Change.pdf | 1. Complex project designs that do not match local capacities on implementation wouldnegatively affect achievements of outcomes. Before restructuring, the implementation of activities was delayed due tothe complex project design with multiple implementing agencies, which initially overwhelmed local capacity. It was reflected in thepre-restructuring achievements of outcomes. After restructuring, the responsibilities for implementation and coordination wereunified to be under a single agency, while ensuring the commitment and oversight from other sectoral agencies and provinces.In addition, international experts were placed to support local technical officers in pairs. These contributed to theimprovement in the post-restructuring achievements of outcomes. 2. PDO andindicators on community resilience without focus on specific aspects of resilience nor clear guidance on measuring methods wouldcause uncertainties in development goals and implementation procedures. The broad scope of the original andrevisedPDO statements and outcome indicators caused confusion during implementation. Articulating the Projects focuson a specific aspect of resilience, such as community adaptive capacity, would have supported the project implementation.Additional analysis would be needed regarding methods to design and measure indicators that capture multiple dimensions ofresilience as well as impacts of projects on long-term resilience goals.
P112612 | Morocco - Public Administration Reform IV | Middle East and North Africa | Morocco | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2010 | 2011 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/661781474566109555/text/000020051-20140625061224.txt | http://documents.worldbank.org/curated/en/661781474566109555/pdf/000020051-20140625061224.pdf | Lessons in the ICR are all supported. Of particular merit is the lesson that the visibility of the reform needs to be scaled up. Administrative reforms such as those supported by the series take many years to deliver substantial improvements in administrative processes, and longer to deliver visible outcomes such as better public services and reduced corruption. Given pressure from civil society groups, such as Morocco's February 20th movement, such reform programs need to focus on producing and effectively communicating visible short term results of direct benefit to the general public, using the "rapid results approach" and pro-active, external communications. Another lesson is the critical importance of a package of analytical work, technical assistance, investment operations, and operational support to help governments to use DPLs productively.
P112613 | COMMUNITY RESILIENCE TO CLIMATE AND DISASTER RISK IN SOLOMON ISLANDS PROJECT | East Asia and Pacific | Solomon Islands | IDA | FCS | Infrastructure | Urban, Resilience and Land | GEF | IPF | 2014 | 2020 | 2021 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/449171618233828810/text/Solomon-Islands-CRISP.txt | http://documents.worldbank.org/curated/en/449171618233828810/pdf/Solomon-Islands-CRISP.pdf | The following key lessons are taken from the ICR (paras 132 to 136), with some adaption in language:Measuringoutcomes is particularly complex in disaster risk management/climate change adaptationprojects and requires strong attentionduring design and implementation. In this project, the proposed scorecard to measure community risk management capacityand a screening tool to measure national mainstreaming were never developed, hampering guidance on how outcomes would be measured.Instead, most of the regular monitoring focused on outputs and intermediate results indicators.Therefore, common outcomeindicators for climate and disaster reliance projects need to be developed and applied through specific training and advice suitedto the country and project contextMainstreaming disaster risk management/climate change adaptation in sectoralministries takes time and needs to be measurable. Given the wide-ranging impacts of climate change and disasters on thecountry, the projectfocused on institutional change aimed at incorporating climate and disaster risk into key sectors.However, this type of mainstreaming requires time and considerable political influence and has to be clearly traceable throughplanning and budgeting processes.Therefore, mainstreaming climate and disaster risk and resilience should be implementedthrough a government agency responsible for development and budgetary processes, with input from technical ministries asneededCommunity-driven development can be a major challenge for climate and disaster resilience projectsparticularly for remote communities with weak capacity and when inputs are not locally available. In this project, PMU-ledbulk procurement but allowed communities to retain some funds for local purchases, and transparently agreeing on PMU-managed fundsin community sub-grant agreements. This helped overcome thechallenges while maintaining strong community ownership.
P112615 | Kiribati Adaptation Program - Phase III Project (KAP III) | East Asia and Pacific | Kiribati | IDA | FCS | Infrastructure | Urban, Resilience and Land | GEF | IPF | 2012 | 2019 | 2020 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/246571567622623112/text/Kiribati-Kiribati-Adaptation-Program-Phase-III.txt | http://documents.worldbank.org/curated/en/246571567622623112/pdf/Kiribati-Kiribati-Adaptation-Program-Phase-III.pdf | The ICR (p. 30 -31) provided lessons learned that were adapted by IEG: Engaging local communities inproject activities throughout the project cycle is essential for ensuring the sustainability of project outcomes. In thisproject, community engagement was critical for a successful implementation and subsequent use and maintenance of publicinfrastructure such as coastal protection measures and water supplies. Community engagement evolved from information seeking, tosemi-commercial behavior change campaigns, to empowering residents and allowing for public voice in decision-making and proactivelyrecognizing the needs and priorities of different groups. Understanding local administrativesystems, local contracting and suppliers markets and taking advantage of local expertise are critical for successfulimplementation. In this project, an appropriate contract size and pre-bid training for local contractors allowed for theeventual completion of 13 of the 16 works contracts by local contractors using Force Account in two cases.
P112623 | CORAF Trust Fund | Western and Central Africa | Western and Central Africa |  |  | Sustainable Development | Agriculture and Food | RETF | IPF | 2011 | 2017 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/137351510410039264/text/ICRR-Disclosable-P112623-11-11-2017-1510410029324.txt | http://documents.worldbank.org/curated/en/137351510410039264/pdf/ICRR-Disclosable-P112623-11-11-2017-1510410029324.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.(I) Under some circumstances, delays could be avoided by resorting to modifying the results framework andrevising the indicators, even before a MTR. In the case of this project, the results framework was modified after therecommendations of the MTR, which occurred just one month (August 2015) before the original closing date (September2015).(2). Functional Innovation Platforms (IPs) which bring together all stakeholderscan help infacilitating the implementation of Integrated Agricultural Research for Development activities. The experience with thisproject demonstrated that although establishment of IPs take time, they help in facilitating implementation of integratedactivities and such investments pay dividends.IEG adds the following lesson. Even thoughtraining and technical assistance-related activities are not easily amenable to traditional cost-benefit analysis, it is stillimportant to set up a methodological framework for assessing efficiency ofproject activities.
P112625 | Economic Recovery Development Policy Oeration | Europe and Central Asia | Moldova | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2011 | 2012 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/350411475089593230/text/000020051-20140624214829.txt | http://documents.worldbank.org/curated/en/350411475089593230/pdf/000020051-20140624214829.pdf | IEG agrees with the lessons cited in the ICR. The ICR contains useful lessons which highlight the importance of strategic and extensive analytic work, coordination with other development partners and selectivity in the design of the operation. It was reasonable and appropriate for the Bank to focus on reforms for which there was strong support both from the government and other development partners.
P112626 | Liuzhou Environment Management Project Phase II | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2011 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/388731556670348202/text/China-CN-Liuzhou-Environment-Management-II.txt | http://documents.worldbank.org/curated/en/388731556670348202/pdf/China-CN-Liuzhou-Environment-Management-II.pdf | The ICR (page 26) draws three lessons from the experience of implementing this project (with some adaptation oflanguage).One. A careful consideration of local conditions and analysis based on local data isrequired for design of wastewater treatment plants. In this project, the wastewater treatment plants weredesigned based on national standards,rather thanwastewater influentlocal data. This resulted in oversizedwastewater treatment plants, with the actual capacity for wastewater treatment plants exceedingtherequirements.Two. A careful consideration of localconditions is required for aspects pertaining to financial sustainability of wastewater treatmentplants. Projects should clearly define and indicate how investment costs, operating costs and debt servicing are expectedto be covered and by whom. Lack of clarity on these points can lead to incorrect definition ofindicators.Three. Raising awareness and involving the beneficiaries from the initial stages ofpreparation can be helpful for the financial sustainability of wastewater services. In this project, the focus was oncollecting and treating domestic wastewater.Limited attention was paid to engaging and educating the beneficiaries, whichresulted in ab inability of the counties to raise tariffs for wastewater services.The IEG draws thefollowing lesson.Flexible arrangements can aid in realizingproject outcomes. The design of thisproject aimed at reuse of sludge to acement factory. Since thecement factory was unable to receive the planned volumeof sludge due to reduced market demand for cement, the design made alternative arrangements forreuse of sludge through abrick production factory. This ensurednot only full treatment and disposal of sludge, but also ensured that sludge managementwas consistent with the environmental sustainability objectives.
P112632 | Cofinancing Grant to PNPM for Decentralized Management of Natural Resources and Renewable Energy | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2009 | 2013 | 2015 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/224161474941756137/text/000012394-20150108104021.txt | http://documents.worldbank.org/curated/en/224161474941756137/pdf/000012394-20150108104021.pdf | The following lessons are taken from the ICR with some adaptation of language:The blending of many trust funds can cause fragmentation in implementation. This project used trust funds primarily to complement other resources to extend finance to sub-projects in more villages than would otherwise be feasible. It did not use trust funds in a strategic fashion to pilot, innovate, take risks, and learn--for example, via impact evaluation. Building on an established platform such as PNMP does not ensure smooth implementation. For example, there were avoidable delays in disbursement of funds that forced communities to undertake activities within very short time periods. As stated in the ICR (p. 35), "The annual block grant cycle is often incompatible with the financing requirements of biological [natural resource management] projects". Multi-year financing should be considered.Communities tend to prefer green subprojects that generate income or save costs for them (for example tree planting on private lands). Such subprojects are often more sustainable but are usually placed on private lands and result in benefits to only a subset of community members. Design of benefit sharing mechanisms is complicated since it is hard to ensure accurate recording of costs and revenues. The result may be inequitable distribution of the benefits from subprojects. Other CDD projects promoting green or climate change related activities are likely to encounter similar issues. IEG adds the following lesson:A well designed and implemented M&E framework is of particular importance to a pilot operation. In this case, a weak M&E framework and poor M&E implementation made it difficult to evaluate the outcomes of the project and to draw lessons for future initiatives of a similar nature in Indonesia and elsewhere.
P112635 | CM-Agricultural Competitiveness Project | Western and Central Africa | Cameroon | Blend | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/979741515623720274/text/ICRR-Disclosable-P112635-01-10-2018-1515623711407.txt | http://documents.worldbank.org/curated/en/979741515623720274/pdf/ICRR-Disclosable-P112635-01-10-2018-1515623711407.pdf | The ICR included five lessons. The following are emphasized with some adaptation of language: Assessmentof the availability and sustainability of service providers and key stakeholders is a necessary step prior to launching adecentralized support delivery model in agriculture. It is important to assess the availability of the appropriate serviceproviders; and the likelihood of sustainability of the approach. Based on these assessments, the project should select the keystakeholders based on their mandate and capacity. To ensure the success of project implementation there is aneed fora clear definition of respective roles and responsibilities of the different parties and theirinter-linkages. The projects experience showed thatinvolving a multitude of players(among which were National/Regional Coordination Units, teams of experts, OALs and Focal Points) added to the projectscomplexity. In this context, an unambiguous division of labor would have eliminated the possibility of mismatching skillswith tasks. Successful rehabilitation of rural roads needsto follow athorough plan fromidentification to maintenance. The projects experience demonstrated that it is important toconcentrate on theroads that are priorities in a limited geographic area; and carefully assess the type of rehabilitation needed and the capacity oflocal contractors (depending on the state of the road, commensurate with its actual/expected use to connect producers to inputs andmarkets). Also, ensure that engineering studies are ready at the start of projects that include road rehabilitation works;andformally involve a road engineer in the Banks supervision team. Finally,define modalities for medium and long-termmaintenance.
P112684 | Forum for Agricultural Research in Africa (FARA) Trust Fund | Western and Central Africa | Western and Central Africa |  |  | Sustainable Development | Agriculture and Food | RETF | IPF | 2009 | 2019 | 2020 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/154301578688581971/text/Western-Africa-FARA-Trust-Fund.txt | http://documents.worldbank.org/curated/en/154301578688581971/pdf/Western-Africa-FARA-Trust-Fund.pdf | The ICR included fifteen lessons and recommendations. The following three are emphasized with some adaptation oflanguage: Quality supervision and operational support needs stable TaskTeamleadership.High Task Team Leader turn-over at the end of the MDTF was not conducive to quality supervisionand operational support. Significant delays with disbursement (2017-2018) partly arose from these changes. Arigorous ME design is needed at entry combined with active supervision and adequate implementation capacity toensurecapturing the projects outcomes. The ME set-up was complex whereas capacity for ME was limited. Effort wasneeded to assess the capacity and provide a minimum level of understanding of results-based ME. Anexit strategy is needed to ensure sustainability beyond donor support.FARAs size was overestimatedandit eventually became anisolated large organization with high levels of salaries and at times superfluous expenses, requiringsignificant resources to stay functional. FARA became to some extent a victim of the fluctuating donor priorities, both DevelopingPartners and the constituency questioning value for money. FARA has not been able to design a sustainable exit strategy fromcontinued donor support.The following lesson is emphasized by IEG: Regionalprojects need rigorous background analysis and studies to support an adequate project design and implementation arrangements, andhence ensure a higher chance of achieving the desired outcomes.Regional projects are challenging to coordinateand require a clear understanding of the conditions on the ground. Also, such projects need realistic PDOs that could potentiallybe achieved within the implementation time-frame and available funding.
P112688 | AFCC2/RI-East Africa Agricultural Productivity Program | Other | Africa |  |  | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2016 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/849981486421902831/text/ICRR-Disclosable-P112688-02-06-2017-1486421893661.txt | http://documents.worldbank.org/curated/en/849981486421902831/pdf/ICRR-Disclosable-P112688-02-06-2017-1486421893661.pdf | The ICR drew eleven lessons from the project. Those that had broader implications beyond EAAPP were asfollows: Project Design. Agricultural researchactivities can have an enhanced impactwhen linked to extension, seed multiplication and agriculture input supplies are integrated into the overallproject design.For example EAAPP included downstream activities with a high level participation of farmersthatmakeagricultural research more relevant. Allocation of RegionalResponsibilities in Regional Programs. In planning regional projects, substantialtime should be allowed to have allparties agree on how to collaborativelydetermine their respective roles. For example,Kenya had its own wheat researchprogram, but agreed to cede research leadership in wheat to another country.. ProjectOversight. Establishing a steering committee at a high level for a regional project can provide a necessary boost toprojects requiring cross border cooperation. For example the Permanent Secretary level steering committee for EAAPPintroducedat the mid-term reviewaccelerated technology sharing andpromoted discussions of modalitiesforbetter cooperation in technology sharing, while also promoting the broader perspective of the whole agricultural valuechain. Spillover Effects. Implementers of regional agricultural programs should lookfor ways to capitalize on spillover effects. For example, new agricultural technologies reached countries outside ofparticipating countries. These countries also contributed new technology, innovations and management practices that were notnecessarilytheir comparative advantage. Research Institutions as Public Goods.Regional Centers of Excellence offer a special advantage to agricultural research and development in that they are regional publicgoods that are made available to the scientists and development professions of multiple nations. For example, RegionalCenters of Excellence contribute to the strengthening regional collaboration and remain an asset shared by the participatingcountries and other countries. However, questions remained regarding the sustainability of the centers in terms of theirbudgeting and staffing and hence the lesson is that these issues need to be addressed.This Review suggestsanother lesson, namely: Integrity of Bank Commitments. Requirements by the World Bank thatcountry clients meet triggers to qualify for second phases of a project should be accompanied by a Bank commitment to contribute tofinancing a second phase if the triggers are met.
P112700 | Georgia: First Development Policy Operation (DPO-1) | Europe and Central Asia | Georgia | IBRD | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2010 | 2018 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/352991530210847614/text/Georgia-first-second-and-third-development-policy-operations.txt | http://documents.worldbank.org/curated/en/352991530210847614/pdf/125186-PPAR-P112700-P117698-P122202-PUBLIC.pdf | 6. Lessons 6.1 The design of DPO programs during times of crisis usually involves a dilemma between providing predictable budget support to the client country, to help preserve stability, and deepening or expanding the reform agenda. Meeting the need of budget support entails a risk of undermining the quality of the reform program supported by the World Bank or the ability of the program to go beyond reforms that would in any case have been implemented by the authorities or supported by other development partners. In Georgia, the World Bank made the choice of providing predictable budget support mostly by extending and deepening the reforms supported by the precrisis operations (PRSOs), limiting the inclusion of new reform areas in the program. With a few exceptions, the content of the DPO series was broadly adequate to achieve the program objectives. The comprehensiveness of the World Bank's previous engagement on the reform agenda through the PRSO series, the World Bank's extensive analytical work, the government's commitment to the reform agenda and crisis mitigation program, and technical assistance (by the World Bank and other donors) to build capacity in key areas of the reform program were all factors that contributed to the positive outcome. 6.2 In the absence of unemployment insurance or other active labor market programs, scaling up Georgia's TSA program was the only option available to mitigate the shortterm impact of the crisis. As the TSA program was well designed and targeted, the World Bank's support was fully justified and helped extend protection to the vulnerable during the crisis. However, cash transfer programs, such as the TSA, are mainly geared toward the chronically poor, whereas many of those affected by crises are households falling into temporary poverty. Also, these cash transfer programs often lack the institutional flexibility in targeting and management information systems to quickly absorb households that may have poverty characteristics different from the chronically poor, which the programs conventionally target. Moreover, they do not include help for workers to return to productive employment. To improve country preparedness to mitigate the social impact of crises, program complementarity, adaptability, and servicelevel efficiency play an important role. The World Bank could advocate complementary social protection schemes\. formal sector contributory schemes; safety nets, including cash transfers relatively well targeted to the poor; and complementary categorical benefits. Developing relevant knowledge and data on groups that are most affected by crises is of key importance. The introduction of unemployment insurance would have merited support by the 2009â€“11 DPO program, especially to help address the possible employment impact of deeper trade integration entailed by the DCFTA with the European Union. 6.3 In a fiscally constrained environment, a move to UHC may not necessarily bring an improvement in the financial protection of the poor. In Georgia, some improvements in health coverage of the poor achieved under the MIP reforms supported by the DPO series were sustained under the UHC program, and access to inpatient services was further enhanced. However, despite a slight decline in out-of-pocket health spending, there was no decline in the share of households that experience impoverishing effects of out-of-pocket expenditures. Moreover, the structure of the current UHC system and incentives embedded in it are a major driver of costs and fiscal overruns that limit the authorities' fiscal space to improve the coverage of the most vulnerable. As shown by Georgia's move to UHC, it is strongly advisable that such transitions be well prepared, with good checks and balances and quality assurance mechanisms in place that help contain the potentially high cost of UHC systems. The World Bank could play a more proactive role in advising governments on the best way to prepare such transitions. 6.4 The World Bank can play a supportive role in helping to focus government's efforts even in policy areas where other development partners mainly drive country reforms. This was the case in Georgia with the trade-related reforms required for the DCFTA with the European Union. These would have been very likely implemented even in their absence as prior actions in the DPO series, as Georgia was keen to fulfill the requirements for starting the DCFTA negotiations with the European Union. However, including these reforms in the DPO series helped focus the government's efforts on reforms important for strengthening export potential over the medium term while, given capacity limitations, this focused effort helped avoid spreading resources thin. The World Bank could have added more value by advising the government on how to prioritize regulatory convergence with the European Union directives, based on the World Bank's prior experience with Eastern European countries during their accession negotiations with the European Union.
P112712 | Second Emergency Demobilization and Reintegration Project | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2010 | 2018 | 2019 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/854621537827196430/text/Rwanda-RW-Emergency-Demob-and-Reintegration.txt | http://documents.worldbank.org/curated/en/854621537827196430/pdf/Rwanda-RW-Emergency-Demob-and-Reintegration.pdf | The ICR (paragraphs 89 to 94) included six lessons learned from the project. This Review considered that the followingspecific lessons were particularly important with general application to other demobilization and reintegrationprojects. Involving families of ex-combatants is critical for a successful demobilization andreintegration program. This project included families of ex-combatants and provided spouses and dependents withaccess to benefits, which supported an enhanced economic and social integration of ex-combatants into localcommunities. Reintegration programs require adequate resources to provide mental health and disabilityservices to be successful. In this project the financingof Integrated Rehabilitation and Production Workshops(IPRWs) and Narrative Exposure Therapy (NET) to support ex-combatants suffering from post conflict traumas were innovative andcritical toaddressing their mental health issues.
P112713 | Capacity Building in Public Financial Management | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2010 | 2015 | 2016 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/804671467114202808/text/ICRR-Disclosable-P112713-06-28-2016-1467114181287.txt | http://documents.worldbank.org/curated/en/804671467114202808/pdf/ICRR-Disclosable-P112713-06-28-2016-1467114181287.pdf | IEG concurs with the lessons drawn by the ICR (ICR p. 40), with some minoradaptation.There is a need for TFcontributors to synchronize the processes for signing of Administration Agreements to avoiddelays.The projects institutional arrangements need to address coordination andimplementation requirements within the implementing institutions to complement arrangements geared to coordination with externalpartners, as a crucial element for the success of the project. Coordination arrangements engaging implementingagencies management would help to identify and address instances where key stakeholders are not informed of the purpose ofreforms, and their roles and responsibilities, and tackle implementation constraints as they arise.Establishment of a robust management structure within the key stakeholders would also mitigate the risks of staff turnover byclearly distributing responsibility for implementation across a wider range of staff. In the case of this project, the lack ofclarity in the distribution of roles and responsibilities down through the institutions, along with frequent replacements of keyproject implementing staff, had negative effects on the borrower performance. PDO concepts suchas efficiency, effectiveness and accountability which are interrelated would need to be clearly spelled out in terms of measurabledimensions of PFM performance that are relevant in the country context. The importance of identifying key milestones in thedelivery of these outputs is critical to facilitate monitoring during implementation.
P112719 | Uzbekistan Bukhara and Samarkand Sewerage Project | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Sustainable Development | Water | IDA | IPF | 2010 | 2022 | 2023 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099305012232240489/text/P1127190233dbb0b20af610191053e4505c.txt | http://documents.worldbank.org/curated/en/099305012232240489/pdf/P1127190233dbb0b20af610191053e4505c.pdf | The ICR included four lessons. The following three are emphasized with some adaptation of language:1.Successful public sector reforms require a gradual approach with sectoral reforms and enough time for changes tomaterialize.Public sector reforms require time, trust, and flexibility, and realism in timing and the achievement ofresults. In a country context where the WSS sector is still maturing, additional time should be built into project implementation,recognizing that these changes are likely to have a profound effect on implementation. This alsohas implications for thelending instruments that best support public sector reforms. For example,a series of interventions with a number ofcredits/loans linked to the Governments medium-term program toward incremental changes has proved successful in achieving amore ambitious intervention. Also, support through selective entry points can show success and can form the basis for laterprogress, even in difficult areas such as public service reform. Sector reform requires strong country ownership and to this endthe Bank needs to tailor its support to the pace of reform.2. Implementation readiness is a critical element ofprojects that if not appropriately addressed may lead to unnecessary implementation delays.Projects need to be readyfor implementation to reduce delays that carry over the entire project period and hinder holistic project implementation. In BSSP,delays that originated due to lack of readiness resulted in increased pressure over time to deliver on major, but late,construction works, which had a negative impact on softer project interventions and can be argued to have lowered project ambitionsin these areas. Initial implementation delays can be reduced by completing more works during project preparation such as (a)preparation of request for proposal for consulting services, (b) approval of feasibility studies by the Government, (c) preparationof tender documents for the first contract packages, and (d) advance actions for the procurement of consulting services orconstruction contracts.3. If project design does not reflect clearimplementation roles for implementingentities, it may impede decision-making in complex projects. The involvement of too many entitiesin projectactivities, particularly in procurement decision-making, can cause major delays and reduce the authority of implementing entitiesto make required decisions. The BSSPs experience demonstrated that the lack of project management autonomy was a keycontributor to the poor performance of the project in its early years. Also, theinterference from national entitiesinthe day-to-day project activities can be an additional impediment for progress if not planned for in design.
P112759 | Shandong Ecological Afforestation | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | IPF | 2010 | 2017 | 2017 | ICRR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | High | http://documents.worldbank.org/curated/en/732881498764039046/text/ICRR-Disclosable-P112759-06-29-2017-1498764031399.txt | http://documents.worldbank.org/curated/en/732881498764039046/pdf/ICRR-Disclosable-P112759-06-29-2017-1498764031399.pdf | .Lessons1. Specialistinputs from Bank staff or consultants can be determining factors in recognizing, identifying, preparing and implementing a project.Introducing the new paradigm of mixed species ecological afforestation required a departure fromChinas tradition of forest monoculture plantations. Specialist knowledge provided the awareness to identify the newapproach, and the technical skills to design and implementit.2. Interlinkages, operationallyand intellectually, between researchers, extension staff and farmers improve effectiveness of a changeagenda.Such interlinkages, for instance, helped explore and develop planting methodologies with 30percent lower costs than expected atappraisal.3. Changing mind-setscan be a necessary and high payoff activity in innovation.The Bank team, progressively joined byChinese decision makers and implementers, had to persuade and demonstrate the new approach to a largely skeptical community ofdecision makers, foresters and villagers. Without such outreach, changing the afforestation approach, despite the larger benefitsof ecological afforestation, would have metresistance.4. Environmentalimpacts should be the primary yardstick for estimating the benefits of an environmental project.Ascurrently presented, the ERR is estimated as if it were for a fruit and timber project. Key environmental benefits such as fromimproved soil and water conservation, protected water catchments, and reduced soil erosion are not included in the maincalculation. While such environmental impacts can be difficult to measure, broad estimates are possible, at least for morequantitative discussion. In the case of the project, some soil and water conservation benefitswere estimatedandwere included in the ERR discussion and ERR estimates, but onlyin the sensitivity analysis rather than as part of the mainestimate of the ERR.5.In a pilot project especially, key results data needsinformation on source, methodology and collation.The ICR presents even core data withoutbackground on data source, measurement technique, and sampling. This leaves the reader with no basis to assess the quality of thedata. All that is generally available are, without background,two numbers - baseline value and actual, with little basisprovided to appreciate the degree of accuracy.
P112761 | Bangladesh Food Crisis Development Support Credit | South Asia | Bangladesh | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2009 | 2010 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/922081474396988236/text/000020051-20140620071803.txt | http://documents.worldbank.org/curated/en/922081474396988236/pdf/000020051-20140620071803.pdf | Building on the ICR the following lessons are highlighted.While the operation was not designed to address structural issues, it has highlighted the importance of critical reforms that would allow Bangladesh to achieve food security and fiscal sustainability over the medium term. These include reforms of the tax system, administered prices of energy and fertilizers, and the fertilizer marketing system.Bank assistance in program design and implementation can effectively compensate for the Borrower's limited capacity. The Bank implemented this operation in the context of an overall weak governance environment. However, in this operation, the Bank worked closely with the government to prepare a timely response, monitored the implementation of safety net programs ,and advised the government to take remedial actions when problems were encountered.
P112762 | Tanzania Poverty Reduction Support Credit 9 | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2012 | 2013 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/544361498229290227/text/Tanzania-TZ-PRSC-9-1st-in-a-3rd-series.txt | http://documents.worldbank.org/curated/en/544361498229290227/pdf/Tanzania-TZ-PRSC-9-1st-in-a-3rd-series.pdf | The ICR brings the following lessons, with which the IEG review agrees. A series ofdevelopment policy operations that focuses on a limited, well-researched, jointly designed and monitored reform agenda, is likelytohave more traction than those with broad and dispersed focus. The PRSC 9-11 series focused on two pillars and fivepolicy areas, in contrast to the two preceding it, which encompassed four pillars and a wide range of reform areas. A smaller andsharper focus made it easier to implement and monitor the program and adjust it in a timely manner as the circumstances demandedit, which was instrumental in achieving the outcomes. The move from broad business environment reforms to streamlining processes inselected areas has yielded better outcomes. Narrowing the focus facilitatedconcentrating efforts in fewer areas, but made the program prone to unreachable targets during the duration of the program.The outcome indicator should be achievable both because of the program and as a measure of realism. While theoutcome indicators of the PRSC 9-11 program were clear and well-defined, some of the program targets were set too high (share ofMKUKUTA to reach 100%), or number of signed PPP project at 4). A key reason for over-ambition was drawing the targets from thegovernments long-term development plans and strategies to align them with the governments objectives, but thesetargets were somewhat inappropriate for a short-term program more oriented to the budget cycle.IEGadds the following lesson:The experience of the program shows that inadequate indicators andoutcome targets can affect the assessment of a programs actual development outcome. This suggests that closemonitoring of program results during implementation is as important for program success as monitoring the implementation of theprograms prior actions and triggers.
P112765 | PUBLIC FINANCE MANAGEMENT, EMPLOYMENT, AND PRIVATE SECTOR DEVELOPMENT PROGRAMMATIC POLICY LOAN | Europe and Central Asia | Poland | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2009 | 2009 | 2012 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/362241475091443427/text/000020051-20140625055611.txt | http://documents.worldbank.org/curated/en/362241475091443427/pdf/000020051-20140625055611.pdf | The ICR contains good lessons, the following two of which stand out. First, a well-designed program requires a solid analytical foundation to help identify issues and areas where reform is likely to succeed. Second, a program focused on a few core areas in urgent need of reform is more likely to be internalized and owned by the government.
P112780 | Jamaica Energy Security and Efficiency Enhancement Project | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2011 | 2018 | 2019 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/243211542052096842/text/Jamaica-JM-Enegy-Security-Efficiency-Enhancemt.txt | http://documents.worldbank.org/curated/en/243211542052096842/pdf/Jamaica-JM-Enegy-Security-Efficiency-Enhancemt.pdf | The following lessons are taken from the ICR with some adaptation oflanguage:1. A relatively small, but targeted technical assistance operation cancontribute to important sectoral policy and institutional changes. The impact of technical assistance and of specificreports and studies led to improved laws and regulations, which helped to attract private sector investment in the targetedareas.2. Developing a robust resultsframework with measurable indicators and insuring appropriate capacity building for measuring and analyzing the indicators areimportant to provide evidence of the projects outcomes. In this case, there were several gaps. For example, noinformation was available on cost savings or increase in renewable energy generation through the LoC. The degree of attainment oftheobjective increase energy efficiency was not measured.Consistency in designing indicators which more clearlyestablish attribution would have beenhelpful.3. Where there are severemacroeconomic constraints, securing fiscal space to ensure disbursement against all planned activities in a yearcanbedifficult. Continuous monitoring, re-estimation of expected disbursements, and constant communication with the MoFcould help mitigate the risk but may not eliminate it as the fiscal space issue depends on factors beyond the projectsscope.
P112821 | ML- Governance and Budget Decentralization Technical Assistance Project | Western and Central Africa | Mali | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/769291528842824631/text/Mali-ML-Governance-and-Budget-Decent-TA-Proj.txt | http://documents.worldbank.org/curated/en/769291528842824631/pdf/Mali-ML-Governance-and-Budget-Decent-TA-Proj.pdf | The ICR offers the following lessons: Project management units overloaded with projects or responsibilities forreform are unlikely to fulfill all their responsibilities for every project or reform under their purview. To prevent problems inproject implementation it is important to set up a project implementation unit dedicated to carry out all the activities of theproject. In countries affected by conflict and violence, decentralization projectscan achieve outcomes throughafocus on building capacity and improving the dialogue between the Government and citizens through the adoption of adequatepractical tools, such as citizens budgets or citizen surveillance committee reports. Successful and timelyimplementation of project activities depends on adequate levels of technical assistance. The long absence of a knowledgeableprocurement specialist contributed to delaying the implementation of this project; when the Bank provided a qualified procurementprofessional to assist the country, it was possible to remove technical bottlenecks and expedite the execution of theproject. Building capacity must be an on-going process in countries with low capacity and frequent rotation of qualifiedgovernment staff. Doing so is necessary to ensure that the technical knowledge of the qualified staff is preserved even whenthe personnel rotates frequently.The IEG review offers the following lessons: One size is unlikelyto fit all. The experience of this project shows that a framework prepared for monitoring general reforms in public financialmanagement should be complemented with a project-specific framework that captures the characteristics and nuances of the design andimplementation challenges of each individual project. Lofty objectives require proper results indicators. Thisprojectsexperience indicates that a good results framework is necessary to assess project outcomes properly;thatrequires ensuring that the interventions and results indicators lead to achieving the projects objectives, evenbroad and lofty ones (e.g., 2, 3, and 4).
P112838 | China Wuhan Second Urban Transport | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2019 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/398201574091778722/text/China-CN-Wuhan-Second-Urban-Transport.txt | http://documents.worldbank.org/curated/en/398201574091778722/pdf/China-CN-Wuhan-Second-Urban-Transport.pdf | Following lessons are adapted from the ICR: Traffic Demand Management (TDM) measures are necessary toaccommodate rapidly urbanizing environments such as reducing traffic congestion and lowering emissions. In the short term,public transport must be made more attractive through the implementation of bus priority schemes and better modal integration.However, in the longer term, more restrictive forms of TDM such as parking management, congestion charging, and drivingrestrictions that help reduce congestion need to be promoted. An Integrated Corridor Managementapproach can improve service quality for all users in a selected corridor. The project demonstrated that installingon-street priority for buses on two corridors and constructing sidewalks, bike lanes, and bus lanes within the same right-of-wayimprovedmobility for citizens in Wuhan. With the separation of NMT, buses, and general traffic, buses run faster with morepassengers. Lack of adequate synchronization of resettlement activities with civil works can causesignificant time and cost overruns. The demolition work for the JAE was seriously delayed by a lack of counterpart fundsand land acquisition problems that led to the projects delay. A high level of institutional involvement was necessary toprovide these funds, which were only provided after the Deputy Mayor assigned strategic importance to the project along the JiefangAvenue. The PMO needs to have the experience and ability to deal with district governments, because closecoordinationcoordination with them and an explicit division of responsibilities is also necessary.
P112872 | Second Customs Reform and Trade Facilitation Project | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2010 | 2018 | 2019 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/246651556892187878/text/Afghanistan-AF-Customs-Reform-Trade-Facilitation.txt | http://documents.worldbank.org/curated/en/246651556892187878/pdf/Afghanistan-AF-Customs-Reform-Trade-Facilitation.pdf | Five lessons are drawn from the ICR (pages 44-46), with some adaptation.Projects in Afghanistan must be flexiblewith project design, the work program, the implementation arrangements, and even the ME plan. The political, economic,and security situation changes abruptly and the FCV environment is particularly challenging in Afghanistan. The newgovernment requested a third phase to the customs reform program, to which the Bank responded with the provision of additionalfinancing to the ongoing project while the new government considered its future priorities. The government requesteddispensing with the services of the UNOPS, to which the Bank authorized the ACD to implement the activities associated with theadditional financing using the ACDs own internal implementation unit. The Banksflexibility allowed theproject to progress toward its objectives.The use of the UNOPS as implementing partner of the ACD was appropriategiven the low technical and institutional capacity of the ACD, particularly with infrastructure development. It also helpedthat the UNOPS was capable with logistics, communications, and security. These were important contributions by the UNOPS tothe project in the context of the challenging FCV environment in Afghanistan. It was important, however, that the UNOPSsupported the ACD to build capacity in many aspects of project implementation and management. Eventually, the ACD implemented theactivities supported by the Banks additionalfinancing using its own implementation unit.The employment ofkey ASYCUDA staff under UNCTAD contracts helped reduce staff turnover, particularly of highly-skilled information technology (IT)staff. Staff turnover had been a major concern since the predecessor Emergency Customs Modernization and Trade FacilitationProject was started in 2004. UNCTAD employment contracts were valuable because they offered higher pay and better securityarrangements. However, UNCTAD employment can only serve as an interim solution, as the ACD will eventually have to design apay structure that offered better salaries and job security.Continuity in the composition andstaffing of theproject unit was a critical success factor with this project, according to the ICR. Many of the project staff had previouslyserved with the predecessor project, the Emergency Customs Modernization and Trade Facilitation Project, which helped with stafffamiliarity with the project objectives and project operations. Moreover, the UNOPS Team Leader, the UNCTAD Field Commander,and many in the middle management of the ACD were involved with the project, from project start to project closing. Thecontinuity in project staffing and management ensured a consistent attention to project implementation.Standard Bankprocurement guidelines which, among others, require procurement only from authorized dealers can be problematic in some countries,including Afghanistan. Many equipment manufacturers do not have authorized dealers in Afghanistan. Many bids receivedfor supply contracts were from un-authorized dealers, derailing the bidding process. Eventually, the project had to resort tousing UN Long-Term Agreement (LTA) suppliers. Future Bank projects in Afghanistan and elsewhere where this situation appliesshould carefully consider this procurement risk.
P112893 | Kabeli Transmission Project | South Asia | Nepal | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2017 | 2019 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/787781547484632697/text/Nepal-NP-Kabeli-Transmission-Project.txt | http://documents.worldbank.org/curated/en/787781547484632697/pdf/Nepal-NP-Kabeli-Transmission-Project.pdf | 1. A robust monitoring and evaluating system is essential in a country where theImplementing Agencys capacity is limited. The project was built upon lessonsinformed by an earlier project in the country and equipped with some preventive measures to avoid project implementation failure.Nevertheless, the project was not implemented efficiently and effectively. One of the reasons was the lack of a robust monitoringand evaluation system. Due to the complexities and limited capacity of the IAs, there were a lot of points where the project wasstalled. A robust ME system, such as regular meetings with a periodic review of indicators and action plans, could have been aplatform for project stakeholders to gather and change its project managementapproach.2. Adaptability of the project is the key to mobilizing citizenengagement. Unlike Component 1 and Component 2, Component 3 showed significant success in the project. One of the reasonscould be the close dialogue with the beneficiaries and adaptation of the project. The beneficiaries continuously requested gridelectricity instead of micro-hydro schemes. This was not anticipated in the project design, but close dialogue with citizensdiscovered the genuine needs of the beneficiaries and the project effectively adjusted its activities by applying a standard designof the 11 kV mini-grid to squeeze in the time for construction. Even though this alternative solution was not able to meet theoutput indicator, the satisfaction level of the beneficiaries was sufficient as the project efficiently managed the citizensexpectations.3. A periodic review of the Theory of Change and the results framework is critical tobring stakeholders in an appropriate direction. A lack of causal relationship in theory of change of the projectnegatively influenced project implementation. It could be assumed that the lack of on-grid rural electrification indicator underComponent 2 resulted in dropping this activity, which was transferred to another project. An effective theory of change and validresults framework could have clarified the causal relationships of the project, and the consequences might have beendifferent.
P112901 | Pakistan Punjab Cities Governance Improvement Project | South Asia | Pakistan | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2013 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/631791561384016268/text/Pakistan-PK-Punjab-Cities-Governance-Improvement.txt | http://documents.worldbank.org/curated/en/631791561384016268/pdf/Pakistan-PK-Punjab-Cities-Governance-Improvement.pdf | The ICR offered eight lessons from this operation that could benefit other similar operations in the future. Some of these,slightly edited, are presented below: Applying project-funded interventions, such as procurement,financial management, environmental and social management systems, into all development spending by city governments and water andsanitation agencies can provide official andstaff with relatabletangible benefits. For example, in the case ofenvironmental and social safeguards systems, cities and water and sanitation agencies internalized safeguard considerations in itsmunicipal development processesby strengtheningtheir compliance monitoring and meeting mandatory reportingrequirements. In the case of improvements in the financial system, for example, substantial increases in revenues and savings inexpenditures were realized. Cities and WASAs increased their own source revenues, reduced inefficient expenditures in energy andpremiums in delayed maintenance of service delivery assets. Performance grant mechanisms require predictabilityin the flow of funds. Delayed releases of promised resources affect the planning and implementation of planned investmentsand affect the credibility of local authorities who wish to establish accountability . As a result of the experience in thisproject, the follow-on Punjab Cities Program provided a more effective and predictable mechanism in the relevant legaldocuments. Adearth of skillsets needed to successfully achieve the objectives of an urban and regionalreform program need to be accompanied by training and capacity building endeavors. For example, in this project, whennewly elected local governments took office in January 2017 and all key City District Government officials were remapped toprovincial departments, there was an immediate need to bring new officials who were unfamiliar with the project systems up tospeed. New and extensive training programs for new officials were implemented over the last year of the project, which contributedto the need to extend the project by a year. The project team reported in its May 30, 2019 email that the new officials assumedtheir responsibilities and continued to operate the systems even after project closing. By using their ownsystems and procedures, local governments have greater chances of adopting and institutionalizing how resources are mobilized andspent to implement decentralization. For example, in this project, to improve its own source revenue mobilization, theCity Governments conducted field surveys to update its consumer base for (i) licensing fees on trades and vocations; (ii)advertisements and billboards; (iii) rents from municipal properties; and (iv) classification of land use. WASAs conducted consumersurveys to identify leakages from illegal connections and to verify connection types. Resources improved because of electronicbilling. Illegal water connections were detected. Water meters were installed. Tariff rates were rationalized. City governmentsprepared consolidated Annual Development Plans using specified templates reflecting all on-going, new, and planned investmentscategorized by sector, by entity, and whether or not these were new, rehabilitation, or replacement assets. WASAs prepared detailedasset inventories to identify inefficiencies, and prioritize maintenance and replacement needs. These data sets were the evidenceused to create the three-year rollingintegrated development expenditure and asset management plans.
P112902 | Karachi Port Improvement Project | South Asia | Pakistan | Blend | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2011 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/396001540229575512/text/Pakistan-PK-Karachi-Port-Improvement-Project.txt | http://documents.worldbank.org/curated/en/396001540229575512/pdf/Pakistan-PK-Karachi-Port-Improvement-Project.pdf | The ICR(pages 26-27) draws the six lessons from the experience of implementing this project. Of these, the fourmostimportant lessons were, with some adaptation of language.(1) A simple and adequate ME system, including welldefined and easily measurable indicators, can aid in project implementation. The indicators selected during design wereeasily measurable and since KPT was maintaining data on the shipments handled at KPT, wereused effectively during projectimplementation. In this project, the Bank team observed lack of interdepartmental coordination and lack of timely reporting ofprogressto senior management at KPT. Although not part of the original project implementation arrangement, KPT agreed to theformation of a Project Steering Committee within KPT for project monitoring approvals and follow up. This helped in takingtimelydecisions after discussions between the members of the committee.(2) Activities critical to projectimplementation and with direct bearing on the outcomes should not be placed outside the control of the project. In thisproject, during appraisal KPT had informed that dredging activities will not be outsourced, as KPT had its own fleet ofdredgers.The main backhoe dredger became non operational in 2015. While efforts were being made to get the dredgeroperational, KPT could have outsourced dredging of the area adjacent to project berths. This would have resulted in all berthsbecoming operational. This option however could not be exercised as the dredging operations were not included in the projectscope.
P112906 | Health System Strengthening and Response to Epidemiological Emergencies Project | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2010 | 2012 | 2013 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/599441474572111118/text/000020051-20140626001403.txt | http://documents.worldbank.org/curated/en/599441474572111118/pdf/000020051-20140626001403.pdf | The following lessons are taken from the ICR with some adaptation of language:Donor partnerships can provide benefits such as technical expertise and established implementation mechanisms, although there may be additional transaction costs. In the case of this project, PAHO offered extensive technical assistance for epidemic preparedness as well as facilitated drug procurement through its revolving fund. However, complications in establishing procurement processes through PAHO led to significant implementation delays.The storage capacity (availability and quality) for drugs needs to be adequately assessed for a project that includes large-scale procurement of drugs. In the case of this project, the limited capacity of storage facilities negatively affected access to medicines and the longer-term sustainability of the project outputs.
P112943 | MU-Manufacturing and Servs Dev and Compet | Eastern and Southern Africa | Mauritius | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | IPF | 2010 | 2013 | 2013 | ICRR | Less than 10 million |  | Satisfactory |  | Satisfactory | Modest | http://documents.worldbank.org/curated/en/827161474576878609/text/000020051-20140625233929.txt | http://documents.worldbank.org/curated/en/827161474576878609/pdf/000020051-20140625233929.pdf | The following are key lessons emerging from both the NCO and NCO Review:Proactivity and agility are needed to meet the changing needs of Middle Income Country clients and in developing new lines of business. The Project serves as an example of the Bankâ€™s responsiveness and agility in meeting the Borrower's development priorities. Sector Investment Lending was no longer considered an appropriate instrument for Mauritiusâ€™ evolving needs for policy and institutional support. The Bank team used this as an opportunity to adopt an innovative approach to successfully transform low-disbursing investment lending into development policy lending, with broadly the same competitiveness agenda.Coordination with other development partners can enhance coherence in policy dialogue. In this context, the Bank team worked with other development partners such as the African Development Bank, Agence Francaise de Development and European Union to increase leverage and synchronize messages.Ensuring that appropriate institutional arrangements and key personnel are in place prior to Board approval or effectiveness aids implementation.Adequate monitoring of project development outcomes requires appropriate indicators developed at the design stage. In the case of this project, there was no indicator to measure the job creation objective.Underestimation of risks, including those related to the weak capacity of the implementing agency and of fiduciary and procurement staff can be expected to hamper project implementation.
P112956 | Nigeria Lagos Urban Transport Project 2 | Western and Central Africa | Nigeria | Blend | Non-FCS | Infrastructure | Transport | IDA | IPF | 2010 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/551151520551117170/text/Nigeria-NG-LUTP-II-FY10.txt | http://documents.worldbank.org/curated/en/551151520551117170/pdf/Nigeria-NG-LUTP-II-FY10.pdf | IEG has selectedfour lessons from the ICR, with some adaptation of the language. It is important todevelop an incremental phased approach to a Bus Rapid Transit system with a focus on early deliverability. In the case ofLagos, the first BRT-lite implemented under the first World Bank -financed project created awareness and appreciation of theconceptand made it politically and technically possible to embark on a more ambitious agenda and extend the BRT system. At the sametime, while applying an incremental, phased approach to demonstrate the concept and build popular momentum, it is critical todevelop the BRT network, not just a single corridor. And it is important to show sensitivity to the city-specific context ratherthan adopt a best-technology, one-size-fits-allsolution. Competition for the market and integration of informal transportshould be soughtto improveefficiency gains ofa BRT. The project evidenced that LAMATAsnegotiating capacity may be limited, with the existence of a single operator in Lagos. International experience in urban areasshows that multiple competing operators have generally improved the productivity of public transport systems. The transition from asingle operator to a competitive environment in Lagos may allow efficiency gains in the tendering of future BRT corridors. Effortsto eliminate informal transport from the BRT corridor were not effective in Lagos: informal transport remained an importantcomponent of overall transport services. In the creation of a unit within aninstitution, it is important to develop a thorough stakeholder analysis which recognizes and incorporates the system of incentivesgoverning the institutions behavior. Thetransport planning unitscreated within thelocalgovernment areasregularly undermined the strategic efforts being made by the broader city administration at astate level. These issues were not simply a question of the TPUs low capacity; the underlying factors have a substantiallystructural component. The new units sustainability depends on a design that recognizes and tries to incorporate the systemof incentives governing the behavior of the institutions where the new unit ishosted. The intelligent transport system (ITS)is needed to be planned in such away that it would be flexible enough to accommodate multiple bus-operator models, to potentially introduce smart cardsfor BRT, and to facilitate integration with other modes of transport in the future. It is important toallow sufficient time for bidders to prepare high-quality proposals, consider instructions to bidders that would encourageinternational firms to collaborate with local partners through joint ventures, bring ITS expertise on board in the first phases ofthe project preparation to advise on the design and planning process, plan for a phased deployment with adequate time for testing,and strengthen the ITS capacity withinthe implementing agencyto closely monitor deployment and rollout.
P112975 | Cameroon - Competitive Value Chains | Western and Central Africa | Cameroon | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2010 | 2017 | 2018 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/770961520435260444/text/Cameroon-CM-Competitive-Value-Chains.txt | http://documents.worldbank.org/curated/en/770961520435260444/pdf/Cameroon-CM-Competitive-Value-Chains.pdf | The ICRs lessons contrastedsome aspects of this projects poor performance to conditions which might have ledto better performance, namely: a more realistic design drawing on multiple perspectives and capacities (e.g. IFC advisoryservices);a good practice results framework: a project coordination unit with a better defined role for line ministries andperformance-based contracts; lower turnover among Bank and government teams; better assessment of reputational risk and earlierpreparation of safeguard documents; and finallya more effective communication strategy. The absence of these good practicesin this project however, did not necessarily support them as lessons in the ICR. The ICRwas, however, in a position todrawstrategic lessonsdirectly fromthe projectspoor performance, namely: a need for the Bank tobetter define its strategic role following closure of a non-performing projectwhose objectivewas closely associatedwith the Bankscountry assistance strategy.This Review rephrases below some of the ICRlessons which had broader application than those concerning the details of this projects poor performance mentionedabove.1. Complexity of design of a project if not commensurate with the competencyand experience of the Project Coordination Unit can lead tounatisfactory project results.This projects original designwas hampered by: (a) a complex design, including studies andtechnicalassistancewhich did not contribute to the achievement of the projects objectives; and (b) a new PCU in a Ministryinexperienced in project implementation. Performance of the PCU was very consequently poor both before and after a Level 1restructuring.2. A project whose success depends on policy reforms needs relevant institutionalcapacity at the start of the project. Strengthening capacity for safeguard compliance, studies and TA were notfront-loaded into this projects preparation design, or timed very early in implementation action plans. Delays in launchingstudies and TA meant that implementation of other components were also delayed, introducing uncertainty in project implementationwhich in turn led tounsatisfactory results and high risks of unsustainability 3. Projects whichseek to catalyze more productive private sector activities need thorough coordination at all stages between all relevantWorldBank Groupinstitutions. In this project, coordination among relevantWorld Bank Group institutions wassuccessful in project preparation, but not during design of the first Level 1 Restructuring. The resulting fundamental shift indesign from 50%/50% matching grants on a competitive basis to100% direct financing of assets for pre-selectedprivate actors was contrary to normal WBG principles of maintaining a level playing field and supporting market incentives as thedeterminant for resource allocation.
P112998 | Public Works and Urban Management Project | Eastern and Southern Africa | Burundi | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2009 | 2015 | 2017 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/315291477400579501/text/ICRR-Disclosable-P112998-10-25-2016-1477400554758.txt | http://documents.worldbank.org/curated/en/315291477400579501/pdf/ICRR-Disclosable-P112998-10-25-2016-1477400554758.pdf | The ICR (p. 17-18) states 4 lessons that are summarized and slightly edited as follows: Encouragingbeneficiaries to participate in prioritizing infrastructure investments is useful when re-engaging constituents after a war whileinstitutions are rebuilt. Financial contributions from beneficiaries is also a good indicator of institutionalaccountability. Poorer communities who may not be able to raise adequate contributions could benefit from national governmentassistance. A leveraging strategy considering needs and redistributive aspects of available resources could be adopted to equitablyreach target communities. Introducing new responsibilities to nascent institutions, like private managers ofmarkets, benefit from long term technical engagement not only when introducing new tools but also while implementing them.For example, when markets were passed on to private contractors to manage, a phased or pilot approach may be useful towork out kinks in contract provisions and incentives. In another case, city governments now obligated to include operations andmaintenance of completed infrastructure assets may benefit from support not only during the planning stage but also seeing themthrough the implementation of these new budget items. Devolution and decentralization are complex policies thathappen over a long period, and more so in a fragile environment. Matching existing capacity with realistic targetscanhelp build incremental foundations for future actions to take a hold.
P113002 | Social Safety NetsProject | South Asia | Nepal | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2009 | 2015 | 2015 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/313661468186255864/text/ICRR14783-P113002-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/313661468186255864/pdf/ICRR14783-P113002-Box393191B-PUBLIC.pdf | Lessons reported in the ICR and adapted by IEG:Budgetary top-up to existing government programs can be an expedient way to respond to emergencies, but may put sustainability of benefits at risk. In the case of this project, the injection of additional financial resources helped to address the immediate food crisis, but interventions to improve the quality of the program were not undertaken and therefore the benefits likely diminished when funding ended.A project that is initially conceived and designed as an emergency operation can be used as an opportunity to begin addressing longer-term challenges, once the peak of the crisis has passed. In the case of this project, the approval of significant additional financing was used as an opportunity to shift focus to the government's capacity to address chronic food insecurity, including adding interventions to build capacity and to demonstrate policy options. The formal revision of the project objective also helped to emphasize the shift in project focus.
P113027 | CM-Community Development Program Support Project Phase-II | Western and Central Africa | Cameroon | Blend | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/587191475116312715/text/000020051-20150312114824.txt | http://documents.worldbank.org/curated/en/587191475116312715/pdf/000020051-20150312114824.pdf | IEG draws the following lessons from the preparation and implementation of this project:In CDD projects, it is important that the possibility of elite capture is taken into account at the design stage, and that the criteria and procedures for selecting target communes and vulnerable groups are fully and clearly explained.Ability to evaluate the projectâ€™s results depends to a large extent on the design and implementation of a robust M&E framework in which indicators and targets are closely related to outcomes. In this case, the goal of the APL Program is â€œimprove opportunities and livelihoods of the peopleâ€ in the beneficiary areas, which requires evidence that final outcomes improved significantly due to the project, were not driven by other factors such as programs of other partners, and were sustained.Development outcomes of CDD projects can be subject to a significant degree of risk, which can best be addressed by adequate attention to factors such as the robustness of the governing legal and regulatory framework, the institutional and financial adequacy of provisions for operation and maintenance, and post-project (or program) continuity in the institutional arrangements established.
P113028 | Mumbai Urban Transport Project-2A | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/230121506531565452/text/ICRR-Disclosable-P113028-09-27-2017-1506531537604.txt | http://documents.worldbank.org/curated/en/230121506531565452/pdf/ICRR-Disclosable-P113028-09-27-2017-1506531537604.pdf | Adapted from the ICR (paras 86-89): In an environment where major restructuring of institutions isnot possible, a first step could be to enhance the implementing agencys capabilities to tackle longer-term sustainabilitychallenges through technical assistance. For example, the studies performed under the technical assistance component have increasedMumbai Railway Vikas Corporation (MRVCs) understanding for long-term planning, customer service enhancements, non-fareboxvalue capture, and safety. Thecomplexities of large urban transport systems and the inevitable presenceof exogenous factors highlight the need forindicatorsto measure outcomesthat areattributable to projectinterventions. The indicators and targets developed for MUTP-2A reflected an assumption that MUTP-2B activities would beimplemented in a phased manner that complemented MUTP-2A. Since MUTP-2B was not implemented as envisaged,some targetsforproject indicators could not be achieved. The project experience shows that integration of newrolling stock designs with legacy station platforms may cause delays due to configuration issues. It may have been possible toreduce delays through additional engineering due diligence, formal coordination mechanisms, and/or more proactive engagement aroundthe design and approvals processes.
P113030 | Local Development Program Support Project II | Western and Central Africa | Chad | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2015 | 2017 | ICRR | >=10 million & <25 million | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/339221473882694177/text/ICRR-Disclosable-P113030-09-14-2016-1473882681334.txt | http://documents.worldbank.org/curated/en/339221473882694177/pdf/ICRR-Disclosable-P113030-09-14-2016-1473882681334.pdf | The ICR suggested an excellent set of lessons. In briefthey were: Development objectives(PDOs) and the scope of interventions for projects supporting decentralization need to be realistic. PDOs should be lessambitious and more realistic for countries with limited implementation capacity and a fragile politicalenvironment. CDD operations need to adapt to the capacity of national institutions. Forexample, an important lesson emerging from both LDPSP 1 and 2 is that bottom-up development projects that use CDD approaches arechallenging to implement and scale up, because they require extensive support with respect to capacitybuilding. Multi-disciplinary expertise is required in support of decentralization.As they build on participatory mechanisms and reach out to all segments of the local population at the grassroots,decentralization programs are necessarily cross-cutting and therefore complex. Innovative proceduresare necessary to work in the adverse context of fragile states. For example, the context of fragile states where thesecurity situation often does not permit field work, it is necessary for both the Bank and the Government to adopt innovative waysof doing business. Project remedies should be clearly identified as different from overall dialogue betweenthe Bank and the Borrower. The rules of Bank engagement with Government counterparts for each project should beclearly spelled out both internally and with the Government. For example,it should be made clear what the Bank aims toachieve without compromisingeither the individual project objectives or the broader dialogue with theGovernment Realistic implementation risk assessment should result in considering alternative institutionalarrangements. For example, the risk of failure or inadequacy of project arrangements was notflagged as high as part of LDPSP 2 implementation, and, therefore, no particular alternative arrangements wereconsidered to mitigate this risk should it happen.This Review suggests an additional lesson: The Bank need not always comply with Government requests on project designs. In this case the Government insistedon a national scope for the LDPSP 2 following the LDPSP 1 pilot. The Government put pressure on the Bank by agreeing tocontribute almost two-thirds of the total project cost. The Bank did not agree to the projects proposed national scopebut pursued the excessively large project anyway. Irrespective of the Bank/country relations this was obviously the wrongdecision and a costly one for the Government in terms of its reputation among the population. It was also costly for the Banksreputation as a trusted partner.
P113032 | ET: Agricultural Growth Program | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/339541521833858063/text/Ethiopia-ET-Agricultural-Growth-Program.txt | http://documents.worldbank.org/curated/en/339541521833858063/pdf/Ethiopia-ET-Agricultural-Growth-Program.pdf | The ICR included six Lessons. The followingfour Lessons are emphasized with some adaptation oflanguage: Exchange visits can serve as an effective mechanism to convince policy-makers toconsider new initiatives that have worked in other places with a similar context. The Livestock MarketDevelopmentsub-projects demonstrated that public-private partnership (PPP) models can be successful in Ethiopia. After studytours to Djibouti and Somalia, the sub-project successfully piloted PPPs for quarantine stations, which are government owned andrun by the private sector on a profitability basis. To ensure thesuccess of capacity-buildingactivities, a systematic, consistent, and uniform approach is needed. Many ad hoc training programswere conducted under the project, but the quality of the training was questionable and was not assessed. The project did not take asystematic approach to building capacity. With this lesson in mind, a capacity development support facility was established underthe AGP2. It is providing technical assistance using a consistent, uniform approach to capacitybuilding. Against a small holder agricultural setting, buildingentrepreneurial capacityof farmer groups and cooperativesis critical to achieving agricultural commercialization. The projectexperience demonstrated that farmer groups and cooperatives are needed to enable aggregation in a smallholder agricultural setting.The establishment of groups must be accompanied by attention to building their entrepreneurial capacity. Without it, there will belimits to the extent and speed at which agricultural commercialization in Ethiopias smallholder system andagriculture at large can be achieved. The functioning and performance of agricultural cooperatives needs to be evaluated toimprove their potential in helping farmers and other value chain actors participate inmarkets. Creating and strengtheningCommunity Investment Groups (CIGs)is an effective wayto mainstream gender into projects. The project experience demonstrated that the establishment of CIGsincreased the participation of women and youth in the project. It alsoallowed the project to focus on constraints that womenand youth face by strengthening the specialized women and youth CIGs. Targeting youth in the creation and strengthening of CIGsproved effective in increasing youth participation in the agricultural sector. The project helped youth to achieve higheragricultural productivity and incomes. However, more analytical work is needed to identify youth-headed households and disaggregatedata.
P113036 | North East Local Services Improvement Project (NELSIP) | South Asia | Sri Lanka | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2010 | 2018 | 2019 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/862791538871685933/text/Sri-Lanka-LK-N-E-Local-Services-Improvement.txt | http://documents.worldbank.org/curated/en/862791538871685933/pdf/Sri-Lanka-LK-N-E-Local-Services-Improvement.pdf | The Government prepared a comprehensive document highlighting seven key lessons from this operation and presented in variouslanguages for public consumption. The ICR incorporated these lessons and presented8 in the ICR. Some of them are slightlyreworded below: Participatory planning, transparent project prioritization, and introduction of voice, are simpledesign components that could be effectively used to support local government authoritiesto foster social cohesion, strengthenlocal institutions while delivering infrastructure services, and enhance accountability. These mechanisms, including participatorymonitoring, establishing social accountability committees, and grievance redress mechanisms could be used to reduce the risk tosustaining project outcome and can serve as take off points for future engagement in the area of local area developmentsupport. Another institutional support mechanism that could be promoted is the use of a body such as an independent auditagency to verify subproject outputs and their findings as part of the eligibility criteria for fiscal transfers to localauthorities. Alow capacity starting point for participating local authorities unfamiliar with Bank policies andprocesses requires a robust just-in-time training program in areas critical to project implementation such as Financial Management,Procurement, and Contract Administration. Based on the projects experience with low contract management capacity, clusteringsimilar subprojects may be useful during implementation. The use of geospatial data may be an effective way to visualizethe impact of a project (before and after) especially when there are numerous subproject local governmentinvestmentsinvolved. There needs to be an adequate system in place to control for attributing the changes in visuals directly to the project.In this case, after project close, the Bank analyzed 982 (of 1,214) sub-projects and conducted in depth analysis of 12 sub-projectcases studies to estimate the number of sub-project beneficiaries. The studies used satellite date and isochrome maps to measureimproved connectivity to local assets (e.g., schools, markets). Assets and residential units within the radius were mapped toestablish likely travel patterns and assessed site suitability. Results depicted reduced travel time and improved overallaccessibility.
P113069 | Bhutan Development Policy Credit 1 | South Asia | Bhutan | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2012 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/185681473933127833/text/ICRR14945-P113069-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/185681473933127833/pdf/ICRR14945-P113069-Box396299B-PUBLIC.pdf | This assessment suggests the following two lessons:1. A two year DPC Program focusing on a limited number of actions of doubtful criticality, and with modest technical capacity in Government is unlikely to achieve much progress in achieving welfare results. If these are to materialize later, such programs need follow-up by complementary actions that may help to yield a return in the shape of measurable economic outcomes.2. Monitoring of progress in a DPC will be difficult when baselines and targets are reflected by indicators that do not clearly quantify an achievement. Under the Bhutan DPOs, baselines and targets were enumerated in a way that would not be expected to measure adequately the extent to which an intended outcome was to be achieved. As a result, the extent of progress towards these could not be properly assessed.
P113078 | Geothermal Clean Energy Investment Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2012 | 2019 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/885681575910794528/text/Indonesia-Geothermal-Clean-Energy-Investment-Proje.txt | http://documents.worldbank.org/curated/en/885681575910794528/pdf/Indonesia-Geothermal-Clean-Energy-Investment-Proje.pdf | The Banks support for geothermal operations mighttarget risk mitigation at the early drillingstagesthrough a portfolio approach to support exploration drilling across several projects, some of which may be moresuccessful than others. The project illustrates the risk associated with resource uncertainties inherent in most geothermaloperations. Though concessional finance provided by the Clean Technology Fund (CTF), combined with the World Bank loan, could helpbring down the projects capital costs, it could not mitigate the risks arising from the uncertainties of resourceavailability, which called for more wells to be drilled than originally anticipated. Though Pertamina, as the equityprovider, fully absorbed these risks, the company was slow in approving the additional funding needed for additional wells, whichresulted in considerable delays in project implementation.Even then, the approval was on a conditional basis for Lahendong,where the final decision to provide funding was made contingent to confirmation of the first well drilling results. Technical Assistance (TA) support is crucial to achieving successful outcomes, especially when the client isnot completely familiar with World Bank operations and has limited capacity. TA support helped PGE prepare the planned investmentsin Ulubelu 3 and 4 and Lahendong 5 and 6, with high-quality Environmental and Social Impact Assessments (ESIAs), feasibilitystudies andprocurement bidding packages. The capacity built in PGE will now remain in the company, which could utilize it forplanned and on-going other operations. PGE should be in a position to contract out ESIAs, feasibility studies, and establishthe right criteria and capacity to ensure that these works are up to international standards.
P113084 | Disaster Risk Management DPL w/Catastrophe Deferred Draw Down Option | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2009 | 2012 | 2016 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/414991473920825791/text/ICRR14919-P113084-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/414991473920825791/pdf/ICRR14919-P113084-Box396299B-PUBLIC.pdf | Highlighted from the ICR lessons: In order to rapidly respond to a disaster, it is as important to have measures in place for identifying affected areas and disaster response priorities, as it is for a timely disbursement of funds. .A diagnostic of the countryâ€™s legal framework at appraisal and a constant dialogue with the governmentâ€™s legal department during supervision can be an effective tool to identify legal constraints that would allow the country to benefit from the revolving feature of this type of loan and act accordingly. ..Given the revolving option of the credit line, the Bank needs to develop a more consistent result framework to correctly assess the feasibility of achieving the development objective within the constraint of the total time available for implementation. Added by IEG:Relevance of design is essential for positive results that can be attributed to the operation being reviewed. Binding the policy areas and performance indicators to an operation's objective through well designed M (ii) care should be taken to avoid double counting results that may be attributable to another operation; (iii) the DPL objective, its policy areas and indicators, and results should all be on a similar and feasible scale.
P113084 | Disaster Risk Management DPL w/Catastrophe Deferred Draw Down Option | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2009 | 2012 | 2018 | PPAR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/836871500398088497/text/114745-PPAR-P113084-PUBLIC.txt | http://documents.worldbank.org/curated/en/836871500398088497/pdf/114745-PPAR-P113084-PUBLIC.pdf | 6. Lessons 6.1 The experience with the CAT DDO in Colombia shows that the instrument can help advance the DRM reform agenda and strengthen the system to respond to disaster risks. As a DPL, the loan shifted the World Bank's counterpart on DRM issues from the Ministry of the Interior and Justice to the MOF and the DNP. This allowed the World Bank to have a dialogue with the government at a higher, more strategic level than in the past, and to ensure that financial dimensions of disaster risk are fully incorporated in the DRM system and the costs and benefits of the proposed solutions are assessed appropriately. Moreover, with its renewal feature, the CAT DDO provided a platform for the World Bank to engage with and support the government over the long term. 6.2 Naturally, a CAT DDO alone is likely to be insufficient to build a system to manage disaster risks. In Colombia, the CAT DDO was part of a substantial DRM portfolio and culminated an engagement that included both knowledge and financial support over a long time. Even so, it took time for the World Bank's ideas to be accepted, and costly disasters had to occur for the government to seriously consider the ideas and take action. But when the government did come around, the World Bank was ready to assist. The common understanding of what needed to be done helped to ensure good implementation of the program despite lack of experience with this new instrument on the part of both the World Bank and the government. 6.3 At the same time, the design and implementation of the CAT DDO in Colombia raised some issues that deserve further clarification. There was a tension between the loosely defined requirement that the borrower must implement a DRM program and the government's concern over maintaining access to the CAT DDO funds at all time. This concern was a key reason why the government opted for modest results indicators to be sure that it would not lose access to the contingent credit for missing program targets. Obviously, having a secure access to a contingent line of credit is an important part of any disaster financing strategy. It would thus be very useful for the World Bank to provide further clarity on how the requirement to implement a DRM program would be assessed as a disbursement condition and how it relates to CAT DDO results monitoring.
P113099 | LR-Urban and Rural Infrastructure Rehabilitation Project | Western and Central Africa | Liberia | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2009 | 2017 | 2018 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/183031525863291394/text/Liberia-LR-Urban-and-Rural-Infra-Rehab-Project.txt | http://documents.worldbank.org/curated/en/183031525863291394/pdf/Liberia-LR-Urban-and-Rural-Infra-Rehab-Project.pdf | The ICR draws the following lessons from the experience of implementing this project, with some adaptation oflanguage.(1) Sectorreforms can beimplementedin a Fragile, Conflict and Violence (FCV)context, through aprogrammatic gradual approach, that spreads the expected reformsover several operations,whileindividual project adopts arealistic reform objective. Benefiting from the previous Bank engagement in the transportsector in Liberia, thisproject demonstrated thatmore sustainable sector gains can be achieved within a relatively shorttime (of ten years), provided conditions such asa long term programmatic commitmentto building institutional capacityare met.(2) In a low capacity context, it may be beneficial and sustainable in the long term, to build thecapacity of existing staff as well as young university graduates to take on key sector and industry roles. Under theauspices of this project, at least 20 well-trained professional were trained in road asset management. This capacity can beexpected to remain in-country, given thedemand for qualified human resources for reconstructionneeds.(3) In a fragile context, simplifiedimplementation arrangements throughinvolving aminimum number of entities for delivery of infrastructure services can behelpful.Givenmultiple stakeholders withconflicting interests, full responsibility and decisionmaking for infrastructure delivery could rest with one main entity, while keeping theother stakeholders informed, Inthis project ownership of the FuelUnloading Facility (FUF) was lacking due to the multitude of low-capacity stakeholdersentrusted with the responsibility of making decisions regarding the FUF.(4) In a post-conflict environment, it isnecessaryto assess the impact of capacity building activitiesas the feedback would help intargeting of futureinterventions.Ifoptions such as Impact Assessments (IAs) arenotfeasible due to lack of data, otheroptions need to be considered such as simpler participative methodologies such as focus group discussions and key informantinterviews.
P113102 | Yemen Schistosomiasis | Middle East and North Africa | Yemen, Republic of | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2010 | 2018 | 2019 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/446951548342926149/text/Yemen-Republic-of-RY-Schistosomiasis-Control-Project.txt | http://documents.worldbank.org/curated/en/446951548342926149/pdf/Yemen-Republic-of-RY-Schistosomiasis-Control-Project.pdf | The ICR (pp. 26-27) offered several lessons, restated by IEG:Leveragingcomparative strengths of partners under clear terms of reference maximizes partnership effectiveness. Partnershipsthat were developed by the project under clear terms of reference with the World Health Organization, the Schistosomiasis ControlInitiative of the Imperial College -London, and the End Fund leveraged the core comparative strengths of these agencies inthe interest of the project.Integrating relevant health system strengthening activities with avertical disease approach promotes sustainability and resilience. The project focused primarily on immediate needs,butcould have dealt with relevant health system strengthening aspectssuch as the integration of drug distribution forschistosomiasis with the regularhealth system.When a vertical approach fora disease control project is adopted, maintaining its single disease purpose maximizes the likelihood of its progressandcost-effectiveness. Although primary attention toschistosomiasis was temporarily dilutedby theintroduction of deworming and other neglected tropical diseases, the project was focused on attaining its stated objectives andmaintained its primary attention on schistosomiasis control.
P113134 | Madagascar - Emergency Food Security and Reconstruction Project | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2009 | 2013 | 2014 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/525081474493108938/text/000020051-20140626123311.txt | http://documents.worldbank.org/curated/en/525081474493108938/pdf/000020051-20140626123311.pdf | The following lessons are drawn from the ICR (pp. 25 - 27):Flexibility in implementation of a project in a volatile political environment can be critical. As part of humanitarian response permitted under OP7.30, the project was able to disburse a cash-for-work component prior to other components and thereby help cushion immediate adverse effects on vulnerable populations. Increased autonomy of the implementing agency, restrictive controls to personnel changes, and an objective use of targeting criteria can help protect against political interference. In the fragile political environment in which this project was implemented, these measures proved valuable while a collaborative relationship with the main authorities was maintained. Finding synergies across ongoing efforts in disaster management can strengthen a program. During implementation of this project, for example, the Ministry of Health used the opportunity of vulnerable workers assembled on cash-for-work project sites to provide health services directly to them and deliver targeted awareness campaigns.
P113145 | Benin Emergency Urban Env. Project | Western and Central Africa | Benin | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2011 | 2018 | 2018 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/310511530233036562/text/Benin-Benin-Emergency-Urban-Env-Pr.txt | http://documents.worldbank.org/curated/en/310511530233036562/pdf/Benin-Benin-Emergency-Urban-Env-Pr.pdf | The lessons are taken from the ICR with some adaptation of language.An emergency project can achieve resultsbeyond just basic emergency measures if project management is flexible. This project was designed as an emergency responsethat was linked to longer-term reconstruction and prevention efforts. Two additional rounds of financing helped expand the scopeand longer-term impact of the project.Moving from an impact-focused to an output-focused results framework mayjeopardize a projects ability to adequately report on results. An oversimplification of the indicators makes itchallenging to capture the full impact of the project. Yes/no target values for PDO indicators does not capture theextent ofoutcomes achieved by the project.To establish an Early Warning System (EWS)is highly complex and costly, requiringexpertise, analysis, preparations, needs assessments and capacity building prior to its design and implementation.Establishing an EWS in an urban setting is ambitious, and especially in environments that lack administrative and implementationcapacity.Flood maps are an important analytical foundation for the planning of interventions, to track andvisualize progress and to evaluate its impact. This is one of the main lessons from the projectthat should bereflected in new project designs.Effective communication and outreach may be a key element of successfulimplementation. The project benefited from having high visibility in the country partly owing to a generous communicationsbudget used to raise awareness among the general public about the projects objectives and achievements.
P113148 | SB: Telecommunications and ICT Development Project | East Asia and Pacific | Solomon Islands | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2010 | 2015 | 2016 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/253541468296466114/text/ICRR-Disclosable-P113148-06-10-2016-1465565211071.txt | http://documents.worldbank.org/curated/en/253541468296466114/pdf/ICRR-Disclosable-P113148-06-10-2016-1465565211071.pdf | The ICR (page 21-22) draws the following main lessons from this project. Particularly in a project where countrycapacity is weak, at the design stage it is necessary to ensure that experienced counterparts are in place before effectiveness andtechnical assistance activities are provided to the relevant ministry.Recruiting counterpart staff in advance canhelp in furthering thelegislative framework component of the project. A more upfront and documented discussion withthe implementing agency is needed regarding what areeligible expenditures under the project arenecessary.A significant amount of time and effortcan beexpended for resolving the issue of ineligibleexpenditures. Having a formal Mid Term Review can beuseful,even if there isgood performanceduringthe initial years of theproject. A formal mid term review canhelpin engaging higher level officials andthereby advancing a key policy component. Having continuity of staff within the project implementation unit canbe very helpful in successful completion of the project.
P113151 | Vietnam Industrial Pollution Management Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2013 | 2019 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/232911561752079781/text/Vietnam-VN-Industrial-Pollution-Management.txt | http://documents.worldbank.org/curated/en/232911561752079781/pdf/Vietnam-VN-Industrial-Pollution-Management.pdf | The ICR (p. 29-30) provided useful lessons learned which were adapted byIEG: If indicatorsto ensure monitoring of Industrial Zones compliance with industrial wastewater treatment regulations are omitted in theResults Framework, there is a risk that reporting on compliance will be jeopardized. In this projects ResultsFramework no such indicator was included but in a pollution abatement project in Lebanon an indicator measuring regularlypublished monitoring reports covering environmental compliance of IZs by authorities was selected.Selecting indicators that can be monitored in sufficient detail and on a regular basis is critical for ensuring morereliable monitoring of outcomes. In this project the data used to assess IZs compliance with industrial wastewaterregulation was derived from the provincial DONREs on-site monitoring activities which only took place on a bi-annual orquarterly basis, making reliability of such few data points low. Average representative sampling with more samples being averagedout or continuous sampling and including minor flexibilities for exceedances would have been beneficial for measuring improvementin compliance. Leaving some degree of flexibility in the project design is useful for adjustingactivities during implementation when needed. This project defined the exact rules and regulations to be reviewed andrevised, the technical specifications for the technical equipment to be procured, and the locations for AMSs to be installed, notallowing for sufficient adjustment to accommodate circumstances on the ground. This resulted in significant implementationbottlenecks and delays.
P113156 | ETHIOPIA GLOBAL FOOD CRISIS RESPONSE PRO | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2011 | 2012 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/756031474572015479/text/000020051-20140624203245.txt | http://documents.worldbank.org/curated/en/756031474572015479/pdf/000020051-20140624203245.pdf | Building on the project experience this assessment identifies four major lessons: The risk of a short-run emergency response compromising a long term World Bank supported reform effort should be assessed at design. Steps to bring the reform effort back on track if needed after the emergency should be identified. Health safety and environmental implications need particular attention in emergency projects such as FSP since their rushed implementation schedule often does not allow for mitigation plans to be put in place before implementation. Inadequate attention to the limits of country capacity and effective coordination with agencies, such as WFP, that have traditionally been in the forefront in dealing with food crisis situations can hamper both the timeliness and effectiveness of the food crisis response. A more sophisticated system of estimating demand, including an estimate of the optimum level of strategic fertilizer reserves between one season and the next would be important for ensuring efficiency of resource use in Ethiopia which is entirely dependent on centralized imports for its fertilizers.
P113156 | ETHIOPIA GLOBAL FOOD CRISIS RESPONSE PRO | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2011 | 2011 | PPAR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/172231468275111806/text/628340PPAR0P110e0only0900BOX361502B.txt | http://documents.worldbank.org/curated/en/172231468275111806/pdf/628340PPAR0P110e0only0900BOX361502B.pdf | 10. Lessons 10.1 Building on the project experience this assessment identifies four major lessons\. 10.2 The risk of a short-run emergency response compromising a long term World Bank supported reform effort should be assessed at design. Steps to bring the reform effort back on track if needed after the emergency should be identified. An emergency situation does not allow the time to do detailed analytical work in support of lending. Yet, it is always possible to do a quick review of past interventions, to understand the long term goals that the Bank has been pursuing in a sector and assess if there is a possible risk to them from the emergency response. Steps to bring the reform effort back on track if needed after the emergency should be identified. While the arrangements under the FSP that allowed AISE to emerge as the sole importer may have contributed to timely allocation of foreign exchange and procurement of fertilizers, it set back the whole reform process being supported by the Bank over the last decade with fertilizer marketing reform. 10.3 Health safety and environmental implications need particular attention in emergency projects such as FSP since their rushed implementation schedule often does not allow for mitigation plans to be put in place before implementation. In the FSP the ESMP was prepared long after most of the fertilizer had been distributed. However, the Bank could have easily drawn on the experience of past projects that have supported agricultural inputs distribution and marketing to understand their environmental and social implications and ensured that basic health and safety mitigation measures were incorporated whether the ESMP was undertaken or not. 10.4 Inadequate attention to the limits of country capacity and effective coordination with agencies, such as WFP, that have traditionally been in the forefront in dealing with food crisis situations can hamper both the timeliness and effectiveness of the food crisis response. In Ethiopia import of fertilizers to contribute to agricultural production for the coming season supported through the FSP disrupted the import of food aid to avert a humanitarian crisis being undertaken by WFP. The conflict arose because of shortage of port capacity and transportation logistics. Better planning and coordination between the World Bank project and WFP and realism about the size of the project could have avoided the conflict between the two different kinds of support provided by the two organizations. 10.5 A more sophisticated system of estimating demand, including an estimate of the optimum level of strategic fertilizer reserves between one season and the next would be important for ensuring efficiency of resource use in Ethiopia which is entirely dependent on centralized imports for its fertilizers. The current demand estimation process for fertilizers is based on a cumbersome administrative process that involves a large number of actors at various levels of the government and little attention is paid to price sensitivity of demand which influences the rate of fertilizer application. Over the last several years demand has been over-estimated and has contributed to large over-stocks that fluctuate from year to year. Development both of a sound system of demand estimation and a strategic level of stocks based on economic analysis of all costs and benefits, including consideration of frequent delays caused by the congestion at the Djibouti port, could avoid wastage of scarce foreign exchange resources.
P113160 | MONSTAT: Strengthening the National Statistical System of Mongolia | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2009 | 2015 | 2016 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/231591467995380077/text/ICRR14885-P113160-PUBLIC.txt | http://documents.worldbank.org/curated/en/231591467995380077/pdf/ICRR14885-P113160-PUBLIC.pdf | The ICR (pp. 23-25) identifies several valuable lessons, including the following:Establishing twinning partnerships with international institutions is beneficial for obtaining statistical expertise and sustained engagement with international experts, not just during project implementation but also after a project has been completed. Through this project's twinning operation with the National Statistics Office of Germany and the Korea Statistical Office, the project particularly benefited in terms of knowledge sharing and direct access to relevant processes and procedures. Combining a local Task Team Leadership with a Task Team Leadership at headquarters allows for provision of technical assistance and addressing of delays promptly in the field, while at the same time ensuring access to additional technical resources at headquarters. The ICR (p. 24) states that the decentralization of task team leadership after the Mid-Term Review had a positive impact on the achievement of this projectâ€™s objectives.Broadening a national statistical system goes beyond the NSO. This project fostered collaboration between the NSO, regional statisticians, and statisticians in line ministries and government agencies through working groups and regular seminars to discuss common statistical challenges.
P113167 | AFCC2/RI-Enhancing Institutional Capacities on REDD issues for Sustainable Forest Management in the Congo Basin | Other | Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2012 | 2019 | 2019 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/179221558014220522/text/Africa-Regional-REDD-Congo-Basin.txt | http://documents.worldbank.org/curated/en/179221558014220522/pdf/Africa-Regional-REDD-Congo-Basin.pdf | The ICR provided some important lessons particularly for regional projects. The most relevant ones follow withsome modification of language.Addressing complex coordination needs between regional and nationalactivities as well as among donors can lead to successful implementation of regional projects. The coordinationbetween national and regional activities remained a challenge. With four national level FCPF REDD+ readiness activities implementedat the same time as the project, extra work was needed to avoid duplication and ensure alignment with FCPF. In addition, it iscritical for national projects to pay close attention to the regional context during their design, this can also be resolvedthrough coordination. The support provided by Forest Carbon Partnership Facility to civil society and indigenous peoples reshuffledthe distribution of power within the civil society organizations nationally. Meanwhile, leaders at the regional level were notinvolved nor in control of the events at the national level, which led to a disconnect between the national and the regionallevels. This created issues with the legitimacy of the civil society groups working on climate change under the project. Inaddition, in order to avoid duplication of works and activities, communication was established between national FCPF projects andFAO, and no-objections were only provided by the World Bank after verification with theseparties.Including small budget envelopes for country-specificactivities in regional projects can increase buy-in of countries. Although the amountsunder the national envelopes was administratively cumbersome (created procurement challenges), these were very useful and flexible.These envelopes helped to have direct discussions with the national teams; therefore, to keep them engaged and involved with theproject. Also, this led to the regional team better understand the challenges and be perceived as a service provider.
P113172 | Ghana Natural Resource and Environmental Governance - DPO | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | DPF | 2009 | 2010 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/380701474595840851/text/000020051-20140625083557.txt | http://documents.worldbank.org/curated/en/380701474595840851/pdf/000020051-20140625083557.pdf | The ICR identifies a number of lessons:Shifting from investment projects to sector budget support can increase government ownership and improve dialog between agencies. Government buy-in is much stronger when they feel more completely in charge of the agenda and strategic decision making. Dialog between agencies is improved when they work together on budgeting of a joint program with less direct involvement from the Bank.A lack of upfront sectoral strategic and budgetary plans can reduce the impact of sectoral budget support. If they need to be improved, this should be formalized within the framework.A program framework that concentrates on outputs will not be useful during implementation and will be unable to demonstrate results. A framework should be based on sector strategies rather than substituting for them.Development policy lending has limitations when used as the only vehicle of support, and may be more effective when combined with other instruments (such as a technical assistance facility). It may be difficult to achieve policy reform and to improve sector management systems through a single instrument.The dual complexities of a multi-donor approach across multi-sectoral work add significant challenges to design and supervision, and multiply transaction and processing costs. Alternative approaches may have been for different donors to explicitly lead support different technical areas, to differentiate disbursement triggers across donors based on sectoral leadership, or to coordinate donors based on unity of purpose rather than unity of instrument.Complex policy reforms can be hindered by the annual processing requirements of a programmatic DPO with 12 month projects. This design means that there is only a 6 month gap between disbursal of one operation and the delivery of prior actions for the next operation, leaving very little time to discern outcomes from the previous set of actions.IEG also finds that:The need for consensus and harmonization in multi-donor operations reduces the ability to adjust programs during implementation.There is a risk that sharing design and monitoring of program triggers and indicators with other development partners will lead to a system that does not focus on key policy results and/or does not provide sufficient evidence to meet Bank accountability requirements.
P113172 | Ghana Natural Resource and Environmental Governance - DPO | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | DPF | 2009 | 2010 | 2014 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/816671468030535916/text/889590PPAR0P1000Box385285B00PUBLIC0.txt | http://documents.worldbank.org/curated/en/816671468030535916/pdf/889590PPAR0P1000Box385285B00PUBLIC0.pdf | 6. Lessons 6.1 The experience of NREG offers a number of useful lessons about using development policy operations for sectoral interventions, about donor harmonization, and about natural resource management. Lessons about Development Policy Operations 6.2 Earmarking funds from a DPO to specific agencies can partly undermine the choice of instrument. It can shift perceptions of responsibility by agencies to the Bank rather than to the government, it can disrupt the relationship between the finance ministry and the line ministries by inserting the Bank, and it can mean that responsibility for the operation is delegated from government to the agencies reducing overall government program ownership. In this case, it led to the program to be implemented more along the lines of investment lending projects at the agency level â€“ though without the financial management, procurement, or safeguards required for investment lending. 6.3 There is a risk that in sectoral DPOs with one-year operational cycles, technical and policy advice to the client can be crowded out by processing requirements. In this program, the short period between disbursement of one operation and assessment of triggers for the next meant that only moderate progress could be made under each operation. Combined with the large number of outputs and targets being tracked, this meant that much of the supervision process focused on verification rather than client support and engagement. A short program horizon also led to selection of very intermediate outcomes for program development objectives, which meant that the program framework and monitoring and evaluation progress were not focused on addressing the main outcomes of concern in the sector (resource degradation, environmental damage, etc.). 6.4 Program documents should clearly distinguish between the description of policy areas and the program being implemented, the specific prior actions and triggers, and the indicators needed to assess performance. Prior actions and triggers are disbursement conditions, meant to represent the elements of the program critical for success or reforms that are politically difficult to produce. A DPO does not need to formally track the production of every output in the program. Creating too many output-oriented targets can cause agencies to focus on producing specific outputs, at the expense of more outcome-oriented policy progress. Outcome indicators should be separate from the disbursement condition verification process, and should be selected to provide useful information to guide the program during implementation, and to allow assessment of progress on broad outcomes of interest. Development policy operations require trust in government that they will do the right thing, rather than a design that micromanages the program. 6.5 In this program, some triggers and targets were useful, while others were focused on outputs of secondary importance that arguably could have been included in the program without being formal disbursement conditions or targets. Some triggers and targets were quite subjective, which added tension to the verification process. 6.6 Sectoral development policy operations may need complementary technical assistance and support. Sectoral DPOs are implemented by line ministries that often do not have the skills or capacity to implement policy reform programs quickly, and so may require high levels of client support and engagement. Donors cannot expect that government will necessarily purchase its own technical assistance with budget support funds\. developing country governments are often reluctant to pay for expensive international experts, even when that technical expertise may be valuable. In this operation a lack of technical assistance arguably led to delays and difficulties in some of the more complex activities, like the design and implementation of the wood tracking system. Particularly in sectors with complex political economy and social dynamics such as natural resource management, a lack of accompanying tools (such as rigorous political economy and/or social analysis) conducted upfront make it difficult to address underlying problems. 6.7 Sectoral development policy operation programs should include a long-term plan for addressing what will happen at the end of the program. If budget support funds are used to significantly increase the budgets of specific agencies, then there are risks that progress will not be sustained when donor support ends at the end of the program. Explicitly planning for the transition period at the end of programs might help to reduce these risks. Lessons about donor harmonization 6.8 Donor harmonization is important, but has tradeoffs. Large, harmonized programs can have higher reach and a greater ability to function as a single platform for sector reform. But coordination between donors adds significantly to preparation and supervision burden, which may reduce the time left for wider stakeholder outreach. A clear and formal division of labor between development partners within the harmonized program could help to reduce this burden and improve the accountability of individual donors. If such agreements are informal then they may not last as staff turnover occurs, accountability may be dispersed, agencies may not focus efficiently on providing specialist expertise, and duplication may emerge. There needs to be a clear understanding and formal agreement between partners about monitoring and evaluation and who in government will be accountable. Harmonized programs may also be less flexible, as the agreement of all partners is needed before major design frameworks can be revised. A key challenge for harmonization is that each agency has its own rules and procedures, and there may be significant differences across agencies in expectations (for example, the Bank's DPO instrument is not the same as sector budget support instruments of other donors). 6.9 Introducing parallel financing into a sector with harmonized budget support can fracture harmonization. It can encourage government agencies to focus on bilateral relationships with individual development partners rather than engagement through the harmonized mechanisms. Lessons about Natural Resource Management 6.10 Civil society can play a useful role in natural resource management if government and civil society groups are able to collaborate productively. This requires government ministries and agencies that are willing to listen and act collaboratively, and civil society groups that can coordinate to focus messages and engage in a productive rather than purely adversarial manner. Donor pressure can have a positive role in improving this relationship. 6.11 Addressing social conflict is important, but progress is difficult to assess without social assessment analysis that describes the causes of conflict and measures conflict levels and changes over time. Tracking tools that are not connected to an ability to take actions may have little impact. 6.12 Creating and publishing environmental ratings of large companies can help to provide public pressure on the private sector to improve their environmental performance. Self-reporting backed by audits and inspections can be a cost-effective means of generating ratings if the process is designed in a way to avoid governance risks, such as by having a clear rules-based methodology for translating data into ratings.
P113173 | PCB Management Project | Western and Central Africa | Nigeria | Blend | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2012 | 2016 | 2017 | ICRR | Less than 10 million | Highly Unsatisfactory | Highly Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/201061477325719837/text/ICRR-Disclosable-P113173-10-24-2016-1477325697661.txt | http://documents.worldbank.org/curated/en/201061477325719837/pdf/ICRR-Disclosable-P113173-10-24-2016-1477325697661.pdf | The ICR draws the following lessons from implementing this project. A clearassessment of the implementation capacity of agencies and the political economy context at the design stage is critical foridentifying appropriate implementation arrangements. In the case of this project, the Federal Ministry of Environment wasselected as the implementing agency, with the Power Holding Company of Nigeria playing a small role. A capacity assessment was notmade during project preparation to identify capacity and hencethe optimal implementing arrangements and this impacted onproject performance. External influencessuch as privatizationthat may affect projectimplementation need to be adequately anticipated at the design phase. In the case of this project the externalinfluences such as privatization of the power sector, which had been anticipated impacted on projectperformance. Delaysin holding an MTR can contribute to lost opportunities. In the caseof this project, the MTR was held about 2.8 years into a four-yearproject.This allowed little time within the projecttimeframe for addressing the issues that arose. A careful design of public awareness campaigns with adequateinformation on how to reduce or manage environmental risksisimportant toavoid negative environmentalrepercussions. In the case of this project, although the public awareness campaigns hadsome impact on making peoplemore aware of PCB risks, the campaigns did not provide adequate information on how to reduce or managethese risks. In this projectcase, one consequence was that the power company workers wereunwilling to work with transformersafter the campaigns becausethey perceived the risk to be high, suggesting weaknesses in linking communication campaigns to mitigation measures andtraining.
P113176 | Economic Management and Governance Reform Grant 2 | Western and Central Africa | Central African Republic | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2011 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/671181474483417440/text/000020051-20140624190307.txt | http://documents.worldbank.org/curated/en/671181474483417440/pdf/000020051-20140624190307.pdf | Donor coordination is essential to providing support for an agreed program. In this case, lack of expected donor support curtailed an important reform.Reforms for countries such as CAR need to be focused on the key basic achievements required in a step by step development process, such as this.
P113184 | Pacific Regional Connectivity Program | East Asia and Pacific | Tonga | IDA | Non-FCS | Digital | Digital Development | IDA | IPF | 2012 | 2019 | 2019 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/287101560546147298/text/Tonga-Pacific-Regional-Connectivity-Program.txt | http://documents.worldbank.org/curated/en/287101560546147298/pdf/Tonga-Pacific-Regional-Connectivity-Program.pdf | The ICR (pages 30-31) draws the following main lessons, from the experience of implementing this project, with some adaptationof language.(1) In small country situations,careful consideration should be given tocountrycharacteristics and needs includingscale and growth, andactivities need to be designed and tailoredaccordingly. Unlike many prior Bank financed ICT projects with public-private partnerships, this project envisioned astrong role for the public sector at appraisal,given the small size of the market andrelatively limitedtelecommunications traffic. The project attempted to address monopoly risks through strengthening regulatory oversight andincreased private sector participation during implementation. This approach could be relevant for the Small Island DevelopingStates.(2) Technical assistance activities need to be designed based on a careful consideration of public sectorcapacity and availability of skilled resources. The technical assistance and training provided under this project couldhave benefitted from more follow-through (such as through training activities) aimed atlonger-term implementation support.Moreover,special attention needs to be given to theadequate staffing of the institutions responsible for ICT policy andregulation, training and education, and attracting from abroad to Tonga the necessary skills/competence.(3) Giventhe quick pace of social change from the rapid growth of fast Internet access, it would be useful to invest in awareness raisingprograms aimed at promoting digital skills. This could include cooperation with civil society organizations and throughacademic partnerships.
P113199 | Food Crisis Response Project | South Asia | Afghanistan | IDA | FCS | Sustainable Development | Water | SPF | IPF | 2009 | 2011 | 2013 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/130861474490017796/text/000020051-20140625071417.txt | http://documents.worldbank.org/curated/en/130861474490017796/pdf/000020051-20140625071417.pdf | The following two lessons are taken from the ICR with some adaptation of language:In countries with difficult terrain and scattered communities, a robust three tier implementation structure can improve oversight of project activities. In the case of this project, oversight management was provided by the National Solidarity Program headquarters in Kabul, while Facilitating Partners and non-governmental organizations monitored activities at the community/district level, and community priorities were intended to be reflected through elected councils. In post conflict situations and fragile states-where continuous and intensive implementation assistance/supervision is needed, decentralized task teams are essential. In the case of this project, the task teams provided support to communities, and helped to expedite preparation and implementation of sub-projects. IEG would add a third lesson:Arrangements should be made, within the constraints imposed by a difficult security situation, for the adequate reporting, monitoring and evaluation of the results of project activities on the ground. Given the deteriorating security situation, monitoring of project implementation in Afghanistan has become the greatest challenge. To address this situation, the project team explained that NSP III is currently deploying local monitors in high risk areas, using ICT (smart phones) to collect geo-referenced real time data, as well as â€˜third partyâ€™ firm to monitor progress and quality of sub-projects implementation.
P113202 | Health System Performance | Western and Central Africa | Benin | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2010 | 2017 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/367791535139937616/text/Benin-BJ-Health-System-Performance-proj-FY10.txt | http://documents.worldbank.org/curated/en/367791535139937616/pdf/Benin-BJ-Health-System-Performance-proj-FY10.pdf | The ICR (pp. 47-48) offered several useful lessons, including the following lessons re-formulated byIEG:Insufficient political support jeopardizesRBF sustainability. This wasnoted atthe end of this project. While political commitment to development objectives remained steady, the newgovernment did not support the RBF mechanism becauseit perceived the RBF approachas a distribution of bonuses to healthstaff (Section 7 and ICR, p. 38).Adequate verification of results helps tominimize thegaming of the system since RBF paymentsto facilities and staff would be commensurate with actualperformance (Section 4).Enhanced autonomy of health facilities promotesperformance. Suchautonomy, although limited,enabledtheprocurement of medicines and equipment(Section 4).The ICR noted that the volume of services would likely have been higher if the autonomy of healthfacilitieshad beenmore extensiveas originally designed.
P113218 | SO Rapid Response Rehab of Rural Livel | Eastern and Southern Africa | Somalia | IDA | FCS | Sustainable Development | Agriculture and Food | SPF | IPF | 2009 | 2011 | 2012 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/570551474570567791/text/000020051-20140624201605.txt | http://documents.worldbank.org/curated/en/570551474570567791/pdf/000020051-20140624201605.pdf | The ICR includes a number of lessons from the project experience, some of which are adapted below:Assigning project implementation and management responsibilities to reputable and experienced institutions that are operating in the country can be a viable implementation option for project implementation under precarious security and governance conditions arising from civil strife. In this case, the timely implementation of the project was attributed to the familiarity of FAO and its implementing partners within the project area, as well as the good relationship established with the local communities and authorities. Basing recovery and rehabilitation programs on the production of traditional crops is important under circumstances when normal trading is disrupted. Traditional crops substituted for imported foods in the local markets can reduce the impact of soaring global food prices on consumers.The provision of area specific agricultural inputs can have a significant impact on crop yields and production.
P113219 | SL-DPL-FOOD CRISIS RESPONSE | Western and Central Africa | Sierra Leone | IDA | FCS | Human Development | Social Protection & Jobs | SPF | DPF | 2009 | 2009 | 2010 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/613691474492307386/text/000020051-20140620074226.txt | http://documents.worldbank.org/curated/en/613691474492307386/pdf/000020051-20140620074226.pdf | The ICR offers three lessons and two are highlighted because the messages of the first and second lessons are similar.The lessons are presented with slight modification from the ICR wording.It would be preferable to use existing mechanisms for M&E instead of creating new set-ups for such one-shot, crisis response operation.There were advantages gained from keeping the design of the operation simple and well focused on Government priorities and country circumstances. This DPG focused only on reduction of tariffs and excise rates of basic items, provision of inputs, and targeted feeding programs.
P113219 | SL-DPL-FOOD CRISIS RESPONSE | Western and Central Africa | Sierra Leone | IDA | FCS | Human Development | Social Protection & Jobs | SPF | DPF | 2009 | 2009 | 2013 | PPAR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/259651468303550867/text/761970PPAR0P070IC0disclosed04010130.txt | http://documents.worldbank.org/curated/en/259651468303550867/pdf/761970PPAR0P070IC0disclosed04010130.pdf | 4. Lessons 4.1 Attempts to lower prices through reducing tariffs on imported foodstuffs have direct consequences on government revenues yet may have only marginal impact on consumer prices relative to the much larger impacts off international price changes. The impact of the tariff reductions on rice prices (about six percent) was small, and insignificant relative to the doubling of food prices influenced by international market forces. The impact on households' cost of living was even smaller. Meanwhile, Government had taken an array of separate actions to buffer the increase in rice prices, which are likely to have had greater short-term impact and at lower cost than the tariff reductions. This raises the question as to whether the operation was an efficient way of mitigating the price increases. 4.2 The effectiveness of a cash-for-work program can be compromised in its effort to target benefits to particular social groups in the absence of\. (i) clear criteria and processes that ensure objective selection of communities and individual beneficiaries; (ii) communities as the primary deciders on the type of works to be done and selection of the participating individuals; and (iii) greater women's participation and differentiation of activities better suited for women. The Social Action Project's cash-forwork program primarily reached its target groups, especially for youths. But selection processes for the individual participants were not uniformly applied, allowing situations where vested interests influenced selection of the individuals. Communities felt that their participation could have assured more objectively based selection of the beneficiaries, and choice of investments responding better to the communities' priorities. Women's participation would have been higher if work activities had been differentiated between more strength-based activities for men and less physical tasks for women. 4.3 High community participation helped the Social Action Project's communities to ownï¿½? their sub-projects and foster interest in maintaining their investment and operating the service. The project's community sub-projects were mostly effective in establishing community institutions, infrastructure and services, and there are some indications that they might be sustained beyond the short-term. An IEG review of the Bank's experience with social funds found that a common experience with such funds was that community infrastructure was not adequately maintained and that the facilities and services were relatively short-lived. Whereas a common approach for social funds is to place the infrastructure as first consideration, with participatory processes often in a less dominant role, the Social Action Project placed communities and community processes at the fore. Decisions, implementation and operations were the community's responsibility, and necessarily required a high degree of interaction and cooperation which helped create collective â€•ownershipâ€– of the asset and service. The luxury of choosing a highly participatory approach may not be there for social funds responding to urgent disaster recovery, but where possible, participatory approaches may have better chances of sustainability. 4.4 Add-on emergency components to existing projects, which experience has shown often encounter implementation difficulties, have greater chances of success with an established institutional base. The addition of the cash-for-work program to the Social Action Project benefitted from an experienced field-oriented agency (NaCSA) operating in all the country's districts. It had also done a small pilot for cash-for-work giving it at least a minimal base for scale-up. 4.5 In a food emergency operation there may be a trade-off between a rapid, largerscale response at the cost of some reduction in quality, compared with a better prepared operation that is slower in mitigating the emergency. The cash-for-work program was prepared quickly, when rice prices were still high, and was implemented quickly. However, had the program been prepared in a more deliberated way, and implemented with less haste, it is likely that there would been fewer design and implementation shortcomings. The way forward 4.6 While these operations addressed the short-run impact of food price increases, and Government's 2009 food security framework and 2012 policy implementation plan provide many of the actions that would enhance food security further, there is no comprehensive longer-term food security plan showing the inter-linkages between the various actions and institutions involved. The design and value of the food crisis grant and the cash-for-work program helped Sierra Leone respond to the immediate needs of the food emergency. The Bank portfolio as a whole also potentially contributes to improved food security (such as the projects related to health, education, youth employment, roads and marketing chains). But without a comprehensive plan to integrate such operations within an overall food security strategy, to consider gaps in emergency response, to reduce future vulnerability, and to think through institutional responsibilities and coordination, relevant needs and potential synergies may be missed. Such a plan would also benefit from a more integrated agricultural development program to draw the Government's ongoing actions to promote agricultural development into a more interlinked strategy.
P113220 | Productive Safety Net APL III | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2010 | 2015 | 2017 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/535081495645599152/text/ICRR-Disclosable-P113220-05-24-2017-1495645585022.txt | http://documents.worldbank.org/curated/en/535081495645599152/pdf/ICRR-Disclosable-P113220-05-24-2017-1495645585022.pdf | The ICR (pp. 44-47) identifies ten lessons, of which IEG cites four: Commitment tohigh levels of governmentdonor coordination is likely a key factor for success. The central role of the Governmentand the Banks leadership in the DCT contributed to the longevity and effectiveness of the partnership. TheDonorCoordination Team provided technical support and a forum for government-donor coordination, and the Semi-annual Joint Review andImplementation Support missions, with participation from Government officials at all levels, DPs, and other stakeholders,strengthened cooperation. Programmatic approaches to investment lending can provide suitable supporttoa program with a longer-term vision. In this case, the segmentation of financing and interventions into phasesfacilitated ongoing program implementation, evaluation, learning, and adjustments. The initial short and contained phases withspecific objectives enabled the program to be scaled up and broadened, based on the experience of the earlierphases. Use ofa consolidated results framework that includes indicators and targets adoptedby the Government and DPs can be challenging. The Bank selected a subset of indicators from the Governments broadand comprehensive results framework for the APL series. However, it was challenging to agree to targets for these indicators, withthe Government wanting stretch targets to motivate staff but theDPs desiring more realistic, achievabletargets. Institutional reform and changing the roles and responsibilities of front line workersrequires allocation of appropriate time and effort. The goal of the HABP to transform extension services from asupply-side to a demand-driven model, with simultaneous engagement of financial service providers to extend credit to PSNP clients,as well as reform of the roles and responsibilities of staff who had been working primarily as agricultural extension agents, waschallenging given the scale and time frame for the program.
P113221 | CAR Food Response Project | Western and Central Africa | Central African Republic | IDA | FCS | Infrastructure | Urban, Resilience and Land | SPF | IPF | 2009 | 2012 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/198851474904087110/text/000020051-20140626001454.txt | http://documents.worldbank.org/curated/en/198851474904087110/pdf/000020051-20140626001454.pdf | The ICR offers a number of lessons of which the following are the most important (with some reformulation of language):1. For emergency operations prepared under OP 8.0, intense implementation support will often be needed immediately following effectiveness to rapidly close any â€œreadiness gapsâ€ and ensure successful outcomes. 2. Outsourcing implementation to non-governmental partners can be an effective strategy in fragile states. The design of Component 2 as the government in the role of coordinator with subsidiary agreements with NGOs lowered the risks and increased the quality. The major shortcoming of this design can be the high overhead cost associated with engaging non-traditional partners.3. Weak institutional capacity, including the lack of technical, managerial, administrative, and policymaking skills as well as of motivation within key ministries hinders development impact from Bank investments, but cannot be adequately addressed through emergency operations.
P113222 | Niger : Emergency Food Security Support Project | Western and Central Africa | Niger | IDA | Non-FCS | Sustainable Development | Agriculture and Food | SPF | IPF | 2009 | 2010 | 2011 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/801411474899589124/text/000020051-20140624164257.txt | http://documents.worldbank.org/curated/en/801411474899589124/pdf/000020051-20140624164257.pdf | In order to succeed, emergency operations need to be simple in design, and must address the short-term priorities of government and beneficiaries. Simplicity of design does not preclude development of a solid results framework with practical indicators and supporting baseline and target values. Emergency operations must do due diligence to avoid undermining governance: in this case, the scope offered by fertilizer procurement for corrupt dealings was headed off by including a joint government-donor committee (CRC) and representatives of farmer cooperatives at critical steps in the process.Bank-sponsored analytical work, prepared before the operation or in parallel to, has an invaluable role to play in facilitating decisions about which project and program design options are most likely to be viable.The Global Food Crisis Response Program has demonstrated that the Bank can respond swiftly and effectively to emergencies of this nature, and in a manner that is congruent with the long-term development needs of the country concerned.
P113235 | Economic Reform Support Grant III (DPL) | Eastern and Southern Africa | Burundi | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2011 | 2012 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/652431475098487535/text/000020051-20140624211939.txt | http://documents.worldbank.org/curated/en/652431475098487535/pdf/000020051-20140624211939.pdf | The ICR draws several important lessons from the experience of the ERSGs. Most noteworthy are: 1. The program did not focus on â€œoutcomesâ€, but rather â€œactivitiesâ€ and â€œoutputsâ€. Hence, future operations need to be â€œresults-orientedâ€.2. The program also did not focus sufficiently enough on monitoring and evaluation and, hence, there needs to be greater focus on M fraud and abuse of government funds; and voice and accountability.
P113241 | Sixth Poverty Reduction Support Grant | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2011 | 2019 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/899921541176155707/text/129569-PPAR-P104990-P106083-P113241-P117495-PUBLIC.txt | http://documents.worldbank.org/curated/en/899921541176155707/pdf/129569-PPAR-P104990-P106083-P113241-P117495-PUBLIC.pdf | 6. Lessons 6.1 The following lessons emerge from the design and implementation experience of the PRSF 4â€“7 series\. â€¢ Programmatic DPF can be an effective form of support for a well-defined, country-owned reform program. In Rwanda, the PRSF 4â€“7 series backed a wellarticulated and sound development strategy with strong implementation arrangements, the 2008â€“12 EDPRS. Arguably, however, value-added of the series stemmed more from the predictable financing that it provided for the overall program and its encouragement to reforms through regular, institutionalized monitoring of progress, than from advancing the achievement of specific objectives and outcomes. â€¢ It is difficult to be definitive about the efficacy of a DPF series unless the results framework is tight-knit, the reforms supported have the requisite depth, and there is a strong and direct causal link between these reforms and the outcomes sought. Under the PRSF 4â€“7 series, progress was made in several cases toward the objectives and desired outcomes. However, the role of the policy actions that the series supported in bringing about that progress versus other contributory factors was not always clear. â€¢ A commitment to providing regular, predictable financing in the form of (multisector) general budget support operations implies that the World Bank needs to be prepared to accommodate dilution or deferral of reform content relative to what is foreseen at the outset. This underscores the importance of entering into such a commitment only in instances in which the World Bank has confidence in the government's long-term intent to see reforms through in good faith despite delays and temporary reversals rooted in technical or political economy factors. In Rwanda, there were several delays and setbacks; for example, the implementation of a revised tariff structure for electricity was continually deferred and diluted. However, all triggers specified in the operations under the PRSF 4â€“7 series (or their equivalent in terms of the substance of the policy actions) were eventually achieved, though in some cases with several years' delay, suggesting that the World Bank's confidence was well placed. â€¢ The World Bank can face a hard choice between adhering to a CPAF in a multisector budget support series and fulfilling the good-practice prescriptions in its operational policy for DPF. In Rwanda, confining prior actions and outcome indicators in the PRSF 4â€“7 series to those found in the CPAF offered clear advantages, such as institutionalized M&E and lower transactions costs, particularly for country authorities. However, CPAF design shortfalls and selectivity in its coverage spilled over into the series, leading to inconsistencies with good practices prescribed under the World Bank's operational policy for DPF. It was often difficult in the PRSF 4â€“7 series to trace the causal links between prior actions (many of which lacked depth) and outcomes sought. Moreover, certain objectives the series sought originally, such as fiscal decentralization, were pursued later through insufficiently focused measures and outcome indicators that were constrained to align with those in the CPAF. â€¢ Successful deployment of an IFMIS can be facilitated by high-level commitment and performance monitoring, sustained external support, and system ownership. In Rwanda, top-level attention to imihigo (performance contract) monitoring included a focus on successive phases of IFMIS rollout, which also received steady technical and financial support from the World Bank (through parallel DPF and investment project financing, and later Performance for Results financing) and from other partners (notably through a Public Financial Management Basket Fund supported by the European Union and the U.K. Department for International Development). In addition, Rwandan authorities believed that the IFMIS's in-house development gave the system's users a greater stake in its successful deployment. 1The World Bank later prepared an analysis of why the reduction in poverty during this period was limited. See World Bank 2013a. 2The precise estimates of poverty, and especially their comparability over time, have been a source of contention in the past. However, the figures cited here have been widely referenced in World Bank operational documents and are taken to be good enough. 3Rwanda's fiscal year was changed in July 2009 from calendar year to July to June to align with East African Community norms. 4There is, in fact, some ambiguity as to whether Poverty Reduction Support Grant 5 or PRSG-6 was the first operation to be aligned entirely with the Common Performance Assessment Framework. PRSG-5 was sometimes labeled a transition operation from the standpoint of being aligned with the Common Performance Assessment Framework (see, for instance, annex 2 of the program document for Poverty Reduction Support Financing 7 (World Bank 2011), but elsewhere (for example, paragraph 53 of the program document for PRSF-7), it was asserted, The PRSG-5 operation was the first operation that aligned the series with the . 5This Project Performance Assessment Report uses the term policy actions to refer to the entirety of measures recorded in the policy matrix and results framework as implemented before the approval of a given operation. By contrast, the term prior actions refers to the subset of measures (usually depicted in bold type in the policy matrix and results framework) that was formally identified as necessary for the approval of the operation. 6 The limitations of an ex post logical framework where objectives evolved over the four-year lifespan of the series can be illustrated with reference to prior action (i) under the program development objective of enhancing the skills of the population. At first, it is unclear how an assessment of the basic education system contributes to the intermediate objective of revamping the strategic and institutional framework for postâ€“basic education, although it arguably speaks to the ultimate objective of enhancing the skills of the population. The answer is that the initial focus in PRSG-4 had been on reducing the pupil-teacher ratio in the nine-year basic education program, but it shifted (exclusively) to postâ€“basic education from PRSG-5 onward. 7 The concept of (structural) depth was originally developed and used in IMF (2007). 8The SMART criteria require indicators to be specific to the objectives toward which progress was to be measured; measurable; achievable; relevant in the sense of appropriate to measure progress toward the objectives; and time-bound. 9 The East African Community fiscal year runs from July to June, in contrast to Rwanda's prior fiscal year, which followed the calendar year. Predictable provision of financing for well-performing countries was a key premise of the Poverty Reduction Support variant of programmatic development policy financing. 11The 2011 and 2015 figures are from the Rwanda Ministry of Education's 2015 Education Statistical Yearbook, which reports the transition rate to upper secondary â€”that is, from senior 3 to senior 4 (GoR 2016, 40). (http\.//mineduc.gov.rw/fileadmin/user_upload/Amatangazo/2015%20Education%20Staiatical%20 YearbookF.pdf). 12Some related (more disaggregated) indicators were tracked during the implementation period of the FY11 Skills Development Project, but this was after the PRSF series' closure. 13As indicated previously, the Skills Development Project was implemented after the PRSF series' closure. 14In addition, the National Institute of Statistics of Rwanda's 2015 Integrated Business Enterprise Survey indicates that almost 80 percent of respondents viewed the availability of skilled or technical labor as no problem (and another 13 percent viewed it as a minor problem). 15The law governing community-based health insurance is Law No. 62/2007 of December 30, 2007. Submission of the law to Parliament was a PRSG-4 prior action. 16For useful background on the evolution of community-based health insurance in Rwanda, see, for example, Kalisa et al. (2015). 17Details of the performance-based financing system implementation and its results are discussed in Basinga et al. (2010). The paper reports on data produced from a prospective quasiexperimental evaluation design that was nested in the pay-for-performance program rollout and compared facilities in a treatment group with those in a control group that continued to receive input-based financing for a two-year period for prenatal care and child preventive care. The study found that significant increases in the provision of some services, such as in-facility deliveries by pregnant women, were associated with pay-for-performance. The results suggest that financial incentives are significant and have a larger impact for services in which providers have more control, such as prenatal care quality. The study also suggested that for services that depend more on patient behavior, such as the decision to seek prenatal care, the program could consider providing financial incentives directly to the patient rather than the provider. 18See the figures for the percentage of children under age five using insecticide-treated bed nets under World Development Indicators (https\.//data.worldbank.org/data/source/worlddevelopment-indicators). 19In fact, implementation of a revised tariff structure was later envisioned (in PRSF-8, approved in November 2011) as one of the triggers for PRSF-9â€”which, given the demise of general budget support in 2012, never materialized. 20The bulk of the increase in access over the PRSF 4â€“7 series' life span appears to have taken place in 2009. This likely reflected a significant increase in generation capacity in that year. 21The number of households and enterprises with access to electricity increased from 91,332 in 2006 to 159,516 in FY10 (compared with a target of 139,000) and to 308,326 in 2011â€“12 (compared with a target of 270,000). Generation capacity increased from 60 megawatts in 2006 to 84 megawatts in FY10 (compared with a target of 80 megawatts) and to 157 megawatts in FY12 (compared with a target of 130 megawatts). 22A subsistence level of electricity (30 kilowatt-hours per month) would be unaffordable for more than three-quarters of the unelectrified population. In recent years, fiscal transfers to the energy sector have declined from 2.5 percent of gross domestic product in FY14â€“15 to 1.4 percent in FY16â€“17. 24In addition, some of the measures lacked depthâ€”for example, completion of a tariff study and validation by Rwanda Utilities Regulatory Authority and the Ministry of Infrastructure. Others, such as the removal of the import duty and value-added tax on liquefied petroleum gas to promote its use and reduce dependence on charcoal, had no direct relation to the electricity outcomes targeted, although they arguably contributed to improving cost effectiveness (and environment-friendliness) in the broader energy sector. 25These investment project financing operations were the FY05 Urgent Electricity Rehabilitation Project and the FY10 Electricity Access Scale-up and Sectorwide Approach Development Project. 26 Implementation Completion and Results Report, page 66. 27 Implementation Completion and Results Report Review, section 4. 28See NISR (2016). Note that the standard for measuring urban access is 200 meters or less from the source and rural access is 500 meters or less. 29 The target for 2011/12 was later revised downward to 37 percent under PRSF-8. 30 The World Bank was Co-chair of the Rural Sector Working Group at the time. 31The 2011/12 figure is from the Implementation Completion and Results Report Review (efficacy section, objective 3), and was slightly under, but close to, the target for that year (PRSG-6 program document, page 44). 32Lack of prior consultation with development partners and other stakeholders (for example, though the Agriculture and Rural Development Sectoral Working Group) meant that alternative solutions to fraud concerns, such as the use of electronic wallets, could not be debated. 33 See also Implementation Completion and Results Report, page 40. 34 See Implementation Completion and Results Report Review, section 4 (objective 3). 35In particular, there are discrepancies in the land area subject to radical terracing between the National Institute of Statistics of Rwanda's seasonal agricultural surveys and figures reported in Implementation Status and Results Reports for the Transformation of Agriculture Sector Program-for-Results operation. 36 Law no. 40/2008 of August 26, 2008, established the organization of microfinance activities. 37 The 2008 figure is from Kantengwa (2010). The later figures are from AMIR (2015). The 13.9 percent of gross domestic product target for 2012 is from the PRSG-6 program document (table 9, page 41). 39Savings and credit cooperatives now account for an important segment of the microfinance institution sector (AMIR 2015). 40According to the website of the Financial Sector Reform and Strengthening Initiative\. The FIRST initiative is a multidonor grant facility that provides short to medium-term technical assistance to promote sounder, more efficient, and inclusive financial systems. Since its inception in 2002, FIRST has funded over 600 projects in about 120 countries, with commitments over $135 million. For more information, visit the website at https\.//www.firstinitiative.org/. 41Several districtand sector-level officials gave the mission demonstrations of the SmartFMIS' capabilities. 42Despite changes in Public Expenditure and Financial Accountability methodology between the 2007 and 2010 PEFAs and the 2017 PEFA, the constituents of this score are unchanged, so the scores are comparable. 43The latest figure is taken from the Implementation Status and Results Report for the Public Sector Governance Program-for-Results operation. 44The Implementation Completion and Results Report (page 47) provides details concerning the substance of the amendments. For instance, they were designed to bring the provisions of the law in line with (i) the revised mandate of the Rwanda Public Procurement Agency, resulting from the full devolution of the procurement function to the procuring entities; and (ii) the Common Market for Eastern and Southern Africa (free trade area) procurement framework (which Rwanda joined in 2004). 45 Separate independent review panels also operate at the district level. 46The Implementation Completion and Results Report Review for the PRSF 4â€“7 series reported that the share had increased very modestly to 75 percent by 2012, missing the target of 87 percent by the series' end. However, the 2010 Public Expenditure and Financial Accountability appears to contradict this because it affirms that 86.6 percent of all contracts above the threshold were awarded by open competition. This is also more consistent with the 2015 Crown Agents findings (Crown Agents 2015). 47See Crown Agents findings (Crown Agents 2015). Similarly, the Rwanda Public Procurement Agency's Annual Activity Report for 2015â€“16 (dated January 2017) affirms, based on its procurement audits, that more than 88 percent of public procurement by value took the form of open bidding. However, it is notable that the Rwanda Public Procurement Agency's reach does not encompass all aspects of a broader concept of public procurement. For instance, as discussed in the section on electricity, many power purchase agreements that the Rwanda Energy Group entered into with independent power producers were negotiated bilaterally rather than tendered competitively. 48Three aspects were scored under procurement in the 2010 Public Expenditure and Financial Accountabilityâ€”the previous methodology\. evidence on the use of open competition for contract award, extent of justification for use of less competitive procurement methods, and existence and operation of a procurement complaints mechanism. All received an A score, despite the subsequent strengthening of the independent complaints mechanism (assessed according to six distinct criteria under the new methodology followed in the 2017 PEFA). 49For example, citizen report cards for 2014â€“16 show citizens' overall net satisfaction with local government services as increasing from 60 percent in 2014 to 75.9 percent in 2016. Trends for many individual service categories (health, for example) are similar. For more detail, see World Bank 2018b. 50For further details, see the discussion in the Implementation Completion and Results Report for the PRSF 4â€“7 series (World Bank 2012, 49â€“50). 51A 2010 census of public sector workers (including workers at the local government â€”province, district, and sector-level, and in-service delivery units such as educational institutions, hospitals, and health centers) showed that approximately 46 percent of workers had been in their current position less than three years and 62 percent had been in their current position less than five years. However, no subsequent census of public sector workers has been made available that would allow comparisons over time.
P113266 | WAPP APL4 (Phase 1) - Côte d'Ivoire, Sierra Leone, Liberia, and Guinea Power System Re-development | Western and Central Africa | Western and Central Africa |  |  | Infrastructure | Energy & Extractives | IDA | IPF | 2012 | 2023 | 2025 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099110824130539635/text/P113266-13b45553-4ba9-42e4-980f-23dea45c3aa7.txt | https://documents.worldbank.org/curated/en/099110824130539635/pdf/P113266-13b45553-4ba9-42e4-980f-23dea45c3aa7.pdf | This review has drawn three lessons based on the information in the ICR.Insufficient measures to ensure thefinancial viability of regional electricity transmission companies can jeopardize the achievement and sustainability of theoutcomes in increased supply of cheaper and cleaner electricity. Since the transmission line constructed under the projectpassed through four countries, it was decided the four project participating countries would establish a regional transmissioncompany to construct and later operate and maintain the transmission line rather than the national transmission companies. Thisproved to be an appropriate approach in completing the construction and commissioning of the transmission line, but the measureswere insufficient to ensure the financial viability of the regional transmission company. The assumptions used at appraisalregarding the financial viability of the utility did not materialize. A second additional financing could not be processed thatcould have helped the utility to address its short-term financial issues. The project currently yields its expected results inelectricity trade and reduction in cost of electricity generation in Liberia and Sierra Leone, but this depends on the nationalgovernments covering the cost of debt repayment obligations of the regional transmission company. The sustainability of the projectoutcomes is at high risk because of the weak financial viability of the regional utility. The ICR (p.38) states that thefinancing plan needs to consider an initial period where revenues from operations may not fully covercosts.The development impact of mega transmission projects can be increased if such investments arecomplemented by distribution network investments on a timely basis. While the project objectives were to reduce the costof electricity generation in Liberia and Sierra Leone and increase the supply of electricity through the transmission line to bebuilt under the project, the ultimate goal of increased availability of electricity was to increase access to electricity in thesetwo countries with low electrification rates. The project did not finance any distribution network expansion investment, which wasto be implemented by the respective national utilities separately. There were delays in those investments, which resulted in fewerpeople getting access to electricity, and lower electricity demand. Although the transmission line was a transformationalinvestment connecting four countries electricity grid and should be expected to result in higher electrification rates inthe medium and long-term, such development impacts could be achieved earlier if distribution network infrastructure is built intandem with the transmission line investments.Transborder electricity transmission infrastructure investmentsaccompanied by technical assistance to regional power utility can accelerate the technical and eventually commercial integration ofcountries under a regional power pool. The project consisted of two separate subprojects, one investment project for theconstruction of the CLSG transmission line and the establishment of the regional transmission company, and the other technicalassistance project for the synchronization of the West African Power Pool (WAPP) zones. These two projects complemented each otherin achieving the project objectives. The transmission line was a critical investment in connecting four countries to the WAPPsystem through a high voltage transmission capacity, and the technical assistance was critical to allow the flow of electricityunder a synchronized regional electricity system. The technical integration of the national electricity networks under the WAPPsystem was a critical first step towards achieving a regional power market. The technical assistance project also supported thedevelopment of a commercial framework for that purpose.
P113268 | Emergency Agricultural Productivity Support Project | Western and Central Africa | Guinea | IDA | FCS | Sustainable Development | Agriculture and Food | SPF | IPF | 2009 | 2012 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/893001475111737891/text/000020051-20140626104534.txt | http://documents.worldbank.org/curated/en/893001475111737891/pdf/000020051-20140626104534.pdf | The main lessons identified by the ICR with some rewording are as follows:Setting up and implementing an adequate M&E system is a key project requirement. In this case, neither the M&E institutional responsibilities, nor the data collection, consolidation and utilization methods were well thought out or defined. If baseline assessments cannot be made during preparation, then they need to be carried out as early as possible thereafter, and impact evaluations adequately designed and implemented. Capable producer organizations may be a good entry point for a sustainable input distribution mechanism. Where private input distribution systems are ineffective, access to rural finance is limited, and public distribution channels are not robust or transparent, well-organized smallholders can act as an entry point for building a successful, sustainable input distribution system.Strong involvement of producer organizations in project implementation is a key factor for success on the ground. Involvement of the National Confederation of Farmers Organizations of Guinea, including its farmer federations at the regional level and unions at the prefecture level, and village associations in distributing the input packages fostered a sense of ownership at the grassroots level.Sufficiently well-thought-out capacity building is essential for public entities to fully match their capabilities to their responsibilities in project implementation. The National Agency of Agricultural Advisory Services needed capacity building mainly on internal planning and M&E implementation for updating results indicators in a timely way. Also, the operational capacity of research stations and seed multipliers remained weak.
P113273 | LR Smallholder Tree Crop Revitalization Support Project | Western and Central Africa | Liberia | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2012 | 2019 | 2020 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/475051584554087377/text/Liberia-LR-Smallholder-Tree-Crop-Project.txt | http://documents.worldbank.org/curated/en/475051584554087377/pdf/Liberia-LR-Smallholder-Tree-Crop-Project.pdf | The following lessons were provided by the ICR and presented here with some adaptation:1.Projectactivities need to be adequately timed and sequenced in order to yield the greatest possible outcomes. Forexample, in the case of building processing factories and warehouses, it is important to complete these activities early in theproject. If they had been available at the beginning of the project, the benefits from access to the facilities could havecontributed to generating increased income (ICR, para. 81iv).2. Treecrop projects may need longer than fouryears to test results. For example, it takes several years for tree crops to mature, particularly if they were newlyplanted or replanting is involved. As a result, some of the positive or negative outcomes of the project will not be know forseveral more years (ICR, para. 81iv)The following lesson is provided by IEG:3. Atthe design stage, it is important to test assumptions thoroughly and corrective actions mapped out accordingly. Theproject made several assumptions that did not materialize during the implementation of the project. For example, the projectassumed that it could secure long-term credit schemes for the farmers until the new tree crops would mature, which did notmaterialize. Similarly, the project made unrealistic assumptions about in-kind contributions of seeds, fertilizers, andagrochemicals. The inability to meet these assumptions reduced the quality of outcomes and made the achievement of the objectivesmore difficult. To fully test assumptions, the project team needs to have extensive upfront consultations and negotiations withpotential partners and private sector, particularly in FCV contexts (ICR, para 81iii).
P113301 | Economic Governance and Poverty Reduction Credit | Western and Central Africa | Ghana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2011 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/318171474851404174/text/000020051-20140624202542.txt | http://documents.worldbank.org/curated/en/318171474851404174/pdf/000020051-20140624202542.pdf | There are three important lessons:(1) Need for realism in setting targets and objectives, especially taking into account the need for parliamentary approval of measures in a democratic system. Even though some measures can be implemented by decree, Parliamentary approval is desirable for important measures such as a number of measures included in this operation, as it broadens support for the program and improves sustainability. Nevertheless, it entails costs in terms of timing which need to be taken into account. (2) Harmonization is important to reduce costs in terms of time to key government officials and development partners. Especially where an important harmonization framework is in place (as in the case of Ghana), or where the Bank and the Government are seeking to establish such a framework, the Bank and DPs need to ensure that the parameters of an MDBS program are broad enough to allow a rapid response to deteriorating conditions. (3) Public confidence is an important consideration in preparation and implementation of key operations in country assistance strategies such as this DPC. As was the case with this DPC, care should be taken to present to the public the substance of the operation in a convincing way.
P113301 | Economic Governance and Poverty Reduction Credit | Western and Central Africa | Ghana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2016 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory |  | http://documents.worldbank.org/curated/en/642251469189437185/text/106279-PPAR-P127314-P117924-Box396280B-PUBLIC-disclosed-7-21-16-ppar-ghanaecon-0716.txt | http://documents.worldbank.org/curated/en/642251469189437185/pdf/106279-PPAR-P127314-P117924-Box396280B-PUBLIC-disclosed-7-21-16-ppar-ghanaecon-0716.pdf | 6. Lessons 6.1 Ghana again became a substantially indebted country that must direct a substantial share of its revenues to debt servicing, and it did so within a decade after a major debt relief under the Heavily Indebted Poor Countries Debt Initiative. This highlights the importance of prudent macrofiscal management in post-HIPC countries, and emphasizes that the World Bank has to place in its policy lending for helping its clients to preserve borrowing space. 6.2 Adequate macroeconomic management is a critical precondition of budget support (which relates to the previous lesson). The World Bank made the right choice to focus on restoring fiscal discipline as part of risk mitigation for the Economic Governance and Poverty Reduction Credit in 2009. Similarly, its choice not to deploy development policy operations (DPOs) in 2013â€“14 because of the lack of an adequate macroframework was also correct. Ghana's case also shows that the World Bank is not a substitute for the IMF in a challenging context that requires a comprehensive macroeconomic program. In this respect, Ghana is a good example of World Bankâ€“IMF cooperation. 6.3 Ghana's case shows that DPOs deployed in an extremely weak public financial management environment are unlikely to be successful. Ghana experienced a deterioration in resource allocation during 2008â€“12 because of debt-financed expenditure hikes that led to interest payments of about 7 percent of gross domestic product per year, taking precious resources away from pro-poor spending, thus undermining Ghana's overall growth and poverty reduction agenda and the effectiveness of the World Bank's budget support. This emphasizes the importance of the quality of public resource use in both public financial management and public resource allocations, as a pre-condition of budget support success. 6.4 Donor coordination on budget support can be difficult in a challenging environment like that in Ghana in 2008â€“13. Assessment of eligibility for budget support is still a controversial area in relationships between various donors. Despite a move toward performance criteria based on agreed-to actions, various donors may interpret different shocks differently, which will affect donor coordination. Dealing with macro and fiscal mismanagement when macroframework is not formally a part of the performance assessment can be an especially contentious issue. 6.5 Fiscal pressure can crowd out discretionary expenditures, and service delivery sectors are especially vulnerable. The World Bank can use DPF operations to take a crucial role in protecting pro-poor expenditures in such an environment. 6.6 Giving due weight to the underlying factors of fiscal imbalances and addressing them appropriately is crucial. Measures taken to contain the public wage bill and mitigate fragmentation of bank accounts were insufficient to translate into lasting results. 6.7 The World Bank has a crucial role in providing advisory services that are complementary to budget support. A more proactive engagement in estimating the fiscal impact of the single spine salary reform introduction could have helped in designing a phased approach consistent with the long-term budgetary envelope.
P113337 | Iraq: Banking Sector Reform | Middle East and North Africa | Iraq | IBRD | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | RETF | IPF | 2009 | 2013 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/152931475113840552/text/000012394-20150309080010.txt | http://documents.worldbank.org/curated/en/152931475113840552/pdf/000012394-20150309080010.pdf | Lessons from the ICR, adapted by IEG:Bank Group operations in fragile environments need to be underpinned by strong analytical work and draw upon the experience of what has worked and what has not in other fragile country environments.Effective cooperation with other development partners can provide the leveraging necessary to push reforms in difficult work environments.
P113341 | Health Professional Education Quality Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2010 | 2015 | 2016 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/478231468189274167/text/ICRR14786-P113341-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/478231468189274167/pdf/ICRR14786-P113341-Box393191B-PUBLIC.pdf | The ICR (pp. 23-24) provides several lessons, adapted here:Strong collaboration between government and non-government entities is essential for higher education reform processes. In this case, involvement and commitment of professional associations and associations of professional schools was key to the development and ratification of accreditation and examination standards and processes.When providing incentive grants, variation in interest and capacity must be taken into account. In this case, there were significant differences in participation, disbursement, and results among FAP-recipient medical schools because these factors were not adequately considered.A country's legislative environment will strongly govern efforts to introduce new accreditation and examination standards, and legislative approval can be a lengthy and challenging process. Adequate political economy analysis is essential for understanding these processes, and a project's timeline should taken them into account.
P113349 | Health System Improvement Project | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2011 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/295801624992049372/text/Uzbekistan-HEALTH-SYSTEM-IMPROVEMENT-PROJECT.txt | http://documents.worldbank.org/curated/en/295801624992049372/pdf/Uzbekistan-HEALTH-SYSTEM-IMPROVEMENT-PROJECT.pdf | The ICR (pp. 26-27) provided a series of useful lessons, some of which are adapted here:Health reform reliesheavily on government commitment and political processes. In this case, government ownership was critical to supportingreforms through legislative processes,but political reluctance and opposition to more far-reaching hospitalrationalizationconstrained the scope and approach of project design.Close coordination with other technicalagencies can produce important benefits and synergies. In this case, work with the World Health Organization and U.S.Centers for Disease Control and Prevention was central to the development of clinical protocols and national health accountsreports.Continuousandlong-term engagement of the Bank in a specific sector pays off, thoughin this case, it is a work in progress. Engagement through the previous Health I and Health II projects, which supportedcomprehensive reform of primary care and piloted case-based payments for hospitals, both laid the ground work for theinvestments supported by this project and sustained an ongoingdialogue about pathways for engaging in more difficultfinancing and structural reforms in hospital care.
P113350 | Sector Support for Education Reform Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/498341593109304230/text/Kyrgyz-Republic-Sector-Support-for-Education-Reform.txt | http://documents.worldbank.org/curated/en/498341593109304230/pdf/Kyrgyz-Republic-Sector-Support-for-Education-Reform.pdf | The ICR (pp. 30-31) offered lessons and recommendations, including the following lessons, restated byIEG:Projects that are closely aligned with education sector priorities and programs have a greaterlikelihood of advancing further educational improvements and reforms.The project was fully aligned with elements ofthe national strategy, and such alignment reinforced commitment and facilitated implementation and institutionalization of improvedpractices.Institutionalization of new teaching-learning practices is facilitated by propersequencing of project/program activities.Under the project, input provision such as textbooks, teaching-learningmaterial, and digital learning material was well sequenced with the introduction of innovative approaches such as classroomobservation tools and competency-based curricula, concurrently supported by a training and capacity building program.Implementation schedules also ensured that classroom inputs were available for teachers when they completed their training, thusenabling the application of new skills and assessment of training impact.Standardized classroomobservation tools, such as the Classroom Assessment Scoring System, provide an opportunity to holistically measurewhat happens in the classroom and help understand what drives better learning. Under the project, the assessment tool alsohelped in identifying teachers professional development needs, informing in-service teacher training programs, and providingfeedback to teachers to become more effective.Policies granting greater school autonomy arereinforced by added interventions to build capacities at the school level for planning, budgeting, and quality aspects, and toempower local communities and parents to engage with school management, as undertaken by the project.Also,communications and outreach efforts helped stakeholders to be informed and engaged in school affairs, and contributed to generatefurther support from teachers, school administrators, parents and communities.In addition, IEG identifiedthe following lesson:Advancements in education sector reforms can be achieved with minimumfunding.The project focused on influencing sector conditions and practices that foster improved learning outcomes inbasic education, at a relatively small cost of US$15.2 million.
P113370 | eBenin Project | Western and Central Africa | Benin | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2010 | 2015 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/271891483124582888/text/ICRR-Disclosable-P113370-12-30-2016-1483124554986.txt | http://documents.worldbank.org/curated/en/271891483124582888/pdf/ICRR-Disclosable-P113370-12-30-2016-1483124554986.pdf | The ICR draws the following main lessons from implementing this project.(1). Resistance to change can derail anadministration modernization program that embarks in e-Government. The experience with this project demonstratedthat, the change has to happen at every level of the administration organizations. Mitigation measures need to be adequatelyincluded in project design and adequate resources need to be expended in awareness building programs and training.(2)Government transformations from paper-based to digital represents a massive undertaking in terms of time and resources andrequires leadership, governance and skills. The experience with this project showed that placing the leadership ofthe e-Government program in the Ministry in charge of ICT may not be the ideal governance arrangement to insure that changes arespread across the administration. Higher level involvement such as the Prime Minister or President may be more appropriate atthe preliminary stage for any e-Government transformation program.
P113372 | Pakistan Poverty Reduction and Economic Support Operation (PRESO) | South Asia | Pakistan | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2012 | ICRR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/513841474906421518/text/000020051-20140624202406.txt | http://documents.worldbank.org/curated/en/513841474906421518/pdf/000020051-20140624202406.pdf | IEG concurs with the ICR on the need for broad-based stakeholder consultations to underpin challenging policy reforms. IEG also agrees with the importance of addressing capacity and institutional issues as well as sound analytical work to complement and inform policy based lending. However, in IEG's view, the experience with PRESO is not robust enough for delineating appropriate contexts for the use of stand-alone DPOs.
P113374 | Benin: Emergency Food Security Support Project | Western and Central Africa | Benin | IDA | Non-FCS | Sustainable Development | Agriculture and Food | SPF | IPF | 2009 | 2011 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/362591475111657930/text/000020051-20140625073233.txt | http://documents.worldbank.org/curated/en/362591475111657930/pdf/000020051-20140625073233.pdf | The main lesson identified by the ICR with some rewording is as follows:Project implementation plans should consider the fact that major procurement of goods takes time. Thus emergency projects, rather than trying to change the procurement procedures, could consider differing implementation arrangements to enable quick realignment with actual inputs. In this project, it took 6 months to procure fertilizer through international competitive bidding, although only 3 months was envisaged. The project responded by revising the target area to suit the agricultural season. IEG also finds that: For emergency projects, objectives need to be time bound and simple. In this case there was a disconnect between the stated objectives and the project design, because the objectives included medium to long-term goals of expanding farmers' access to inputs that could not to be achieved under this project.
P113402 | Sri Lanka - Higher Education for the Twenty First Century Project | South Asia | Sri Lanka | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2010 | 2016 | 2017 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/585331498838674928/text/ICRR-Disclosable-P113402-06-30-2017-1498841632328.txt | http://documents.worldbank.org/curated/en/585331498838674928/pdf/ICRR-Disclosable-P113402-06-30-2017-1498841632328.pdf | The ICR mentions, and the ICRR endorses, the lessons below,which are based on clear information and evidence in theICR. They are paraphrased from the ICR (pg. 19). It is efficient to apply the principle of subsidiarity to adecentralized system such as a university network, as it leads to smooth implementation Multiple rounds of competitivegrants afford the opportunity to learn from the grant-making process, improve the competitive process, and identifyresults A full set of reforms needs to be considered for outcomes that depend on multiple systems. In the case ofthe current project, commercialization of research projects was not achieved by universities because of the lack of requiredprocedures and legislation.
P113415 | Emergency Infrastructure Rehabilitation and Energy Project | Western and Central Africa | Togo | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2009 | 2016 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/794361496929872793/text/ICRR-Disclosable-P113415-06-08-2017-1496929863717.txt | http://documents.worldbank.org/curated/en/794361496929872793/pdf/ICRR-Disclosable-P113415-06-08-2017-1496929863717.pdf | The ICR (p. 21-23) provides several useful lessons learned: If there is weak capacity to ensure theprojects compliance with safeguards, fiduciary policies and project management, it is critical that training to strengthencapacity is being provided at the beginning of the project implementation. This project faced safeguard issues until April 2012 dueto the lack of training of the responsible staff, resulting in non-compliance with the Banks Resettlement Action Plans andEnvironmental Management Plans. In order to ensure the sustainability of a project, strengthening operation andmaintenance arrangements, coordinating with other development partners and including beneficiaries in the process iscritical. Integrating GEF-funded activities into an IDA project brings higher visibility to the energy efficiency agenda.However, it is important that the scope of activities is feasible. In this project, a test laboratory was developed, however, thedecree to start the operation of the laboratory has not been signed yet.
P113416 | Egypt - Wind Power Development Project | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2010 | 2019 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/980101612480030748/text/Egypt-Arab-Republic-of-EG-Wind-Power-Development.txt | http://documents.worldbank.org/curated/en/980101612480030748/pdf/Egypt-Arab-Republic-of-EG-Wind-Power-Development.pdf | This review has drawn three lessons incorporating material from the lessons listed on page 21 of theICR.Overestimated project costs can lead to large amount of savings that can adversely affect the overall projectimplementation and project efficiency. Because of the lower actual cost of the 280 km double circuit transmission linethan the cost estimated at appraisal, US$106 million was saved. To utilize these savings, additional transmission activities wereadded to the project, but the project implementation agency, i.e., EETC, financed parts of these additional activities through itsown funds. Later, the EETC could not identify new activities to be funded by these savings. The project team suggested directcontracting method to utilize the funds before project closing and also informed the EETC that early cancellation of funds wouldhave been considered (ISR 17, p.4). At project closure, US$37.9 million of the loans (IBRD, US$12.2 million; CTF, 25.7million) hadto be cancelled without fully achieving the expected outputs from the additional transmission investment activities. Theoverestimation of project costs has been a recurring issue in similar energy projects in Egypt.Ambitious projectdevelopment schedules that seek to involve the private sector on a new model, such as build-operate-and-own (BOO), can put theachievement of the project objective at risk. The project had a very ambitious schedule for the development of the first250MW wind power plant project by a private investor on the BOO model; it was expected that the first power plant would startcommercial operation within three years. The financial close of the remaining 2,250MW capacity was expected within five years ofproject implementation. Such investments require longer time for detailed technical, contractual and commercial assessments toachieve bankability for project financing. The political events between 2011 and 2014 had an adverse impact on the development ofthese wind power projects, but even without this force majeure, the project schedule was very ambitious. The financial close of thefirst wind power investment was achieved during project implementation, but the start of the commercial operation of the powerplant was delayed beyond project closing.Absence of a dedicated project team can result in poor project managementif the project implementation entity does not have sufficient project implementation capacity. The project implementationunit (PIU) within the EETC did not have adequate and experienced staff. The turnover of the heads of the PIU was frequent. Someproject activities were undertaken by departments not reporting to the PIU. These led to poor project management that manifesteditself in delays in the preparation of bidding documents and ineffective contract supervision. The Banks projectteams efforts to remedy the situation was partially successful. As a result, some project activities to be financed by thesavings could not be completed before project closing.
P113421 | Afghanistan Pension Administration and Safety Net Project | South Asia | Afghanistan | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2010 | 2018 | 2019 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/945631545142612751/text/Afghanistan-AF-Pension-Admin-and-Safety-Net.txt | http://documents.worldbank.org/curated/en/945631545142612751/pdf/Afghanistan-AF-Pension-Admin-and-Safety-Net.pdf | The ICR (pp. 23-24) offered several lessons, including:Government ownership andcommitment is key to implementation of reforms in challenging political and security environments. In this case,implementation of the pension component covering survivors of martyrs and disabled persons suffered because of the limitedinvolvement and leadership of relevant government entities.Third-party arrangements canbridge capacity gaps and facilitate effective implementation. In this case, the delivery of cash through mobilebanking services in provinces where conventional banking services were not available was central to implementation of safety netactivities.
P113435 | Bangladesh - Primary Education Development Program III | South Asia | Bangladesh | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2012 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/938091545534548536/text/Bangladesh-BD-Primary-Education-Dev-Program-III.txt | http://documents.worldbank.org/curated/en/938091545534548536/pdf/Bangladesh-BD-Primary-Education-Dev-Program-III.pdf | The followinglessons are taken from the ICR, with some modification of language: Communitymobilization efforts encouraging bottom-up citizens engagement are important for advancing education reforms. Aneffective communication strategy is an essential approach for ensuring the understanding and eventual buy-in of school stakeholdersabout the need, importance, and benefits of quality of education, and thus of the measures carried out to improve schooleffectiveness and increase learning outcomes. The school management committees and the wide stakeholder consultation processesestablished under PEDP3 are prominent ways of engaging citizens/civil society. Lack of attention tolearning outcome results may jeopardize an education programs development outcomes. Without an enhanced focus onensuring foundational numeracy and literacy, especially in the first 3 grades of primary education, as an essential requirement inthe ongoing education reform in Bangladesh, necessary improvements in learning outcomes might be jeopardized. Despite theremarkable progress made by Bangladesh in increasing access to pre-primary and primary education, and improving the primary cyclecompletion rate, the NSA results show that learning outcomes are alarmingly low and have been declining throughout the programperiod. Low and uneven learning outcomes, especially in math and Bangla in the first three grades of primary education, continue tobe a key issue of concern. Improving school quality is a gradual and holistic process and a very lengthy endeavor contingent upon anumber of additional interventions that need to strongly, timely, and effectively articulate and synergize at the classroomlevel, for example: (i) ensuring that teachers are able to teach effectively under the new revised curriculum and articulate thelearning inputs provided by PEDP3; (ii) ensuring the adequacy of teacher-student contact hours in the classroom; (iii) carrying outperiodic, systematic, random on-site monitoring to assess how the different learning-related interventions are being implemented inthe classroom and, if warranted, to develop and implement appropriate remedial and preventive measures; and (iv) using findings ofthe various learning assessments (NSA, PECE, etc.) to design and implement appropriate preventive and corrective measures. TheQ-LEAP design rightly focuses on improving education quality, as measured by learning outcomes in language and mathematics,especially in the first three grades of primary education. A comprehensive intervention like PEDP3requires more effective horizontal articulation among its key activities and timely vertical coordination across all theimplementing entities at all levels of decision-making. The key interventions/subcomponents of PEDP3 contributing to thePDO performed well on their own. But there was little interaction and feedback across these interventions, limiting theirsynergetic impact on teaching-learning practices, teacher training, and improving learningoutcomes. Capacity building is critical for successful program implementation. Advancing andsustaining ongoing education reforms will require strengthened horizontal and vertical institutional linkages among key actors andgreater clarification of their roles, responsibilities, and accountability mechanisms. When limited institutional capacity isdetected for implementing sound interventions, it is important to prepare an appropriate institutional capacity developmenttime-bound action plan at the very beginning and ensure that that it is implemented in an effective and timely fashion.
P113438 | BI - Food Crisis Response Development Policy Grant | Eastern and Southern Africa | Burundi | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | SPF | DPF | 2009 | 2010 | 2011 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/957161474659790905/text/000020051-20140620082243.txt | http://documents.worldbank.org/curated/en/957161474659790905/pdf/000020051-20140620082243.pdf | In responding to shocks, like the global food price crisis of 2008, it is important to make the most of "stroke of the pen" reforms (e.g. changes in import duties) that can be implemented rapidly and have immediate impact. New spending programs are also important but will take longer to implement and may pose coordination problems. As in the case of this operation in Burundi, the response package needs to contain an appropriate mix of actions with immediate and less immediate effect.Grant operations of this type can have a bigger impact if they are not isolated interventions but (as in the Burundi case) form part of a broader program of budget support that is pursuing compatible objectives.There is a need for donors to be flexible and timely (avoiding the temptation to micro-manage the various components of government response to the crisis); but this should not result in a looseness in specifying the division of responsibilities (which agency will do what). In this project, a memorandum of understanding specifying the respective obligations of the government and the WFP might have helped resolve some of the implementation problems faced by the school feeding program.
P113438 | BI - Food Crisis Response Development Policy Grant | Eastern and Southern Africa | Burundi | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | SPF | DPF | 2009 | 2010 | 2012 | PPAR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/396661468016845407/text/674710PPAR0P110C0disclosed070250120.txt | http://documents.worldbank.org/curated/en/396661468016845407/pdf/674710PPAR0P110C0disclosed070250120.pdf | 6. Lessons 6.1 The choice of instruments and policy measures for an emergency food crisis intervention needs to take into account the local causes of poverty and hunger. In the case of the Burundi food crisis operation, recent sector work emphasized the centrality of long-run constraints to agricultural productivity to these problems, while the analysis in the Program Document gave the impression that the main problem for Burundi was short-term in natureâ€” caused by the 2007-08 spikes in world commodity prices. This was presumably a necessary expedient to justify application to the Global Food Crisis Response Fund. The Program Document further created the false impression that the tax exemption program would necessarily enhance food consumption by the poor and vulnerable. There was enough available evidence at the time of grant preparation to demonstrate that the root cause of food insecurity in Burundi lay in the lack of investment in agriculture following the civil war, and the overall poverty trap resulting from failure to attain the levels of growth achieved in other post-crisis countries. 6.2 For budget support as for other operations, it is difficult to assess results in the absence of a clear framework setting out links between policy actions, outputs, and outcomes and of baseline measures of the outcomes against which progress can be measured. The food crisis grant operation for Burundi did not clearly specify the links between the various actions that were supported and the outcomes underpinning project objectives. There was a lack of agreement between the main text of the Program Document and the Actions Matrix in terms of the number of objectives, and there was no indication of what actions would be taken in support of the objectives of preventing an increase in social unrest and enhancing fiscal stability. 6.3 Scaling up of safety nets is a common strategy in an emergency situation, but expanding a program to new areas may take time. In the case of Burundi, not all schools had the necessary infrastructure to support the feeding program, and local management had to be put in place in the new areas. There were significant delays due to funding arrangements. Together, this resulted in a 7-month delay in expanding the school feeding program to vulnerable provinces.
P113441 | Nepal: School Sector Reform Program | South Asia | Nepal | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2010 | 2020 | 2017 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/787851498846023332/text/ICRR-Disclosable-P113441-06-30-2017-1498846012061.txt | http://documents.worldbank.org/curated/en/787851498846023332/pdf/ICRR-Disclosable-P113441-06-30-2017-1498846012061.pdf | The ICR (p. 30-31) included several lessons that IEG synthesizes as follows: Decentralization in the educationsector can be beneficial for dividing responsibilities actors on all different levels, but accountability of roles andresponsibilities needs to be clearly defined. In this project, the Ministry of Education was responsible for decision making whilethe district authorities implemented those decisions, and the local communities delivered front line services, allowing forincluding all different actors critical for achieving the development objectives. However, a compliance system was lacking,and there were accountability gaps. Collaboration between all development partnerscan lead tomoreefficient and effective preparation and implementation. In this project, all development partners agreed on a singleappraisal document, including a joint economic and financial analysis. Also, when a development partner provided sometechnical assistance, it benefited the collective preparation process. This allowed for a more coherent approach and reduced theburden on the Ministry of Education.
P113450 | LR - Reengagement and Reform Support Program 2 | Western and Central Africa | Liberia | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2011 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/463961474665244233/text/000020051-20140624195711.txt | http://documents.worldbank.org/curated/en/463961474665244233/pdf/000020051-20140624195711.pdf | The ICR contains good lessons, the major ones of which can be summarized as follows. Even in a post-conflict country, with limited implementation capacity, a reform program can be successful if (1) there is genuine and strong government commitment; (2) the program is designed to be politically feasible; and (3) the program is supported by technical assistance to make up for local capacity shortcomings.
P113451 | Mali: Poverty Reduction Support Credit 3 | Western and Central Africa | Mali | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2013 | ICRR | >=50 million & <100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/525111474567084998/text/000020051-20140625225506.txt | http://documents.worldbank.org/curated/en/525111474567084998/pdf/000020051-20140625225506.pdf | The ICR provides some important lessons, several of which are adapted here:1. Development policy operations that do not carefully reflect on the experiences of similar previous initiatives can easily fall into the trap of repeating earlier mistakes. Despite the discontinuation of the previous PRSC series in Mali (which was ultimately assessed unsatisfactory), the Bank immediately recommenced with a new series, before a self-evaluation of the experience could be completed and before the Bank and Government could formally review the reasons for poor performance. Yet the new program sought many of the same policy changes, even though the underlying political environment had not evolved. This diminishes the Bank's credibility in encouraging important reforms, as PRSC support can be seen as guaranteed irrespective of the results.2. Technical assistance is critical to help a low capacity administration implement a complex reform program. In Mali, the technical assistance project that was intended to be implemented in parallel with the PRSC was significantly delayed, only becoming operational in August 2011, at the end of the series. This delay hampered the program, in this case with regard to improving capacity to deliver decentralized services. Programs that are intended to be complementary with other Bank activities--technical assistance, analytical and advisory services, investment lending, etc.--should be adjusted as the timeline for delivery of those products changes.3. The selection of indicators appropriately matched to program objectives, with ambitious but realistic targets, signals the importance the Bank places on development outcomes. For PRSCs 3-5 in Mali, many indicators were dropped mid-course, replaced, or altogether ignored, a symptom of lack of realism. More than a few were focused on inputs and processes. Baselines were highly unreliable. It is thus not surprising that the Government did not take seriously its responsibility to monitor results.In addition, IEG offers the following lesson:4. Stretch reforms in areas with strong entrenched interests or that are politically sensitive require deeper commitment than typical reforms, and should be limited in number for a given operation or series. In Mali, these included introducing private participation into the cotton sector, creating a mechanism to increase electricity tariffs in line with costs, and reducing the focus on incentives in investment promotion. Each of these reforms was delayed considerably and ultimately failed. Given the obvious challenges in implementing each of these reforms as evidenced by past efforts, an approach that focuses the Government's energy and political capital on one key issue head on, while laying the groundwork and building consensus for the others, may be more effective.
P113456 | Togo: Economic Recovery and Gov. Grant 2 | Western and Central Africa | Togo | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2011 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/669111474570018561/text/000020051-20140624183919.txt | http://documents.worldbank.org/curated/en/669111474570018561/pdf/000020051-20140624183919.pdf | As often happens, implementation of this operation was stronger in those areas (public financial management, financial sector) that are under the direct control of the borrower (i.e, the government) than in those (phosphates, cotton, energy) that depend on other government agencies.Good performance on reform objectives (e.g., public financial management) does not guarantee success in achieving higher order objectives, particularly if the operation's design fails to properly consider the links of the former to the latter.As a corollary, failure to include this link in the M & E design may weaken awareness of those links and impede adequate information/analysis needed to correct policies. By way of example, establishing the links of reforms in the key productive sectors to higher order outcomes (investment) and monitoring investment in those sectors might have enriched the dialogue on the reforms and perhaps help achieve stronger progress in those areas. Nevertheless, this operation provides an example of well thought-through reform outcome indicators that facilitated the monitoring and assessment of its reform objectives.
P113457 | Paraguay Public Sector Reform | Latin America and Caribbean | Paraguay | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2009 | 2011 | 2012 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/884061475082278600/text/000020051-20140625070938.txt | http://documents.worldbank.org/curated/en/884061475082278600/pdf/000020051-20140625070938.pdf | Lessons in the ICR are all supported. Political space for difficult reforms can arise from the election of a new, reform-minded government, by urgency stemming from a financial crisis, and by drawing on the support of like-minded coalitions of politicians, key officials, NGOs, international financial institutions, and other stakeholders. Another crucial lesson is the importance of a mutually reinforcing package of properly sequenced analytical work, technical assistance, and parallel assistance from other donors to help governments to use DPLs productively. As part of such a mutually reinforcing package, the value added of the DPL can be to elevate the policy dialog, to support a programmatic frame with targets, medium term outcomes and monitoring requirement for policy planning cycle, and to facilitate congressional support to pass needed laws, decrees and approvals. On the other hand, falling short of the targets can put the borrower over the time limit for continuing the planned follow-on operations of a DPL series.
P113468 | Guinea Bissau--Food Price Crisis Response Program | Western and Central Africa | Guinea-Bissau | IDA | FCS | Sustainable Development | Agriculture and Food | SPF | IPF | 2009 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/345671467986262492/text/ICRR14658-P113468-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/345671467986262492/pdf/ICRR14658-P113468-Box393183B-PUBLIC.pdf | The ICR offers a number of lessons of which the following are the most important (with some reformulation of language):Capacity constraints in fragile countries must be properly mitigated during design and implementation. The project experience showed that Bank teams shouldn't assume that the recipient is familiar with Bank methods and procedures, including accounting, procurement and M (ii) intense Bank supervision and â€œhandholdingâ€ following effectiveness, including on-the-ground procurement and M and (iii) a rapid baseline survey or equivalent information gathering to ensure appropriate targeting and M&E. Community participation and the involvement of national NGOs enhances the sustainability of impacts. According to the ICR, one result of strong community contributions to the design and implementation of micro-projects was that equipment distributed by the project has been relatively well maintained at project closing. Involvement of NGOs in providing technical assistance and on the job training to producer groups increased the likelihood of continued capacity building and guarantees that new development management skills stay in the communities that need them most.The scale of an operation such as this should be consistent with the objectives. The resources available seem to have been too limited to have a major impact on food security.
P113488 | Sri Lanka - Transforming the School Education System as the Foundation of a Knowledge Hub | South Asia | Sri Lanka | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2012 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/227591558382762017/text/Sri-Lanka-LK-Transforming-School-Education.txt | http://documents.worldbank.org/curated/en/227591558382762017/pdf/Sri-Lanka-LK-Transforming-School-Education.pdf | The ICR (p. 27) provideduseful lessons, some of which are adapted here byIEG: Implementing a communication strategythat clearly describes objectives,roles, and responsibilities is critical for ensuring the success of a large reform program. This project did nothave a communication strategy, and at the beginning of implementation coordination between departments in the MoE and partnershipsbetween the MoE and provinces were weak. Coordination improved mainly because the directors of the relevant MoE branches made aneffort to do so. Building capacity at all implementation levels is criticalto successful projectimplementation. In this project, capacity was continuously built at the central ministry and the provinciallevel. However, inadequate staffing and capacity constraints, especially at the provincial, zonal, and school levels, led toimplementation challenges such as those noted in the Mid-Term Review (see Section 5 for more details). Continuous capacity buildingefforts at lower implementation levels would have been beneficial. Project designs that are flexible to adapt tochanging circumstances can be beneficial. The project was embedded in the governments five-year national educationsector strategywhich was updated on a yearly basis based on changing circumstances. The Bank team stated thattheupdated strategywas usefulin providinga coherent overarching framework for implementation.
P113492 | Philippines GFRP DPO | East Asia and Pacific | Philippines | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2009 | 2011 | 2013 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/142961474587945830/text/000020051-20140625070454.txt | http://documents.worldbank.org/curated/en/142961474587945830/pdf/000020051-20140625070454.pdf | The following lessons may be drawn from the preparation and implementation of this operation:The chances of a successful outcome of a DPO are considerably enhanced by both technically sound pre-existing and ongoing analytical work and by extensive and long-standing policy dialogue over the areas of reform to be addressed. Under such circumstances, there is also an enhanced possibility that the DPO itself will further policy dialogue even in difficult and politically complex areas such as that of rice trade and subsidy policy in the Philippines.The goals of a single DPO, and the prior actions selected to achieve them, need to be realistic in terms of what can be achieved in a short time frame. This operation was carefully designed in this respect and avoided trying to address more complex long term issues which would likely have made it impossible to address the food and related social assistance emergencies in a timely manner.SILs and TALs ongoing or under preparation in the policy areas covered by the DPO can provide important synergies. In this case, the DPO capitalized on the dialogue underpinning the preparation of the SWDRP, and succeeded in broadening the dialogue beyond the implementing agency of that project. Through the SIL, the Bank was also able to track progress of the program supported by the DPO and avoid the need for a separate M&E system.There are also potential synergies between reforms in one sector and those in another. In this case, these were achieved by combining policy actions in both the agricultural and social protection sectors. The DPO was thus able to deepen and extend policy dialogue in both areas.
P113493 | Second Northern Mountains Poverty Reduction Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2010 | 2018 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/460571585343013375/text/Vietnam-VN-2nd-Northern-Mountains-Poverty-Redctn.txt | http://documents.worldbank.org/curated/en/460571585343013375/pdf/Vietnam-VN-2nd-Northern-Mountains-Poverty-Redctn.pdf | The following lessons were extracted from the ICR: Infrastructure projects need to be of thehighest quality in order to have sustainable impact on the lives of the beneficiary. For example, while the project wasable to implement infrastructure across several districts, about 35% of interviewed households considered the status of theinfrastructure worse than before the project began (ICR, para. 80). Infrastructure projects were reported as below standards due toinappropriate designs, low quality construction, and poor supervision (ICR, para. 80). The project needed additional mechanisms toensure quality, safety, functionality and compliance with environmental standards (ICR, para. 80). One-off trainings are insufficient to improve agricultural productivity. For example,it is known that in order for farmers to increase their livelihood activities, it takes several production cycles. The projectdesign emphasized practical and hands-on training, however not a lot of farmers completed trainings for multiple production cycles(ICR, para. 81). The project design also did not consider how best to provide continuous technical advisory services to the farmersupon completion of the project (ICR, para. 81). Local governments are better prepared fordecentralization efforts if they receive adequate and relevant institutional capacity. For example, theproject contributed towards building capacity at the district and provincial levels (ICR, para. 82). This work supported andprepared local government for the time when the Vietnam government will implement its full decentralization agenda (ICR, para.82).
P113506 | Emergency Demobilization and Transitional Reintegration Project | Eastern and Southern Africa | Burundi | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2009 | 2014 | 2015 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/790431468184740595/text/ICRR14666-P084022-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/790431468184740595/pdf/ICRR14666-P084022-Box393183B-PUBLIC.pdf | Three of the ICR lessons have been selected and slightly modified by IEG:D and (ii) define an operational framework with clearly defined risk mitigation measures to address the issue starting with demobilization camps, and throughout reinsertion to ensure that ex-combatants receiving reintegration support.DDR projects providing medical and mental health support should be designed based on a thorough assessment of in-country capacity. Under this project, a clearer identification of the risks associated with limited in-country capacity for provision of medical and mental health support would have allowed: (i) designing adequate mitigation measures from the onset, including a capacity building plan, to use the project as an opportunity to strengthen national medical and mental health services; and (ii) ensuring that some limited in-country services (prosthetics) were not temporarily overwhelmed by demand from project beneficiaries, at the detriment of the general population.Small implementation structure with activities outsourced to local organizations can reduce risks of political interference and help mitigate limited institutional capacity. The implementation framework used in the subject project could be used in situations where there are high risks of political interference in the D&R process. This project ensured that technical activities were implemented by technical agencies competitively recruited and somewhat sheltered from direct political interference.
P113540 | AIDS-SUS (National AIDS Program - National Health Service) | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2010 | 2016 | 2017 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/970751481130548799/text/ICRR-Disclosable-P113540-12-07-2016-1481131445763.txt | http://documents.worldbank.org/curated/en/970751481130548799/pdf/ICRR-Disclosable-P113540-12-07-2016-1481131445763.pdf | The ICR (pp. 35-36) includes several valuable and insightful lessons, including:1. Inclusion of too manyindicators poses an untenable burden on an implementing agency, especially in a results-based financing environment. In thiscase, achievement of objectives was hindered from the start by an unwieldy results framework that overtaxed the capacity of weakME systems and did not completely and adequately measure progress toward intended outcomes.2.Decentralization will stall without proper attention to local institutional capacity and appropriate governance mechanisms andincentives. In this case, weak capacity of the decentralized units impacted implementation of planned activities andachievement of intended outcomes. Training should focus not only on technical capacity building, but also financial,procurement, management, and ME modules, and where appropriate, staff turnover should beanticipated.3. HIV/AIDS is a constantly evolving epidemic, and addressing it adequately requiresappropriate investment in surveillance as well as prevention, treatment, and care. In this project, planned analytic studiesto identify at-risk groups were not conducted in a timely manner, preventing flexible deployment of resources that could have ledto greater achievement of objectives.
P113542 | Kenya Informal Settlements Improvement Project (KISIP) | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2020 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/757601607626374850/text/Kenya-KE-Informal-Settlements-Improvement-Proj.txt | http://documents.worldbank.org/curated/en/757601607626374850/pdf/Kenya-KE-Informal-Settlements-Improvement-Proj.pdf | The ICR draws the following three main lessons from the experience of implementing this project, with some adaptation oflanguage.1. Design for informal settlements projectsneeds to be flexible for accommodating the tenureregularization process. In this project, manyinformal resettlements did not allow the project interventionstoconform toconventional planning standards without displacement. Flexible standards had to be adopted to minimizedisplacement.Such flexibility should be captured in the countrys planning instruments, such as establishing SpecialPlanning Area (SPA) which allow for flexible standards.2. Planning for post-construction maintenanceofinfrastructure needs to be addressed prior tointerventions. In this project, provisions for adequatemaintenance of infrastructure wereidentified as an ongoing issue during supervision. The lesson is that discussions on thecost of operating and maintaining infrastructure and services need to take place during project preparation, in order to establishclear institutional arrangements for operation and maintenance of the rehabilitated infrastructure assets.3. Arealistic time frame is required that is line with the scope of project activities.Infrastructure investments inthis project could only commence after community engagement. The original time frame was unrealistic, given the time requiredforcommencing infrastructure activities based on community participation.
P113586 | Southern Sudan Emergency Food Crisis Response Project | Eastern and Southern Africa | South Sudan | IDA | FCS | Sustainable Development | Agriculture and Food | SPF | IPF | 2009 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/499491561587761452/text/South-Sudan-S-Sudan-Emerg-Food-Crisis-Res-P.txt | http://documents.worldbank.org/curated/en/499491561587761452/pdf/South-Sudan-S-Sudan-Emerg-Food-Crisis-Res-P.pdf | The ICR contained an excellent set of lessons. The following three lessons were chosen from those in the ICR with someamendments in language.1. In fragile and conflict environments considerimplementing the project with reputable NGOs that are familiar with the context. For example, in this project,working with NGOs that knew the context and had relationships with local leaders was critical to gaining access and implementactivities on a timely basis. The project was effective at working with NGOs that had experience implementing agriculturalactivities and could hit the ground running rapidly. That said, the World Bank and the implementing agencies must also createthe time to ensure that there is a common vision, including an understanding of goals, methodologies, and monitoring priorities(ICR, para 94).2. In fragile and conflict environments, project designneeds to be flexible, adaptive, and with longer implementation timelines. A flexible and adaptive managementapproach by the government and NGOs partners ensured that the project could continue to operate even as local circumstanceschanged. For example, in Northern Bahr el Ghazal, government and an NGO partner shifted activities once the initial plan of adonkey-powered traction did not work due to a tse-tse fly infestation (ICR, para. 94). That said, small grants lasting ashort period of time prevented planning for longer engagement and created trust issues with communities (ICR, para.94).3. Fragile and conflict environments also provide space to innovate. For example, NGOpartners, working with government scientists, were able to introduce good quality seeds with traits beneficial to the South Sudancontext. For example, they introduced Red Beauty groundnut, which was more tolerant of rosette and leaf spots. They alsointroduced NERICA rice which is more resistant to environmental stress and contains more protein than traditional varieties (ICR,para. 94).
P113621 | WBG Support for Fiscal Sustainability and Public Financial Management | Middle East and North Africa | West Bank and Gaza |  | FCS | Equitable Growth, Finance and Institutions | Governance | SPF | DPF | 2009 | 2010 | 2011 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/935911474663696867/text/000020051-20140624164605.txt | http://documents.worldbank.org/curated/en/935911474663696867/pdf/000020051-20140624164605.pdf | The experience of DPG 2 shows that for a reform plan to succeed ownership is needed at all levels of government, central as well as local. The delays in transferring electricity distribution from municipalities to distribution companies illustrate the difficulties of carrying out reforms when the local authorities are reluctant. This experience suggests the need for central authorities to secure agreement with the local authorities in advance.The experience of DPG 2 also shows that reforms take time to mature and show results. Some actions were not carried out during the existence of DPG 2 perhaps because the time frame was too ambitious.
P113623 | Strengthening the Management of Agriculture Public Services (GFRP) | Latin America and Caribbean | Haiti | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2015 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/128701468185354140/text/ICRR14760-P113623-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/128701468185354140/pdf/ICRR14760-P113623-Box393191B-PUBLIC.pdf | The following five lessons are emphasized with some rearrangement and adaptation of language:Institutional capacity building projects require relatively greater Government support and intense supervision. The project experience demonstrated that a relatively small institutional capacity building project, even in a country fraught with crises and challenges can, if the government is truly on board, and with intensive Bank supervision, result in significant improvements in the way a Ministry performs its mandate. Such projects, even when involving modest lending amounts, require significant implementation support with many staff weeks and adequate supervision budgets. However, these transformations might not be permanent gains unless continued follow up is maintained. Implementation without a Project Implementation Unit (PIU) in a situation of weak institutional capacity can be slower than with a PIU, but can yet be useful. When a project is implemented directly within the ministry without a PIU, the project design and implementation arrangements must be simple and well defined at preparation and design stage. Implementation speed must be expected to be slower than with a PIU. Moreover, institutional projects are time consuming, but have potential for high rewards. Client ownership of results frameworks is key. Results frameworks need to be simple and the linkages between the activities and the indicators need to be readily understood by the client in order to have adequate ownership and buy in to collect the necessary data to assess the outcomes.Policy dialogue is needed for institutional change and subsidy reform. Policy dialogue at the ministerial level, ownership of technical staff and active involvement of a broad range of stakeholders are important for institutional change and subsidy reform.To decrease the chances of policy reversal, a pilot approach is advised followed by scaling up. The voucher mechanism introduced a major re-thinking of how farmers receive subsidies. Before jumping into the full scale project, the ministry tested a small-scale innovative methodology. This type of small scale approach is also critical to show results and generate broad support from policy makers, donors and beneficiaries. Once scaling up is launched, efforts to keep key stakeholders informed about the project will need to be maintained to show the benefit of the reform.
P113625 | Guinea Food Crisis Response Development Policy Grant | Western and Central Africa | Guinea | IDA | FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | SPF | DPF | 2009 | 2010 | 2011 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/651971474553341039/text/000020051-20140620082151.txt | http://documents.worldbank.org/curated/en/651971474553341039/pdf/000020051-20140620082151.pdf | In fragile, conflict-ridden states such as Guinea, a high premium attaches to effective coordination between the Bank, IMF and other development partners. It may be difficult to maintain government support for measures to increase food security once the world price of food staples falls back from crisis levels.When designing an intervention of this nature it is critical to respond quickly, to be flexible, and to keep the operation simple and well-focused on government priorities.
P113629 | AFCC2/RI-Centre for Coordination of Agricultural Research and Development for Southern Africa (CCARDESA) | Other | Africa |  |  | Sustainable Development | Agriculture and Food | RETF | IPF | 2014 | 2019 | 2020 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/667091593207124442/text/Africa-CCARDESA-MULTI-DONOR-TRUST-FUND.txt | http://documents.worldbank.org/curated/en/667091593207124442/pdf/Africa-CCARDESA-MULTI-DONOR-TRUST-FUND.pdf | The following lessons were drawn based on those in the ICR (p.26-27) with some modification of language:Robustfinancial management systems, competent staffing for key management and operational functions, and rigorous internal controlmeasures are crucial to minimize the risk of fiduciary misconduct in an organization with a high level of autonomy. Themisappropriation ofCCARDESAs own funds during the first half of the MDTF emerged from the inefficient internal checkand balance system contributed by the weak recruitment and retainingof key finance staff with suitable experience andleadership, ill-adapted and outdated accounting software, insufficient Board oversight, lack of independent audit review,inadequate due diligence of sub-grant management, absence of risk register, and lack of a fraud and irregularitiespolicy.Leveraging partnerships and co-financing can be an effective meansto contribute to regional RD capacity building and knowledge sharing. In response to the MDTF financing gap atapproval and the funding cut during the second half of its operation, CCARDESA adjusted its position from implementation towardsfacilitation through partnership formation and co-financing of regional programs and projects through the facilitation of its corestaff. This strategic shift not only allowed CCARDESA to leverage additional sources of financing but also strengthened thecoordination of agricultural RD, thereby enhancing the outreach of capacity building and dissemination of knowledge in theregion.Robustgovernanceofregionalinstitutionsrequiressufficientengagement,capacityandfrequencytobeeffective.Although the CCARDESA Board largelyfulfilled its functions, it was dispersed across 15 Member States and its leel of engagement did not allow Board Members to fullyunderstand the operations and to exercise sufficiently robust oversight. Stronger governance practices in terms of Board tenure,frequency of meetings, board orientation and recruitment practices would have been useful to allow Board members to understand theorganization and make stronger contributions.
P113638 | Indonesia Sixth Development Policy Loan | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2010 | 2011 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/537231475327857616/text/000020051-20140624191402.txt | http://documents.worldbank.org/curated/en/537231475327857616/pdf/000020051-20140624191402.pdf | The lessons arising from the overall series are presented in the ICRR for the Sixth Development Policy Loan - P113638.
P113734 | Road to Europe: Program of Accounting Reform and Institutional Strengthening (REPARIS) | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2007 | 2010 | 2012 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/605011474663743405/text/000020051-20140625054253.txt | http://documents.worldbank.org/curated/en/605011474663743405/pdf/000020051-20140625054253.pdf | Building financial reporting infrastructure takes time to execute and have it in place. When project designers pay insufficient attention to timing problems, they are likely to underestimate the time needed to complete a project, putting in jeopardy its potential benefits.The experience in FYR Macedonia shows once more that procurement is a stumbling block for projects when the Bank fails to allocate adequate resources to train and guide the executing agencies in Bank procedures and methods.The experience of this project shows that reform â€œen blocâ€ is likely to neglect aspects of sequencing and timing, and to produce sub-standard results. This was the case when the project set up training for audit oversight without having defined previously the authority of the oversight members.
P113757 | SL-Decentralized Service Delivery Program | Western and Central Africa | Sierra Leone | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2010 | 2012 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/829821474665130784/text/000020051-20140626112057.txt | http://documents.worldbank.org/curated/en/829821474665130784/pdf/000020051-20140626112057.pdf | Lessons from the ICR, adapted by IEG:A phased, long-term approach to supporting the Government's decentralization reform agenda can be effective in low-capacity, fragile contexts. This project drew upon capacity built in a previous operation, and then reviewed outcomes and experience to inform the follow up operation. Key benchmarks were clearly identified to mark the Government's progress in implementing the reform agenda.Capacity building activities need to be properly sequenced to support effective project implementation. In the case of this project, although there was some element of "learning by doing" in allowing LCs to access sector grants quickly, capacity building support could have been front-loaded before allowing the fiscal transfers to take place.Adequate attention to and investment in M&E tools can produce useful data, even in low-capacity contexts. This project's National Public Service Survey and Comprehensive Local Government Performance Assessments were conducted within the existing national system, with some fine-tuning, and provided information that led to project adjustments.
P113766 | China Energy Efficiency Financing II | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2010 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/668101508188934493/text/ICRR-Disclosable-P113766-10-16-2017-1508188927162.txt | http://documents.worldbank.org/curated/en/668101508188934493/pdf/ICRR-Disclosable-P113766-10-16-2017-1508188927162.pdf | The project yielded a number of valuable lessons, of which the ICR presents the following (withparaphrasing):The continuing commitment and appropriate internal organization of PFIs are essentialfactors in the success in EE lending. Commitment needs to be demonstrated in management involvement, formation of andlong-term support for dedicated teams, provision of incentives to staff, and flexibility and innovation in developing and adaptingfinancial products.A model that is successful for one type of PFI may require significant effortsand modification to replicate successfully with another type of PFI. This project was patterned on the successfulexperience of CHEEF I, with the intent of extending the EE on-lending model to a large commercial bank with nationwide reach. CMBC,however, is more commercially oriented than the PFIs for CHEEF I, which are state-guided banks (and a policy bank, in the caseof EXIM) that are more attentive to policy imperatives and subject to the influence of government interlocutors. As a result,CMBCs project team did not enjoy consistent, strong backing from top management throughout the project, as was the case forCHEEF I. The contrast in results between CHEEF I and CHEEF II provides powerful evidence that the design offered for market-drivenbanks needs to be different than for policy-oriented banks and the value of persuasion is limited for the formergroup.Where financing is permitted to be used for both EE and RE projects, it is possible, andprobably likely, for the funds toflow mostly toward one or the other instead of being allocated equally between RE andEE. This was demonstrated by the flow of 85 percent of the parallel financing to RE projects as a result of marketconditions and government policies. This can be seen as allowing flexibility, depending on the objective of the project. If aproject is intended to finance both, it is worthwhile to consider setting boundaries on the amount that can go toward each type ofproject.The commitment of a commercial PFI to implement a credit line should be evaluated carefullyat the project design stage. Without a clear policy environment to stimulate demand by sub-borrowers for commercialfinancing of EE investments, commercial lending institutions will have difficulty sustaining a business case for promoting suchlending. Where there is a risk that implementation will not be sustained, innovative approaches could be built into the design, forexample, dates by which certain shares of disbursement must be reached for the project to continue. A design that introducescompetition between two or more lenders could also be considered, under which all PFIs have equal access to a limited pool. Thiscould guard against the inability or unwillingness of a given PFI to implement the project.
P113794 | Red Sea and Gulf of Aden Strategic Ecosystem Management GEF Project | Middle East and North Africa | Middle East and North Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2014 | 2019 | 2020 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/278841571666387620/text/Middle-East-and-North-Africa-1W-Strategic-Action-Plan-for-Red-Sea-II.txt | http://documents.worldbank.org/curated/en/278841571666387620/pdf/Middle-East-and-North-Africa-1W-Strategic-Action-Plan-for-Red-Sea-II.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptationof language.(1)Regional projects require more time and effort in the startup phase to mobilize differentstakeholders and this should be recognized in project design. The experience of this project showed that the startup phasetakes longer in a regional project as the coordination effort can bemore complex, particularly in view of the differences inimplementation capacity across countries.2). Strong political support and financial support from member countriesand a leadership structure is a pre-requisite for regional projects. As a regional entity with a clear mandate, PERSGA wasstrongly supported by member countries. This was evident during implementation, where member countries (with the exception ofYemen) continued to commit financial resources to the project, elevating co-financing to above expected levels.(3)A careful consideration of local traditions and capacities is required for effective community-based alternative livelihoodprojects. The experience of this project showed that developing alternativeprojects, taking into account locallyavailable technologies, traditions and capacities, contribute to successful completion of livelihood projects.
P113801 | SN - Economic Governance Project | Western and Central Africa | Senegal | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2010 | 2016 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/448591501510082713/text/Senegal-T-an-C-2017.txt | http://documents.worldbank.org/curated/en/448591501510082713/pdf/Senegal-T-an-C-2017.pdf | Three lessons are drawn from the ICR, with some adaptation (ICR, pages 27-28).1.A poorlydesigned Results Framework diminishes a governments ability to measure, report, and evaluate the results of aproject. The Senegal Economic Governance Project had a vague PDO statement that failed toarticulate the ultimateoutcome of the operation. The Results Frameworklisted results indicators that tried to encompass all variety of projectoutputs. Consequently, the ME plan could not correctly offer evidence of the results of the project.2. A political economy analysis (PEA) of a project helps a government to better understand the risks involved withefforts to advance policy and institutional reforms in politically difficult sectors and areas. Anti-money laundering,anti-corruption, and public procurement reform are politically difficult causes anywhere. The Government could not get the Ministryof Finance customs and tax offices to sign off on anti-bribery pledges with the private sector. The chamber of commerce and privatedonors have not signified a willingness to continue funding a private anti-corruption organization. The judiciary was notamenable to performance evaluation. Certain governance initiatives were dropped at restructuring for lack of interest on the partof the Government. A rigorous PEA could have identified these risks and shaped the scope of the project and help design riskmitigation measures.3. Caution should be observed when using Doing Business (DB) Report indicators tomeasure the results of medium- to long-term investment climate and other private sector development interventions.Regulatory reforms take considerable time to work through the governance system and the larger economy before their effects andimpact can be reflected in many of these DB indicators. In some cases, the formulation and the methodology for measuring readingsoff these indicators change. In 2016 and 2017, the DB Report redefined the minority investor protection index to include theextent of ownership and control and exclude strength of the governance structure --- Senegalsranking to dropped to 155th following the revision in 2016 from 122nd the year before.
P113844 | Metro Manila Wastewater Management Project | East Asia and Pacific | Philippines | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2012 | 2020 | 2022 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/885111637189224147/text/Philippines-Manila-Wastewater-Management-Project.txt | http://documents.worldbank.org/curated/en/885111637189224147/pdf/Philippines-Manila-Wastewater-Management-Project.pdf | The ICR (paragraphs 83-85) provided three lessons based on the projects implementation experience. These arepresented below, with some adaptation of language:Engagement needs to be sustained to help shape solutions andachieve development results in the urban water and sanitation sector. The Bank has supported the development andimplementation of GOPs major wastewater management strategies over the past 40 years. Through lending support, learninginitiatives, as well as policy and analytical advice, the Bank brought in global knowledge and expertise, distilled lessons fromimplementation experience, and applied that learning into succeeding operations. As the fourth lending operation in Metro Manila,the MWMP incorporated the lessons learned from predecessor projects, while taking into account current conditions andchallenges.The project design stage should include stakeholders at all government levels that have a critical rolein supporting the implementation of interventions in densely populated areas. The MWMP involved construction of STPs andconveyance systems in densely populated areas that require the issuance of construction permits and land acquisition, for whichLGUs play a critical role. The project was delayed when permits were not issued on time. This could have been avoided if the LGUshad been considered as part of the institutional set-up of the project. Likewise, LGUs could have facilitated land acquisition andcoordinated with utilities and national government agencies in the implementation of different infrastructure projects at theproject sites. The MWMP also experienced challenges in obtaining the right of way as the conveyance systems passed through landowned by different entities, LGUs, and individuals. In addition, the project was affected by other infrastructure developers andutilities operating in the project sites and would have benefitted from close coordination with these entities. The constructionimpacts on the public in terms of increased traffic congestion, socio-economic disruptions, and inconveniences were substantial.These concerns could have been anticipated and addressed through the LGUs.Flexibility is important and needsto be applied during implementation to allow implementing agencies to respond to unanticipated factors. The projectallowed financing of other wastewater investment subprojects as long as these were agreed among the Bank, Guarantor, Borrower, andthe concessionaires and had passed the eligibility criteria set forth at appraisal. This flexibility allowed the inclusion of theUniversity of the Philippines and Marikina conveyance systems without the need for a formal restructuring process. This flexibleapproach should be considered in future operations, to allow for the scope of work to change without need for majorrestructuring.
P113893 | First Programmatic Debt and Fiscal Sustainability Development Policy Loan | Latin America and Caribbean | Jamaica | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2011 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/157771474663158112/text/000020051-20140626110946.txt | http://documents.worldbank.org/curated/en/157771474663158112/pdf/000020051-20140626110946.pdf | The ICR draws a number of familiar lessons. One of these lessons concerns the need for care in designing a results framework close enough to the operation to allow attribution. The FSDPL's indicators were too high-level and were subject to the influence of external factors such as the macro environment which were not under the Government's control. Another lesson concerns the sequencing and timing of complex reforms. These must be carefully programmed and expectations about short-term outcomes must be realistic.The second issue could have been addressed by coordinating more closely with other development partners, namely leaving macro type issues to the Fund and focusing on more structural and institutional reforms where the Bank has more comparative advantage. The FSDPL tended to confuse these. While the impetus for the program may have stemmed from the urgent macro situation, the policy measures themselves were not particularly aimed at macro adjustment.
P113896 | AR San Juan SWAP | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | IPF | 2010 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/480961468190787743/text/ICRR14695-P113896-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/480961468190787743/pdf/ICRR14695-P113896-Box393183B-PUBLIC.pdf | The following lessons draw on those presented in the ICR:Effective technical assistance is appropriately focused. Technical assistance needs to be selective, focused on essential issues, and calibrated to the clientâ€™s absorptive capacity. None of these aspects was sufficiently taken into account in this project, resulting in weak performance on technical assistance.DLIs determine priorities. Reforms and policy measures that are not linked to disbursements receive lower priority during implementation. That was the case with several planned TA activities that were not implemented during this project. DLIs strengthen borrower commitment.Ownership by authorities is key. As with any results-based lending, the need for a reform champion is key , as this form of lending can be a complex instrument and reforms can be contentious. The content and phasing of reforms would have to be determined by the capacity of reform champions to implement them.Focused programs stand a better chance of success. It is important to keep the overall program simple and focused on a few critical reforms. An agenda that is too broad can become complex and diffused.
P113904 | Mekong Delta Region Urban Upgrading Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2012 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/908231568059989038/text/Vietnam-Mekong-Delta-Region-Urban-Upgrading-Proj.txt | http://documents.worldbank.org/curated/en/908231568059989038/pdf/Vietnam-Mekong-Delta-Region-Urban-Upgrading-Proj.pdf | The ICR presented six lessons from the operations. This Review identifiedthree as most relevant for Bank-widelearning. They arepresented below with some editing of the ICR text on which they arebased: In situ upgrading provided more benefits than demolition and rebuilding when improving urbaninfrastructure.In this project, this strategy preserved existing social networks and was less disruptive topeoples way of life. This strategy was especially helpful to ethnic minority groups who had strong attachments to theirexisting neighborhoods. In situ design also provided incentives for housing investments to create affordable and centrally locatedhousing stock for the urban poor, including migrants. For example, some households rented out space for small businesses alongimproved alleyways or rented rooms in their homes to students or workers who were encouraged by the improved flood control andincreased safety in the areas that received in situ upgrading. Flexible, adaptable functional standards could be adopted for insitu design to reflect community preferences, while maintaining compliance with planning standards for tertiary infrastructure. Inthis project, local governments and the MOC worked with the community to make sure that flexible design complied with localregulations. Functional standards such as alleys that are 2 - 4 meters wide to allow small firetrucks and maintenance vehiclesaccess to the area when needed, were allowed even though the minimum standard in cities master plans called for roads to beat least 6 meters wide. Encouraging community participation throughout the project cycle leads to ownershipand sustainability of outcomes. When beneficiaries participate in the planning and implementation of the improvements intheir surroundings, ownership is fostered and sustaining the results of project interventions becomes an organic component ofproject turnover. For example, during consultations, residents agreed to contribute to expand the alleys in the neighborhood thatwould be improved. Women and ethnic minorities were consulted separately to enquire about their preferred scope of project works.Organizing meaningful participation by the community is time consuming and required substantial effort in building the capacity oflocal authorities. Communication strategies, mobilizing community groups, conducting workshops and running campaigns also need tobe planned in terms of the time and resources needed throughout the project cycle. Regionalclustering of beneficiary cities facilitates coordination and reduces transaction costs. The 6 target cities in thisproject in the Mekong Delta Region had similar characteristics and challenges. By clustering them in one project,efficiencies in coordination were achieved. Transaction costs were reduced.Peer-to-peer learning among the cities wasencouraged.TA packages and contracts were bundled into cost effective contracts. Smaller and less experienced PMUs weresupported in a timely fashion.
P113949 | VN - Mekong Delta Water Management for Rural Dev | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2011 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/151781533739011434/text/Vietnam-VN-Mekong-Delta-Water-Mgmt-for-Rural-Dev.txt | http://documents.worldbank.org/curated/en/151781533739011434/pdf/Vietnam-VN-Mekong-Delta-Water-Mgmt-for-Rural-Dev.pdf | The standout lesson identified in the ICR for this project (page 28) is as follows (with some reformulation oflanguage):While water resource management in delta regions requires an integrated approach to address all water relatedissues, including agriculture, irrigation, sanitation, and climate change adaptation, project success can be attained through astrong results framework, and implementation arrangements with sufficient capacity building. The project had a lofty vision, whichtried to integrate water for agriculture and water for people, and introduced climate changeadaptation as a cross-cutting element. This was associated with additional technical complexity, sensitivities to changingenvironment, and the need for multi-sectoral solutions. In such a scenario, a stronger results framework, close monitoring andsupervision, as well as sound implementation arrangements with sufficient capacity building support are key to projectsuccess.
P113971 | Integrated Growth Poles and Corridor Project 2 | Eastern and Southern Africa | Madagascar | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2015 | 2020 | 2020 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/905691592249481740/text/Madagascar-Integrated-Poles-and-Corridor-Project-2.txt | http://documents.worldbank.org/curated/en/905691592249481740/pdf/Madagascar-Integrated-Poles-and-Corridor-Project-2.pdf | Three lessons are drawn from the ICR (pages 16-21, 23-26, and 43-44), with some adaptation.Successfulinstitution building is a necessary requirement in growth pole projects to enhance private sector developmentand tostrengthen public-private cooperation. This project spearheaded the creation of the National Cocoa Council, composedof private and state stakeholders, and assisted the Council to implement the National Cocoa Plan, drafted in 2018. It alsohelped establish the inter-professional Cotton Committee, a private body, and the inter-ministerial Cotton Council, a publicagency. In tourism, this project supported the operationalization of the Tourism Confederation of Madagascar and planned forthe creation of the Route Development Committee, composed of private and state stakeholders in the industry. Theseinstitutions either served as platforms for dialogue between the government and the private sector or represented the interests ofprivate industry in negotiations with the government over policy, regulation, industry programs. Building these institutionswerecrucial to ensuring the sustainability of public-private sector cooperation in these industries.Funding for the operation and maintenance of municipal infrastructure projects is often overlooked in regionalinfrastructure development programs within a country. In this project, no provisions were made for the futurefinancing of the operating and maintenance costs of the local roads, water, and sanitation systems built under the project by localgovernments. The ICR observes that certain construction standards were upgraded during project implementation in an attemptto lessen future maintenance costs of the infrastructure facilities. Such measures to reduce maintenance, however, cannot bea sustainable solution to the maintenance problem. The national and local governments must design collaborative plans to meettheoperating and maintenance costs of local infrastructure that are not covered by the national budget and agree on optionsat project preparation and appraisal.Projects that use macroeconomic variables as results indicators canforecast these variables and usedeviations from forecasts as measures of project efficacy. In this project,jobs created, businesses formed, revenues earned, and exports earned were used as measures of the achievement of the projectobjectives. But these macroeconomic variables are also driven byfactors other than those introduced by the project,including market demand, commodity prices, population growth, and even a time trend, as well as, potentially, by project-specificinterventions. Project management can assessthese impacts. Oneapproach is to forecast the macroeconomic andprojectvariables using statistical methods. The effects that are not due to fundamental macroeconomicfactors canarguably be credited to the project.
P114008 | AR-GEF Sustainable and Transport and Air Quality Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Infrastructure | Transport | GEF | IPF | 2009 | 2015 | 2015 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/342521468179355272/text/ICRR14781-P114008-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/342521468179355272/pdf/ICRR14781-P114008-Box393191B-PUBLIC.pdf | The ICR identified the following three lessons, which are presented here with slight modifications: The value of associating GEF operations to larger urban transportation projects needs to be evaluated on a case-by-case basis. Although linking GEF Projects to larger Bank operations has become common practice, in order to leverage funds and save supervision and coordination costs, this link could also result in slower implementation of GEF projects (given their relative priority vis-Ã -vis the larger operation at Government level), and the setting of overly ambitious objectives which go beyond the scale and time-frame of the GEF Project.The selection of implementation arrangements under GEF Projects raises political economy questions that need to be thoroughly analyzed during appraisal. In the case of this GEF grant, the option of placing implementation at city-level was discussed during project preparation, however, a decision was taken between the Federal Government and the Bank to keep implementation centralized, given formal lending requirements and existing local capacity. This added complexity and in many cases caused delays in project execution.Grants, such as GEF operations, should be used as â€œcatalyst financingâ€ as they provide an important vehicle in moving forward innovative issues. Although overall such funding tends to be limited, the nature of this funding increases positive public acceptance and receptivity to new, cutting-edge initiatives.
P114008 | AR-GEF Sustainable and Transport and Air Quality Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Infrastructure | Transport | GEF | IPF | 2009 | 2015 | 2018 | PPAR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/437631500649305080/text/117037-PPAR-P114008-PUBLIC.txt | http://documents.worldbank.org/curated/en/437631500649305080/pdf/117037-PPAR-P114008-PUBLIC.pdf | 7. Lessons 7.1 Broad and ambitious long-term objectives can result in implementation and efficacy challenges when the scope and timeframe of the project are limited. The experience with the Argentina GEF shows that there should be some flexibility in designing the objectives of GEF operations to keep them aligned with the actual scope and timeframe of the project. 7.2 When selecting project implementation arrangements, whether centralized at the national level or decentralized, the World Bank should assess local capacity issues with care and realism. In the case of the Argentina GEF, strong capacity at the local level and commitment to the project were essential to successful implementation in the city of Rosario, where most of the investments in assets funded by the project were made. 7.3 The rationale for linking the implementation of GEF projects with that of larger urban transport operations needs to be assessed on an individual project basis. Though there are some benefits of linking operations, including in saving supervision costs and leveraging funds, the experience with the Argentina GEF prior to the restructuring which led to the creation in 2013 of the Unidad Ejecutora Central, the new PIU, shows that parallel implementation of related projects can slow down the implementation of the GEF operations, because of their usually smaller scale. 7.4 While overall funding under GEF operations is often limited, GEF projects can promote innovative sustainable transport policy initiatives. Through the Argentina GEF, local authorities were exposed to global conferences and best-practice training programs, which contributed to positioning sustainable transport in the public debate and agenda. The average rate of motorization in Latin America of about 100 vehicles/1,000 inhabitants is still relatively low by international standards. The other two country projects are in Brazil and Mexico. These included local technical and implementation capacity, local authorities' commitment, and quality of submitted proposals. More details on the Buenos Aires Urban Transport Project are in IEG's PPARâ€”Buenos Aires Urban Transport Project. The performance of the World Bank Group FY2015â€“18 Strategy is discussed in Argentinaâ€” Performance and Learning Review of the Country Partnership Strategy for the Period FY15â€“FY18. Washington, D.C. Window 1 Freight Transport Management and Window 5 Travel Demand Management were not included under the Argentina GEF Project. However, there were no irregularities in the implementation of any specific operations funded by the GEF Project. 8PKF Uruguay. 2013. Argentina-Forensic Audit on World Bank Loans No. 7442-AR, No. 7794-AR, and TF093048. Final Report-Phase 1, dated April 2013. 9World Bank. 2013â€“14. Integrity Vice Presidency's Final Investigation Reports on Urban Transport Projects in Argentina. The discussion in the ICR under the Efficacy section does not focus exclusively on the activities funded under the GEF Project, but makes also reference to various other initiatives implemented by the Municipalities, either with their own funding or with other non-GEF sources of external financing. The PTUMA project was expected at appraisal to finance the construction of this BRT system in Posadas. Recent studies conducted on bike-share systems implemented in a number of large cities worldwide suggest that on average the main three substituted transportation modes are public transport for about 40 percent of users, walking for nearly 30 percent and private vehicles for just about 15 percent. A review of these studies is in Elliot Fishman, Bikeshare\. A Review of Recent Literature, Transport Reviews, December 2015. The first restructuring of the Global Environment Facility project modified some of the original indicators of the Results Framework. However, IEG has chosen not to undertake a split rating evaluation, as this would not make a material difference to the assessment of the project achievement against this project development objective. This estimate is based on information provided by the Pedestrian and Bicycle Information Center. 23 For example, the cost effectiveness of the Orange Line bicycle lanes in Los Angeles County are estimated between $1,068 and $1,727 per ton of CO2e reduced. Greenhouse Gas Emissions Costeffectiveness Study, Los Angeles County Metropolitan Transportation Authority, June 2010. As discussed in paragraph 4.6, the 280 bicycles which are not available to the public are stocked in a warehouse and are used to replace those bicycles which are undergoing maintenance.
P114010 | BR-GEF Sustainable Transport and Air Quality Project (STAQ) | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | GEF | IPF | 2010 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/142371488326447398/text/ICRR-Disclosable-P114010-02-28-2017-1488327362165.txt | http://documents.worldbank.org/curated/en/142371488326447398/pdf/ICRR-Disclosable-P114010-02-28-2017-1488327362165.pdf | The ICR provides a number of useful lessons. The following were prominent: The sustainable urban transport agendais critical if overall GHG emissions generated in the sector are to be reduced. It also observes that morecomprehensive policies such as prioritizing public transport and NMT (Non-motorized Transport) in the city as a whole...althoughpresenting modest result in emissions savings in the short term, set an initial trend that will have effects in urban developmentin 10 to 30 years by improving the quality of service of less-pollutant (sic)transport modes, therebyincreasingthe attractiveness of collectiverelative to private transport modes. The selection of an NGO as theprincipal project Executing Agency had both advantages and disadvantages with regards to project implementation and outcomes.On the one hand, in the present case ANTP demonstrated a risk adverse attitude with regard to not engaging in new activitiesthat could generate costs beyond those budgeted for the administration of a GEF project. On the other, it showedrelative independence and agility in redirecting planned activities that were not being properly advanced by participatingagencies. As a corollary not mentioned by the ICR, in undertaking project appraisal, the Bank needs to take theseadvantages and disadvantages, particularly the latter,clearlyinto account. Implementing agenciesneedadequate resources; otherwise the quality of their essential activities may be jeopardized.Additional lessonsthatcould havebeen highlighted are: Project objectives should be realistic given the amount of resourcesand nature of the project involved. In the present case, as the ICR recognizes,it was not realistic to expect that a GEFgrant of US$ 8.5 millionfor what was essentially a technical assistance and training project would be likely to have ameaningful direct and short-term impact on GHG emissions. Project ME arrangements need to be properly designed andput in place during preparation or at the very least during the initial stage of implementation and properly supervised by the Bankfrom day one. This was clearly not the case in the present project and contributed totheir persisting poor performanceand negligible utilization throughout project implementation. ICRsshould assess achievement of project objectivesas theyare explicitly stated in the Financial Agreement. In the present instance, the objectives specifically referredto the provision of assistance to Selected Agencies, but the ICR did not evaluate project performance in this regard,nor was the Results Framework properly designed to facilitatethis task.
P114012 | Sustainable Transport and Air Quality | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Infrastructure | Transport | GEF | IPF | 2010 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/516291498856133027/text/ICRR-Disclosable-P114012-06-30-2017-1498856122331.txt | http://documents.worldbank.org/curated/en/516291498856133027/pdf/ICRR-Disclosable-P114012-06-30-2017-1498856122331.pdf | The following lessons were drawn from the ICR:1. A clear scope of TA activities is important foraccountability. The scope of the GEF grant and its components were only TA and studies. Its over-arching objectiveswere at a higher level. Achieving the objectives totally relied on counterpart funding, which significantly exceeded the GEFgrant amount. The grants timeframe was too short to realize the achievement of theobjectives.2. Additionality requirements in climate finance could induce overly ambitiouscommitments by the eligible beneficiaries. The competition to be an eligible beneficiary during the GEF TA appraisal madecities promise too much. The additionality requirement forced cities to link the studies to be financed by the GEF project with alarge amount of actual investments within the short timeframe.3. The conditionality of policyadoption--as a funding eligibility requirement--can help ensure that the investment was spent as intended. For thecities to implement the results of the GEF TA studies, they needed to develop and adopt the PIMUS (i.e., integrated sustainablemobility master plan).
P114042 | Urban Youth Employment Project | East Asia and Pacific | Papua New Guinea | Blend | FCS | Sustainable Development | Social Sustainability and Inclusion | IDA | IPF | 2011 | 2020 | 2020 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/429091592862113014/text/Papua-New-Guinea-PNG-Urban-Youth-Employment-Project.txt | http://documents.worldbank.org/curated/en/429091592862113014/pdf/Papua-New-Guinea-PNG-Urban-Youth-Employment-Project.pdf | The ICR offered the following four lessons from the operations that other task teams may find useful toconsider for futuresimilar projects: Unemployed or underemployedyouth, when given a second chance, could becomeproductive participants in economic activities. In this project, the training and curated employability of trained youthled to considerable demand. Its success was attributed to an urban target regionwith a sufficient number of large businessesand hence more employment options for OJT programs. The YJC activities may be less sensitive to an urban setting and could bereplicable in non-urban settings. However, project expansion would be dependent on available staff to deliver the projectarrangements used in this project. The lesson from this project was that giving underprivileged youth a second chance allowed themto actively participate in the economic activity of their communities. Basic life skills and job readiness skillsare significant foundations in structuring the Theory of Changeto make young peoplecompete in the jobmarket.An Active Labor MarketProgram like theone under the project was comprehensive and coveredtraining, wage subsidies, and work placements. This strategy matched the unemployed school dropouts to jobs and employers afterreceiving training. The trainees secured on-going employment when they demonstrated workplace skills that employers valued morethan technical skills. Employers valued the investments in the BLS and PET because these prepared the youth to join the work forcewith the expected attitude. The lesson from this operation was that equipping the target youth with basic life skills andjobreadiness are valued by employers for job security. A strong mentoring and coaching program, combined with softand practical life skills facilitate a change in attitudes among at-risk youth. In this project, the skills and coachingof the trainers and community facilitators influenced a change in understanding of at-risk youth on work responsibilities,diversity in the work place, gender equity, improving health and nutrition. However, the data showed that the time was too short toachieve a turn around for young people with complex needs and contexts. The lesson from this operation was that psycho-socialsupporttherapies wereimportant to consider in supporting out-of-work youth to foster their labor forceparticipation. At-risk youth need more time anda variety ofpaths to employment andemployability. In this project, employers expressed the need to go beyond the basic life skills and practicalemployability training and confidence boosting. They noted the need to create a more varied cadre of employable youth with higherlevel skills. This could be achieved by extending the timesupporting trainees andintroducing trade apprenticeships ortechnical vocational educational training (TVET). The lesson from this operation was that there are numerous ways to achieveemployability of at-risk youth so that they could improve their condition and contribute to a wider economic activity.
P114069 | Shandong Energy Efficiency Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2011 | 2019 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/391201584548256778/text/China-CN-Shandong-Energy-Efficiency.txt | http://documents.worldbank.org/curated/en/391201584548256778/pdf/China-CN-Shandong-Energy-Efficiency.pdf | The firstlessonis taken from the ICR with some adaptation of language. The second one is derived from theICR.Inadequate risk analysis at appraisal, which results in underrating important risks, can adverselyaffect project implementation and the achievement of the project objectives. The two major risks identified at appraisal,i.e., the macroeconomic downturn and obstacles in subproject development pipeline, were rated as moderate. However,thedifficulty in identifying industrial energy efficiency subprojects at creditworthy small enterprises, which were interested infinancial leasing model, continued through project implementation. The situation worsened as a result of economic downturn. Thisnecessitated two project restructuringsin which renewable energy projects wereadded to the project scope as eligiblesubprojects, the disbursement ratio of the World Bank loan proceeds was raised from 50 percent to 80 percentbecause projectimplementing companies could not raise sufficient domestic fundsand project closing dates had to be extended due to slowproject implementation. Furthermore, projects focus had to shift from large state-owned economic enterprises (SOEs) to smallenterprises, and in the latter part of project implementation back to large SOEs, again,to achieve project objectives.However, this resulted in longer project implementation since identifying and executing subprojects at SOEs took longer time. Ifthe large subproject implemented by Shandong Iron and Steel Group Rizhao Co., Ltd, which is a SOE, had not been implemented, theproject would have most likely fallen short of achieving the project objective.If the implementation capacity ofleasing companies is not adequately addressed, projects promoting financial leasingmight face problems during implementationand not fully achievetheir objectives. One of the barriers which adversely affected project implementation was thecapacity of the project implementing units (PIUs). Guotai had sufficient capacity to implement financial leasing operations throughleveraging its large balance sheet and originating projects as a result of its extensive network; it also increased the number ofstaff working in its energy saving industry department. On the other hand, despite having a considerable technical strength andreputation, Rongshihua was faced with implementation delays and procurement issues. Some subprojectsidentified by Rongshihuahad to bedropped because of failure to obtain requisite guarantees needed for counterpart fundingor non-compliance withthe procurement requirements under the legal agreement and the operation manual. Despite disbursing 100 percent of its loan amount,Rongshihua could not reach the energy saving target, becauseit had to finance several solar photovoltaic subprojects, whichhad low energy saving capacity, to compensate for not being able to finance energy efficiency projects. Furthermore, the high staffturnover rate within PIUs with expertise in energy efficiency technology and financing, especially towards the end of the projectimplementation, weakened the project implementing capacity of the PIUs and resulted in significant project implementationchallenges.
P114077 | CM - Lom Pangar Hydropower Proj. (FY12) | Western and Central Africa | Cameroon | Blend | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2012 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099121324023523721/text/P114077-c6eb441f-f8e8-4c71-b414-08f2d4da2801.txt | https://documents.worldbank.org/curated/en/099121324023523721/pdf/P114077-c6eb441f-f8e8-4c71-b414-08f2d4da2801.pdf | IEG derives the following lessons, drawn from the ICR: For a project implemented in the context of weakgovernance and a breakdown of public accountability, the World Bank needs to step up its mitigation measures in fiduciary oversightof project implementation: There is a stark contrast between the mostly satisfactory achievement of theprojects outcome and the largely unsatisfactory financial management of the projects resources. This points tolimitations to the ability of legal covenants and implementation arrangements to transform weaknesses in a borrowers systemsof management of public resources. The most the World Bank can do in such circumstances is to strengthen mitigationmechanisms and provide technical assistance in parallel to the PIU and other related agencies. Theborrowers commitment to a projects results and objectives is key to their achievement during implementation:Bank teams need to be attentive to the borrowers commitment to a project and monitor risk mitigation measuresaccordingly. For the current project, while the country context was not optimal, it was clear that the borrower was ready toprovide every contribution needed to move the operation forward. Despite tight budget constraints, the borrower came up withthe needed counterpart funds, albeit with some delays as when BDEAC faced internal financial difficulties, the Governmentjoined hands with AfDB to provide the advances to launch the construction of the hydropower plant and transmission line. Throughoutproject implementation, the borrower provided counterpart funds that allowed the project to move forward in critical areas such asES risks, social welfare of works, etc. For projects with a dam construction component,reservoir impoundment must be prepared way ahead to allow for the preservation of timber wealth: Forest sitesplanned to host hydroelectric projects should be surveyed 3-6 years ahead of the effectiveness date, to allow time toorganize timber removal.
P114107 | Wenchuan Earthquake Recovery | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2009 | 2016 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/748431494856876983/text/ICRR-Disclosable-P114107-05-15-2017-1494856851848.txt | http://documents.worldbank.org/curated/en/748431494856876983/pdf/ICRR-Disclosable-P114107-05-15-2017-1494856851848.pdf | The following lessons are drawn from theICR (ICR, paragraphs 118-125) with slight modifications: Projectownership at the highest level (central government)fosters ownership at lower levels (implementing levels) ofgovernment. Complex projects (like the Moba Gorge dam and ancillary water treatment plant) are best implemented at theright administrative level, say at the provincial level (Gansu) rather that the municipal level (Longnan). In addition, similarcomplex andnew construction projects may benefit from a separate, stand-alone operation instead of being part of an emergencyreconstruction lending operation. When Building Back Better Plus followinga disaster, using a generalframework approach to identify the projects to be implemented rather than specifying these ahead of time allows for prioritizinginvestment needs during recovery. More complex projects may be separated and allowed to mature. For example, the reconstruction ofprimary schools in Gansu was prioritized by the national reconstruction program.Vocational and secondary schools were addedto the subprojects under the educationsector. In another case, some roads that met delays because of resettlement issues wererealigned or dropped in favor of other subprojects.
P114111 | CAR - Emergency Power Response Project | Western and Central Africa | Central African Republic | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2009 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/574621523398000971/text/Central-African-Republic-CAR-Emergency-Power-Response-Project.txt | http://documents.worldbank.org/curated/en/574621523398000971/pdf/Central-African-Republic-CAR-Emergency-Power-Response-Project.pdf | The ICR (pages 26 and 27) draws the following main lessons from the experience of implementing thisproject.(1) A simpledesign andcoordination withinterested external donors areimportant in achieving outcomes in a fragile environment.Inthis project, the relatively simple design allowed several activities to be implemented in the first two years of the project life.Given that funding in fragile environments is scarce, bringing in external donors helped in getting the needed resources andtechnical capacity to supply the planned activities and to generate results on the ground.(2) Asimple results framework and design(with limited number of components and activities) and implementationfocused on realistic achievements can be useful in post-conflict countries andenvironments. In the context of this project, a shorter list of performance indictors would have been more realistic andeasy to track in an environment with low capacity and limited data availability.(3) An effectiveProject Implementation Unit (PIU) and continuity of leadership on the part of the Bank supervision team can be useful in copingwith the risks in a fragile environment. In this project, the PIU was already familiar with the Banks fiduciaryrequirements. This in conjunction with continuity of leadership by the supervision team aided in completion of projectactivities.(4) In post-conflict countries and environments with weak implementation capacity, itwould be useful to simplify project design and focus on limited key achievements. Although the PDOs of restoring reliableelectricity supply to customers and improving the financial and operational performance of the sector was important in the countrycontext and to the government and Bank strategies,the experience of this project showed that the quality of achievementscould have been improved, if resources had been spent only on energy generation, transmission and distribution activities and allaspects related to issues ofoperational and financial efficiency of the electricity company left to a follow-onproject.
P114119 | PH - Chiller Energy Efficiency Project | East Asia and Pacific | Philippines | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2010 | 2017 | 2018 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/336471504638112807/text/ICRR-Disclosable-P114119-09-05-2017-1504638100993.txt | http://documents.worldbank.org/curated/en/336471504638112807/pdf/ICRR-Disclosable-P114119-09-05-2017-1504638100993.pdf | The ICR draws the following main lesson from the experience of implementing this project.(1) Under certainconditions, the use of small-scale financial subsides can be a sound investment option to catalyze interest and support broadernational energy efficiency goals. This project usedtwo types of funding - grant and market-based measures foraddressing thefinancial andtechnicalbarriers to adoptingcommercially-available energy efficientalternatives at design. Given that market-based measures were not used, the project had another measure through grants and thisenabled utilization of the remaining available funding without compromising the projects objective or its overallstructure.
P114138 | Water Conservation Project II | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2012 | 2017 | 2018 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/569701522880167267/text/China-CN-Water-Conservation-II.txt | http://documents.worldbank.org/curated/en/569701522880167267/pdf/China-CN-Water-Conservation-II.pdf | The ICR summarizes five key lessons derived from the project (Ref. ICR Para. 87 - 91). Of these, three stand out asrelevant to this project specifically and also applicable more broadly: Albeit more complex in design, thecomprehensive approach of combining engineering works and measures to improve agricultural water management with incentives forfarmers was key to get farmers to adopt the projects approach. Developing incentives for farmers in the form ofsustained increases in income was important in mitigating the risk of farmers likely reluctance to reduce water use or paymore for water. Well thought-through and proven financing models are requiredto ensure the sustainabilityof WUAs. Closely related to improving farm incomes and sustaining agricultural water infrastructure is establishingviable local institutions, in this case the WUAs. The financial viability of the WUAs over time will be a good indicator ofthe likelihood of infrastructure sustainability. Strategic pilotactivities in the project areas are key todemonstrate advanced concepts forsuccessful implementation by the project. It would perhaps be clearer to say thatpilot activities are key to providingbeneficiary farmers andthe Governmentopportunities to learn fromandassess the value of innovations. The projectcan then supportscaling up, as may be appropriate and desirable,based on the pilot experience.IEG-identified lesson:For projects thatare expected todirectly impact beneficiary incomes and livelihoods,building assessments of poverty impacts into baseline analysis andME systems is key to measuring a projects contributionto both the World Banks andrecipientGovernmentsbroader poverty alleviation goals.A projects specific development objectives mightnot be explicitly poverty-focused, but measurement of poverty impacts can still be important in assessing the value of Bank andGovernment investments. This project appears to have had poverty impacts that would have been useful to monitor.
P114154 | Public Sector Development Policy | East Asia and Pacific | Thailand | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2011 | 2013 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/668971475116696555/text/000180307-20141203051021.txt | http://documents.worldbank.org/curated/en/668971475116696555/pdf/000180307-20141203051021.pdf | This Review supports the lessons cited in the ICR, especially the importance of implementing reforms at the time of economic crisis and the need to consider other instruments if there are uncertainties about borrowers' commitment to utilize funding in a timely manner. The review adds the following lessons:Re-engaging with clients after a long hiatus in borrowing may prove difficult even with a client with strong institutional capacity. In Thailand's' case there were regulatory impediments to engage with external creditors (fiscal legislation stipulating that the deficit can not be covered by external borrowing) which affected the design of the operation.Although the macro aspect of the stimulus packages is critical, a strong focus on targeting poverty and vulnerability should also be a priority, especially in countries with sufficient institutional capacity to prepare and deliver public expenditure programs in a relatively short period of time.
P114174 | Haiti Education for All Fast-Track Initiative Catalytic Fund | Latin America and Caribbean | Haiti | IDA | FCS | Human Development | Education | RETF | IPF | 2010 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/814531483050123953/text/1483050122768-0000A8056-ICRR-Disclosable-P114174-12-29-2016-1483050117790.txt | http://documents.worldbank.org/curated/en/814531483050123953/pdf/1483050122768-0000A8056-ICRR-Disclosable-P114174-12-29-2016-1483050117790.pdf | Lessonsoffered byIEG include: Sound ME design in place at the outset of a project,with indicators and targets that are specific, realistic and measurable, is necessaryto ensure appropriate and adequateassessment of progress and achievement of stated objectives. Mid-term reviews are also key to ensuring that projects remainrelevant and on-track and that results are measurable. Additional Bank supervision, careful adherence to Bank procedures,and rigor in Implementation Status Reports in projects that are identified as potential problem projects or atrisk and which take place in a disaster or emergency context is essential, in case it is necessary to restructure and foreffective monitoring and implementation. Clear documentation regarding implementation processes is important forassessment of progress, in this case concerning the selection, vetting and monitoring process of grant compensation applications byan externally contracted agent.
P114182 | Provincial Energy Efficiency Scale-up Program | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2011 | 2017 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/583421512423274801/text/ICRR-Disclosable-P114182-12-04-2017-1512423263870.txt | http://documents.worldbank.org/curated/en/583421512423274801/pdf/ICRR-Disclosable-P114182-12-04-2017-1512423263870.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.(1) Tailoring approaches at the subnational level can aid in national Energy Efficiency (EE)goals. Working closely with each province and designingappropriate set of activities in each province helped incontributing to the national EE goals.(2) A flexible approach to project design can providescope forinnovation. One key development, not foreseen at design, was equipping inspectors in Jiangxi and Shanxi provinces withsoftware and hardware, including body cameras.This multiplied the enforcement capability of inspectors. This wasmade possible by developments and cost reductions in mobile technologies that could not have been predicted, but which provided anopportunity that the provinces were able to exploit quickly.(3) While having multiple Project Management Offices(PMOs) can introduce complexities in management, it can also provide an opportunity for realizing significant benefits through peerlearning. In the case of this project the Jiangxi and Shanxi PMOs benefitted greatly from Shandongs early experienceand greater implementation capacity of energy efficiency measures.(4) Attribution of outcomes tocapacity building projects can be challenging. Thetypically long chain of causality makes it challenging to designan indicator that could be attributed to capacity building project activities. However, in projects which mainly support technicalassistance and capacity building activities as in the case of this one, efforts still need to be made to measure the impact oftraining activities supported by the project.
P114204 | ELETROBRAS Distribution Rehabilitation | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2010 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/190321548790271333/text/Brazil-ELETROBRAS-Distribution-Rehabilitation.txt | http://documents.worldbank.org/curated/en/190321548790271333/pdf/Brazil-ELETROBRAS-Distribution-Rehabilitation.pdf | The Bank team conducted evaluation workshops in Brazil during the December 2017 ICR mission, whereinthemain lessons presented below (with some IEG paraphrasing) were identified and discussed. The ICR (paragraphs 113 to 123,pages 33 to 35) provides a more extensive set of lessons and recommendations, with some references to future sectoroutlook.1. A sound database and the regularization of customers need to be includedaspart of the initial project design and prioritized onceimplementation starts. The re-cadastering of customersis a crucial step to addressing massive fraud in a systematic way, and can bring considerable benefits in terms of improvingcommercial management and financial performance.However, regularization of customers is a costly and lengthy process, hencethe extensive relistingneeds to bepart ofproject design and given high priority at the start-up of projectimplementation.2. The capacity of distribution companies need to bestrengthened so thattheycan adequately andsystematically detect and correct massivepractices of fraud.While theAdvanced Metering Infrastructure (AMI) was able to break the culture of fraud among the relatively small number of large MVclients, all of whom were included in the AMI system, it is much more difficult to address the huge numbers of illegal connectionson LV lines. The need to relist these led to a tsunami of cases that the DisCos were not prepared to regularize in theshort time required. A much scaled-up effort that includes regularizing and shielding the billing of LV customers, as well as legalsupport to unlock interventions in invaded areas, seem to be required to accelerate the response capacity of theDisCos.3. Close supervision and intensive support are required to facilitate large, complexand innovative procurement packages. Bank project teams need to conduct a comprehensive capacity assessment duringproject preparation and appraisal, so that capacity gaps can be filled early on (such as appointing a field-based TTL, aprocurement expert, and/or a specialized engineering firm) and implementation delays can be minimized or avoided. New biddingdocuments can also be developed and tailored to combine goods and information technology services, as was done for theinnovativeAMI contract in this project.4. The Results Framework and the performanceindicators need to be adjusted in line with the realistic factors that affect financial and operational performance. Inthis project, the indicator for total loss reduction as a percentage of total energy was too broad. It proved tobe highly sensitive to too many external factors that were beyond the projects control, and thus was notaccuratelyindicative of the projects contribution.
P114236 | Agricultural Productivity and Food Security Project | Western and Central Africa | Burkina Faso | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2010 | 2020 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/537011608754254958/text/Burkina-Faso-BF-Agricultural-Productivity-Food-Sec.txt | http://documents.worldbank.org/curated/en/537011608754254958/pdf/Burkina-Faso-BF-Agricultural-Productivity-Food-Sec.pdf | The ICR lists sixlessons arising from the project (para 80-83), of which this review has chosen 4as being mostuseful for similar projects. Based on available information arising fromthe projects implementation, IEG suggests twoadditional lessons which werestimulated by this review.The ICR highlighted in a sound manner 4 strategiclessons, as summarized below.Lesson 1:Scaling-up a warrantage systemcan enhance access tofinance for smallholdersand improvefood supplies to rural markets.Thisproject supported warrantage arrangements to stabilize the supply of basic food in local markets while also providing anopportunity for farmers to access microfinance loans, guaranteed by warranted cereal stocks. Duringproject implementation,farmers mobilized loans totalling FCFA1.4 billion, which offered them the means to pay for vital family needs (e.g. childrensschool fees/expenses)and investments in their agricultural activities/enterprises). Also, in a Sahelian country likeBurkina Faso, with only one rainy season, food storage at all levels is an important food security tool for managing climate shocksand building community resilience against climate change. The lesson from this projectis that scaling-up thisinitiative requires explicit and appropriate policies and regulations to govern the warrantage or warehouse receipt system, toensure quality infrastructure to minimize postharvest losses, as well ascapacity building amongfarmers in post-harveststorage strategy and among warehouse managers to ensure regular food supplies in rural markets at competitive priceswhilealso covering storage costs.Lesson 2: An E-Voucher Systemcanencouragethe private sector to expand its participation in input distribution in the agricultural sector. Theintroduction of an E-Voucher System in this project (the first in Burkina Faso) contributed to a strong foundation for the growthof the fertilizer and seeds industries, drivenby a more competitive private sector. Thelessons arising from thisexperience include the need to: (a) establish timely advance planning of the e-voucher operation;(b) compilea reliableand complete potential beneficiary database; (c) strengthen or changedistributors for better control of the platform; (d)strengthen awareness campaigns for producers on the various aspects of the operation; and (e) communicationto farmers oneligibility criteriafor participation in the inputvoucher system(especially seed and fertilizer) in conjunctionwitha warrantage system.Lesson 3: Strengthening Governments collaborative capacitycanprovide improved delivery of support services to farmers:The project provided a sound templatefor empoweringgovernment technical servicesto provide support services through a PIU.The ICR identifies key elements whichPAPSA promoted to achieve this approach namely: (a) adherence to performance-based managementfor the participating governmentinstitutions;(b) strengthening the staff capacity ofimplementers (using project funds); and(c) motivating andincentivizing them to meet project targets in service delivery. The lesson is that these elements were successful inthis project and could be successfully applied other similar projects;Lesson 4: Multi-stakeholder innovationplatforms, driven by private sector actors can lead to improvedvalue chains. The project supported innovationplatforms as a means to: (a) expand the role of private sector actors in value chain development; (b) ensure compliance withregulations to ensure farmers deliver products which comply to a standard that the private sector can process and sell on domesticand international markets; and (c) improve agricultural processing and enhancecoordination of value chain actors.Thelesson is that farmersand processors need to produce products which meet the standards established innational andinternational markets;There one additional lessons arising from this ICR review, as follows:Lesson 5:Importance of Financing the Strengthening Agricultural Research System and Research-Extension Linkages: Anassumption of the project, as implied in the PAD (and the ToC in the ICR) is that there will be a national agricultural researchsystem with the required capacities and effectiveness to generate and sustain appropriate technologies on an on-going basis,especially suited for smallholder needs, coupled with strong and explicit research-extension linkages, to ensure high levels offarmer adoption. Experiences from other countries which aim to promote expanded, competitive and sustainable food productionand market supplies highlight the importance of including explicit support for these 2 key elements, which were not includedin the PAPSA design, although recognizing that there was a parallel project providing support to the agricultural research systemin Burkina Faso (WAAPP). Therefore,there may have been amissed opportunity, by relying entirely on theWAAPP, which also was trying to cover other countries, while also some aspects of the research system wereaddressed to someextent during implementation. The lesson is thatBank teams can usethe results from past and on-going agriculturalresearch and extension projectsin a country (as relevant)and include research and extension modulesnew projectsto continue to strengthen and scale up agricultural technological advances in contemporary operations.
P114240 | The Gambia - Growth & Competitiveness | Western and Central Africa | Gambia, The | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2011 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/927931497633329971/text/ICRR-Disclosable-P114240-06-16-2017-1497633320041.txt | http://documents.worldbank.org/curated/en/927931497633329971/pdf/ICRR-Disclosable-P114240-06-16-2017-1497633320041.pdf | Each FCV context differs and a thorough understanding of the countrys unique FCV context is important to develop aproject thats relevant to the countrys most critical needs. The Gambias FCV characteristics mainly pertain tothe governments lack of accountability and transparency, and the threat of elite capture. The GCP serves as a good exampleof a project that appropriately adopted goals, measures, expectations, and supervision to the specific features of theGambias FCV context.In subsequent communication, the ICR team reiterated points it raised in the ICRin paragraphs 100-103, that the complexity of Bank procedures and the difficulty that Borrowers may have in understanding them canbe a cause of delays from having to re-do procurements, backing out ineligible expenses, or poorly-written terms of reference thatrequire revisions. It is also important that project and borrower teams understand pre-requisites for implementation like hiring ofkey staff and the adoption of laws and regulations critical to implementation. For this reason, Bank teams may consider the use ofeffectiveness conditions. The ICR mentions many of these issues throughout the text and a range of remedial actions discussed orimplied: paras. 30, 32, 45, 55, 82, 83, 91, and 92.
P114240 | The Gambia - Growth & Competitiveness | Western and Central Africa | Gambia, The | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2011 | 2016 | 2022 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099825504042238150/text/IDU1c8a48bc5184b714bb11a6191f271ce4d4383.txt | http://documents.worldbank.org/curated/en/099825504042238150/pdf/IDU1c8a48bc5184b714bb11a6191f271ce4d4383.pdf | 3. Lessons 3.1 It is crucial to have a permanent funding mechanism for smooth functioning and sustainability of an SWBR. Because lack of funding is a major issue, the registry implemented by the project depends on the Ministry of Justice and the Ministry of Trade, Industry, Regional Integration and Employment for funding. An option would be to retain a portion of the revenues generated by business registrations to apply toward operations and maintenance of the registry. 3.2 Matching grant schemes need to be timely in the projectâ€™s trajectory and carefully targeted to participantsâ€™ specific needs. A lack of benefits from the vegetable and poultry outgrower programs was mainly due to the addition of these programs just two years before project closing. Because access to finance is overwhelmingly the most frequently identified constraint for firms in The Gambia, and access has worsened over time, MSME beneficiaries of the matching grant scheme needed funding after training to purchase equipment to meet market demands. However, by design, the projectâ€™s matching grant scheme did not include a provision for funding MSMEs. 3.3 For working with low-capacity clients, especially in fragile and conflict-affected countries, design should be simple and include a realistic set of components or activities implementable by the PCU. The scope of the project was complex, with several activities. As a result, the project narrowly focused on tourism. The Gambia could have benefited from a separate project focused on the competitiveness of the tourism sector to include product development, marketing, and infrastructure development. 3.4 Public-private dialogue to instigate investment climate reforms needs a key champion at the highest level of the government to bring the public and the private sector entities together to adopt and implement reforms. Evidence from several better- performing countries in Sub-Saharan Africa show that a champion at the highest level of the government can play an important role in improving the investment climate by leading discussions on investment climate reforms and tracking the progress of these reforms. 1 For detailed information on project components and activities, refer to World Bank (2010). 2The National Business Council comprises representatives from five cabinet ministries (public sector) and executives from seven companies (private sector). 16
P114253 | Education for All Fast-Track Initiative Catalytic Fund Phase III | Middle East and North Africa | Yemen, Republic of | IDA | FCS | Human Development | Education | RETF | IPF | 2010 | 2014 | 2015 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/548501475115180891/text/000180307-20141203050822.txt | http://documents.worldbank.org/curated/en/548501475115180891/pdf/000180307-20141203050822.pdf | Lessons from the ICR, adapted by IEG:Satisfactory quality-at-entry is a key factor for project performance in fragile environments. In the case of this project, strong project preparation included simple project design, realistic targets, and the use of existing implementation arrangements. Contracting female teachers in remote, rural areas can be a facilitating factor in increasing enrollment rates for female students. In the case of this project, stakeholders reported that there was a strong perception in the local communities that " the presence of female teachers encouraged a cultural shift in promoting girls' education" (ICR, page 14). Particularly if the teachers are locally recruited, there is also a higher likelihood that they will remain in the project areas and continue teaching and therefore also contribute to project sustainability.The use of an externally contracted agent to monitor project implementation can be critical in context of social or political unrest. In the case of this project, direct supervision of project activities by the Bank team was made impossible by the civil unrest; however, task team leaders confirmed that the third party monitoring agency was important for verifying implementation on the ground (including the quality of civil works), and making recommendations for follow-up actions (ICR, page 21). These actions helped to sustain project momentum in spite of the fragile context.The preparation of school maintenance plans was not given adequate consideration in the project design. In the case of this project, the lack of such plans pose a significant risk to the sustainability of the project achievements.
P114264 | Ghana Commercial Agriculture | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2012 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099200003272326404/text/P1142640db569901f092bf00c9af80a1c3c.txt | http://documents.worldbank.org/curated/en/099200003272326404/pdf/P1142640db569901f092bf00c9af80a1c3c.pdf | The ICR presents six relevant and sound lessons which have broader application beyond this project. The section belowconsolidates key aspects of these lessons into three lessons, together with their strategic implications (ICR, paras. 69 74).Lesson 1: For large scale irrigation development, ensuring realistic implementationtimeframe and structuring PPPs with sequential investment outlays by the partners is likely to succeed vs. being overly optimisticand using co-financing approaches.First, teams often underestimate the time required to rehabilitate largeirrigation schemes. At appraisal, the timelines envisaged were too ambitious and did not consider the impact of the procurementprocesses, climate change or extreme weather events. As a result, the client could not have completed the rehabilitation of theirrigation schemes without extending the projects closing date.Second, because of the high cost of water conveyancestructures, prospective investors are likely to be attracted if the Government bears that responsibility and the private investorsfinance subsequent land development and on-site infrastructure. However, such an approach needs a fallback position in the eventprivate sector demand falls below expectations. Under this project, water delivered through the upstream conveyance infrastructure,and from which the private sector benefited, also was serving smallholder farmers. The use of sumps for temporally water storageallowed for efficient water use between smallholder farmers and private investors. In addition, it is important to sufficientlyassess private sector enthusiasm and evidence of commitment before designing a project in which private sector participation is acritical element.Lesson 2: It is important to identify design and financing challenges earlyduring implementation in order to undertake timely and effective remedial actions. During the Implementation SupportMission of June 23-July 11, 2014 (only 11 months after project effectiveness), the Banks implementation support team and theGovernment counterpart team were already seriously concernedabout the feasibility of the Accra Plains PPP as designed, andhad started exploring options. This early response resulted in the projects re-orientation that underpinned the firstrestructuring, thus ensuring a rapid turnaround in project implementation. This experience of focused and sustained engagement withthe Project Coordination Unit and all the other project partners is critical for timely detection and correction of projectimplementation challenges. Innovative aspects of project design (e.g., sound safeguard instruments for the projects matchinggrant scheme, and other innovations) will require appropriate and timely technical and administrative support duringimplementation. Also, ensuring appropriate financing arrangements will be vital to help ensure smooth and timely implementation.The funding arrangements for the USAID grant and the IDA financing were initially joint (often times splitting the funding ofcertain activities in stipulated proportions). Difficulties in the availability of the USAID grant handicapped project activitiesand triggered a restructuring of the project. Lesson 3: Out-grower schemes are effectivewhen coupled with arrangements for working capital for the participants. Anchor farmers had to mobilize working capitalfor themselves and for their out-growers, which most found difficult to do, and when they did, they suffered losses from lowrepayment rates. Such schemes could include financial literacy training, linkages with financial institutions, revolving funds, andother mechanisms to ensure timely and sustainable access to finance by the participants.
P114271 | Customs Institutional Strengthening | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2009 | 2012 | 2013 | ICRR | Less than 10 million |  | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/476261474565893244/text/000020051-20140625232824.txt | http://documents.worldbank.org/curated/en/476261474565893244/pdf/000020051-20140625232824.pdf | The project might have been better structured as fee-for-service AAA instead of a TA loan. The Bank's eventual contribution under the project (which the Government appreciated), could have been delivered as AAA (see NCO, par. 12) with much less of an administrative burden on the client, while the Bank would have avoided the risk for a project where its role was unclear.
P114291 | Tanzania - Accelerated Food Security Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2009 | 2014 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/778291468187455854/text/ICRR14728-P114291-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/778291468187455854/pdf/ICRR14728-P114291-Box393183B-PUBLIC.pdf | The following main lessons have been adapted from the ICR: (i) An agricultural input supply program would likely get larger benefits if accompanied by intensified agricultural extension. Crop yields increased appreciably, reaching appraisal targets. However, based on international experience, with improved cultivation practices accompanying the use of inputs, yet larger yield gains might have been possible. (ii) An emergency response project should focus on a rapidly implementable program of short term actions, avoiding longer-term investments. Inclusion in the project of irrigation and other investments turned the operation to a hybrid between emergency response and investment, and lengthened the project implementation period.(iii) Institutional mainstreaming may still require targeted â€œshoring â€“upâ€ support. Procurement capacity was a particular weakness and might have been bolstered through out-sourcing most activities to a consulting firm, or some other pragmatic solution.
P114292 | HT Emergency Bridge Reconst & Vulnerab Reduction Project | Latin America and Caribbean | Haiti | IDA | FCS | Infrastructure | Transport | IDA | IPF | 2009 | 2015 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/593471498856743955/text/ICRR-Disclosable-P114292-06-30-2017-1498856733908.txt | http://documents.worldbank.org/curated/en/593471498856743955/pdf/ICRR-Disclosable-P114292-06-30-2017-1498856733908.pdf | IEG has selected three lessons from a longer list in the ICR, with some adaptation of the language: Inpost-conflict and disaster-prone countries, the provision of resources to address emergency issues is critical in projectdesign. This project was developed to respond to the urgency generated by FGHI of 2008, and no provision was made torespond to the emergency resulting from the 2010 earthquake and subsequent hurricanes. Project design was not prepared toanticipate another emergency and had to be restructured substantially. Incorporation of an emergency component into project designthat could be triggered depending on emergency circumstances may ensure a swift response andflexibility. Institutional reforms are difficult in volatile countries that are prone to naturaldisasters and support needs to be provided at two levels: information management and inter-ministerial coordination. Underthis project in Haiti, the difficulties in the reform of SNGRD and the limited capacity of MPCE in the wake of the earthquakeemphasized the need to work on two levels: (i) the strengthening of sectoral ministries in the collection and management ofinformation with regards to the management of crises and disasters; and (ii) inter-ministerial coordination for decision making andplanning of mitigation measures (prevention, resilience). Improved information collection and management isimportant to ensure adequate disaster risk management programs and policies. Haiti continues to face difficulties in thecollection and archiving of disaster-risk information and in generating an improved understanding of their vulnerabilities andrisk. To improve resilience and better coordination and planning in vulnerability reduction activities, the enhancement ofinformation management at both national and local level is critical.
P114294 | Rural Corridors and Biodiversity | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2015 | 2022 | 2023 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099061223193566713/text/P11429408a211402508d4500c69160e76cb.txt | http://documents.worldbank.org/curated/en/099061223193566713/pdf/P11429408a211402508d4500c69160e76cb.pdf | The ICR (p. 30-31) included threelessons/findings. Two of them were adapted and listed belowtoindicatelessons IEG drew from the project: Designing projects with broad geographic scopeandgenericdevelopment objectives usingflexible investment and institutional strategiesadapted to local circumstancescanresult in diffusion of effort, dilution of impact, and difficulties measuringoutcomes. This projectsobjective was broad and covered a wide geographic scope. The projects Results Framework lacked accurate definitions andexplicit measurement methodologies, makingmonitoring of progress andcredibly verifying theachievementofobjectives very challenging. Effective and successful participatory project implementation processes are morelikely to achievepositive sustainable project outcomes ifthey areplanned during project design. In thisproject, visible participation of representatives of provincial governments and civil society at the project design phase wasimportant and successful for strengthening bonds and credibility among local entities which enhanced the projectsimplementation andimpact.
P114338 | Eastern Dedicated Freight Corridor - I | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2011 | 2019 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | https://documents.worldbank.org/curated/en/099062024194515944/text/P114338-a3bf1be1-c074-4dbd-a46f-71e4565539b7.txt | https://documents.worldbank.org/curated/en/099062024194515944/pdf/P114338-a3bf1be1-c074-4dbd-a46f-71e4565539b7.pdf | The ICR draws the following three main lessons from the experience of implementing this project, with some adaptation oflanguage.1. The Banks long-term strategic support may raise the potential for success in enabling State OwnedEnterprises (SOEs) harness commercial financial markets and introducing fundamental changes in a countrys railsector. The time frame for large-scale, long-term reforms in a countrys rail sector are typically long. Thesestrategic reforms require the SOEs to evolve from a traditional government-funded organization to a commercial, market-focused andoperationally efficient entity. Likewise, long-term engagement by the Bank can enable the Bank to facilitate adoption of soundsocial, environmental and fiduciary policies.The lesson is that Banks long-term support may be necessary to facilitatesuch reforms.2. Careful planning for managing and coordination of land acquisition may be required, in countrieswhere subnational entities are involved in land acquisition. In India, national-level projects rely on state governmentsfor the complex process of land acquisition. The process in this project required intensive coordination between the DedicatedFreight Corridor Corporation Limited (DFCCIL), the state government land offices, the contractors and local governments. Over time,as land acquisition delays impeded construction, DFCCIL became much more systematic in coordinating land acquisition as it came torealize that coordination with local authorities was in the interest of timely project completion.3. A carefulassessment of the World Banks capacity and the contractors capacity may be required when new contracting structures areintroduced for the first time. This project conceptualized the Design-Build lump sum contract to ensure equitable risksharing between DFCCIL and the contractors. However, the project failed to foresee the time required for Banks internalapprovals, financial challenges faced by contractors and delays in land acquisition by DFCCIL. This contributed to the delays inthe initial years.
P114348 | Water Resources and Irrigation Sector Management Program 2 | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2011 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/891911548872741680/text/Indonesia-Water-Resources-and-Irr-Mgmt-Program-2.txt | http://documents.worldbank.org/curated/en/891911548872741680/pdf/Indonesia-Water-Resources-and-Irr-Mgmt-Program-2.pdf | The ICR (page 26) draws the following three lessons from the experience of implementing this project, with someadaptation of language. (1) Participatory irrigation management by enabling farmers toparticipate in sector development, can help in increasing the sense of ownership by WUAFs. The participatoryirrigation management in this project, by involving farmers in regulatory development, resulted in improved allocation of water tofarmers. The success of this approach is attested to by the fact that the government is extending it to national level irrigationschemes.(2) Clarity of the legal framework is required for the sustainability of the participatory irrigationmanagement approach. The uncertainties created by the annulment of the law no 7/2004, were partly mitigated by temporarydecrees. It is important that legislation be enacted to replace Law no 7.(3) On-granting mechanisms can help inimproving the capacity of districts for project implementation.Although delays were experienced in view of the lackof clarity of the mechanism, these were resolved and such mechanisms, by providing more independence to the districts inimplementing their annual work program, can aid in improving their capacity for projectimplementation.IEG draws the following lesson.A robusttheory of change requires a clear chain between project activities and expected outcomes, as well as indicators which enableprogress in meeting objectives to be measured. In this case, there were no outcome indicators for monitoring performancewith respect to the objectives of improving the capacity for basin water resource management.
P114373 | Second Fiscal and Institutional Development Policy | Latin America and Caribbean | Guatemala | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2011 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/814771474564391608/text/000020051-20140625060805.txt | http://documents.worldbank.org/curated/en/814771474564391608/pdf/000020051-20140625060805.pdf | The ICR points out the limits of short-term actions such as those supported by the series, in supporting politically controversial reforms. Actions requiring legislative approval will be difficult (e.g. tax reform) without a strong impetus of public support (access to information). Reforms that must be sustained over a long time period to achieve success (improved financial sector supervision) need support from multiple operations, while some measures that could be introduced under the authority of the executive (improved tax administration) did deliver short turn results (reduced evasion). Further, the impetus of external economic pressure can add an impetus to reform when both authorities and the Bank can be flexible enough to respond at the right time. Going beyond the ICR, the uneven outcome of PFM and procurement reforms indicates that there are limits to what can be achieved with new laws, formal processes, and electronic systems. Drawing on the WDR2011, future work might explore the functioning of informal flows of resources through patronage networks, and see if there are good practices where these resources support valuable public goods, and opportunities for using such practices to help design more far-reaching reforms of the formal public resource management system.
P114409 | GEOFUND 2: ARMENIA GEOTHERMAL PROJECT | Europe and Central Asia | Armenia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2009 | 2013 | 2014 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/736711474897057765/text/000020051-20140626103543.txt | http://documents.worldbank.org/curated/en/736711474897057765/pdf/000020051-20140626103543.pdf | The following lessons are taken from the ICR, with some adaptation of language:There are considerable advantages in staging this type of project, with the next phase conditional on the results of the prior stage or phase.Appropriate mobilization of both international and local expertise can be beneficial to the technical quality of the work carried out and hence to the outcome. Less costly interventions may be equally or more efficient than dearer options, In this case, cheaper survey methods were used which prevented the costs of exploring potential geothermal drilling sites from becoming prohibitive.The project demonstrated the importance of flexibility regarding both the types of field investigation works that should be financed and the time needed for implementation. In this case, results of field scouting and other basic field work warranted a different type of follow-up field study than that provided for in the projectâ€™s initial design. Moreover, in a phased approach such as that adopted here, it is important to anticipate the need for a second phase, and to allow enough time for its planning and implementation. Such flexibility can prevent the need for a time-consuming restructuring, which had to be undertaken here, and which led to further delays since favorable weather conditions were missed.
P114441 | Price Vulnerability (Food Crisis) /former Product ID: P113225 | Latin America and Caribbean | Nicaragua | IDA | Non-FCS | Human Development | Social Protection & Jobs | SPF | IPF | 2009 | 2011 | 2012 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/310431474630908692/text/000020051-20140624202938.txt | http://documents.worldbank.org/curated/en/310431474630908692/pdf/000020051-20140624202938.pdf | The following lessons are taken from the ICR with some adaptation.(a) High level commitment, both by the Bank and Government, is critical in preparing emergency operations and increasing effectiveness. (b) In the case of emergency projects, a simple design is a key factor for success. Complexity in design and the low state of readiness of the agencies concerned, as in Component 2 of this project, pose major implementation challenges.(b) The probability of success of a Bank project in an emergency situation increases when the Bank relies on a well established, credible and effective program in the country (e.g. PINE).(c) Emergency operations provide an opportunity for crafting longer-term responses to vulnerability. In time of crisis governments realize their ability to respond depends on the importance of given to establishing effective social protection systems.(d) The importance of monitoring and evaluation should not be underestimated in emergency operations.
P114463 | Development Policy Credit | South Asia | Maldives | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2010 | 2014 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/207791474663527211/text/000020051-20140626075850.txt | http://documents.worldbank.org/curated/en/207791474663527211/pdf/000020051-20140626075850.pdf | IEG agrees with the lessons highlighted in the ICR, including the necessity to limit the scope of the reforms to only the most urgent and essential areas in Bank engagement with countries that have inexperienced governments; and the importance of focusing on building technical capacities for economic governance, etc. In addition, this operation highlights once again the challenges that the Bank faces in implementing a programmatic series in a volatile and unpredictable environment including existing trade-offs in the selection of the type of DPO engagement (programmatic series vs single-tranche operations vs tranched operations). This operation also highlights that although prior actions are important (as building blocks for follow-up reforms), they cannot fully guarantee satisfactory program implementation if underlying conditions are missing.
P114508 | Pakistan: Third Partnership for Polio Eradication Project | South Asia | Pakistan | Blend | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2009 | 2014 | 2015 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/292311467986335514/text/ICRR14772-P114508-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/292311467986335514/pdf/ICRR14772-P114508-Box393191B-PUBLIC.pdf | The ICR (p. 20) identifies valuable lessons, including the following:Using already existing program management systems allows for a much faster implementation start. In this project, implementation structures from previous projects were utilized, and a project-specific implementing agency was not set up, which saved time and money since skilled staff were already available and paid out of the governmentâ€™s budget. This made the sustainability of project outcomes after project closing more likely.Polio eradication efforts can be integrated into routine immunization strengthening, not diverting resources from Pakistanâ€™s Expanded Program on Immunization.
P114515 | Integrated Solid Waste Management Project | Europe and Central Asia | Belarus | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2010 | 2017 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/500031539610987818/text/Belarus-INTG-SOLID-WASTE-MGT.txt | http://documents.worldbank.org/curated/en/500031539610987818/pdf/Belarus-INTG-SOLID-WASTE-MGT.pdf | Fourlessons were selected from the ICR, with some modification of the language: Thelatest,more advancedtechnologies may distract decision-makers from recognizing more cost-effective andcontext-appropriate solutions in the local context. In this project experience, one of the factors contributing to a delayin finalizing construction of the planned materials recycling facility was that local decision-makers decided to re-open options,including the idea of refuse-derived fuel (RDF) technology. The World Bank technical team helped educate the decision-makers aboutcost-benefit considerations of the options, and supported the government in selecting a cost-effective approach most appropriate tothe local context. More complex, expensive technology would have made the investments financiallyunsustainable. Educating the market may be necessary to anticipate andassuage international investors and contractors perceptions of country- and/or sector-specific risks. Aninvestigation of why international equipment suppliers did not respond to the first bidding process to construct and supply the MRFin Belarus revealed that international firms had no prior experience doing business in Belarus, and did not feel comfortableresponding to a government tender for goods due to the lack of certainty about institutional capacity, regulatory framework andlocal market dynamics. In countries with limited private sector investment into the sector, project teams should anticipatepotential concerns and proactively reach out to potential bidders. The dynamic natureof a countrys sector environment should be taken into account when making projections of a projectssustainability. Thenewly constructed recycling plantunder this projectis sensitive to potential forreduced flows. Two unanticipated factors contributed to lower flows: Scavenging of glass did not occur in any meaningful volume atthe time of project design, likely because pre-separated waste containers did not exist and the city had not yet started promotingwaste separation city invested in waste separation containers and made containers easily accessible, suddenly recyclable glassbecame easy and attractive to scavenge; as such, less glass flowed to the MRF. Secondly, an Extended Producer Responsibility (EPR)scheme not envisaged at project design, contributed to a decrease in volume of waste flowing to the MRF. The EPR systemincentivized commercial businesses to direct their pre-sorted waste towards recycling companies, so that the recyclables can becounted against businesses EPR mandatedtargets. Multi-channel and ongoing public outreach and information campaigns arecritical to promote participation in recycling. Since the viability of the MRF is dependent on the quality of inputs, thisproject was dependent on the participationof ahigh percentage of residents and businesses in waste separation atsource. The government deployed various approaches for getting its message out about the benefits of recycling, and how the newprogram worked (in terms of closing trash chutes in residential buildings) ) as well as targeting schools and educationalinstitutions.
P114609 | Catalytic Fund EFA/FTI | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2011 | 2015 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/778431467999702100/text/ICRR14758-P114609-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/778431467999702100/pdf/ICRR14758-P114609-Box393191B-PUBLIC.pdf | Lessons drawn from the ICR, adapted by IEG:Decentralization of school construction to the community level can build greater commitment to education and increase enrollment of out-of-school children. In the case of this project, the use of community-based contracting, alongside provision of grants for supplies and training in school management, led to increased efforts of village education committees to ensure enrollment of students.Effective use of M&E can impact government policies. In the case of this project, pilot activities - such as the school feeding and community-based school readiness programs - were carefully evaluated, and the results informed decisions of the government to either end programs or continue them, even with its own funding.
P114617 | LAO PDR: Rice Productivity Improvement Project | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Sustainable Development | Agriculture and Food | SPF | IPF | 2009 | 2012 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/742821474593084547/text/000020051-20140625235547.txt | http://documents.worldbank.org/curated/en/742821474593084547/pdf/000020051-20140625235547.pdf | The following lessons derive from the ICR:It is necessary to avoid ambiguity in the project development objectives of an emergency operation to ensure the most efficient design and implementation arrangements. The project experience showed that it should be clear up front if the focus is on short term activities of emergency nature or longer term measures that includes broader structural and policy issues. Choice of en emergency operation that has short time frame in planning and implementation is not the best option for objectives that require longer term approaches.Seed multiplication activities need to be combined with parallel extension scale-up support for larger numbers of farmers, using seed packages. The project experience demonstrated that seed production is suitable for more advanced farmers. Also significantly longer capacity building support than just two cropping seasons is required to establish strong seed producer groups.Projects dealing with the seed sector need to address both demand and supply side issues. The number of target groups to be established and supported, and related seed production targets, should be carefully calibrated against potential demand. Also remunerative outlet for the groupâ€™s seed outputs or to support the development of distribution channels should also be considered and arrangements for those should be included in project design.
P114766 | Kazakhstan Moinak Electricity Transmission Project | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2010 | 2013 | 2014 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | High | http://documents.worldbank.org/curated/en/635451475113809325/text/000180307-20141202142139.txt | http://documents.worldbank.org/curated/en/635451475113809325/pdf/000180307-20141202142139.pdf | The following lessons are taken from the ICR with some adaptation of language: Early consultation with civil society and NGOs can help avoid project implementation problems. In this project, during preparation, it proved to be critically important to hear from the NGO community and take into account their concerns in the final project design. The concerns related to initial routing of the 2 transmission lines, and a timely re routing decision ensured that the lines did not encroach upon GOK-defined Specially Protected Natural Areas.The development of a relationship of trust and confidence is key in projects of a relatively specialized nature involving sector reforms and institutional change. In this case the continued involvement of the same Bank staff over a few projects has led to the modernization of the electric power sector in Kazakhstan that is far ahead ofother Former Soviet Union countries.Even projects with limited land acquisition and no relocation of people require adequate attention from the outset from the Bank team. The lack of consistent involvement of a qualified social scientist experienced with land acquisition issues both during preparation and implementation resulted in delays in approving the Land Acquisition Plan (LAP), and risked the project becoming out of compliance with the relevant safeguard covenant in the Loan Agreement. This lesson also highlights the importance of early technical assistance and capacity building with in the clientâ€™s institutions.
P114810 | Amazon Region Protected Areas Program Phase II (GEF) | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2012 | 2018 | 2018 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/791431524518810217/text/Brazil-BR-GEF-Amazon-Region-Prot-Areas-Phase-2.txt | http://documents.worldbank.org/curated/en/791431524518810217/pdf/Brazil-BR-GEF-Amazon-Region-Prot-Areas-Phase-2.pdf | The most notable lessons learned are takenfrom the ICR (p. 18 to 20) with some modification oflanguage: Cost modelling of PA management and of conservation fund dynamics are essential tools forlong-term conservation planning: This project conducted extensive cost modelling on the Protected Areas to estimatea more accurate overall budget for the program and for a long-term conservation fund. This modelling provided the necessaryinformation for the establishment of the Transition Fund such as the capitalization requirements, time limit for the sinking fund,and the governments Protected Area budget required to achieve the total incorporation of the ARPAprogram. Traditional income-generating activities for Protected Areas such as eco-tourism, concession agreements,end entrance fees might not work everywhere. In this project, as well as in Phase 1, such income generatingactivities were unsuccessful in the Protected areas due to their remoteness, lack of transportation infrastructure, health andsanitation concerns, and high costs. Therefore, other revenue generating mechanisms such as procuring compensation money fromlarge-scale development projects, were identified. Allowing the management approach to be adapted is critical forthe management of Protected Areas over a long-term period since it allows for flexibility. Over a 15 yearimplementation period the ARPA program developed different methodological tools to address budgetary, institutional and politicalchanges. This had a positive impact on the implementation of activities.
P114822 | Seychelles Development Policy Lending | Eastern and Southern Africa | Seychelles | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2010 | 2011 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/978301475089526681/text/000020051-20140624195758.txt | http://documents.worldbank.org/curated/en/978301475089526681/pdf/000020051-20140624195758.pdf | There are three important lessons: (i) A well designed communication strategy is vital to build public support for reform; (ii) Offering training and job placement and establishing a welfare system is essential to facilitate a reduction of the role of the state in the economy; and (iii) Providing technical assistance and creating effective partnerships in designing the reform program increase the likelihood of success.
P114827 | Second Gujarat State Highway Project (GSHP II) | South Asia | India | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2014 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099140006132227748/text/P11482705a705d037097280e5f222f195bd.txt | http://documents.worldbank.org/curated/en/099140006132227748/pdf/P11482705a705d037097280e5f222f195bd.pdf | Two lessons are taken from the ICR with some modification of language.Insufficient market interest toinnovative financing and contracting schemes can significantly delay project implementation and critically affect the achievementof project objectives. The project introduced innovative financing and contracting schemes that were to be implemented forthe first time in Gujarat. At appraisal, it was assumed that market interest would be sufficient. However, contrary to theexpectations, the market was not sufficient even for the related consultancy services. Some contracts had to be bid multiple timesresulting in project implementation delays. Some road works could not be completed by the original closing date (COVID-19 pandemic,too, adversely affected project implementation in 2020). Although project preparation took five years, a market interest assessmentwas not conducted during appraisal.A modified-annuity type PPP contract for road works can reduce the financialburden on government finances while ensuring sustainability of roads in the medium-term. Sixty-one kilometers of highwaysbetween Mehsana and Himatnagar was upgraded to four lanes through a pilot PPP Annuity-basedDesign-Build-Finance-Operate-Maintain-Transfer (DBFOMT) concession. This contract facilitated private sector participation andinvestment in public works maximizing finance for development while reducing financial burden on the Government of Gujarat.Furthermore, the inclusion of maintenance in multi-year periods should be expected to ensure the sustainability of road assetsdeveloped under the project.
P114841 | Northern Areas Reduction-of-Poverty Initiative Project -- Women's Economic Empowerment Project | South Asia | Bangladesh | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2012 | 2019 | 2020 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/451021571764082802/text/Bangladesh-BD-Northern-Areas-Reduction-of-Poverty.txt | http://documents.worldbank.org/curated/en/451021571764082802/pdf/Bangladesh-BD-Northern-Areas-Reduction-of-Poverty.pdf | The ICR (p. 19-20) provided lessons learned which were adapted by IEG: When project activities aredesigned to depend upon one another (i.e. one component cannot start until another is finished), adequate sequencing of projectactivities becomes critical. In this project, this was the case regarding the construction of DTCs before the start of thetraining program. In this project, the delay in the construction of the DTCs led to a delayed start of the training program, whichhad a negative impact on project outcomes. A flexible Results Framework with adequate, realistic and measurableoutcome indicators may contribute to the documentation of the achievement of the PDO. In this project, a proposed ImpactEvaluation was planned to be the basis for data collection. However, once it was dropped, the projects ME experiencedcritical shortcomings. Also, the Results Framework included indicators to measure changes in wages, which is a long-term outcome,and the challenge of tracking trainees after graduation was not taken into account. When a project includes twoimplementing agencies, a clear distinction of roles and responsibilities is important to ensure sufficient authority to makecritical decisions in a timely manner to avoid implementation delays. In this project, the roles and responsibilities werenot sufficiently defined and none of the agencies had sufficient authority to make critical decisions in a timely manner whichresulted in implementation delays.
P114847 | Project to Improve Education Quality in Malawi | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2010 | 2015 | 2016 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/822211468090566380/text/ICRR-Disclosable-P114847-06-10-2016-1465573349531.txt | http://documents.worldbank.org/curated/en/822211468090566380/pdf/ICRR-Disclosable-P114847-06-10-2016-1465573349531.pdf | This ICRR endorses the following lessons (summarized and reworded from the ICR, p. 22): The ODL can be a rapidway of improving availability of teachers in rural or remote areas, but the approach should be comprehensive to achieve thisobjective, including provision for ateacher wage bill for recruitment and deployment, and a functioning personnel managementsystem to ensure that teachers are recruited and deployed to areas where there are shortages to achieve desired pupil:teacherratios. Although thenet enrollment rateandprimary completion rateare usual measuresof project outcomes, they may not work in situations where age-specific data for the school-going population is not readilyavailable. This underscores the importance of careful consideration of data quality and collection modalities while determiningoutcome indicators.In addition, this ICRR notes that a key lesson is to implement evaluations in a timely way tounderstand whether and how investments in relatively new and innovative interventions contribute to desired outcomes. In thecase of this project, two interventions were new ODL and student bursary packages but neither was evaluatedrigorously in a timely manner to assess the effectiveness of these interventions or to take stock of implementationchallenges.
P114859 | Lesotho Health Sector Performance Enhancement | Eastern and Southern Africa | Lesotho | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/772681592584581770/text/Lesotho-LS-Health-Sector-Performance-Enhancement.txt | http://documents.worldbank.org/curated/en/772681592584581770/pdf/Lesotho-LS-Health-Sector-Performance-Enhancement.pdf | The ICR (pp. 37-38) contained several insightful lessons,four of which are summarized here byIEG: Piloting and phased implementation of PBF projects is good practice. In thiscase, the experience of the two pilot districts allowed for smoother implementation and scale-up in subsequentdistricts. The absence of PBF budget items in MOH and other sector budgets is a risk for sustainability of thebenefits of PBF-like interventions. In this case, PBF is not yet institutionalized in government budget and accountingsystems, posing a risk to the projects development outcomes. Early staffing of key positions is essentialfor quick start-up. In this case, there were delays in getting the project up to speed due to low or no staffing in keyareas: the PPTA, the MOH PBF Unit, and key FM staff. PBF is facilitated by concurrent health system strengtheningin human resources and drug supply management, as was undertaken by the project.
P114863 | Community Nutrition Project | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Human Development | Health, Nutrition & Population | SPF | IPF | 2010 | 2014 | 2015 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/303241474941547114/text/000012394-20150309080317.txt | http://documents.worldbank.org/curated/en/303241474941547114/pdf/000012394-20150309080317.pdf | The ICR offers 17 lessons (p.20-22). IEG provides additional observations on some of these lessons:Involving HC staff in in paying cash transfers affects their workload and may hamper service provision (e.g., increased waiting time per unit service delivery time). It would be more efficient to use a third party payor for cash payments to women under the CCT.It is possible to build institutional capacity even in weak capacity settings. An institutional capacity and readiness assessment during the preparation stage could have strengthened readiness conditions for complex initiatives being piloted for the first time. Effective project management requires early proactivity, including undertaking necessary restructuring to respond to on-ground realities and align project activities, timelines, resources to address implementation and other challenges.IEG offers two additional lessons for future iterations of the projectA complete theory of change can greatly aid in both the design of the project and the metrics and and PDO indicators used to measure its progress. Paying particular attention to the assumptions implicit in a CCT for health can help the project be better planned and executed. Impact evaluations can be powerful tools, but they must be adequately planned for.
P114866 | Secondary Educ. Development Program II | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2010 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/961201513785227703/text/ICRR-Disclosable-P114866-12-20-2017-1513785220198.txt | http://documents.worldbank.org/curated/en/961201513785227703/pdf/ICRR-Disclosable-P114866-12-20-2017-1513785220198.pdf | The ICR (p. 29) provides useful lessons learned: A results-based approach can bebeneficial in a decentralized context to ensure an alignment of incentives between the national and local levels with a strongemphasis on accountability. In this project, communication and coordination issues between implementing partners atdifferent government levels led to implementation challenges and a focus on inputs/outputs rather than onresults. Ensuring sufficient technical capacity for implementation and clear definition of roles of staff indifferent implementing agencies at the outset is critical to avoiding implementation delays. This project experiencedimplementation delays from the beginning due to the need to hire key staff and due to the lack of clarity between different roles.Ensuring that key staff is already being put in place during project preparation, and formalizing implementing arrangements withclear accountabilities during project implementation, will have a positive impact on project implementation.
P114910 | El Salvador Public Finance and Social Sector DPL | Latin America and Caribbean | El Salvador | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2009 | 2011 | 2012 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/226701474491496313/text/000020051-20140625080143.txt | http://documents.worldbank.org/curated/en/226701474491496313/pdf/000020051-20140625080143.pdf | There are a number of general conclusions going beyond this particular operation. First of all, extensive work on consultation and consensus-building throughout an operation can pay large dividends in removing blockages to difficult reforms. In particular, in countries where there is a possible change of government, it is important that the opposition be consulted, and that they agree to support the changes supported by a DPL. Secondly, a two tranche operation may be appropriate when there is a possibility of a change in government during implementation. It helps to reinforce a possible new Government's commitment to the reforms, while avoiding the costs of approving a second operation. Finally, the productive use of DPLs is enhanced when there is complementary analytical work, technical assistance, and well-coordinated assistance from other partners.
P114931 | Land Husbandry, Water Harvesting and Hillside Irrigation | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2010 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/715891556892378988/text/Rwanda-RW-Land-Husband-Water-Harvest-Hill-Irrig.txt | http://documents.worldbank.org/curated/en/715891556892378988/pdf/Rwanda-RW-Land-Husband-Water-Harvest-Hill-Irrig.pdf | 1. A major extension of a projects implementation period might be appropriate if the extension is forstrategic reasons, is expected to be economically viable, is adequately resourced. and is practically implemented.Theunusual step of doubling the project period was: to maintain the momentum of the field development program, which wasstillacquiring experience, to facilitate the involvement offinancing partners in Rwandas sector-wide agriculturaldevelopment program; and, to further consolidate institutional links. An alternative would have been a new project providingopportunity for a fresh look at the development program, but the LWHs extended program was effectively implemented,contributing to the broader and longer-term goals of Rwandas rural developmentprogram.2. Success with a long-term project extension is facilitated by a clear strategyand technical features.Amongst the factors driving the success of the projects additional 4 yearprogram were: the extension benefitted from the experience of LWHs first four years; technical and institutionalfeatures were already tested and remained largely the same; Government and the Bank were dedicated to a sector-wide ruraldevelopment program; and other donors were willing to support LWHs program without variance in project implementationfeatures, including combining their funds with the Bank into a common financingbasket.3. Monitoring should place particular focus on monitoring the outcomes of thedevelopment objectives.For assessing the outcome of the commercialization objective, the only direct measure ofoutcome was the share of commercialized products as a percentage of total farm production. It would have beendesirable to know how commercialization was defined, how it was measured, what commercialization activities were most viable, andwhat particular crops and marketing or processing activities were involved. Other supporting evidence. proxy data,oradditional monitorable indicators, would also have been desirable.4. A flexibleapproach in the proportion of different components and activities in rural development projects provides scope for enhancingoutcomes.LWHs field development program was adjusted during project implementation to increase the proportionof the land husbandry activities, thereby reducing the proportion of the larger irrigation schemes, which provided lower returnsand were more difficult for farmers to manage. Local conditions were taken as the determining factor for developing eachwatershed.
P114937 | Economic Governance Reform Grant - DPG 2 | Western and Central Africa | Guinea-Bissau | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2011 | 2013 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/812781474508225175/text/000020051-20140625082751.txt | http://documents.worldbank.org/curated/en/812781474508225175/pdf/000020051-20140625082751.pdf | There are three main lessons that can be drawn from the experience of this project:Even in a difficult environment characterized by political instability and weak capacity, progress can be achieved by focusing policy lending on a few actions that are in line with the countryâ€™s own priority, politically feasible and technically ready thanks to a sufficient body of knowledge built through analytical work and technical assistance.Monitoring and evaluation should rely on predictable funding, possibly from the Bank through parallel operations or the use of trust funds. The M&E performance was negatively affected by the design choice of not creating new M&E systems and relying on the existing PRSP process or studies like the PEFA updates funded by other donors. In practice, the principle of avoiding duplication of efforts should be accompanied by an assessment on whether the need improvements or funding is likely to materialize within the program timeframe and by the preparation alternative measures in case either or both would fail to materialize.Not all risks can be managed by the Bank, in particular those concerning political instability. It is nevertheless clear that any progress will depend on the ability of the donor community to properly address the dominance of the military in the countryâ€™s history since independence and the infiltration of drug cartels in the countryâ€™s economic and political life. Without addressing the root causes of political instability, any progress achieved could remain essentially fragile.
P114949 | Zambia Water Resources Development Project | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=25 million & <50 million | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/712211582563576867/text/Zambia-ZM-Water-Resources-Development.txt | http://documents.worldbank.org/curated/en/712211582563576867/pdf/Zambia-ZM-Water-Resources-Development.pdf | The ICR draws the following main lessons that are presented here with some adaptation of language:1. A sharedunderstanding between the government and the bank is especially required for a project designed as a frameworkproject.Mostactivities in this project were subject to substantial delaysdue to the inadequateunderstanding of the implementing agencies regardingtheBankssafeguards and fiduciary requirements. Further,to support effective implementation of framework projectsin a context of weak implementation capacity, it would be help tolay out clear milestones atthe start through the use of disbursement triggers. For instance, a list of investments inaccordance with clear prioritization criteria could be a first-year milestone and as a disbursement condition in the FinancingAgreement.2. Involvement and better clarification of the roles of other ministries can be helpful insecuring project ownership in projects where many ministries are involved. Many of the projects outputs andoutcomes in this projectsuch as ancillary infrastructure of the small-scale infrastructurewere linked to otherministries such as agriculture, fisheries and forestry. Bettercollaboration would have helped in clarifying the roles andresponsibilities of the ministries.3. Projects implemented in vast geographical areas couldbenefitfrom regular supervision by local consultants. Theactivities in this project were spread over ageographically vast area. The logistics of supervision by a single consultant proved to be very challenging. To mitigate the risksand manage the complexity, the project could have been strengthened with local consultants visiting the sites regularly andproviding guidance to the Project Management Team.
P114963 | Caribbean Regional Communications Infrastructure Program | Latin America and Caribbean | Caribbean |  |  | Digital | Digital Development | IDA | IPF | 2012 | 2021 | 2023 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099145008222251270/text/P1149630c92f8e0570865105103a01d626b.txt | http://documents.worldbank.org/curated/en/099145008222251270/pdf/P1149630c92f8e0570865105103a01d626b.pdf | The ICR draws the following main lessons from implementing this project, with some adaptation of language.1. Anassessment of the technical and institutional challenges that are likely to be encountered in regional projects can help inreducing delays during implementation, especially in countries with low capacities. The experience of this project showedthat while there are potential cost savings associated with a pooled procurement approach, the risk is high that economic benefitsmay be foregone in trying to harmonize legal and regulatory frameworks during implementation.2. Developing aregional approach to digital development may require long-term engagement and extended project timelines.While theargument to adopt a regional approach has merits in small states, the experience of this project showed that in low capacityenvironments, engagement may require technical assistance, technical and implementation capacity building and financing to continueoperations over a prolonged time period.3. Identifying a strong regional champion can be particularlyhelpful in projects of a regional nature. The experience of this project showed that while the regional grant to theCaribbean Telecommunications Union (CTU) was small in terms of the financial amount, it was still critical to enable regionalcoordination and discussions at the regional and at the local levels.
P114971 | PY Energy Sector Strengthening Project | Latin America and Caribbean | Paraguay | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2011 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/144041577727068940/text/Paraguay-PY-Energy-Sector-Strengthening-Project.txt | http://documents.worldbank.org/curated/en/144041577727068940/pdf/Paraguay-PY-Energy-Sector-Strengthening-Project.pdf | First lesson was selected from the ICR with some adaptation of language. Second lesson was derived from theICR.If internal approval processes necessary for project effectiveness and the legal framework under which theproject implementing agency will execute the project are not fully taken into consideration and incorporated into project design,project implementation can face serious delays and require a closer supervision by the World Bank project team. Theproject became effective 14 months after it was approved by the World Bank Board, because a law had to be passed by the parliamentin Paraguay. Furthermore, being a government institution, but not a state-owned economic enterprise, ANDE had complex andcumbersome operational and financial processes. This manifested itself in slow processing of contracts and inadequate monitoring ofproject activities, including safeguard policies. As a result, the World Bank project team had to supervise the projectimplementation more closely than such a project would require with a more flexible and agile project implementing agencyexperienced in executing projects according to the relevant World Bank guidelines.Proactivity of the projectteam in revisingthe results frameworkbased on the findings during early stages of projectimplementationwillhelp better capture the achievement of the project objectives.In this project, theoriginal results framework included indicators which were not directly related to the achievement of the projectobjectives. Furthermore, other indicators were designed to measure the system wide changes, not the changes caused by projectintervention. Also, baseline figures and targetsfor some indicators needed to be revised to capture the full impact of theproject.The restructuring resulted insome indicatorsbeing dropped, othersbeing revised and newonesbeing added, reflecting different and better measures of the projects achievement. After the revision, these indicators were betterable to encompass outcomes related to the first and the second objectives (though, unfortunately, for thethird objective, no new PDOindicator was introduced to capture improvements in the performance of ANDE)
P114987 | Rapid Employment Project | East Asia and Pacific | Solomon Islands | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2010 | 2019 | 2020 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/415421566829960480/text/Solomon-Islands-SB-Rapid-Employment-Project.txt | http://documents.worldbank.org/curated/en/415421566829960480/pdf/Solomon-Islands-SB-Rapid-Employment-Project.pdf | The ICR (pages 28-30) draws the following main lessons from implementing this project, with some adaptation oflanguage.(1) A workfare approach can be an effective rapid response mechanism toemergencysituations. This project demonstrated the ability to generate quick and visible results that benefittedthemost vulnerable in the short run but eventually thewhole community,by shiftingfrom an emergency responsemechanism to a more development-oriented approach aimed at improving service delivery in urbanareas.(2) Combiningpre-employment training and real work experience can providetangiblebenefits in terms of income and higher propensity to enter the labor market. The feedback on this project from annualsurveys indicated thatthe project aided in developing beneficiaries skills for entering thelabormarket.(3)Although the strategies for encouraging participation of women and youth wassuccessful,disaggregation of data could have helped in exploring the remaining socio-cultural barriers to genderdifferences.Although the project achieved its targets for participation of women and youth,socio-culturalfactors precludedequal access to benefits for women following the project. For instance, the surveys indicated that more maleparticipants believed that the rapid employment scheme was useful for accessing further employment as compared to females.Disaggregation of data could have helpedto explore whethercapacity building activities would by themselves be enoughfor addressing severe structural obstacles for greater participation by women in the labor market.
P114991 | Hungary - Financial Sector and Macro Stability Loan (DPL) | Europe and Central Asia | Hungary |  | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2010 | 2011 | 2012 | ICRR | Less than 10 million |  | Moderately Unsatisfactory |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/318371474591999221/text/000020051-20140625061759.txt | http://documents.worldbank.org/curated/en/318371474591999221/pdf/000020051-20140625061759.pdf | The Bank needs to have clearly documented policies regarding access to and costs of borrowing, especially for higher income borrowers where access and graduation from IBRD borrower status may be an issue.
P115052 | Third National Program for Community Empowerment in Rural Areas (PNPM-Rural | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2010 | 2013 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/653551475783228388/text/000180307-20150108103559.txt | http://documents.worldbank.org/curated/en/653551475783228388/pdf/000180307-20150108103559.pdf | The following lessons are taken from the ICR with some adaptation of language:Capacity building of an implementing agency responsible for a nationwide Community-Driven Development (CDD) program requires substantial time and effort. The capacity building exercise would include clear definition of roles and responsibilities within various departments of the implementing agency, and would focus on: (a) improving oversight of fiduciary compliance; and (b) ensuring, through training, more effective procurement procedures.A robust Management Information System (MIS) is essential for a nationwide Community-Driven Development (CDD) program. If the same system as in preceding operations is to be used, identified shortcomings should be addressed in the development of the new MIS. Project preparation should strategically plan for addressing the shortcomings in the MIS to ensure effective implementation and gather lessons from the experience.Pre-financing of block grants by Government can be effective, but procedures for non-compliance should be agreed in the Loan Agreement to prevent delays in disbursement from both central and local government.The quality of facilitators is one of the main drivers of community-based project implementation quality. For this reason, procedural guidelines for recruitment, selection, mobilization, and performance evaluation of community facilitators and national/regional management consultants should be incorporated in the Loan Agreement. Procedures would include regulations for use of designated budgets and performance indicators to monitor the carried out action.
P115067 | Support to Oportunidades Project | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2009 | 2014 | 2015 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | High | http://documents.worldbank.org/curated/en/712471475113583168/text/000020051-20150113010716.txt | http://documents.worldbank.org/curated/en/712471475113583168/pdf/000020051-20150113010716.pdf | The following lessons are drawn from the ICR:Lessons with respect to CCTs (abridged):In a time of crisis, CCTs in place can be scaled up in terms of coverage or generosity, ensuring targeted, pro-poor support. However, they are limited to households with children, and other mechanisms may also be needed, depending on the poverty profile of the country.CCT programs cannot be thought of in isolation from other social policies, and achieving human capital accumulation goals will require adaptation of the supply of social services (coverage and quality).A shift in vision from a program to a systemic approach can enhance efficiency and effectiveness of the program, but also requires strong institutional leadership, and commitment from all actors involved.A rigorous evaluation agenda provides legitimacy and support for CCT programs as well as the evidence base to introduce changes in program operation that can improve outcomes. This evidence base is especially important in the context of the need to build stronger links with other social programs.Lessons with respect to Bank assistance:Timely, focused, technical assistance can help a project not only respond to crisis, but can also be an opportunity to undertake reforms. In Oportunidades, technical assistance was used to improve operational design for a second generation of Oportunidades.Working closely with development partners and institutions, such as the IADB, while challenging and time-consuming, can leverage the impact of the avice that is being provided.The choice to use a Sector Investment Loan (SIL) instead of Development Policy Lending (DPL) can facilitate being more engaged in the operational details.
P115102 | Third Infrastructure Development Policy Loan | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2010 | 2010 | 2014 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/835061474576042640/text/000020051-20140625184514.txt | http://documents.worldbank.org/curated/en/835061474576042640/pdf/000020051-20140625184514.pdf | The ICR lists several lessons including the need to link performance indicators to development objectives through a results framework. In addition, there are lessons on how to retaining the focus on the overall objectives: with so many indicators, not all equally important, progress on some inputs and the urgent need to specify "prior actions" for the next loan give an illusion of progress.One additional lesson is the need for a thorough a mid-term review that takes stock of any progress, and alerts senior officials in government on what remains for the objectives to be attained. If an important issue was overlooked initially, or framed poorly (e.g. regressive subsidies instead of how to de-politicize electricity pricing), a mid-term review could have introduced it as a prior action for the loan that followed. A series of programmatic loans require mid-course corrections, and subsequent loans should not proceed on autopilot with perfunctory approvals.
P115109 | Access to Finance for Small and Medium Enterprises | Europe and Central Asia | Armenia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2009 | 2013 | 2014 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/442051474939124681/text/000020051-20140626115900.txt | http://documents.worldbank.org/curated/en/442051474939124681/pdf/000020051-20140626115900.pdf | There are four main lessons that can be drawn from the experience of this project:As noted in the ICR, onerous safeguard and fiduciary requirements slow down project implementation. Designing information requirements to minimize compliance costs, while serving the safeguard objectives, would help ensure successful implementation. Concerning procurement, requirements for competitive bidding should be kept realistic and the eligibility of the purchase of used equipment reconsidered.A weak causal chain in project design can damage the performance of otherwise successful projects. Increasing access to credit by SMEs is a means to an end, not an end in itself. From the limited evidence available, it is highly likely that the project had a positive impact on higher-level objectives, but this could not be proved. The learning potential of projects should always be realized, provided costs are reasonable. The impact of the project on value added, employment and taxes could have been measured and important lessons could have been learned. Project implementation capacity is organization-specific, and should therefore always be built as part of the project unless there is prior experience with Bank project management. GAF had a strong experience in managing KfW projects whose rules are different from the Bank. Capacity building on Bank rules and procedures should have been carried out during project start-up and included in project design.
P115120 | Second Programmatic Fiscal Mgmt and Competitiveness Development Supplemental Financing | Latin America and Caribbean | Peru | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2009 | 2015 | 2017 | PPAR |  | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/725661488828202108/text/110742-PPAR-PUBLIC.txt | http://documents.worldbank.org/curated/en/725661488828202108/pdf/110742-PPAR-PUBLIC.pdf | 6. Lessons 6.1 The experience of this DPL series highlights what can be expected from the World Bank's engagement with a well-performing middle-income country. 6.2 A programmatic DPL series is a powerful tool for supporting long-term reforms. When a strong ownership of the client is demonstrated, a programmatic series of operations can offer the World Bank and its client win-win solutions. For the World Bank, a multiyear program of support gives it a chance to pursue an extended and coherent analytical agenda that may not be feasible in multiple one-off operations. To the client, the programmatic series offers a real-time opportunity to engage with the reforms (including both the costs and benefits) and to make adjustments along the way. In the case of Peru, the government was able to advance its investment climate agenda early on and to learn about the need for deeper and longer-term challenges of upgrading the quality its workforce and technologies. The successive rounds of ever deeper reforms on trade and competitiveness, while incomplete and not implemented with maximum efficacy, would have been difficult to accomplish through separate operations, which are invariably interrupted by changes of priorities and political mandates. 6.3 World Bank supervision of the implementation of these operations should cover all aspects of the program to take full advantage of the learning opportunities offered by a programmatic series. It should pay greater attention to not only emerging risks during the period of program implementation, but also factors affecting the sustainability of the achievements in long-term policy reforms. In the case of Peru, supervision of the core program seemingly focused only on a few development objectives and outcomes, and left unattended a complete pillar of reforms. No explanation is given for this in any of the Implementation Status and Results Reports. This may have resulted in issues not being identified and therefore not addressed, in time leading to less progress than expected or reversal of outcomes achieved. It limited the ability of the World Bank and other stakeholders to fully understand and learn from the experience of this DPL series. 6.4 Reforms move to subnational levels, though their implementation may pose a challenge depending on the framework of fiscal decentralization. Despite all the positive steps that the government had taken to enhance efficiency in the allocation of fiscal resources, there remains a pressing need to rationalize the fiduciary and regulatory norms and the multiplicity of control and auditing instances. According to MEF officials interviewed for this evaluation, these have proliferated and seem to be driving a wedge between the central and regional governments' capacity to focus on results rather than procedures, a central objective of results-based budget management. Another area of clear priority is for the government to continue to place strong emphasis at the central and subnational levels on a robust and rigorously appraised public investment program, and enhance its assistance to subnational governments in identifying, designing, and implementing their own programs, particularly in meeting infrastructure deficits (for example, roads, water and sanitation). To do so, the government should consider placing greater emphasis on subnational tax revenue collection and more efficient distribution of fiscal transfers to subnational governments, areas that proved somewhat lagging during the implementation period of this DPL series. 6.5 The application of the DDO in this DPL series illustrated the World Bank's willingness and ability to support Peru at the time of the global financial crisis. It also showed the extent to which the World Bank's new arsenal of financing instruments was able to respond to the needs of middle-income countries where both the volume and the timing of financing are important for risk management purposes. As a tool for risk management, the DDO gives clients access to a large line of credit that is affordable and fast disbursing, which helps maintain the confidence of investors and deter the resolve of speculators. As a debt management tool, the DDO offers the government an insurance policy on its debt-service and priority expenditure commitments without raising the level of external debt in advance. The discretion to call on the World Bank loan in the amount it needs when it needs to allows the government to optimize its debt structure. Moreover, by extending the loan period by up to six years and not requiring the client to draw down the loan, the DDO facilitates World Bank engagement with clients who do not need World Bank financing but value its formal and sustained support for their policy reforms. This is particularly valuable for engaging with well-performing middle-income countries. 6.6 Yet, the present example also illustrates possible tensions between the independent selection of IBRD-financing terms and the monitoring of the World Bank's development effectiveness. In this DPL series, the DDOs were requested and approved for risk management and crisis response purposes, but this important development objective, for which two large loans were granted in record time, was not tracked. Although monitoring of the macroeconomic framework and program implementation continued until closure of the DDOs, the depth of supervision was restricted to verification of preconditions for drawdown, as required for all DDOs, and did not try to capture the effectiveness of the loans for all their development objectives. This raises a question as to whether overall program design or continued periodic supervision should attempt to explicitly include indicators of risk management and crisis containment, to capture overall development impact of the DPL series. As this practice was repeated in multiple DPL series in Peru (and elsewhere), a substantial amount of World Bank resources is at stake. 6.7 A parallel issue is that with its longer drawdown period and its renewal feature, the implementation period of a DPL-DDO extends beyond the program implementation period of a normal DPL, which has consequences on the expected outcomes. This calls for attention especially in situations where the DDO was added to an ongoing DPL series, such as in Peru, which had a set of coherent, noncrisis-related policy objectives and a predetermined program period that did not (and could not) anticipate the additional crisisrelated objective and the extended program implementation period. The World Bank's DDO guidelines only require the monitoring of macroeconomic stability and the continued implementation of the program. Questions can thus be raised on whether there should be any more detailed supervision or scope for review of the overall program at the time of a DDO's approval and renewal or readjustment of the IBRD-financing terms with regard to repayment options as the country's debt management profile may have altered. Notwithstanding, the trade-off relative to the flexibility of the loan instrument is also important. These issues merit further debate.
P115143 | Financial Rehabilitation Development Policy Loan 1 | Europe and Central Asia | Ukraine | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2010 | 2010 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/803981474637068014/text/000020051-20140625193606.txt | http://documents.worldbank.org/curated/en/803981474637068014/pdf/000020051-20140625193606.pdf | IEG agrees with the ICR that it would have been useful to include outcome indicators that would allow for a more objective assessment of performance in the short term. Specifically, it would have been useful to have allowed for the possibility of assessing progress in a short span to properly supervise the project and evaluate its impact. Those indicators could have also been usefully linked to more quantitative benchmarks, with appropriate baselines and more clearly specified time line for implementation.IEG agrees with the lesson given in the ICR that it is important to maintain a policy dialogue in support of longer-term strategic goals, even in a difficult political environment. However, the Bank should have waited until there was a credible government before proceeding with the programmatic series. With the benefit of hindsight, it is clear that the outcomes of the PFRLs are less likely to be sustained and a second round of restructuring of the banking sector is in the offing. The risk of failures was already high due to the poor governance in the financial sector. It is also essential to have clear agreed and measurable outcome indicators for such operation to ensure its success.
P115145 | Public Finance and Social Sector Development Policy Loan | Latin America and Caribbean | Dominican Republic | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2011 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/185271475091976136/text/000020051-20140624214216.txt | http://documents.worldbank.org/curated/en/185271475091976136/pdf/000020051-20140624214216.pdf | The lessons cited in the ICR are mostly supported: the need for flexibility in times of crisis, while using the crisis as an opportunity for reform, closely aligning with the Government's reform program to ensure commitment, fostering inter-agency coordination, and maintaining good supervision. IEG questions one of the ICR lessons: that outcome indicators should be within the executive control of the agency to which the policy action corresponds. While such indicators will generally be the easiest to achieve, there will be some areas where results can only be achieved through close inter-agency coordination. The Bank should not shy away from such more challenging reforms.
P115173 | Public Finance and Competitiveness Development Policy Loan with Deferred Drawdown Option | Latin America and Caribbean | Costa Rica | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2009 | 2011 | 2012 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/764911475101377095/text/000020051-20140624201303.txt | http://documents.worldbank.org/curated/en/764911475101377095/pdf/000020051-20140624201303.pdf | IEG broadly concurs with the lessons noted in the ICRR, in particular, the lessons pertaining to the importance of government commitment/ownership of the reform program and keeping the reform program well defined and focused to enhance the prospects for positive results.
P115177 | Protecting the Poor under Global Uncertainty Development Policy Loan | Latin America and Caribbean | Panama | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2009 | 2010 | 2011 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/739761475100415016/text/000020051-20140624190619.txt | http://documents.worldbank.org/curated/en/739761475100415016/pdf/000020051-20140624190619.pdf | IEG concurs with the lessons drawn from this operation (the Bank should not in a crisis budget support situation limit its interventions to areas where the Bank has an ongoing operation, the design of a one tranche DPL that spans administrations should seek to minimize the risk to the delivery of results). With regard to the latter, the ICR recommends a results framework that is independent of or robust with regard to the decisions of an incoming administration. In practice, that may be quite confining depending upon timing since it may limit sharply the period for implementation and raises serious issues about sustainability of any achievements. An alternative that may be less confining if achievable would be to seek consensus and commitment among contesting parties on both objectives and implementation targets. At the very least, the Bank might examine the campaign promises of credible contesting parties and avoid areas where promises have been made that run directly counter (as did the cash for elderly program promised by the party that ultimately won the 2009 election) to program objectives.
P115183 | Argentina Basic Protection Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2009 | 2016 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/802251497633273782/text/ICRR-Disclosable-P115183-06-16-2017-1497633264202.txt | http://documents.worldbank.org/curated/en/802251497633273782/pdf/ICRR-Disclosable-P115183-06-16-2017-1497633264202.pdf | The ICR (pp. 20-21) provides several useful lessons, including the following:Complementing aresults-based financing mechanism with traditional technical assistancecan providesupportto critical projectareas. However, during project preparation it isimportant to take into account thatan operations duration islikely to be determined by technical assistance activities, aswas the case in this project.In orderto be able to attributeobserved outcomes to the activities and outputs of the project,aprojectsResultsFrameworkideally includesindicators that measure outcomes that are dependent on the implementation of projectactivities. In thiscase, one of the PDO-level indicators (number of SCE beneficiaries exiting into formalemployment) was influenced by factors outside the projects control,primarily the countryseconomic conditions.
P115183 | Argentina Basic Protection Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2009 | 2016 | 2021 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/824821614092081064/text/Argentina-Basic-Protection-Project.txt | http://documents.worldbank.org/curated/en/824821614092081064/pdf/Argentina-Basic-Protection-Project.pdf | 3. Lessons 3.1 The choice of indicators is critical for incentives to be effective, especially when a short implementation time is expected. But the definition of some of the DLIs and the information used to determine their targets were not discussed in detail at appraisal. The expansion of FA was not included as a DLI. Likewise, the reasons for not including DLIs for the technical assistance component were not discussed, meaning that no attention was given to the mismatch between the time needed for the institutional strengthening and the time needed to comply with the disbursement conditions. The fast pace of disbursement of the original loan (six months) and the low targets set for some of the DLIs call into question the ambitiousness of the DLIs and the projectâ€™s contribution to their achievement. Furthermore, agencies responsible for implementing the actions needed to comply with the DLIs were not the ones receiving the disbursed funds, reducing their incentives to comply. Although this arrangement is common in Program-for-Results operations, the experience with this project confirms that it could be problematic. During the additional financing, interests were not aligned between the Ministry of Finance (which received the funds) and ANSES (which had to comply), leading to implementation delays and compromised results. 3.2 This PPAR had to clarify the understanding of â€œeffectiveness,â€ since the meaning was not explicitly stated in project documents. This absence of a definition calls into question the adequacy of the indicators included in project completion documents and ultimately the efficacy assessment of project objectives. 3.3 Institutional strengthening of the MTESS statistics area was an important additional aspect of the World Bank support, given the peculiar context in which this project was implemented. Yet the project did not have a formal way to capture this aspect in its monitoring framework. Nor were there DLIs associated with the institutional strengthening, despite its importance to achieving project objectives. Indicators associated with this component were focused on the outputs produced (that is, the surveys and the availability of key social protection indicators), not on the use of the information obtained with these surveys or on changes in policies or programs as a result of them. Similarly, there were no indicators reflecting progress on the capacity created within the MTESS to conduct similar surveys in the future. 12 1Plan Jefes y Jefas de Hogares was an emergency workfare program implemented in 2002 after Argentina suffered a severe political and economic crisis. Beneficiaries received a monthly benefit equal to Arg$150 ($50) in exchange for working four to six hours per day in community services and small construction and maintenance activities. Eligible people were unemployed, headed a household, and had children. The number of beneficiaries peaked in 2003 at more than 2 million. Starting in 2005, its beneficiaries were migrated to the other two programs, Familias por la Inclusion Social and the Training and Employment Insurance Program, until the program was discontinued. 2Familias por la Inclusion Social was a conditional cash transfer implemented between 2005 and 2009 to provide income support to vulnerable families. The number of beneficiaries peaked at almost 0.7 million; most were former participants of the Plan Jefes y Jefas de Hogares. Beneficiaries received Arg$200â€“380 per month ($67â€“127) depending on the number of children they had. Benefits were conditional on childrenâ€™s vaccination and schooling. An additional Arg$60 per month ($20) was given to beneficiaries participating in training courses, attending primary or secondary school, or participating in community projects. The program was discontinued in 2009. 3 Created through Decree 1602/09 (IncorporaciÃ³n del Sistema no Contributivo de AsignaciÃ³n Universal por Hijo para la ProtecciÃ³n Social), which modified the Law of Family Allowances (Law No. 24714) to add a noncontributory subsystem, the Universal Child Allowance targets families of unemployed workers without unemployment insurance and informal workers with children under 18. Domestic employees, monotributistas (individuals that pay taxes under a simplified regime), and beneficiaries of other compatible work programs with incomes below the minimum wage are also eligible. Children should be Argentines or have at least three yearsâ€™ residence in Argentina. All qualifying children in the National Social Security Administration databases are automatically enrolled, and eligibility is determined monthly. The allowance is paid to the mother (or, in her absence, to the other parent or guardian) for up to five children. Eighty percent of the transfer is paid monthly, and the remaining 20 percent is withheld to encourage compliance with health and education conditionalities. To receive the withheld portion of the transfer, the parent or guardian must show proof that children ages 5 to 18 years have regular school attendance, a complete or ongoing vaccination schedule in place, and regular health check ups, and that children under five years of age are enrolled in the Sumar program. 4 National Social Security Administration Resolution 393/09, article 10, notes that when childrenâ€™s custody is shared by two parents, the mother is given preference over the father to receive the transfer. 5Proposals were broadly in agreement on the type of benefits to be offered and on the importance of requiring conditionalities. They diverged on how to determine eligibility, how to distribute transfers, what the source of funding would be, and what agency would be in charge of implementation (Repetto, DÃ­az Langou, and Marazzi 2009). 6 Negative outflows are available at US SEC (2019). 13
P115199 | Public Expenditure Support Facility (DPL-DDO) | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2009 | 2011 | 2013 | ICRR | Less than 10 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/284971475099709913/text/000020051-20140625083107.txt | http://documents.worldbank.org/curated/en/284971475099709913/pdf/000020051-20140625083107.pdf | In a short term crisis, the DDO instrument is probably better than a long-term loan, since it offers support without being disbursed. However, should the DDO be disbursed, it can actually serve as a negative factor, indicating government weakness.Triggers for DDO disbursement should be flexible enough to allow for changes in market conditions.The DDO would be a more popular instrument if the commitment did not count 100% against the capital allocation even when it is not drawn.Policy based lending in a crisis requires an on-going program of AAA and/or engagement with the Government prior to the crisis to be thoroughly familiar with policy issues. It is unwise to eliminate AAA programs when countries are no longer borrowing, when there is possibility of a rapid return to borrowing in a crisis.
P115199 | Public Expenditure Support Facility (DPL-DDO) | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2009 | 2011 | 2017 | PPAR | Less than 10 million | Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/117961498483865977/text/110741-PPAR-P160001-PUBLIC.txt | http://documents.worldbank.org/curated/en/117961498483865977/pdf/110741-PPAR-P160001-PUBLIC.pdf | 6. Lessons 6.1 The DPL DDO proved to be an effective instrument to assist Indonesia in responding to financial market turbulence in the aftermath of the 2008 global financial crisis. Indonesia was not facing a balance of payments crisis, its budget was in balance, and it had low levels of public and foreign debt. Yet, the country was threatened with rapidly rising borrowing costs that could potentially trigger self-fulfilling twin currency and debt crises. Sending the right signals to defuse market tension is crucial in such circumstances. Designed as contingent line of credit and streamlined in 2008 to provide greater certainty to borrowers to access the contingent funds, the DPL DDO fulfilled this role well, especially without an IMF program or contingent IMF financing in place. 6.2 In Indonesia, the credibility of the DPL DDO on market confidence was dependent on the government's credibility in maintaining prudent economic policies. Making the drawdown of the DPL DDO funds conditional on market borrowing conditions can strengthen the government's commitment to maintain fiscal discipline despite the crisis, and thus leverage the impact of such operations on investor confidence. Unique among the World Bank's DPL DDO operations, the PESF clearly articulated the disbursement conditions upfront at the government's request.6 The current loan thus illustrates that when the DPL DDO is used strictly for crisis response purposes, it is possible for the World Bank to define drawdown conditions in advance. 6.3 The implementation of the PESF also illustrates that using a crisis response operation to support longer-term structural reforms may require strong client commitment and sustained post-crisis support. As an emergency operation, the PESF's policy program appropriately focused on critical short-term measures targeted at boosting market confidence. While it also included support for long-term reforms, achieving the expected results of these reforms was ultimately beyond the scope and timeframe of the PESF, and depended critically on post-crisis Bank support through the regular DPL series.
P115217 | Maputo Municipal Development Program II (MMDP II) | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/807191519141932483/text/Mozambique-MZ-Maputo-Municipal-Development-Prog-II.txt | http://documents.worldbank.org/curated/en/807191519141932483/pdf/Mozambique-MZ-Maputo-Municipal-Development-Prog-II.pdf | The ICR presented a dozen lessons from this operation. The most important are listed below: A country canuse the opportunity offered by a strategic vision in pursuing sector reform (e.g., municipal development),by an optimal useof an appropriate lending instrument such as an Adaptable Program Loan (APL).In this project, the Government, bothat the national and local levels, committed, through effort and counterpart resources,its largest and capital city Maputo asa laboratory to showcase what a long term engagement (i.e., two phases of five years each), could achieve by sequencinginterventions that engaged its citizens (annual Citizen Report Cards) to strengthen accountability and institutional processes,studies and practical evidence that inform the way forward, deliver improved municipal infrastructure services and mobilizerevenues. Project design benefits from having control over the whole spectrum of infrastructure delivery. For example, anew landfill was evidently needed but because it was funded outside the project, the solid waste component of the project wasdeemed completed even if there were heightened environmental and health risks from the accumulation of waste absent the completionof another disposal siteby project close. In addition,an Integrated Financial Management System (SIGEF), which waspending implementation from the first phase of the APL, and originally was a trigger to proceed to Phase 2 (thisproject) becamea standalone project, which was cancelled in the end. The project required an integrated financial managementcomponent for sustainability so the project came up with alternative modules and a non-computerized solution, which affectssustainability.
P115217 | Maputo Municipal Development Program II (MMDP II) | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2017 | 2020 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/777631588168466281/text/Mozambique-ProMaputo-Maputo-Municipal-Development-Program-MMDP-I-and-II.txt | http://documents.worldbank.org/curated/en/777631588168466281/pdf/Mozambique-ProMaputo-Maputo-Municipal-Development-Program-MMDP-I-and-II.pdf | 3. Lessons 3.1 In low-capacity settings, where cities are barely able to meet service delivery needs, it may be necessary to deliver critical services while incrementally building municipal capacity for sustained service delivery over time. The World Bank's approach in Maputo was appropriately sequenced to support strengthening the capacity of the CCM, especially by helping it to increase tax collection and revenue raising potential. It also helped deliver critical services that simultaneously improved the well-being of the city's citizens, providing opportunities for learning by doing. 3.2 Interventions in land administration require a thorough analysis of the local, institutional, and political economy conditions. Rapid urbanization often requires immediate action, even in contexts of low capacity, poor governance, and dysfunctional land markets. However, given the high risk, a deeper understanding of ways to navigate the complex environment could help shape the interventions, with adequate tools and mitigation measures to achieve sustainable reforms. 3.3 Excessive reliance on external expertise can undermine knowledge transfer and ultimately sustainability in municipal development projects. The World Bank's support to the CCM is instructive\. attempts to mainstream implementation within the structure of CCM in the first phase led to contractual oversight challenges and implementation delays. These delays prompted a switch to a dedicated program management unit in the second phase that relied heavily on international consultants. Although the switch improved project implementation, the hiring of and excessive reliance on external technical consultants, remunerated at a much higher rate than local staff, and the urgent need for the external consultants to focus first on service delivery created tension between the local and international staff. This situation resulted in a lack of knowledge transfer between the two groups. When selecting an approach, good project oversight must be balanced with long-term sustainability by ensuring that adequate capacity is transferred to local staff. 3.4 Achieving outcomes in solid waste management in low-capacity contexts requires a viable financial plan and mechanisms for capital and recurrent expenditures which may include contributions from national and local governments, private partnerships, and user fees. As the World Bank's investments in Maputo show, such a financial plan requires a certain level of public sector support to deliver basic services and to manage and supervise private sector contracts. Also, in such contexts, it is unlikely that the local private sector can fill all service delivery gaps. The project demonstrates that in such contexts, where service delivery needs to be rolled out incrementally, it is unrealistic to expect full cost recovery from the sector's own fees and resources. Rather, a viable financial plan for sustained service delivery requires mechanisms that involve multiple actors (providers and users) across the solid waste management value chain. 3.5 Although achieving universal access to solid waste management is a significant achievement in low-capacity contexts, outcomes are undermined if investment in waste disposal is insufficient, especially for the most vulnerable. The World Bank's support for solid waste management in Maputo lacked a value chain approach\. universal access was achieved but the plan (outside of project financing) to build a sanitary landfill to ensure safe disposal was not achieved. Because the existing dump site in Maputo was already at maximum capacity, this plan was a vital part of the city vision to promote human welfare by improving the solid waste management sector. Waste disposal currently poses significant health and environmental risks to city residents. Risks are also associated with the health problems experienced by the trash-picking community at the site and with the need for alternative livelihoods as part of a resettlement package. A modern sanitary landfill could also contribute to cost recovery by lowering operation and maintenance costs and by producing revenue from biogas generation. 3.6 Land use transformation brought about by infrastructure investments can contribute positively to the local tax base, but it can also negatively affect poorer residents when land and housing prices rise. As shown by the World Bank's support for infrastructure investments in Maputo, land use change (such as that resulting from road and drainage improvements) can stimulate private investment in housing and business development. If systems are in place, new formal housing units can be entered into the land registry and cadastre, and increased property tax collection can strengthen capacity for sustained service delivery. Likewise, business development can have multiplier effects on local job creation and growth. At the same time, an unmanaged process can quickly drive up housing and land prices in a way that forces poorer residents to migrate far from their places of employment or even to unsafe living areas (such as slums).
P115247 | Ghana---Social Opportunities Project | Western and Central Africa | Ghana | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2010 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/813701557759064260/text/Ghana-GH-Social-Opportunities-Project-FY10.txt | http://documents.worldbank.org/curated/en/813701557759064260/pdf/Ghana-GH-Social-Opportunities-Project-FY10.pdf | The ICR (p. 32-33) provided useful lessons, adapted here by IEG:Mainstreaming social protection into national and decentralized structures and identifying roles and responsibilities iscritical to ensure sustainability. While this project made efforts to mainstream social protection into national anddecentralized structures, it lacked a clear transition plan in terms of roles and responsibilities for supervision of activitiesfor the decentralized government to fully take over the program when the project closed. Impactevaluations and studies that are conducted by local academic institutions in cooperation with local governments are more likely tobe implemented. Under this project, the LEAP and LIPW impact evaluations were conducted by the Institute of Socialand Statistical Research at the University of Ghana, allowing for analysis and dissemination of results in a locally comprehensiblemanner that resulted in policy-making in near real time. Introducing strong management tools impactsoutcomes and trustamong beneficiaries. This project designed a MIS for the delivery of payments to LIPWbeneficiariesthat linkedbeneficiaries to banks and other commercial players and allowed for atransition frommanual to electronic systemsfor the LEAP and LIPW programs.
P115261 | HT: Emergency School Reconstruction Project | Latin America and Caribbean | Haiti | IDA | FCS | Human Development | Education | IDA | IPF | 2009 | 2012 | 2013 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/931431475094056091/text/000020051-20140625233617.txt | http://documents.worldbank.org/curated/en/931431475094056091/pdf/000020051-20140625233617.pdf | IEG's interpretation and synthesis of the main lessons presented in the ICR (p. 14) are:Even though a country may be motivated to improve safety, efforts to adopt a safety strategy and standards may lag. It proved difficult to develop a comprehensive Plan for Safer Schools with this project. This failure related to lack of commitment from the Ministry to enact changes. As a result, the Ministry did not exhibit strong leadership, and so the demonstration effects from the project for subsequent school building were blunted. In projects that build schools, the Bank must establish an early review process of the designs to ensure adherence to standards. This implies that the Bank must invest resources into this activity and, by doing so, improve on the local design. It also means that adequate supervisory resources by the Bank, including an architect/engineer, need to be employed to ensure that designs are followed.
P115318 | DRC Street Children Project | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2010 | 2016 | 2016 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/807651468247256120/text/ICRR-Disclosable-P115318-06-09-2016-1465496299261.txt | http://documents.worldbank.org/curated/en/807651468247256120/pdf/ICRR-Disclosable-P115318-06-09-2016-1465496299261.pdf | From the ICR:Establish strategic partnerships to capitalize on learning and strengthengovernment response. Tackling the issue of street children is a relatively new field for the Bank, especially in Africa.By working through experienced NGOs partners, the Bank seized the opportunity to learn about and scale up good practices and helpthe government engage productively with NGOs to jointly develop standards of practice appropriate to the local context whileinforming the design of future Bank projects. In doing so, the project made a long-lasting contribution to thesector.New strategies are required to reach older street children. One of theintermediary indicatortargets that the project did not meet was the number of children who benefited from participation in a vocational training program.This was largely because the age requirement to participate in vocational training is 15 years and very few of the children livingon the street were 15 years and above. The project found that many of the older children, who had once lived in the street, wereliving in group-houses that they had organized themselves and paid for with the earnings they made through their work in thestreet. These youngsters were less inclined to take advantage of drop-in centers, making them more difficult to find andserve. Future projects could link this population group to youth interventions geared toward addressing their specificneeds.Investing in street children prevention could be more effective if coupled with savings and incomegenerating activities. At-risk families are usually poor families. Addressing their needs, either through cashtransfers or micro-level savings-investment opportunities may help to reduce a major obstacle to creating an environment thatencourages greater family cohesion.From IEG:Fiscal and Economic analysis as a basis forchoice of approaches in the future.Even a simple cost analysis could have been informative, for instance inmapping the eventual fiscal costs of the models being explored in the project. Affordability to maintain the mechanisms promotedunder the project should be a major risk in a country with constrained budget resources. Moreover, cost effectiveness orbenefit cost analysis would also have beenuseful, considering the variety of interventions that are advocated in theproject.
P115343 | Fast Track Initiative Catalytic Fund Grant - 3 | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2010 | 2013 | 2015 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/888041475115662523/text/000012394-20150109131438.txt | http://documents.worldbank.org/curated/en/888041475115662523/pdf/000012394-20150109131438.pdf | The ICR (pp. 26-27) presents three generic lessons, summarized here: Low capacity environments may require longer time periods to achieve results. Restricting operations to shorter than needed duration creates incentives to design projects with ex ante expectations of project extensions.It is possible but challenging to transfer implementation from a PMU to an implementing agency with weak capacity. In order to support capacity building as well as project implementation, technical assistance is needed to guide and transfer implementation knowledge and capacity to the agency.Programmatic-like operations provide opportunities for the Bank to learn and improve its operations. Presenting lessons learned does not substitute for fully incorporating these lessons into future operations.
P115347 | School Based Management (APL II) | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2010 | 2014 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/235311467998768893/text/ICRR14738-P115347-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/235311467998768893/pdf/ICRR14738-P115347-Box393183B-PUBLIC.pdf | The ICR (pp. 19-20) contains the following lessons, which IEG fully supports:Evaluating the impact of school autonomy programs on learning outcomes creates considerable methodological challenges in programs where a school's participation is voluntary because of the self-selection bias. Yet it is essential to know whether such programs indeed help achieve the ultimate objective of improving education quality and learning outcomes. Therefore, the design of such evaluations requires careful thought from the outset.Local education authorities play a key role in the implementation of federal programs such as PEC. It is therefore important that state agencies have the capacity to help implement a program and that the technical support extended to them is in line with local capacity needs. States can adequately monitor and evaluate program performance only if they are provided with the means and incentives to properly report the necessary information.Effective program implementation depends on states providing their counterpart contribution on time, and hence measures need to be identified that they do so. Use of country systems for the procurement of consulting services in countries with a strong fiduciary environment, such as Mexico, helps avoid unnecessary implementation delays caused by the application of dual (Bank and country) rules. The potential positive effects of school autonomy can only be fully reaped if capacity at the school level exists to adequately assess school performance and challenges at the school level, if a plan is devised and implemented to effectively address those challenges, and if attention is paid to providing effective training for school managers.
P115351 | Samoa Agriculture Competitiveness Enhancement Project | East Asia and Pacific | Samoa | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2012 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/423691574785717688/text/Samoa-Samoa-Agriculture-Competitiveness-Enhanc.txt | http://documents.worldbank.org/curated/en/423691574785717688/pdf/Samoa-Samoa-Agriculture-Competitiveness-Enhanc.pdf | The ICR offers the following lessons, with some amendment of language by IEG:It is important to ensurethat the project team is closely integrated with the teams from the implementing Ministry and that it is adequatelystaffed. In the case of the Samoa project, the team was too small for the amount of supervision required (ICR p. 31) andthe lack of integration resulted in issues around the ownership for the counterpart ministry;It isimportant to consider local capacity and counterpart capacity in project design and if necessary, budget for supplementalconsultants to assist with implementation. In the case of the Samoa project, the difficulty of attracting and retainingproject staff affected the efficiency of the project and its implementation (ICR p. 37) and there were capacity deficiencies inMinistry of Agriculture and Fisheries staff.It is important that the design of outcome indicators takesinto account data availability and the consistency of data used for monitoring and evaluation. In the case of Samoa,inconsistencies and lack of availability of data hampered implementation, which was not anticipated in project design andnecessitated project staff collecting data from farmers.IEG adds the following lesson:Failure to draw on analytical work by development partners and/or their projects in the same sector can compromiseproject design and the selection of local counterparts. In the case of Samoa, the design of the project needed to betteremploy existing analytical work from all development partners.
P115386 | Nigeria - Public/Private Partnership Program | Western and Central Africa | Nigeria | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2011 | 2018 | 2020 | ICRR | >=25 million & <50 million | Highly Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/908311571764138188/text/Nigeria-Public-Private-Partnership-Program.txt | http://documents.worldbank.org/curated/en/908311571764138188/pdf/Nigeria-Public-Private-Partnership-Program.pdf | Threelessons are drawn from the ICR (pages 34-37), with some adaptation.A coherent legal andregulatory framework is a basic requirement for a PPP program. Among various deficiencies, Nigerias ICRC Act of2005,the countrysoperative PPP legislation at the time of project implementation,lacked: (a)claritywith the mandates of variouspublic authorities operating in the PPP market; (b) a regulatory design governing theidentification, prioritization, and approvalof PPP proposals; and, (c) provisions authorizing the grant of incentives to PPPprojects. At the same time, according to the ICR (pages 53-56), there were conflicts betweenprovisions of theICRCAct of 2005and those of otherlaws and regulations--- the Public Procurement Act of 2007, the FiscalResponsibility Act of 2007, and even the draft ICRC PPP Regulationsof 2017 ---with the legal and regulatory treatmentof various aspects of the PPP program. Anew and comprehensive PPP law that would have addressed these issueswasdeemed politically infeasible bythe Federal Ministry of Finance because of prevailing tensions between the executiveand legislative branches of government.Asound institutional framework and strong institutional capacityare vital to a PPP program. Most institutional frameworks for PPP operations elsewhere globally provide for: (a) acentralized PPP agency that promotes and coordinates PPP activities; (b) a Ministry of Financebody that assessesfiscalcommitments and liabilities; and, (c) line ministries that are responsible for identifying, preparing, and implementing PPPprojects. For this project, the roles of the ICRC, the Federal Ministry of Finance, the Bureau of PublicEnterprise, andvarious other ministries, departments and agencies in the PPP program were not well-defined, either by law, regulation orpolicy. The ICRC,Nigerias regulator of PPPs under the ICRC Act of 2005, was also thedeveloper of PPPs under this project, a conflict-of-interest that the Bank thought would be temporary and remedied withthe passage of a new PPP law. The Bureau of Public Enterprise, responsible for privatizations, construed its mandate toinclude PPPs. The Nigeria Sovereign Investment Authority took on a role as either developer of, or investor in, PPPs.And, the governments line ministries, departments and agencies, responsible for building the PPP pipeline, failed to identifycredible projects,or to move those in the pipeline forward (some projects were withdrawn from the pipeline).A robust pipeline of high-quality projects, drawn from a credible pubic investment management process,is essentialto launch and sustain a PPP program. Nigeria had a thin pipeline of high-quality projects and did not have asystematic public investment management process by which ministries, departments and agencies could propose, develop and seekapproval of high-quality projects. The result, according to the ICR (pages 22-23), was a succession of hastilyconceived and poorly structured PPPs. The four projects that were most advanced in the preparation process followingsupport provided by the project --- the Kuje Water Supply Project, the Kirikiri Lighter Terminal Project, theOnitsha RiverPort Project, and the Silos Project --- could not reach commercial closure by the closing of the six and a half-year project.
P115396 | Public Investment Capacity Building Project | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2009 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/483941493319955965/text/ICRR-Disclosable-P115396-04-27-2017-1493319942149.txt | http://documents.worldbank.org/curated/en/483941493319955965/pdf/ICRR-Disclosable-P115396-04-27-2017-1493319942149.pdf | The ICR draws the following main lessons from implementing this project.(1). A holisticapproach to capacity building through a stand-alone dedicated project can contribute to the success of a project.The case of this project demonstrated that if the government is interested in a holistic targeted approach to capacity building andis willing to borrow for such purposes, such an approach may yield better results than an approach having many smallercapacity-building projects scattered around different projects across the portfolio.(2). While impact evaluationsare important, it is important to select the correct method of evaluation. This project made provisions for someevaluation of training activities through qualitative surveys based on interviews, focus group discussions and questionnaires,which were clearly not sufficient for the scope of the project. It would have been more appropriate to provide forrobustevaluation methods, such as through impact assessments based on randomization techniques.(3).Commitment on the part of both government and development partners can contribute greatly to the success of aproject. In the case of this project, the commitment of both the government and development partners led to targetedconsolidated efforts to tackle problems with the quality and efficiency of investment projects.(4).A short project preparation time could contribute to poor design. This project was prepared in three months fromconcept to approval, to accommodate the governments request. However, rushed preparation time undermined the quality atentry as there was not enough diagnostics of the specific problems faced in the preparation and implementation of infrastructureprojects until then. This in turn affected the choice of indicators.(5). Creation of knowledge materials in thelocal language in addition to English, can help in providing opportunities for self-learning beyond the projectlife. One of the important outputs of the project was the creation of the training web portal, which contained theentire library of training materials throughout project implementation in both English and in Azerbaijani. This made the portal aunique knowledge source to the Azerbaijani public service as well as the wider public for providing opportunities forself-learning, beyond the project life.
P115398 | Cote d'Ivoire - SME Revitalization and Governance Project | Western and Central Africa | Cote d'Ivoire | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2010 | 2015 | 2016 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/591011467995081932/text/ICRR14911-ICRR-PUBLIC-P115398-Box396265B.txt | http://documents.worldbank.org/curated/en/591011467995081932/pdf/ICRR14911-ICRR-PUBLIC-P115398-Box396265B.pdf | The ICR drew four lessons and the two most relevant (with editing) are:Even experienced implementing agencies may have capacity problems. In this project, the implementing agency, a private sector firm, had previously implemented another Bank project. However, lack of capacity in key areas such as project management and M&E led to implementation delays. Fostering public-private dialogue can be beneficial for re-building trust in a post-conflict environment. In this project, strengthening the Government- Private sector Consultation Committee built a basis for future engagement between the government and the private sector.
P115400 | SIR DPL3 | Europe and Central Asia | Bulgaria | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2009 | 2010 | 2011 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/835901475100372628/text/Bulgaria-First-Social-Sectors-Institutional-Reform-Development-Policy-Loan-sir-Dpl1.txt | http://documents.worldbank.org/curated/en/835901475100372628/pdf/Bulgaria-First-Social-Sectors-Institutional-Reform-Development-Policy-Loan-sir-Dpl1.pdf | The lessons arising from the overall series are presented in the ICRR for SIRDPL III, project ID 115400.
P115401 | Energy Small and Medium Size Enterprise | Other | Africa |  |  | Infrastructure | Energy & Extractives | RETF | IPF | 2009 | 2015 | 2016 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/573241473924481093/text/ICRR14938-P115401-Box396299B-PUBLIC.txt | http://documents.worldbank.org/curated/en/573241473924481093/pdf/ICRR14938-P115401-Box396299B-PUBLIC.pdf | Â· The project demonstrates that SMEs, and NGOs like GVEP, can provide cost-effective support to government agencies in implementing energy access programs to benefit hard-to-reach customers. Government agencies do not have a comparative advantage in direct delivery of such programs, for which SMEs, which are lean and nimble and quickly able to respond to changing market conditions, can serve as a more effective implementation vehicleTargeted technical assistance (TA) is a crucial success factor in supporting SME development in the energy sector. Project preparation resources and targeted TA can serve as quasi-project equity to help make energy projects more bankable and move a greater number of well-prepared energy investments forward.
P115414 | NELSAP Regional Agricultural Trade and Productivity TA (Phase II) | Other | Africa |  |  | Sustainable Development | Agriculture and Food | RETF | IPF | 2010 | 2013 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/657691474635717108/text/000020051-20140626115333.txt | http://documents.worldbank.org/curated/en/657691474635717108/pdf/000020051-20140626115333.pdf | The ICR offers a number of lessons of which the following are the most important (with some reformulation of language):Integrating regional projects into country partnership strategies and ensuring linkages between the regional projects and country specific projects is a key factor for success and sustainability. Clear institutional arrangements are needed to ensure uptake and integrate knowledge produced by regional TA projects in the design and supervision of country specific operations. Regional projects with strong technical assistance content that require the participation and engagement of multi-sectoral, multi-country and multi-partner stakeholders would benefit from having a three phased approach and an exit strategy. The three phases would be: Phase I for consensus and awareness building and design. Phase II for project implementation. Phase III for consolidation of the outcomes, post completion operation and transition to next stage. The project design should include a well articulated exit strategy and sufficient time and resources to ensure uptake and sustainable use of the outcomes.
P115426 | Energy Efficiency Development Policy Loan | Europe and Central Asia | Poland | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2011 | 2012 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/211791474586622602/text/000020051-20140626112900.txt | http://documents.worldbank.org/curated/en/211791474586622602/pdf/000020051-20140626112900.pdf | Two lessons stand out from the implementation of this DPL:(i) The time-frame to implement a DPL operation matters, because it determines which kind of policy measures can be completed toward the achievement of identified outcomes. In the case of a single-tranche operation, the scope of outcomes should be scaled down, while a larger scope of outcomes can be envisioned in the case of a programmatic DPLs.(ii) A strong analytical work and sustained policy dialogue with the country authorities have to underpin the design and approval of a DPL. Policy reforms require, among other things, a champion in the government as well as a strong constituency. A successful DPL has to gain adequate insights related to the above from preliminary political economy studies, and a sustained dialogue with the key reformers in the beneficiary country.
P115427 | The Gambia EFA-FTI Catalytic Fund 2009-2011 | Western and Central Africa | Gambia, The | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2010 | 2014 | 2015 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/227871475115915207/text/000180307-20141203061356.txt | http://documents.worldbank.org/curated/en/227871475115915207/pdf/000180307-20141203061356.pdf | Lessons from the ICR, adapted by IEG: In a context where the Bank has a long-standing partnership and sound track record with a Government, there are opportunities both to adopt incremental improvements and to introduce innovative approaches to address identified needs. Enhancing the quality of teacher training programs and providing performance incentives are important measures for improving educational quality.Lessons from IEG: Given the complexity of improving educational results, implementing numerous and disparate activities may not necessarily be an inefficient approach, assuming that each activity can be justified within the framework of a sector-wide approach.
P115436 | NIGER - Niger EFA-FTI Basic Educ Project | Western and Central Africa | Niger | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2010 | 2012 | 2014 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/180301474505074485/text/000020051-20140626000705.txt | http://documents.worldbank.org/curated/en/180301474505074485/pdf/000020051-20140626000705.pdf | The lessons learned section of the ICR (page 32) covers a number of issues relating to community participation and girls' education that have been well known for some time, such as: (a) the need to limit an implementation area when access and costs are high; (b) interventions to improve the attendance of girls require a package that addresses social constraints as well as basic infrastructure; (c) communities need extensive training and coaching to be able to implement self-managed projects; and (d) communication between the Government and communities needs to be good for such systems to work fully. Two further lessons are offered by IEG:It is rarely safe to depend on materials and equipment left by a previous project for implementation of a newer project, as equipment can be faulty and the demands of those using the equipment usually take precedence over any new requirements. Where the Bank acts as an implementing agency for an outside body, there needs to be clarity on project design requirements so that the project is implementable within Bank regulations for financing and evaluation.
P115464 | CAPE VERDE - Recovery and Reform of the Electricity Sector Project | Western and Central Africa | Cabo Verde | Blend | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2012 | 2018 | 2020 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/663301563473159442/text/Cabo-Verde-CV-Recovery-Reform-of-Electricity-Sector.txt | http://documents.worldbank.org/curated/en/663301563473159442/pdf/Cabo-Verde-CV-Recovery-Reform-of-Electricity-Sector.pdf | The first lesson is taken from the ICR with some adaptation of language. The second lesson is derived fromdiscussions with the project team. Government commitment and ownership are criticalto achievingsector reforms and utility restructurings. At the time of appraisal, Cape Verde was faced with an electricity supplyemergency. The governments and ELECTRAs focus was on the construction of the HFO-fired power plants. Therefore, theloss reduction plan and other project activities to reform the electricity sector could not be implemented as planned due to lackof governments and ELECTRAs ownership. During the first three years of project implementation, there was no progressin loss reduction plan. After the government change in 2016, general lack of responsiveness of the energy sector authoritieson implementation issues has slowed down project implementation (ISR dated April 6, 2017, p.2). Despite some momentum gainedtowards the end of project implementation, there was no outcome achieved in loss reduction or sector reform when projectclosed. High institutional capacity of the project implementation unit (PIU) and the sector utility is aprerequisite for successful and smooth implementation of infrastructure development activities. The PIU had experience inWorld Bank projects. The members of staff were knowledgeable about relevant World Bank guidelines. There was no issue in theprocurement of HFO-fired power plant investments. ELECTRA appointed an environmental and social specialist satisfactory to theWorld Bank, and successfully implemented safeguards policies. The HFO-fired generators were commissioned more than one year beforethe original project closing date.
P115486 | LIFELINE ROADS IMPROVEMENT PROJECT | Europe and Central Asia | Armenia | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2009 | 2014 | 2015 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/835131468188953642/text/ICRR14665-P115486-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/835131468188953642/pdf/ICRR14665-P115486-Box393183B-PUBLIC.pdf | .The ICR draws the following lessons:Project readiness could enable quick implementation of civil works and thereby contribute to providing temporary employment and quick economic support to rural areas hit by financial crisis.Incremental improvements can be made during project implementation (such as incorporating road safety features) by adjusting to changing conditions.Road safety audits can be successfully incorporated with road construction and rehabilitation works when there is government ownership. And support for road safety programs can be obtained from communities, which consider road safety a major problem.
P115561 | China HCFC Phase-Out Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | MONT | IPF | 2013 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/709631590527535619/text/China-China-HCFC-Phase-Out-Project.txt | http://documents.worldbank.org/curated/en/709631590527535619/pdf/China-China-HCFC-Phase-Out-Project.pdf | The ICR (p. 36-37) provided several lessons learned which were adapted by IEG: Increasing local capacityto manage and monitor ODS-phase out is essential for achieving sustainable phase-out targets. In this project,strengthening the capacity of local EEBs has supported China in its efforts to monitor the use of HCFC-141b in the consumptionsector by registering foam enterprises consuming HCFC-141b. Increasing access of SMEs to alternative technology,reducing costs and safety risks, and increasing market access of cyclopentane technology can be effective through the participationof system houses in the supply of cyclopentane pre-blended polyol. In this project, the public-private partnership betweenFECO and system houses allowed for the transfer of technical assistance and technology to a large amount of smaller foamenterprises through existing market networks.
P115563 | Uganda Health Systems Strengthening Project | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2010 | 2017 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/390791529937195971/text/Uganda-UG-Health-Syst-Strength-Project-FY10.txt | http://documents.worldbank.org/curated/en/390791529937195971/pdf/Uganda-UG-Health-Syst-Strength-Project-FY10.pdf | The ICR (p. 31-32) provided several lessons and recommendations,including:When a project makes significant investments ininfrastructure and equipment, it is critical that the government provide an adequate budget to cover maintenance and incrementalcosts to ensure the sustainability of such investments. In this case, the MOHhas budgeted for maintenance ofexisting infrastructure and the operation and replacement of equipment. However, since the facilities have recently beenrenovated and the equipment is new, the maintenance costs are generally low. This will change in the future, and an increasein budget to appropriately maintain the investments made under the project will benecessary.Continuity and in-country presence of task team can enhance the quality of support andensure appropriate course correction. In this case, strong supervision, including through independent validation andaudit, helped direct resources effectively toward achievement of intermediate outcome and outcometargets.
P115564 | Save Our Species (SOS) | Other | World |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2011 | 2016 | 2017 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/852941496237980891/text/ICRR-Disclosable-P115564-05-31-2017-1496237973968.txt | http://documents.worldbank.org/curated/en/852941496237980891/pdf/ICRR-Disclosable-P115564-05-31-2017-1496237973968.pdf | Summary of Lessons from the ICR:The ICR suggested that nine lessons could be drawn from the project.Some of these lessons had no or limited basis in terms of evidencein ICR and others were narrowly focused on the project. Thefollowing is a summary of lessons from the ICR that had a general application and were evidencebased: Beneficiaries of programs that rely on self-reporting need to understand they will not be penalizedfor disclosing difficulties and failures. The experience of the SOS Secretariat confirms that, once grantees understoodthat they would not be penalized, beneficiaries were more willing to ask for advice and transparently report lessons learned. Whilenot discussed in the ICR, the lessons stated that the SOS secretariat made concerted efforts at promoting a culture oftransparency, allowing grantees to report failures as long as lessons learned were described. (ICR, page22) The organizations that administer a funding mechanism should be managerially as well as technicallycompetent. As this project shows, governance and management capacity had to be adequate to administer the projectportfolio, and choosing a recipient institution based on technical competence alone was a mistake. The IUCN and SOS Secretariatwere examples of technically sound organizations that needed to build management capacity over the projectperiod. A sound fundraising strategy needs to be diversified and flexible to change as needed. Designingand focusing a strategy on one sector or one donor type is a major challenge. There was no evidence in the ICR that the IUCNor SOS made an assessment of theincentives for potential donors to contribute to financing the cost of conservingspecies.Further lessons identified in thisreview: Self-reporting of results needs to be based on a random sample ofparticipants. An evaluation of information from participants based on a random sample can provide strong evidenceand could have provided substantially better information the less than completeself-reportingprovidedbygrantees.
P115566 | Fifth Power System Development Project | South Asia | India | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2010 | 2019 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/720541615564016314/text/India-IN-POWERGRID-V.txt | http://documents.worldbank.org/curated/en/720541615564016314/pdf/India-IN-POWERGRID-V.pdf | This review has drawn two lessons.Right-of-way (ROW) issues need to be identified and addressed significantlybefore implementation start-up in order to avoid delays that lower the projects economic efficiency and create financialrisks, both of which deter the achievement of the project objective. Almost all schemes financed under the project facedserious ROW issues causing lengthy implementation delays. ROW issues had already started during the implementation of Third PSDP.After the adoption of government guidelines in 2015 that made ROW payments compulsory to landlords, there were some improvements inproject implementation, but ROW issues continued beyond project closing because of delays in states adoption of theseguidelines in their respective jurisdictions or in processing payments. Delays caused by ROW issues resulted in economic rates ofreturn that were lower than the hurdle rate of 12 percent for most of the schemes.When Borrower systems are used,Borrowers need to ensure adequate enforcement of its own safeguard policies and procedures in a manner that also achievescompliance with the requirements of the Banks safeguard policies. In this project, the Bank piloted the Use ofBorrower Systems for environmental and social policies. POWERGRIDs Environmental and Social Policy and Procedures were foundto be acceptable by the Bank, but evidence shows that enforcement of these policies to ensure adequate accommodation facilities andlabor practices for workers was not satisfactory. The camps did not have sufficient beds for workers, some camps lacked adequatewater source or number of restrooms, some did not have separate kitchens and bath areas did not exist.
P115592 | SOCIAL PROTECTION | Latin America and Caribbean | Honduras | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2010 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/913701578682518335/text/Honduras-HN-Social-Protection.txt | http://documents.worldbank.org/curated/en/913701578682518335/pdf/Honduras-HN-Social-Protection.pdf | The ICR (pp. 26-27) offered several lessons and recommendations, including the following lessons restated byIEG:Adopting a collaborative approach with other development partners facilitates the pursuit of commonobjectives.Under the project, IADB was the main partner, and effective collaboration avoided duplication and ensuredfocus on this area of policy that was a priority for the government of Honduras.A thorough understanding of thetrade-offs to be made promotes the balancing process between swift project preparation and ensuring adequate, in-depth analysisthat allows for a realistic assessment of implementation capacity and potential.In this instance the rapidpreparation of the project ensured ownership by the government; however, the relatively light analysis of existing capacityoverlooked challenges in that regard, which ultimately led to bottlenecks and delays in implementation.Securingsupport to the project, notably in the context of political change, is facilitated by evidence generated by impactevaluation.In this case, the results of two impact evaluations conducted under the project helped maintain focus andsupport throughout the project cycle, providing valuable feedback regarding progress, challenges andsuccesses.In addition, IEG identified the following lesson:Adopting a strategic approachthat ensures that a number of conditions are in place, such as appropriate legal framework and political commitment, is necessaryin support of CCT scale up. In this case, some of these conditions were not in place to support the proposed alternativepayment mechanism, and the piloting did not translate to the national level despite its success
P115608 | Mexico Framework for Green Growth Development Policy Loan | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2010 | 2011 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/195541474631308956/text/000020051-20140625055130.txt | http://documents.worldbank.org/curated/en/195541474631308956/pdf/000020051-20140625055130.pdf | Four lessons are drawn, with modification, from the ICR. The fifth lesson is drawn by IEG.1, Extensive dialogue on prior actions and desired objectives is necessary if a technically complex environmental DPL is to be successful. Without continuing substantive dialogue with the client government the enactment of essential reforms could be at risk, particularly if the country is also faced with a serious economic crisis. The implementation of technically sophisticated reforms to promote energy efficiency and renewable energy generation requires the creation of specialized directives and guidelines to enable an appropriate regulatory framework. The implementation of these regulations and policies requires the support of highly qualified specialists.2. Continuing technical dialogue and support from the Bank can lead to unanticipated results that help advance mutual objectives and reduce risk for the government. The adoption by the Borrower of a rigorous safeguard framework, such as that of the Bank, is facilitated by the Bank's commitment to finance an ongoing technical assistance program to the country. .3. Inter-institutional coordination is one key to enabling a successful program. A multi-sector environmental operation requires effective coordination and substantial cooperation among participating agencies. The commitment of a government to a green growth agenda and the leadership of key ministries is essential to establish a successful coordination process and knowledge sharing among the different sectors.4. A continuing monitoring of results indicators is required to identify challenges to compliance with middle-term goals. When medium-term outcomes are targeted after closure of an operation, monitoring their progress is still essential in order to identify problems in their implementation. This requires that the government utilize or create an institutional mechanism to monitor such medium-term targets and indicators as CO2 reductions.5. A clear causal chain between an Operation's outputs and intermediate outcomes on the one hand and its stated development objectives on the other, together with indicators to measure progress in achieving the latter, are necessary to evaluate the Operation's efficacy.
P115634 | Disaster and Climate Risk Management Project | Europe and Central Asia | Moldova | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2017 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/418361498065510127/text/ICRR-Disclosable-P115634-06-21-2017-1498065496323.txt | http://documents.worldbank.org/curated/en/418361498065510127/pdf/ICRR-Disclosable-P115634-06-21-2017-1498065496323.pdf | The top three lessons from the ICR are summarized below (ICR, p. 26 ff.): Integrating capacity-buildingactivities (e.g., strategic, operational, and investment planning) into the design of Institutional management activities mayprovide stability, especially in politically volatile conditions. For example, operation plans couldprovidecontinuitywhen political upheavals result in agency management reshufflings. Assessing if the beneficiary agencyhas in place standard procedures and production processes that would optimize the use of new, modern, state-of-the arthydrometeorological equipment may better inform capacity building interventions. For example, if the beneficiary agency does nothave the standard processes in place, capacity-building investments could be included inthe scope of investment procurementefforts.In addition, maintaining communication with the agency responsible for budgetingoperations and maintenance ofnew equipment (such as the Ministry of Finance) is critical to obtaining adequate resources. Using numerous projectmanagement teams - for fiduciary, compliance purposes, and overall coordination- may be a practical strategy when there areseveral implementing agencies involved in a project. However, clarifying roles, responsibilities, andaccountabilities at thetime of project preparation would address future misconceptions or problem areas.Thisstrategy is even more compellingwhen various management actors are from differingpolitical affiliations.
P115638 | Pakistan: Social Safety Nets Development Policy Credit | South Asia | Pakistan | Blend | Non-FCS | Human Development | Social Protection & Jobs | IDA | DPF | 2010 | 2012 | 2013 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/281131474637101671/text/000020051-20140625224632.txt | http://documents.worldbank.org/curated/en/281131474637101671/pdf/000020051-20140625224632.pdf | These lessons are derived from the ICR (pp. 17-18):Linking a development policy operation to technical assistance or investment operations with a strong emphasis on technical assistance can help ensure that policy reforms are sustained and institutionalized. In this case, the credit provided leverage for the technical assistance project, and the impact of the cancellation of the second tranche of the development policy credit was allayed by the parallel technical assistance loan.Strong Government commitment and political will are essential prerequisites for advancing a safety net reform agenda. In this case, the Government of Pakistan took politically difficult but necessary decisions, including the abandonment of politically based beneficiary identification systems in favor of objective, poverty-based measures.A strong analytical base is important in facilitating rapid introduction of reforms that involve difficult institution-building challenges. In this case, extensive prior analytical work helped to identify and mitigate political and institutional risks before those risks could impact implementation and outcomes.
P115642 | DRC Emergency Project to Mitigate Impact of Financial Crisis | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2009 | 2011 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/693851474908339011/text/000020051-20140624201046.txt | http://documents.worldbank.org/curated/en/693851474908339011/pdf/000020051-20140624201046.pdf | IEG broadly concurs with the lessons outlined in the ICR but would like to highlight the following two in particular:For this type of emergency project, the PCU is an adequate structure as its knowledge of Bank procedures, acquired through implementation of other Bank-financed projects, was critical to fast project implementation. Intensive supervision and fiduciary support is needed particularly for this type post-conflict emergency operation to ensure that the project remains on track and funds are not misappropriated.
P115647 | E-Society and Innovation for Competitiveness (EIC) Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2011 | 2016 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/985761500312732836/text/ICRR-Disclosable-P115647-07-17-2017-1500312717077.txt | http://documents.worldbank.org/curated/en/985761500312732836/pdf/ICRR-Disclosable-P115647-07-17-2017-1500312717077.pdf | Of the four lessons proposed in the ICR, the following were selected for theirgeneralapplicability: Partnerships with local stakeholders enhance sustainability of results and reinforceinstitutional capacity building. Project partnerships with universities, research institutions and industry associationsare conducive to sustaining and even scaling up results post-project (ICR, para 75c). Having regularstaff of ministerial units in charge of implementing core project activities helps anchor institutional strengthening.These are elements of a governance structure conducive to cementing knowledge and keeping it beyond the projects life. Inaddition, using local staff avoids escalation of project management costs for consultants (ICR, para. 75d)Lessonsuggested by IEG The rapidly evolving IT technology calls for flexibility and readiness to restructureproject activities scope and reallocation of funds. In a fast-evolving IT sector, locking in a project to specificcomputer technology or not considering theimpactof project activities and the actionsby private sector partiesoperating in the same field may result in project setbacks or causethe project to becomeredundant.
P115659 | Urban Transport Sector DPL | Middle East and North Africa | Morocco | IBRD | Non-FCS | Infrastructure | Transport | IBRD | DPF | 2011 | 2012 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/940471474631704406/text/000020051-20140625224005.txt | http://documents.worldbank.org/curated/en/940471474631704406/pdf/000020051-20140625224005.pdf | The ICR draws the following lessons from the preparation and implementation of this operation:The support of urban transport sector reform through single tranche DPOs requires a sufficiently long implementation period to carry out and assess the impact of the reforms, and accompanying the operation by appropriate investments and technical assistance. In a complex sector such as urban transport, a series of single tranche DPOs has the advantage of allowing for flexibility in supporting reforms that are implemented at different speeds. Furthermore, they make it easier to adapt and accompany reforms when priorities shift with time. That said, however, goals such as greater sector efficiency are likely to require accompanying investments in infrastructure and equipment, as well as technical assistance to key institutions, both central and local.It is difficult for a DPO, by its nature, to influence decision making at the local level since this depends on many factors, many of them political, which are beyond such an operation's scope. Since urban transport strategies and projects in Morocco are conceived and implemented by local authorities, building capacity there and providing direct incentives for their decision making process, is a necessary complement to a DPO.Reforms requiring inter-ministerial coordination move more slowly than others. In order to achieve a successful implementation of the proposed reforms, it is essential to build consensus among the different stakeholders and ensure smooth cooperation. While awaiting the development of the required institutions to fully assume their intended functions, the Bank has to initially play an important role as a catalyst in fostering program coordination. Given its important policy implications, the timely and successful implementation of the DPO reform program requires continuous support from senior government counterparts. The risks associated with the multiplicity of implementing agencies, and sometimes divergent views regarding the respective roles of the various existing and newly created agencies could be assuaged by strong involvement of senior counterparts on key issues, thus ensuring the progress on reforms during the implementation of the DPO.
P115659 | Urban Transport Sector DPL | Middle East and North Africa | Morocco | IBRD | Non-FCS | Infrastructure | Transport | IBRD | DPF | 2011 | 2012 | 2016 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/632691468304811669/text/106390-ppar-P115659-PUBLIC-morocco-2016.txt | http://documents.worldbank.org/curated/en/632691468304811669/pdf/106390-ppar-P115659-PUBLIC-morocco-2016.pdf | 6. Lessons The UT DPL served as a declencheurâ€”a triggering operation that helped to accelerate much-needed policy reforms, support institutional strengthening priorities within major sector agencies, and implement key measures to unblock the main impediments to improved sector performance. It included selected priority actions that needed to be taken in the short term, within the framework of client-driven reforms, and against a historical baseline in which little or no effort was being made to address mounting UT sector issues. Based on the project's own experience, this section presents the main lessons on the roles of the government, the Bank, and the lending instrument itself, which may be relevant in designing future development policy lending interventions\. Â· For DPLs to achieve results, the broad and early participation of the various implementing agencies and local governments as well as a strong reform momentum by the government, must be in place at entry. Credible government actions to accelerate the implementation of policy reforms are necessary prior to Board approval. There also needs to be evidence of broad participation by multiple implementing agencies and local governments, starting as early as the preparation of the sector and other technical studies that would underpin the design of the DPL. The Bank's dialogue with the main champions within government needs to be broadened early to achieve buy-in and engagement beyond the central counterparts, particularly in urban transport where the executive responsibilities lie with cities. The degree of cooperation achieved among the multiple implementing agencies and through the local authorities was due in large part to the credible process of consultation and stakeholder participation during the UT DPL's preparation and implementation. Â· Flexible and adaptive responses by the government are required to continue pursuing the DPL's objectives when specific actions do not achieve expected results. For example, the CNDU and the AODU lacked the convening power and legitimizing authority expected when they were created by the central government and the local authorities of Greater Casablanca, respectively. In response, the government strengthened and empowered DDUT (under the DGCL of the MOI)â€”originally the technical Secretariat of CNDUâ€”to assume many of the responsibilities of the CNDU itself, which ceased to function. Similarly, when AODU proved unable to assume its assigned roles despite large budgetary outlays, the Greater Casablanca authorities abolished the AODU (in March 2015) and transferred its planning, investment, and management roles to Casa Transports. Â· The Bank's convening authority and intellectual leadership need to support the government's work on consensus building and interagency coordinationâ€”especially at the initial stages of DPLs. During the critical process of selecting and justifying key reform actions, the Bank needs to ensure that the government is building consensus among multiple stakeholders at the national and local levels that may be at widely different stages of readiness (in terms of institutional capacity) and willingness to implement reforms (given the local political economy and its system of incentives). The effectiveness of the Bank's convening power is best served by providing intellectual leadership through evidence-based sector analysis, a strategic dialogue, and a defensible menu of priority actions. Some respondents during the IEG mission have expressed concerns that the Bank's high-value analytical and advisory assistance may be eroding in favor of operationally oriented project preparation work. Â· The Bank has an important role to play in ensuring that all investment options are analyzed, with a view to selecting the least-cost options. As part of its due diligence, the Bank needs to ensure, especially in broad-ranging sector DPLs, that all investment options are appropriately assessed within a sector planning framework, with a view to identifying and selecting the least-cost options. The government has put in place eligibility criteria to incentivize municipal investments and allocate government financial support to those with highest returns. Such prioritization and efficient resource allocation criteria should be applied in comparing tramway expansion with bus rapid transit and other options, in light of overall urban transport needs. For example, as discussed in paragraphs 4.23 and box 4.2 of this report, it would be important to analyze whether spending 40 percent of all urban transport investments on expansion of tram lines would be worthwhile, considering the large number of other road, traffic, and bus-related investment needs in Morocco's other cities. Â· Sector DPLs could be more effective if accompanied by parallel investment lending and technical assistance, or designed as a programmatic series that would expand the implementation time frame to several years. The urban transport sector is inherently very complex, straddling land use, environmental, and social issues, as well as national and local jurisdictions. Reforms can be fully achieved only over the long term, thus requiring step-by-step approaches and a rigorous prioritization of short-term actions that could most effectively lay the groundwork for future reforms. In this context, a short-duration DPL cannot be expected to directly impact decision making at the local level, which depends on political and other factors that are beyond the influence and implementation time frame of DPLs. Capacity building at the local levels can be more readily achieved by investment lending and technical assistance support. Their absence would explain why the UT DPL's second objectiveâ€”to increase the efficiency and supply of urban transport services and infrastructureâ€”was achieved only to a modest extent.
P115664 | Emergency Monrovia Urban Sanitation Project (EMUS) | Western and Central Africa | Liberia | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2010 | 2017 | 2018 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/734831506708143315/text/ICRR-Disclosable-P115664-09-29-2017-1506708134222.txt | http://documents.worldbank.org/curated/en/734831506708143315/pdf/ICRR-Disclosable-P115664-09-29-2017-1506708134222.pdf | The lessons are taken from the ICR with some modification of language: In fragile contexts, a simple andflexible project design may be key to achieving the development objectives. An aim to gradually re-establishinfrastructureand basic services with realistic targets in fragile contexts where these have been interrupted or discontinued maybe a crucial element contributing to achievement of the PDO. The combination of a gradual re-establishment of basic servicescoupled with institutional strengthening activities is key. Engaging the private sector to deliver Solid WasteManagement (SWM) is not a panacea in fragile and conflict-affected contexts. There might be too low capacity also in theprivate sector to manage parts of the SWM value chain. Building capacity in the public sector both to deliver basic services and tomanage and supervise private sector contracts are crucial elements in fragile contexts Achieving financialsustainability for Solid Waste Management in fragile and capacity-constrained contexts requires an incremental, long-term approach.National governments commitment to provide sustained funding to the operation of SWM services in addition tofinding solutions for increased revenue income are crucial building blocks to achieve financial sustainability. Such measures taketime to implement and will need to be done carefully and sensitively Integrating the PIU into the localgovernment has the potential to greatly enhance local capacity. The integration of the EB-trained PIU staff into the localgovernment has the potential to contribute to capacity building and institutional strengthening of localinstitutions. Solid waste data collection through weighbridges coupled with an independent third-party to monitorsolid waste data is important to minimize the risk of fraudulent practices. Continuous and thoroughconsultation and engagement of local communities around landfill sites is a necessity for successful solid wasteoperations. Effective handling of complaints and a solid communications strategy coupled with adequate management oflandfill sites may reduce local resentment with solid waste operations.
P115695 | China: Bayannaoer Water & Environment Comprehensive Management Project | East Asia and Pacific | China | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2011 | 2019 | 2020 | ICRR | >=50 million & <100 million | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/313971582225863535/text/China-CN-Bayannaoer-Water-Env-Comp-Manage.txt | http://documents.worldbank.org/curated/en/313971582225863535/pdf/China-CN-Bayannaoer-Water-Env-Comp-Manage.pdf | The ICR draws the following main lessons with some adaptation of language.1. Projects shouldconsiderflexible designs and implementation approaches to better mitigate macroeconomic risks. This project wasdesigned to mitigate water and environmental problemsfrom coal-led industrial developmentand assumed the continuedgrowth of heavy industries in the municipality. Although macroeconomic risks were recognized at design,the project was unableto overcome the risks due to the changes in macroeconomic conditions.It would have been useful to have considered moreflexible technical designs (such as phasing of investments and scalable facilities) or more flexible financing instruments (such asno-interest credit lines or competitive grants to allow the industrial estates to take risks).2. Projects shouldhave realistic PDOs that are consistent with the results framework. This project had weakness in the design and realism ofthe PDOs. The original and revised PDOs in this project were not clearly defined and were overly ambitious. Future projects shouldcarefully follow Bank guidelines to define realistic and clearly structured PDOs, with clear and logical connection to the projectcomponents, the outcome indicators and the indicator target values. The experience of this project shows that for projects withsimilar flaws, the PDOs and the results framework should be proactively corrected through early restructuring.3.Hard investments in physical infrastructure need to be better aligned with soft investments in policy andinstitutional development to achieve better water and environment management. This project invested hardwastewater treatment and water reclamation infrastructure and encountered risks associated with macroeconomic uncertainty. Futureprojects could more holistically analyze a portfolio of demand management and support political/institutional/managerialinvestments in addition to the hard treatment and reclamation infrastructure optionsto support better water and environmentmanagement.
P115700 | Belarus DPL | Europe and Central Asia | Belarus | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2010 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/504351474566178383/text/000020051-20140625065737.txt | http://documents.worldbank.org/curated/en/504351474566178383/pdf/000020051-20140625065737.pdf | The following lesson comes from the ICR:When the government cannot ensure a suitable macroeconomic framework in the medium term, the medium-term effectiveness of a Bank-supported reform program can be weakened or undone. Moreover, hard prior actions are unlikely to mitigate the risk to a reform program caused by financial indiscipline.When a government lacks sufficient capacity to carry out a broad reform program (e.g., social assistance) this is unlikely to succeed if the Bank does not accompany it with proper technical assistance.
P115709 | Financial Sector DPL, Latvia | Europe and Central Asia | Latvia |  | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2010 | 2010 | 2012 | ICRR | >=100 million | Highly Satisfactory | Highly Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/316021475072573304/text/000020051-20140624200658.txt | http://documents.worldbank.org/curated/en/316021475072573304/pdf/000020051-20140624200658.pdf | There are three important lessons:(i). In cases severe financial distress, developing a program based on strong government ownership is essential. Only in these circumstances can wide-ranging economic and social reforms be defined and implemented. (ii). It is important for the Bank and other donors to invest in close collaboration which has a very large pay-off, especially when programs with a wide-ranging impact need to be developed quickly. (iii). The Bank should evaluate its role in "post-graduation" countries. In this case, some important reforms were initiated under the DPL but could not be implemented, especially, the Action Plan on Financial Consumer Protection, and the development of well-targeted subsidies for mortgage relief.
P115717 | South Sudan Gender Support & Development Project | Eastern and Southern Africa | South Sudan | IDA | FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2010 | 2013 | 2015 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/628121474942003617/text/000012394-20150108103651.txt | http://documents.worldbank.org/curated/en/628121474942003617/pdf/000012394-20150108103651.pdf | The following lessons, emphasizing those that would be applicable in other post-conflict environments, are taken from the ICR with some adaptation of language: 1. In post-conflict settings with extremely weak institutional capacity, continuing post-conflict insecurity and serious accessibility challenges due to the lack of infrastructure, projects should start at small-scale and be gradually scaled-up; experience suggests that nation-wide coverage at project start-up is over-ambitious. Small-scale and a focused set of activities should be prioritized to draw lessons for future expansion of coverage and scope. 2. In a post-conflict setting it is especially important to have realistic timetables for physical construction components. 3. It takes time to build capacity; capacity cannot be built within one two-year project â€“ in any setting, but especially not in a new country where government and donor support is starting with a low level of capacity and with a need for capacity to be cross-sectoral.
P115724 | Basic Education Capacity-Recipient executed | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Human Development | Education | RETF | IPF | 2007 | 2013 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/244241474665107389/text/000020051-20140626113925.txt | http://documents.worldbank.org/curated/en/244241474665107389/pdf/000020051-20140626113925.pdf | Lessons adapted from the ICR (pp. 21-22):The use of large scale longitudinal surveys such as the LGCA provides a good capacity development needs assessment tool to a project.Grant planning, submission and approval, disbursement, and expenditure verification are time-consuming but contribute to a more effective district response to its needs, improved financial management practices, and better transparency and accountability.When decentralized planning and budgeting are envisioned as a means for improving services, they must be accompanied by a clear funds flow mechanism to ensure that there are no delays in implementing the plan.Lessons from IEG: Where a projectâ€™s essential objective is to develop district capacity, the ICR must demonstrate not only what capacity has been developed but also how this occurred and varied across districts.
P115725 | Education TF Support Program BOS-KITA | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Human Development | Education | RETF | IPF | 2009 | 2010 | 2012 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/321141474483436383/text/000020051-20140624192017.txt | http://documents.worldbank.org/curated/en/321141474483436383/pdf/000020051-20140624192017.pdf | 1. Program design must take into account the strong potential for cascade training to distort the training message. Spending more training time at the bottom (where BOS implementation takes place) and less at the top would be more effective. 2. The training in financial management was not conducted in a manner that engaged trainees, since trainings were conducted top-down, did not use real-world practical problems, and used trainers of variable quality. Further, a one-day training session at the school-level was insufficient for meeting the knowledge and skill requirements necessary for school-level BOS management teams to produce integrated school plans, budgets and reports, and use BOS funds effectively.3. High staff turnover at the district level limits the sustainability of training.4. Remote regions were not properly integrated. These regions are more likely to have personnel with low average training (due to remoteness), and therefore in greater need of assistance on managing decentralization.5. Supervision from the top all the way to the bottom is essential as is the availability of training materials and handbook.
P115732 | Latvia First Special Development Policy Loan: Safety Net and Social Sector Reform Program | Europe and Central Asia | Latvia |  | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2010 | 2011 | 2013 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/934861474629254151/text/000020051-20140626103734.txt | http://documents.worldbank.org/curated/en/934861474629254151/pdf/000020051-20140626103734.pdf | Investing in economic and social data analysis in good times and on a regular basis is all the more relevant in a time of crisis. The existence of regular reviews of spending and outcomes in the social sectors allowed the Government to rapidly design a relevant strategy to respond to crisis.Reforming social insurance, especially pensions, during a crisis is very difficult. The reform experience in Latvia has shown that pension expenditures exhibit very high inertia in times of recessions and even extremely reform-minded governments are not able to quickly reduce spending on such programs. Pension spending actually increased by 27 percent in real terms over 2008-2010. Although the Constitutional Court ruling about the pension reform was very specific and related to the lack of consultation on allowing cuts in pensions, the Government did not pursue the proposed reform.Reforming the social sectors during good times creates fiscal space to react during economic downturns. Contrary to Latvia, some countries among the EU12 started earlier to implement policies aiming at counteracting the demographic decline, which is large and certain: per capita financing and school consolidation in education, improved targeting of social assistance, increased retirement age, hospital consolidation, and increased focus on primary care provision, among others. Taking early steps: (i) allows limiting the cuts needed when a crisis occurs as poorly targeted social insurance expenditure can boom during economic contraction, (ii) accelerates fiscal consolidation as structural reforms consume time and political capital before actually providing fiscal savings, (iii) provides fiscal space through deficit and debt reduction allowing for counter-cyclical policy through discretionary policies, and (iv) prevents massive lay-offs of public workers at a time of crisis when increased unemployment would command the exact opposite policy.Budget rules should take into account economic cycles. It is important to consider the trajectory of social protection expendituresâ€”particularly unemployment benefits and social safety net support programsâ€”across the economic cycle in designing fiscal rules and buffer stock savings mechanisms.
P115737 | Mongolia-Development Policy Credit | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2009 | 2010 | 2011 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/753351474939089090/text/000020051-20140620084916.txt | http://documents.worldbank.org/curated/en/753351474939089090/pdf/000020051-20140620084916.pdf | The experience with this project suggests the following lessons:(a) As expected, results remain subject to risks where prior and intermediate actions are critical but not sufficient to achieve objectives as formulated. In this operation, risks to objectives materialized as commitment to better fiscal arrangements might have been somewhat weakened by the new affluence from higher mineral revenues. (b) Related to lesson (a) above, the "one-off" or "single tranche" design of the operation, while understandable given the uncertainties of the government's reform program, implied that objectives should have been better tailored to what the implemented and the likely future reforms supported by the operation were to achieve with an acceptable degree of likelihood. There is of course a minimal scope of reforms that would be needed to achieve objectives of any validity in terms of results on the ground. (c) It is important to distinguish sharply between reforms and objectives. Evaluation was rendered difficult for the mining sector, where neither the Letter of Development Policy nor the Program Document articulated clearly what was to be expected from "clarifying the mining policy framework".
P115761 | Thailand HCFC Phaseout Project (Phase I) | East Asia and Pacific | Thailand | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | MONT | IPF | 2014 | 2020 | 2021 | ICRR | >=10 million & <25 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/723821601519046290/text/Thailand-Thailand-HCFC-Phase-out-Project.txt | http://documents.worldbank.org/curated/en/723821601519046290/pdf/Thailand-Thailand-HCFC-Phase-out-Project.pdf | The ICR (p. 31-32) included several useful lessons learned, including: Combining investment incentiveswith policy and future market demand is critical for phasing out the use of HCFC in the foam and AC sectors. This projectprovided sub-grants for enterprises willing to phase out HCFC which resulted in obtaining buy-in for the introduction of theHCFC-141b ban. The introduction of a ban then resulted in larger foam enterprises and system houses to prepare to decrease theirdemand for HCFC-141b. Providing examples for adopting new technologies is useful for getting thestakeholders buy in. In this project evidence for the adoption of technologies by one of the leading manufacturesin Japan supported consensus building among stakeholders. Also, the collaboration between the FTI and Japans Ministry ofEconomy, international Trade and Industry was critical for triggering private sector investment in promoting HCFC-32.
P115762 | Vietnam-HCFC Phase-out Project (Phase I) | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | MONT | IPF | 2013 | 2017 | 2018 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/133071530232976322/text/Vietnam-VN-HCFC-Phase-out-Project-Stage-I.txt | http://documents.worldbank.org/curated/en/133071530232976322/pdf/Vietnam-VN-HCFC-Phase-out-Project-Stage-I.pdf | The ICR (pp 30-31) includes lessons learned adapted by IEG:Effective policy action - licensing HCFC-basedpolyols. The licensing and quota system as aregulatory measure to control and eliminate ODSs remains the mosteffective tool for ensuringcompliance with the MP. The implementation of a licensing requirement for imported HCFC basedpre-blended polyol is next most effective mechanism for identifying and uncovering private sector users of thesubstances.Effective project management tools. The MIS, as main tool for implementation and monitoringshould be used as a model to establish a system that identifies and tracks all ODS users in the country. Given the future phasedownof HFCs, which many of these enterprises may be using the development of a large-to-day activities and interactions with thebeneficiaries.Adaptive management - a delicate balancing art. Its important to maintainbalance between ensuring project activities consistency to Bank procedures, while giving due consideration to clienttechnical and financial capacity. Financing requirements of the enterprises proved to be substantial as they were obligated tofinance new equipment upfront, and then be compensated after contract signing with suppliers based on a payment schedule While theupfront payment was challenging for some enterprises, a results-based disbursement mechanism would be more effective duringimplementation.The Sectorapproach provides more flexibility in project implementation than thegroup project approach. While groupapproach accelerates implementation progress at the initial phase it lacks flexibility to accommodate likely changes at theenterprise level. A Sector approach, can help better manage HCFC verification at the enterprise level. Under asector approach, project proposals are approved at the sector/sub-sector level based on the size/type of allidentified eligible enterprises and the HCFC consumption in the sector/subsector. A full sector approach can help bettermanage HCFC verification at the enterprise level as validation of HCFC consumption is carried out on site during projectimplementation by reviewingconsumption figures.
P115763 | HCFC Phase-out in the PU Foam Sector Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | MONT | IPF | 2014 | 2024 | 2025 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | https://documents.worldbank.org/curated/en/099100824191542775/text/P115763-4cb59c78-49b0-4fd5-9c36-f7713e09d5dd.txt | https://documents.worldbank.org/curated/en/099100824191542775/pdf/P115763-4cb59c78-49b0-4fd5-9c36-f7713e09d5dd.pdf | The ICR (p. 30) included several lessons learned, which were adapted by IEG: Providing financialincentives to local foam system houses through a voucher system to invest in alternative technology can ensure that system housesas well as SMEs keep their share of the local market. In this project, without the voucher system, it would have beenunlikely the system houses would have formulated HFO polyol on their own, and SME beneficiaries were to continue to rely onHCFC-141b, especially given the high prices of HFOs by international system houses. Combining financialinvestments in the private sector with regulatory control can allow for a sustainable phaseout of HCFC-141b. In thisproject, the partially financing of the phasing out of the HCFC-141b, using the quota system as well as regulatory control to banthe import and use of HCFC-141b after completion of the technology conversion was critical for achieving HCFC-141btargets. Collaboration among different entities involved in the subject area can be critical for a successfulphasing out of HCFC-141b in the foam sector. In this project, regular interministerial coordination meetings between theMinistry of Environment and Forestry, Ministry of Trade, Ministry of Industry, and Ministry of Finance aroundimplementationprogress and bottlenecks allowed for the development of a forward-looking approach to integrating policies andprovisions that include both HCFCs and HFCs.
P115767 | Nepal-India Electricity Transmission and Trade Project | South Asia | Nepal | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2022 | 2023 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099062723170032325/text/P11576702e6b3206d09bf901d0f7103cd51.txt | http://documents.worldbank.org/curated/en/099062723170032325/pdf/P11576702e6b3206d09bf901d0f7103cd51.pdf | This review has drawn three lessons based on the information in the ICR.A mismatch between the output-basedformulation of the project objective and the project design can lower projects efficiency in achieving the projectsobjectives and complicate the assessment of the projects higher-level development outcomes. The project activitiesfinanced under Component A of the project were sufficient to achieve the project objectives to increase power transmission capacityand the power trade between India and Nepal. However, the outcomes expected from the achievement of power trade between the twocountries were not defined. Furthermore, the project activities under Component B would have been expected to improve thereliability and quality of electricity supply in Nepal but the project objective did not capture such outcomes. Therefore, thesignificant delays in the construction of the transmission lines in Nepal that were not directly related to increasing thetransmission capacity between India and Nepal resulted in a 58-month project closing date extension. This had a significant adverseeffect on the projects administrative and operational efficiency. Furthermore, the mismatch between the project objectiveformulation and the project design complicated the assessment of the projects development outcome. Despite the incompletionof the transmission lines that would strengthen the transmission grid in Nepal, the project was successful in completing thetransmission line between India and Nepal and facilitating power flow from India to Nepal. However, the projects outcomecould only be rated Moderately Unsatisfactory because of absence of development outcomes and inefficiencies related to theconstruction of transmission lines within Nepal.Insufficient communication with communities affected by theproject and inadequate implementation of safeguard policies can adversely affect project implementation and achievement of projectoutputs. Some project-affected communities in Nepal were not aware that transmission lines would pass through theirvillages. These communities were not appropriately consulted during project preparation or implementation and informed about theright-of-way issues. An information dissemination and communication plan was not prepared (ICR, p.26). These led to objections fromthe communities and significantly delayed project implementation. Additionally, the shortcomings in safeguard policiesimplementation led to project delays. The project signed contracts for the construction of the transmission lines in Nepal withoutfirst obtaining forest clearance permits and completing compensation payments to project-affected communities (this is related tothe right-of-way issues). These also led to project implementation delays. As a result, the project closed without completing thetransmission line works in Nepal that would strengthen the transmission grid in the country.Absence of anowners engineer can critically affect project outputs and outcomes if the project implementing agency does not havesufficient technical and project implementation capacity. The NEA had insufficient capacity to manage transmission lineworks at a large scale and scope as defined under Component B. Therefore, the project was to hire an owners engineer tosupport the NEA in project design, procurement, contract management, and supervision. However, because of unsuccessful bidding, theproject could not hire an owners engineer. This resulted in significant shortcomings in project design, procurement, andcontract management such as inefficient transmission line route design, cancellation of contracts, insufficient of supervision ofworks, and inadequate implementation of safeguard policies.
P115782 | Sierra Leone EFA FTI Program | Western and Central Africa | Sierra Leone | IDA | FCS | Human Development | Education | RETF | IPF | 2009 | 2013 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/511201475099751171/text/000020051-20140626105637.txt | http://documents.worldbank.org/curated/en/511201475099751171/pdf/000020051-20140626105637.pdf | A number of lessons were reported in the ICR (p. 27), which IEG has synthesized to the following:Projects that are implemented in post-conflict settings need to anticipate that implementation and disbursements will be initially slow. EFA-FTI projects are typically implemented in three years. This short duration is not enough time to build necessary capacity and implement large-scale civil works, which are often needed in these settings. This three-year time limit for Global Partnership for Education projects should be reconsidered. A strong government project implementation team must be in place prior to project effectiveness and remain throughout project implementation. In this case, key Secretariat appointments were delayed, resulting in slow implementation progress. These delays, along with the short implementation period, contributed to implementation problems. Strong Bank supervision and knowledge of Bank procedures is essential for implementing projects in post-conflict countries. In the case of this project, the implementation unit was unfamiliar with Bank procedures and would have benefited from earlier support from the Bank on its procedures. The presence of a Bank education specialist in-country was invaluable to provide daily support and monitor project implementation. Experience with other Bank-supported projects in post-conflict countries has shown that having the TTL in-country is critical for ensuring timely project implementation. The project was developed and implemented within the context of structural and institutional decentralization. Because the final decentralization mechanisms could not be fully understood until the implementation process itself started, the implementation of the project was bound to be slow. Projects that contain decentralized implementation will require an initial period of adjustment, as capacity cannot fully be built beforehand (as the final decentralized mechanisms cannot be fully understood until the implementation process is started).
P115816 | Education For All - Fast Track Initiative Catalytic Fund Bridge Grant | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Human Development | Education | RETF | DPF | 2010 | 2010 | 2013 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/312961474489961434/text/000020051-20140625061356.txt | http://documents.worldbank.org/curated/en/312961474489961434/pdf/000020051-20140625061356.pdf | Lessons as identified in the ICR:Allow more time for teams to adapt to changes in Operational Policy rules in a multi-donor context. In this case, the team was under pressure to prepare and deliver a one-year operation on time and adjust the operation to new rules for FTI. More time should be given in a multi-donor context to the dissemination and implementation of rule changes to ensure all partners endorse the new rules. A sector-specific FTI focal person could improve sector-wide collaboration. FTI operations involve heavy donor collaboration which justifies an FTI focal point for the Africa education sector. Outcome indicators still should be reported even for single tranche DPOs. Although this was just a one-year DPO with a single disbursement, it still supports the implementation of an ongoing sector strategy which collects outcome indicators. Decentralizing textbook procurement can substantially reduce procurement time and stock-outs. This operation found that a web-based system to handle all book orders from schools catalyzed the process.
P115836 | Wetlands Conservation Project | Western and Central Africa | Sierra Leone | IDA | FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2011 | 2016 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/627061512426413892/text/ICRR-Disclosable-P115836-12-04-2017-1512426404163.txt | http://documents.worldbank.org/curated/en/627061512426413892/pdf/ICRR-Disclosable-P115836-12-04-2017-1512426404163.pdf | 1 . The Project was designed on the basis of experience with the other biodiversity projects in West Africa,especially the GEF-3 Sierra Leone Biodiversity Conservation Project (BCP). This resulted in a robust design and synergies. Buildingon results achieved by other Bank projects can lead to improved project outcomes.2 . The efficiency ofProject implementation benefited from the synergy with a related Bank project - IDAs Rural and Private Sector DevelopmentProject (RPSDP). Using the RPSDPs PMT that had trained staff was very important for the efficient Project implementation.Also, the credibility of the RPSDP supported a positive reaction to the Project among the stakeholders. The lesson is that usingexisting institutional structures (in particular, created by other Bank projects) can be both a cost saving measure and a means toincreased sustainability of project achievements.3 . The project significantly benefited from theGovernment commitment to wetland conservation. This also increased sustainability of the project outcomes.This was achievedby regular and continued communication with the stakeholders from the start of the project preparation and involved the centralgovernment, local authorities, traditional authorities, and local communities. Such approach is time consuming but necessary inprojects involving multiple stakeholders with varying interests and different degree of understanding of the project objectives andbenefits.
P115874 | Vietnam Power Sector Reform Development Policy Operation | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2010 | 2012 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/610661477325282202/text/Vietnam-VN-Power-Sector-Reform-DPO.txt | http://documents.worldbank.org/curated/en/610661477325282202/pdf/Vietnam-VN-Power-Sector-Reform-DPO.pdf | Five lessons are drawn from the ICR (pages 57-60), with some adaptation.One, the implementation of a complexmulti-part, multi-period, multi-operation, sector reform DPO requires a singular attention to the end-program goals and objectives.Delays in one period must be compensated for by accelerated action in another to keep the reform momentum going. Shortfalls in onereform area must be remedied by compensatory effort in another to keep the program goals within reach. Considering that a delay indivesting from power generation may have dulled private investor interest, Vietnam must now considerother meanstoincrease investment in new generation capacity in the light of rising demand for electricity.Two, technical progresswith a reform effort must be matched by political action --- that is, progress with the political steps needed to secure the reformoutcomes. The development of generation market rules, the installation of an information technology system, and the conduct ofactual trading in electricity made for robust technical progress with creation of a competitive market for power generation. But,the technical gains would have been hollow without a willingness by the Government to cede complete political control over thetariff setting and adjustment system to a rule-based mechanism.Three, a sector reform program must always berealistic, both with the scope and scale of the reformsas with the timeline. The realism of prior actions and expectedoutcomes must be rigorously scrutinized both during appraisal and implementation, including with regard to the macro-economicenvironment and the political setting in which the reform plan is to be pursued. The pressure to disburse the loan proceeds,for budget support purposes in a DPO like the PSRDPO, is ever present, but the option remains that the budget support can be scaledback to match the measure of progress made with the reform program.Four, a market reform program entails more thanjust transparency in the operation of the market, it also invokes transparency in theenactment of policy and institutionalreforms. Transparency of the Governments decisions is vital to gaining the confidence of stakeholders that the reforms aregeared to the public interest. It was important in the implementation of the PSRDPO that the prior actions required of theGovernment and that the results of various reform initiatives were disclosed and disseminated to market participants and to thepublic.Five, an energy sector reform program requires substantial technical assistance, which the Bank and theborrower must commit to provide, including on an ongoing basis. The PSRDPO benefitted from technical assistance provided duringprogram preparation, in the implementation of various technical aspects of the reform program, and for the design of the next stepin the long-term plan --- the creation of a competitive wholesale market. The Bank successfully mobilized grant funding for some ofthese requirements and supplied its own technical expertise for many other activities. The Government should financially supportother technical assistance requirements.
P115886 | Agricultural Productivity and Diversification | Western and Central Africa | Benin | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2011 | 2022 | 2023 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099515001132338486/text/P115886062e9c80e8081b20f727ef14bb99.txt | http://documents.worldbank.org/curated/en/099515001132338486/pdf/P115886062e9c80e8081b20f727ef14bb99.pdf | The ICR presents 4 strategic lessons arising from this project (ICR, paras. 74 77). The key elements of these lessons,which especially have relevance for other similar type of agricultural projects, are highlighted below (including some enhancementswith respect to the ICR findings).(a) Lesson 1: Promoting a strong private sectorinvolvement in the seed production system is key to improving and sustaining the supply of planting materials to producers.During the projects implementation, due to various constraints, it was challenging for the research and publicentities to supply the needed volume of breeder seed for onward multiplication by seed producers and private seed companies. Theseconstraints have limited the development of the seed system and its ability to supply enough seeds to fully meet producersdemand, and therefore, to promoting a wide scale farmer adoption of improved seeds. Agricultural development projects seeking topromote sustainable access to improved seeds and planting materials should include priority activities to foster a strong privatesector involvement in the seed system, including enforcement ofa sound harmonized regulatory framework and a cleardemarcation of the roles of key stakeholders and their strengthened capacities to fulfil effectively their mandates; these actionswould help ensure wider farmer adoption of improved seeds, and therefore, to contribute to achieving higher productivitylevels;(b) Lesson 2: Creating an improved enabling policy and institutional environment iskey for achieving increased private sector investments in the relevant value-chains. The expanded and sound role of aninclusive private sector in the agricultural sector, similar to the approach being followed by the Ministry Agriculture, Livestockand Fisheries (MAEP), needs to be mainstreamed and institutionalized, and become the standard practice in the MAEP, and otherrelevant entities. Although the project had mobilized a modest amount of private sector investments (only $5.0 million), inretrospect, more progress could have been achieved if the MAEP was more proactive in reaching out to other ministries (Ministry ofFinance, of Trade and Industry, APIEx) and relevant private sector entities to capitalize on synergies and share experiences andbest practices for promoting and achieving an expanded private sector role in the targeted value chains. Future projects seeking topromote the development of agricultural value-chains should include in their design a clear and comprehensive private sector actionplan, with a clear strategy on how the Ministry of Agriculture and relevant private sector entities will reach out to and engagerelevant public institutions and private sector stakeholders for achieving a strengthened and expanded role of an inclusive privatesector;(c) Lesson 3: Priority and sound institutional reforms in the agricultural sector are important toformulate and implement for empowering producers apex organizations and interprofessional bodies, to promote sustainably anexpanded role of an inclusive private sector. The sustainability of these private sector organizations and the effectivefulfillment of their functions (advisory services, training, policy dialogue, promotion of value chains) require the properformulation and implementation of their resource mobilization strategy, which is strongly dependent on the prevailing regulatoryenvironment. The project supported the preparation of the resource mobilization strategy and funded some of the activities includedin their workplan. The project supported the MAEP in drafting and transmitting the law on inter-professional organizations to thenational assembly for its promulgation (submitted in 2021). This law set the framework for the organization of inter-professionalbodies and their funding mechanisms. Recently, this law was merged with another relevant law, which is now being reviewed foradoption by the National Assembly. This legislative gap has limited the funding available for private sectorinter-professional bodies to fulfill their mandates. Future similar projects seeking to expand and empower inter-professionalentities (and other relevant private sector actors) should accord high priority to the timely formulation, approval andimplementation of these types of institutional, legislative, funding and partnership reforms;(d) Lesson 4:Promoting expanded access to finance, availability of inputs, and efficient and effective advisory services are keyingredients for fostering the widespread and sustainable adoption of productivity-enhancing technologies and food and nutritionsecurity. The project supported strategic value chains, and effectively used a blend of targeted capacity buildingactivities, and adequate financing instruments (matching grants and competitive funds) to facilitate the expanded availability andaccess to inputs (seeds, fertilizers, chemicals, fingerlings, fish and poultry feed, animal breeds, veterinary products),equipment, and support small scale irrigation schemes. This strategic support resulted in the adoption of productivity-enhancingtechnologies, with positive impacts on production, income, and food and nutrition security. Agricultural development projectsseeking to promote the adoption of technologies for enhancing food and nutrition security and competitive value chains shoulddesign and implementing an integrated approach, customized to each country conditions and requirements. Also, it is important tohelp ensure that relevant follow-up projects help consolidate, expand and sustain these strategic improvements and results.
P115938 | Rapid Response Child-Focused Social Cash Transfer and Nutrition Security Project | Western and Central Africa | Senegal | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2009 | 2013 | 2014 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/184541474664725687/text/000020051-20140626080021.txt | http://documents.worldbank.org/curated/en/184541474664725687/pdf/000020051-20140626080021.pdf | The project achieved remarkable results as it surpassed targets for all key indicators. To an important extent this may have been driven by a strong community-based communications strategy and a broad, inclusive approach to community mobilization for health and nutrition, as illustrated by these lessons drawn from the ICR:Effective communication for behavior change and counseling can achieve results. To do so, they require precise messages on the promoted behaviors, built on positive examples that appear easy to take on, and including a description of how the promoted behavior should be accomplished. The scale-up of the NEP was built on extensive knowledge of the implementing partners on the challenges in keeping children healthy but was also built on the positive practices already performed. The project showed the way by, for example, linking local food demonstrations to the period when children start complementary feeding practices.Community-based nutrition is an essential platform for service delivery of other social and health related packages. The initial mobilization of targeted communities for nutrition activities successfully absorbed the social transfer pilot. Distribution of bed nets has also proved to be an easy expansion of the original nutrition activities. Extensive mobilization of communities can provide the crucial contact between children and other public and private interventions.Effective strategies to combat the multiple causes of malnutrition require flexibility in addressing them. Interventions that are narrowly focused on direct health and nutrition interventions leave less room for innovative and adaptable approaches. They also limit inclusiveness in excluding indigenous community organizations that are not directly health or nutrition-focused, but nevertheless can bring valuable experience to bear. The project under review used NGOs to tap into such local level resources and act as a catalyst for innovation, moving hand-in-hand with effective communications initiatives.
P115938 | Rapid Response Child-Focused Social Cash Transfer and Nutrition Security Project | Western and Central Africa | Senegal | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2009 | 2013 | 2017 | PPAR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/314151497365405800/text/110290-FR-PPAR-P070541-P097181-P115938-PUBLIC.txt | http://documents.worldbank.org/curated/en/314151497365405800/pdf/110290-FR-PPAR-P070541-P097181-P115938-PUBLIC.pdf | 6. Lessons Â· These three projects demonstrate that formidable results can be achieved within the time frame of a four-year project. Phase I was highly successful in establishing a new innovative program, a strong capacity for its successful management and 61 implementation, and tangible results in the intervention areas. The three projects together also demonstrate that capacity and institution building is a medium-term, incremental process. The gradual decentralization of program oversight, the evolving roles and involvement of local governments, CEAs, and other sectors could not have happened all at once. The time invested is well worth the quality of this program's mature design and capacity. Â· Cross-sectoral coordination and teamwork coalesce around shared objectives. A truly multisectoral approach cannot be achieved solely through an organigram or sectoral work plans with resource allocations. Rather, a shared objective and sense of mandate and accountability to contribute to that objective light the way. This applies to local and central levels alike. Â· A management style that supports an evidence-based, participatory learning culture will culminate in strong ownership of the program and the continual improvement of its performance and effectiveness. The evidence base of the program has been strong and continues to grow with new evidence about sector wide coverage and support of other partners. There is scope for the further enhancement of evidence and learning by prioritizing and supporting research. Senegal has untapped technical capacity in nutrition that could be exploited. Â· Senegal's nutrition policy and program have attracted many partners, both national and international, but inadequate coordination of this financial and technical support has undermined its overall effectiveness. Considerable scope exists for enhancing the aid effectiveness of nutrition interventions by preparing and brokering a fully costed, prioritized multiyear program with a fully developed inventory of available financing and technical support. Â· The measurement of coverage is complex but critical to assess program efficacy. It was difficult to reconcile the robust outcomes in the intervention areas with modest trends at the national level, in the absence of detailed data on program coverage. It is not enough to measure geographical coverage. Even program coverage by target group (for example, children under age five years) does not provide sufficient detail. The REACH survey is a landmark in the program's capacity to define and assess coverage by specific intervention and by specific age group. 63
P115954 | Irrigation Development Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2012 | 2020 | 2021 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/992031610641806932/text/Bosnia-and-Herzegovina-IRRIG-DEVT.txt | http://documents.worldbank.org/curated/en/992031610641806932/pdf/Bosnia-and-Herzegovina-IRRIG-DEVT.pdf | The ICR included six lessons. The following three are emphasized with some adaptation of language: Thedesign of irrigation projects needs to include on-farm improvements, such astertiary systems, to ensure delivery ofirrigation services to farmers. The project financed the construction of the network up to the farm gate (main systems),leaving on-farm improvement works for the cantons/municipalities and the farmers to complete, whichdelayed the start ofscheme operations. The lesson is that in order not to delay improved irrigation services to the beneficiaries it is advisableto concurrently implement both the main infrastructure and tertiary on irrigationimprovementsirrespective of financingarrangements There is need for a policy or master plan to guide investments in agricultural water management.The project experience showed that implementation issues arose due to lack of a coherent vision foragricultural water management in bothFBiHand RS. The lesson is that there is need for an investmentstrategy or policy vision document that will guide implementation of the next generation of irrigationinvestments. To ensure local buy-in, local partnerships need tobe built into the implementationarrangements. In order to solve the potential causes of project implementation delays (mainly in FBiH), the nationalimplementation teams engaged directly with mayors and municipalities. Roundtable discussions and clear communications andagreements on mutual expectations and responsibilities with frequent follow up, accelerated the issue of work permits, co-financingwas mobilized, location of absentee farmers were identified and all social safeguards issues were resolved. The lesson isthat these partnerships and discussionsresulted inrapid progress on the rehabilitation of the irrigationschemes/systems.
P115958 | Second Programmatic Private Financial Development Policy Loan | Europe and Central Asia | Serbia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2010 | 2011 | 2012 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/872231474854897739/text/000020051-20140624213637.txt | http://documents.worldbank.org/curated/en/872231474854897739/pdf/000020051-20140624213637.pdf | 1. Some flexibility in implementing programmatic lending is important if the Bank is to be able to adjust programs to meet needs as they appear, this case, due to changing world market conditions. PFSPDL II, in this case, was productively modified to help Serbia pro-actively reform its banking and financial sectors to address problems that could have arisen from the world financial crisis. 2. Good coordination remains an imperative. In this case, close coordination with the IMF and EU donors were key to insuring the resources needed for reform, as well as the incentive of EU membership.
P116011 | Egypt Enhancing Access to Finance for Micro and Small Enterprises | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2010 | 2016 | 2017 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/561301478291754219/text/ICRR-Disclosable-P116011-11-04-2016-1478291737610.txt | http://documents.worldbank.org/curated/en/561301478291754219/pdf/ICRR-Disclosable-P116011-11-04-2016-1478291737610.pdf | Five lessons are drawn from the ICR, with some adaptation (ICR, pages 43-45).Liquidity is not always the bindingconstraint to MSE lending. Demand for the microfinance line of credit byTier-1NGO microfinance institutions was lowerthan expected. MostTier-1microfinance institutions had existing lines of credit with banks, and did not face animmediate need for liquidity support. A combination of financial and non-financial support may have been more effective inaddressing market deficiencies related to financial exclusion. In addition, a segmentation of the financial service providersaccording to target client type, geographic and sector concentration, and liquidity position would have helped to ensure that theBank-financed line of credit had an incremental effect.The promotion of financial inclusion may require investmentsin infrastructure and operational capacity. The microfinance line of credit aimed to have service agents lend to MSEs through postoffice branches, but the experiment failed. Egypt Post did not have the infrastructure (the network capacity, among others) or theoperational capacity (the staff capacity, principally) to pull off the innovation. An alternative initiative --- the partnershipbetween Egypt Post and select microfinance institutions --- was confined to cash-in and cash-out functions for loan disbursementand repayment.To be sustainable, it is vital that MSE financing be provided on a commercial basis and avoidintroducing market distortions or promoting entitlement programs. Financing under this project was to be provided in commercialterms using a cost mark-up methodology. It is equally important that the perception thatMSE financingis provided on acommercial basis be upheld. Many stakeholders had requested information on the pricing terms and conditions by which the SFDon-lent funds to participating financial institutions. To this end, pricing arrangements needed to be disclosedtransparentlyand reported in regular monitoring and supervision documents. In some cases, implementation arrangementsneed to be firmed up ahead of project effectiveness. The inordinate delay in establishing the wholesale financing facility stalledprogress with the microfinance lending component of the project. It would have helped if the contractual arrangement between SFDand the Commercial International Bank for the establishment of the wholesale financing facility had been finalized before, or as,the project became effective.Combining Bank financing with advisory and analytical work improves project outcomes.This MSE finance project benefitted from technical assistance provided through the World Bank-IFC Regional MSME TechnicalAssistance Facility. It also helped that the Egyptian authorities engaged the Bank in intensive policy dialogue throughout theproject implementation period.
P116020 | Banking Sector Support Loan | South Asia | India | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2010 | 2010 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/879611474905424229/text/000020051-20140625055919.txt | http://documents.worldbank.org/curated/en/879611474905424229/pdf/000020051-20140625055919.pdf | The present operation has features which reflect aspects of the Bank's approach to crisis lending which raise larger questions for the Bank. First, the Bank needs to consider the content of crisis loans. BSSL1, on its own, had negligible medium term reform content. Although some reform was back-loaded in the second operation, it was not eventually realized. As expressed by the ICR, in times of crisis, the Bank has to be ready to â€˜leave asideâ€™ the normal mindset of a DPL, whose focus is generally on medium term support. The present operation may also reflect the need for the Bank to review its crisis lending instruments. Second, in some cases where support is precautionary, the Bank may use a wider spectrum of instruments, such as the DDO, and discuss these with borrowers. As pointed out in the ICR, the signaling value of a crisis loan can be as important as the actual disbursement of funds. A third lesson, also recognized in the ICR, is that if the Bank is to make precautionary loans, it must speed the time from loan identification to Board approval. It took one year from the Governmentâ€™s request until the BSSL was approved by the Board.
P116064 | Kenya Agricultural Input Supply Program | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Sustainable Development | Agriculture and Food | SPF | IPF | 2009 | 2010 | 2012 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/175401474489869599/text/000020051-20140624194600.txt | http://documents.worldbank.org/curated/en/175401474489869599/pdf/000020051-20140624194600.pdf | Five lessons were drawn from this program in the ICR. With some comments, they were as follows: Vouchers can be used effectively in post-conflict settings if the necessary organizational structures for retailing and redemption of coupon (vouchers) are intact and efficient. The necessary condition, however, is close monitoring of leakages and taking actions to block the leakages when they occur.Private dealers can and will participate effectively. The necessary condition is that dealers receive timely payments for the redeemed vouchersAn exit strategy through linkages with credit markets is highly desirable. Such an exit strategy is certainly desirable but will only be successful if the voucher scheme is designed and costed (e.g. ensure the optimum amount of fertilizer) to replicate actual conditions farmers will face when the voucher scheme is phased outTargeting and flows of funds constitute major challenges in implementation.A well-managed voucher program can forestall return to public intervention in supply and distribution of fertilizer, and build essential private sector presence in the sector. But, a voucher program is nevertheless a public intervention albeit with less distortions than if the government controls the fertilizer market. As was apparently the case in 2009, the government entered the fertilizer market as a supplier despite the presence of a voucher program and distorted (lowered) the market price. This probably had a negative effect on those fertilizer dealers who had themselves imported fertilizer. From the experience of this program two additional lessons can be identified, namely:The targeting mechanism and targeting outcomes for a voucher program should be monitored very closely and the government needs to be prepared to take immediate action if leakages or distortions in the targeting mechanism appear.Any evaluation of a voucher program should be based on the real (economic) benefits and costs of the program.
P116080 | Export Finance Intermediation Loan | Europe and Central Asia | Croatia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2010 | 2017 | 2018 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/850871506536725265/text/ICRR-Disclosable-P116080-09-27-2017-1506536712557.txt | http://documents.worldbank.org/curated/en/850871506536725265/pdf/ICRR-Disclosable-P116080-09-27-2017-1506536712557.pdf | The ICR section devoted to lessons learnedcomprised mostly recommendationsand findings. The key lesson from theimplementation of this project is thata wholesale model seems to be preferable to a retail lending model. Thus, a wider rangeof financial intermediaries increases the number and diversity of potential project beneficiaries, enables new financialintermediaries to gain experience in working with international organizations, and encourages healthycompetition.
P116088 | Finance and Private Sector Development | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2010 | 2012 | 2012 | ICRR | >=100 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/716711474509747526/text/000020051-20140625185046.txt | http://documents.worldbank.org/curated/en/716711474509747526/pdf/000020051-20140625185046.pdf | The most important lesson of this operation is the importance of continuous Bank engagement in a countryâ€™s financial sector through knowledge services and lending operations. Thanks to its continued engagement with Colombiaâ€™s financial sector, the Bank was able quickly to adapt an already programmed DPL in support of Colombia's capital markets development, to incorporate relevant preventive measures to ensure the resilience of the financial system in light of the 2008 global financial crisis, as well as to advance the medium-term reform program to develop the capital markets.
P116125 | Poland Employment, Entrepreneurship & Human Capital Dev. Policy Program DPL | Europe and Central Asia | Poland | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2009 | 2010 | 2012 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/362241475091443427/text/000020051-20140625055611.txt | http://documents.worldbank.org/curated/en/362241475091443427/pdf/000020051-20140625055611.pdf | The ICR contains good lessons, the following two of which stand out. First, a well-designed program requires a solid analytical foundation to help identify issues and areas where reform is likely to succeed. Second, a program focused on a few core areas in urgent need of reform is more likely to be internalized and owned by the government.
P116152 | Second Programmatic Environmental Development Policy Loan | Latin America and Caribbean | Peru | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2010 | 2013 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | Five lessons are drawn from the ICR (pages 32-36), with some adaptation.One, strengthening environmentalgovernance by public institutions and mainstreaming environmental sustainability in private industry are long-term processes andneed considerable time to implement. The ENVDPL benefitted from the decision to structure the ENVDPL1 as a deferred drawdownoperation (DDO), which kept ENVDPL1 active for five years, well beyond the original one-year life of the operation. The longer timeperiod accorded the Bank the opportunity to systematically help strengthen the institutional capacity of the Government, enablingpublic agencies to meet the prior actions of the reform program.Two, building a reform program requiresextensive analytical work, including not just of the technical and the institutional but also the political economy dimensions ofthe reform effort. Perus Country Environmental Analysis (CEA) of 2007 served as the organizing analytical documentunderpinning the environmental management reform plan advanced by the ENVDPL. The CEA thoughtfully: examined the shortcomings ofthe national environmental management system in the country, and identified priorities that were consistent with thecountrys development agenda and could be linked to poverty reduction.Three, government ownership is essentialto the effective implementation of policy reforms. Political commitment was secured across the spectrum of agencies responsible forenvironmental management in the country, and at key levels of the organization in these public agencies. The top-line agenciesresponsible for implementing the reforms measures --- MEF, the newly created MINAM, PRODUCE, MEM, and MTC --- were individually andcollectively committed to the reform agenda.Four, framing poor air quality as detrimental to poverty reduction helpscatalyze action to address the air pollution problem. The negative effects of air pollution were demonstrated to be significantlyhigher on the poor and on the vulnerable in Peru --- women, the elderly, and children. Poor air quality stunted productivity andeducational performance, constraining the opportunities of the poor and the vulnerable for economic advancement. By highlightingthese findings, the Government succeeded in raising an awareness of the air pollution problem and in mobilizing a broad base ofstakeholders for the ENVDPL to address the problem.Five, measures to address MELs need to be constantly evaluated.The Government completed all the measures designed to completely identify MELs and to commit resources to remediate the high-risksites. Yet, mining-related social conflict has not decreased in Peru, where at least a fourth of the social conflicts in 2008-14were mining-related. The 2016 study Peru: Policy Options to Enhance Environmental Sustainability in the Mining Sectoridentified five issues: the fear of pollution; competition over land and water resources; cultural and social issues that are notadequately addressed, leading many communities to oppose mining activities; the asymmetry of power relations between industry andthe communities; and, the lack of confidence among communities that the Government can adequately protect the environment.
P116167 | HIV/AIDS Support Project 2 | Western and Central Africa | Niger | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=10 million & <25 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/713011512766073725/text/ICRR-Disclosable-P116167-12-08-2017-1512766066056.txt | http://documents.worldbank.org/curated/en/713011512766073725/pdf/ICRR-Disclosable-P116167-12-08-2017-1512766066056.pdf | The ICR (pp. 27-28) offers several useful lessons, including the following lessons editedbyIEG: The mapping of sites frequented by HIV/AIDS vulnerable population groups facilitates access of suchgroups to a package of combined preventive activities such as sensitization, condom use, and referral to healthfacilities, as was observed under the project through a socio-geographic mapping of hotspots for HIVtransmission. The involvement of community-based organizations and NGOs in communication activities forbehavioral change, and referral of key vulnerable groups such as commercial sex workers to health facilities for screening, areimportant strategies to promote synergy of actions between the public sector and the community to promote HIV/Aidsprevention. An important catalyst was good working partnerships with the civil society andNGOs. The timely implementation of community interventions is facilitated by early recruitmentof NGOs. Under the project, community interventions were initially delayed pending the contracting ofNGOs.
P116194 | EG-Giza North Power Project | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2010 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/248441543258384477/text/Egypt-Arab-Republic-of-EG-Giza-North-Power-Project.txt | http://documents.worldbank.org/curated/en/248441543258384477/pdf/Egypt-Arab-Republic-of-EG-Giza-North-Power-Project.pdf | The following three broadly applicable lessons summarized from the six presented in the ICR with someparaphrasing:1. An agile and flexibleproject can increase the project impact. In this project, when the additional generating capacity was needed, the Bank andGoE responded by expanding an ongoing project more efficiently than starting a new one. A site was already provided and a laborforce was in place. There were economies ofscale.2. Managing the environment andsocial framework can be a challenge for large facilities associated with a Bank project but were not financed by the Bankproject. As part of 2016 project restructuring, the project financed the gas pipelines for other power plants that werenot financed by the project. The Bank team had to undertake substantial efforts for a small investment component to cooperate withthe Government and GASCO on due diligence of large power plants as associated facilities. For new projects, the World Banksnew Environmental and Social Framework allows more flexibility on associatedfacilities.3. Greatly expanding thescope of the project late in its life can create procedural problems. In the case of the Giza North Project, the gaspipelines were added to the project in the Spring of 2016 with the loan for these lines due to close on December 31, 2017. Due tothis delay in starting these pipelines and the lack of capacity in certain governmental units, the RAPs have been delayed and notall had been completed by the time of loan closure. Furthermore, the implementation of the RAPs needed to continue to be supervisedeven though the Bank had very limited leverage, since it provided only a small part of the cost of the various power projects, andthe loan had already closed.
P116199 | GZ-Gaza Electricity Network Rehabilitation Project | Middle East and North Africa | West Bank and Gaza |  | FCS | Infrastructure | Energy & Extractives | SPF | IPF | 2012 | 2020 | 2021 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/833141624414508782/text/West-Bank-and-Gaza-GZ-Gaza-Electricity-Network-Rehab.txt | http://documents.worldbank.org/curated/en/833141624414508782/pdf/West-Bank-and-Gaza-GZ-Gaza-Electricity-Network-Rehab.pdf | There are three key lessons learned from thisoperation that couldbe of interest to management and teams working insimilar FCV environments.Adaptive management and adjustment of expectations: In FCV environments orcountries emergingfrom such status it is important to adjust expectations and to restructure and sequencesupportactivities to ensure progress, even if more incremental than previously envisaged. In this project adjustments were made to replacethe prepaid metering activities with a scale up of the SCADAsystem after repeated failures by the Borrower to designastrategic metering plan and after repeated procurement failures.In these circumstances it remains, nevertheless,important to properlyalign the changes or adjustmentsof activities with outputs and outcomes in acoherent theoryof change.Supporting common platforms for project coordination and reporting: Operating different projectcoordinationandreporting platforms to meet the needs of different development partners is often taxing even forsophisticated Borrowers and is much more so for FCV countrieswhich typically have less capacity andresources.Coordinating with other development partners conserves scarce donor capacity and improves the qualityofME systems and hopefully that of the dialogue. In Gaza, different developmentpartners appeared to have differentcounterparts in Government and different reporting mechanisms. Even though the project was designed as a single project withparallel financing by the World Bank and IsDB, there was no sharing of information or any form of coordination.Virtualimplementation support, including consultants support and capacity building: In contexts where physical access toclients and project sites is restricteddue to a countrys FCV status, instead of waiting for conditions to improve, theBankshould rely on virtual implementationmissions, and so should other external experts and consultants to theproject. In this project the use of virtual meetings proved effective in conducting acceptance testing for equipmentmanufactured outside the country.
P116201 | MA-National Initiative for Human Development 2 | Middle East and North Africa | Morocco | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | PforR | 2012 | 2016 | 2019 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/638391560976428231/text/Morocco-MA-National-Initiative-for-Human-Dev-II.txt | http://documents.worldbank.org/curated/en/638391560976428231/pdf/Morocco-MA-National-Initiative-for-Human-Dev-II.pdf | The ICR (page 26) draws four lessons from the experience of implementing this program. The three most lessons from theexperience of implementing this program, with some adaptation of language.One. Systematic local empowerment andCDDs programs can be useful for improving local governance but such programs may require long timeframes. For over adecade, INDH aimed at promoting CDD program with participatory decision-making structures involving the government, local electedofficers and civil society representatives including women and youth. The long-time frame helped in increasing the inclusiveness ofwomen and youth in local governance. Two. Although it is necessary to incorporate income-generatingactivities in CDD programs from the outset, strong provisions for risk management are required. This program showed thatwhile it is both feasible and desirable to include income-generating activities as incomes are important for livelihoodimprovement, incorporating of such activities require careful planning, preparation and selectivity and strong complementarysupport (such as through business training and market analysis).Three. While a national CDD program requiresstrong central management in its early phase, it is necessary to encourage local management as the program matures. Theexperience of this operation showed that once the program was rolled out and operational, local decision-makers were keen to learnfrom what was happening in their area and to experiment with new management approaches (such as participatory monitoring andevaluation) tailored to the local context.The ICR (pages 26-28) draws six lessons regarding the value-added of using PforRinstrument. Of these, the three most important lessons are, with some adaptation of language.One. The PforRinstrument allowed to focus on systemic change and capacity building and these can have positive implications for sustainabilitybeyond the ambit of the program. The DLIs helped the government in strengthen its audit capacity and theenvironmental and social guidance prepared under the auspices of this program had been adopted by the Non-GovernmentalOrganizations.Two. The PforR approach can help in reducing the transactions costs for the client. In thisoperation, the approach allowed the Bank to support many subprojects in fiduciary and safeguard procedures.Three.Administering the PforR approach may require additional Bank flexibility and resources. Client unfamiliarity with theapproach in the case of this operation led to greater reliance on Bank guidance and considerable involvement on the part of theBank team in the preparation of procurement documents.The IEG draws the following lesson from thisprogram.The targets for DLIs needs to be carefully assessed at appraisaland if need be, scaled upwards through a project restructuring. The targets for many of the indicators in this operationwere realized in the first year of operation itself, suggesting that the original targets may have been modest in terms of thelevel of ambition.
P116214 | Fourth Programmatic Fiscal Managment Development Policy Loan | Latin America and Caribbean | Peru | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2011 | 2012 | 2013 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/208431474588004209/text/000020051-20140625224545.txt | http://documents.worldbank.org/curated/en/208431474588004209/pdf/000020051-20140625224545.pdf | The following lessons were identified by IEG's review and the ICR:Sweeping and sustained reforms (such as Peru's) require strong borrower ownership, a well-defined strategy, a highly consultative approach with country stakeholders, and a response donor consortium. Close coordination with international actors helped the Government to implement its comprehensive reform programs over several years.Sustaining fiscal and related public sector management reforms can be challenging. They place a premium on a 'building blocks' approach (for example, ensure aggregate fiscal policies are in place before undertaking expenditure re-prioritization). At the same time, it is important to be flexible in launching various reform initiatives when public institutions demonstrate a readiness to undertake and internalize institutional changes. An important lesson from Peruâ€™s experience is the need to design flexibility into the program in order to respond to new challenges over the course of reform implementation. Peru was successful in adjusting to the changes in global financial markets while remaining faithful to the objectives of its reform program. The Bank acted as a responsible partner and provided both financial resources and technical advice as needed to enable government to carry on its reform program. The use of the deferred drawdown option (DDO) can be helpful in managing the uncertainties for a volatile global environment. It enables countries to have additional insurance to weather the global financial crisis as the availability of financing from the World Bank increase market confidence and access. It also provides a stamp of approval of good housekeeping.
P116214 | Fourth Programmatic Fiscal Managment Development Policy Loan | Latin America and Caribbean | Peru | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2011 | 2012 | 2017 | PPAR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/725661488828202108/text/110742-PPAR-PUBLIC.txt | http://documents.worldbank.org/curated/en/725661488828202108/pdf/110742-PPAR-PUBLIC.pdf | 6. Lessons 6.1 The experience of this DPL series highlights what can be expected from the World Bank's engagement with a well-performing middle-income country. 6.2 A programmatic DPL series is a powerful tool for supporting long-term reforms. When a strong ownership of the client is demonstrated, a programmatic series of operations can offer the World Bank and its client win-win solutions. For the World Bank, a multiyear program of support gives it a chance to pursue an extended and coherent analytical agenda that may not be feasible in multiple one-off operations. To the client, the programmatic series offers a real-time opportunity to engage with the reforms (including both the costs and benefits) and to make adjustments along the way. In the case of Peru, the government was able to advance its investment climate agenda early on and to learn about the need for deeper and longer-term challenges of upgrading the quality its workforce and technologies. The successive rounds of ever deeper reforms on trade and competitiveness, while incomplete and not implemented with maximum efficacy, would have been difficult to accomplish through separate operations, which are invariably interrupted by changes of priorities and political mandates. 6.3 World Bank supervision of the implementation of these operations should cover all aspects of the program to take full advantage of the learning opportunities offered by a programmatic series. It should pay greater attention to not only emerging risks during the period of program implementation, but also factors affecting the sustainability of the achievements in long-term policy reforms. In the case of Peru, supervision of the core program seemingly focused only on a few development objectives and outcomes, and left unattended a complete pillar of reforms. No explanation is given for this in any of the Implementation Status and Results Reports. This may have resulted in issues not being identified and therefore not addressed, in time leading to less progress than expected or reversal of outcomes achieved. It limited the ability of the World Bank and other stakeholders to fully understand and learn from the experience of this DPL series. 6.4 Reforms move to subnational levels, though their implementation may pose a challenge depending on the framework of fiscal decentralization. Despite all the positive steps that the government had taken to enhance efficiency in the allocation of fiscal resources, there remains a pressing need to rationalize the fiduciary and regulatory norms and the multiplicity of control and auditing instances. According to MEF officials interviewed for this evaluation, these have proliferated and seem to be driving a wedge between the central and regional governments' capacity to focus on results rather than procedures, a central objective of results-based budget management. Another area of clear priority is for the government to continue to place strong emphasis at the central and subnational levels on a robust and rigorously appraised public investment program, and enhance its assistance to subnational governments in identifying, designing, and implementing their own programs, particularly in meeting infrastructure deficits (for example, roads, water and sanitation). To do so, the government should consider placing greater emphasis on subnational tax revenue collection and more efficient distribution of fiscal transfers to subnational governments, areas that proved somewhat lagging during the implementation period of this DPL series. 6.5 The application of the DDO in this DPL series illustrated the World Bank's willingness and ability to support Peru at the time of the global financial crisis. It also showed the extent to which the World Bank's new arsenal of financing instruments was able to respond to the needs of middle-income countries where both the volume and the timing of financing are important for risk management purposes. As a tool for risk management, the DDO gives clients access to a large line of credit that is affordable and fast disbursing, which helps maintain the confidence of investors and deter the resolve of speculators. As a debt management tool, the DDO offers the government an insurance policy on its debt-service and priority expenditure commitments without raising the level of external debt in advance. The discretion to call on the World Bank loan in the amount it needs when it needs to allows the government to optimize its debt structure. Moreover, by extending the loan period by up to six years and not requiring the client to draw down the loan, the DDO facilitates World Bank engagement with clients who do not need World Bank financing but value its formal and sustained support for their policy reforms. This is particularly valuable for engaging with well-performing middle-income countries. 6.6 Yet, the present example also illustrates possible tensions between the independent selection of IBRD-financing terms and the monitoring of the World Bank's development effectiveness. In this DPL series, the DDOs were requested and approved for risk management and crisis response purposes, but this important development objective, for which two large loans were granted in record time, was not tracked. Although monitoring of the macroeconomic framework and program implementation continued until closure of the DDOs, the depth of supervision was restricted to verification of preconditions for drawdown, as required for all DDOs, and did not try to capture the effectiveness of the loans for all their development objectives. This raises a question as to whether overall program design or continued periodic supervision should attempt to explicitly include indicators of risk management and crisis containment, to capture overall development impact of the DPL series. As this practice was repeated in multiple DPL series in Peru (and elsewhere), a substantial amount of World Bank resources is at stake. 6.7 A parallel issue is that with its longer drawdown period and its renewal feature, the implementation period of a DPL-DDO extends beyond the program implementation period of a normal DPL, which has consequences on the expected outcomes. This calls for attention especially in situations where the DDO was added to an ongoing DPL series, such as in Peru, which had a set of coherent, noncrisis-related policy objectives and a predetermined program period that did not (and could not) anticipate the additional crisisrelated objective and the extended program implementation period. The World Bank's DDO guidelines only require the monitoring of macroeconomic stability and the continued implementation of the program. Questions can thus be raised on whether there should be any more detailed supervision or scope for review of the overall program at the time of a DDO's approval and renewal or readjustment of the IBRD-financing terms with regard to repayment options as the country's debt management profile may have altered. Notwithstanding, the trade-off relative to the flexibility of the loan instrument is also important. These issues merit further debate.
P116215 | First Programmatic Public Sector, Competitiveness and Social Inclusion Development Policy Loan | Latin America and Caribbean | Uruguay | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2011 | 2012 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/498441587144187138/text/Uruguay-UY-1st-Prog-PubSect-Comptitiv-Soc-I-DPL.txt | http://documents.worldbank.org/curated/en/498441587144187138/pdf/Uruguay-UY-1st-Prog-PubSect-Comptitiv-Soc-I-DPL.pdf | The following lessons are drawn from the ICR:.Business regulations need to be aligned with businesspractices. In this series, the Government and Parliament laid down a legal and regulatory framework hoping that itwould make participation in formal capital markets attractive. This turned out not to be the case: a more careful analysis ofprivate sector incentives could have promoted an approach that would have been more attractive to the privatesector.Technical assistance can be an essential complement to development policylending. In this project, an institution-building technical assistance loan provided financing as well as knowledgeand advice to agencies implementing the reforms. Government officials stressed to the ICR mission that the technicalassistance loan was crucial for implementing key components of the DPL, such as the transition to performance budgeting, expansionof e-government and reform of customs.World Bank participation in a high-income country in acrisis situation provides market signaling that can encourage policy reforms. Prior to the series, the governmentwas facing fiscal financial constraints that threatened to delay or even stop progress on key policy reforms, including inparticular the ones that subsequently would be addressed under the PSCSI series. The series, especially its first phase,brought the government the means and confidence to continue with its reform process (ICR, p.11)..
P116226 | Support to the Social Protection System in Health | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2010 | 2014 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/524301475112597438/text/000020051-20150113011326.txt | http://documents.worldbank.org/curated/en/524301475112597438/pdf/000020051-20150113011326.pdf | Lessons drawn from the ICR (pp. 19-21) and adapted by IEG:In the immediate aftermath of an economic crisis, the need to respond rapidly and to produce immediate results would need to be balanced with flexibility in project design to account for rapidly changing factors. In the case of this project, the design was simple; however, the results framework could have been updated to account for changing enrollment numbers and to include access indicators reported by the more than 45 studies delivered under the project. The project could have addressed inequality issues in the project design and reflected in the project results framework. In this case, there are large inequalities across States and socio-economic groups; however, the loan disbursed a per capita amount based on the number of individuals enrolled. Given the size of the loan and large inequalities across States, the focus could have been on a poverty-adjusted disbursement amount and targeted implementation support to the lowest-performing sub-national entities. In addition, IEG identified the following lesson: The appropriate use of lending instrument is important to achieving the objectives of Government and Bank support. In this case, the horizontal segmentation of the health system is considered one of the main impediments to improved health sector performance. Considering that the Seguro Popular had already more than the target population insured before this project became effective, a complementary DPL could have taken reforms to a next level and addressed structural issues that impact insurance effectiveness and access to health care for low-income groups.
P116226 | Support to the Social Protection System in Health | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2010 | 2014 | 2018 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/126441531152514335/text/124870-PPAR-P116226-P166377-PUBLIC.txt | http://documents.worldbank.org/curated/en/126441531152514335/pdf/124870-PPAR-P116226-P166377-PUBLIC.pdf | 5. Lessons 95. In times of economic crisis, if the country has a well-designed health program in place, the World Bank's financial support can be effective in helping the government to sustain and expand access to health services, protecting the poor from the adverse effects of the crisis. Mexico was suffering from a severe economic crisis in the year 2009, when the World Bank project was approved. The fiscal consequences of the economic crisis were putting at risk the expansion of Seguro Popular, as planned in the National Development Plan and national health sector strategy. Therefore, in a situation of limited fiscal space, World Bank financing created the fiscal space necessary to sustain and expand a national program to protect the poor. 96. IPF can be an efficient alternative to DPF if there is government ownership of the national program and a strong M&E system to monitor results. Both DPF and IPF can provide large-scale disbursements to governments, the former through budget support linked to prior actions and triggers; the latter through cofinancing large national programs like Seguro Popular. However, IPF, unlike DPF, can provide technical assistance as well as multiyear support and ensure that financial resources are used for a specific sectoral use. These are potentially positive features, as they can help sustain long-term reform efforts in a specific sector or program. Such a program effectively takes on key features of the World Bank's new PforR lending instrument that links disbursements to defined results. 97. It may not be possible to achieve UHC in fragmented health systems without an individual mandate for health insurance coverage. The main reason is the presence of adverse selection. Thus, under a voluntary system, the individuals who are most likely to seek health coverage are those who are older and who are less healthy than average. The experience of SPS confirmed that Mexico fell short of achieving universal coverage, as a sizable portion of the population not covered by the CSS still did not enroll in the heavily subsidized SPS until their health status worsened. 98. In decentralized health systems, to achieve the desired changes at the local level, the use of incentives (compatibility) should be preferred to the use of regulations and aligned with the institutional capabilities of the agents. According to the decision-space model (a principal-agent model first proposed by Bossert 1998) the central government (principal) can use diverse tools to shape the behavior of the state (agent), such as monitoring, reporting, inspections, performance reviews, contracts, matching grants, transfers, and so on (see World Bank 2015). In Mexico starting in 2014, the government introduced upper limits to SPS expenditure as it was concerned the states were not utilizing the SPS resources in the best way. However, the measure did not achieve the expected improvements and, instead, reduced the possibility of improving allocative efficiency at the state level.
P116230 | Egypt: Sustainable POPs Management Project | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2014 | 2022 | 2023 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099171002012324300/text/P116230003750203b0bac60429683ca1095.txt | http://documents.worldbank.org/curated/en/099171002012324300/pdf/P116230003750203b0bac60429683ca1095.pdf | The ICR (p. 28-29) provided several lessons learned that may be useful for future projects related to management and disposal ofstockpiles of obsolete pesticides. Two of them are presented below with rephrasing. Local institutionalinvolvement can be critical for addressing a delivery challenge caused by a sudden increase in foreign disposal costs strengtheninga local disposal capacity. In this project, costs for disposal/incineration in France and Sweden increased by 40 percent.Since the project worked with local incinerators to comply with international requirements, the second batch of OPs was disposedlocally increasing Egypts long-term capacity of an environmentally sound and cost-effectivedisposal. Designing an implementation plan that identifies potential bottlenecks is critical for achieving settargets. This project encountered several implementation challenges including local regulations, customs clearances andworking with foreign contractors, which resulted in the project not being able to achieve its target of 1,000 tons PCBdecontamination.
P116236 | PAMSIMAS Support Trust Fund | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Sustainable Development | Water | RETF | IPF | 2009 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/405721549908851209/text/Indonesia-ID-PAMSIMAS-Support-Trust-Fund.txt | http://documents.worldbank.org/curated/en/405721549908851209/pdf/Indonesia-ID-PAMSIMAS-Support-Trust-Fund.pdf | The lessons are taken from the ICR (pages 34-35) with some adjustment tolanguage: Partnership and collaboration between stakeholders are important for successfulimplementation of a large-scale program. The instruments developed under the program to boost partnership andcollaboration were the following: institutional (collaborative task force), planning (single plans for all), single informationsystems (web-based MIS), and support systems (facilitators). Use of ICT helps maintain a high level oftransparency in all aspects of the project cycle. All information about the project was made available on theprojects website, including payment advice from the State Treasury Office and audit findings. The policy of transparency andopenness aimed at creating public trust and confidence in the project. Investments in sanitationinfrastructure are important to secure benefits of hygiene and sanitation behavior programs in CDD projects. People in thevillages were not always able or willing to invest in private sanitation facilities. The project therefore provided communalsanitation facilities in schools and public locations so everybody would have access to sanitary facilities.
P116264 | Third Results & Accountability (REACT) Programmatic DPL | Latin America and Caribbean | Peru | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2011 | 2014 | 2016 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial |  |  | This review highlights the following lessons from the ICR:Ownership. Acritical success factor was the high level of government ownership of the policy reforms supported by the program. The Peruviangovernment strongly endorsed the case for more transparency about outcomes. Support for the program came both from the Ministry ofEconomy and Financeand from line agencies. This was coupled with broad public support (among civil society, the privatesector, and the press) for many of the reforms being implemented under the REACToperation.Participation. Support was also reinforced by the government of Perusgenerally participatory approach to policy reform. Multi-stakeholder dialogues were carried out at critical stages of policy designand implementation. This dialogue helped boost support from governmental and nongovernmental actors and counteract the resistanceof interest groups potentially affected by some reforms. Stakeholder engagement also helped mobilize the necessary politicalsupport for additional budgetary assignments to fund critical interventions to strengthen accountability and improve results ineducation, health, and nutrition. Perhaps more importantly, the participatory approach was at the core of the bottom-upaccountability measures promoted by the reform agenda, which encouraged the establishment of voice and client power mechanisms topromote awareness of poor quality in the provision of services among parents and policy makers and demand and track improvementsand results.Strong AAA work and accompanying operations. Much of the initialmomentum for the REACT Program was attributable to the impulse from RECURSO. RECURSO used mass media as a way to mobilizesupport for change and as a communication channel to inform parents about what they should expect for their childrensdevelopment outcomes. In addition, a package of services --includinglending and technicalassistanceinhealth, nutrition, social protection, and education --was critical in strengthening the implementation and sustainability ofthe policies supported by the REACT series.
P116273 | West Africa Regional Communications Infrastructure Program | Western and Central Africa | Western and Central Africa |  |  | Infrastructure | Transport | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/795621526400710959/text/Western-Africa-3A-West-Africa-Reg-Comm-Infrast-Progr.txt | http://documents.worldbank.org/curated/en/795621526400710959/pdf/Western-Africa-3A-West-Africa-Reg-Comm-Infrast-Progr.pdf | Two of the lessons that were developed by the ICR, are as follows (with some revisedlanguage): A more robust approach that tackles both demand and supply side of the ICT sector,ideally in parallel or a programmatic phased approach would ensure sustainability and ensure higher adoption rates to further drivedown costs. International connectivity infrastructure and national backbone infrastructure are key to creating supply sideeffects. The result has been increased penetration based on increased demand. The next stage is the development of digital skillsand creation of demand from citizens, businesses, government agencies, etc was outside of the scope of the project. Failing toaddress this this gap will result in citizens of both countries not leveraging the available capacity. For somedifficult reforms in the ICT sector such as privatization of an incumbent operator, passing a PPP law, a Development PolicyOperations (DPO) may be a viable option, particularly if the governance structures are weak. Despite their social,economic and historical similarities, Liberia and Sierra Leone had completely different experiences establishing their PPPs. Thedifference in outcomes can be attributed to government commitment, sector policies and governance structures. Moving forward, thestrength of governance structures needs to be assessed to determine the appropriateness and simplicity of PPP models. Wheregovernance structures are considered too weak to sustain the management of a PPP, then consideration should be given to includingDPO as an instrument to strengthen implementation.Using other regional project lessons, IEGdeveloped the following lesson: A thorough political assessment of high-level national commitment toregional commitment coupled with communication campaign is required for regional projects that include tough reforms. Forregional projects such as this,a communications strategy and implementing agencies is necessary to ensure that all stakeholdersunderstand the objectives and desired results of the project.
P116318 | SVP-Additional Grant Financing for the Water Resources Planning and Management Project - Phase II | Other | Africa |  |  | Sustainable Development | Water | RETF | IPF | 2009 | 2013 | 2015 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/686661475117360720/text/000020051-20150312115234.txt | http://documents.worldbank.org/curated/en/686661475117360720/pdf/000020051-20150312115234.pdf | The ICR draws an extensive number of lessons, most of which are specific to the Decision Support System. Lessons applicable more generally also to other Bank Operations are as follows: For a Bank team to provide sufficient technical support and encouragement requires adequate long term resources, appropriate team skills-mix, and attention to continuity of staff. The ICR calls for a better way to draw upon Bank professionals across the Bank. The division of roles and responsibilities between local/national professional staff and international consultants should be carefully considered in order to assure ownership and local sustained capacity. Lessons more specifically related to Decision Support Systems are: A decision support system has the potential to stimulate rigorous water management and cooperation between participating riparian states. The benefits of a decision support system take time to emerge.Public access to the tools and data is important to spread and maximize knowledge and understanding across the basin beyond the riparian governments. Developing data and information sharing protocols is critical for success. A DSS is a living asset that requires ongoing adaptation, refinement and software.
P116323 | Abidjan-Lagos Trade and Transport Facilitation Program - APL-2 | Western and Central Africa | Western and Central Africa |  |  | Infrastructure | Transport | IDA | IPF | 2012 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/418891591379503136/text/Western-Africa-3A-Abidjan-Lagos-Trade-and-Transp-APL-2.txt | http://documents.worldbank.org/curated/en/418891591379503136/pdf/Western-Africa-3A-Abidjan-Lagos-Trade-and-Transp-APL-2.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.1. The combination of hard and soft components in a first generationcorridor project canhelp in strengthening the overall impact of the regional program. Investment activitiesfinanced along the road, port and borders in this project, were complemented through trade facilitation awareness. The lesson isthat such projects can be a prelude to second generation corridor projects to include elements of growth and toencourage governments to improve coordination of joint regional reforms.2. Implementation readiness is keyto avoid potential delays and cost overruns. In this project, there was a long delay between the time when the technicalstudies were done and when the works had started (leading to additional degradations on the infrastructure). The technical designsneeded to be modified and this contributed to the cost overruns and delays during implementation. The lesson is that infrastructureprojects should ensure that all the required technical and economic studies are of high quality and, if needed, recruit specialiststo strengthen the client capacity.3. While counterpart financing can be helpful in raising the degree ofgovernment commitment, it isnecessary to ensure that the government provides proof of adequate budgetary commitment.About 40% of the appraisal estimate of the project cost in this project, wasto come through counterpart funding.Delays in mobilizing counterpart funding contributed to significant delays in implementing the infrastructure component of theproject. The lesson is that when counterpart funding of this magnitude is involved, it is necessary to ensure that the governmentprovides proof of adequate budgetary commitment and that this be made a condition of project effectiveness.4. Allmeasures available to the team (including hard decisions like the suspension of disbursement) should be used when important issuesare identified during implementation. The partial suspension of disbursements due to shortcomings insocial safeguards compliance in this project, served as the basis for increased high-level dialogue with the government. Duediligence measures (road safety and occupational health and safety measures)taken to lift the suspension,led toadditional positive outcomes which benefitted theworkers and the population living in the area of the projectinvestments.
P116353 | Higher Education Development Policy Program - Second Operation | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Education | IDA | DPF | 2011 | 2011 | 2016 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/115001468185394084/text/ICRR14827-P104694-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/115001468185394084/pdf/ICRR14827-P104694-Box394823B-PUBLIC.pdf | The series highlights the difference between changes in the legal framework and changes on the ground. It supported an ambitious package of reforms for all three operations. However, the reform's impact was perhaps less than could have been expected. One clear lesson is that the Bank has to look beyond the legal framework and take into account political considerations and the challenge of pushing a reform forward. The series showed how a DPO and an investment credit can support one another. The investment credit supported a great deal of the logistics necessary to monitor the reform. It also supported efforts to implement the steps required to turn the approved policies (prior actions) into reality. The overall reform benefits from this dual channeling of reform. The ICR's discussion of lessons (pages 27-28) also mentions these points. In addition, it introduces several other lessons, including: In Vietnam, consensus building takes time, and Bank support should reflect this. Likewise, the Bank's support can show flexibility in identifying prior actions for the next step of a DPO series. Identifying realistic outcomes is important, and too often DPO series focus more on developing prior actions and triggers. The selection of outcomes needs to take into account the time necessary for the policy to have impact. This was not the case for this DPO series, particularly for HEDPO I and HEDPO II.
P116354 | Higher Education Development Policy Program - Third Operation | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Education | IDA | DPF | 2013 | 2014 | 2016 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/115001468185394084/text/ICRR14827-P104694-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/115001468185394084/pdf/ICRR14827-P104694-Box394823B-PUBLIC.pdf | The series highlights the difference between changes in the legal framework and changes on the ground. It supported an ambitious package of reforms for all three operations. However, the reform's impact was perhaps less than could have been expected. One clear lesson is that the Bank has to look beyond the legal framework and take into account political considerations and the challenge of pushing a reform forward. The series showed how a DPO and an investment credit can support one another. The investment credit supported a great deal of the logistics necessary to monitor the reform. It also supported efforts to implement the steps required to turn the approved policies (prior actions) into reality. The overall reform benefits from this dual channeling of reform. The ICR's discussion of lessons (pages 27-28) also mentions these points. In addition, it introduces several other lessons, including: In Vietnam, consensus building takes time, and Bank support should reflect this. Likewise, the Bank's support can show flexibility in identifying prior actions for the next step of a DPO series. Identifying realistic outcomes is important, and too often DPO series focus more on developing prior actions and triggers. The selection of outcomes needs to take into account the time necessary for the policy to have impact. This was not the case for this DPO series, particularly for HEDPO I and HEDPO II.
P116384 | TG- Education For All-Fast Track Initiative Program | Western and Central Africa | Togo | IDA | FCS | Human Development | Education | RETF | IPF | 2011 | 2015 | 2016 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/192441468101662390/text/ICRR-Disclosable-P116384-06-01-2016-1464821809296.txt | http://documents.worldbank.org/curated/en/192441468101662390/pdf/ICRR-Disclosable-P116384-06-01-2016-1464821809296.pdf | The ICR presents a number of lessons (pages 31-32), including: A community-based approach to construction, whilea complex undertaking, can provide a number of important benefits. In this case, community-based construction of classroomsproceeded with fewer delays and cost overruns compared to that implemented by a construction management agency. Applyinga phased approach to development activities can pay high dividends in terms of its development effectiveness and impact. Inthis case, phasing of both community-based construction and training activities permitted learning-by-doing. Theestablishment of a robust FM system capable of tracking project expenditures at the beneficiary levelis most efficientlyimplementedat the design phase of any operation.In addition, IEG identifies threefurtherlessons: Revisions to a projects componentswill allow for appropriate ME only if theyoccursufficiently early in a projects lifecycle. In this project, restructuring occurred at a late stage in theprojectand thereforedid not allow for optimal ME and also necessary changes to safeguards. In particular,this project could have included additional output and outcome indicators thatwould have contributed to increasedunderstanding of quality of teaching and teaching materials, as well as how quality factorscan be better operationalized infuture projects and the impact of quality improvementson access and retention. Pilot studies conducted within aprojectcan onlyinform future project development and policy making if they are rigorously monitored andevaluated. In the case of this project, evaluation of the piloting of new textbooks in Mathematics and Reading, as well ascurricula for pre-school and literacy training and improving teacher practices, should have been carefully evaluated and reportedon. This represents a missed opportunity for learning. Consistent with experiences from other similar projects,designing an operation closely aligned with the governments ESP and PRSP and with strong government ownership and an emphasison capacity building at all levels is essential to effective implementation and sustainability. In the case of this project,the overall design and alignment with government priorities and preferred approaches contributed substantially to overalleffectiveness and sustainability of the project, as highlighted by the fact that many of the project activities are being continuedor scaled up under the follow-up project (PERI 2).
P116398 | Medium Cities Development Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2012 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099060623110527587/text/P1163980e54d110c809ed8036d18e3aba4c.txt | http://documents.worldbank.org/curated/en/099060623110527587/pdf/P1163980e54d110c809ed8036d18e3aba4c.pdf | The operations identified three lessons, slightly paraphrased below (ICR, paragraphs 83-85): ReasonableOM budgetcommitmentsand the political willto raisetariffs,need toform part ofconditionalityfor investing in project-financed infrastructure investments.In this project, the citiesprepared and implemented an asset management plan for project-financed infrastructure.The cities of Lao Cai andVinhdidnot have sufficient OM resources. Project design did include a covenant that requiredcitiestodevelopa roadmap towards cost recovery using tariffs, but its implementation was unclear.The underbudgeting of OMin Vietnamese cities persisted becauseother expenses were deemed more important. These cities remained marked byaresource-constrained environment. National-level policies continued to discourage increasing tariffs for wastewater andwater infrastructure. Clearly delineating the advantages and disadvantages in implementing multi-cityprojects supports flexible implementation. In this project, the multi city approach with similar project investmentsprovided some flexibility and economies of scale in implementing the project. A singularoverarching PDO supported by alimited number of outcome indicators focused the work toward achieving outcomes. Similar componentsfor each project city,facilitated efficiencyinassessingspecific needs and capacity. Additional financing to compensateforexchange rate losses and more time required because ofland procurement delays allowed targeted reallocation ofresources - more funds to build on the momentum of progress achieved. The alternative design was to have three separatecity-centered projectswith the same development outcomes. The disadvantage would have beenhigher administrative costs.The advantage would have been customized implementation periods for each city building on progress achieved to inform the design ofsubsequent implementationperiods. Realistic cost estimates usually informgoodprojectdesign but insubnational level projects in Vietnam, conservativetimelines may be more usefulwhenland acquisition and resettlement are involved.In this project, delays resultedfromlengthyland acquisition processes,resettlement needs that were more expensivethan anticipated atappraised, and uncertain availability ofgovernment resources. Risk assessment underestimatedthe cost of land and didnot foresee delays in the central governments provision of counterpart financing. When usingcounterpart funds for thepurchase of land as avital factor insuccessful implementation, conservative timelines may be more appropriateto consider.
P116410 | Eskom Investment Support Project | Eastern and Southern Africa | South Africa | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2010 | 2021 | 2023 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099050008302233590/text/P11641005ba39809e092dd021954cfbbc7e.txt | http://documents.worldbank.org/curated/en/099050008302233590/pdf/P11641005ba39809e092dd021954cfbbc7e.pdf | Of the several lessons in the ICR, the following two have high value for broad applicability andreplicability:Rushed preparation of projects identified as urgent can lead to larger problems than thosetheyare designed to solve: The Medupi and Kusile projects were rushed responses to counter the looming power crisis due topoor generation capacity planning. As a result, short-cuts, such as the use of a virtual design from another plantimplemented more than ten years before were used for the MCPP and these turned out to be unsuitable for the project. The projectthat was rushed to deliver energy in five years was completed only eleven years later and even then, is delivering power at levelswell below targets and industry benchmarks.Detailed knowledge of industry design standards and specifications forequipment through own staff and/or through experienced external engineering consultant services is critical for ensuring thatspecifications are consistent with the industrys capacity to deliver. Eskom prepared detailed bidding/contractspecifications with the objective of reducing quality problems based on many years of special experience with coal-fired plants.However, some OEMs have standard designs for their equipment, which are either expensive or not possible to change. The case withthe instrumentation and controls was an example, where the OEM did not comply with Eskoms specifications. Eskom thencanceled the contract, causing huge delays and a mix of controls in the plant to this day. Other contractors, especially localones, realized that they could not meet Eskoms specifications and did not bid, leading to few bids being received for somepackages. In such cases, Eskom could have requested waivers under the Public Procurement Preferential Acton local contentrequirements and used international bidding procedures. A further problem was that due to shortage of experienced staff andcomplexity of Eskoms project management arrangement, some deviations from specifications were not detected early, which mademaking changes difficult and costly and contributed to delays. (ICR, pp. 55-56)Understanding and securingagreement with the borrower and government agencies onthe timelines for critical decisions on their part is essential forsuccessful projectimplementation. Even though the World Bank had no prior experience of working with Eskom and theSouth African Government, it would have been possible to review the processes and timelines for key approvals or authorizationsneeded for implementing the project activities, such as those required under the Public Financial Management Act (PFMA) or forlicensing of renewable investments by the National Electricity Regulator of South Africa (NERSA). Specific decision timelines couldthen have been negotiated with the GoSA agencies for key activities and incorporated in implementation action plans. (ICR, p.56)
P116426 | EFA Fast Track Initiative Catalytic Fund Grant for Lesotho | Eastern and Southern Africa | Lesotho | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2010 | 2015 | 2016 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/428361468089963943/text/ICRR-Disclosable-P116426-05-02-2016-1462195123063.txt | http://documents.worldbank.org/curated/en/428361468089963943/pdf/ICRR-Disclosable-P116426-05-02-2016-1462195123063.pdf | Lessons drawn from the ICR (page 22), adapted by IEG: Innovative institutional arrangements (to foster efficiencyand sustainability) can be appropriate but require intensive analysis and preparation in the design stage. A phased approachmay be particularly useful in order to quickly incorporate lessons learned. A centralized procurement strategy forperipheral civil works, although initially counter-intuitive, can be more effective and efficient, since it consolidates small andscattered bids. In the case of this project, procurement for classrooms and latrines within thesameschoolswas adequately managed in one lot.In addition, Ateacher incentiveprogramcan bean effective approach to improving the quality of teaching in remote areas; however, the lack ofsustainability of such a program and the lack of timely evaluation of the results detract from the apparent short-term success ofthe program in this case.
P116437 | Education for All-Fast Track Initiative | Western and Central Africa | Cameroon | Blend | Non-FCS | Human Development | Education | RETF | IPF | 2011 | 2012 | 2013 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/689181475110793910/text/000020051-20140625225642.txt | http://documents.worldbank.org/curated/en/689181475110793910/pdf/000020051-20140625225642.pdf | The lessons presented in the ICR (page 23) are useful and should prove valuable to the government and to future IDA and EFA-FTI projects. In particular: Developing systems requires informed risks. Although the contract model was already established, the project was designed to deepen the government's ownership. The Bank was able to take advantage of its knowledge and experience in Cameroon to work with the government. Data are fundamental. While the project started out with a baseline, data collection was slow and did not appear to be used by the education sector. Simplicity in design can facilitate project implementation. The project had a simple and easy-to-understand design. This allowed both the government and the Bank to diagnosis problems and resolve them. It also helped to support specific government policy goals. In addition, IEG offers several complementary lessons: Simple projects can still benefit from complementary technical assistance and a robust monitoring and evaluation system to provide feedback to policy makers and the Bank. Technical assistance and research allow the government and the Bank to understand different options to improve the efficiency and equity of interventions. Dated covenants do not substitute for project readiness. One of the main justifications for changing this project into an investment loan was the need to strengthen financial management in the project, and this was to be done through a special audit. Instead, this special audit was delayed until near the end of the project.
P116441 | Ghana Education For All Fast Track Initiative | Western and Central Africa | Ghana | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2009 | 2011 | 2013 | ICRR | Less than 10 million |  | Unsatisfactory | Unsatisfactory | Unsatisfactory |  | http://documents.worldbank.org/curated/en/765621475112005698/text/000020051-20140625081455.txt | http://documents.worldbank.org/curated/en/765621475112005698/pdf/000020051-20140625081455.pdf | The ICR recorded the following lessons:Strong project supervision with knowledge of Bank procedures is important to avoid implementation complications. Significant project implementation problems need to be escalated to Senior Management quickly so that mitigation measures can be discussed and developed.Project design needs to set a realistic time frame for accomplishing the activities. Projects that include large procurement and packages of goods and civil works cannot be implemented in ten months.
P116520 | Timor-Leste Second Chance Education Project | East Asia and Pacific | Timor-Leste | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2011 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/534451525095108000/text/Timor-Leste-TL-Second-Chance-Education-Project.txt | http://documents.worldbank.org/curated/en/534451525095108000/pdf/Timor-Leste-TL-Second-Chance-Education-Project.pdf | IEG draws two main lessons from the ICRs account of the experience of preparing and implementing thisproject: When a focus on service delivery, however apparently urgent, precedes the establishment of a robust legal, policy,regulatory and institutional framework, systemic sustainabilitycan becomedifficult if not impossible to achieve, andthe quality of services may also be undermined.A focus on the systemic framework also coincides with the Bankscomparative advantage and normal emphasis. Lack of information and weak data management were identified asrisks during the preparation stage. Such risks need to be mitigated if their materialization is not to affect negatively both thepace and quality of project implementation and the ability to monitor projectoutcomes.
P116521 | Flexible and Open Distance Education Project | East Asia and Pacific | Papua New Guinea | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2011 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/816991497972827118/text/Final-ICRR-P116521-PNG-July-31-2017.txt | http://documents.worldbank.org/curated/en/816991497972827118/pdf/Final-ICRR-P116521-PNG-July-31-2017.pdf | The ICR (pp. 25-26) highlights several useful lessons, including: Extensive needs assessments whenre-engaging within a sector can help the Bank tobetter understand the sector,Government and implementing partnercapacity, and overall constraints in the sector. In this project, project staff poorly understand the time and effort required todesign and roll out curriculum and the capacity of staff to implement the project. Understanding the limitations ofexisting platforms for data collection is essential when creating project indicators. In this project, project staff assumed thatFODE staff had the ability to collect student-level information about course enrollment, test enrollment, and completion rates. Thedata system was limited, however, and a new system was produced only by the end of the project.Because of these limitations,theproject had torevise its objectives and indicatorsat the restructuring. Curriculum design anddevelopment takes time, and the project design phase is the appropriate point to conduct relevant and appropriate curriculum needsassessments. After 40 years of not updating the FODE curriculum in PNG, it was considered necessary to update all subject mattermodules for Grades 7 12 curricula (ICR, p. 25).
P116542 | AFR:Central African Backbone - APL1B | Western and Central Africa | Western and Central Africa |  |  | Infrastructure | Transport | IDA | IPF | 2011 | 2013 | 2014 | ICRR | Less than 10 million |  | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/146641475074047944/text/000020051-20140626111604.txt | http://documents.worldbank.org/curated/en/146641475074047944/pdf/000020051-20140626111604.pdf | The following lessons may be drawn from the experience of this cancelled operation:Regional projects requiring close coordination between two or more countries involve considerably high risk than projects in a single country, when there are differences in commitment to project goals between the countries and in the capacity necessary to achieve them. In this case, a de-linking of the countries in the initial stages could have enabled progress in the CAR. The coordination necessary to ensure the physical interconnection of the regional infrastructure and the international institutions to be put in place to manage the regional backbone could have been designed and established at a later stage.When substantial redesign is necessitated by an unforeseen exogenous occurrence, a careful analysis of the consequences of the change, and the introduction of appropriate compensatory measures, is essential to create a possibility of achieving the projectâ€™s goals. In this case, Cameroonâ€™s withdrawal from the CAB Program significantly altered the parameters of the project and made achievement of its original objectives considerably more difficult. Except for planning an alternative connection to that which was planned through Cameroon, little was done to address the issues caused by the withdrawal, despite warnings from the advisers about the considerably reduced attractiveness of the PPP arrangements in Cameroonâ€™s absence.Sending an inadequately prepared project to the Board, and changing complex and numerous pre-Board conditions to effectiveness conditions, greatly increase the possibility that the project will not succeed. In this case, the decision to proceed rapidly to Board presentation appears to have been motivated by the availability of IDA resources that would otherwise have been lost. However, it is difficult to argue that they were put to good use.
P116557 | First Development Policy Loan in support of the Plan Maroc Vert | Middle East and North Africa | Morocco | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | DPF | 2011 | 2012 | 2016 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/571301467987909640/text/ICRR14830-P116557-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/571301467987909640/pdf/ICRR14830-P116557-Box394823B-PUBLIC.pdf | IEG supports the three lessons identified in the ICR, has rephrased them below:(i) Incentives for for stakeholders: In the case where incentives for the Finance Ministry and the sector ministry are aligned, the synergy is powerful. In these circumstances, the Bank can still add considerable value beyond just resource transfer by further analytic work to help finalize and operationalize the program and to prepare for its implementation;(ii) Ownership/Coordination: An additional value of Bank support using a DPL operation is to help create a platform for agencies collaboration that otherwise may have divergent agendas. The Bank can also contribute to transparent, evidence-based and objective dialogue around thorny issues, including political economy constraints to reform implementation.(iii) Value added of DPLs and MTEF: The linking of a DPL to a sectoral MTEF aligns incentives for both the Finance Ministry and the line ministry, and provides investment resources to accompany and help implement reforms that otherwise might not take place or might not yield their intended returns.
P116595 | Eastern Nile First Joint Multipurpose Program Identification (JMP1 ID) | Other | Africa |  |  | Sustainable Development | Water | RETF | IPF | 2010 | 2013 | 2016 | ICRR | Less than 10 million | Highly Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/190481468185395882/text/ICRR14873-P116595-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/190481468185395882/pdf/ICRR14873-P116595-Box394823B-PUBLIC.pdf | These draw partly from the ICR evidence and findings but with adjustment of language.Careful assessment at preparation and continued monitoring of government ownership, commitment and political changes should be a priority in regional projects that involve a number of countries with possibly different and/or conflicting agendas. In this project initial assessment of the depth of commitment may have been optimistic and more sustained and deeper assessment of what was politically feasible would have been important to manage expectations and to align targets to achievable results. There is a need to be realistic about the time required to implement complex regional projects. In this case there was excessive optimism about what could be achieved in a short project period in a project involving several government partners with different agendas.In a partnership project with several countries, it is important to secure at the outset a common understanding among partners of the level and type of analysis needed, as well as the level of effort required of all parties. In the context of this project, while SSEAâ€™s are relatively new tools and therefore inherently challenging, the complexity of the JMP1 ID SSEA in this case was further complicated by the size of the project area and its transboundary nature. It is critical to develop and agree on terms of engagement which would specify the required resources, (financial and personnel), the time frame of analysis, and the level of effort required from the implementing agency, governments, local authorities, other stakeholders and those conducting the analysis.
P116602 | Urban Local Government Support Project | Western and Central Africa | Mali | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2020 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/545401603815322277/text/Mali-ML-Urban-Local-Government-Support-Projec.txt | http://documents.worldbank.org/curated/en/545401603815322277/pdf/Mali-ML-Urban-Local-Government-Support-Projec.pdf | The ICR offered as many as 20 lessons and recommendations thatfuture similar operations may consider. The report presentedthe lessons into seven categories: operating within a Fragile, Conflict, and Violence-affected (FCV) environment (2); supportingdecentralization (7); institutional arrangements (2), project design (3); ME (2); implementation (2);and compliance withsafeguards and fiduciary requirements (2). Some of these lessons are provided below. Projects implemented inFragile, Conflict, and Violence-affected (FCV) countries may benefit from incorporating benchmarks totrigger resourcereallocation or restructuring as part of measures to mitigaterisks from escalatingfragility. In this project,despite a long history of conflict in Mali, conditions were stable at project start. Shortly thereafter, conditions deterioratedfollowing the 2012 coup dtat. Implementation was suspended until implementation could safelyresume.Future project design may identifyconditions, benchmarks, and indicators that could trigger remote monitoring,restructuring, or resource reallocation.Theresults framework may include thosetriggersto achieve thePDO. Aperformance-based grant systemmay be an effective vehicle to build capacity and providepredictable, transparent inter-governmental transfers. In this project, the central government assessedthe performance of a local government against agreed upon criteria. These criteria aimed to strengthen local government capacity toplan, manage, and deliver services. This periodic assessment facilitatedan improved relationship between the central and thelocal governments. This assessment also helped define an effective role for the central governmentundertakingdecentralization. In addition, this project was restructured to introducea consultative process in achievingperformance-based criteria. Thisimproved citizen participation, fostered accountability, and encouraged transparency.Positive feedback on citizen engagement, including at the neighborhood and village development committees, resulted in theirinclusion in the design of the follow-on Decentralization project. Risks associated withpassing newlegal measuresmay signal the non-readiness of a project activity.In this project,appropriate laws werestill beingfinalized during project implementation before support could be given to the Greater Bamako district activity.Risks from legislative delays were not adequately assessed and the delay resulted in the activity being dropped. Fundswereinstead used to add 5 more target ULGs.
P116608 | Mauritius Fourth Development Policy Loan | Eastern and Southern Africa | Mauritius | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2012 | 2013 | ICRR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | High | http://documents.worldbank.org/curated/en/713521475098269117/text/000020051-20140625192948.txt | http://documents.worldbank.org/curated/en/713521475098269117/pdf/000020051-20140625192948.pdf | IEG concurs with the ICRâ€™s findings that the success of the reform program in Mauritius was largely due to strong government ownership and a participatory approach which involves all key stakeholders in society. Close coordination with key donors in harmonizing conditionality enabled the government to implement a single comprehensive reform program. An important lesson from Mauritiusâ€™s experience is that the ability to respond to new challenges is essential for successful implementation of the reform program. The program was also sharply focused and internally consistent and therefore easier to implement and monitor.
P116656 | Zhejiang Qiantang River Basin Small Town Environment Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2011 | 2017 | 2018 | ICRR | >=50 million & <100 million | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/648791510407747809/text/ICRR-Disclosable-P116656-11-11-2017-1510407735750.txt | http://documents.worldbank.org/curated/en/648791510407747809/pdf/ICRR-Disclosable-P116656-11-11-2017-1510407735750.pdf | The ICR selected three lessons from the ICR, with some adaptation of language. Realistic financingmechanisms, with costs borne by tariffs/user fees and higher level government subsidies ,can help in financing small towninfrastructure. Small towns have relatively weak financial capacity to build and operate environmental infrastructure. Inthis project, the city/county level governments who were responsible for loan repayment, financed the capital cost of buildingwastewater and solid waste management in small towns. The OM costs of wastewater and solid waste components were borne by acombination of tariff/user fees and government subsidies. This arrangement addressed the financial challenge in small townsandmobilized resources from both governments and users, and thereby ensuredsustainability. Preparing and implementingOM plans and financial projections areinstrumentalfor improving financial and institutional sustainability of small-town environment infrastructure.Preparation of OM action plans and financial analysis mandated as legal covenants in the case of this project contributed toensuring OM sustainability. The differential tariffs incentivized the locals to reduce their wastewaterdischarges. It is important that technical design of environmental infrastructure in smalltownsistailored to local circumstances to ensure cost-effectiveness. In the case of this project, theoriginally proposednew small-scale WWTPshad to be given up based on comparison of options and cost-effective analysisduring implementation.
P116666 | Tanzania Poverty Reduction Support Credit 8 | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2011 | 2013 | 2012 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/714031474571401951/text/000020051-20140625065432.txt | http://documents.worldbank.org/curated/en/714031474571401951/pdf/000020051-20140625065432.pdf | There are four important lessons:1. Realistic monitoring frameworks are important tools for effective reform, important for government, but also for the Bank and other donors. MKUKUTA, well intentioned though it was, clearly provided an overly optimistic and ambitious framework for monitoring and evaluation. As the Bank modified its approach to monitoring over this PRSC series, it produced a more meaningful framework. Still, the use of WBI governance indicators is not ideal, as they are measures relative to other countries, whether or not such countries are comparable to Tanzania. Poverty head counts were (and are) only available with a considerable lag, and so cannot reflect current progress, even though having the desirable property of broadly capturing progress, or lack of it. 2. There are drawbacks to long term commitments of budget support which need to be carefully weighed against the benefits, in terms of government efficiency, of being able to count on budget resources over time. In this case, it appears that not only was there a downward trend in performance, but that donor support may have also contributed to what appears to be a sustainability issue -- the high level of government expenditures relative to GDP, and, within that, the high level of wages. 3. Stationing key staff in country offices is important in enabling the Bank to provide good advice, even if that does not always translate into results. This good practice should be continued. 4. Far-reaching reform programs need to be carefully tailored to human capacity constraints. In this case, the sophisticated process supporting implementation outpaced the human resources available, especially on the government side, which was also limited by availability of dependable office communications (such as email). For the future, the Bank should seek to support reform programs more realistically grounded in capacity.
P116666 | Tanzania Poverty Reduction Support Credit 8 | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IDA | DPF | 2011 | 2013 | 2013 | PPAR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/542381468133184866/text/781880PPAR0Tan00Box377382B00PUBLIC0.txt | http://documents.worldbank.org/curated/en/542381468133184866/pdf/781880PPAR0Tan00Box377382B00PUBLIC0.pdf | 4. Lessons 4.1 The implementation of PRSCs 1-8 spanned nearly a decade during a period of sustained macroeconomic stability and fast economic growth, offering lessons both for Tanzania and other countries with similar development challenges. 4.2 Lesson 1\. Direct and sustained focus and clarity of vision over the entire course of implementation of PRSC programs that cover many years is required to facilitate lasting reforms particularly with regard to public sector governance. There is a significant risk of backsliding when attention is shifted to other priorities. Yet joint budget support is a messy attempt to reach a common understanding, always subject to change, with a wide range of domestic stakeholders and international development partners. In Tanzania, intense dialogue and very high government commitment led to early successes in improving public financial management and budget execution in the first PRSC series. But some achievements stagnated or were reversed in the second series, when attention was diluted to include a broad range of sectoral reforms and other aspects of governance. 4.3 Lesson 2\. PRSCs can make little progress without a foundation of trust between the Bank and the government, and among development partners at the institutional and individual levels. Without sufficient trust, negotiated and agreed-upon triggers can quickly be transformed into more heavy handed conditions, whereby the level of future support is determined by strict adherence to pre-identified policy changes. In these circumstances, a scaled-back operation, more tightly focused around areas of agreement might gain more traction than one used as an enforcement mechanism for previously agree reforms that no longer have political backing. 4.4 Lesson 3\. PRSC programs risk becoming irrelevant if the design, scale, and scope are not adjusted as conditions change. The advance expectation that such changes will occur may smooth the transition should events warrant a scaling back of the program. Circumstances changed substantially during the second PRSC series in Tanzania\. reform champions in government and among development partners moved on; the presumption that sustained growth of 6-8 percent would lead to significant poverty reduction proved false; a new President was elected; and the country was affected by higher food and fuel prices and by the global financial crisis. The mechanisms for dialogue also need to evolve so that the program can continue to support and influence policy decisions at the highest strategic level. To avoid misunderstanding, the Bank and government could plan in advance to recalibrate the program at a set point during implementation. 4.5 Lesson 4\. The lack of well-defined and realistic objectives and a fully developed results framework makes adjustment to changing circumstances difficult. A results framework that clearly explains how policy actions are expected to lead to desired outcomes, in light of the support provided through investment lending and by other development partners, can provide a results-focused discipline to the program, improving selectivity in the process. 4.6 Lesson 5\. Regular reporting on key outcome indicators is essential so that data can drive adjustments to the PRSC program. Adequate investment in statistical capacity and the creation of a robust monitoring and evaluation system that addresses each step of the results chain to identify the key drivers of success or failure, while remaining focused on a few key outcome indicators, can help guide long PRSC series as circumstances evolve. Policy makers need to be aware of trends in outcomes in order to adjust the program accordingly. In Tanzania, reliable data on, for example, income poverty were available only once every seven years or so. Interim poverty simulations suggested significant poverty reduction as a result of sustained growth, but these projections turned out to be inaccurate. Household surveys every 3-4 years could provide much more timely and meaningful data to policymakers to allow for evidence-based adjustments during implementation. 4.7 Lesson 6\. Transitioning to the use of PRSCs as the primary instrument for resource transfer is only likely to be successful in rare circumstances, when strong central ministries can fully pursue a sector-inclusive dialogue representing the perspectives of key players throughout government. PRSCs themselves have very limited leverage in sector ministries, and the number and specificity of sector-specific triggers are necessarily curtailed when many sectors are covered. 4.8 Lesson 7\. Elevating to the national dialogue sector-specific structural reforms that stalled at the sector level does not guarantee their implementation. Even as the depth of sector exposure and experience permitted the sector content to be brought opportunistically into the PRSC, there is no evidence that this accelerated sector reforms or achieved greater cross-cutting momentum. Indeed, many of the same obstacles can prevent these reforms from taking hold, as was the case in energy, transport, agriculture, and water. Moreover, policy reforms committed to by central ministries are likely to be seen by implementing agencies, less vested in the PRSC program, as externally-imposed conditions, and subverted rather than adopted.
P116680 | Energy Efficiency Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2012 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/204681496781690771/text/ICRR-Disclosable-P116680-06-06-2017-1496781685441.txt | http://documents.worldbank.org/curated/en/204681496781690771/pdf/ICRR-Disclosable-P116680-06-06-2017-1496781685441.pdf | The ICR provides the following key lessons, as paraphrased here: The creation of a Government institution toimplement Energy Service Agreements (ESA) with public sector institutions can be an effective model for introducing and testing theconcept of energy savings investments. The Energy Service Agreement (ESA):(I) allows public institutions to financeEE without incurring debt, (ii) retains energy cost savings for the duration of the ESA, and (iii) outsources procurement,management and risks to a third party. Because ESAs involve long-term investment paybacks, grants are needed to provideboth the initial and expansion working capital. Net Present Value-based bidding encourages innovation and theintroduction of new technologies that can have a significantly impact on cost efficiency. A comprehensive ME programthat includes measurement and verification of individual subproject outcomes proved to be an essential element in the successfulimplementation of the ESAs andNPV-based decision-making. The beneficiary and contractors all monitored subproject performanceindicators (indoor temperature, lighting intensity, energy bills, etc.), which helped minimize disputes among thestakeholders.
P116680 | Energy Efficiency Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2012 | 2016 | 2019 | PPAR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/357251558102995116/text/Armenia-Energy-Efficiency-Project.txt | http://documents.worldbank.org/curated/en/357251558102995116/pdf/Armenia-Energy-Efficiency-Project.pdf | 5. Lessons 5.1 Energy efficiency revolving funds can be market enablers by partnering with commercial and financial institutions, but there are few prospects for scale up and energy efficiency market transformation without the commitment of private businesses. Ultimately, the domestic financial sector is the key source of sustainable energy efficiency finance. Piloting new models for energy efficiency service provision needs to create suitable local conditions and develop the capacity of commercial financiers through initial cofinancing and risk mitigation. The R2E2 Fund in Armenia did not make systematic efforts to work and partner with financial institutions and other commercial players in the implementation of energy efficiency subprojects. The approach of creating a model of energy services provision for which the R2E2 Fund is the main agent and construction companies are largely passive implementing subcontractors limits longerâ€term market impacts. In such a setting, the risks of continuity of energyâ€saving services become the risks of the continuity of the revolving fund itself. 5.2 Practical demonstration of the technical and financial feasibility of an innovative energy efficiency transaction program can only influence positive systemic change in the legal and regulatory framework if there is government commitment to the approach and longâ€term funding. A new financing agreement was piloted under this GEF project to enable public entities to implement energy efficiency retrofits without affecting the budget of the subproject entities. As a result, public organizations were able to enter into financing agreements that paid for the investment through future monetized energy savings. However, without sufficient government oversight and commitment to these approaches, the sustainability of the model is impossible. The government adopted ESAs as sample agreements for energy efficiency procurement only for the project's duration, and ESAs cannot be applied after project closure. The project demonstrated the actual energy efficiency improvements have the capacity to repay the investment, but this requires legal support, access to capital and a system for the application of savings to future investment. 5.3 Appropriate legislation and regulation can provide incentives to undertake energy efficiency measures, but they are not sufficient without a strong government energy efficiency agency in place that is responsible for monitoring and enforcement. The energy efficiency regulatory and legal framework has advanced significantly (attributable to the project in part), but enforcement and actual implementation are still lagging in several dimensions. Although the government enacted a new modality of energy efficiency delivery in the public sector that was operationalized successfully under the project, it has not followed up with measures to ensure a wider replication and scaleâ€up. A market transformative policy function cannot be farmed out to a revolving fund or a public energy service company lacking authority. The government of Armenia has no effective institutional focal point for energy efficiency implementation support, though this is critical for the wider diffusion of the successful energy efficiency delivery mechanisms in the public sector. As a result, international donors largely set and implement Armenia's energy efficiency agenda. 5.4 The design of a pilot project needs to go beyond demonstration effects and lay the foundation for sustainable operations over time. Although this energy efficiency project effectively targeted public facilities with the highest potential for energy savings, essentially harvesting lowâ€hanging fruit, the broader project experience revealed that many public buildings in Armenia did not comply with the eligibility criteria. They are in a poor state of maintenance and repair that would require substantial investments in structural rehabilitation, not just energy efficiency retrofits. Energy cost savings alone supported by the project will not be sufficient to cover the required investments in these buildings unless supplemented by concessionary budgetary funds or grants. Instead of being developed as a direct payment agent to finance the retrofits, the R2E2 Fund could have focused on enabling commercial financing by acting as an intermediary guarantee fund. As a guarantee fund, it could have fully deâ€risked principal payments to commercial banks on a rolling basis, thereby attracting commercial financing. However, because the R2E2 Fund made direct payments, it largely decapitalized itself without leveraging its initial funding to attract commercial financing.
P116681 | IRRIGATION REHABILITATION EMERGENCY PROJECT | Europe and Central Asia | Armenia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2010 | 2013 | 2014 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/699831475116462778/text/000180307-20141203043837.txt | http://documents.worldbank.org/curated/en/699831475116462778/pdf/000180307-20141203043837.pdf | The following lessons are emphasized in the ICR: Projects that are simple in design and singularly focused perform well and have a high likelihood of achieving their objectives. The project design was guided by the fundamental principle of rapidly commencing project activities and generating rural employment to the maximum extent possible to address the growing threat of poverty from the prevailing economic and fiscal crisis. The project comprised two straight-forward, well targeted components that lent themselves to swift and efficient implementation. Also, the benefits of simple projects are relatively easy to disseminate among the local populations which stimulates a high degree of buy-in and support.Addressing priority needs of local populations is critical for the successful implementation of rural development projects. By targeting the most pressing needs of the local communities, the project generated much support and good will among the local populations which ensured its success right from the start. In this context, placing local people at the center of the whole implementation process has the added benefit of encouraging and enhancing beneficiary participation in decision making in rural development assistance efforts. This results in better designed projects that have a higher likelihood of implementation success.\Projects prepared rapidly must have in-built flexibility to respond to emerging needs and situations. Projects prepared on a fast track basis often have limited time for detailed preparatory work and adequate due diligence. This opens the door to encountering issues during project implementation that the team might not have faced had there been sufficient time for thorough preparatory work. It is therefore critical that a strong element of flexibility is built into project design so that project activities can be adjusted and issues that may arise during implementation can be addressed rapidly and appropriately.Irrigation Projects can provide an important safety net for rural populations, especially during times of economic downturn. The project demonstrated that irrigation projects can serve as a significant source of public employment. Irrigation projects do not necessarily need to be designed as capital-intensive efforts. A labor-intensive design is in fact preferable under certain circumstances, such as times of economic downturn, when rural populations are facing rising unemployment and loss of incomes.Establishing and strengthening Water User Associations (WUAs) is a long-term undertaking. While organized user groups are essential for solving irrigation management problems and sustaining the physical infrastructure of the system, there is no â€˜blue-print,â€™ one-size fits all institutional model for setting up a WUA. Given the complex and diverse management problems of irrigation systems, establishing and strengthening WUAs is a time intensive effort that requires several years of sustained support by the Government.
P116696 | Kazakhstan - Tax Administration Reform Project | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2010 | 2022 | 2024 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099100423092511739/text/P1166961d1ced33b18d6c14d701a8bf14f063ad73b6b.txt | http://documents.worldbank.org/curated/en/099100423092511739/pdf/P1166961d1ced33b18d6c14d701a8bf14f063ad73b6b.pdf | The IEG concurs with the lessons drawn from the ICR, which included: The instrument usedshouldreflect the nature of the change sought. Inthis case, Development Policy Financing might have provided greaterincentives for the government to implement reforms, compared to Investment Project Financing. The ME frameworkshould be not only well designedbut carefully monitored to provide early alerts when project implementation is beingconfronted with challenges.Further, IEG finds that the adoption of an ITMS should carefully consider anyinstitutional and political factors that may delay or prevent its adoption. In this case, the merger of the tax and customsservices limited SRCs ability to design and to launch the process, along with the adoption of the e-government digitalstrategy thatwas a pre-requisite to the completion of a feasibility study for the IT component.
P116748 | Electricity Supply Reliability Project | Europe and Central Asia | Armenia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2011 | 2024 | 2025 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial |  |  | IEG derives the following lessons drawn from the ICR:1. Investments in transmission grid strengtheningneed to be accompanied by tariff and other reforms. Transmission grid investments are often considered public goodsto be financed by concessional borrowing. However, there can be a significant disparity between the economic and financialviability of the transmission network. Tariff reforms are often necessary to ensure the commercial viability of theseinvestments. This is borne out by the economic and financial analysis of the project, which showed a wide disparity betweenthe economic and financial rates of returned estimated by the ICR (Annex 4, p.38), with the EIRR based on an imputedwillingness to pay of consumers at roughly four times the current tariff calculated at 15 percent, against anFIRR, based on actual tariffs, of only 5 percent.2. When bundling several individual infrastructureinvestments into one project, sequencing of the investments becomes critical. In the project, therestructurings of 2014 and 2017 introduced substation investments that could only be implemented in phases, for technicalreasons. As a result, procurement of the last of these substations could only be started in 2020. In hindsight, thiscould have been avoided with closer attention paid during preparation of the restructurings to the alignment of disbursementprojections, procurement and technical planning.3. The use of reputable engineering, procurement andconstruction (EPC) contractors and owners engineer firms for project implementation and supervision can enhance theeffectiveness and efficiency of projects involving design, procurement and construction activity, irrespective of the implementingagencys technical capabilities. The project demonstrated that the advantages of maintaining an arms-lengthrelationship can help ensure clear accountability for project execution. The owners engineer can provide moreobjectivity to protect the borrowers interests. During the projects implementation, when attempts were made toproceed without external contractors or a supervising engineer, this led to unfavorable outcomes.
P116774 | Social Safety Nets & Employment Support Project | Europe and Central Asia | Bosnia and Herzegovina | IBRD | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2010 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/865861475166451177/text/ICRR-Disclosable-P116774-09-29-2016-1475166434832.txt | http://documents.worldbank.org/curated/en/865861475166451177/pdf/ICRR-Disclosable-P116774-09-29-2016-1475166434832.pdf | These lessons are drawn by the IEG review:Reform in transition economies is difficult: transition (andtransitioning) economies are often rooted in tradition, and prior systems will create winners and losers.Introducing reforms requires a rigorous assessment of readiness to undertake change that results in winners and losers. InBH, the introduction of better targeting and more relevant coverage was likely to do so. The introduction of mitigatingcircumstances was necessary. In the case of this project, the inclusion of a job brokerage and employment support componentwas to serve that purpose by facilitating the integration of the losers, e.g. the ones rejected from the socialassistance system, into the labor market, essentially developing a springboard out of indigence.Having a cleargovernment reform strategy in place at the outset is essential for introducing new institutions. Having onesignifies political acceptance of change and facilitates mobilizing the government bureaucracy to apply new procedures andinstitutions. In BH, government commitment to safety net reform was not obvious at any point in time, except as a means tobetter budget balance, and this affected the outcomes of the project.The following lesson is selected from the ICRreview:A communications strategy can be an important means to facilitate reforms in order toinfluence deeply held and politically and emotionally charged mindsets by informing the public of facts and lifting the publicdialogue to debate numbers and fact rather than emotionally charged history. In BH, the communications strategy related to a policynote preceding the project was able toenter the rights-based debate and distinguish between rights-based (those who need andthose who are not poor) versus entitlement-based benefits.
P116783 | Senegal EFA-FTI Catalytic Fund | Western and Central Africa | Senegal | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2010 | 2015 | 2016 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/809841468332416745/text/ICRR-Disclosable-P116783-03-14-2016-1457971738725.txt | http://documents.worldbank.org/curated/en/809841468332416745/pdf/ICRR-Disclosable-P116783-03-14-2016-1457971738725.pdf | Lessons drawn from ICR (pages 29-30) and adapted by IEG: A multi-phase approach to construction helps to takestock and modify activities as needed. In the case of this project, although aformal evaluation of phase oneconstruction activities was not conducted as planned, a technical analysis was still carried out and led to introduction ofsignificant changes, most notably the addition oftwo construction management agencies,to increase the pace ofconstruction. The use of a standardized architectural design for classrooms can contribute to efficiency and ensureadherence to quality standards. In the case of this project, although there were some initial challenges in technicalcapacity to build according to specifications, the quality of civil works was considered overall satisfactory. Alignmentwith the governments sectoral program helps to increase efforts at coordination. In the case of this project, thegovernment lent strong support to coordination among donors, as several different projects were being implemented in support of thecommon goal to achieve universal primary education. Analytic work carried out during implementation can have meaningfulimpact on the direction and pace of reform. In this case, the 2010 survey undertaken with Bank support facilitated deeperunderstanding of the factors driving high repetition and dropout rates at the grade 1 and grade 5 level, leading to importantpolicy changes.
P116787 | Programmatic Financial Sector Development Policy Loan | Europe and Central Asia | Montenegro | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2012 | 2013 | 2015 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/783241475117831338/text/000012394-20150109131207.txt | http://documents.worldbank.org/curated/en/783241475117831338/pdf/000012394-20150109131207.pdf | The following lesson is taken from the ICR with some adaptation of language:Close coordination on policy dialogue and technical assistance with other partners, such as the IMF, EU, and EBRD, may be particularly effective in the case of a financial sector DPL, given the complementarities in partnersâ€™ expertise and areas of interest. The following lessons are drawn by the IEG: Two related policy-based operations could be a rational strategy when there is a clear need for the extended period of policy dialogue and technical assistance to ensure sustainability of policy reforms. The use of a policy-based guarantee (PBG) (instead of a traditional DPL) would not undermine the effectiveness of such a strategy if the policy triggers for a PBG remain meaningful and consistent with the objectives of the entire strategy.Sustainable recovery of the banking sector requires a clearer strategy for resolution of the problem of non-performing loans (NPL). Insufficiently addressed NPLs is retarding the development of the financial sector in both short and medium term, regardless of progress made on the legal, regulatory and supervision sides.
P116846 | Clean Production & Energy Efficiency | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2012 | 2017 | 2018 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/580011528129407761/text/Vietnam-VN-GEF-Clean-Production-Energy-Efficie.txt | http://documents.worldbank.org/curated/en/580011528129407761/pdf/Vietnam-VN-GEF-Clean-Production-Energy-Efficie.pdf | In the ICR, lessons and recommendations are provided in paragraphs 80 to 86, of which the main ones are quotedbelow:(1) Targeted policy-based interventions are effective ways to build stakeholder capacity, strengthenthe sector dialogue and gather the analytical data required to design larger-scale follow-up interventions.(2) Lack ofsupporting financing mechanisms is a barrier to the scale-up of EE actions, especially for entities that have a weak financingcapacity and limited access to capital markets.(3) Lack of adequate measuring, reporting, and verification (MRV) systemsat the national level weaken the ability to monitor and enforce laws and regulations and potentially undermine the long-termeffectiveness of policy interventions.(4) Timely design and implementation of the ME framework is critical to themonitoring of project progress and the assessment of project outcomes.In paragraph 84, the ICR notes thatVAs constitute an innovative approach for promoting EE, but that they have a limited impact on EE improvement, and that parallelsupport mechanisms and incentives should be provided to VA enterprises to maximize the impact of the VA approach. IEG notesthat the pilot VA program was not officially launched untilDecember 2016,six months before the actual closing of theProject, and so it appears rather premature to opine onits effectiveness. The follow-on EE investment projectswill support additional measures including financial incentives to scale up the VA approach in industrial sectors. The impactof the VA approach therefore remains to be tested. Alarger question therefore remains as to whether this will be aneffective approach over the long term. Course correction may be needed over time as the extent of demonstrated resultsbecomes clear, with a possible need to move to a mandatory enforcement approach, for exampleas recently seen inChina.IEG also notes that the Project result indicators did not specify any criteria for the appropriate orminimum level of EE ambition of the MoITs industry action plans and circulars (e.g. minimum 10% improvement of EE per unit ofproduction in a specified time period). Attention to this could be warranted, given that they constitute key sectorregulations that will drive the progress of EE improvements in the relevant industrial sectors. IEG does acknowledge theresult measurement challenges posed by a Project such as this that is basically TA that is supportinganEEtransformation ina rapidly evolving and highly competitive industrialecosystem and a relatively weakinstitutional and regulatoryenvironment.
P116860 | Local Government Capacity Building Project | Middle East and North Africa | West Bank and Gaza |  | FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2005 | 2012 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Negligible | http://documents.worldbank.org/curated/en/883151475085662263/text/000020051-20140626000900.txt | http://documents.worldbank.org/curated/en/883151475085662263/pdf/000020051-20140626000900.pdf | Â· Implementing improved financial management in local governments is an essential element of improving local governance and oversight, but it must be resilient to management changes, technical challenges, and possible contractual disputes during implementation.Â· Full project appraisal to ensure high quality at entry is essential for a satisfactory outcome. The decision not to carry out a full design in this case resulted in some activities not being properly appraised. Even those projects which do not formally require full appraisal and documentation could well benefit from going the extra mile by documenting the project fully in a standard format, to make sure that lessons learned are incorporated and risk is properly evaluated.Â· Impact of changes in Bank Policy for projects under implementation should be not be underestimated and should be well communicated to Clients.During the seven year life time of the project, Bank policies and procedures changed several times. They included instituting a new Bank reporting system. While such changes can be expected during the course of a project, they should be communicated to clients beyond the project level.Â· Operating in conflict environments necessitates a high level and creativity of supervision, especially for projects aimed at institutional and financial reform. While this operation achieved positive, but limited results, its financial reform element was in jeopardy for extended periods of time, due to contractual disputes aggravated by volatile macro-context. These were only overcome thanks to additional efforts by all parties,including strong engagement by the Bank supervision team and management and use of video conferencing to communicate with staff and beneficiaries in GazaÂ· When needed as it often can be in conflict areas, project restructuring should be encouraged, with clear instructions and guidance to task teams. In hindsight in this case, it was clear that restructuring was overdue without their being any formal reason for not pursuing it. The lack of restructuring, notwithstanding the minor amendments of the last two years of implementation, allowed the project to drift away from a results framework and its M&E that could have guided the operation toward a more successful result. Â· Innovation in important areas such as local government financial management needs to take into account the real technical capabilities locally to implement the proposed changes.
P116919 | Alma Transmission Project | Europe and Central Asia | Kazakhstan | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2011 | 2015 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/559141471040533156/text/ICRR-Disclosable-P116919-08-12-2016-1471040525340.txt | http://documents.worldbank.org/curated/en/559141471040533156/pdf/ICRR-Disclosable-P116919-08-12-2016-1471040525340.pdf | The following lessons learned are consistent with those in the ICRs second, third and the fourth lessons (p.21,ICR).1 Bank standard prequalification criteria may not always be efficient and effective for selecting a qualified contractor ata reasonable price for a turnkey EPC contractor where a tight delivery period is critical. Thus, in appropriatecircumstances, it would be worth considering prequalifying only those companies experienced in similar turnkey contracts to beimplemented within a short period and outside of the country of their origin. On the other hand, this would reduce competition.2 Lack of consistent andclose involvement of a Bank team member can result in excessive project implementation delays and being out of compliance withcovenants in the LA. 3 The development oflong relationships with the implementing agency can help overcome implementation delays to complete the project on time and achievethe PDO. The project provided this lesson from the LAP and its experience with turnkey contractprequalification.
P116923 | Abyei start up emergency project | Eastern and Southern Africa | Sudan | IDA | FCS | Infrastructure | Urban, Resilience and Land | RETF | IPF | 2009 | 2011 | 2015 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/872851467997914688/text/ICRR14629-P116923-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/872851467997914688/pdf/ICRR14629-P116923-Box393183B-PUBLIC.pdf | The ICR offers two lessons that are valued by IEG:The approach of relying on a PCU to both implement an emergency project and be the main channel for capacity building efforts is viable as long as strong controls are put in place to prevent manipulation by the PCU. In the case of ASEP, the dual role of the Project Coordinator (PC) as the coordinator of the PCU and the member of the oversight committee allowed the PC to easily manoeuvre around any given situation, particularly related to staff capacity and procurement. The role of the international procurement consultant is critical in emergency projects. Terms of Reference for the international procurement consultant should be fully agreed upon prior to implementation or grant signing as in the case of ASEP . In the event that the Bank recognizes any inappropriateness within the organization, it is critical that the Team notify the management and seek guidance. When replicating or founding implementation arrangements for emergency projects in conflict situations, it is highly important to analyze the enabling and disabling factors of the arrangements and adopt a hybrid model to suit the specific intervention. In the case of ASEP, the Bank team considered the PCU model under the â€˜Blue Nile Projectâ€™ for the implementing agent, without fully deliberating how the implementing responsibility was allocated under the â€˜Blue Nile Projectâ€™. This was particularly critical for an extremely difficult and politically volatile situation such as in Abyei, when project duration was limited and changing the already established structure was politically difficult.And IEG draws one further lesson:The Bank and the MDTF donors have to collaborate beyond disbursement of the sanctioned Grant funds.In the case of ASEP, some of the MDTF donors were placing pressure on the Bank to speed up disbursement and keep the Project effective in an environment where the implementation arrangements were failing and the project should really have been closed. As a measure to address similar situations, it is mandatory to up-front establish mutually agreed controls for Grant disbursement and for bringing the donors fully on board with the Bank to address politically debatable situations in the project locale. The latter would help the Bank to stall the funding if and when politically sensitive issues escalate beyond the Bankâ€™s control as in ASEP, where replacing the Project Coordinator was more than attainable.
P116937 | Social Sector Reform Development Policy Loan | Europe and Central Asia | Albania | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2011 | 2012 | 2014 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/704121475089453139/text/000020051-20140625232605.txt | http://documents.worldbank.org/curated/en/704121475089453139/pdf/000020051-20140625232605.pdf | IEG draws the following two lessons from the experience of preparing and implementing this operation:Single-tranche DPLs are likely to be appropriate instruments for supporting medium term sector reform only when such reforms require temporary budget support or generate significant fiscal costs.It is unlikely that prior actions supported by a single-tranche DPL would have measurable outcomes over short periods of time. The operation under review is a case in point.
P116937 | Social Sector Reform Development Policy Loan | Europe and Central Asia | Albania | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2011 | 2012 | 2014 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/859991468203968107/text/880740PPAR0P08050Box385272B00OUO090.txt | http://documents.worldbank.org/curated/en/859991468203968107/pdf/880740PPAR0P08050Box385272B00OUO090.pdf | 4. Lessons 4.1 This combined evaluation of the Health Systems Modernization Project and the Social Sector Development Policy Loan has revealed a number of cross-cutting lessons. Both projects\. were grounded in analytic work and technical assistance; supported farreaching reforms; sought to exploit synergies across various forms of Bank support and lending instruments; and faced a range of challenges inherent in reform implementation. 4.2 A number of common lessons emanating from these two projects are presented below. These lessons become even more interesting when juxtaposed against the lessons distilled from two relevant IEG thematic reviews of, respectively\. (a) the effectiveness of the World Bank's analytic work and technical assistance (Box 4.1.); and (b) the effectiveness of the World Bank's support to health, nutrition and population sectors, with a focus on health reform (Box 4.2.). Each of these reviews was world-wide in scope and provides insight and perspective to experience gleaned from the two Albania projects that are the subject of this review.
P116951 | Public Expenditure Crisis Development Policy Loan | Europe and Central Asia | Bosnia and Herzegovina | IBRD | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2011 | 2014 | ICRR | >=100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/323481474939291622/text/000020051-20140626110806.txt | http://documents.worldbank.org/curated/en/323481474939291622/pdf/000020051-20140626110806.pdf | There are three main lessons to be gleaned from the implementation of the first programmatic DPL:1. DPL operations need to take into account political-economic considerations facing a member government, particularly during periods of crisis. Political economic analysis is critical to the design and implementation of politically sensitive and/or contentious reforms. The Bank drew upon extensive analytical work and consultations with key stakeholders affected by the reform, yet seems to have not fully understood the influence and impact of key beneficiary groups and the constitutional questions involving the move to a means-based social protection system. The Bank should redouble its efforts to ensure that a comprehensive socio-political analysis is conducted at both the design stage and during implementation.2. The design of a DPL operation during a period of crisis needs to find the right balance between addressing an immediate financing need and the desire to make progress on critical reforms. The global financial crisis spilled over into the BiH economy, contributing to large fiscal and balance of payments deficits and the urgent need for exceptional financing. Although the operation was successful in supporting the immediate macroeconomic stability objective, it failed to go beyond the initial measures that served as prior actions for the first DPL, resulting in the cancelation of the two remaining DPLs. Despite the fact that the Bank assessed alternatives and decided to pursue a three-year DPL series, a one-off operation would likely have been more appropriate and provided greater flexibility to deal with the changing circumstances. 3. Sequencing of reforms can lead to better outcomes. Given the multiple interests and stakes involved in reform, it is important to assess carefully the best path forward and sequence measures in order to have the highest chance for success. There were two key interest groups regarding the PEDPâ€”the general public who was concerned about excessive spending on the wage bill and abuse of social program benefits and the war veterans and their families who were the direct beneficiaries of these social programs. As indicated in the ICR, the PEDP may have had a better chance of success therefore if the reforms had been sequenced to address first the public wage bill and eligibility audits issues (which had broad-based public support) , rather than starting with the politically contentious issue of targeting war veteran benefits (which had a powerful and vocal constituency).
P116965 | Influenza Prevention and Control | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2010 | 2013 | 2012 | ICRR | Less than 10 million |  | Moderately Unsatisfactory |  |  |  | http://documents.worldbank.org/curated/en/549201475090859988/text/000020051-20140625072356.txt | http://documents.worldbank.org/curated/en/549201475090859988/pdf/000020051-20140625072356.pdf | The following lessons are taken from the NCO, with some adaptation:Non-incremental financing incentives: The Bank should assess the value-added of a non-additional loan in middle-income countries such as Mexico. Although agencies receive strong technical support under Bank-financed projects, this incentive could be outweighed by Bank fiduciary and safeguard requirements, as was the case with this project.Anti-corruption policy and its application under emergency situations: Although anti-corruption measures aim to limit exposure to fraud and corruption risks and to manage reputation risks to the Bank and the Borrower, these measures limit the flexibility of quickly prepared and disbursed operations. Particularly in emergency situations, there is room for further work to find balance in the way the Bank engages on corruption issues. In this case, emergency policies (OP/BP 8.00) were not fully aligned with anti-corruption policies.Efficacy of the emergency instrument in health emergencies: In public health emergencies, it is often difficult to predict the course of the emergency or the damage caused to human lives and health. Other instruments may provide a more effective option to respond to client needs, in view of the fiduciary requirements related to emergency purchases.
P116974 | AR Third National Communication UNFCCC | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2011 | 2015 | 2016 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/944671468208162662/text/ICRR-Disclosable-P116974-06-22-2016-1466624300813.txt | http://documents.worldbank.org/curated/en/944671468208162662/pdf/ICRR-Disclosable-P116974-06-22-2016-1466624300813.pdf | The ICR draws the following main lessons from implementing thisproject.1A careful assessment of the implementation period is required both during preparation and at restructuring.In the case of this project, despite the slow pace of execution, the project closing date was extended by only 18 months during thesecond restructuring.The project closing date was extended again by seven and half months.2 Long delaybetween project design and execution can result in high transactions costs. A project that faced significant initialdelays in getting operational may require working within a changed context, with new actors and/or circumstances. This cancause high transaction costs and efficiency losses, in particular for a smalloperation.
P116984 | Development Policy Loan | Europe and Central Asia | North Macedonia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2011 | 2012 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/945591475082198092/text/000020051-20140625061139.txt | http://documents.worldbank.org/curated/en/945591475082198092/pdf/000020051-20140625061139.pdf | The ICR listed two important program specific lessons: (i) DPLs prepared in response to crisis have to be processed quickly, and must help shape government's immediate response yet not lose sight of medium- term objectives; and (ii) Having a Bank presence on the ground, and most of the operation team on the ground with a previously established dialogue helped lay the basis for the design and relatively fast processing of the loan.
P116989 | AR Road Safety | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2018 | 2018 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/512841526651127007/text/Argentina-AR-Road-Safety.txt | http://documents.worldbank.org/curated/en/512841526651127007/pdf/Argentina-AR-Road-Safety.pdf | The ICR (para 76) presented several useful lessons adapted by IEG: Empowering the leadagency can generate results in the medium and long terms. Empowering and providingthe lead agencywith thenecessary legal, financial, and human resources in a sustained manner to effectively manage road safety in a country, and holdingthe agency accountable for national road safety outcomes, following Safe System Approach principles is important. The projectfollowed recommendations by the World Bank and WHO to help Argentina transition to a Safe System Approach, under the responsibilityof the lead agency, and to achieve the stabilization of traffic fatalities in thecountry. Multi-sectoral and multi-jurisdictional coordination can be achieved through appropriateincentives and instruments. The ANSV led formal meetings of the FCRS, carried out over 180,000 operations jointly withtraffic enforcement forces, delivered numerous trainings and workshops, created a national drivers licensing system, andfinanced evidence-based RSIs in municipalities through the Incentive Fund. Safe infrastructure designis an essential element of the Safe System Approach, because road design can mitigate the severity and consequence of roadcrashes, even if human error contributed to the crash. The difference in performance in the three corridors highlights theimportance of significant investments in safer infrastructure. The most successful corridor wasthe RN9 segment between thecities of Rosario and Crdoba, where significant changes in safety standards of infrastructure tookplace. The creation and longer-term sustainability of a robust road safety data management system isessential for understanding the magnitude of the problem, which is often understated, to be able to set realistic goals,inform interventions, and measure the effectiveness of actions.
P117000 | Economic and Social Development Policy Loan | Latin America and Caribbean | Grenada | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2011 | 2012 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/172221474592104237/text/000020051-20140625082157.txt | http://documents.worldbank.org/curated/en/172221474592104237/pdf/000020051-20140625082157.pdf | 1. Lack of close supervision can critically affect the successful outcome of an operation. The change in the TTL after Board approval created a gap in program supervision. As a result, Bank staff were not able to closely monitor implementation of the DPL and provide timely advice and suggested remedial measures well before the closing of the operation. The Bank should therefore ensure that key project manager positions are filled in a timely manner, particularly at the commencement and initial implementation phases of an operation. 2. The lack of clearly defined institutions and responsibilities undermines the quality of program monitoring as well as the likely outcome of the operation. The program did not focus sufficiently on M&E in terms of the institutions that would be charged with these responsibilities. Bank staff and the authorities should therefore endeavor to ensure that M&E institutions and responsibilities are well defined and empowered, including the role of stakeholders and beneficiaries, at the onset of the design of future operations.3. The selection of inadequate indicators undermines program monitoring and the operation's objectives. Certain key data ultimately used for measuring outcome indicators were lacking or were not carefully though through. This resulted in the government's inability to measure actual outcomes and/or measure outcomes through proxies that did not directly correlate to the outcomes trying to be assessed. Moreover, exogenous factors (i.e., higher world oil prices) affected the certain outcome indicators (i.e., fuel costs for government vehicles) which had nothing to do with the stated objective (i.e., reducing government waste). Bank staff and the authorities should therefore redouble their efforts to identify and assess appropriate indicators for measuring development outcomes at the design stage of future operations.4. A multi-year programmatic approach is likely to be more effective in addressing long-term development objectives than a single tranche stand-alone operation. There was an active debate amongst staff during the design phase of the DPL/DPC regarding the pros and cons of a stand-alone operation versus a multi-year program. The decision was taken to pursue the stand-alone program given (a) the urgent need to react quickly to the global financial crisis and (b) the fact that the Regional Partnership Strategy would not be finalized and considered by the Bank's Executive Board until a later date. A programmatic operation, however, would likely have had a stronger development impact and mitigate the program risks by having a medium-term approach to both policy reform and the related financial support.5. In small states, policy based programs need to be relatively simple and focused if they are to be successfully implemented. These countries often face severe institutional capacity constraints. Moreover, because of the small size of such member countries, Bank staff tend to design a single operation over a multi-year period and therefore include several policy reforms at once. It would be more effective to design a more focused, relatively simple program backed by well-crafted technical assistance aimed at building local capacity which would, in turn, result in a greater likelihood of the operation being implemented fully.
P117016 | Economic and Social Development Policy Loan | Latin America and Caribbean | St. Lucia | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2011 | 2012 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/994611474852035555/text/000020051-20140625081847.txt | http://documents.worldbank.org/curated/en/994611474852035555/pdf/000020051-20140625081847.pdf | A stand-alone one-year program is not effective in supporting a substantial reform agenda. A programmatic approach, supporting a multi-year phased program should yield better results. DPL operations require a good grasp of the country's political economy, sound preparation and consultation. This allows to match the reform program to the ground realities, and enhances ownership by the client.In the context of a weak public sector, a DPL operation should be simple in design, and should be coupled with technical assistance and close supervision.
P117016 | Economic and Social Development Policy Loan | Latin America and Caribbean | St. Lucia | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2011 | 2014 | PPAR | >=10 million & <25 million | Moderately Unsatisfactory |  |  | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/311331468303048351/text/882400PPAR0P110C0disclosed060110140.txt | http://documents.worldbank.org/curated/en/311331468303048351/pdf/882400PPAR0P110C0disclosed060110140.pdf | 6. Lessons 6.1 The DPL has four key lessons\. 6.2 A single tranche, standalone DPL is not the best instrument to address both shortterm and medium-term challenges. The one-off DPL shored up St Lucia's finances through the influx of funds. However, its stated objectives were medium or long-term for which the single operation DPL was not adequate. A programmatic series of DPLs would have been a more appropriate instrument for engagement, allowing the government time to implement St. Lucia's ambitious program, particularly given known capacity constraints. 6.3 In DPLs that are provided in the context of financial crisis to support the macroeconomic stabilization and fiscal constraints, this needs to be explicitly recognized and evaluated to assess its effectiveness. In cases where this is not recorded as an objective, the documentation does not fully recognize the intent, nor credit the DPL with what it achieves. 6.4 Lack of understanding or experience by the borrower requires factoring in additional time to allow for delays and greater investment in building a better understanding of process and purpose. Such situations also require greater stakeholder consultations both before and during implementation to ensure and enhance understanding. This being the first DPL, the government of St Lucia was not conversant with the Bank's internal DPL process. The Borrower's Response (ICR, Annex 4) indicated a lack of complete appreciation of the pre-board requirements or their significance in the loan process. This highlights the need for deeper and more inclusive internal discussion to attain support of key stakeholders and buy-in. 6.4 Close supervision is instrumental for achieving Program outcomes in one-off DPLs with a more medium-term outlook and targets and outcome indicators to be met at the end of the Program. Close supervision is necessary to help in achieving the DPL and reform program's targets. In addition, following up and providing or financing technical assistance if necessary, together with country dialogue to build local capacity, could be useful to bolster reforms and enhance sustainability in the medium-term and both a good supervision plan and methods to support sustainability should be considered at the outset.
P117023 | Jordan Recovery Under Global Uncertainty Development Policy Loan | Middle East and North Africa | Jordan | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2012 | 2013 | ICRR | >=100 million | Unsatisfactory | Moderately Satisfactory | Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/356441474509840658/text/000020051-20140625224458.txt | http://documents.worldbank.org/curated/en/356441474509840658/pdf/000020051-20140625224458.pdf | The ICR suggests five lessons from the DPL. Of these, IEG found the following to be relevant and grounded in the experience in Jordan:1. DPLs that include medium- to longer-term policy reforms may require close monitoring and supervision by Bank staff, beyond the time that prior actions have been completed, and a programmatic series should be considered at the design stage.2. Objectives are more likely to be achieved when measures selected for inclusion in a DPL are at an advanced stage, especially when they address issues where the political environment is very complicated.3. Good outcomes are more likely in crisis-response DPLs when development objectives and the associated policy actions in a DPL are specifically tailored to the country's circumstances at the time of implementation, rather than based on objectives that were designed years earlier.
P117038 | Emergency Social Safety Net Enhancement (EC Food Facility Grant) | Middle East and North Africa | Yemen, Republic of | IDA | FCS | Human Development | Social Protection & Jobs | RETF | IPF | 2010 | 2012 | 2013 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/512381474559226147/text/000020051-20140626000758.txt | http://documents.worldbank.org/curated/en/512381474559226147/pdf/000020051-20140626000758.pdf | We agree with the lessons listed in the ICR, particularly the following two lessons: Â· Emergency operations embedded within the context of ongoing country strategies can be effective instruments. This project was provided through institutions that were at the center of the Bankâ€™s assistance strategy in alleviating poverty, which facilitated the preparation of the Grant in an emergency manner, and ensured the lessons during implementation could be fed into the preparation of future operations in support of SFD and SWF. Â· The results framework and expected outcomes and outputs should be designed to reflect what an operation can reasonably accomplish and measure during implementation.In addition, IEG offers two complementary lessons:Â· Depending on country context, particularly if an economic crisis emerges during project implementation, the number of participants in public works programs may be higher than expected, resulting in a lower benefit level and potential inclusion of non-targeted households/individuals. Â· Building up the financial management capacity of the implementing agency ahead of time is important to ensure effective project implementation.
P117043 | Public Sector Reform Development Policy Loan | Latin America and Caribbean | Paraguay | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2012 | 2014 | 2015 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/540751475116798489/text/000012394-20150312105648.txt | http://documents.worldbank.org/curated/en/540751475116798489/pdf/000012394-20150312105648.pdf | The following lessons are derived from the lessons section in the ICR.The experience of this loan shows that during times of political instability institutional change is feasible when the government is committed to the reforms agreed to.Broad results indicators, which might be easily impacted by factors outside the intervention supported by the program, carry the risk of compromising the actual achievements measured and their attribution to the program.Clear government commitment to reforming a policy makes it possible to explore and carry out more complex policy options. Focusing on large taxpayers rather than on improving basic processes exemplifies this situation.
P117081 | Integrating Climate Change in the Implementation of the Plan Maroc Vert | Middle East and North Africa | Morocco | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | GEF | IPF | 2011 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/798291488488545373/text/ICRR-Disclosable-P117081-03-02-2017-1488488537774.txt | http://documents.worldbank.org/curated/en/798291488488545373/pdf/ICRR-Disclosable-P117081-03-02-2017-1488488537774.pdf | The projects experience yields the following main lessons: (variants oflessons 1 to 3are also discussed inthe ICR.)1. The monitoring of project impactis particularly important fora pilotproject testing technological changes.The ME of the project was primarily management information to monitorproject progress and physical achievements. There waslittle monitoring of the impact of the innovations on yields andsustainability, and, therefore, only a limited empirical basis for knowledge-based mainstreaming. (sections 3b,4 and10).2. Integration of a pilot project within the institutional structure and processes of the agenciesresponsible for project activities, sets a better stage for subsequent mainstreaming.The project was implemented bythe agencies normally responsible for the sector, entirely using the existing central and regional agencies. (In this case, even aPIU was eschewed). By using Moroccos existing institutional structure, subsequent mainstreaming of successful pilotactivities is reported in the ICR as being easier. (section 3b)3. When addressing strategicpriorities,but where knowledge of how to implement programs tohelp respond to the priorities is limited, a small pilotproject, can lever large change. The pilot can provide practical experience for designing and implementing asubsequentscale-up based on lessons from the pilot. Measuring impact should be a core part ofsuch apilotingexercise.The project has provided valuable experience for scaling up a climate change adaptation program. It wouldhave been more valuable if the impacts of the different technologies had been systematically assessed.4. Projectobjectives need a context of higher goals.This projects objective - to strengthen the capacityof .......institutions and farmers to integrate climate change adaptations(by farmers) - makes no reference as to what impact, or higher level goal(s),the project is expected to achieve. In otherwords, specifying more precisely what is meant by integrating climate change adaptations. The implicitgoals mighthave included effects such asyield increases, lowercosts, more resilience to extreme climatic events, and otherbenefits. This context would bettersharpen actions towards the projects ultimate goal to introduce effective climatechange adaptation technologies.However, the projects log frame and ME program was on physical progress. Questionssuch as the benefits from training (rather than only the numbers trained), and yield changes and resilience compared withnon-project farmers, wouldbetter link purpose and action.
P117082 | Tunisia Northern Tunis Wastewater Project | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2010 | 2021 | 2022 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099900005052236308/text/P1170820cdfd73051098e80920185c31551.txt | http://documents.worldbank.org/curated/en/099900005052236308/pdf/P1170820cdfd73051098e80920185c31551.pdf | (Reference ICR paras. 98 to 102).The ICR provides a number of lessons learned from the projects experience.Based thereon, the IEG derives the following lessons:Fostering coordination and cooperation, before focusing oninstitutional change, is key to achieving stakeholderengagement and results for TWW reuse activities:TheProjects experience has shown that the establishment of formal intersectoral committees for cooperation is anessential part of project design. TWW reuse is at the end-point of a vertical value chain that (i)spans various jurisdictions(Ministries of Environment, Health and Agriculture);(ii)encompasses issues ranging from upstream industrial and solidwaste pollution affecting the quality of the wastewater; (iii) efficacy of the wastewater treatment system which can lead totensions between the TWW providers and users; (iv) behavior and willingness of farmers to reuse TWW for crop production; (v)regulatory and pricing issues, and competition with other water sources. In the case of the Project, the Sidi Amor TWW reuse pilotproject created a platform to bring the different stakeholders to the same table; initiate dialogue that would not happenotherwise; and foster cooperation mechanisms.Tackling marine pollution requires a holistic environmentalremediation approach. The submarine outfall financed by the Project addressed the main source of contaminationat Raoued Beach. However, coastal waters are the recipients of various sources of pollution whose control falls under differentjurisdictions (e.g. municipalities improving their storm-water and solid waste management; industries managing their effluents;agriculture controlling fertilizer usage). Multi-sectoral approaches may be necessary for achieving this type ofobjectives.Preparation teams and Bank management need to balance Project readiness and pressure todeliver with extended implementation timelines: The Project was prepared undera tight timeline to be able torespond to the GOTs request. Although the decision may be the right one in the circumstances prevailing at the time,Bankmanagement and teams need to account for extended implementation timelines to ensure proper designs and ensurequality.Implementing projects in rapidly deteriorating conflict and fragile environments requires proactiveaction, time and flexibility: In situationsof conflict and fragility of governance, it is necessary for Bankteams to act early and as frequently as necessary to correctthe course of implementation. Without project restructurings,closing date extensions, and flexibility in the Banks procurement procedures, achievement of the PDO would not have beenpossible and opportunities for additional benefits incorporated in the Project wouldhave been lost.Anadditional lesson derived byIEG from the experience under the projectis the following:Inprojects where the realization of important outcomes depends upon the prior or in parallel implementation of activities notfunded under the project (as was the case under this project), project design needs to give particular attention to mitigating therisks involved in case these intended complementary investments are delayed or not executed. In the case of the project,the dropping of the planned parallel project to be executed by MARHP significantly reduced the ambition of the project and limitedthe realization of an important outcome - the reuse of TWW in agriculture.
P117088 | Financial Sector and Public Financial Management Development Policy Credit | Western and Central Africa | Nigeria | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 2010 | 2010 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/432611475071512547/text/000020051-20140624202456.txt | http://documents.worldbank.org/curated/en/432611475071512547/pdf/000020051-20140624202456.pdf | There are two important lessons:1. Diagnostic work should be carried out and utilized as the basis for reforms. The Finance Minster as a technocrat played an important role in supporting the development and implementation of the reform program. 2. Stationing team leaders in resident missions has a big payoff. The team leaders for both the financial and the fiscal components of this operation were stationed in the field, which enabled them to coordinate between themselves and,equally important, dialogue intensively with the government as and when this was needed. 3. Local ownership and voices in support of reform programs are important especially where such reforms are seen as contentious. In this case, the Bank stayed in the background while Nigerians argued the case for reform, thereby reducing the level of politicization of the dialogue.
P117102 | CM-Sanitation Project | Western and Central Africa | Cameroon | Blend | Non-FCS | Sustainable Development | Water | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/523671524145369479/text/Cameroon-CM-Sanitation-APL.txt | http://documents.worldbank.org/curated/en/523671524145369479/pdf/Cameroon-CM-Sanitation-APL.pdf | The ICR presented 7 lessons (ICR, paragraphs 83-89), the three leading were: To optimize impact on hygiene andsanitation, a sanitation project needs to include access to water supply and consider the demand of beneficiaries. For example,beneficiaries expressed that access to water for hand washing was more conducive to improved hygiene and reduced diseases amongstudents, especially girls, leading to the adding of the construction of bore holes and school latrines. For another, an earlyassessment of the project identified dry latrines as the more suitable and affordable for both urban and rural areas but duringimplementation, beneficiaries preferred water-flushed rather than dry latrines, particularly in the urban areas in Douala. This ledto lowered urban participation. Designing complex sanitation projects, which include sludge treatment plants forexample,require the availability of land at the planning stage even before design studies. Including pilot components indesign requires flexibility, particularly when incorporating affordability and innovative design. For example, latrine design needsto adapt tolow water tables, or presence of pests in bore holes, or access to emptying services in urban areas, or preferencefor water-flushed as opposed to dry latrines. A proactive assessment of initial conditions, including demand for dry or flushlatrines would have informed the differentiation of an acceptable design in urban and rural areas. A pioneering projectin any sector requires arealistic timeframe for implementation and adequate assessment of challenges to be faced duringimplementation. Recognizing that counterpart staff unfamiliar with implementing a sanitation project, a complex design not vettedagainst user demand, ambitious targets in a limited time, and a plan of actions to mitigate technical risks and low initialcapacity need to be recognized at appraisal.
P117103 | National Solidarity Program III | South Asia | Afghanistan | IDA | FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2010 | 2017 | 2019 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/552641540746143100/text/Afghanistan-AF-National-Solidarity-Program-III.txt | http://documents.worldbank.org/curated/en/552641540746143100/pdf/Afghanistan-AF-National-Solidarity-Program-III.pdf | There is a need to manage expectations by the Government and donors about the peacebuilding impact that a CommunityDriven Development (CDD) project can have, including one that has been implemented over several phases with a relatively largedonor investment. CDD can build trust within communities and among them toward the government. But its ability toinfluence exogenous forces (recruitment, insurgency) remains untested.Likewise, there is a need to preserve theneutralityand not politicizeCommunity Development Councils by using them for military or security purposes,sothatthe legitimacy that has been earned by the better performing councils does not becomeeroded.Not all problems can be solved at the community level, so there is a need for closecoordination with line agencies and district and provincial levels of government for effective service delivery. Lineagencies must be responsible for actions beyond communities control, such as ensuring teacher and health worker quality,providing engineering expertise, ensuring appropriate operations and maintenance interventions and coordinating subprojectslinkages with higher level infrastructure trunk networks (roads, sewerage, etc.) In the case of NSP III, appropriateplatformswere needed to allow public service providers to coordinate with CDC and CCDC leadership or sub-committees at thelocal level, underpinned by closer coordination at the center.There are trade-offs involved inimplementing a national CDD project via a parallel PIU structure - and any transition into Government systems should be a gradualone. NSPs structure of contracted staff paid at higher salaries that civil servants (but consistent withGovernment consultant salaries), operating largely independently within the ministry, may have allowed it to recruit and retainmore qualified staff, operate more effectively and delivery services in rural areas where the civil service does not have apresence. Buteven with recent Afghanization and convergence towards civil service normsthe higher costs underminesustainability and limit the impact of institutional strengthening efforts, if still concentrated within a PIU rather than theministry as a whole. Furthermore, such convergence/transition processes must be a gradual one to avoid impacting projectperformance, as for example happened with HR functions on the NSP III.NGOparticipation in CDD programs can be essential, but careful training, selection and contract management are needed to ensureconsistent implementation performance. FPs played a key role in the success of NSP III, as with earlier phases. However,gaps in training, selection of less-experienced NGOs, and output-based contracts that may have prioritized subproject completionand block grant utilization over participatory aspects apparently contributed to uneven performance under NSP III.
P117107 | Liaoning and Shandong Technical and Vocational Education and Training Project | East Asia and Pacific | China | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2010 | 2016 | 2017 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/701581485365002768/text/ICRR-Disclosable-P117107-01-25-2017-1485364989993.txt | http://documents.worldbank.org/curated/en/701581485365002768/pdf/ICRR-Disclosable-P117107-01-25-2017-1485364989993.pdf | IEG concurs with lessons learned as set out in the ICR (p. 25), many of which are tied to the specifics of the project type inquestion, such as: The need to pay attention to scheduling of activities for curricular reforms to be successful;and, The potential desirability of a competitive bidding process for participation (by schools) in innovative initiativesto ensure local commitment and buy-in, and the benefits of delegating to allow for autonomy in effectively tailoringapproaches.IEG also concurs with lessons with broader reach such as: The benefits, in terms ofcoordination and efficiency, of working through a single coordinating agency (rather than multiple agencies). In this instance, thefact that each province operated to a different structure meant effectively meant the operation of two independent sub-projects,and this hadimplications that impacted timing and sequencing as well as learning and evaluation.and, The assertionthat demand-driven design of TVET programs can produce strong outcomes i.e, where courses and programs are designed in response toidentified student and local industry need. In this instance, pre-project rates of graduation in both provinces were already high.The key outcome associated with the introduction of a competency based approach calibrated tolocal need, was a significantincrease in the rate of employment of graduates in jobs associated with their field of study. This ensures greater rates ofefficiency and sustainability in the longer term.
P117148 | West Africa Agricultural Productivity Program APL (WAAPP-1B) | Western and Central Africa | Western and Central Africa |  |  | Sustainable Development | Agriculture and Food | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/708821506708097658/text/ICRR-Disclosable-P117148-09-29-2017-1506708079977.txt | http://documents.worldbank.org/curated/en/708821506708097658/pdf/ICRR-Disclosable-P117148-09-29-2017-1506708079977.pdf | The ICR included six lessons. The following are emphasized with some adaptation of language: For longterm investments such as agricultural research long term program lending should be used to ensure sustainability.TheWAAPP-1 showed sound results, but they are unlikely to be sustained because the Bank decided to retract its commitment to theprogram. The World Bank undermines its credibility as a development partner by withdrawing from a commitment to financially supportlong term lending program that is delivering good results in its early phases. The adoption of a value chainapproach in agricultural projects calls for a multidisciplinary research teams. As agricultural technology no longerfocuses primarily on production aspects, the degree of complexity increases and the inclusion of additional scientific disciplinesbecomes necessary. A new balance needs to be struck between natural scientists, social scientists, engineers and agriculturalpolicy makers. The task of accelerating adoption of released technologies requires added attention to and strengthening of thenational extension systems, including the training of key extension staff to the MSc and PhD level and the creation of extensiondepartments at university level. Strengthening producer organizations (associations, federations, cooperatives)is critical to enable the use of new technologies and technical innovations that require economies of scale. Buildingsocial capital, including strong producer organizations, should be a major focus of national extension systems and extension agentsshould be trained accordingly in how to work with farmer groups, communication theory, sociology, adult pedagogy and psychology,but also agricultural planning, business administration and market analysis.
P117152 | Kakheti Regional Roads Improvement Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2016 | 2016 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/409421468036838824/text/ICRR-Disclosable-P117152-06-10-2016-1465566393301.txt | http://documents.worldbank.org/curated/en/409421468036838824/pdf/ICRR-Disclosable-P117152-06-10-2016-1465566393301.pdf | The following lessons were selected from the ICR, with some adaptation: Successfulimplementation of new reforms in road safety requires strong ownership of the implementing agency but also close collaboration withall the stakeholders. This projecthelped build relationship between RD and MIA/Police and develop closecollaboration between these two parties to ensure the sustainability of results. Mainstreaming ofthe design-build approach in the government program may require enabling legislation. Asper Georgias current legislative framework, lump-sum payments cannot be made for works delivered and levels of services metas stipulated in the contract conditions. More awarenessis needed about the advantages of this approach. In addition, adesign-build contract approach needs careful fine-tuning during a pilot stagebefore fullymainstreaming it intotheroad asset management practices. Careful estimation of traffic forecast in a design phase isimportant, in particular when the initial condition of a road is poor. In this project,diverted traffic was under-estimated at appraisal, asnormal traffic volumes were suppressed by the poor initial condition ofthe roadand were using alternative routes. A significant increase in traffic beyond estimateshas also implications forthe technical specifications/ engineering design of the road.
P117152 | Kakheti Regional Roads Improvement Project | Europe and Central Asia | Georgia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2016 | 2021 | PPAR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/739481595013234359/text/Georgia-Secondary-and-Local-Roads-Project-and-Kakheti-Regional-Roads-Improvement-Project.txt | http://documents.worldbank.org/curated/en/739481595013234359/pdf/Georgia-Secondary-and-Local-Roads-Project-and-Kakheti-Regional-Roads-Improvement-Project.pdf | 3. Lessons 3.1 It is impossible to implement a holistic road safety approach through a small, regional project without the formal involvement of key road safety stakeholders. In this case, not all road safety activities were implemented as planned, and the road safety subobjective was not achieved. In hindsight, this was mainly because of the small size of the road safety activities, the project's regional nature, and, above all, the lack of inclusion of the key road safety stakeholders as project implementation agencies. 3.2 A sustained engagement on road safety over time can help transform the road safety culture in a country. The Georgian experience showed that, even if the road safety activities under both projects were not successful, the World Bank's insistence on road safety activities in all its road projects, the provision of capacity strengthening for the road agency, regular outreach to road safety stakeholders (including civil society), and support through technical assistance helped the country realize the urgency of the need for action and promoted the road safety agenda. However, the cultural shift related to road safety took time to materialize and depended on a sustained engagement over time. 3.3 Upgrading a road that is barely passable can make it less safe despite the implementation of road safety engineering measures. The road department carried out a road safety audit in the design phase, implemented road safety engineering measures, and organized a one-time road safety campaign. Nevertheless, the number of road fatalities increased. Because road improvements lend themselves to speeding, more than just normal road safety engineering measures are required to make a new road safe, including above all speed restrictions and their strict enforcement. 3.4 Measuring improved road safety resulting from project interventions requires a carefully designed approach. In Georgia, road safety improvements were measured through the difference in fatality numbers at two points of time in a specific region. This raised attribution issues. To avoid some shortcomings, the number of fatalities could have been weighted by the vehicle-kilometers driven, population, or any other relevant parameter for the region. The indicator could also have looked at annual weighted averages for several years instead of two points of time only. A control group for a similar region should have been established. Finally, instead of or in addition to measuring the number of fatalities in a region, indicators could have been devised to assess the impact of individual road safety measures to help improve such measures in the future. 3.5 The successful introduction of performance-based maintenance and rehabilitation contracts requires contractors to be aware of the paradigm shift such contracts imply to avoid work delays and financial losses. Before launching the first new contract, the road department organized a workshop for the construction industry and provided contractors with the opportunity to ask questions in the prebid meeting. This was not enough, and contractors had difficulty grasping the lump sum payment concept and shifting to the long-term planning perspective of you invest today to save tomorrow, which this contract modality entails. It led to several missed performance targets, the need to redo works, and financial losses to the contractor. 1Georgia's road network under the responsibility of the road department consists of 1,528 kilometers of international roads and 5,297 kilometers of secondary roads (source\. www.georoad.ge). Local governments are responsible for about 15,000 kilometers of local roads. 1The road department carried out basic, routine maintenance through 24 contracts, 23 inputbased, two-year contracts covering specific zones, and 1 five-year performance-based rehabilitation and maintenance contract, for which rehabilitation was completed. Road department management showed an interest to possibly move to more performance-based maintenance in the future. 2 Maintaining roads in better condition results in economic savings to users and reductions in transport costs many times greater than the maintenance expenditures (Harral, Smith, and Paterson 2011b). 3Periodic maintenance and rehabilitation are lumped together into the same expenditure item, and separate figures are not available. 4For instance, the average expenditure on transport in Indonesia between 2007 and 2017 was 1.5 percent of its gross domestic product. This includes private sector and investment by state-owned companies (World Bank 2019). 5A design and build contract combines the design and construction or rehabilitation of a road in a single contract, and payments are made on the basis of outputs or a lump sum (for example, a specified dollar amount per kilometers of road completed to a certain standard) and not on inputs (for example, the amount of gravel and asphalt used to rehabilitate a road). This was how the design and build contract worked in the Georgian context, where it was normally used for smaller rehabilitation works, and contracting out the road designs separately would not have been economicalin those cases. 6 A performance-based rehabilitation and maintenance contract is a long-term contract, normally between 5 and 10 years, which combines initial road rehabilitation (including its design) with a period of routine maintenance. The rehabilitation and maintenance activities are generally both paid based on outputs or a lump sum (for example, kilometers of road rehabilitated or kilometers of road corresponding to a predetermined level of service each month during maintenance). The first performance-based rehabilitation and maintenance contract in Georgia covered a road network of 117 kilometers, including the initial rehabilitation of 37.5 kilometers, followed by maintenance and the maintenance only of 79.5 kilometers. The contract's duration is five years, and payments for both the rehabilitation and maintenance works were based on outputs or performance. 7The first Secondary and Local Roads Project was followed by a second and third SLRP. The second SLRP closed in June 2019, and the third is ongoing. 8 The main benefits associated with design and build contracts include better rehabilitation and maintenance work quality (because the contractor is financially liable for defects during the full contract period), more consistent levels of road service, less corruption (because of fewer financial transactions), better focus on innovation and sharing risks, fewer contract modifications and cost overruns, and lower life cycle costs (Lancelot 2010; Gericke, Henning, and Greewood 2014; World Bank 2016). 9Comparing road work contracts is difficult, mainly because road designs may vary significantly and therefore may have very different costs and implementation time requirements. 10IEG visited this road when it already started to get dark, therefore defects might not have been detected. Sobieniak, Janusz. 2018. Georgia\. Output and Performance-Based Contracting Experience, Unpublished Draft Report. World Bank, Washington, DC. 12Again, any cost comparison between different roadwork contracts is difficult. In addition, performance-based maintenance and rehabilitation contracts and traditional input-based contracts are very different in terms of risk allocation, and therefore the results of their comparison need to be interpreted with caution. 13Maintenance costs might not be comparable because the performance-based contract covers clearing the maintenance backlog and maintaining the road to specified service levels or facing payment reductions; the road department's costs for traditional maintenance are based on norms, and the scope of the maintenance works may not be comparable to the service level of the performance-based contract; and the road department's traditional maintenance costs are measured by quantities, and there is no risk associated with not achieving the performance standards. 14On the methodological side, the comparison in fatalities between the Kakheti region and Georgia as a whole is in absolute numbers and does not consider possible differences in the amount of vehicle-kilometers driven in the two areas because these data were not available for the country overall. If higher GDP per capita is taken as a proxy for higher vehicle ownership and use, the Kakheti region (with a GDP per capita of GEL 5,819 in 2017), however, fares even worse because the national per capita GDP is much higher (GEL 10,166). In addition, because of data limitations, a one-point-in time baseline is compared with the average of the past five years. These one-point-in-time data could be outliers. 15Article 7 of the 1997 Law on Local Self-Governments states that the repair, reconstruction, and construction of road of internal use of municipalities is a function of local government. Article 16 of the 2005 Law on Local Self-Governments, in force since the beginning of 2006, reiterates local governments' responsibility for roads by specifying that the maintenance, construction, and enhanced development of local roads is a function of local government. Finally, the 2014 Law on Local Self-Governments specifies that the management of local roads and of the traffic on these roads is a function of local government.
P117157 | STRENGTHENING PUBLIC HEALTH CARE SYSTEM | Latin America and Caribbean | El Salvador | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2012 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/594741556547574717/text/El-Salvador-SV-Strengthening-Public-Health-Care-Syst.txt | http://documents.worldbank.org/curated/en/594741556547574717/pdf/El-Salvador-SV-Strengthening-Public-Health-Care-Syst.pdf | The ICR (p. 27) offered several useful lessons, including:World Bank financial supportcan sustain priority government agenda through periods of crisis. In this case, the negative impact of the 2009 globalfinancial crisis threatened the social sector gains El Salvador had made in the preceding decade. Bank support enabledcontinued attention to coverage and quality of health services to the urban poor.Risk assessments will notproduce adequate mitigation measures if they do not realistically take likely challenges into account. In this case, eventhough the risks posed by gang violence in targeted areas and low procurement capacity were identified in appraisal documents, theywere not acknowledged and dealt with in the formal risk assessment framework. As these risks materialized, the project wasnot as equipped to cope with their impact as it might have been with more in-depth assessment andplanning.IEG offers one additional lesson:In the absence of key outcome indicatorseffectively measuring a projects development objectives, assessment of achievements and outcomes is problematic. In thecase of this project, although equity concerns were embedded in the projects selection of intervention areas, there were noactual measures of the projects impact on improved equity in the utilization of health services.
P117161 | Tunisia Employment DPL | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | DPF | 2011 | 2011 | 2013 | ICRR | >=50 million & <100 million | Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/427591474577544054/text/000020051-20140625190737.txt | http://documents.worldbank.org/curated/en/427591474577544054/pdf/000020051-20140625190737.pdf | The following lessons are drawn from the ICR:Solid political-economic analysis in DPLs, which tackle difficult reforms such as in the labor sector, are essential to better understand the constraints caused by embedded political interests and corruption. In countries with favoritism and rent-seeking, this would include issues of governance and accountability. Operations that seek to improve the efficiency and effectiveness of job entry would require measures to ensure the jobs are there to be entered. Otherwise they will not be effective.Employment programs are regressive if they focus on University graduates who are a small and privileged population group. Better outcomes may result from improving the work and business environment for the large number of low-income workers active in the informal sector and in agriculture.
P117170 | 5M- Regional Coordination on Improved Water Resources Management and Capacity Building in Cooperation with NASA | Middle East and North Africa | Middle East and North Africa |  |  | Sustainable Development | Water | GEF | IPF | 2011 | 2015 | 2016 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/935661467034683710/text/ICRR-Disclosable-P117170-06-27-2016-1467034661388.txt | http://documents.worldbank.org/curated/en/935661467034683710/pdf/ICRR-Disclosable-P117170-06-27-2016-1467034661388.pdf | The ICR draws the following main lessons from implementing this project. A regional operation can helpwhenthere are common problems across several countries. In the case of this project, countries excelled in variousaspects of the project and hence could learn from each other. This aided in assimilating new technologies. Workshopsand training courses were also more efficient with the participation of four countries. Detailed project implementationplans are necessaryeven for technical assistance projects. In the case of this project, lack of detailed implementationplans delayed implementation in the initial years of the project. The marked improvement in project performance highlightedthe importance of applying Bank protocols during project preparation even for technical assistance projects,so that theproject starts well and quickly. A good coordinating body can be extremely useful, particularly for a regionalproject. In the case of this project, the regional coordinating agency the Arab Water Council -played a crucialrole in coordinating with all participating countries and this aided in the implementation of the project by the ProjectCoordination Units in eachcountry.
P117201 | Morocco - Sustainable Access to Finance DPL | Middle East and North Africa | Morocco | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | DPF | 2010 | 2012 | 2013 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/700671475075426049/text/000020051-20140625231955.txt | http://documents.worldbank.org/curated/en/700671475075426049/pdf/000020051-20140625231955.pdf | IEG agrees with the lessons highlighted in the ICR, including the importance of strong Government ownership, the need for better planning for major legislative initiatives such as the ones for establishment of independent authorities. In addition to these lessons, the experience of this program highlights the importance of well designed monitoring and evaluation framework with sensible target values for outcome indicators. The experience of this sectoral DPL also highlights the importance of a macroeconomic framework in the program that could have helped to moderate the impact of subsequent socks and to better adjust to the new challenges. The premium on including a macro-framework in a sectoral DPL is high in a situation when there is no dedicated Economic Policy DPL operation by the Bank or an IMF program in place.
P117203 | Smallholder Agriculture and Social Protection Support Operation | East Asia and Pacific | Cambodia | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | DPF | 2010 | 2010 | 2013 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/109501475071497570/text/000020051-20140624203550.txt | http://documents.worldbank.org/curated/en/109501475071497570/pdf/000020051-20140624203550.pdf | The first lesson is from IEG, the last two are from the ICR (p.21, with some editing).Addressing policy and institutional weaknesses through a single-tranche DPO is difficult when capacity is very weak. The farmer organization objective in the present operation was particularly problematic in this regard.Implementation of a useful M&E system requires results to be identified and expressed as objectively verifiable target indicators. While targets need to reflect true aspirations, program design should carefully assess whether they are reasonably achievable and verifiable, given the country context, institutional constraints, technical feasibility, and implementation period. Cross-sector programs require a clear understanding of incentives faced by all implementing agencies. In the case of multi-ministerial programs, in addition to the coordination capacity of the lead agency, incentive structures need to be understood to determine how those who benefit only tangentially from the program will be motivated to pursue the reform agenda.
P117212 | Zimbabwe Emergency Agriculture Input Project | Eastern and Southern Africa | Zimbabwe | Blend | FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2010 | 2012 | 2015 | ICRR | Less than 10 million | Satisfactory | Highly Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/971791475116585164/text/000012394-20150107101501.txt | http://documents.worldbank.org/curated/en/971791475116585164/pdf/000012394-20150107101501.pdf | The ICR lists a number of lessons learned from the Project. The more important and relevant include:The risks associated with emergency humanitarian projects (OP8.00 operations) can be minimized by the use of existing experienced institutions for implementation.In emergency situations, where government institutions are very weak, a strong case can be made for using the private & NGO sectors as implementing agents, providing the government is agreeable.The use of vouchers to provide agricultural inputs, rather than cash in an emergency situation is effective in accurately targeting aid, as it limits the opportunity for expenditure on items other than the intended inputs. A voucher system also provides flexibility in the use of input subsidies, as these can be adjusted at the wholesale level, without distorting retail markets. Avoidance of political interference and elite capture is critically important in operations of this nature. Such risks can be mitigated by appropriate implementation arrangements involving the private sector and civil society, and by securing an undertaking from the Authorities not to interfere in the implementation of the project. However, adequate monitoring and evaluation of actual results on the ground are also important to ensure that targeted beneficiaries coincide with actual ones.IEG Adds another lesson:Provide details of independent impact assessment and survey data that verify assertions made about project achievements in the ICR. Failure to do so will results in IEG downgrading of outputs/outcomes on the basis of inadequate evidence.
P117225 | Burundi - Energy Efficiency Project | Eastern and Southern Africa | Burundi | IDA | FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2012 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/429781475270629365/text/ICRR-Disclosable-P117225-09-30-2016-1475270613833.txt | http://documents.worldbank.org/curated/en/429781475270629365/pdf/ICRR-Disclosable-P117225-09-30-2016-1475270613833.pdf | The ICRR provides seven lessons from which IEG has summarized following:1. Energy efficiency projects have tobe sufficiently large and build effective institutions to have a national impact. This project that set out to achievedevelopment and adoption of national guidelines, policies and regulations in less than four years, in addition to technologicalupgrading, had little budget clout or support from a sector-wide approach.2. Continuousawareness-raising and incentives are essential to sustain consumers use ofenergy-efficient technology. EEP surveys revealed that continuous awareness campaigns are required to ensure that thehouseholds that received the free CFLs would voluntarily purchase additional or replacementCFLs.3. A combination of pre-paid meters and CFLs can have more impact in reducing consumptionand increasing awareness of the benefits of the CFL than distribution of CFL alone.
P117229 | Comoros Development Policy Grant | Eastern and Southern Africa | Comoros | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2011 | 2013 | ICRR | Less than 10 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/965201474483070151/text/000020051-20140625230417.txt | http://documents.worldbank.org/curated/en/965201474483070151/pdf/000020051-20140625230417.pdf | IEG broadly agrees with the lessons drawn in the ICR:It is critical for such projects to create and maintain a strong link with TA activities. It accelerates the pace of activities, strengthens the Governmentâ€™s capacity and ownership and contributes to the sustainability of the reform agenda. It also creates economies of scale for monitoring and supervision.A close coordination with the IMF and other donors is also critical for creating and maintaining momentum for reforms. The pursuit of such a major objective as debt relief helps creating a favorable policy window.Progress indicators in fragile countries should ideally be flexible and reasonably simple to collect, such that monitoring can take place even in an uncertain environment.
P117234 | Sixth Poverty Reduction Support Credit (PRSC6) | Eastern and Southern Africa | Mozambique | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2011 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/172141475111853059/text/000020051-20140626111920.txt | http://documents.worldbank.org/curated/en/172141475111853059/pdf/000020051-20140626111920.pdf | The lessons from the ICR are broadly supported by this Review: Clearly specified policy and institutional reforms are central to ensuring that outcome indicators in performance assessment frameworks are linked to concrete actions rather than vague aspirational goals. PRSCs will have the greatest impact when they focus on a road map of prioritized institutional changes and related policy measures. Progress can best be measured with indicators linked to concrete actions, while ensuring that effective monitoring will be achievable within the limits of statistical and M&E capacity.The risk to reforms can be mitigated by addressing potential political economy constraints throughout the reform process. Reforms to public resource management, and strengthening the legal and institutional framework for business development and efficient land use, will inevitably attract the attention of powerful interests. While some controversial reforms will be delayed or blocked by political processes, the risk of this can be mitigated through an inclusive consultative process, supported by careful analysis of under-appreciated benefits that can help to build coalitions of supporters.Reformers may gain better traction by shifting focus in response to changing conditions. Reform priorities can often be usefully adapted to better respond to changing economic and social conditions and international developments. Implementation challenges may also be resolved by switching focus to a different policy area where there is a critical mass of political support and/or implementation capacity, rather than pushing for results that are unattainable within the time frame of the series.Reform success requires that implementation capacity constraints be identified in advance in order to guide the design and provision of technical assistance. Poverty reduction programs tend to be ambitious and complex, requiring capacity at many levels for reform implementation, and appropriate and timely monitoring and evaluation. Meeting these challenges requires an adequately designed and targeted program of technical assistance, in the short run, coupled with sustained capacity-building support over the long run.
P117237 | Nigeria First Lagos State Development Policy Credit | Western and Central Africa | Nigeria | Blend | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2012 | 2016 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/515921467996682925/text/ICRR14832-P117237-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/515921467996682925/pdf/ICRR14832-P117237-Box394823B-PUBLIC.pdf | IEG concurs with the lessons drawn by the ICR (ICR pp. 33) with some adaptation of language:It is important to design a state level operation in such a manner that continuity can be maintained even in the face of unanticipated delays in financial support. Issues may arise at the National Assembly that may lead to delays. The Bank needs to continue its engagement until the program can be adjusted to the mutual satisfaction of all parties. The design of a sub-national government operation would need to properly account for interplay between federal and state policies. For a sub-national government DPO, the team needs to clearly identify who is in charge of policy formulation that is supported by the program. If the federal government is in control of a policy, it is important that the program design allows sufficient space for a state government to counter adverse impacts from factors outside their control. In this circumstance, targets for results indicators can be moderated and take into account the unanticipated risk due to the federal governmentâ€™s policy actions.Coupling a DPO with long-term technical assistance supports the implementation of prior actions and fosters sustainability of the reform. Technical assistance support may continue even in the absence of a programmatic engagement. When the reform focuses on public sector modernization through the deployment of an integrated financial management information system, it is important to consider and mitigate the risks associated with internet connectivity and ICT capacity. Care must be taken when applying Investment Climate Assessment recommendations and indicators. It is critical to consult an in-depth sector diagnostic prior to reform.
P117238 | MW-PRSC-3 | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2011 | 2012 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/725301474854089207/text/000020051-20140625083421.txt | http://documents.worldbank.org/curated/en/725301474854089207/pdf/000020051-20140625083421.pdf | The ICR highlighted six key lessons learned from the implementation of the PRSG series that are appropriate, noteworthy, and should inform the preparation of future DPOs. 1. The importance of government ownership. Key institutional reforms in agriculture and social protection were not implemented because of a lack of buy-in across the government. 2. The need to assess the political economy of sensitive reforms. The political economy dimensions of certain key reforms under the PRSG series (i.e., maize marketing, fertilizer subsidy, and social protection) were underestimated. As result, progress in implementation in these areas was slow and policy reversals occurred. 3. There is merit in working within a harmonized framework. CABS provided the authorities and Bank staff with a harmonized framework for the provision of budget support that also enhanced the quality of policy dialogue across donors and provided political leverage for good governance. 4. Flexibility in the program assessment framework should be encouraged. It is difficult to foresee all the relevant issues and internal/external developments at the beginning of a DPO series. 5. A robust and flexible M&E framework is important for tracking progress in PDOs. The MGDS M&E framework did not generate sufficiently comprehensive information for monitoring outcome indicators, particularly regarding tobacco market, fertilizer market, and commercial justice reforms. 6. The bar for policy reform should be set sufficiently high enough to mobilize change while avoiding overly ambitious and complex measures. An important lesson learned from earlier DPOs was that programs should be focused given existing institutional capacity constraints.
P117242 | The Tanzania - Housing Finance Project | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2010 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/920091593207252084/text/Tanzania-TZ-Housing-Finance.txt | http://documents.worldbank.org/curated/en/920091593207252084/pdf/Tanzania-TZ-Housing-Finance.pdf | The ICR draws the following threelessons from the experience of implementing this project, with someadaptation of language.1. There could be great benefits to taking on relatively riskier projects aimed at creatingfinancial markets, by combining judicious public investments,and catalyzing private investments, to reach new marketsegments. While the government does have a strategic role in creating financial markets, for sustainable development ofthese markets, they must leverage private finance and investment, as was the case in this project. The lesson from this project isthatprivate capital even in countries with less developed financial markets, can be mobilized through judicious publicinvestments.2. Developing microfinance for low and medium segment of the population, requiresdedicatedefforts, especially in new markets. While this project applied microfinance development in Tanzania at atime while the government tended to play a large role in the market, it took a while for the financial sector to align incentivesfor market development through injecting liquidity in the market. The lesson is that extensive efforts may be required withgovernment stakeholders for developing housing microfinance projects.3. Various options need to be considered forfinancial sustainability of mortgage finance companies. In this project, this aspect was addressed through issuance ofbonds by TMRC. An alternative method would have been to allocatepart of the project fund to inject Tier II capital to TMRC atan early stage of the project, and enable issuance of bonds later on. The ICR notes that this was an important lesson reflected insubsequent housing finance projects in other countries.
P117243 | Sustainable Management of Agricultural Research and Technology Dissemination (SMARTD) | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2013 | 2019 | 2020 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/220981588903811477/text/Indonesia-Sustainable-Management-of-Ag-Research.txt | http://documents.worldbank.org/curated/en/220981588903811477/pdf/Indonesia-Sustainable-Management-of-Ag-Research.pdf | The following six lessons are drawn largely from the ICR (paras. 119 124), together with a number ofadjustments of both substance and language in order to sharpen the natureand implications ofthe lessons:1.Integrate a Theory of Change, a Results Frameworkand an ME System in Project Management: The ICRhighlighted the shortcomings and supporting evidence of the project design in not formulating a sound results framework andoperational ME system (with realistic targets and data collection methodologies) from the outset. Also, the ICRrecognized the shortcoming of not fully embedding the PMU of SMARTD Project in IARRD by the end of the project. Accordingly,the lesson is that a successful project is based ona logical and comprehensivetheory of change and supporting resultsframework, a sound and operational ME system, and solid integration of the capacities of thePMU in the overallinstitutional management of a project.2. Balanced Reliance onLocal Staff and Consultants:Generally, this project demonstrated a sound balance in the reliance on government staff with selective consultant support(especially short term) for strategic activities and for which there was weak local capacity, rather than over reliance on externalconsultants.This included the PIU being comprised of seniorand experienced staff from the IAARD, thereby enablingclosecollaboration between IAARD and PIU technical staff. The ICR showed how this balance contributed toenhanced sustainablelocal research capacityand a platform for research managementdevelopment. At the same time, the projectbenefitedfrom adopting relevantinternational practices introduced by consultants. The lesson is thatthere areconsiderable benefits for a research organizations sustainable developmentfrom abalance of local and internationaltechnicalresearch staff.3. Strategic Importance of Knowledge Management Strategy:The SMARTD Project demonstrated a project that generated less immediately tangible outcomes which take time tomaterialize and whose impact did not become visible in the field until later phases of implementation. Moreover, the SMARTProjectlacked an explicit knowledge management (KM) strategy, and did not show evidence of influencing key institutions suchas the Ministry of National Development Planning and the MoF. This is exacerbated in the case of agricultural research, which oftensuffers from low visibility among decision makers who give priority to value for money and to expecting short-termresults. Although short of an economic and financial analysis, the success stories presented in the GoI Project CompletionReport/PCR, for example, do show that much thought was given to showcasing a good sample of technologies covering a range ofIndonesias many different agro-ecological settings. The lesson from this projects experience is that a sound KMstrategy in which success stories are presented clearly and shared widely, based on astrong and effectiveMEsystem, will generate evidence on the benefits from agricultural research and generate the rationale forcontinued financialsupport for such research4. Projects canFosterInstitutional Reforms: The SMARTDProject demonstrates how a project can contribute to and catalyze strategic institutional changes. Public sector institutions, suchas IAARD, from the outside may look too large and too entrenched to be influenced successfully through time-bound interventionssuch as the SMARTD Project. By focusing on transparency and fair competition among researchers and using various mechanisms (e.g.,an earmarked budget for competitive grant-funded schemes), SMARTD Projectmanaged to find the right incentive mix that nudgedIAARD out of its relative isolation. The lesson is that this project demonstrated the success of adifferent way of doingthings among the countrys community of agricultural researchers, based on active multi-stakeholder collaboration that putsfarmers and agri-food system actors in the drivers seat. Such good practices have become ingrained in the dailyroutines of research and extension staff working in the field, who are expected to continue to follow up on both centrallydetermined and locally determined agricultural research priorities.5. Strengthening AgriculturalResearch-Extension Linkages: Cross-country experiences, strongly confirmed by SMARTD Project, reaffirms the strategic roleof a project to strengthen synergies and functional links between public agricultural research and decentralized extension systems.Notwithstanding the reported farmer high adoption rates (about 80%), the SMARTD Project assumed the existing and decentralizedextension system was adequate to provide the needed linkages to channel effectively to the different types of farmers the improvedtechnologies generated by the project, for a wide range of commodities. SMARTD Project managed to contribute to further bridge theinstitutional divide between research and extension through several modest project-supported activities (e.g, opportunities forextension staff to get international exposure by attending seminars and workshops, allowing them to take stock of good practice andlatest developments in approaches to extension). Drawing on relevant international experience, the lesson is the benefitsfrom agricultural research projects to take aproactive role in strengthening effectiveresearch-extension linkages, fromthe outset of project design through measures such as assessing the status of research-extension linkages; and identifying keysuccessfulactions which could be scaled up. 6.Sound ME Systems are NecessaryforEconomic Analysis and Sustained Financing of Agricultural Research: Theanalysis of this projectsefficiency highlighted the shortcomings of the projects relatively weak ME system andthe absence ofanimpact assessment for the project. Accordingly, one lesson from this project is the crucial importance of ensuring aprojects ME system including arrangements for conducting a sound impact assessment of the project, especially for anagricultural research project such as SMARTDwhich addresses a strategic sub-sector in the economy and which will requirecontinued investments in the future. The other lesson is that without regular assessments of a research projectsefficiency continued financing in agricultural technologicaldevelopment will be severelyjeopardized.
P117244 | Rio State Fiscal Sustainability, Human Development and Competitiveness DPL | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Human Development | Education | IBRD | DPF | 2010 | 2011 | 2012 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/420721475072597953/text/000020051-20140624212828.txt | http://documents.worldbank.org/curated/en/420721475072597953/pdf/000020051-20140624212828.pdf | Two lessons are drawn form this project:1. The project provides a case that appears to validate the effectiveness of a Manchester type of triage system to allocate patients to emergency care attention. Although the data is not comprehensive, the system appears to have raised access to emergency care. But the question remains on the extent to which the emergency selection protocol in Rio (an adaptation of the Manchester approach) discriminated correctly emergency from non-emergency cases, as previous experiences in other countries suggest it should have.2. Outcome indicators may fail to capture the intended outcomes that result from a given policy. One case is where the indicator depends on a set of other variables in addition to the given the policy. An example from this project is the level of tax revenues, which increased primarily due to higher levels of GDP. Accordingly, a better indicator might have been the ratio of tax revenues to GDP. Another case is provided by the indicators on education, which included teachers trained and students enrolled. Both are output indicators that failed to capture the intended outcomes (completion, learning). Accordingly, failure to conduct the impact evaluation that intended to measure the outcomes was a significant pitfall in the implementation of the results framework.
P117248 | Deepening MTBF and Strengthening Financial Accountability | South Asia | Bangladesh | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2010 | 2015 | 2016 | ICRR | >=50 million & <100 million | Highly Unsatisfactory | Highly Unsatisfactory | Unsatisfactory | Highly Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/381861467992518303/text/ICRR14837-P117248-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/381861467992518303/pdf/ICRR14837-P117248-Box394823B-PUBLIC.pdf | The ICR (p. 32-35) identifies several valuable lessons, including the following: Having large contracts can facilitate procurement in an environment with limited capacity, as a large number of small procurements may overburden units responsible for procurement. However, this practice can also present high risk. In this project, a time-based contract of US$43 million for almost all technical inputs was executed by a single firm, which struggled to identify and retain experts for all different technical areas. This had a negative impact on the quality of some inputs provided.Time-based contracts may be appropriate for projects with few anticipated challenges. However, for a complex project with weak capacity to ensure value for money, this type of contract can present a disadvantage. In this project, the limited monitoring capacity at the PMCU had a negative impact on ensuring value for money in regards to outputs provided by the contractor.Ensuring consensus between the government and the Bank about the scope of a reform agenda is critical for a successful project and reform effort. In this project, the Bankâ€™s reform agenda was overly ambitious and beyond the governmentâ€™s reform scope. As a result, several activities for which there was little demand within government were not implemented.
P117270 | ML-Fourth Poverty Reduction Support Credit | Western and Central Africa | Mali | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2011 | 2013 | ICRR | >=50 million & <100 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/525111474567084998/text/000020051-20140625225506.txt | http://documents.worldbank.org/curated/en/525111474567084998/pdf/000020051-20140625225506.pdf | The ICR provides some important lessons, several of which are adapted here:1. Development policy operations that do not carefully reflect on the experiences of similar previous initiatives can easily fall into the trap of repeating earlier mistakes. Despite the discontinuation of the previous PRSC series in Mali (which was ultimately assessed unsatisfactory), the Bank immediately recommenced with a new series, before a self-evaluation of the experience could be completed and before the Bank and Government could formally review the reasons for poor performance. Yet the new program sought many of the same policy changes, even though the underlying political environment had not evolved. This diminishes the Bank's credibility in encouraging important reforms, as PRSC support can be seen as guaranteed irrespective of the results.2. Technical assistance is critical to help a low capacity administration implement a complex reform program. In Mali, the technical assistance project that was intended to be implemented in parallel with the PRSC was significantly delayed, only becoming operational in August 2011, at the end of the series. This delay hampered the program, in this case with regard to improving capacity to deliver decentralized services. Programs that are intended to be complementary with other Bank activities--technical assistance, analytical and advisory services, investment lending, etc.--should be adjusted as the timeline for delivery of those products changes.3. The selection of indicators appropriately matched to program objectives, with ambitious but realistic targets, signals the importance the Bank places on development outcomes. For PRSCs 3-5 in Mali, many indicators were dropped mid-course, replaced, or altogether ignored, a symptom of lack of realism. More than a few were focused on inputs and processes. Baselines were highly unreliable. It is thus not surprising that the Government did not take seriously its responsibility to monitor results.In addition, IEG offers the following lesson:4. Stretch reforms in areas with strong entrenched interests or that are politically sensitive require deeper commitment than typical reforms, and should be limited in number for a given operation or series. In Mali, these included introducing private participation into the cotton sector, creating a mechanism to increase electricity tariffs in line with costs, and reducing the focus on incentives in investment promotion. Each of these reforms was delayed considerably and ultimately failed. Given the obvious challenges in implementing each of these reforms as evidenced by past efforts, an approach that focuses the Government's energy and political capital on one key issue head on, while laying the groundwork and building consensus for the others, may be more effective.
P117275 | The Gambia Integrated Financial Management Information System Project | Western and Central Africa | Gambia, The | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2010 | 2021 | 2022 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/960741630332642424/text/Gambia-The-Integrated-Fin-Mgt-Infor-System.txt | http://documents.worldbank.org/curated/en/960741630332642424/pdf/Gambia-The-Integrated-Fin-Mgt-Infor-System.pdf | The following lessons were drawn from the ICR:A well-defined PDO can facilitate tracking project progresstowards its objectives. In this project, the PDO was initially too broad. the PDO should have been formallyamended to reflect the significant expansion in scope.Political commitment and ownership of the borrowermatter. An explicit target IFMIS completion date could be announced early in project implementation and monitored closelyat the highest level.The context for implementing reforms in a challenging environment need to be well understood.PFM reforms cannot be achieved focusing only on technical solutions but need to be accompanied by behavioral andpolicy change.
P117279 | Third Reengagement and Reform Support Program | Western and Central Africa | Liberia | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2011 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/355301490883742632/text/Liberia-LR-RRSP-3-Budget-Support.txt | http://documents.worldbank.org/curated/en/355301490883742632/pdf/Liberia-LR-RRSP-3-Budget-Support.pdf | The first three lessons are taken from the ICR with some adaptations; the fourth is drawn by IEG:In fragile countries, it is essential to select the prior actions carefully, which should be critical to the governmentsoverall reform program, and take into consideration implementation capacity. Such an approach is necessary not only to reduce thetransaction costs for the Authorities, but also to increase the probability of full action implementation and long termsustainability. In this case, only three previous actions were selected, all of which were critical to the Governmentsoverall program, and fully owned. The harmonization of external support contributes to the reduction of transactioncost for the Government. The Common Assessment Framework (CAF) plays an important role in harmonizing such support. The effect ofthe CAF in reducing the transaction cost on the government could be even greater with more commitment to the instrument, since thedialogue is centered on a single agreed matrix. There was stilla great deal ofbilateral dialogue, at the initiativeboth Government and of the external partners. It is important to engage with political actors outside the Executivebranch, particularly the legislature and civil society. In the case of Liberia, the political economy of the country was such thateven though the Presidents party was in the majority in the Legislature, the President was not necessarily the leader of theparty in the legislature. Thus, in spite of the Executives endorsement of a Bank operation, the legislature had the capacityto override it. An earlier engagement with political party leaders and other key players could have led to a more successfulresult. In fragile and post-conflict countries, the establishment of a steering committee representing governmentand external partners is a critical tool to coordinate the national construction agenda. This was the case of Liberia, where aLiberia Reconstruction and Development Committee (LRDC), was established, chaired by the President of Liberia herself,andcomposed ofthe Ministers of Defense, Finance, Planning and Economic Affairs, and Public Works, as well as majorpartners including the United Nations, the United States, China, the World Bank Group, the European Commission, the InternationalMonetary Fund, the African Union and the Economic Community of West African States.
P117281 | Economic Governance & Recovery Grant III | Western and Central Africa | Cote d'Ivoire | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2011 | 2013 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/461131474939457016/text/000020051-20140625111922.txt | http://documents.worldbank.org/curated/en/461131474939457016/pdf/000020051-20140625111922.pdf | The main lessons identified in the ICR and by IEG's review include the following:A well-designed, non-programmatic series of stand-alone operations can form the basis for reasonably predictable policy-based support, even in highly uncertain political environments. This lesson is consistent with IEG's findings that adjusting the content of programmatic DPOs in the midst of crises is generally difficult (see, for example, IEG's 2010 study, The World Bank Group's Response to the Global Economic Crisis (p. 108).The choice of the appropriate counterparts in government is an essential element for success, especially if these counterparts are real influences or decision makers.Even in a difficult environment characterized by political instability and weak capacity, progress can be achieved by focusing policy lending on a few actions that are in line with the countryâ€™s own priority, politically feasible and technically ready thanks to a sufficient body of knowledge built through analytical work and technical assistance.Additionally, IEG noted that operations like EGRG3 are better monitored from the field, particularly where there is a determined government counterpart who needs support. When the Bankâ€™s Task Team Leader (TTL) is not in the field, the use of a locally based co-TTL should be considered.
P117282 | Economic Recovery and Gov. Grant 3 | Western and Central Africa | Togo | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2011 | 2012 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/935741474587172455/text/000020051-20140624212345.txt | http://documents.worldbank.org/curated/en/935741474587172455/pdf/000020051-20140624212345.pdf | Two lessons are drawn from the experience of this operation: Good performance on reform objectives (e.g., public financial management) does not guarantee success in achieving higher level objectives, particularly if the operation's design fails to properly consider the links of the former to the latter.As a corollary, failure to include the link of reforms to higher level objectives in the M & E design may weaken awareness of those links and impede adequate information/analysis needed to correct policies. By way of example, establishing the links of reforms in the cotton company to higher order outcomes (investment in the cotton sector) and monitoring investment in that sector might have enriched the dialogue on the reforms needed and perhaps helped achieve stronger progress in this area.
P117287 | BJ- Poverty Reduction Support Grant - PRSC 6 | Western and Central Africa | Benin | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2012 | 2013 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/344761474558359159/text/000020051-20140625225901.txt | http://documents.worldbank.org/curated/en/344761474558359159/pdf/000020051-20140625225901.pdf | The ICR draws a number of important and appropriate conclusions about defining realistic objectives and selecting results indicators that can be attributed to actions supported by the operation; and pursuing narrower, but deeper reforms, with more coherence across policy areas. (p. 52)Two lessons from this review are first, that linking the various triggers and prior actions more tightly to AAA, and to Benin's development challenges, explicitly defining objectives and expectations, and ensuring that accompanying measures would be undertaken could have improved outcomes, or at least strengthened the dialogue and monitoring.Second, while oversight during preparation of the various operations flagged potential problems, more explicit guidance from best practice findings would have been beneficial, for instance keeping the focus on a single sector in infrastructure, or maintaining a consistent dialogue in education and civil service reform throughout the series.
P117310 | Results in Nutrition for Juntos SWAp | Latin America and Caribbean | Peru | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2011 | 2017 | 2018 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Highly Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/276641530385034229/text/Peru-PE-Results-Nutrition-for-Juntos-SWAp.txt | http://documents.worldbank.org/curated/en/276641530385034229/pdf/Peru-PE-Results-Nutrition-for-Juntos-SWAp.pdf | The ICRR presented a number of well-noted lessons learned.First, arange of factors need to cometogether and mutually reinforce to support change: factors such as strong understanding of the clients political economydynamics, presence in a country, availability of resources, and cutting-edge solutions. In that regard, the timing for this projectwas right with reference, for example, to a confluence of factors including economic growth, political awareness, and civilactivism, as well as the Banks own experience in relation to nutrition leading to a multi-sectoral approach to amulti-faceted problem, and the use of evidence-based interventions to ensure a technically rigorous design (ICR, p. 19).Second, effectiveness potential is enhanced where responsibility for implementation is assigned to an administratively capable andpolitically influential agency endowed with the necessary technical competencies. TheICR commended relevant governmentparties (MEF, Department of Public Expenditure, and others) in that regard. Third, it is vital thatrequired incentives areboth understood and correctly implemented. The project built on existing success in its three focus areas that allowed for thetransfer of additional resources to local governments based on results (with an emphasis on better planning), thereby aligning theincentives of different actors (from regional governors to local mayors, executing agencies,and local health clinics anddoctors). Finally, robust and timely monitoring is important in achieving results, as it draws attention and focus to need when andwhere it arises.The ICR also made three recommendations: (i) even more flexibility than is allowed underexisting instruments, including Program-for-Results, will be required tofoster innovative interventions; (ii) World Bankteams, as well as borrowers, should make a conscious effort to be as coordinated as possible, and to align incentives accordingly,from the design phase onwards; and (iii)Bank teams need to be more business-focused to ensure longer-term traction andinfluence.IEG adds the following:Whenpromoting innovative solutions thatrequire significant investment, ensuringpolitical buy-incan avoid the possibility of efforts being reduced,withreference to sustainability,to a technical exercise. In this case, the waning support behind the multi-sectoralapproach and the lack of budget to support technical platforms threatens the sustainability of what look like promising innovationsand positive outcomes. A similar point can be made with reference to service delivery more broadly. Successful and sustainableservice delivery requires a full scan of the territory to ensure, upstream, that all the necessaryenabling conditions aresatisfied (e.g., regulatory, legal, technical, etc.), supported as the effort moves downstream by adequate inputs (e.g., humanresources, technology, service standards, etc.), and effected through appropriate delivery mechanisms/models and supports (e.g.,through a centralized orcommunity-driven developmentapproach, through a multi-sectoral effort or sector-specificeffort). In this case, despite positive work,sustainability is threatened due to a shift in a number of factors based on athreat that, to some extent, was known to the Bank team.On a related point, the ICR (pp. 1-2) commented onthe positive role played by the MEF in achieving synergiesto formalize commitment to achieving better results and greateraccountability on nutrition outcomes by including the PAN among the programs to be monitored under the performance-based budgetingpilots. The ICR stated that the success of PAN rested on three pillars: use of result-based budgeting; a unified approach with noone entity having ownership of nutrition (a shared priority under shared responsibility); and specialized trainingfor public servants. However, the ICRnotedrisks to development outcome given a return, subsequent to project closing,to a more fractured approach. In that regard, not havinga single entity responsible for such a critical challenge asmalnutrition may, in fact, be interpreted as a weakness rather than a strength that may threaten sustainability andfocus.Finally, to design effectivebehavioral change, it is necessary to put people at the center ofthe development process and to invest in understanding their circumstances, motivations, and the trade-offs they make, etc. Theincentive designed in this instance required a mother to present with oneinfant after which she would continue to receive thebenefit, whether or not she registered children subsequently born into the family. Thismayresult in lower ongoingdemand for health and nutrition services at the local levelwith possible knock-on effects for the reduction in malnutrition.IEGs CRIISP model provides useful guidance on the effective design of behavior change.
P117310 | Results in Nutrition for Juntos SWAp | Latin America and Caribbean | Peru | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2011 | 2017 | 2019 | PPAR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Highly Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/521261562082391212/text/Peru-Juntos-Results-for-Nutrition-Project.txt | http://documents.worldbank.org/curated/en/521261562082391212/pdf/Peru-Juntos-Results-for-Nutrition-Project.pdf | Lessons 6.21 Long-term engagement is critical to a deep understanding of complex malnutrition challenges. The World Bank's long engagement in Peru was critical to the deep understanding of the country's malnutrition challenges\. long-term support, dialogue, and a collaborative working relationship enabled an innovative project design that required coordination among various implementing agencies at multiple levels of service delivery. 6.22 Attitudes toward nutrition need to change at all levels to make a difference. Peru's commitment to reducing malnutrition started at the highest level of government. It required interinstitutional coordination from MEF, MINSA, MIDIS, SIS, RENIEC, and regional and local governments. Evidence from the field suggests attitudes are changing. For example, red, green, and yellow color-coded cards are being used to monitor and guide local-level goals and outcomes. And, in remote areas, health staff have begun to give priority to women and children who come to the health centers on market days. 6.23 It is important to address both the supply and demand for health and nutrition services. Addressing the many factors that influence nutrition is complex and challenging. Increased demand must be met with an increase in the availability of services. In the case of Peru, financial incentives and accountability measures were used to increase both the supply and demand for services through performance-based budgets, CCTs, a guaranteed package of services, health insurance, and improvements in the identification of eligible households. 6.24 Understanding the causes, consequences, and corrective actions required to reduce malnutrition can lead to changes in behavior. At approval, mothers had little knowledge of a child's normal growth process and little awareness of the link between a child's growth, development, and nutrition and health. Communication, CRED counseling, and community engagement helped increase awareness and understanding among mothers. Evidence from the field suggests the mothers' knowledge and awareness regarding nutrition and its effect on development played a role in increasing the demand for nutrition services. 6.25 Changes in beneficiaries' behaviors cannot be assumed; they must be monitored. Given the complexity of the project and the causal chain, there were unexpected implementation challenges or barriers to changing behavior. For example, remoteness was an issue that hindered mothers' ability to attend CRED sessions. Other examples include the following\. not boiling water because traditional containers are now made differently and a bad taste leaches into the water, many families do not have electricity and refrigeration to keep healthy foods, and people in higher areas cannot realistically eat meat more than once per week. In such cases, monitoring behaviors is critical to address unexpected constraints to behavior change.
P117318 | Cusco Regional Development | Latin America and Caribbean | Peru | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2014 | 2019 | 2020 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/547851588904129809/text/Peru-PE-Cusco-Regional-Development.txt | http://documents.worldbank.org/curated/en/547851588904129809/pdf/Peru-PE-Cusco-Regional-Development.pdf | The ICR offered the following lessons from the operations that other teams may consider for future similarprojects: There is a need for continuous assessment of implementing agency capacity to identify wherecritical interventions may facilitate progress. Implementing agencies with limited capacity may require a more hands-onapproach. In this project, with the delay in effectiveness overtaken by a change in leadership due to the elections, the key teammembers who were experienced in Bank processes were no longer at the helm when the project became effective. The implementingagency took time replacing key staff and there was a high turnover noted that required more frequent training to help navigate Bankrequirements, particularly procurement strategies, financial, and safeguards compliance. Having the task team in the country mayprove useful and allows for more frequent face time with the clients but the counterpart entities also needs to showtheir commitment to the project and its objectives. Adequate resources are required to accompany thecapacity-strengthening of weak institutions. An institutional capacity assessment prior to appraisal may be strengthenedby an integrated approach that consider the management, technical, fiduciary, and safeguards capacity that would supportinstitutional sustainability. Such an assessment could identify critical risks that may impact project implementation and formulateappropriate risk mitigation measures. The capacity assessment prior to appraisal was not used for this project. Risk mitigationmeasures could introduce flexibility with procurement thresholds to respond to project needs. Projects in difficult contexts suchas this project need adequate financing and investments in capacity building. In this project, project management was at 11.7percent of total project cost. Achieving specific milestones -- as theimplementation experience expands andstrengthens institutional capacity -- could be used to trigger a sequence of activities leading to the achievement ofprojectobjectives. An incremental, programmatic approach may be useful for projects implemented for the first time by subnationalgovernments with weak capacity. This project showed that the regional government was ill equipped to implement complex projectswith numerous components and activities, especially as they were required to navigate complex bureaucratic processes associatedwith the national investment system. This project showed that a programmatic, sequential approach with a simplified project design,reasonable number of components, accompanied by building implementation capacity may be a less riskyproposition. Astrong social sector team could help overcome sensitive community issues duringimplementation.Projects with social components require that the implementation agency include a strong social team.In this project, there was a lack of such staff to support this aspect of the project. There were no clear and effectivecommunications or social outreach strategy to address the concerns raised by affected communities when landfill sites wereselected, for example.
P117323 | Indonesia Power Transmission Development Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2011 | 2020 | 2021 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/201911608755401615/text/Indonesia-Indonesia-Power-Transmission-Development.txt | http://documents.worldbank.org/curated/en/201911608755401615/pdf/Indonesia-Indonesia-Power-Transmission-Development.pdf | This review has drawn two lessons incorporating material on lessons listed on pages 33-34 of the ICR.Anintervention scattered in a large project area may make establishing attribution difficult. All 77 substations werecommissioned and energized at project closure. The project objective level indicators, i.e., increase in electricitysales and reduction in the frequency and duration of outages, captured the outcomes achieved at the systemlevel; therefore, it was not possible to measure the exact extent of the development impact of the project, and establish fullattribution between the projects intervention and the outcomes achieved as a result of this intervention. Theprojects intervention was on the critical path to achieve the remarkable results in meeting increased electricity demand andimproving the electricity supply reliability, but because of the nature of the projects intervention, itbecamedifficult to demonstratefull attribution, absence of which resulted in a Moderately Satisfactory outcome rating rather thanHighly Satisfactory.Direct lending to project implementing utilities may improve project implementationefficiency. In this project, PLN had to get approval from the Ministry of Finance for annual budget and disbursement (ICR,p.34). Because of long processing times of such approvals, payments to contractors were delayed between December and February everycalendar year. This resulted in delays in contract implementation. The project team, supported and directed by the CountryManagement Unit, facilitated the issuance of a Presidential Decree that allowed direct loans to state-owned-enterprises, includingthe PLN.As a result of this decree, for any future projects, the processing of invoices and payments to contractors could beaccelerated, and project implementation efficiency could be improved. However, direct lending may not be applicable to all futureprojects since the government and PLN have specific criteria of which project to use direct lending mechanism.
P117341 | HaJia Railway | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2014 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099910005132224940/text/P117341071f7c50f60bed40579f122a6989.txt | http://documents.worldbank.org/curated/en/099910005132224940/pdf/P117341071f7c50f60bed40579f122a6989.pdf | The ICR draws the following main lessons from the experience of implementing this project which IEG supports,with someadaptation of language.1. Limited Bank financing can provide project stakeholders with confidence that economic,fiduciary, and safeguard aspects of large infrastructure projects are adequately carried out. This and the other railprojects financed by the Bank followed theBank policies and procedures in fiduciary management and environmental and socialsafeguards, despite the Banks small financing contribution (five percent of project costs). Capacity assessments, trainings,establishing project management arrangements, preparation of adequate financial management, procurement, environmental and socialdocuments were carried out and prepared. All this gave the project stakeholders confidence that these aspects of implementationwere properly carried out.2. For a railway or any other large infrastructure project to be successful (andcost-effective), long term planning,strong government commitment, and an experienced implementing agency areessential. In this project, the China Railway Company (CRC) took the major responsibility for planning, financing andimplementing individual projects, for creating delivery mechanisms, for collaboration with local governments, and foradministration of Chinas national railway services. This enabled the contractors to make long-term commitments and broughtcosts down.3. Good project management is essential for the success of a large and technically complexinfrastructure investment projects. In this project, two parties, namely the Hajia Railway Company (HRC) and the localgovernment, each with quite different incentive structures and resource windows were responsible for separate but interrelatedtasks. The railway company was tasked with the responsibility of building the project quickly, so had little incentive to take thetime to examine planning and engineering options to minimize impacts. The local government was tasked toacquire land andrelocate project affected persons on a timely basis to match construction schedule. This misalignment of accountabilities createdchallenges and contributed to the delays in resettlement in this project.
P117345 | Seventh Poverty Reduction Support Credit - Supplemental Financing | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2010 | 2013 | PPAR |  | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/542381468133184866/text/781880PPAR0Tan00Box377382B00PUBLIC0.txt | http://documents.worldbank.org/curated/en/542381468133184866/pdf/781880PPAR0Tan00Box377382B00PUBLIC0.pdf | 4. Lessons 4.1 The implementation of PRSCs 1-8 spanned nearly a decade during a period of sustained macroeconomic stability and fast economic growth, offering lessons both for Tanzania and other countries with similar development challenges. 4.2 Lesson 1\. Direct and sustained focus and clarity of vision over the entire course of implementation of PRSC programs that cover many years is required to facilitate lasting reforms particularly with regard to public sector governance. There is a significant risk of backsliding when attention is shifted to other priorities. Yet joint budget support is a messy attempt to reach a common understanding, always subject to change, with a wide range of domestic stakeholders and international development partners. In Tanzania, intense dialogue and very high government commitment led to early successes in improving public financial management and budget execution in the first PRSC series. But some achievements stagnated or were reversed in the second series, when attention was diluted to include a broad range of sectoral reforms and other aspects of governance. 4.3 Lesson 2\. PRSCs can make little progress without a foundation of trust between the Bank and the government, and among development partners at the institutional and individual levels. Without sufficient trust, negotiated and agreed-upon triggers can quickly be transformed into more heavy handed conditions, whereby the level of future support is determined by strict adherence to pre-identified policy changes. In these circumstances, a scaled-back operation, more tightly focused around areas of agreement might gain more traction than one used as an enforcement mechanism for previously agree reforms that no longer have political backing. 4.4 Lesson 3\. PRSC programs risk becoming irrelevant if the design, scale, and scope are not adjusted as conditions change. The advance expectation that such changes will occur may smooth the transition should events warrant a scaling back of the program. Circumstances changed substantially during the second PRSC series in Tanzania\. reform champions in government and among development partners moved on; the presumption that sustained growth of 6-8 percent would lead to significant poverty reduction proved false; a new President was elected; and the country was affected by higher food and fuel prices and by the global financial crisis. The mechanisms for dialogue also need to evolve so that the program can continue to support and influence policy decisions at the highest strategic level. To avoid misunderstanding, the Bank and government could plan in advance to recalibrate the program at a set point during implementation. 4.5 Lesson 4\. The lack of well-defined and realistic objectives and a fully developed results framework makes adjustment to changing circumstances difficult. A results framework that clearly explains how policy actions are expected to lead to desired outcomes, in light of the support provided through investment lending and by other development partners, can provide a results-focused discipline to the program, improving selectivity in the process. 4.6 Lesson 5\. Regular reporting on key outcome indicators is essential so that data can drive adjustments to the PRSC program. Adequate investment in statistical capacity and the creation of a robust monitoring and evaluation system that addresses each step of the results chain to identify the key drivers of success or failure, while remaining focused on a few key outcome indicators, can help guide long PRSC series as circumstances evolve. Policy makers need to be aware of trends in outcomes in order to adjust the program accordingly. In Tanzania, reliable data on, for example, income poverty were available only once every seven years or so. Interim poverty simulations suggested significant poverty reduction as a result of sustained growth, but these projections turned out to be inaccurate. Household surveys every 3-4 years could provide much more timely and meaningful data to policymakers to allow for evidence-based adjustments during implementation. 4.7 Lesson 6\. Transitioning to the use of PRSCs as the primary instrument for resource transfer is only likely to be successful in rare circumstances, when strong central ministries can fully pursue a sector-inclusive dialogue representing the perspectives of key players throughout government. PRSCs themselves have very limited leverage in sector ministries, and the number and specificity of sector-specific triggers are necessarily curtailed when many sectors are covered. 4.8 Lesson 7\. Elevating to the national dialogue sector-specific structural reforms that stalled at the sector level does not guarantee their implementation. Even as the depth of sector exposure and experience permitted the sector content to be brought opportunistically into the PRSC, there is no evidence that this accelerated sector reforms or achieved greater cross-cutting momentum. Indeed, many of the same obstacles can prevent these reforms from taking hold, as was the case in energy, transport, agriculture, and water. Moreover, policy reforms committed to by central ministries are likely to be seen by implementing agencies, less vested in the PRSC program, as externally-imposed conditions, and subverted rather than adopted.
P117355 | DJ-Rural Community Development and Water Mobilization Project (PRODERMO) | Middle East and North Africa | Djibouti | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2011 | 2020 | 2021 | ICRR | >=10 million & <25 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/978771607987150170/text/Djibouti-DJ-Rural-CDD-Water-Mobilization.txt | http://documents.worldbank.org/curated/en/978771607987150170/pdf/Djibouti-DJ-Rural-CDD-Water-Mobilization.pdf | The ICRincluded four lessons. The following three are emphasized with some adaptation oflanguage: There is a need to ensure that the enabling environment for specific project interventions isassured.For example, in this projectthe regenerationof vegetative cover, particularly tree cover,was introduced to reverse desertification to ensure the feasibility of micro dams, soil and waterconservationworks.Such interventions are more essential than ever in the context of climate change in Djibouti andalike countries. Accessible innovation, advisory services and access to markets are key elements for sustainableagriculture and livestock development. The projectfocused mainly on water mobilization units and less on agricultureand livestock development. The adoption of advanced agricultural technologies (e.g. micro-irrigation, greenhouses, hydroponics),requires cutting-edge skills compared to more traditional agriculture. Such skills can be acquired through well-trained, andexperienced teams providing agricultural and management advice. However, marketing advice to producers to improve their economicperformance in the newly irrigated areas was not an objective of the project.Nevertheless, the lesson from this project isthat producers who adoptadvanced agricultural technologiesrequire commercial partnerships with buyers and inputsuppliers (along the lines of productive alliances) to generate sustained profits. Beneficiariescontributions to income-generating activities(IGAs) strengthened their ownership of these activities and the likelihood ofsuccess.IGAs are a high-risk project component that requires careful planning, preparation, selectivity, and strongcomplementary support such as business skill development; participatory preparation, review, and monitoring of business plans; andmarket analysis).The 10% contribution requested to access matching grants for IGAs was accepted by all participants in thisproject. Even the poorest found the means to meet this threshold for disbursement of the matching grant. The lesson is that thisrequirement prevented distortions in eligibility and provide an incentive to be successful. Indeed most IGA participants weresuccessful, which was attributed to a large extent to the requirement for 10% contribution, which instilled a sense of ownershipamong beneficiaries.
P117365 | Urban Water and Sanitation Project | Western and Central Africa | Niger | IDA | FCS | Sustainable Development | Water | IDA | IPF | 2011 | 2021 | 2022 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099315103282210892/text/P1173650067af10d60be630feab2392ab4a.txt | http://documents.worldbank.org/curated/en/099315103282210892/pdf/P1173650067af10d60be630feab2392ab4a.pdf | IEG derives the following lessons drawn from the ICR:Delegation of water service provision to private companiesin public-private-partnership can be effective in achieving significant and sustained gains in access and servicequality. From the implementation of its affermage model in 2001 to the time the project closed, Nigersurban water sector has demonstrated substantial gains in operational performance, while simultaneously increasing the populationserved by nearly 220 percent, reaching nearly 4 million customers in 2020, 98.4 percent of the population within SPENsservice area (up from 73.4 percent in 2011). Nonrevenue water decreased from 20 percent to 15 percent of water production, and thebill collection ratio increased by 18 percentage points from 79 percent to 97 percent, before falling to percent to 88 percent bythe time the project closed, likely due to the significant number of poor and vulnerable communities that started receivingservices under the project (ICR pages 2 and 18). SEEN, a subsidiary of the French transnational company Veolia, has effectivelyleveraged the vast global experience of its parent company to introduce improved processes and build staff capacity for effectivewater systems management. Meanwhile, performance-based elements are embedded in the contracts of both SPEN and SEEN and monitoredby the sector regulator to improve accountability and incentivize performance.The leveraging of complimentary Bankinstruments and activities can improve the prospects of achievingambitious objectives. To strengthen the financialsustainability of the water service providers, the project included as a PDO results target, restoration of financial equilibriumof the urban water sector. This required the government to clear its arrears and to implement a tariff adjustment plan, but neitherthe Ministry of Water and Sanitation, nor the implementing agencies had sufficient leverage to bring this about. The Bank team usedthe opportunity of the preparation of the Second Laying the Foundation for Inclusive Development Policy Financing to agree with thegovernment on three prior actions to strengthen the sustainable delivery of water and sanitation services. These were (a) theclearance of arrears, (b) the issuance of a presidential decree approving a water tariff adjustment plan, and (c) issuance ofpresidential decrees appointing the director general of the Water Regulatory Authority and the president and members of the WaterRegulatory Council. Similar synergies across the Bank portfolio can allow Bank teams to expand the scope and impact ofprojectsincluding through influencing higher-level government actorsand should be considered duringpreparation.Where government interference in procurement is a significant risk, clear measures needto be put into place to prevent mis-procurement and consequent delays in project implementation. Political interference inthe procurement process led to significant delays throughout the project implementation period. In addition, commitments made bythe GoN during project preparation were not always respected by subsequent administrations. For example, in direct opposition to aprovision in the subsidiary agreement with SPEN, Nigerien customs authorities sought to collect custom duties and indirect taxesfor project-related expenses during its final year of implementation. Task teams can incorporate measures in the project design toreduce the likelihood of political interference and ensure continuity across administrations. For example, this project helped toreduce the impact of political interference by insisting on a role for the procurement specialist of the PCU in the procurementdecisions of SPEN and the General Directorate of the Sanitation. Other useful measures included (a) leveraging ministerial generalsecretaries and other civil servants in key discussions to preserve institutional memory; and (b) thoroughly briefing new ministersat the start of their mandate on their responsibilities under the project, financing agreements, and prior commitments by previousadministrations.Continuous dialogue by the Bank team throughout project implementation is critical to ensurechallenges are addressed as they arise, particularly in fragile and low-capacity countries. Having members of theBanks project task team based in country allows for more consistent follow up to identify and address challenges. TheBanks final task team leader, who had been a team member from the inception of the project, was based in Niamey. He metweekly with the PCU and implementing agencies during the final year of implementation. This allowed for the quick identification ofchallenges and implementation of remedies. For example, the task team maintained constant dialogue with the government officials toencourage them to take action to strengthen the sustainable delivery of water and sanitation services through clearing arrears,agreeing on a tariff adjustment plan, and reestablishing an independent water regulator.
P117370 | Second Poverty Reduction Support Credit (PRSC 2) | Eastern and Southern Africa | Zambia | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2012 | 2014 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/629931474633174326/text/000020051-20140626112412.txt | http://documents.worldbank.org/curated/en/629931474633174326/pdf/000020051-20140626112412.pdf | The broad thrust of the lessons in the ICR is supported:Success will be more likely in reform areas which coincide with the Governmentâ€™s own priorities and where the Bank has other instruments to engage outside the budget support frameworkWhile a budget support framework can provide a platform for sustained dialogue, by itself it has limited leverage in influencing Government policy and institutional actions in situations where official development assistance is sharply declining as a share of Government resources. The Bank should be cautious in proceeding with programmatic approaches such as PRSCs when government commitment is uncertain, and donor priorities are shiftingThe Bank should effectively manage transitions within the Bank team to ensure that reform programs stay on track, and relationships are protected between the Bank, Government, and development partners.There is a need to develop more granular, outcome indicators of public sector performance that are achievable within the term of a PRSC series. Sectoral operations are important to carry out alongside PRSCs in supporting energy sector reforms, with energy outcome indicators that address core issues of sustainability. In addition, the Bank should use indicators in policy operations that are forward looking, and not seek targets that have already been achieved prior to the appraisal of such operationsThe Bank should also carefully consider the implication of changes to the basic underpinnings of the macro framework, such as a sharp uptick in the fiscal deficit, during implementation of a PRSC programFinally, a lesson learnt from PRSC3 is that in the face of waning commitment to the original program from Government and donors, closing the series early and moving forward on a new programmatic basis may yield better development outcomes than persisting with the original design.
P117377 | Prevention and Management of Influenza Type Illness and Strengthening of Argentina's Epidemiological System Project | Latin America and Caribbean | Argentina | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IBRD | IPF | 2010 | 2014 | 2015 | ICRR | >=100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/319821475112620806/text/000020051-20150113010818.txt | http://documents.worldbank.org/curated/en/319821475112620806/pdf/000020051-20150113010818.pdf | Lessons from the ICR, adapted by IEG: Emergency loans obviously focus on the immediate issue, but this project demonstrates the potential benefits of avoiding tunnel vision and thinking broadly when designing emergency projects. The need to respond to the A/H1N1 epidemic also provided an opportunity to strengthen surveillance and laboratory systems and build up long-term preparedness, which are important components of national health systems.Using existing technical and administrative structures to implement projects has significant positive externalities. By avoiding the establishment of stand-alone project coordinating units typical for externally funded projects, this project was able to build sustainable in-house capacity and foster greater cooperation among different health units.
P117382 | DRC Establishing Capacity for Core Public Management | Eastern and Southern Africa | Congo, Democratic Republic of | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/650521528388674846/text/Congo-Democratic-Republic-of-DRC-Capacity-for-Core-Public-Management.txt | http://documents.worldbank.org/curated/en/650521528388674846/pdf/Congo-Democratic-Republic-of-DRC-Capacity-for-Core-Public-Management.pdf | The ICR (pp. 22-24) offers several insightful lessons, including:Government ownership andcommitment increase when implementation occurs through a permanent structure established by the government. In this case,SENAREC, as a permanent institution under the Ministry of Planning, enjoys full support of the central government, contributing toefficacy and sustainability of outcomes.Locating responsibility and authority under a single agency helpsto define and increase accountability for performance. In this case, the initial arrangement under three implementingagencies led to blame-shifting when shortcomings emerged. Putting one agency, SENAREC, in charge facilitated theidentification of lines of responsibility and authority.Achieving gender targets requires deliberateaction. In this case, gender data on training participants was not even collected initially because of a lack ofprioritization, awareness, and willingness. Once these elements were put in place after the mid-term review, specific actionswere implemented to attempt achievement of gender targets.IEG offers the following additionallesson:Anchoring training centers at independent entities such as universities involves trade-offsbetween capacity and sustainability. In this case, the use of government training centers -- to the extent that such centersexist -- would likely have low absorptive capacity and involve political risk. On the other hand, their location atuniversities calls into question the potential for their operation as a cohesive network, given the need for acquisition andmaintenance of costly technology and the uncertainty of full cost recovery.
P117384 | Public Sector Modernization Project II | Europe and Central Asia | Armenia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2010 | 2017 | 2019 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/539431559231050030/text/Armenia-PSMP-II.txt | http://documents.worldbank.org/curated/en/539431559231050030/pdf/Armenia-PSMP-II.pdf | The four most important lessons drawn by the ICR are the following (with some modification of language)(ICRpages 23-34).(1) Overlap with follow up projects can helpinensuring continuity in a programmatic series of operations. ThePSMP II was prepared andbecame effective while PSMP I was still being implemented. Thetwo projects were implemented by the same Bank and governmentteams. This helped inensuring that thetwo projectsfocused on the key constraints on public sectorreforms.(2) The experience of this special investment loan showed that such public-sector reformprojects are likely to be successful when they are complemented by pillars in development policy loans. While the pillarareas in the latter supported policy reforms, technical assistance and capacity building activities provided in thisproject, helped in ensuring implementation of key policy reforms.(3) The project designshoulduse indicators that measure attributes, that can be attributed to project support.TheCPIA indicatorsenvisioned at design, proved to be unworkable in practice, as the indicators were not sufficiently granular tocapture project level impact data.(4) Built-in flexibility can be useful for responding toopportunities for public sector reforms. The projectdesignallocated funding foractivities aimed ataddressing the unforeseen needs of the government and supporting interventions, if opportunities arose during implementation. Thishelped the project management to support the governmentspriority in the e-health system.
P117393 | Vietnam School Readiness Promotion Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2013 | 2017 | 2018 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/154121528725260009/text/Vietnam-VN-School-Readiness-Promotion-Project.txt | http://documents.worldbank.org/curated/en/154121528725260009/pdf/Vietnam-VN-School-Readiness-Promotion-Project.pdf | The ICR (pp. 24-25) provides several useful lessonslearned: Integrating project activities into the daily work of the responsible ministry and collaborating with different departments within theministry is conducive tosuccessful implementation. In this project, the PMU was establishedwithin the MOETs Department of Early Childhood and Education and coordinated by the ministrys Department of Planningand Finance. The ministrys systems, staff, and functional departments were used to implement the projectsactivities, allowing for the project to be integrated into the ministrys daily work rather than being a separate workstream. Supporting already existing government programs increases efficiency and sustainability of projectactivities. This project provided budget support and used ongoing budget lines without creating additionaltransaction costs. This allowed for a smooth transition after project closing. Providing technicalassistance activities in addition to budget support is important to improvingasystems overall quality. In this project, while only fivepercent of project funding was used for technical assistance activities, thisactivitywas criticallyimportant forstrengthening the professional developmentof ECE staff, developing ECE policies and regulations, andbuilding capacityfor financial management, project management, and monitoring and evaluation. Combining different types of MEactivities while also providing technical assistance to build capacity cancontribute to highMEquality. This project combined various assessments, the use of DLIs, and regular project indicator monitoring whilealso providing technical assistance in various areas such as strengthening planning and reporting systems for ECE, and supportingindependent verification and performance audits for DLIs. Combining all these different activities resulted in high qualityME.
P117393 | Vietnam School Readiness Promotion Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2013 | 2017 | 2019 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/254991560184295154/text/Vietnam-Education-Projects-School-Readiness-and-Escuela-Nueva.txt | http://documents.worldbank.org/curated/en/254991560184295154/pdf/Vietnam-Education-Projects-School-Readiness-and-Escuela-Nueva.pdf | 5. Lessons 5.1 IEG identifies the following lessons from its evaluation of the two operations\. â€¢ In addition to lending, the World Bank can add value through the transmission of knowledge from experiences and lessons that help shape reforms. This included World Bank economic and sector work, study visits, the introduction of international experts, and the introduction of lessons gleaned from an experienced team that built on the long-standing relationship of mutual trust between MOET and the World Bank. The World Bank's knowledge capability was a useful complement to the implementation capacity of the education system in Vietnam. For SRPP, the World Bank advocated and helped support the rollout of a systemwide approach through preschool accreditation to improve quality. Since closure, the government has moved to universalize enrollment beyond kindergarten and has further refined the school selfassessment process. VNEN introduced a new pedagogic philosophy into the primary education system. Many teachers have expanded their pedagogical skills and the model laid part of the foundation for the current curriculum reform and associated teacher training. â€¢ When significant pedagogical changes are required of teachers, incentives, support, and long-term commitment are needed (probably more than education systems realize). The changes envisioned in both of these operations were neither simple nor easy. Studies show the importance of follow-up support to facilitate the application of in-service training. Within the education system, existing mechanisms provide follow-up support to teachers such as school visits, principal feedback, and peer-to-peer learning at school cluster meetings. Some of these mechanisms were applied under both projects, but VNEN employed them more extensively. For example, during the school year, two to four technical support team meetings and training sessions were conducted for VNEN schools. These meetings and sessions involved classroom observations, interviews with teachers and school management, review of logbooks, and exchange of experiences with principals and teachers. E-learning was used under SRPP for follow-up knowledge. Although it may serve to bridge at least some of the existing gaps in follow-up support, e-learning is unlikely to represent a panacea. Constraints in the implementation of SRPP e-learning modules suggest the need to address these issues. This emphasizes the need for long-term commitment and to leverage existing mechanisms more fully to bring about the kind of quality teaching envisioned. â€¢ When scaling up or adopting a systemwide approach, it is important to understand and design this approach in accordance with the decentralized context and challenges faced at the various levels of administration. SRPP required provincial and district officials to provide follow-up support after faceto-face cascade training and to provide technical knowledge to the preschool accreditation and school self-assessment process. Follow-up support to teachers in SRPP and VNEN was implemented more effectively in some provinces than in others. An analysis was conducted (by SRPP) to understand how the decentralized systems operated and to detect capacity constraints. Yet design and implementation did not differentiate resources or technical support to provinces and districts to address differences in capacity. As a result, disadvantaged provinces had much lower percentages of accredited schools. The DLIs set an appropriate incentive for the central level but not for provincial and district levels. â€¢ Targeting disadvantaged areas does not translate into targeted efforts for specific vulnerable groups. The self-selection process under VNEN was used to encourage a demonstration effect in locations where ethnic minority and other 27 disadvantaged populations were present. The school selection process under VNEN favored the best schools (for demonstration effect) in locations where ethnic minority and other disadvantaged populations were present but not necessarily schools in which such children were concentrated. The targeting strategy was implemented to generate the momentum needed to support the further adoption of the model in all provinces (this resulted in greater voluntary adoption in the wealthiest provinces). Although this approach is sensible, it may have missed opportunities to target even more ethnic minority children. SRPP provided lunch subsidies to disadvantaged families, but all other aspects of the project were applied systemwide. A social assessment detected multiple enrollment barriers for ethnic minorities, such as distance from school or parental knowledge, that were not addressed. The baseline survey substantiated the higher level of vulnerability among ethnic minority children (compared with those who speak Vietnamese). Considering the critical juncture for language development during the early years, targeted action was needed to support learning in the first language and introduction to Vietnamese. â€¢ When scaling up, the importance of consultation and communication cannot be underestimated. The literature suggests that scaling up programs requires those promoting the innovation to convince stakeholders of the effectiveness of the intervention. Both of these operations had broad political support. Despite the attention to communicating with stakeholders, particularly during the early stages of VNEN implementation, the scaling up of the model proved challenging. The communication challenge was associated with substantial changes for teachers and divergence from what parents traditionally experienced in school and, more particularly, the expansion of the model to nonproject voluntary schools that did not benefit from the same concentration of support as their project-based counterpart schools. Education is a heavily debated topic in Vietnamese society, suggesting the critical role for sustained and sophisticated communication regarding planned change.
P117394 | Fostering Innovation through Research, Science and Technology (FIRST) | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2013 | 2020 | 2021 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/675071607123677463/text/Vietnam-VN-Science-Technology-Innovation.txt | http://documents.worldbank.org/curated/en/675071607123677463/pdf/Vietnam-VN-Science-Technology-Innovation.pdf | Lessons drawn from the ICR (pages 29-30), adapted by IEG: Given the nature of the STI sector and the emphasis onfast-paced innovation,a cumbersomegrant processfor private sector beneficiaries (including start-ups) can be ahindrance to effective and timely responses. In the caseof this project, highly centralized and slow approval processesfrom the public sector led to extensive delays in grant project start-up. Streamlined fiduciary processes (includingdelegation of responsibilities to the grantee organizations, with clearance required for only major changes) resolved theimplementation bottlenecks. Strong collaborationbetween the public and private sectors, facilitated by effectivepartnership mechanisms,is critical todeveloping the STI sector. In the case of this project, public researchinstitutions were able to provide resources (financial and knowledge) with private enterprises providing innovative ideas andmarket relationships. The various grant-making schemes helped to establish and institutionalize partnerships and processesbetween the sectors.
P117407 | EG - Helwan South Power Project | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2013 | 2019 | 2021 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/425031605805927994/text/Egypt-Arab-Republic-of-EG-Helwan-South-Power-Project.txt | http://documents.worldbank.org/curated/en/425031605805927994/pdf/Egypt-Arab-Republic-of-EG-Helwan-South-Power-Project.pdf | The ICR draws the followingmain lessonfrom the experience of implementing this project with some adaptation oflanguage.1. Using country specific historical data in benchmarking can lead to overestimation of project costs andunder-utilization of project funds. The actual plant costwas about 40 percent lower than the appraisalestimate.Whileother factors,such as competitive bidding and exchange rate changes during implementation, wereat play as well,the lesson is that the appraisal estimate should be based not only on country historical data,butalso benchmarked on global market prices to avoid under -utilization of project funds. This is especially so, given that costoverestimation has been a recurring issue in similar energy projects in Egypt, such as in the Ain Sokhna Power Project and the WindPower Development project.The ICR draws the following lesson from this project.1. Strict technicaldesigns can adversely affect the development impact of the project, if conditions fundamentally change. Given the countrycontext at appraisal, the power plant was designed to run on both natural gas and heavy fuel oil. During project implementation,the discovery of large proven natural gas reserves resulted in a rapid increase in the construction of more efficient combinedcycle gas turbine power plants. The technical design of the Helwan South Power Plant could not be revised under these newconditions. Egypt has now a large surplus of generation capacity, and there is a risk that the power plant would not be used at theestimated capacity, resulting in a lower than expected development impact.
P117414 | Supporting Civil Society Participation in Improving Education Sector Results | Other | World |  |  | Human Development | Education | RETF | IPF | 2010 | 2012 | 2017 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/795261475163295727/text/ICRR-P117414.txt | http://documents.worldbank.org/curated/en/795261475163295727/pdf/ICRR-P117414.pdf | Lessons drawn fromthe ICR adapted by IEG: From the Bank side, when signing a grantagreement, it is critical tomake sure that its partners have a clear understanding about their roles and responsibilitiesbefore implementation starts. Adequate resources and time for project preparation and supervision, regardless ofaprojectsfunding modality, are essential for successful implementation.Lessons drawn byIEG: In some circumstances, both the Bank and the Borrowercan learn more from a full-scale externalevaluation commissioned by donors and partners than from an ICR. This was not a regular Bank project. For such a complex andmulti-layered project that involved many stakeholders, the regular implementation completion and results report format was not thebest way of assessing effectiveness. Ensuring the same rigor in designing, implementing and supervisingtrust fundedprojects as for IDA/IBRD-fundedprojectscan leadto better outcomes and lower reputational risks for theBank. For a project of large scale, supporting capacity-building of CSOs in many countries, carrying out a beneficiarysurveycan unearth many lessons related to the capacity building of civil society and the larger groups ofstakeholders engaged in education advocacy in these countries.
P117417 | Nepal: Second HNP and HIV/AIDS Project | South Asia | Nepal | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2010 | 2016 | 2017 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/182401495645541846/text/ICRR0020588-REVISED-PUBLIC-P117417-ICRR-20170728.txt | http://documents.worldbank.org/curated/en/182401495645541846/pdf/ICRR0020588-REVISED-PUBLIC-P117417-ICRR-20170728.pdf | The ICR (pp. 26-27) offers several lessons, including: Effective governance is a fundamental prerequisiteforsmooth health systems functioning. In this case, both strategic and ground-level governance issuesprevented effective response to ongoing challenges. The Banks follow-on project is designed to address these basicissues. Reform agendas will falter in the absence of realistic assessments of institutionalcapacity. In this case, project preparation did not take adequately into account concerns about human resourcedeployment, procurement and financial management systems, and overall political economy issues.IEG offers thefollowing additional lesson: Reliance on external surveys and other methods of data collection risks inabilityto measure and demonstrate achievement ofdevelopment objectives. In this case, the projects own ME did notcontain adequate baseline and outcome data covering the entire project period, particularly for key targetpopulations.
P117421 | Mongolia - Development Policy Credit 2 | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2011 | 2013 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/516021474905719529/text/000020051-20140625191133.txt | http://documents.worldbank.org/curated/en/516021474905719529/pdf/000020051-20140625191133.pdf | Election cycles affect program implementation and that has to be taken into account in designing reform-based budget support operations, There should be greater focus on understanding the implications of and the potential risks for programs under preparation arising from excessive political promises during the campaign.Once introduced, universal cash transfers are very difficult to withdraw even if they have specific sun-set clauses, especially if the high commodity prices can support these expenditures in the near term. The Bank should fully engage with relatively poor resource rich countries at the very early stage to help them to avoid the introduction of transfers that are not fiscally sustainable, are socially counterproductive, and are difficult to withdraw.Although the IMF has the main responsibility for the dialogue on macro and fiscal sustainability issues, the Bank can usefully include quantitative targets on fiscal and macro performance in a DPO, in consultation with the IMF, especially when the Fund program had already ended. Mongolia needed to gradually move to the balanced budget in 2013, as required by the Law, and the program could have supported that by introducing fiscal targets to help to move smoothly to that objective.
P117440 | Income Support and Employability Project | Latin America and Caribbean | El Salvador | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2010 | 2017 | 2017 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/995861497633250271/text/ICRR-Disclosable-P117440-06-16-2017-1497633234137.txt | http://documents.worldbank.org/curated/en/995861497633250271/pdf/ICRR-Disclosable-P117440-06-16-2017-1497633234137.pdf | The ICR (pp. 20-22) offers several useful lessons, including the following lessons adapted byIEG:A temporary income support program effectively responds to a crisis when it combinespredictable income with training and community activities to improve the participants employability and earnings,as undertaken by the project.Effective targeting of beneficiariesrequiresa combination of technical methods with validation by local community knowledge. Under the project,local leaders and Associations for Community Development were involved in the validation of the temporary income participationrosters.Designing and implementing a cash transfer program in high-crime areas require ownership bylocal actors because of their knowledge of the territory, local stakeholders, and prevailing risks. The governmentextended efforts to enhance municipality ownership, as municipalities could manage risks in their own territory, work closely withcommunity leaders and police, and implement security protocols to ensure the safety of programparticipants.A strong inter-sectoral coordinating body caneffectively facilitate thedevelopment of a social protection system. The Technical and Planning Secretariat of the Presidency had adequatepolitical and technical leverage to coordinate main stakeholders, reach inter-sectoral consensus, follow up on the implementationof social protection programs, and ensure the provision of financial resources by the centralgovernment.The TTL identified another lesson during the TTL meeting with IEG Team(4/19/2017):Legislationwill be most successfullyimplemented whenaccompanied by framing the rulesthat would facilitateexecution of the new law and make it operational. Under the project, initial effortsunderstandably focused on processing the Social Protection and Development Law. Implementation of the law progressed onlywhen an operational manual was developed.
P117440 | Income Support and Employability Project | Latin America and Caribbean | El Salvador | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2010 | 2017 | 2019 | PPAR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/506141559229971762/text/El-Salvador-Income-Support-and-Employability-Project.txt | http://documents.worldbank.org/curated/en/506141559229971762/pdf/El-Salvador-Income-Support-and-Employability-Project.pdf | 6. Lessons 6.1 A crisis period can create opportunities for broader reform of an existing social protection system through projects that adequately balance short and long-term objectives.. The onset of the global economic crisis in El Salvador revealed the social protection system's limitations. The government's desire to protect affected groups quickly, coupled with its limited fiscal space, showed the need for coherent and sustainable social programs that are cost-effective and reach the neediest. Project design supported the PATI while incorporating longer-term support to build a universal social protection system. Additionally, the reforms of the social protection system initiated with the project provided the government with the institutional framework and tools that, if sustained, would enable a more rapid response in the face of future shocks. 6.2 Ensuring high participation and higher incomes for vulnerable groups requires interventions that are specifically tailored to address the needs of these groups. The project included women and youth as part of its categorical targeting, but both faced barriers to participation in the program. For example, youth faced barriers to participation and completion, specifically the risk of violence and coercion because they had to move across different gang territories to attend training sessions and community activities. Women's participation could have been higher if the program had arranged for childcare. Additionally, evidence indicates that women and youth also faced several barriers to paid employment such as traditional gender roles and employers refusing to hire youth from high-crime areas. These findings call for rejecting one-size-fits-all approaches in favor of interventions specifically tailored to the needs of each vulnerable group. 6.3 In an emergency context, a project can be implemented rapidly and effectively using the country's existing capacity when the project relies on an implementing agency with a proven track record and is accompanied by close World Bank supervision. The project relied on FISDL for implementing the PATI program because the agency had experience working in similar settings, including engaging with municipalities and providing monetary transfers based on targeting mechanisms. Proactive and flexible World Bank supervision complemented this preexisting capacity. Consequently, the government started piloting PATI before effectiveness, and once the project started disbursing, it reached 56 percent of beneficiaries within the first two years, despite being a new and complex program targeting urban high-crime areas. 6.4 The support of knowledgeable local actors is critical for the successful implementation of an intervention in areas affected by high levels of crime and violence. The territorial division of gangs in El Salvador limited the mobility of PATI beneficiaries and program staff by creating borders that, though invisible, could not be crossed without facing coercion and violence. These invisible borders are mostly well-known to locals but unknown to outsiders. Municipalities brought deep contextual knowledge of crime and violence dynamics that were highly instrumental to maneuvering in a dangerous environment.
P117443 | GZ-Water Sector Capacity Building | Middle East and North Africa | West Bank and Gaza |  | FCS | Sustainable Development | Water | SPF | IPF | 2011 | 2018 | 2019 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/523481537536578696/text/West-Bank-and-Gaza-GZ-Water-Sector-Capacity-Building.txt | http://documents.worldbank.org/curated/en/523481537536578696/pdf/West-Bank-and-Gaza-GZ-Water-Sector-Capacity-Building.pdf | The ICR formulated valuable lessons, the most relevant ones are asfollows: Breaking reform TA into more phases or with clearer milestones ensures that TA can iteratively adapt to the reformenvironment as it evolves and avoid funding unnecessary outputs. Similarly, outsourcing reform TA as large firm contracts should beavoided, particularly, where the anchor reform document (law or policy) has not been endorsed by the cabinet (orequivalent). Partitioning TA to the reform between World Bank and recipient execution ensures improvedefficiency. This partitioning should depend on the (a) level of expertise, (b) flexibility, and (c) country ownership required fordifferent tangible and intangible parts of the reform. The institutionalization of functions (for example, utility performancemonitoring) needs to be supported with revenue assignments to finance those functions. The reform instruments and the performancemonitoring of service provision should be integrated to ensure that there is a feedback loop to drive the evolution of reforminstruments and that reform instruments support performanceimprovements.IEGs assessment drew the followinglesson: Adequate sector assessment needs to be completed during theproject appraisal stage so that more effective and efficientproject design can be developed. During appraisal there were two critical reviews that had not been concluded (Institutional WaterSector Review and the Legislative Review), which left reform objectives unclear, and resulted in a weak results framework. At thesame time the recipient had to draft the terms of references (TORs) for the external TA contract, which led to an unclearly definedexternal TA contract that created inefficiencies later on during implementation.
P117444 | GZ-Palestinian P. NGO IV | Middle East and North Africa | West Bank and Gaza |  | FCS | Infrastructure | Urban, Resilience and Land | SPF | IPF | 2011 | 2017 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/106431520773396039/text/West-Bank-and-Gaza-GZ-Palestinian-PNGOIV.txt | http://documents.worldbank.org/curated/en/106431520773396039/pdf/West-Bank-and-Gaza-GZ-Palestinian-PNGOIV.pdf | The lessons presented in the ICR are not all formulated in a way that can easily translate into general lessons in the ICRR. Thelast lesson presented in the ICR is a notable lesson, though; Flexible designs may permit initiatives tomature in fragile, conflict and violent contexts. The World Banks engagement in the NGO-sector in the West Bank andGaza over the past two decades has resulted in a viable governance system for NGOs and a transparent grant-making mechanism.Continuous and flexible support has allowed for innovations to be piloted and scaled up. IEG has added thefollowing lessons:Identifying relevant indicators at the outcome level enables a project to document achievementsbeyond mere outputs. When a projects results framework lacks indicators at the outcome level, documentation ofachievements towards development results becomes difficult, as shown in the current project.Even in projectsdelivered in FCV environments, there needs to be careful thought and effortin understanding what success looks likeand what evidenceis required tosufficiently tell this story.
P117449 | Hebron Regional Wastewater Management Project - Phase 1 | Middle East and North Africa | West Bank and Gaza |  | FCS | Sustainable Development | Water | SPF | IPF | 2015 | 2024 | 2025 | ICRR | Less than 10 million | Highly Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | https://documents.worldbank.org/curated/en/099110824124535953/text/P117449-3b1969ef-0c09-4346-8b61-dca030c20bfb.txt | https://documents.worldbank.org/curated/en/099110824124535953/pdf/P117449-3b1969ef-0c09-4346-8b61-dca030c20bfb.pdf | 1. Identifying stakeholders needs, interests, and values is critical to projectsustainability and implementation. This project demonstrated that limiting engagement largely to stakeholders at thecentral level and designing the project around their interests creates significant pitfalls that can halt project implementationand result in undesirable outcomes. Task teams need to understand the views of stakeholders who are most impacted by the project(i.e. those potentially benefiting and those who would be responsible for administering assets after project closure) in order todesign the project so that it is fit for purpose.2. The West Bank and Gaza have a uniqueadministrative and geopolitical relationship with Israel that extends to water resources and transboundary water issues influencingthe PWAs water resource strategy including wastewater treatment. Israel charges the PA for the volumes and qualityof wastewater received from the West Bank and Gaza. Assessing viable institutional and financial arrangements along withtechnologies that match local capabilities will be important to understand if those arrangements and technologies can meet Israelistandards allowing the PA to reduce or eliminate the chargebacks. Operating and maintaining wastewater infrastructure that does notmeet Israeli standards could create a double burden on the PA if it is financing capital investments and operating and maintenancecosts of municipal providers wastewater treatment, and also being charged by the Israeli government for not meeting itsstandards.3. Project design for wastewater projects should account for the provision ofwater supply services when the quality of water supply is poor. This project was silent on improving the quality of watersupply despite the problems of intermittency. In contexts where the quality of water supply provision is poor, households are alsoless inclined to pay for water supply services. Moreover, global sector knowledge shows that households have a higher willingnessto pay for water services than wastewater services, and water supply revenues often help offset the true costs of wastewaterprovision. In a context where billing and collection rates are low for water supply and the quality of water supply is poor theexpectation that households would begin paying for wastewater let alone water supply is unrealistic. In such contexts, projectdesign should address both issues and tailor the interventions to resource constraints.4.Financing complex projects that have longer durations such as this project should consider the complexity of donorrelations and interests. Donor coordination can be complex and cumbersome because it involves the participation of severallayers of decision-makers in different organizations to secure and release funding. Particularly for projects that have longimplementation periods, donor interests and priorities may change with time and could negatively impact the project outcomes. Thenumber of financing institutions that will contribute to a project should be balanced with the risk of shifting organizationalpriorities over time.
P117495 | Seventh Poverty Reduction Support Grant | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2012 | 2019 | PPAR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/899921541176155707/text/129569-PPAR-P104990-P106083-P113241-P117495-PUBLIC.txt | http://documents.worldbank.org/curated/en/899921541176155707/pdf/129569-PPAR-P104990-P106083-P113241-P117495-PUBLIC.pdf | 6. Lessons 6.1 The following lessons emerge from the design and implementation experience of the PRSF 4â€“7 series\. â€¢ Programmatic DPF can be an effective form of support for a well-defined, country-owned reform program. In Rwanda, the PRSF 4â€“7 series backed a wellarticulated and sound development strategy with strong implementation arrangements, the 2008â€“12 EDPRS. Arguably, however, value-added of the series stemmed more from the predictable financing that it provided for the overall program and its encouragement to reforms through regular, institutionalized monitoring of progress, than from advancing the achievement of specific objectives and outcomes. â€¢ It is difficult to be definitive about the efficacy of a DPF series unless the results framework is tight-knit, the reforms supported have the requisite depth, and there is a strong and direct causal link between these reforms and the outcomes sought. Under the PRSF 4â€“7 series, progress was made in several cases toward the objectives and desired outcomes. However, the role of the policy actions that the series supported in bringing about that progress versus other contributory factors was not always clear. â€¢ A commitment to providing regular, predictable financing in the form of (multisector) general budget support operations implies that the World Bank needs to be prepared to accommodate dilution or deferral of reform content relative to what is foreseen at the outset. This underscores the importance of entering into such a commitment only in instances in which the World Bank has confidence in the government's long-term intent to see reforms through in good faith despite delays and temporary reversals rooted in technical or political economy factors. In Rwanda, there were several delays and setbacks; for example, the implementation of a revised tariff structure for electricity was continually deferred and diluted. However, all triggers specified in the operations under the PRSF 4â€“7 series (or their equivalent in terms of the substance of the policy actions) were eventually achieved, though in some cases with several years' delay, suggesting that the World Bank's confidence was well placed. â€¢ The World Bank can face a hard choice between adhering to a CPAF in a multisector budget support series and fulfilling the good-practice prescriptions in its operational policy for DPF. In Rwanda, confining prior actions and outcome indicators in the PRSF 4â€“7 series to those found in the CPAF offered clear advantages, such as institutionalized M&E and lower transactions costs, particularly for country authorities. However, CPAF design shortfalls and selectivity in its coverage spilled over into the series, leading to inconsistencies with good practices prescribed under the World Bank's operational policy for DPF. It was often difficult in the PRSF 4â€“7 series to trace the causal links between prior actions (many of which lacked depth) and outcomes sought. Moreover, certain objectives the series sought originally, such as fiscal decentralization, were pursued later through insufficiently focused measures and outcome indicators that were constrained to align with those in the CPAF. â€¢ Successful deployment of an IFMIS can be facilitated by high-level commitment and performance monitoring, sustained external support, and system ownership. In Rwanda, top-level attention to imihigo (performance contract) monitoring included a focus on successive phases of IFMIS rollout, which also received steady technical and financial support from the World Bank (through parallel DPF and investment project financing, and later Performance for Results financing) and from other partners (notably through a Public Financial Management Basket Fund supported by the European Union and the U.K. Department for International Development). In addition, Rwandan authorities believed that the IFMIS's in-house development gave the system's users a greater stake in its successful deployment. 1The World Bank later prepared an analysis of why the reduction in poverty during this period was limited. See World Bank 2013a. 2The precise estimates of poverty, and especially their comparability over time, have been a source of contention in the past. However, the figures cited here have been widely referenced in World Bank operational documents and are taken to be good enough. 3Rwanda's fiscal year was changed in July 2009 from calendar year to July to June to align with East African Community norms. 4There is, in fact, some ambiguity as to whether Poverty Reduction Support Grant 5 or PRSG-6 was the first operation to be aligned entirely with the Common Performance Assessment Framework. PRSG-5 was sometimes labeled a transition operation from the standpoint of being aligned with the Common Performance Assessment Framework (see, for instance, annex 2 of the program document for Poverty Reduction Support Financing 7 (World Bank 2011), but elsewhere (for example, paragraph 53 of the program document for PRSF-7), it was asserted, The PRSG-5 operation was the first operation that aligned the series with the . 5This Project Performance Assessment Report uses the term policy actions to refer to the entirety of measures recorded in the policy matrix and results framework as implemented before the approval of a given operation. By contrast, the term prior actions refers to the subset of measures (usually depicted in bold type in the policy matrix and results framework) that was formally identified as necessary for the approval of the operation. 6 The limitations of an ex post logical framework where objectives evolved over the four-year lifespan of the series can be illustrated with reference to prior action (i) under the program development objective of enhancing the skills of the population. At first, it is unclear how an assessment of the basic education system contributes to the intermediate objective of revamping the strategic and institutional framework for postâ€“basic education, although it arguably speaks to the ultimate objective of enhancing the skills of the population. The answer is that the initial focus in PRSG-4 had been on reducing the pupil-teacher ratio in the nine-year basic education program, but it shifted (exclusively) to postâ€“basic education from PRSG-5 onward. 7 The concept of (structural) depth was originally developed and used in IMF (2007). 8The SMART criteria require indicators to be specific to the objectives toward which progress was to be measured; measurable; achievable; relevant in the sense of appropriate to measure progress toward the objectives; and time-bound. 9 The East African Community fiscal year runs from July to June, in contrast to Rwanda's prior fiscal year, which followed the calendar year. Predictable provision of financing for well-performing countries was a key premise of the Poverty Reduction Support variant of programmatic development policy financing. 11The 2011 and 2015 figures are from the Rwanda Ministry of Education's 2015 Education Statistical Yearbook, which reports the transition rate to upper secondary â€”that is, from senior 3 to senior 4 (GoR 2016, 40). (http\.//mineduc.gov.rw/fileadmin/user_upload/Amatangazo/2015%20Education%20Staiatical%20 YearbookF.pdf). 12Some related (more disaggregated) indicators were tracked during the implementation period of the FY11 Skills Development Project, but this was after the PRSF series' closure. 13As indicated previously, the Skills Development Project was implemented after the PRSF series' closure. 14In addition, the National Institute of Statistics of Rwanda's 2015 Integrated Business Enterprise Survey indicates that almost 80 percent of respondents viewed the availability of skilled or technical labor as no problem (and another 13 percent viewed it as a minor problem). 15The law governing community-based health insurance is Law No. 62/2007 of December 30, 2007. Submission of the law to Parliament was a PRSG-4 prior action. 16For useful background on the evolution of community-based health insurance in Rwanda, see, for example, Kalisa et al. (2015). 17Details of the performance-based financing system implementation and its results are discussed in Basinga et al. (2010). The paper reports on data produced from a prospective quasiexperimental evaluation design that was nested in the pay-for-performance program rollout and compared facilities in a treatment group with those in a control group that continued to receive input-based financing for a two-year period for prenatal care and child preventive care. The study found that significant increases in the provision of some services, such as in-facility deliveries by pregnant women, were associated with pay-for-performance. The results suggest that financial incentives are significant and have a larger impact for services in which providers have more control, such as prenatal care quality. The study also suggested that for services that depend more on patient behavior, such as the decision to seek prenatal care, the program could consider providing financial incentives directly to the patient rather than the provider. 18See the figures for the percentage of children under age five using insecticide-treated bed nets under World Development Indicators (https\.//data.worldbank.org/data/source/worlddevelopment-indicators). 19In fact, implementation of a revised tariff structure was later envisioned (in PRSF-8, approved in November 2011) as one of the triggers for PRSF-9â€”which, given the demise of general budget support in 2012, never materialized. 20The bulk of the increase in access over the PRSF 4â€“7 series' life span appears to have taken place in 2009. This likely reflected a significant increase in generation capacity in that year. 21The number of households and enterprises with access to electricity increased from 91,332 in 2006 to 159,516 in FY10 (compared with a target of 139,000) and to 308,326 in 2011â€“12 (compared with a target of 270,000). Generation capacity increased from 60 megawatts in 2006 to 84 megawatts in FY10 (compared with a target of 80 megawatts) and to 157 megawatts in FY12 (compared with a target of 130 megawatts). 22A subsistence level of electricity (30 kilowatt-hours per month) would be unaffordable for more than three-quarters of the unelectrified population. In recent years, fiscal transfers to the energy sector have declined from 2.5 percent of gross domestic product in FY14â€“15 to 1.4 percent in FY16â€“17. 24In addition, some of the measures lacked depthâ€”for example, completion of a tariff study and validation by Rwanda Utilities Regulatory Authority and the Ministry of Infrastructure. Others, such as the removal of the import duty and value-added tax on liquefied petroleum gas to promote its use and reduce dependence on charcoal, had no direct relation to the electricity outcomes targeted, although they arguably contributed to improving cost effectiveness (and environment-friendliness) in the broader energy sector. 25These investment project financing operations were the FY05 Urgent Electricity Rehabilitation Project and the FY10 Electricity Access Scale-up and Sectorwide Approach Development Project. 26 Implementation Completion and Results Report, page 66. 27 Implementation Completion and Results Report Review, section 4. 28See NISR (2016). Note that the standard for measuring urban access is 200 meters or less from the source and rural access is 500 meters or less. 29 The target for 2011/12 was later revised downward to 37 percent under PRSF-8. 30 The World Bank was Co-chair of the Rural Sector Working Group at the time. 31The 2011/12 figure is from the Implementation Completion and Results Report Review (efficacy section, objective 3), and was slightly under, but close to, the target for that year (PRSG-6 program document, page 44). 32Lack of prior consultation with development partners and other stakeholders (for example, though the Agriculture and Rural Development Sectoral Working Group) meant that alternative solutions to fraud concerns, such as the use of electronic wallets, could not be debated. 33 See also Implementation Completion and Results Report, page 40. 34 See Implementation Completion and Results Report Review, section 4 (objective 3). 35In particular, there are discrepancies in the land area subject to radical terracing between the National Institute of Statistics of Rwanda's seasonal agricultural surveys and figures reported in Implementation Status and Results Reports for the Transformation of Agriculture Sector Program-for-Results operation. 36 Law no. 40/2008 of August 26, 2008, established the organization of microfinance activities. 37 The 2008 figure is from Kantengwa (2010). The later figures are from AMIR (2015). The 13.9 percent of gross domestic product target for 2012 is from the PRSG-6 program document (table 9, page 41). 39Savings and credit cooperatives now account for an important segment of the microfinance institution sector (AMIR 2015). 40According to the website of the Financial Sector Reform and Strengthening Initiative\. The FIRST initiative is a multidonor grant facility that provides short to medium-term technical assistance to promote sounder, more efficient, and inclusive financial systems. Since its inception in 2002, FIRST has funded over 600 projects in about 120 countries, with commitments over $135 million. For more information, visit the website at https\.//www.firstinitiative.org/. 41Several districtand sector-level officials gave the mission demonstrations of the SmartFMIS' capabilities. 42Despite changes in Public Expenditure and Financial Accountability methodology between the 2007 and 2010 PEFAs and the 2017 PEFA, the constituents of this score are unchanged, so the scores are comparable. 43The latest figure is taken from the Implementation Status and Results Report for the Public Sector Governance Program-for-Results operation. 44The Implementation Completion and Results Report (page 47) provides details concerning the substance of the amendments. For instance, they were designed to bring the provisions of the law in line with (i) the revised mandate of the Rwanda Public Procurement Agency, resulting from the full devolution of the procurement function to the procuring entities; and (ii) the Common Market for Eastern and Southern Africa (free trade area) procurement framework (which Rwanda joined in 2004). 45 Separate independent review panels also operate at the district level. 46The Implementation Completion and Results Report Review for the PRSF 4â€“7 series reported that the share had increased very modestly to 75 percent by 2012, missing the target of 87 percent by the series' end. However, the 2010 Public Expenditure and Financial Accountability appears to contradict this because it affirms that 86.6 percent of all contracts above the threshold were awarded by open competition. This is also more consistent with the 2015 Crown Agents findings (Crown Agents 2015). 47See Crown Agents findings (Crown Agents 2015). Similarly, the Rwanda Public Procurement Agency's Annual Activity Report for 2015â€“16 (dated January 2017) affirms, based on its procurement audits, that more than 88 percent of public procurement by value took the form of open bidding. However, it is notable that the Rwanda Public Procurement Agency's reach does not encompass all aspects of a broader concept of public procurement. For instance, as discussed in the section on electricity, many power purchase agreements that the Rwanda Energy Group entered into with independent power producers were negotiated bilaterally rather than tendered competitively. 48Three aspects were scored under procurement in the 2010 Public Expenditure and Financial Accountabilityâ€”the previous methodology\. evidence on the use of open competition for contract award, extent of justification for use of less competitive procurement methods, and existence and operation of a procurement complaints mechanism. All received an A score, despite the subsequent strengthening of the independent complaints mechanism (assessed according to six distinct criteria under the new methodology followed in the 2017 PEFA). 49For example, citizen report cards for 2014â€“16 show citizens' overall net satisfaction with local government services as increasing from 60 percent in 2014 to 75.9 percent in 2016. Trends for many individual service categories (health, for example) are similar. For more detail, see World Bank 2018b. 50For further details, see the discussion in the Implementation Completion and Results Report for the PRSF 4â€“7 series (World Bank 2012, 49â€“50). 51A 2010 census of public sector workers (including workers at the local government â€”province, district, and sector-level, and in-service delivery units such as educational institutions, hospitals, and health centers) showed that approximately 46 percent of workers had been in their current position less than three years and 62 percent had been in their current position less than five years. However, no subsequent census of public sector workers has been made available that would allow comparisons over time.
P117590 | Science, Technology and Innovation | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2011 | 2016 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/555001496684641923/text/ICRR-Disclosable-P117590-06-05-2017-1496684630907.txt | http://documents.worldbank.org/curated/en/555001496684641923/pdf/ICRR-Disclosable-P117590-06-05-2017-1496684630907.pdf | The ICR (p. 23) notes several lessons learned:(1)Implementing agencies may need guidance at thebeginning of a project toformulateclearroles and clear allocation of resources. In this project, there wereearly instances where COLCIENCIASs role was not clear in relation to other entities.(2) Implementing agencies hopingto createnew programming can achieve maximum impact through specific articulation of financing and technicalassistance. In this project, COLCIENCIASsupportedpilot investments throughevery step of the process,including calls for proposals, design and implementation ofresearch/business plans, allocation ofinnovation subsidiesto support technical assistance of projects, etc.(4) Bringing in a broad range ofstakeholders can achieve awarenessand outreach beyond the traditional range of partners.This lesson stems fromthis projects experience withengagement with non-traditional partnerssuch aslocal actors, vulnerable communities, indigenous cultures, etc., all ofwhom provided bottom-up understanding of the importance, role, and impact of STI.(5) Guidelines for institutionalstrengthening, including concrete contextual examples and continuous technical assistance, areessential in order to helpan implementing agency with institutionaldevelopment. (6) Unintended impacts of policies can be positive. Inthis case, for example, the Governments introduction ofregional financing for student supportled toincreasedcoordination among regional actors in the STI sector and institutions.
P117596 | China: Guangdong Social Security Integration and Rural Worker Training | East Asia and Pacific | China | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IBRD | IPF | 2013 | 2021 | 2022 | ICRR | >=50 million & <100 million | Highly Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | High | http://documents.worldbank.org/curated/en/194341633449157522/text/China-REG-CN-Social-Security-Migrant-Training.txt | http://documents.worldbank.org/curated/en/194341633449157522/pdf/China-REG-CN-Social-Security-Migrant-Training.pdf | The ICR (pp. 35-37) offered several lessons, including the following lessons restated byIEG:Combining policy reforms with an innovative technical design that addresses the diversity ofsystems facilitates the integration of fragmented social security systems. The project adopted an approach labelled as1+x to maximize convergence without building the system from scratch. Under 1, the project supportedsystem infrastructure for all prefectures and social insurance and labor market applications for lagging prefectures that didnot have well-developed existing systems. Under x, prefectures with more developed systems kept their existingsystems, but had to develop data exchange interfaces with the province and reconcile data with the provincial MIS under a unifiedpolicy framework with common parameters.The diversity of technical training schools and theirdifferent experiences can provide particular lessons and implementation know-how for scaling up technical skills development andcollaboration with industry. The project selected different schools for participating in its development efforts, andthese schools represented a cross-section of different levels of training, including technical specialties, short-term or degreetraining, in-service/on the job training, and urban/rural settings. This allowed the schools to gain experience underdifferentiated contexts, promote apprenticeship incorporating skills across different job tasks, and collaborate with industry toenhance relevance of training, and to contribute to bridging the gaps between supply and demand. The dissemination of suchexperiences was helpful to other technical schools in China.Learning by doing can facilitate andguide the implementation of complex social security integration programs. Under the project, examples included modifyingthe implementation approach from consecutive one-by-one prefectures to a few prefectures in a batch to shorten the time for rollingout the integrated management information system. Higher productivity in data cleaning and migration into the centralizedprovincial information system was reached by widening team involvement and collaboration among provincial, local, and vendorteams.
P117610 | Third Program 135 Phase 2 Development Policy Support Operation | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | DPF | 2011 | 2012 | 2015 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/641111474942570772/text/000180307-20141203060928.txt | http://documents.worldbank.org/curated/en/641111474942570772/pdf/000180307-20141203060928.pdf | A number of useful lessons are highlighted in the ICR. This review also finds that the transfer of resources in challenging areas where poverty proved to be persistent may not be sufficient for poverty reduction if it is not underpinned by long-term and sustained focus on capacity development at the local level. Related to that, the review finds that the Bank needs to consider changing the modality of engagement (moving to investment lending from policy lending) when it is clear that technical assistance will remain a major shortcoming for the project. The review finds that country-wide targeted poverty reduction programs are difficult to implement without being preceded by a pilot program that could help to carefully diagnose the causal chain of resource transfer, capacity building and poverty reduction, and to use the lessons for more successful scaling-up at the national level. Also, the review finds that the Bankâ€™s support for specific government programs should be based on a careful assessment of the design and implementation risks. And lastly, the review finds that in cases where there is a need for more than one ICR for the same series (such as in the case of this series) the final ICR needs to consider covering the series in its entirety.
P117617 | Malawi: Shire River Basin Management Program (Phase-I) Project | Eastern and Southern Africa | Malawi | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2012 | 2019 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/855661578339132242/text/Malawi-MW-Shire-River-Basin-Management-Program.txt | http://documents.worldbank.org/curated/en/855661578339132242/pdf/Malawi-MW-Shire-River-Basin-Management-Program.pdf | The ICR provided some important lessons; the most relevant ones follow with some modification oflanguage:Reversing watershed degradation via a community-led landscape approach requires significant investment instrengthening institutional andcommunity capacityat all levels. The project experience showed that significantinvestment in capacity building and facilitation at the central, district and local levels is needed. The institutions needplanning and decision-making systems and software as well as staff training. The project also showed that communities need adequatetraining and incentive mechanisms to comprehend and to implement various land and water management techniques andpractices.Choices about project design and scope needto consider the capacity of implementingagencies, and project scope has to either matchthis capacity or advance capacity building forproject management withthe implementing agency. The project experienced several issues and delays in implementation due to shortcomings in theimplementing agencys capacity. The technical team was understaffed and unprepared for the task and hiring of additionalprofessional technical and project management staff was not implemented. Any measures agreed to mitigate capacity constraintscouldbe reflected inappropriate covenants in the financing agreement.Inter-agency collaboration onmulti-sectoral projects requires strong government commitment and deliberate design choices. The project was successful ininter-agency collaboration partly because of clear government commitment expressed in a Letter of Policy to the Bank prior toappraisal, followed by the establishment of a multi-agency, multi-sector technical team drawn from all relevant ministries anddepartments to manage project preparation and implementation. In addition, the project was appraised at a time when Governmentpolicy was not in favor of stand-alone Project Implementation Units (PIUs) for delivery of projects. This policy thereforepresented an opportunity to design implementation arrangements that fostered long-term institutional capacity of key land and waterrelated institutions to perform their core mandate.
P117651 | Second Environmental Sustainability and Energy Sector Development Policy Loan | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2010 | 2011 | 2016 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/466851468185965896/text/ICRR14819-P110643-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/466851468185965896/pdf/ICRR14819-P110643-Box394823B-PUBLIC.pdf | Please see the detailed PPAR evaluation carried out by IEG in parallel for more information.
P117651 | Second Environmental Sustainability and Energy Sector Development Policy Loan | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | DPF | 2010 | 2011 | 2016 | PPAR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/833321468189848942/text/99322-PPAR-P110643-P117651-P121651-SecM2015-0300-Box393222B-OUO-9.txt | http://documents.worldbank.org/curated/en/833321468189848942/pdf/99322-PPAR-P110643-P117651-P121651-SecM2015-0300-Box393222B-OUO-9.pdf | 6. Lessons 6.1 The Bank can maximize its development impact by concentrating its strategic engagement including its lending and advisory support in sectors with track records of success. Even in large middle income countries, the Bank can sometimes maximize its impact by engaging in only a few sectors with heavy concentration of support, rather than trying to cover all sectors but being unable to sustain continuous engagement. Turkey chooses to engage with Bank in only a few sectors, based on track records of success in those sectors. The long term engagement of the Bank in the electricity has helped to build a critical mass of operations that allows for significant locally based expertise (multiple sector experts in the Bank's Turkey country office), relationships of trust with key stakeholders, and use of a range of instruments (including investment lending, analytic work, and policy lending) which have relative advantages in supporting particular sub-objectives. 6.2 A well-designed programmatic DPL can be a key instrument in the Bank's long-term engagement. The DPL instrument can leverage the Bank's strengths on technical advice, convening power, and credibility to help support sector reforms that can have substantial impacts. In this DPL series, the electricity sector reforms had a strong design and so were successful in supporting the government's goals of increasing private sector investment in electricity generation. In contrast, the design of the environmental pillar was less well designed and so the DPL provided little additional impact relative to a without-operation counterfactual. 6.3 Prior actions should focus selectively on those reforms that are critical to achieving project objectives but are difficult to undertake because of political or institutional resistance. These are the cases where the DPL's ability to apply some pressure can have an additional impact. In this operation, prior actions on electricity tariff reform, cost-based electricity pricing, and distribution company privatization important effects. 6.4 Prior actions should also ensure that they are additional to what would occur in the absence of the DPL operation. A DPL is unlikely to lead to implementation of major government policies that would not have otherwise occurred, especially in large middleincome countries; effective policy changes require a high degree of government ownership. But a DPL can help governments to increase the pace of reforms and their technical quality if the existence of a prior action or trigger is a significant motivating factor. In this operation, many of the environmental policy reforms were motivated primarily by engagement with the EU rather than the Bank and by a desire for EU harmonization to support potential accession, and so the existence of Bank DPL triggers had little additional impact. If a DPL is used primarily to establish a policy dialog rather than to achieve substantial development results through the prior actions then it may have little impact. 6.5 DPLs can achieve good outcomes when they serve as the culmination of a process of engagement, as in the electricity sector in Turkey. With sufficient background work, DPLs can have significant heavy policy actions from the first operation. This increases the impact, and reduces the risk of failing to achieve positive results should the planned programmatic series not be completed. DPLs may not work as well if used as the initial point of engagement for a sector, as in the environmental aspects of this operation. Hopes that policy dialog through a DPL will then lead to a pipeline of follow-up projects may not eventuate. 6.6 A comprehensive yet well integrated set of market reforms can provide credible signals and incentives to private investors. A wide set of market reforms can provide credible signal to investors; combined program of price reforms, market development, incentives for RE, privatization encourage large scale investment. The order of reforms can be important in determining successful\. privatization can be more effective if investors are confident that there will be clear market demand. 6.7 Changing laws and regulations may not have much impact on environmental outcomes when environmental management agencies are weak and lack implementation and enforcement capacity. In these cases a DPL may not be the most effective instrument for achieving environmental goals. 6.8 A Bank DPL may have little additional impact if the design does not fully incorporate the existing political and institutional motivations. In this case, the primary motivation of the government for many environmental reforms was on EU harmonization, and the Bank's DPL added relatively little to this effort. The Bank may have had more impact if it had covered environmental issues not already covered by the EU harmonization process.
P117652 | Central African Backbone - APL2 | Western and Central Africa | Western and Central Africa |  |  | Infrastructure | Transport | IDA | IPF | 2011 | 2015 | 2016 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/195351468000907344/text/ICRR14846-P117652-Box394823B-PUBLIC.txt | http://documents.worldbank.org/curated/en/195351468000907344/pdf/ICRR14846-P117652-Box394823B-PUBLIC.pdf | The ICR ( page 22) draws the following lessons from the experience of preparing and implementing this project.(!) The World Bank is well positioned to facilitate the financing and implementation of regional projects. This is particularly so when it receives financing requests from several countries involved in that project and there is no regional instrument supporting individual countries.(2) Developing infrastructure through PPP arrangement is useful for empowering the private sector which has the technical expertise while governments can retain a strong governance role.(3) In ICT projects focused on the development of the infrastructure supply side, it would useful to incorporate demand side components such as connecting the schools to the Internet.
P117652 | Central African Backbone - APL2 | Western and Central Africa | Western and Central Africa |  |  | Infrastructure | Transport | IDA | IPF | 2011 | 2015 | 2018 | PPAR | >=10 million & <25 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/668111530296585544/text/126034-PPAR-P108368-P117652-P165413-P165415-PUBLIC.txt | http://documents.worldbank.org/curated/en/668111530296585544/pdf/126034-PPAR-P108368-P117652-P165413-P165415-PUBLIC.pdf | 4. Lessons 4.1 A thorough political economy assessment and high-level national and regional commitment are key ingredients for complex regional ICT projects. The experience from CAB APL 1A illustrates that ICT reforms are politically difficult to implement due to the resistance and influence of incumbent operators. A thorough analysis of the political economy in all countries appears to be a critical tool to use during project preparation. It is essential that the political economy assessment identify high-level national champions (at senior positions close to the level of the President or Prime Minister) who can overcome political economy challenges. Commitment to the necessary reforms should be confirmed with official agreements. In addition, a communication campaign on planned reforms during project preparation and implementation, to sensitize stakeholders and get their continuous buy-in, is essential. 4.2 The experience from the Central Africa Backbone APL 1 and 2 project shows that public private partnership arrangements are difficult to implement in multiple countries, particularly when countries have asymmetrical needs and incentives with respect to increasing competition for the provision of international and national capacity. In CAB 1B, Cameroon perceived the regional PPP as an option imposed by the World Bank from above, considering it as an infringement on their sovereignty; consequently, they rejected the approach. This was also partially because Cameroon had less incentive to take part in the regional PPP, because it already had access to submarine cables and most of its national backbone was already built. Therefore, Cameroon withdrew its participation in the second phase of the project. Chad followed Cameroon and proceeded to have its national backbone built under a separate contract, creating a separate company in early 2012 to manage its fiber optic network in direct contradiction to the regional PPP envisaged under the project. On the other hand, in CAB APL 2, the existence of an upstream regional multi-country project (the Africa Coast to Europe-ACE) connecting up to 23 countries, facilitated the effective connection and implementation of public private partnership arrangement in Sao Tome and Principe. This was achieved as the implementation happened separately within each country jurisdiction based on regionally agreed parameters. 4.3 Technical assistance for the preparation of legislation and sector strategies is only the first step to creating an enabling environment for the ICT sector. The technical assistance can be effective if projects include sufficient resources to adopt legislations and strategies. In CAB APL 1A, there was a need for additional funds to implement the result of the studies developed by the project technical assistance. In Cameroon, for example, the regulatory agencies had to look for additional resources to implement some of the study recommendations. 4.4 Assessing and funding the capacity needs of Regional Economic Communities is important for project coordination and implementation, so that they can carry out their functions effectively. Regional institutions perform important roles, such as convening countries, securing their political commitment; helping them take collective decisions; playing an advocacy role; and performing M&E functions at the regional level. The project experience showed that CEMAC was effective during project design and negotiations but lacked capacity during implementation, particularly on M&E. The World Bank could have supported its needs through better use of its own influencing and coordinating power. 4.5 In weak capacity environments, it is beneficial that the projects build the needed institutional capacity for the Borrower to further/implement the crucial reforms and to ensure the sustainability of the investments in the country. For example, in APL2, the prepared regulations and ICT strategy were not adopted after the project was closed. In addition, although the project connected schools to the internet through last mile investments with planned O&M activities, lack of institutional capacity for monitoring and follow up made the results unsustainable.
P117656 | China: Kunming Urban Rail Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2011 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/689271552331550977/text/China-CN-Kunming-Urban-Rail.txt | http://documents.worldbank.org/curated/en/689271552331550977/pdf/China-CN-Kunming-Urban-Rail.pdf | For the optimization of urban metro routes a geological survey may be necessary. Majorresettlementscontributed tothe delay in the construction of Line 3. An important lesson learned was that detailedgeological investigationsutilizing modern technologies should be carried outto selectthe bestroute andlocation of stations to minimize the dismantling of existing structures and relocation of households. Urban rail projectsinvariably require land acquisition - even when tunneling works are carried out underground - for the construction of stations,ventilation shafts, and other surface facilities, risks related to resettlement must bethoroughly assessed during projectpreparation and during the early stages of implementation.In the case of Kunming and perhaps forother larger cities in China, itis necessary to establish a municipal agency to oversee all modes of transport and to ensuremultimodal integration. The weak coordination between the company and the municipality limited multimodal integrationunder this project. Establishing an apex coordinating body andempowering the implementing agency to do so, or establishing aseparate counterpart agency during project preparation, would have facilitated transport integration under theproject.World Banks value added initiativesto urban transport in Chinathroughtransport-oriented design(TOD) and integration need to be further pursued. At the time of projectappraisal, the Bankwas engaged in a valuable dialogue with the Government and the second to third tier cities on the need tofocus on multi-modal integration to facilitate transit and support the development of compact city growth. China was settingagood example in cross learning from project to project in similar cities, through a good mix of programmatic approach anddecentralization of implementation responsibilities. Going forward, projects in China should address institutional challengesidentified in this projectthat prevented the full benefits of TOD and Integration frommaterializing.Appropriate PDO indicators are neededto capture the progress of multi-modalintegration, as well as compact and Transit Oriented Development. Since the appraisal of this project, the Bank hasprovided improved guidance to staff in defining PDO indicators and these are nowreflected in the Banks ICRGuidelines.Further guidance is that the delivery of the PDOs outcome should fall under the responsibility of theimplementing agency. More recently, accessibility indicators have been used in urban projects to quantify increased access to jobopportunities. There are also additional economic effects that could also be considered to design a projectfor more equitablemobility. Poor people might benefit relatively more from better public transport options,since they are more likely to belocated further away from the city center. A recent study has helped to quantify the differential impacts in terms of access toeconomic opportunities of transport projects. Such impacts have been shown to be directly correlated with changes in density,rents, economic activities and welfare in cities. The promotion of compact city development could help to mitigate the relocationeffects that tend to affect the poorest people. Similar analyses can be used to quantify welfare increases from a good feedersystem, different subsidy/pricing offers across modes, and for coordinating the construction of urban rail with land value captureopportunities.
P117662 | Global Partnership for Education Grant for Basic Education Project | Western and Central Africa | Liberia | IDA | FCS | Human Development | Education | RETF | IPF | 2011 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/835571514478075891/text/ICRR-Disclosable-P117662-12-28-2017-1514478067060.txt | http://documents.worldbank.org/curated/en/835571514478075891/pdf/ICRR-Disclosable-P117662-12-28-2017-1514478067060.pdf | Lessons drawn from the ICR: Direct distribution of education materials to schoolscan enhance accountabilityandeffectiveness (and perhaps efficiency) of the delivery chain but can also be hindered by lack of timely access toEMISdata. In the case of this project, decentralized education officers and school principals were mobilizedtoparticipate in textbook distribution; however, there were discrepancies in thenumber of schools and enrollment data which ledto inaccuracies in delivery of materials. School construction outputs are less likely to lead to sustained educationoutcomes (i.e increased enrollment) without a corresponding maintenance plan.In the case of this project, the lack ofbudget allocated to school maintenance and the lack of human resource capacity to maintain schools is contributing to significantrisk in the development outcomes.
P117665 | Fiscal, Social and Financial Sector Development Policy Loan (DPL) | Europe and Central Asia | Croatia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2010 | 2011 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/342221474630837492/text/000020051-20140624191141.txt | http://documents.worldbank.org/curated/en/342221474630837492/pdf/000020051-20140624191141.pdf | The ICR contains valuable lessons, the most important one of which is that selectivity and political realism are key to the successful outcome of a DPL program. In addition, it is clear that this DPL was only the first step in the process of needed fiscal consolidation in Croatia, which is likely to take several years.
P117666 | Third Development Policy Loan | Europe and Central Asia | Poland | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2011 | 2012 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/362241475091443427/text/000020051-20140625055611.txt | http://documents.worldbank.org/curated/en/362241475091443427/pdf/000020051-20140625055611.pdf | The ICR contains good lessons, the following two of which stand out. First, a well-designed program requires a solid analytical foundation to help identify issues and areas where reform is likely to succeed. Second, a program focused on a few core areas in urgent need of reform is more likely to be internalized and owned by the government.
P117667 | Second Development Policy Loan | Europe and Central Asia | Romania | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2011 | 2011 | 2013 | ICRR | >=100 million | Satisfactory | Satisfactory | Highly Satisfactory | Highly Satisfactory | Substantial | http://documents.worldbank.org/curated/en/150451474555312380/text/000020051-20140625223916.txt | http://documents.worldbank.org/curated/en/150451474555312380/pdf/000020051-20140625223916.pdf | There are three main lessons that can be drawn from the experience of this DPL series:The Bankâ€™s ability to coordinate the design and supervision of its interventions with other key financiers, and to keep a constant dialogue with legislators and other stakeholders is essential to maximize impact and ensure sustainability of reforms, particularly if the latter are long overdue. Dialogue with the opposition is particularly crucial in this respect.The Bankâ€™s ability to assess progress in an independent fashion and demand compliance with agreed policy changes is the foundation of its credibility, particularly in front of the Borrowerâ€™s public opinion. This ability requires a solid analytical capacity, excellent knowledge of the local political economy, ability to withstand pressure to disburse, and willingness to discuss issues with and outside government.Political commitment to reform is crucial and needs to be broad based. The overall reform agenda under extremely difficult circumstances needs to have some degree of support from the opposition, as governments are often short lived during such periods. The Bank can help through dialogue, but without some common ground between government and opposition the risk of policy reversals may be too high.
P117698 | Georgia: Second Development Policy Operation | Europe and Central Asia | Georgia | IBRD | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2011 | 2011 | 2018 | PPAR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/352991530210847614/text/Georgia-first-second-and-third-development-policy-operations.txt | http://documents.worldbank.org/curated/en/352991530210847614/pdf/125186-PPAR-P112700-P117698-P122202-PUBLIC.pdf | 6. Lessons 6.1 The design of DPO programs during times of crisis usually involves a dilemma between providing predictable budget support to the client country, to help preserve stability, and deepening or expanding the reform agenda. Meeting the need of budget support entails a risk of undermining the quality of the reform program supported by the World Bank or the ability of the program to go beyond reforms that would in any case have been implemented by the authorities or supported by other development partners. In Georgia, the World Bank made the choice of providing predictable budget support mostly by extending and deepening the reforms supported by the precrisis operations (PRSOs), limiting the inclusion of new reform areas in the program. With a few exceptions, the content of the DPO series was broadly adequate to achieve the program objectives. The comprehensiveness of the World Bank's previous engagement on the reform agenda through the PRSO series, the World Bank's extensive analytical work, the government's commitment to the reform agenda and crisis mitigation program, and technical assistance (by the World Bank and other donors) to build capacity in key areas of the reform program were all factors that contributed to the positive outcome. 6.2 In the absence of unemployment insurance or other active labor market programs, scaling up Georgia's TSA program was the only option available to mitigate the shortterm impact of the crisis. As the TSA program was well designed and targeted, the World Bank's support was fully justified and helped extend protection to the vulnerable during the crisis. However, cash transfer programs, such as the TSA, are mainly geared toward the chronically poor, whereas many of those affected by crises are households falling into temporary poverty. Also, these cash transfer programs often lack the institutional flexibility in targeting and management information systems to quickly absorb households that may have poverty characteristics different from the chronically poor, which the programs conventionally target. Moreover, they do not include help for workers to return to productive employment. To improve country preparedness to mitigate the social impact of crises, program complementarity, adaptability, and servicelevel efficiency play an important role. The World Bank could advocate complementary social protection schemes\. formal sector contributory schemes; safety nets, including cash transfers relatively well targeted to the poor; and complementary categorical benefits. Developing relevant knowledge and data on groups that are most affected by crises is of key importance. The introduction of unemployment insurance would have merited support by the 2009â€“11 DPO program, especially to help address the possible employment impact of deeper trade integration entailed by the DCFTA with the European Union. 6.3 In a fiscally constrained environment, a move to UHC may not necessarily bring an improvement in the financial protection of the poor. In Georgia, some improvements in health coverage of the poor achieved under the MIP reforms supported by the DPO series were sustained under the UHC program, and access to inpatient services was further enhanced. However, despite a slight decline in out-of-pocket health spending, there was no decline in the share of households that experience impoverishing effects of out-of-pocket expenditures. Moreover, the structure of the current UHC system and incentives embedded in it are a major driver of costs and fiscal overruns that limit the authorities' fiscal space to improve the coverage of the most vulnerable. As shown by Georgia's move to UHC, it is strongly advisable that such transitions be well prepared, with good checks and balances and quality assurance mechanisms in place that help contain the potentially high cost of UHC systems. The World Bank could play a more proactive role in advising governments on the best way to prepare such transitions. 6.4 The World Bank can play a supportive role in helping to focus government's efforts even in policy areas where other development partners mainly drive country reforms. This was the case in Georgia with the trade-related reforms required for the DCFTA with the European Union. These would have been very likely implemented even in their absence as prior actions in the DPO series, as Georgia was keen to fulfill the requirements for starting the DCFTA negotiations with the European Union. However, including these reforms in the DPO series helped focus the government's efforts on reforms important for strengthening export potential over the medium term while, given capacity limitations, this focused effort helped avoid spreading resources thin. The World Bank could have added more value by advising the government on how to prioritize regulatory convergence with the European Union directives, based on the World Bank's prior experience with Eastern European countries during their accession negotiations with the European Union.
P117723 | VN-Public Investment Reform 1 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2010 | 2011 | 2013 | ICRR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/472941474628773814/text/000020051-20140625225553.txt | http://documents.worldbank.org/curated/en/472941474628773814/pdf/000020051-20140625225553.pdf | IEG identified the following lessons from the ICR itself and from the review of the project overall:A crisis response program should have an explicit macro-economic focus, clearly reflected in both Program Development Objective and in the Policy Framework. This is even more critical when the Borrower does not wish to have a program with IMF. Coordination and dialogue between the Fund and the Bank are critical.The need for explicit actions on macro-fiscal management in DPL series depends in part on the quality and credibility of the Bank-country dialogue. In some cases, specific actions can serve as important commitment mechanisms for Governments. At the same time, a robust dialogue can also lead to early action by Borrowers (for example, on macroeconomic issues prior to PIR2).The combination of a relatively short-term contingency lending program with long-standing institutional reforms may be incongruent, unless the program motivates high impact stroke of the pen reforms. In such circumstances, it may be better to front-loading these reforms at the launch of a DPL series, and support institutional reforms through an intensive program of technical assistance and capacity building.Complex institutional reforms should be supported only after a rigorous analysis of political incentives, stakeholder interests, and potential sources of opposition.
P117723 | VN-Public Investment Reform 1 | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | DPF | 2010 | 2011 | 2015 | PPAR | >=100 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/721331467986245693/text/96203-PPAR-REVISED-PUBLIC-VIETNAM-PPAR-FINAL.txt | http://documents.worldbank.org/curated/en/721331467986245693/pdf/96203-PPAR-REVISED-PUBLIC-VIETNAM-PPAR-FINAL.pdf | 6. Conclusions and Lessons Learnt Conclusions 6.1 This review presented an overview of Vietnam's economic and social performance. It assessed the extent to which World Bank DPOs during 2007-12 contributed to its achievements and their sustainability. The main conclusion that emerges from the historical overview is that the country's growth performance during the 1990s and until the mid-2000s was very strong. Effective poverty alleviation also took place during that period, and has been sustained since. This was thanks to transformative measures (especially land reform, enterprise reform and WTO accession) that were taken by Government during the first half of the 2000s (in turn building on earlier reforms) with substantial development partner advice and support, which was generally led by the Bank. 6.2 However, during the period under review (2006-2013) the next generation of transformative reforms (notably as highlighted in the 2007 and 2009 VDRs) were either postponed or diluted, and were thus less effective. Areas such as SOE and financial sector reform, more efficient public investments, anti-corruption, and more effective environmental policies, received insufficient attention. Over the same period, Vietnam departed from the prudent macro-fiscal stance that characterized it in the 1990s early 2000s. 6.3 Past reforms continue to drive strong FDI and buoyant exports. Vietnam can build on these strengths to avoid further loss of growth momentum. This could be based on the implementation select transformative reforms aimed at strengthening the role of the private sector, facilitating the emergence of mediumto large domestic enterprises, and sustainably expanding infrastructure in an efficient manner. The progressive elimination of the stock of contingent liabilities and reducing other risks to the sustainability of fiscal policy would create a more stable macroeconomic environment. One of Vietnam's strengths lies in its social compact, the main elements of which should be maintained, while progressively evolving towards a less paternalistic approach based on stakeholder empowerment. 6.4 The Bank and other development partners can help the country address these priorities through more selective budget support instruments. This is indeed envisaged in the Country Partnership Strategy (2012-16). The 2016-2020 SEDP also provides an opportunity to generate political consensus around these issues in the context of an increasingly complex economy. 6.5 The Bank should be more willing to cease supporting programs should they become so weakened as to make it likely that key objectives would not be achieved. Technical and policy dialogue would be maintained. In this context, high caliber knowledge products will need to continue being prepared, and the relationship of trust that supports frank dialogue with Government needs to be reinforced. Harmonization with all key stakeholders, external and internal, will be important. Strong commitment to deeper reforms would help to sustain Vietnam's economic performance while addressing the challenges of an increasingly complex, middle-income economy, and deepening global integration. Lessons from the Bank's macroeconomic engagement through DPOs. 6.6 The model of the Bank's engagement in macroeconomic and fiscal policies through DPOs in Vietnam since 2007 has not been effective. An important finding emerging from this PPAR is that, while diagnosis of macroeconomic risks was adequate, this was not reflected in program design, despite a highly volatile environment exacerbated by sub-optimal policy choices. This situation was, moreover, aggravated by the lack of an IMF program and the relative weakness of macroeconomic policy dialogue between the Government and the Bretton Woods Institutions. The Bank may have been exposed to reputational risks if its policy lending had been seen as a de-facto endorsement of controversial macro policies. DPOs following those reviewed in this PPAR are still not underpinned by relevant macro policy content, although macroeconomic risks persist. This indicates that the lessons learned during the 2007-2013 period do not appear to have been fully learned. 6.7 Macroeconomic dialogue could advantageously be consolidated in a presence of multiple parallel DPOs. The fragmentation of policy lending into multiple DPOs implemented in parallel in Vietnam during the period of increased macro risks might have weakened Bank's focus on macro framework and even resulted in inconsistencies in policy dialogue. The Bank should have avoided situations when preparation of one operation is held back for concerns over the macro-framework while a parallel DPO is approved and disbursed in the same macro environment. To avoid the repetition of such a situation, there should be a unique and consistent approach towards assessing the adequacy of macroeconomic underpinning of DPOs. When substantial risks are present, policies underpinning the most suitable, in terms of scope and objectives, budget support operation should be reoriented to alleviate them. 6.8 Combining the objectives of external financing for crisis response and promotion of long-standing institutional reforms may not be effective in cases where risks to nonimplementation of reforms are high. The Bank's experience with the Vietnam PIR series indicates that, when financing needs are urgent, it will find itself under pressure to go ahead with disbursements even if the reform implementation is not satisfactory. Crisis response operations should first of all focus on ensuring the sustainability of macro and fiscal framework, and should be underpinned by critical macro, fiscal and structural actions, especially in cases when the IMF is not present operationally. Lessons Learnt â€“ Results and M&E Framework 6.9 Wide-ranging DPOs need to be based on stronger and better quality actions. The importance of each individual prior action increases in multi-sectoral operations with many policy areas because of the implicit limit on the number of total prior actions for operational purposes. If in a series of five operations, for example, each policy area can have a maximum of two or three prior actions in the course of five to six years it is important to ensure that those prior actions have sufficient institutional depth, relevance and criticality. Related to this, in multi-sectoral complex operations there might be no substitutability between the prior actions of unrelated policy areas, which means that weaknesses of prior actions in one sector cannot be offset by relevant and critical prior actions in another sector. 6.10 Lack of focus on and delays in implement essential triggers can weaken the program. In terms of indicative triggers, the Bank has flexibility and discretion in its treatment of the triggers. The transition from Bank's former conditionality framework to the model applied in the series reviewed in this PPAR puts a high premium on sequencing the reforms and ensuring continuity, thus giving considerable significance to the role of triggers for the operations and the overall reform program. Dropping a trigger should be considered as an exceptional event, rather than a regular occurrence, permissible only if the risks to nonimplementation of reforms are duly addressed. 6.11 Partially met triggers require greater attention. Sometimes partially met triggers become prior actions even though they may be less relevant and critical than the originally proposed action. The dilution of content may be to such an extent that these actions would probably not have been considered as prior actions if proposed at the outset. The Bank should pay special attention to possible risks in adopting partially met triggers as prior actions, especially when there is not any realistic expectation that the full original reform will not implemented in a reasonable timetable thereafter. 6.12 It is crucial to have a strong knowledge base for upstream design of reforms and parallel technical assistance to support their implementation. Development partners were willing to put significant resources in these areas, in order to complement Bank financing and dialogue (Vietnam, prefers not to borrow, even on concessional terms, for TA). Selectivity is therefore needed to ensure that the most pressing needs are addressed. Should unmet demand remain, this may be tackled through complementary Bank TA operations, for instance in support of reform teams.151 However, these operations need to be carefully designed in order to match the timing and sequencing needs of DPOs (an issue that arose in the case of P135), and to ensure that the bulk of resources is allocated to meet specific implementation requirements, as opposed to general capacity building (such as purchase of vehicles and equipment, and training). Furthermore, this approach calls for outsourcing knowledge generation and advice to an appropriate mix of experts, both national and international, who can accompany the reforms in medium-term.152 6.13 The design and implementation of M&E for DPOs remains a challenge, and needs to be reconsidered each time a new operation is considered within a series. The PD.153 for the second PIR mentions a lesson learnt elsewhere, whereby an effective M&E mechanism should not just be based on administrative reporting. However, both the PIR and the PRSC suffer from this issue as M&E is not used as a mechanism for feedback and readjustment of activities to improve impact. The P135 is more successful in this area 151 FIAS 2008\. Reform Teams How the Most Successful Reformers Organized Themselves Reform teams consist of a small group of national experts who together with world-class expertise help Governments implement ambitious reforms. 152 In order to achieve such continuity, the experts' contracts may be based on a retainer model. Sorter procurement may also be achieved through framework contracts, whereby a short-list of competitively prequalified consortia/firms expected activities are called upon to provide experts within short delays of 2-4 weeks. The EU has successfully implemented this approach. 153 para. 71 124 because the mid-term review provided a venue for reassessing the implementation of the program. Even there, the change in PRSC indicators took place only for the last operation, although it had become clear much earlier that the relaxation of policy actions required an adjustment in indicators and goals. In both the PRSC and the PIR series there is a disconnect between development objectives, actions and indicators. In the case of the PRSC, there was a logical chain between objectives and indicators, but it is hard to see how some of the reforms would lead to the intended results (the attribution issue). The issue with the PIR is that while there is strong relationship between the reforms and results, their logical link to the development objectives is weak, especially after key reforms were dropped. Lessons Learnt â€“ Bank Approach 6.14 There is a need to reexamine how the Bank approaches sectoral DPOs and how this instrument is differentiated from investment lending. In Vietnam, the distinction between DPOs and investment loans has become blurred, especially with the practice of earmarking funding for the sector the programs support. It can be argued that the four sectoral DPOs might have been best supported by SWAPs and investment lending. The advantage of DPOs is that they disburse rapidly, support to the consolidate budget, and in practice promotes the use of national fiduciary and safeguards systems. However, this approach limits Bank inputs (say on a key study) on the ultimate use of the resources and their underlying processes. To avoid sharp trade-offs that may discourage the use of the most appropriate lending instrument, it seems that in the case of investment lending, it may be desirable to experiment, at least on pilot basis, with further harmonization/convergence between Bank fiduciary and safeguard procedures and national ones. 6.15 The Bank and other development partners should be willing to walk away from an unproductive policy dialogue and withdraw their support of low impact reforms. The delays in P135 (second operation), the second PIR operation and PRSC 10 appear to have been caused by concerns with the quality of the program. In the case of P135, the mid-term review largely addressed the main concerns. However, the last operations in both PIR and PRSC series cannot be readily justified by the contribution to objectives of the weak reform they supported. 6.16 The Bank's recent guideline that suggest to limit the number of operations in a series to three constitutes an appropriate measure. Long-term DPO series need to be kept relevant by maintaining a high level of ambition with respect to the reforms they support. As evidenced by the second PRSC series, a longer-term approach may be hard to sustain. 6.17 Knowledge generated and/or embodied in Bank operations should be properly documented and made public. Bank disclosure policy call for documents it produces being made public, unless classified as confidential. Furthermore, to the extent possible, documents on which policies are based should be easily identifiable and retrieved. In order to preserve knowledge and improve transparency, PDs should properly refer to studies (in some cases the title cited was incorrect) and provide URL links. There is also a question whether disclosure policy is strictly respected (e.g., some energy studies do not appear to have been made public). 125 6.18 It is difficult to evaluate the performance of DPOs in Vietnam without the benefit of a clear reference on what constitutes the norm. This review identifies strengths and weaknesses in the Vietnam DPOs by referencing their own internal logic. However, it is unable to systematically address questions such as how did the Vietnam second PRSC series compared to other PRSCs in terms of ambition, design, results etc. This may result in inconsistency in ratings across countries and projects (ratings contain a subjective element based on the skills, experience and perception of the evaluation team, as well other factors). This issue seems to argue in favor of a new meta-evaluation154 of completed PPARs on similar DPOs, with lessons learnt and recommendations on a more consistent cross-country approach to be reflected in future individual operation evaluations and/or PPARs. Specific Lessons Learnt from P135 6.19 Budget support may not be the best instrument for financing a sector investment program. While a budgetary support operation for a CDD-type program turned out to be moderately satisfactory in the case of Vietnam, the Bank and other development partners had taken a considerable risk. For most countries, it would be highly advisable that the training, at least of the critical personnel (which in a highly decentralized program means a very large number of people), would be done in advance and that an M&E system were in place at the start of the program. There was much retro-fitting under the P135 series that could have been avoided. 6.20 The state of decentralization needs to be fully factored into the design and implementation of targeted poverty programs. Decentralization of government institutions and introducing greater participation at the commune and village levels was an objective of the program as a tool to empower the targeted communities. Various monitoring indicators were used to measure progress on this front. But they did not provide an idea of what would have been good practice in terms of an optimal level of decentralization and participation given the stage of development. An alternative approach could have been to select a control group of provinces that had been decentralizing on their own and could serve as a comparison group for the provinces attempting to develop decentralized structures under P135. That could have enabled the selection of a group of indicators to be used for measuring success before the start of the operation 6.21 Production support to poor communities needs to be tailor-made and well thought through. Much was made of expanding the production component of the program. But the targeted communities were seriously underdeveloped for good reasons. They were remote, mostly mountainous, often forested, and inhabited by people who have eked out livings in these places for centuries. Such places are notoriously difficult to develop and there are few success stories around the world to give guidance. Packages that had worked in other parts of Vietnam (typically used in the more hospitable lowlands) were not likely to be relevant, and subsidies are not sustainable in the long run. This portion of the program could have been better thought through and explored through a series of pilot projects rather than being a part of a budget support operation. See IEG 2010 for an evaluation of PRSCs based on operations completed and evaluated by 2008. 6.22 Good analytical work, economic and other, contributes to success. Populous countries with large externally financed programs, such as Vietnam, are likely to benefit from an amount and variety of analytical work, typically using standard economic tools. Smaller countries with more modest analytical programs can probably learn useful things from a selective reading of the analytical work performed in more abundantly staffed countries. But Vietnam also profits from relevant non-economic analytical work that illuminates the likely behavior of the people involved both at the highest levels as well as at the village level in a way that informs the design of the programs. This sort of work is important but by its nature country specific.155 6.23 Well-designed impact evaluations are a valuable dimension of M&E. The impact evaluation turned out to be very important in assessing the impact of P135, not only regarding poverty but also non-income components of welfare, participation, decentralization and empowerment. This has direct relevance to other National Targeted Programs in Vietnam and elsewhere. It is important that funding of such activities be included in the original project design as their late inclusion may lead to implementation difficulties. 6.24 Vietnam's social compact was instrumental in supporting certain achievements, but may not be readily replicable elsewhere. Vietnam's reforms have relied on a top-down approach, which nevertheless draws in various stakeholders into the program and strengthens their ownership and voice. This is notably the case for targeted programs such as P135. While the country's history and social compact are quite specific, there are generic elements, such as effective engagement of local political authorities and communities that may be useful elsewhere. An example was Martin Rama's Making Difficult Choices\. Vietnam in Transition (2008). For behavioral implications at the village level the best example would be Edwin Shanks et al CDD in Vietnam (2003).
P117731 | Ethiopia-Transport Sector Project in Support of RSDP4 | Eastern and Southern Africa | Ethiopia | IDA | Non-FCS | Infrastructure | Transport | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/251441580240225684/text/Ethiopia-Ethiopia-Transport-Sector-Project.txt | http://documents.worldbank.org/curated/en/251441580240225684/pdf/Ethiopia-Ethiopia-Transport-Sector-Project.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.(1)Thecivil works contracts, pertaining to social safeguards(such as landacquisition,resettlements and compensation), and utility relocation timeframe and arrangements need to be thoroughly assessedat preparation, to avoid suspension of works during implementation. At the time of appraisal, the three contracts wereready for implementation. However, there were delays in executing all contracts for different reasons such as environmental issuesat the quarry site and delays due to right of way issues.These factors eventually led to the termination of contracts andcancellation of the part of the credit.(2)Opportunities for partial cancellation/extension need to becarefully considered, in case of multi-packaged independent road sub-projects. This project entailedrehabilitation of fiveindependent road segments. When some of the sub-projects caused delays or serious problems to the wholeproject, the possibility of a partial cancellation needs to be considered before closing the entire project. This project wasclosed six months earlier than the original closing date due to the substantial delays and terminations of contracts for two roadsegments. Partial cancellation for these sections, would have enabled financing for the rest of the project roads toward theoriginal closing date.(3)The PDO indicators need to be designed to reflect only the achievements undercontrol of the project. One of the key indicators in this project travel and turnaround time of heavy goods onAddis-Mille Djibouti trade route was clearly outside the project scope (in the territory of Djibouti). The results indicatorshould be designed to reflect the intervention under the projects control.(4)The institutionalstrengthening aspect of the project should be captured in the PDO. In this project, there were no key indicators formonitoring the project activities associated with strengthening the ERAs institutional capacity.
P117745 | EGYPT-Farm-level Irrigation Modernization | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2011 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/199211542818783939/text/Egypt-Arab-Republic-of-EG-Farm-level-Irrigation-Modernization.txt | http://documents.worldbank.org/curated/en/199211542818783939/pdf/Egypt-Arab-Republic-of-EG-Farm-level-Irrigation-Modernization.pdf | The ICR (pages 25-27) draws ten lessons. The following five lessons were judged by this review to be the mostimportant with respect to application to other Bank operations, with some modification oflanguage.(1) Contracts needprovisions for price contingencies duringimplementation.The depreciation of the Egyptian Pound relative to the US$ during the implementation of this projectcaused a severe increase in the prices of inputs for the modernization works. This stalled work progress until alternativearrangements could be made. Allowance made at design for meeting price contingencies would help in reducing delaysin futureprojects.(2) Technical assistance needs to be addressed at design.TheProjectManagement Unit(PMU) lacked the required technical capacity for engineering supervision and thiscontributed to delaysin the initial years of the project.The requiredtechnical assistance to the PMU was addedafter three and halfyears after project effectiveness. The experience of this project demonstrated that technical assistance activities should beincluded in future projects from the project start.(3) Work contracts of significant size andexecuted by competent commercial contractors may be required in countries with weak implementation capacity. The initialapproach in this project envisaged the force account approach administered by community-ledand small contractors.This approach proved to be ineffective for meeting the demands of large scale works, given the lack of capacity of the Ministry ofAgriculture and Land Reclamation and the PMU. Replacing this approach with clustered contracts administered by commercialcontractors speeded up progress in the final years of the project.(4) Progress sequencing ofphysical works can be useful for for marwa/mesqa improvements. In the case of this project, the electricity infrastructureworks preceded marwa/mesqa improvements. Constructing the electricity transmission lines up to the pump station before commencingworks on the Marwas helped in enhancing the farmers trust in the benefits of the project.(5)The involvement of farmers and Water Users Associations (WUAs) in final design and in supervision leads to ownership. Inthe case of this project, a social assessment survey conducted at appraisal showed overwhelming farmer support for electric pumpsas compared to diesel pumps. Alsofarmersrepresented through their marwa committees, mesqa WUAs and agriculturalcooperatives were involved in key stages of the project design and this helped in their commitment to theproject.IEG draws the following lesson from this project.(1) A realisticassessment of the project timelines is required for a robust theory of change. The original PDO of increasing agriculturalprofitabilitywas unrealistic in terms of the project timeframe. This undermined the theory of change and the relevance of theresults framework. This issue was appropriately addressed at the Level 1 restructuring.
P117764 | Decentralized Community Driven Services Project | Western and Central Africa | Benin | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2012 | 2018 | 2019 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/614411544479163754/text/Benin-BJ-Decentralized-Community-Driven-Servic.txt | http://documents.worldbank.org/curated/en/614411544479163754/pdf/Benin-BJ-Decentralized-Community-Driven-Servic.pdf | The ICR sets out a number of context-specific and more generallessons and recommendations drawn from theprojects implementation experience, of which IEG emphasizes the following:Decentralization andthe CDD approach can complementone other in the development of basic social services.In this case, theprojectsuccessfully promoted decentralization with traditional CDD for infrastructure projects. Theprojectalsopresented a strong rationale for integrating the CDD approach in safety net programs. Furthermore,the CDD approach deliveredmore cost effective, higher quality,low-complexity basic service infrastructure than conventional methods.Participationin the CDD program, GMT, and the formation of community associationsraised the level of social awareness and helped toempower communities. The ICR also found thatinclusion of social services in public works programs increased womensparticipation, particularly through the inclusion of day care. Public works projects served to improve the living conditions of thewhole community, generating solidarity between beneficiaries and non-beneficiaries and reducing possible stigmatization associatedwith the cash transfer.There are possible synergies to be realized in the integration of safety netprograms and traditional CDD infrastructure projects based on shared processes and procedures, such as community training.The inclusion of training for both infrastructure and safety net projects can build multiple capacities, reduce costs, and leveragemultiple development outcomes for communities. The integrated approach can also bring about synergies developed through immersionworkshops and site work through which various players (e.g., contractors, their site managers, and site controllers) are broughttogether to develop shared understanding and purpose.AFADeC-type transfer mechanism cansupport effective projectimplementation. The FASeC system was supported and used by other donors and allowed fortheeffective transferof funds to decentralized levels for CDD and for traceability and auditing of resources. TheICR also noted thatmanaging communal and community projects improved communal project management capacity throughlearning by doing with reference, for example,to capacity development in procurement that permittedimplementation by communes. Flexibility to accommodate community priorities is essential, noting thatinfrastructuresub-projects that communities identify as critical may be very different from those planned by central, prefecture, or communallevels. In this regard, the ICR suggested thatadditional time should be built in for developing differentinfrastructure plans, environmental plans,and social safeguard plans for each type of infrastructure for sub-projectneeds.IEG supports the above lessons and adds thefollowing:Thedecision to drop a planned RCT impact evaluation that was presented in the PAD as a critical, strategic toolto support themainstreaming of the pilot social safety net program was unfortunate, regardless of subsequent government decisions aboutthe future of such programs in Benin.The project sought (Component 2) to pilot and test a social safety net program with aview to scaling up the program at the national level. The program was designed toincrease income andconsumption amongthe very poor and to improve the ability to cope with shocks among targeted vulnerable population groups. The assessment andtesting of the model and approach was to be underpinned by an RCT impact evaluation subject to finding sufficient funding through atrust fund or other source; it was always unlikely the client would use borrowed funds to implement an impact evaluation. Inactuality, afunding source was not forthcoming, and theimpact evaluationwas dropped. An alternative, lesselaborate, and less costly evaluation approach was supported under the supervision budget in a laudable attempt by the World Bank team to fill the gap, but that approach did not provide results that were adequately reliable to support policy decisions asintended.
P117822 | SL-Fourth Governance Reform and Growth Grant (GRGG-4) DPL | Western and Central Africa | Sierra Leone | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2012 | 2017 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/980271481138732958/text/Sierra-Leone-SL-GRGG-4-BUDGET-SUPPORT-DPL.txt | http://documents.worldbank.org/curated/en/980271481138732958/pdf/Sierra-Leone-SL-GRGG-4-BUDGET-SUPPORT-DPL.pdf | This review supports some of the lessons cited in the ICR, especially the importance of having a functional Multi-donor BudgetGroup that will assist in the design, formulation and selection of indicators discussed with government. Other lessons cited in theICR with adaptation in language include the following:(i) The Ministry of Financeplays a critical role in ensuring that agreed reforms are implemented by various government agencies. In this case, the Ministry ofFinance did not effectively use its budgeting and resource allocation powers to compel the Ministry of Education to focus on agreedreforms. As a result, the education sector target was not met.(ii) The use of aprogrammatic series provided an opportunity for mid-term corrective measures to be taken by the team towards theachievement of the targets. The Bank team had an opportunity to re-evaluate their indicators after the first twooperationsand introduced new indicators during the thirdoperation (SL-GRGG 6)to help them achieve thedesired outcomes.(iii) Selecting prior actions from the Progress Assessment Frameworkdesigned and discussed with government and other development partners works well and aids monitoring. In this case, the policyreforms were derived from the governments own reform agenda and harmonized with the reforms supported by developmentpartners. This created ownership from all stakeholders during the implementation and monitoring of the Progress AssessmentFramework.
P117838 | First Education Development Policy Loan | Middle East and North Africa | Morocco | IBRD | Non-FCS | Human Development | Education | IBRD | DPF | 2010 | 2011 | 2014 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/449001475114880143/text/000020051-20140626075500.txt | http://documents.worldbank.org/curated/en/449001475114880143/pdf/000020051-20140626075500.pdf | The following two lessons are taken, with some adaptation of language, from those presented in the ICR. The third is drawn by IEG:It is important for DPLs be accompanied by technical support that has the procedural flexibility to allow for just-in-time capacity building and technical assistance. Budgetary support to the education sector should set up a mechanism that will allow for technical assistance to be provided to reforming institutions easily so that when lack of capacity in an unforeseen area arises, it is possible to respond quickly and adequately with the needed support. The internal procedures of most external partners currently do not have the flexibility to make this happen. Multi-donor operations call for a certain willingness to compromise from all parties. Donors often come to an operation involving other external partners with certain priorities of their own. These may differ from those of the government and of other donors. Government counterparts in this case reported that a particular donor may, for example, place strong emphasis on decentralization and school-based management, whereas the government, or other donors, may prioritize activities that favor perhaps a specific sub-sector of the system (e.g. secondary or vocational training). Intermediate outcome indicators can be important for DPLs. As an instrument to support a government program, a DPL must use the government M&E framework. However, this can be complemented by indicators that measure the program's outcome on an annual basis, to indicate that the program is moving in an appropriate direction.
P117864 | Second Rural Electrification | Latin America and Caribbean | Peru | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IBRD | IPF | 2011 | 2018 | 2018 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/178481527626905736/text/Peru-PE-Second-Rural-Electrification.txt | http://documents.worldbank.org/curated/en/178481527626905736/pdf/Peru-PE-Second-Rural-Electrification.pdf | The IEG selected the following main lessons from the ICR, with some modification of language.(1) Stronggovernment commitmentis critical forcreating anenablingenvironment for project implementation.Strong government commitment as reflected throughfavorablesectoral policiessuch as involving theelectricity distribution companies and regional governments in sub-projects, increasing affordability of connections by includingthe connection fee in the capital cost rather than charging the user and usingSolar Home Systems to serve remote populationsand using low-cost technologies for grid extension helped in creating an enabling environment for projectimplementation.(2) The challenges associated with implementing Right-of-Way (ROW) payments need to be addressedearly in the project cycle.Based on the experience of this project, common obstacles faced on the complianceof the Right-of-Way (RoW) payments includeincomplete documentation of land titles and difficulties in locating a number ofdispersed land owners.These issues need to be addressed early and plans for RoWs need to be incorporated into the projectsconditions of effectiveness.(3)Complementing investment activities with technical assistanceactivities that are tailored to the specific needs of the project isrequired foraddressingrural electrificationefforts.Technical assistance activitiessuch as, support to the government and the Electricity DistributionCompanies inimplementing sub-projects,assessment of renewable energy sources and promoting productive uses ofelectricity proved to be useful inimplementing rural electrification sub-projects in thisproject..(4). Although thepromotion of productive uses of electricity can be a beneficial component of arural electrification project, ensuring its sustainability requires consistent and adequate levels of support. Perusexperience highlighted the importance of Non-Governmental Organizations (NGOs) in assisting producers in rural areasadopt electrical equipment.(5) The potential conflict between the long-term nature of rural electrification and short-termpolitical objectives requires a sustained commitment and understanding of authorities to avoid problems in the programs designand implementation. Despite the highly supportive political environment in Peru, the project faced significantimplementation problems dueto a combination of factors including a change in government that resulted in delays in appointingmanagement teams andreluctance on the part of Electrical Distribution Companies to participate in a rural activity that theyperceived as adverse to their financial interest.Addressing these issues requires long-term commitment of the government aswell as building alliances with those interested in sustainable rural electrification (such as local governments, distributioncompanies and other local stakeholders).
P117871 | Regional Disaster Vulnerability Reduction APL1 - Grenada and St. Vincent and the Grenadines | Latin America and Caribbean | OECS Countries |  |  | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2011 | 2022 | 2023 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099200003272311591/text/P11787109285520ca0bdec076bfab92a1d5.txt | http://documents.worldbank.org/curated/en/099200003272311591/pdf/P11787109285520ca0bdec076bfab92a1d5.pdf | Strengthening resilience across the Eastern Caribbean Region requires identification of activities, outputs, andoutcomes at the regional level, not just at the country level. A clear vision and strategy for strengthening resilienceacross the region is required to ensure that activities at this level, for example for enhancing regional connectivity and datasharing across countries, are identified and financed. Including instruments and dialogue on financingreconstruction and recovery in addition to investments in infrastructure can strengthen resilience to natural disasters.The Bank has been assisting the countries of the Eastern Caribbean Region to learn about and adopt innovative riskreduction and risk financing instruments, such as the CCRIF, and the Catastrophe Deferred Drawdown (CAT DDO), a contingent creditline that provides immediate liquidity to countries in the aftermath of a natural disaster. In addition, in both Grenada and SVG, acomprehensive disaster risk management dialogue with the governments allowed for further strengthening of financial protectionmechanisms and strategies through the regional Disaster Risk Financing Technical Assistance. Having more accurateestimates of the costs of compensating project-affected people at the start of the project can help governments budget forthe expenses in a timely manner. The Government of Grenada faced challenges in budgeting for the costs of compensatingpeople affected by various infrastructure projects. Having a clear understanding of the number of people likely to be affectedand the costs of compensating them at the beginning of the project can help the government budget for those costs at the outset ofthe project implementation period. Making use of a dedicated portfolio manager can result in more accurate costestimates of project activities. Actual project costs were much higher than estimated at appraisal, leading to someactivities being canceled while others were delayed while AF was mobilized to cover cost over-runs. Having a dedicated portfoliomanager assess costs of various activities during appraisal in collaboration with all participating ministries and institutions mayhave led to more accurate cost estimates from the beginning.
P117874 | Indonesia Seventh Development Policy Loan | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2011 | 2011 | 2018 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/797511499715567807/text/Indonesia-ID-Seventh-Development-Policy-Loan.txt | http://documents.worldbank.org/curated/en/797511499715567807/pdf/Indonesia-ID-Seventh-Development-Policy-Loan.pdf | The ICR presents a comprehensive list of useful lessons, not only from DPO 7 and 8, but also from the previous series thatremain relevant (ICR, p. 21-23). Particularly noteworthy are the following: A high quality professional workingrelationship between the Bank and key counterparts, both at a policy and working level, is key to a successful reform program. Sucha relationship benefited, in this case, from the presence of a large Bank team in the country office. relationship determines therelevance and impact of prior actions, facilitates implementation and ensures the appointment of counterparts with a high enoughrank to champion the reforms. In areas where this was not the case, implementation lagged or did not take place. Ageneral or umbrella DPO, like those in this series, can be kept manageable by limiting the number of prior actions andpolicy areas, and by providing complementarity to Bank interventions in specific sectors where further operations can be designedwith a view to deepening the reforms.
P117924 | Poverty Reduction Support Credit (PRSC-7) | Western and Central Africa | Ghana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2011 | 2017 | PPAR | >=100 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory |  | http://documents.worldbank.org/curated/en/642251469189437185/text/106279-PPAR-P127314-P117924-Box396280B-PUBLIC-disclosed-7-21-16-ppar-ghanaecon-0716.txt | http://documents.worldbank.org/curated/en/642251469189437185/pdf/106279-PPAR-P127314-P117924-Box396280B-PUBLIC-disclosed-7-21-16-ppar-ghanaecon-0716.pdf | 6. Lessons 6.1 Ghana again became a substantially indebted country that must direct a substantial share of its revenues to debt servicing, and it did so within a decade after a major debt relief under the Heavily Indebted Poor Countries Debt Initiative. This highlights the importance of prudent macrofiscal management in post-HIPC countries, and emphasizes that the World Bank has to place in its policy lending for helping its clients to preserve borrowing space. 6.2 Adequate macroeconomic management is a critical precondition of budget support (which relates to the previous lesson). The World Bank made the right choice to focus on restoring fiscal discipline as part of risk mitigation for the Economic Governance and Poverty Reduction Credit in 2009. Similarly, its choice not to deploy development policy operations (DPOs) in 2013â€“14 because of the lack of an adequate macroframework was also correct. Ghana's case also shows that the World Bank is not a substitute for the IMF in a challenging context that requires a comprehensive macroeconomic program. In this respect, Ghana is a good example of World Bankâ€“IMF cooperation. 6.3 Ghana's case shows that DPOs deployed in an extremely weak public financial management environment are unlikely to be successful. Ghana experienced a deterioration in resource allocation during 2008â€“12 because of debt-financed expenditure hikes that led to interest payments of about 7 percent of gross domestic product per year, taking precious resources away from pro-poor spending, thus undermining Ghana's overall growth and poverty reduction agenda and the effectiveness of the World Bank's budget support. This emphasizes the importance of the quality of public resource use in both public financial management and public resource allocations, as a pre-condition of budget support success. 6.4 Donor coordination on budget support can be difficult in a challenging environment like that in Ghana in 2008â€“13. Assessment of eligibility for budget support is still a controversial area in relationships between various donors. Despite a move toward performance criteria based on agreed-to actions, various donors may interpret different shocks differently, which will affect donor coordination. Dealing with macro and fiscal mismanagement when macroframework is not formally a part of the performance assessment can be an especially contentious issue. 6.5 Fiscal pressure can crowd out discretionary expenditures, and service delivery sectors are especially vulnerable. The World Bank can use DPF operations to take a crucial role in protecting pro-poor expenditures in such an environment. 6.6 Giving due weight to the underlying factors of fiscal imbalances and addressing them appropriately is crucial. Measures taken to contain the public wage bill and mitigate fragmentation of bank accounts were insufficient to translate into lasting results. 6.7 The World Bank has a crucial role in providing advisory services that are complementary to budget support. A more proactive engagement in estimating the fiscal impact of the single spine salary reform introduction could have helped in designing a phased approach consistent with the long-term budgetary envelope.
P117944 | HT 3rd Econ. Governance Reform Operation | Latin America and Caribbean | Haiti | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2011 | 2012 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/812851474488675572/text/000020051-20140624213412.txt | http://documents.worldbank.org/curated/en/812851474488675572/pdf/000020051-20140624213412.pdf | The lessons cited in the ICR -- the need for a simple approach, need to specify better the responsibility of every agency, the need for strong institutional support to back up reforms, and the importance of close donor cooperation --- are all supported. Using DPLs in Haiti's fragile, post-conflict setting is fraught with high risks. Yet if the risks can be properly mitigated, using country systems for donor funds can build public trust in the Government. Improving the effectiveness of formal PFM and procurement systems, and demonstrating that donors have confidence in them, also opens the possibility that there will be greater incentive for elites to invest political capital in these systems, and to reduce their reliance on unclear, informal patronage systems.
P117947 | Support to the National Urban Transit Program Project | Latin America and Caribbean | Colombia | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2012 | 2021 | 2021 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/613451624947620023/text/Colombia-CO-Support-Natl-Urban-Transit-Program.txt | http://documents.worldbank.org/curated/en/613451624947620023/pdf/Colombia-CO-Support-Natl-Urban-Transit-Program.pdf | Key lessons adapted from the ICR areas follows:For a national program to support urban transport,technical requirements should be flexible to adapt to local needs, and based on evidence (i.e., systems should bemademore attractive to users and financial sustainability ensured to facilitate private sector participation). Based on theinitial success of TransMilenio, the national policy established requirements (e.g., use of technology) or even objectives (e.g.,fleet rationalization) that did not fit local needs. Cities across the globe (especially cities in Africa and Asia) have beenimplementing BRTs aiming to replicate the TransMilenio system without taking into consideration the local context and specificneeds of the cities concerned. It is important to highlight the importance on providing customizedtransport solutions foreach city.In Colombia,SPTSs were severely impacted by the influence of TransMilenio as they were overspecified in termsof technology requirements for smaller operations. Several cities sufferedfrom an undersupply of public transport as informalservices advanced whileoperators did not renew their fleets. A Technical Assistance (TA)component directly supporting subnational level implementing entities can help with implementation. Project implementationsuffered from delays due to instability and lack of capacity ofthe implementing agencyas well as the low technicalcapacity of smaller cities. Including the TA component allowed the speeding up of the implementation. Such a TAcomponentbenefited the program implementation and built technically strong teams with experienced specialists at the citylevel.Early consolidation of the environmental and social management capacities is important to ensure timelyproject implementation.Experience has shown that the earlier these teams are onboard and able to participate inproject design and planning, the higher the rate of success for the particular project activity.It is important togo beyondbuilding infrastructure and focus on achieving outcomes through systems operation. Urban transport projectsshould explore system interventions to attract greater demand for public transport, especially in terms of disincentivizingmotorcycles and moto-taxis or integrating informal transport into the system.
P117979 | Uganda - Financial Sector DPL (1 of 2) | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | DPF | 2011 | 2012 | 2015 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/635501468000888669/text/ICRR14747-P117979-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/635501468000888669/pdf/ICRR14747-P117979-Box393191B-PUBLIC.pdf | IEG draws the following lessons from the preparation and implementation of this operation:Implementation of the reform agenda is likely to be adversely affected by objectives that are overambitious in relation to implementation capacity, and by a time horizon too short to address adequately the identified policy issues. The quality of design of DPOs matters for implementation and outcomes. Good design of DPOs needs to clearly link objectives to select, relevant policy reforms and indicators in a clear chain of attribution. Each outcome would have a corresponding indicator and unambiguously defined relevant target with clear baseline that can easily be evaluated ex post.Ownership of reforms may be limited or change quickly during the preparation of a DPO, especially in the context of complex, politically difficult reforms (e.g., pension reform). The extent of ownership requires constant monitoring not only during preparation, but during implementation as well.
P118018 | Cameroon:NGOYLA MINTOM PROJECT | Western and Central Africa | Cameroon | Blend | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2012 | 2018 | 2019 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/596161557329102820/text/Cameroon-Cameroon-NGOYLA-MINTOM-PROJECT.txt | http://documents.worldbank.org/curated/en/596161557329102820/pdf/Cameroon-Cameroon-NGOYLA-MINTOM-PROJECT.pdf | The following synthesize lessons are partly drawn from the ICR with a supplementarylesson suggested byIEG.A Livelihoods Support Mechanism (LSM) is a complex undertaking that requires extensive localeconomic, social and cultural research, requiring dedicated expertise to devise and implement it sustainably. Forexample, in this project to manage high stakeholder engagement, sustainability and capacity risks for this project, the LSM wasintended to be designed and managed by a specialist contractor (PAD para 43). But due to procurementchallenges,implementation was brought in-house to the PIU (ICR para 65). A lack of understanding of cultural and local marketconditions (ICR paras 94, 99, 100),resulted in failures in the initial rounds of micro-projects and the lack ofsustainability of the LSM. These failures could have beenmitigated by retaining a dedicated contractor experienced inlivelihood supportprograms to manage theLSM pilot anddesign its scalingup, as envisaged in the PAD (para46).Legal safeguarding isan effective first step in the very long-term venture of addressingconservationin protected areas, but its long-term effectiveness relies on broad, ongoing stakeholder engagement, appropriatecapacity and financing mechanisms (based on ICR para 98). For example, in this project successful conservation andmanagement improvements in forestreserves were enabled through broad stakeholder engagementin the context ofaparticipatory approach. At project closing, however, uncertain financial resources for conservation and management,stretched local capacity for monitoring, and a lack of clear alternative sustainable livelihoods for communities negativelyaffected by the protection of forest reserves have threatened the ongoing efficacy of these gains. Hence, expectations of securinglong-term benefits from a short-term project must be modest, especially where building capacityand behavior changearealso necessary.PDO statement requires specificity on outcomes/results expected. Inthis project, key terms in PDO indicators were not precisely defined, creating difficulty in assessing project achievements. Forexample, the termimprovements expected, particularly in relation to conservationwas notspecified, which meant the indicator for the outcome (legal classification) was not sufficient to demonstrate results againstconservation. In addition, the objective of increasing access to income generating activitiesdefinedasameasure of successfor those directly benefitting from the project, but without defining access orbenefit, the ICR left significant unanswered questions about the impact of the activities onlocal communities.
P118023 | Third Highway Project | Europe and Central Asia | Azerbaijan | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099325003292218485/text/P11802300a430f0010bb20032d7be2fab6e.txt | http://documents.worldbank.org/curated/en/099325003292218485/pdf/P11802300a430f0010bb20032d7be2fab6e.pdf | The ICR draws the following main lessons from implementing this project, with some adaptation of language.1. Toensure early disbursement, it ishelpful to have more than one high value activitythat cancommence ateffectiveness or shortly afterwards. This project became effective with the design and procurement ready completedfor30 km stretch of the Baku - Shamakhi road whileother sections were still under preparation.2.The introduction of modern management approaches for road maintenance is feasiblefor state-owned entities, but requirestime.The developmentobjectives of this project were initially modest. However, the Bank provided optionsandengaged with the Government in a long-running dialogue on the maintenance of roads. TheGovernment eventually adoptedthe recommendations onthe modernization of motorway management and maintenance, and this led to the Service Level Agreementsbetween theRegional Management Units and the Motorway Management Unit of the Road Administration.3.Implementing agencies should strongly encourage all bidders for works contracts to reflect their foreign currency costs,regardless of historical exchange rate performance. The sudden devaluation of the local currency, during projectimplementationcreated cash flow problems for several contractors, as they had priced the work in local currency but had costsin foreign currencies. While the standard World Bank bidding documents used for the project allowed bidders to include foreigncurrencies, none did so as the local currency had previously been very stable. Consequently, contractors were over-exposed to theeffects of currency fluctuations.
P118026 | Local Government Strengthening Project | Latin America and Caribbean | El Salvador | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2010 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/960721516202747827/text/ICRR-Disclosable-P118026-01-17-2018-1516203654305.txt | http://documents.worldbank.org/curated/en/960721516202747827/pdf/ICRR-Disclosable-P118026-01-17-2018-1516203654305.pdf | The ICR presents six key lessons (ICR, Section 6, paragraph 81), slightly modified below: Communityparticipation enhances the prioritization of local investments. Continued engagement during implementation fostersownership and strengthens support for allocating resources to adequately operate and maintain local investments. Forexample, Building capacity of institutions while implementing locally determined investmentsstrengthens theinstitutions ability to deliver localservices. At the same time, a better assessment of how best to distributefunctions between central and local agencies help to better meet implementation hurdles. For example, Recognizinginfluential actors at the local level and enjoining their participationstrengthen local institutions. For example,the Corporacion de Municipalidades de la Republica de El Salvador (or the Corporation of Municipalities of the Republic ofEl Salvador or COMURES) is an important influence among municipalities that could help promote strategic planning, a voice tosupport better municipal management by adopting tools and systems such as SAFIM and SIGMUNI and promote municipal planning thatincrease transparency and facilitates administration efficiencies. The ICR noted that a lesson learned in socialsafeguard compliance was to expand the role and train staff and environmental teamsto laythe groundwork to establish aDepartment of Social and Environmental Management (ICR, paragraph 34).
P118027 | AF: Development Policy Prog. Series | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2014 | 2015 | 2017 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/655501497981739460/text/Afghanistan-AF-Development-Policy-Prog-Series.txt | http://documents.worldbank.org/curated/en/655501497981739460/pdf/Afghanistan-AF-Development-Policy-Prog-Series.pdf | IEG draws twolessons from the experience of this operation:(i) For difficult reforms in a fragile contexttobe fruitful, they would need tobe measured and balanced. In this case, the operation attempted to address too broad aspectrum, covering a variety of sectors.(ii) Unless full account is taken of the political context, including the possibleimpact of upcoming elections, there is a danger of the program being disrupted by lack of continuity. Incorporating moreflexibility in the design and the implementation of the DPL instrument might increase its adaptability to fragile and post-conflictcontexts.
P118028 | AF: ARTF-2nd Judicial Reform Project | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2012 | 2018 | 2019 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/526601538347541243/text/Afghanistan-AF-ARTF-2nd-Judicial-Reform-Project.txt | http://documents.worldbank.org/curated/en/526601538347541243/pdf/Afghanistan-AF-ARTF-2nd-Judicial-Reform-Project.pdf | The ICR (pp. 28-29) offered several useful and insightful lessons, including the following (restated byIEG):Country strategy usefully guides a projects level of ambition as well as its specific objectivesand activities only if that strategy is grounded in a realistic political economy and security assessment. In this case, arealistic appreciation of political and institutional constraints did not appear until the 2017-2020 Country PartnershipFramework.Political economy analysis cannot rely solely on interaction with a relatively small group ofreform-minded counterparts who many not have a realistic view of the reform landscape, especially at the sub-national level.In this case, the underlying political situation was inadequately considered in the original project design, and it later becameclear that many counterparts did not fully understand the nature of the reforms envisaged by the project and/or were reluctantfully to express objections during the design phase.Incremental design can usefully pair basicinfrastructure with institutional reform. In this case,some of theinstitutional actors were most interested ininvestments in infrastructure and equipment, and these were used as incentives to adopt human resources and pay/gradingreforms. This approach could be more broadly and deliberately adopted.Concern about sustainability ofrecurrent costs cannot wait until a projects conclusion. In this case, in a situation where most of the countryspopulation cannot afford legal assistance, project support for legal aid to indigent individuals cannot be sustained in the longrun. This project might have considered a transition to a hybrid system combining the services of non-governmentalorganizations and private lawyers alongside the state-run legal aid system.
P118036 | Sustaining Social Gains for Economic Recovery | Latin America and Caribbean | El Salvador | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2011 | 2012 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/569431474505040191/text/000020051-20140624214610.txt | http://documents.worldbank.org/curated/en/569431474505040191/pdf/000020051-20140624214610.pdf | There are two important lessons: First, it is critical to have the full commitment of both the Government and the Bank when preparing a rapid operation with a new administration that has limited experience. In this DPL the new government of El Salvador was able to work very closely with the World Bank team in designing the policy actions and outcome indicators, helping to build ownership of the program and ensure that the program's objectives were in line with the government's anti-crisis plan and framework for economic recovery. Second, a program that focuses on a small number of interventions with well defined and measurable indicators is more likely to succeed. It helps the government focus on key reforms, implement them and monitor progress achieved. This is all the more important as the government institutional capacity constraint is binding.
P118045 | Togo Agricultural Sector Support Project | Western and Central Africa | Togo | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2011 | 2021 | 2022 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/472891635282142727/text/Togo-TG-Agricultural-Sector-Support-Project.txt | http://documents.worldbank.org/curated/en/472891635282142727/pdf/Togo-TG-Agricultural-Sector-Support-Project.pdf | The ICR included three lessons. The following lessons are emphasized with some adaptation oflanguage:1.To ensure effective implementation of projects by government entities,the adequacy ofhuman resources in charge of project implementation need to be carefully assessed against therequired workload and combinedwith the provision of the appropriate incentives.Project implementation by existing governmententitiesfosters ownership, improves capacity building, and lays the foundation for improved institutional capacity beyond theproject lifecycle. The ASSPwas implemented by the Ministry of Agriculture and the capacity built remains within the Ministryso that it can continue providing quality support, capacity building and advisoryservices to beneficiaries even after projectclosing. To be effective, the right incentives (better working conditions, training and attractive compensations) are needed tocompensate the staff and retain them to prevent a high turnover. The building up of capacities in institutions also needs to bebased on a strategic vision and resourcecommitment for continuous institutional improvements to beviable.2.Implementing projects underweak procurement capacity and therefore high procurement riskrequiresalternative solutions tobe considered and embedded in project design to mitigate procurement risks.The ASSPwas implemented in a context of weak capacity of government entities in the agricultural sector. Externaltechnical assistance was hired to support the project team in procurement matters, but this assistance came too late. Thissituation was complicated by delays in setting up the evaluation committees and in finalizing evaluation reports. The impact ofthese delays was mitigated by stepping up capacity building, increasing the number of evaluation committees, improving timelinesfor finalizing procurement processes and awarding contracts, and closer monitoring by the Bank team, leading to improvements in theprocurement performanceof the project. To mitigate the risk of procurement for future projects insimilar contexts, itis important to enlist technical assistance and appoint the required staff, train them and set up an adequate number of evaluationcommittees soon after effectiveness for the timely drafting of terms of reference or descriptions of works, the issue ofinvitations to bid, and all the steps that follow inorder to speed up the procurementprocess.3. To restore the productive potential of depleted ecosystems, it is essential toinvolvebeneficiaries as stakeholders of depleted systems in restoration efforts combined with the provision of alternativeincome-generating activities.The ASSP supported the enforcement of a biological recoveryperiod for fish stocks, the restocking of water bodies with fish, the prohibition of harmful fishing practices coupled with thedistribution of fishing nets that comply with authorized standards, and the promotion of alternative income-generating activities.The project experience showed that thesemeasures led to an increase in the population of fish and volume of fish capturescontributing to sustainable fishing in the context of Togo, which was characterized by a growing pressure on halieutic (art offishing) resources. Also, organizing fishermen into groups that help foster the understanding of their role in maintainingfisheries resources have better chances of success than strict enforcement of regulations.
P118053 | Afghanistan New Market Development | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2011 | 2018 | 2019 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/443851533563926715/text/Afghanistan-AF-New-Market-Development.txt | http://documents.worldbank.org/curated/en/443851533563926715/pdf/Afghanistan-AF-New-Market-Development.pdf | The ICR (pages 25-27) draws seven lessons. The followingmain lessons were judged by this review to be the most importantwith respect to application to other Bank operations,with some modification of language.(1) Simplifiedproject design can improve the likelihood of success in a fragile environment. Recognizing thelimited counterpartcapacity and the fragile environment, the project design wassignificantly simplified during preparation (eschewing complexinfrastructure investment and focusing onmatching grants and capacity building components).The simplified designenabled the Project Management Unit tofocus on theFNMD activity.(2) Making provisions for advanceproject preparation funds can be helpfulinfragile situations. In addition to low expressed interest frominternational firms, the implementation of this project was further delayed due to the weak procurement capacity.Projectpreparation funds to support advance procurement/recruitment and capacity building of the MoCIduring project preparationcould have helped in reducing some implementation delays.(3) Even with strong Governmentcommitment, capacity limitations can thwart project implementation.Activities in this project were aligned withthe Governments objectives andinitiatives for developing aprivate-sector led market economy.Despitethis,implementationsuffered significant delays in the initialyears due to factors such astheMoCIslack of familiarity with Bank policies,slow uptake of the matching grants by the private sector,slow reimbursement to SMEsand high turn over of the Project Management Unit staff. The lesson from implementing this projectis that a major effort for capacity building and institution strengthening should precede project implementation to the extentpossible in fragile conflict affected states.(4) Management and supervision of theME data collectionmechanismby the local institution can help in ensuringsustainability. In this project, data collection was theresponsibility of the German Agency for International Cooperation(GIZ) whichwas bound by the timeconstraintsinits contract.Institutionalizing data collection managementin the Ministry of Commerce andIndustry could have facilitatedthe follow up with the beneficiaries and better MEof the project impact could havecontributed to measuring the progress made in Government reforms.
P118064 | UY OSE Sustainable and Efficient | Latin America and Caribbean | Uruguay | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2013 | 2020 | 2021 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/483961608753961941/text/Uruguay-UY-OSE-Sustainable-and-Efficient.txt | http://documents.worldbank.org/curated/en/483961608753961941/pdf/Uruguay-UY-OSE-Sustainable-and-Efficient.pdf | The ICR (paras. 98 to 101) lists a number of lessons. Specially relevant toprojects being implemented in similarenvironments is the following:Lasting institutional transformation for major water supplyandsanitation utilities requires a series-of-projects approach where successive projects build on, enhance and expand on the gainsaccomplished under earlier projects. In case of OSE, strengthening of the utilitys operational and managementcapacity built on significant achievements that resulted from the Banks earlier engagements with OSE.In addition,an IEG lesson that emerges from the experience underthis project is that, when the project includes a largenumber of management strengthening activities, with analytical, strategic,and operational outputs, it is important to ensurethat adequate attention is given to assessing the observed impacts of the outputs. This would require monitoring ofresults and their impacts as a part of ongoing project supervision.
P118070 | MX Economic Policies in Response to the Crisis DPL | Latin America and Caribbean | Mexico | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2011 | 2012 | ICRR | >=100 million | Satisfactory | Satisfactory | Moderately Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/135981474497097539/text/000020051-20140625054601.txt | http://documents.worldbank.org/curated/en/135981474497097539/pdf/000020051-20140625054601.pdf | Bank responded quickly to Government need, and was able to draw on its expertise in several areas to build reform program. The Bank's capacity to respond quickly in a crisis is an important asset. The operation had an important "signaling" effect of showing support for the Government from the World Bank, even though the amount of the loan was small compared to the fiscal or balance of payments gap. Despite this satisfactory outcome, performance might well have further improved if it had been placed in a programmatic context. Therefore, a key lesson is that operations such as this are better if placed in a programmatic context, including measures that are aligned with targets and permit realignments during the life of the operation, rather than a single-shot DPL without a forward looking program. This would permit better dialogue on mitigation measures, should the program go off track. AAA should be on-going even if lending is subdued, so that a knowledge base is maintained against future needs.The operation might have been better designed as a DPL-DDO (DPL with a Deferred Drawdown Option), which would have been less costly to the Government and still provided the necessary signaling of Bank support.
P118090 | EG-Enhanced Water Resources Management | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Sustainable Development | Water | GEF | IPF | 2013 | 2017 | 2018 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/794281500303304294/text/ICRR-Disclosable-P118090-07-17-2017-1500303293516.txt | http://documents.worldbank.org/curated/en/794281500303304294/pdf/ICRR-Disclosable-P118090-07-17-2017-1500303293516.pdf | The ICR draws the following main lessons from implementing this project, with some modification of language.(1)An Integrated, multi-sector approach that goes beyond the prism of the water sector alone can be useful for addressing waterresources challenges. This project showed that implementation of Integrated Water Resources Management (IWRM) is possibleand can yield good results in terms of water savings, improved water quality and better environmentaloutcomes.(2) While adedicated Project Management Unit (PMU) may beessential for managingcross-sectoral interventions, it would be useful to develop incentives for stakeholder participation. In this project, PCUfaced difficulties associated with coordinating all the key water sector players.(3) Participation of localstakeholders is required for IWRM. This project showed that involving local communities can generate positivebenefits. This project showed that public awareness activities built demand for solid waste collection,enticed ruralresidents to pay for this service and helped reduce the discharge of solid waste into open drains.IEG adds the followinglesson.(4) It would be useful to have a beneficiary survey when project activities aim at enhancingtheknowledge and capacity of water sector institutions.
P118101 | SKILLS DEVELOPMENT PROJECT | Eastern and Southern Africa | Rwanda | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2011 | 2016 | 2017 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/773761498228683774/text/ICRR-Disclosable-P118101-06-23-2017-1498228666830.txt | http://documents.worldbank.org/curated/en/773761498228683774/pdf/ICRR-Disclosable-P118101-06-23-2017-1498228666830.pdf | The ICR lists eight lessons (pp. 27-28). Important among these arethe following: Enhanced implementation support and supervision by the World Bank coupled with continued dialogue with the Government can helpbuild capacity for improved project implementation (adapted by IEG). Timely restructuring can play a pivotal role inimproving project implementation and increasing the likelihood of achieving the project development objectives (adapted byIEG). The likelihood of achieving the project development objectives decreases when the completion of project activitiesis dependent on activities that are outside the control of the project. Construction/works shouldbe carefully planned during project preparation and should take into account the capacity constraints that exist in the country,especially when the achievement of project objectives is dependent on the successful implementation of heavy procurement-relatedactivities.Overall, IEG concurs with all of the ICRs lessonsbut adds an important qualification: The ICR notes that a strong ME system has a positive impact on achievement ofproject objectives and that the the strong ME system developed under this project helped inform decisions formaking midcourse adjustments to project activities. IEG would note that the ME system was strong on itsmonitoring dimension as it allowed the tracking ofoutputs, understanding of delivery bottlenecks,andworking out ofsolutions such as the IBT approach. However, the ME system was weak on its evaluationdimension.
P118109 | MN-Mining Infrastructure Investment Supp (P118109) | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2020 | 2021 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/655641611858371087/text/Mongolia-MN-Mining-Infrastructure-Investment-Supp.txt | http://documents.worldbank.org/curated/en/655641611858371087/pdf/Mongolia-MN-Mining-Infrastructure-Investment-Supp.pdf | When designing PPP projects in an evolving political climate where PPP transactions are limited, projects should seeksimpler transaction modalities that can be developed incrementally to incorporate the more nuanced legal mechanisms needed forriskier transactions.The project explored opportunities for public-private partnerships for sub-projects forwhich feasibility studies, ESIAs, and CIAs were conducted. The project supported capacity building for PPP transactions, organizednine meetings and workshops to generate investor interest, and established a project steering committee composed of all relevantministries and agencies to facilitate the governments decision making in selecting the most impactful projects considering thefunding sources. Despite the comprehensive activities undertaken under this project, PPP subprojects had not been implemented bythe end of the project. Given the changing political climate in the country and the high turnover of government officials, it isimportant to create a relatively simple transaction modality for potential investments in order to strengthen the PPP framework.Activiies can then be developed in stages to incorporate the more nuanced legal mechanisms required for riskier transactions. Inaddition, it is important to create a relatively simple transaction pattern for potential investments, which can then be developedin stages to incorporate the more subtle legal mechanisms needed for higher-risk transactions.It is essential tostart screening safeguards and stakeholder engagement early in the project, especially when the clients capacity islimited.At the time of project design, the Bank envisaged that the client would be able to identify sub-projectsand conduct feasibility studies as early as possible. However, political complexities and limited client capacity hindered thegovernment from selecting subprojects early, delaying the Banks involvement and limiting the time to fully investigate therisks associated with the subprojects. The inadequate assessment of safeguards attracted the attention of civil society and led tocalls for an Inspection Panel. This series of inadequate responses have resulted in three lessons learned. First, the clientscapacity to select and manage subprojects needs to be assessed before the project begins. Delays in assessing capacity shortenedthe Banks available engagement time and resulted in inadequate subproject preparation and risk identification. Second, whenselecting sub-projects, early screening of safeguards would enable potential impacts to be identified and mitigation measures to beestablished at that time. The World Bank needs to mobilize the sector and safeguard experts to conduct early engagement withclients. Third, identifying, communicating with, and engaging early with stakeholders who may benefit from or influence thefeasibility study are useful in building a shared understanding with stakeholders about the risks and opportunities of the project.Stakeholder identification informs the engagement strategy by mapping the relationship of stakeholders to the project, theirattitudes, influences, criticisms, and objections.
P118112 | Ghana Skills and Technology Development Project | Western and Central Africa | Ghana | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/778171518099122871/text/Ghana-GH-Skills-and-Technology-Development-Pro.txt | http://documents.worldbank.org/curated/en/778171518099122871/pdf/Ghana-GH-Skills-and-Technology-Development-Pro.pdf | These lessons are adapted from the ICR (p. 31): Close collaboration with Government, other partners, andkey stakeholders is critical in ensuring buy-in to project design, particularly in terms of those activities supporting sectorreforms. This may be achieved when the Bank works closely with the Government and other key stakeholders throughoutpreparation to ensure that a projects design and objectives are tailored to the needs and larger Government strategies for therelevant sector. The incorporation of capacity-building activities into project design is likely to reapimportant dividends in introducing and guiding sustainable change. Capacity building of key government institutions inrelevant sectors may contribute to their strong establishment, enhanced visibility, and improved coordinating efforts in theirrespective sectors. Such entities will have the potential to become strong proponents of continued reforms.Targeted technical ME support during implementation can be useful in addressing any limitations to the ME systemand ensuring the collection and analysis of adequate information to measure progress made under a project. With targetedtechnical ME support provided by the Bank, the ME system for this project was significantly strengthened and capable ofcollecting comprehensive datasets on key inputs, outputs, and outcomes. Competitive skills funds can guideand transform the provision and delivery of training with important dividends for industries and TVET providers alike.Available data and information obtained through the course of this project have demonstrated potential outcomes of the SDFin terms of increased productivity, generation of resources, and the establishment of mutually beneficial partnerships betweenresearch and technology institutes and industry/private enterprises.
P118113 | Third National Program for Community Empowerment in Urban Areas III | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2010 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/853181480297654612/text/ICRR-Disclosable-P118113-11-27-2016-1480297631613.txt | http://documents.worldbank.org/curated/en/853181480297654612/pdf/ICRR-Disclosable-P118113-11-27-2016-1480297631613.pdf | The ICR presents a number of good operational lessons, including the following: Procurement of Oversight ServiceProviders (OSPs) is cost-effective. Through this procurement method, the Implementing Agency was able to provide oversight at asubstantially lower cost than if it had used traditional oversight consultants, while the length of the procurement period wasreduced by more than half relative to traditional contracting. Pre-financing block grants, also known as block grantreimbursement is effective. This also significantly reduced delays in disbursement of block grants compared with the previousPNPN Urban I project. A systematic invoicing verification procedure helps prevent misuse of funds. Development and use ofa verification manual by the Implementing Agency included random third-party confirmation of expenditures and standard reports,among other improvements.It also includes a couple of relevant substantive ones: Performance-basedgrants do not necessarily benefit the poor as they may tend to primarily benefit more capable communities with lower comparativepoverty levels. Although this approach may help to achieve economies of scale, it also tends to favor higher capacity local urbancommunitieshaving below-average poverty incidence. CDD projects can be utilized effectively to build awareness ofnatural disaster risks and help communities to boost their capacity to address them. In addition, procedures and processes adoptedfor disaster risk management in projects such as the present one should be consistent with existing CDD procedures in order toavoid burdening poor communities with further requirements.Finally, although not specifically mentioned in the ICR,this projects experience points to the importance and usefulness of having a comprehensive and well-functioning programManagement Information System (MIS), including for purposes of Monitoring and Evaluation (ME), in place.
P118145 | Regional - Governance and Knowledge Generation | Middle East and North Africa | Middle East and North Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | GEF | IPF | 2012 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/670871498053840459/text/ICRR-Disclosable-P118145-06-21-2017-1498053827789.txt | http://documents.worldbank.org/curated/en/670871498053840459/pdf/ICRR-Disclosable-P118145-06-21-2017-1498053827789.pdf | The ICR draws the following main lessons from this project, with some adaptation of language.(1) In order toachieve sustainability of projects with a regional dimension, a strategic approach should be put in place from the beginning thataims at anchoring the work in a regional institution.This project was conceived to contribute to the overarchingobjectives of the Mediterranean Environmental Sustainable Development Program - Sustainable MED. The link with theprogram was however weakened, given that the there was no permanent MED Regional Knowledge center at closure.(2)Involvement of beneficiaries can facilitate project implementation.In this project, the outputs and outcomes werefully achieved in countries where beneficiaries were involved. Establishment of operational country focus groups for each activityin Lebanon helped in adequate follow up of the activities implementation. Implementation of the project was also facilitatedby mobilization of in-kind financing from the beneficiaries.(3) Selectivity and prioritizing ofspecific outcomes is required for effective monitoring. The experience with this project showed that for projects ofrelatively small size and implemented in a large geographic area, it is important to focus on specific outcomes and projectactivities.(4) It isuseful to consider the advantages and disadvantages associated with aflexibleproject design. The experience with this project demonstrated that while a flexible design allows for betteralignment to the needs of beneficiaries, it also weakened theresults framework. For a project of this size and in the contextof a larger program, it is important to identify all interventions ahead of time and defining the results framework before theproject becomes effective.(5) It is necessary to consider the timeline when proceeding withrestructuring. In the case of this project, halfway through project implementation, Egypt and West Bank and Gaza becamebeneficiaries via a lengthy restructuring. Although West and Gaza had submitted the endorsement letter in February 2012 and Egyptin October 2012, the restructuring became effective only in April 2013. While the design of this project allowed for new countriesto join the project, the actual process of adding the new participants affected the implementation of existingactivities.(6) Capacity building and Knowledge generation/management intervention tend to yield benefits in thelong run. Given that a six month window of evaluation of results can only capture part of the impact, it may be useful tohave an impact evaluation of outcomes in the medium term.
P118150 | Indonesia: Scholarships Prog. for Strengthening Reforming Institutions | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Governance | IBRD | IPF | 2011 | 2018 | 2019 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/682051545327236681/text/Indonesia-Scholarships-Program.txt | http://documents.worldbank.org/curated/en/682051545327236681/pdf/Indonesia-Scholarships-Program.pdf | The following lessons are drawn from the ICR:The approach of staff traininganchored in an agencys institutional development strategy has pitfalls and should be carefully assessed. Aprimary concern is determining the effects on agency capacity; robust outcome indicators should be defined early on. In thisproject, measurement was limited to formal closing of gaps in staff skills, which put the emphasis on the quality of raining thatwas procured.The re-introduction of staff into the internal operating environment should bestructured. The organization should be able to make optimal use of the trained staff. This will require someunderstanding of the value added provided by the training, be it degree or non-degree training. Here,project resultsappear to have been varied, pointing to the neednotonly to identify a skills gap, but to combine that identificationwith some understanding of how the returning trainees could best be utilized.Consideration shouldbe given to the relative cost effectiveness of the training. Training, especially out-of-country and in a highlyranked academic environment, can be costly, and the net value of the training to the organization can even be negative, especiallyif the scholar does not return, or stays only for a short while. In Indonesia, low job turnover in the public sector reducedthis risk, but in higher-turnover environments, returns risk being quite low. Consideration should be given to options,domestic or regional, and always with a good understanding of costs and benefits.
P118152 | Urban Local Government Strengthening Program | Eastern and Southern Africa | Tanzania | IDA | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | PforR | 2013 | 2021 | 2022 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099200012142122424/text/Tanzania000TZ00Strengthening00ULGSP.txt | http://documents.worldbank.org/curated/en/099200012142122424/pdf/Tanzania000TZ00Strengthening00ULGSP.pdf | The operation faced challenges that led to six lessons and recommendations inthe ICR (paragraphs 114-119). Three of theseare presented below with slight modifications: A strong government policy support would benefit the use ofaPforR instrument to strengthenexisting government systems. In this program, government commitment todecentralizationand urbanization was evident during appraisal. Lessons from the preceding operation were incorporated intothe LGDG tousea formula-based, transparent, and predictable system of financial flows to local governments. However,government policy nationalized what used to be local property taxation, a moveaway from decentralization andenhancinglocal resource mobilization. Delays in disbursements from the Ministry of Finance to ULGAs were also a keybottleneck to ULGSP implementation. Performance based infrastructure grants may encourage urbanauthoritiesto improve their performance. In this program, the new UPG window in the LGDGexpanded availableresources for larger infrastructure investment needs of ULGAs. The scoring mechanism for access to UPGs requiredachievingminimum conditions designed tostrengthenULGAsystems. Incentive structures for improved performancewere added to the annual performance assessments including progressive targetsand additional competencies in urban functionsperformed byULGAs such asurban planning, handling of grievances, procurement,and environmental and socialmanagement. The participating ULGAs showed their commitment to strengthened systems by completing their infrastructuresub-projects. The follow on operation, the Tanzania Cities Transforming Infrastructure and Competitiveness (TACTIC)wouldinclude incentives toenhanceinstitutional performance and contribute to financial and socialsustainability. Performancemeasures may be improved to contribute to the sustainability ofinfrastructure investments.In this operation, ULGAs implemented eligible infrastructure investments financedbythe UPGs, a new window under the LGDG system. ULGA performance included budgeting for OM to address sustainability. Otherperformance measures may also have been useful to bolster sustainability of these infrastructure investments. One may specifyindicators along critical junctures in the investment spectrum - from pre- to post-investment phases - that contribute tosustaining these investments. For example, in planning for the infrastructure, more rigorous feasibility assessment may includefinancial viability, selecting appropriate sites, introducing design standards, or potential for private sector participation.Procurement and construction supervision could include quality assurance aspects to complement sustainability features of theinvestments. Close attention to sustainability may mean capacity interventions at preparation beyond familiarization with theassessment process. Introducing prototypical terms of reference for studies, checklists for design standards, and tapping thequality assurance mechanism in place for some national agencies (e.g., NEMC, OSHA) work toward sustaining localinvestments.
P118177 | Pakistan: Sindh Skills Development Project | South Asia | Pakistan | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2011 | 2018 | 2019 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/206401555959935286/text/Pakistan-PK-Skills-Development-Project.txt | http://documents.worldbank.org/curated/en/206401555959935286/pdf/Pakistan-PK-Skills-Development-Project.pdf | The ICR (p. 22-23) provided several lessons learned, adapted herebyIEG: When implementing a new mechanism such as Results-Based Financing, it is critical to allocate sufficient resourcesfor its implementation. In this project, only 20 percent of the project funds were allocated to Results-BasedFinancing despitea lack of experiencein working with such a mechanism, resulting in implementation delays due toadministrative delays in the allocation of funds and release of funds from the line department to the implementingagencies. Supporting a training schemethat has already been established in thecountry is beneficial for ensuring country ownership, taking lessons learned into account and building on already existingexperience. In Pakistan, the BBSYDP had already been implemented for two years, allowing the project design toconsider lessons learned and to build on an already existing trainingstructure.
P118179 | NP Modernization of Rani Jamara Kulariya Irrigation Scheme - Phase 1 | South Asia | Nepal | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2012 | 2018 | 2018 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/334781529515542592/text/Nepal-NP-Rani-Jamara-Kulariya-Irrigation-Proj.txt | http://documents.worldbank.org/curated/en/334781529515542592/pdf/Nepal-NP-Rani-Jamara-Kulariya-Irrigation-Proj.pdf | The ICR (paras 94 to 99) presented several useful lessons and recommendations. The main lessons are presented below with someadaptation of the language: Proper phasing of activities. When infrastructure worksare combined with institutional strengthening and agricultural support, the proper phasing of activities becomes important. Thistends to require coordination across different ministries and departments, and the timely involvement of relevant expertise in theproject office and in the field. Focus on gender. Although the project drew attention to therole of women as water users and Water Users Association (WUAs) members, yet the women faced a number of constraints that need tobe further addressed. For example, the baseline survey of 2013 indicated that women are much less likely than men to own land. Yetland ownership is a precondition for formal WUA membership, including the right to vote on key decisions such as water management,OM, and labor contributions. Currently even the wives of landowning men who left for work in a city cannot participate in WUAdecision making. Furthermore, under the current WUA rules, households need to provide equal amounts of labor contribution for canalmaintenanceindependent of the size of their land holdings. This is likely to create an extra burden for women owning land.More attention needs to be given to such gender-related issues in phase 2. Addressing climaterisks. Climate projections for the region suggest that rainfall is likely to intensify in flood-prone areas, whilewater-scarce regions become even more drought-prone. The phase 1 investments, especially the higher-order infrastructure works forimproved water delivery in the command area (such as improved control of water intake and the more adequate drainage capacity inconnection with the command area protection works), are likely to have helped address some of these climate risks. The activitiesunder phase 2 need to focus on further addressing these climate risks, particularly with the lower-order infrastructure investmentsand the additional command area protection works.
P118187 | Second Education Development Project | Middle East and North Africa | Lebanon | IBRD | FCS | Human Development | Education | IBRD | IPF | 2011 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/902651561833657224/text/Lebanon-LB-Education-Development-Project-II.txt | http://documents.worldbank.org/curated/en/902651561833657224/pdf/Lebanon-LB-Education-Development-Project-II.pdf | Lessons drawn from the ICR, adapted by IEG: Embedding capacity strengthening activities intoexisting institutional processes can help ensure sustainability. In the case of this project, sharing ME results as part ofthe annual review process- for example, the ECERS - helped to ensure use of ME in decisions to update activities.ME data was also used to inform resource allocation decisions at the time of project restructuring. The schoolimprovement process, even with only a modest grant award, can be highly effective if it includes a self-evaluation aspect. In thecase of this project, school administrator training included a self-evaluation process, which identified priority needs and ensureda strong link between the grant funding and actual needs. The self-evaluation can also draw upon results from schoolsurveys. A project can still be effectively implemented in contexts of unanticipated fragility and instability, if thereis flexibility in the project design and a strong, persistent engagement with the client on the ground. In the case of thisproject, restructuring along with additional staff support allowed for a more relevant project design and results framework,additional time for implementation, and responsiveness to changes in government demand and context.
P118188 | Ghana Natural Resource and Environmental Governance - DPO | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | DPF | 2010 | 2011 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/380701474595840851/text/000020051-20140625083557.txt | http://documents.worldbank.org/curated/en/380701474595840851/pdf/000020051-20140625083557.pdf | The ICR identifies a number of lessons:Shifting from investment projects to sector budget support can increase government ownership and improve dialog between agencies. Government buy-in is much stronger when they feel more completely in charge of the agenda and strategic decision making. Dialog between agencies is improved when they work together on budgeting of a joint program with less direct involvement from the Bank.A lack of upfront sectoral strategic and budgetary plans can reduce the impact of sectoral budget support. If they need to be improved, this should be formalized within the framework.A program framework that concentrates on outputs will not be useful during implementation and will be unable to demonstrate results. A framework should be based on sector strategies rather than substituting for them.Development policy lending has limitations when used as the only vehicle of support, and may be more effective when combined with other instruments (such as a technical assistance facility). It may be difficult to achieve policy reform and to improve sector management systems through a single instrument.The dual complexities of a multi-donor approach across multi-sectoral work add significant challenges to design and supervision, and multiply transaction and processing costs. Alternative approaches may have been for different donors to explicitly lead support different technical areas, to differentiate disbursement triggers across donors based on sectoral leadership, or to coordinate donors based on unity of purpose rather than unity of instrument.Complex policy reforms can be hindered by the annual processing requirements of a programmatic DPO with 12 month projects. This design means that there is only a 6 month gap between disbursal of one operation and the delivery of prior actions for the next operation, leaving very little time to discern outcomes from the previous set of actions.IEG also finds that:The need for consensus and harmonization in multi-donor operations reduces the ability to adjust programs during implementation.There is a risk that sharing design and monitoring of program triggers and indicators with other development partners will lead to a system that does not focus on key policy results and/or does not provide sufficient evidence to meet Bank accountability requirements.
P118188 | Ghana Natural Resource and Environmental Governance - DPO | Western and Central Africa | Ghana | IDA | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | DPF | 2010 | 2011 | 2014 | PPAR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/816671468030535916/text/889590PPAR0P1000Box385285B00PUBLIC0.txt | http://documents.worldbank.org/curated/en/816671468030535916/pdf/889590PPAR0P1000Box385285B00PUBLIC0.pdf | 6. Lessons 6.1 The experience of NREG offers a number of useful lessons about using development policy operations for sectoral interventions, about donor harmonization, and about natural resource management. Lessons about Development Policy Operations 6.2 Earmarking funds from a DPO to specific agencies can partly undermine the choice of instrument. It can shift perceptions of responsibility by agencies to the Bank rather than to the government, it can disrupt the relationship between the finance ministry and the line ministries by inserting the Bank, and it can mean that responsibility for the operation is delegated from government to the agencies reducing overall government program ownership. In this case, it led to the program to be implemented more along the lines of investment lending projects at the agency level â€“ though without the financial management, procurement, or safeguards required for investment lending. 6.3 There is a risk that in sectoral DPOs with one-year operational cycles, technical and policy advice to the client can be crowded out by processing requirements. In this program, the short period between disbursement of one operation and assessment of triggers for the next meant that only moderate progress could be made under each operation. Combined with the large number of outputs and targets being tracked, this meant that much of the supervision process focused on verification rather than client support and engagement. A short program horizon also led to selection of very intermediate outcomes for program development objectives, which meant that the program framework and monitoring and evaluation progress were not focused on addressing the main outcomes of concern in the sector (resource degradation, environmental damage, etc.). 6.4 Program documents should clearly distinguish between the description of policy areas and the program being implemented, the specific prior actions and triggers, and the indicators needed to assess performance. Prior actions and triggers are disbursement conditions, meant to represent the elements of the program critical for success or reforms that are politically difficult to produce. A DPO does not need to formally track the production of every output in the program. Creating too many output-oriented targets can cause agencies to focus on producing specific outputs, at the expense of more outcome-oriented policy progress. Outcome indicators should be separate from the disbursement condition verification process, and should be selected to provide useful information to guide the program during implementation, and to allow assessment of progress on broad outcomes of interest. Development policy operations require trust in government that they will do the right thing, rather than a design that micromanages the program. 6.5 In this program, some triggers and targets were useful, while others were focused on outputs of secondary importance that arguably could have been included in the program without being formal disbursement conditions or targets. Some triggers and targets were quite subjective, which added tension to the verification process. 6.6 Sectoral development policy operations may need complementary technical assistance and support. Sectoral DPOs are implemented by line ministries that often do not have the skills or capacity to implement policy reform programs quickly, and so may require high levels of client support and engagement. Donors cannot expect that government will necessarily purchase its own technical assistance with budget support funds\. developing country governments are often reluctant to pay for expensive international experts, even when that technical expertise may be valuable. In this operation a lack of technical assistance arguably led to delays and difficulties in some of the more complex activities, like the design and implementation of the wood tracking system. Particularly in sectors with complex political economy and social dynamics such as natural resource management, a lack of accompanying tools (such as rigorous political economy and/or social analysis) conducted upfront make it difficult to address underlying problems. 6.7 Sectoral development policy operation programs should include a long-term plan for addressing what will happen at the end of the program. If budget support funds are used to significantly increase the budgets of specific agencies, then there are risks that progress will not be sustained when donor support ends at the end of the program. Explicitly planning for the transition period at the end of programs might help to reduce these risks. Lessons about donor harmonization 6.8 Donor harmonization is important, but has tradeoffs. Large, harmonized programs can have higher reach and a greater ability to function as a single platform for sector reform. But coordination between donors adds significantly to preparation and supervision burden, which may reduce the time left for wider stakeholder outreach. A clear and formal division of labor between development partners within the harmonized program could help to reduce this burden and improve the accountability of individual donors. If such agreements are informal then they may not last as staff turnover occurs, accountability may be dispersed, agencies may not focus efficiently on providing specialist expertise, and duplication may emerge. There needs to be a clear understanding and formal agreement between partners about monitoring and evaluation and who in government will be accountable. Harmonized programs may also be less flexible, as the agreement of all partners is needed before major design frameworks can be revised. A key challenge for harmonization is that each agency has its own rules and procedures, and there may be significant differences across agencies in expectations (for example, the Bank's DPO instrument is not the same as sector budget support instruments of other donors). 6.9 Introducing parallel financing into a sector with harmonized budget support can fracture harmonization. It can encourage government agencies to focus on bilateral relationships with individual development partners rather than engagement through the harmonized mechanisms. Lessons about Natural Resource Management 6.10 Civil society can play a useful role in natural resource management if government and civil society groups are able to collaborate productively. This requires government ministries and agencies that are willing to listen and act collaboratively, and civil society groups that can coordinate to focus messages and engage in a productive rather than purely adversarial manner. Donor pressure can have a positive role in improving this relationship. 6.11 Addressing social conflict is important, but progress is difficult to assess without social assessment analysis that describes the causes of conflict and measures conflict levels and changes over time. Tracking tools that are not connected to an ability to take actions may have little impact. 6.12 Creating and publishing environmental ratings of large companies can help to provide public pressure on the private sector to improve their environmental performance. Self-reporting backed by audits and inspections can be a cost-effective means of generating ratings if the process is designed in a way to avoid governance risks, such as by having a clear rules-based methodology for translating data into ratings.
P118196 | Second Dushanbe Water Supply Project | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Sustainable Development | Water | IDA | IPF | 2011 | 2020 | 2021 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/230111617150960342/text/Tajikistan-DUSHANBE-WATER-SUPPLY-II.txt | http://documents.worldbank.org/curated/en/230111617150960342/pdf/Tajikistan-DUSHANBE-WATER-SUPPLY-II.pdf | The ICR (paras. 84to 88) lists a number of lessons learned which are relevant for other projects implemented in similarenvironments.Utility reform takes time andrequires aprogressive combination of infrastructurerehabilitation/modernizationand institutional strengthening. In the case of DVK, gains made under the DWSP needed to besupplemented and reinforced under the SDWSP. Totally, the Bank interventions concerning DVK have spanned 23years..Citizen engagement plays an important part in identifying and sustaining the benefits from projectinterventions. The use of customer awareness campaigns supplemented by periodic Consumer Satisfaction Surveys (CSSs) helpedimprove customer relations and behavior, and enabled DVK to track progress in meeting the intended outcomes.Principalstakeholders need to be proactively involved in acceptance and achievement of project objectives. In the case of the project,both GoT and the Municipalityof Dushanbe were supportive of the project andthe institutional strengthening of DVK,including the implementation of the recommendations of the tariff reform study under the project (ICRpara.84).
P118197 | Alat and Karakul Water Supply Project | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Sustainable Development | Water | IDA | IPF | 2013 | 2022 | 2023 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099535012062237171/text/P118197003da5201a090a503966515f16d1.txt | http://documents.worldbank.org/curated/en/099535012062237171/pdf/P118197003da5201a090a503966515f16d1.pdf | The ICR included five lessons. The following three are emphasized with some adaptation of language:1.Combining a programmatic approach toward incremental sector changescombined with robust sectoral work may strengthen thepotential for successful public sector reforms. Public sector reforms take time, and one has to be realistic about timingand achieving results.Sector reforms also requires strong country ownership combined with tailored Bank-support to the paceof reform in the country. Thishas implications for the lending instruments that best support public sector reforms. Throughthis project andthe Banks engagement in Uzbekistan more generally, sustained support was achieved through a series ofinterventions with a number of credits/loans linked to the Governments medium-term investment program. This approach wassuccessful in achieving gradual sector improvements in the short term and a more ambitious interventionin the long term.Support through modest and selective entry points such as efficiency can show partial success and these can also form the basis forlater progress, even in difficult areas such as public service reform.2. If project readiness is ensuredduring the preparation phase, project delays may be avoided or at least reduced. This projectexperienced several delays, some of which are rooted in the preparation phase. Ensuring project readiness will expedite awarding ofcontracts so that projects can begin immediately, leading to accelerated disbursements and achievement of project outputs on timeand within budget. Initial implementation delays can be reduced by completing more works during project preparation such as (a)preparation of request for proposal for consulting services, (b) approval of feasibility studies by the Government, (c) preparationof tender documents for the first contract packages, and (d) advanced actions for the procurement of consulting services orconstruction contracts.3. Ifenergy efficiency needs isconsidered at the design stage of projects, itmay lead to more climate friendly and sustainable interventions. Energy use is significant in the WSS sector and can oftenbe the single largest energy using sector in a municipality due to pumping requirements. To develop energy-efficient projects, forwater system upgrades, energy audits at the design stage need to be carefully considered to provide a better understanding of afacilitys baseline energy use and help identify additional energy-efficient design elements, and to take into accountmunicipal budgets and operating costs and a municipalitys carbon footprint. While theproject benefitedfromenergy-efficient technologies, suchvariable speed pumps, a technical design flaw was uncovered on the transmissionline, which would have resulted in 50% pump energy savings by increasing the pipe diameter (from 700 to 800 mm).
P118213 | RCIP4 - Regional Communications Infrastructure Program - APL 4 (RI) | Eastern and Southern Africa | Eastern and Southern Africa |  |  | Digital | Digital Development | IDA | IPF | 2014 | 2023 | 2024 | ICRR | >=25 million & <50 million | Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099082323102024792/text/P11821307cc1c003e0bf5709384bc41bafd.txt | http://documents.worldbank.org/curated/en/099082323102024792/pdf/P11821307cc1c003e0bf5709384bc41bafd.pdf | The ICR draws the following three main lessons from the experience of implementing this project.1. A carefulanalysis of political economy considerations of state-owned assets at appraisal may help prevent delays duringimplementation. This is particularly so for countries in FCV settings. This project experienced difficulties bringingtogether key stakeholders for policy dialogue aimed at sector liberalization.2. Prior Government commitment maynot be enough for sustained follow through on key principles agreed for the project. In this project, the Governmentreneged on its commitment to ensure open access. The lesson is that beyond legal covenants and disbursement conditions, it may beuseful to have other mechanisms to encourage the realization of such commitments and reforms, such as budget support programs thatcan accompany the Governments effort to reforms.3. Additional support, particularly on fiduciary matters, mayhelp in low-capacityenvironments. Given the fiduciary issues faced during implementation, the lesson is thatsystematic capacity building on fiduciary issues needs to be incorporated both during preparation and during implementation.
P118239 | Emergency Development Policy Operation | Latin America and Caribbean | Haiti | IDA | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2011 | 2012 | 2013 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/683461474487449988/text/000020051-20140625185441.txt | http://documents.worldbank.org/curated/en/683461474487449988/pdf/000020051-20140625185441.pdf | IEG mainly supports lessons discussed in the ICR. There are two important lessons: Simple and straightforward policy based program to restore institutional functions as fast as possible in a country experiencing major natural disasters (lesson noted in the ICR).Setting priorities to ensure strong government ownership and donor support along the critical path to improved government effectiveness in the immediate recovery period (lesson formulated by IEG).
P118308 | Second Turkey Access to Finance for Small and Medium Enterprises Project | Europe and Central Asia | Turkiye | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2010 | 2015 | 2016 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/802591467989512372/text/ICRR14918-ICRR-PUBLIC-P118308-Box396265B.txt | http://documents.worldbank.org/curated/en/802591467989512372/pdf/ICRR14918-ICRR-PUBLIC-P118308-Box396265B.pdf | The review agrees with three lessons identified in the ICR as summarized below: (i) There is a trade off between expanding SMEs access to long-term finance and maintaining the alignment with business practices for financial institutions: The financial covenants, along with project's fiduciary and environmental requirements increase the transaction costs for PFIs and lead to the financing of only larger and more sophisticated firms. The desire to increase the project's development impact impeded swift project implementation, because of the disconnect between eligibility criteria and disbursement targets in under-served regions. A more effective approach to lending in these under-served regions needs to be considered, in order to address other financing constraints in these regions beside unavailability of financing.(ii) A wholesale lending model is most appropriate for an increased outreach to SMEs: An on-lending design increases the project's overall impact, for the following reasons: (i) a wider range of financial intermediaries increases the number and diversity of potential project beneficiaries and may ultimately lead to funding of under-served firms, (ii) the on-lending design enables new financial intermediaries to gain experience in working with international organizations, which will help them develop other sources of funding, and finally (iii) on-lending encourages healthy competition and causes less market distortion than direct lending, as the benefits are spread over a large share of the financial sector.(iii) Midterm reviews provide opportunities for strengthening a project: Bank teams should take advantage of midterm reviews to assess performance holistically and set expectations for end-project results. Project restructuring may be recommended before midterm review based on borrowers' commitments, changing economic conditions and prior experience with similar operations. While project restructuring can be highly administrative and may put undesired attention on a project, quick restructuring is advisable to avoid losing momentum in project implementation and may yield higher-than-expected results.
P118316 | AFCC2/RI-Lake Victoria Environmental Management Project (Burundi and Rwanda) | Other | Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2011 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/750361559327498718/text/Africa-Lake-Victoria-Phase-II-APL-2.txt | http://documents.worldbank.org/curated/en/750361559327498718/pdf/Africa-Lake-Victoria-Phase-II-APL-2.pdf | The ICR hasfive lessons, three of them are similar to, or the same as, lessons from the LVEMPII APL 1project. The followingare partly derived from the most important of the ICR lessonsbut with adjustments of language.The last two are additional. The level of ambition stated in the project development objectivesneeds to be realistic and attributable even if the objectives arenested within a more ambitious, longer-term,vision,while measurable indicators need to be consistent with those objectives and not inconsistent with a counterfactual. Inthis case, the expectation of water quality improvement in the lake was unrealistic against a deterioratingtrend. Collaboration should be measured not onlythrough agreed end products such as frameworks, policies, and plansbut as improvements at an intermediate outcome level in the following areas:institutional collaborative processes; modalitiesand pathways of communication, qualities of collaborative interactions; nodes of responsibilities; and extent and quality ofsharing of data. In this case, the deliverable frameworks and policies were originally covenanted as outcomesbut were notnecessarilyuseful indicators of changed processes and capacities. In a regional partnership program, it isimportant for realistic planning to examine and understand the political economies and the incentives forindividual partnerswithin each sectorto supportthe proposed reforms and investments. In this case, there were some unrealisticexpectations related to partner incentives for collaborative action. In a long-term lake basin partnership program aimedat enhanced collaboration between partners and agencies, and involving many national players,it is important to ensureownership of investmentsat the level ofnational and local authorities, sanitation companies, asset operators, andcommunity groups. In this case, more could have been done in requiring formal agreements and operating budget commitments and,particularly for the Resource Efficient and Cleaner Production (RECP) activities, more attention could have beenpaidtoperformance incentives. In a long-term program aimed at environmental improvement over a series ofprojects, it is important to treat any one project as a phase in the pursuit of the larger vision and to ensure continuity offunding, staffing, strategy, and institutions. In this case, there were a number of discontinuities including, several years hiatusbetween the first and second project, and now, it appears again between the second and third (in the case of Rwanda and Burundi thefirst and the second). In the total five country program covered by this project and the project supporting Tanzania, Uganda andKenya, there was lack of continuity in the ME system, probably partly due to the hiatus between the first two projects. Bankplanning of long-term programs needs particular focus on sustained support to allow each project to build on the prior project andto ensure cumulative learning. Proactive measures by the supervision team can reduce fiduciary risk in times of politicalcrisis. In this case, there was political conflict in Burundi but the team adjusted quickly, carrying out the MTR off-site, andtightening financial controls which, the ICR notes, could have been taken even further with procurement reviewthresholds. Weak country veterinary systems and weak technical input and coordinationby the Bank can lead tounanticipated consequences with livestock activities. In this case, in Burundi, procurement of goats was not subject to adequatedisease inspection. Significant procurement of livestock in a project calls for veterinary input and tight supervision by theBank.
P118375 | Road Upgrading and Modernization Project | Europe and Central Asia | Belarus | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2011 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/808271490017388797/text/ICRR-Disclosable-P118375-03-20-2017-1490017381594.txt | http://documents.worldbank.org/curated/en/808271490017388797/pdf/ICRR-Disclosable-P118375-03-20-2017-1490017381594.pdf | Three lessons were selected from a list ofseven lessonsidentified by the ICR with some adaptation, asfollows: There is a need for sufficient flexibility in project design. In a case of a sophisticatedclient country, project design as reflected in legal documents needs to consider introducing sufficient flexibility to allow minorchanges without major restructuring and complex approval processes. Monitoring and evaluation design may benefitfrom relying on the existing data monitoring systems. For this project, most of the M E system relied on dataalready routinely collected - the data needed for monitoring the selected indicators was of the type that was normally collected bythe government departments and agencies and thus were easily monitored. The lowest contract bids are not alwayscost-effective and may incur additionla costs during implementation. Based on the experience from Belarus and more widelyin the region,some contractors may present very low prices in winning bids and afterwards delay the execution of worksthrough requests for variations. In addition, when large international contractors obtain awards, they tend to sub-contract asignificant portion of works to local contractors. It is important to verify the past performance of contractors in the region, andbe aware of differences between local legislations and the Banks standard procurement policies.
P118405 | MOLDOVA REGIONAL DEVELOPMENT | Europe and Central Asia | Moldova | IBRD | Non-FCS | Sustainable Development | Water | RETF | IPF | 2009 | 2013 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/642561474593815158/text/000020051-20140626121002.txt | http://documents.worldbank.org/curated/en/642561474593815158/pdf/000020051-20140626121002.pdf | The ICR identified a number of lessons, from which the most striking are summarized below:Leveraging existing Bank projects and implementation structures while designing a new project can be fruitful: When the Bank has ongoing operations, the design and implementation of a new project can achieve important savings by taking advantage of seasoned sector and operational staff and established structures which have been use by closed projects. This arrangement can also leverage the structures and staff of co-financiers and build synergy. Cofinancing carries risks for the Bank and these need to be very carefully appraised. This project had unique financial and administrative arrangement. Since funds for this project were tied to the Financing Agreement between the EC and Moldova, its extension was restricted to the duration of the latter, which meant that grant funds went unused, and the Government had to increase its contribution at a time of fiscal contraction.An integrated approach is warranted when dealing with water projects under CDD projects. For most communities that benefited from access to water supply, the project led to an increase in water connections and consumption in villages. Some beneficiaries installed water flush toilets and washing machines that increases the amount of wastewater produced. As a result, some villages are starting to have issues with managing wastewater. Although this lesson is considered typical for the design of water projects, there is a need to integrate this lesson in the design of social investment funds with water sub-projects, particularly in the case of Community-Driven Development programs.Make certain procurement through International Competitive Bidding is a realistic option considering country risks and project size. Experience in the procurement of the road rehabilitation section â€“ where the total investment was considered too low to attract international bidders but the amount required the use of ICB â€“ revealed the importance of assessing sector entry costs and procurement guidelines to define investment amounts.
P118410 | Mato Grosso do Sul State Road Transport Project | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2010 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/151591495730492459/text/ICRR-Disclosable-P118410-05-25-2017-1495730486150.txt | http://documents.worldbank.org/curated/en/151591495730492459/pdf/ICRR-Disclosable-P118410-05-25-2017-1495730486150.pdf | Three lessons were selected from the five listed in the ICR, with some adaptation: Theimplementation of environmental measures would more effective if these are identified early on and integrated as part of civilworks contracts. Under this project, the issue with land erosion due to inadequate drainage works could not be fullyresolved as the cost of remedial actions was not included in the contract. The experience points to the needfor earlyidentification by the World Bank and/or the client of atypical areas requiring an in-depth environmental plan, including ex-antesite visits by the Bank environmental specialists to ensure the adequacy of planned activities; the need to increase thesupervision role of the regional offices of the road agency, more familiar with local characteristics, in project design; the needto make sure that extensive environmental management knowledge at the central level translates into field operations; and goodintegration of the implementation of environmental measures into constructioncontracts. Sufficient lead time and resources are needed for launching complexinstitutional building components. One of the main reasons for delay in the implementation of technical assistance underthis project was the time required to develop terms of references (TORs) for complex systems and tools. The time and resources wereunderestimated for preparation of TORs by institutions unfamiliar with World Bank procedures and generally lacking the in-housecapabilities for the clear description of goods or services they are procuring. NewInstitutional approaches take time to become accepted and mainstreamed. The project included a pilot projectintroducing the concept of CREMA, a system of performance-based contracts that usually take five or more years. In spite of theproven record of the system in Brazils federal road network and in several states networks, a priori the systemappears more expensive than the conventional ones because the tradeoffs between the short-term benefits of the latter and thelong-term benefits of the CREMA (both in terms of quality and life cycle costs) are not readily evident.
P118423 | Fast Track Initiative Catalytic Grant Fund -2 | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Human Development | Education | RETF | IPF | 2011 | 2013 | 2014 | ICRR | Less than 10 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/193701474590964313/text/000020051-20140626122652.txt | http://documents.worldbank.org/curated/en/193701474590964313/pdf/000020051-20140626122652.pdf | Lessons from the ICR: Good mentoring between a master teacher and a junior teacher and peer learning from each other can contribute to increased teacher effectiveness in a fast-track environment.Lessons from the ICR, adapted by IEG: In addition to improvements in the school environment, educational innovations benefit from a combination of: (i) advocacy and facilitation to help stakeholders and parents learn more about the importance and benefits of the program; and (ii) monitoring of beneficiary satisfaction to provide feedback for the expansion of programs.
P118445 | India: Secondary Education Project | South Asia | India | IBRD | Non-FCS | Human Development | Education | IDA | IPF | 2012 | 2017 | 2018 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/380491529071973473/text/India-IN-Secondary-Education-Program.txt | http://documents.worldbank.org/curated/en/380491529071973473/pdf/India-IN-Secondary-Education-Program.pdf | Lessons drawn from the ICR and adapted by IEG: The sector-wide approach (SWAp) can be an effectivemodality, assuming that strong central government commitment trickles down to decentralized levels (and low fiduciary capacity ismitigated at the decentralized level). In this case, the SWAp instrument contributed to harmonization of donor processes,including monitoring, andlikely reduction intransaction costs, as well asa focus on sector-wide results amongpartners and the government. Embedding ME arrangements in the governments existing systems can bolstergovernments focus on robust ME. However, the quality of the data produced by those systems needs to be sufficientto ensure accurate baseline and target data.
P118531 | Fourth Infrastructure Development Policy Loan | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2011 | 2011 | 2014 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/835061474576042640/text/000020051-20140625184514.txt | http://documents.worldbank.org/curated/en/835061474576042640/pdf/000020051-20140625184514.pdf | The ICR lists several lessons including the need to link performance indicators to development objectives through a results framework. In addition, there are lessons on how to retaining the focus on the overall objectives: with so many indicators, not all equally important, progress on some inputs and the urgent need to specify "prior actions" for the next loan give an illusion of progress.One additional lesson is the need for a thorough a mid-term review that takes stock of any progress, and alerts senior officials in government on what remains for the objectives to be attained. If an important issue was overlooked initially, or framed poorly (e.g. regressive subsidies instead of how to de-politicize electricity pricing), a mid-term review could have introduced it as a prior action for the loan that followed. A series of programmatic loans require mid-course corrections, and subsequent loans should not proceed on autopilot with perfunctory approvals.
P118540 | Santa Catarina Rural Competitiveness | Latin America and Caribbean | Brazil | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2011 | 2017 | 2018 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/764771529071789066/text/Brazil-BR-Santa-Catarina-Rural-Competitiveness.txt | http://documents.worldbank.org/curated/en/764771529071789066/pdf/Brazil-BR-Santa-Catarina-Rural-Competitiveness.pdf | The ICR lists several lessons, particularly focusingon novel instrument adoption. Three of those lessons with a broaderapplication are summarized below with adjusted language:The introduction of novel, complex projectinstruments needs to be carefully prepared and continuously monitored, irrespective of previous country engagements andhistorically demonstrated client capacity. The Bank needs to a priori ensure the readiness and commitment of aclient to adopt an innovative and complex new lending instrument. Technical and administrative preparedness and understanding ofchanges at different levels of project execution is key for a smooth transition and effective execution. Depending on the countrycircumstances, capacity building needs to be regular given leadership transitions and frequent staffturnover.Demand mobilization for new investment support instruments among target beneficiariestakes time and capacity. Beneficiaries need time and customized training to understand and develop demand-driveninvestment proposals. Projects benefit from a realistic allocation of financial and technical resources for early disseminationamong target groups and continuous local technical support for aspired beneficiaries to avoid initial implementationdelays.The organizational capacity of beneficiary groups is a crucial factor in ensuring effectiveexecution of novel demand-driven investments. Strongly organized beneficiary groups are typically better-equipped and moreresponsive to new investment opportunities and can build on a higher capacity in mobilizing resources needed to prepare investmentproposals.
P118560 | Capacity-Building for Palestinian Economic and Regulatory Institutions | Middle East and North Africa | West Bank and Gaza |  | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | SPF | IPF | 2010 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/252081497644584652/text/ICRR-Disclosable-P118560-06-16-2017-1497644572284.txt | http://documents.worldbank.org/curated/en/252081497644584652/pdf/ICRR-Disclosable-P118560-06-16-2017-1497644572284.pdf | The four lessons are drawn from the ICR (pages 53-54), with some adaptation.One, resilient nationalinstitutions are vital to the viability of development projects in fragility, conflict, and violence countrysettings. The four Palestinian Authority institutions supported under this project --- the Palestinian Central Bureau ofStatistics, the Palestine Monetary Authority, the Palestinian Pension Authority, and the Ministry of Finance and Planning --- allfound ways to solve problems under very trying conditions. The PCBS introduced the electronic collection of field survey data inGaza using hand-held tablets. The Gaza-based PPA, responded to the disruptions with business continuity measures,including granting West Bank staff remote access to its work files and databases located at headquarters. The PPA and the MOFP PCUresumed operations fairly quickly after rounds of violence subsided. Institutions that can ably cope with internal challenges andwith external shocks enable development efforts to make headway in difficult settings similar to those faced in the West Bank andGaza.Two, concrete and measurable results indicators are critical to capacity-building and reform-focusedprojects, where the results indicators are often qualitative and subject to varying interpretation. The Bank and theGovernment had to make an extra effort after project effectiveness to craft clear and precise statements of the results indicatorsfor this project, including the baseline conditions and the end-project targets. Greater attention is needed at project preparationto the Results Framework and ME design of capacity building and institutional reform operations to ensure that qualitativetargets are clearly defined and practicably measurable.Three, capacity building and institutional reformoperations may take longer than the project closing date to fully realize their development outcomes, considering the very natureof institution building as a medium- to long-term effort. The project only partially completed the planned outputs andoutcomes for procurement reform, in large part because overhauling the rules and norms by which the Palestinian Authority and itsagencies practiced procurement would be a political process that would take time and effort.Four, agovernment needs to carefully consider the functions and responsibilities it assigns to a project coordination unit, particularlyin a multi-agency operation. The MOFP Project Coordination Unit was burdened with responsibility over many contracts,consultants, and sub-contractors in this four-agency project. The responsibilities of a coordination unit ought to be aligned withits technical capacity, with the organization given sufficient Bank support including through front-loaded training, embedding ofexperts, and more rigorous supervision.
P118561 | CG Rep. Support to Economic Diversification Project | Western and Central Africa | Congo, Republic of | Blend | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2011 | 2018 | 2019 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/714441548270844836/text/Congo-Republic-of-CG-Support-to-Economic-Diversification.txt | http://documents.worldbank.org/curated/en/714441548270844836/pdf/Congo-Republic-of-CG-Support-to-Economic-Diversification.pdf | The ICR (pages 30-32) draws six lessons from the experience of implementing this project. Of these, thefourmost important were as follows (with some adaptation of language).(1) Carefulconsideration of the political economy and macroeconomic conditions isrequired at project appraisal,particularly in the context of a fragile state. In this project, lack of Government Commitment and lack of clarityregarding which of the ministries would be responsible for implementing the project, contributed to the implementation delays inthe initial years of the project.(2) A robust theory of change requires a clear causal chainbetween project activities and expected outcomes, as well as indicators which enable progress in meeting the objectives to bemeasured. No description of the theory of change was included in the original PAD. Addressing this issuewhen theproject was restructured through a Level 1 restructuring would have helped in providinga clearer understanding of projectobjectives.(3) Themodalities for the management ofamatching grant operation needs to be carefully considered at design.The number of steps thatneeded to be taken for administering matching grants need to be carefully articulated. Further,mechanisms such ascommunication with stakeholders and/or using an independent/autonomous firm to manage this activity may be needed, particularly inthe context of a fragile country with likely weaknesses in public administration.(4) The inclusionof a large percentage of total project cost from counterpart funding can pose significant risks to the achievement of projectoutcomes. Given RoCs high oil revenues, the project included a large counterpart funding element which was aimed atensuring government commitment. A significant time elapsed between the collapse in the global oil price during 2014-2016 andactionsremovingcounterpart funding for the financing of this project through theLevel 2 restructuring in2017.Earlier identification of the riskof a decline in oil price could have provided more room for exploring otherfinancing options such as applying foradditional IDA fundingbefore project closure.
P118561 | CG Rep. Support to Economic Diversification Project | Western and Central Africa | Congo, Republic of | Blend | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2011 | 2018 | 2022 | PPAR | Less than 10 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/817281642545191818/text/Republic-of-Congo-Support-for-Economic-Diversification-Project.txt | http://documents.worldbank.org/curated/en/817281642545191818/pdf/Republic-of-Congo-Support-for-Economic-Diversification-Project.pdf | 3. Lessons 3.1 When working with low-capacity clients, especially in countries affected by FCV, design should be simple with a minimum of components and limited requirements for coordination. Slow disbursement of funds and scaling back or abandonment of several activities or components occurred because weak institutional capacity was not adequately captured in the design of the project. This led to delays during implementation, ultimately affecting the achievement of project outcomes. Therefore, the Republic of Congo and the World Bank did not get the maximum net benefit from this project. 3.2 Competitiveness or private sector development projects should focus on the most important binding constraints faced by the private sector, otherwise the businesses or investments they facilitate will not advance. For example, although enterprise survey data at project appraisal indicated that access to finance was one of the four leading constraints to private sector development, it was not addressed through the project. 7 3.3 For investment climate reform type projects, particularly in countries with strong centralized power dynamics, a key champion at the highest level of the government and coordination among the various ministries are crucial to bringing the public and private sectors together and helping identify and implement the reforms needed to improve the investment climate and competitiveness. 3.4 It is crucial for projects involving large counterpart funding, especially in countries where public revenues are highly dependent on natural resources, to consider the risk of commodity price fluctuations for counterpart funding at the time of appraisal and seek to mitigate such risk. 3.5 A matching grant scheme should clearly identify the needs of the beneficiaries at the time of the project design, especially in countries similar to the Republic of Congo that lack an entrepreneurship mind-set, have a large informal sector, and lack funding from financial institutions to firms. In addition, it is crucial for projects to ensure that there is a clear line of separation between the matching grant decision-making process and those running the PIU. 8
P118585 | Ghana: Statistics Development Program (MDTF) | Western and Central Africa | Ghana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2011 | 2013 | 2015 | ICRR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/966681475116980132/text/000012394-20150108150037.txt | http://documents.worldbank.org/curated/en/966681475116980132/pdf/000012394-20150108150037.pdf | Lessons were adopted from the ICR: It is important to have adequate implementation support in place as a requirement for project readiness. Slow project implementation during the first year suggests that the project was not ready for implementation despite claims of project readiness because there was insufficient capacity in the country. Sensitivity in project sequencing to political calendars. Implementation of key activities under the project such as the staff rationalization and retrenchment exercise, integration of staff into other government agencies and definition of an overall training program for GSS were delayed. The retrenchment plan was to be financed under the follow-up project. The Government delayed approval of the follow up project because of sensitivities associated with the retrenchment in an election period. More stakeholder engagement in the staff retrenchment plan would have been essential.Proper sequencing of activities is critical especially in institutional reforms that generally entail information systems development. The ICR notes that (i) training in project management was organized in May 2013, a few months before project closing; (ii) the enterprise architecture (which is essential in projects entailing procedure and organizational reforms) was not envisaged originally and (iii) there was no overall strategic oversight of implementation from Government that included key stakeholders, and (iv) donor funding was not necessarily linked to the Ghana Statistical Development Plan. Close project monitoring facilitates project implementation. The establishment of monthly review meetings with the GSS management to address coordination issues and identify bottlenecks as well as procurement meetings helped accelerate project implementation.
P118585 | Ghana: Statistics Development Program (MDTF) | Western and Central Africa | Ghana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Governance | RETF | IPF | 2011 | 2013 | 2016 | PPAR | Less than 10 million | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Negligible | http://documents.worldbank.org/curated/en/854661472715924111/text/106283-PPAR-P118585-PUBLIC-ppar-Ghana-0816.txt | http://documents.worldbank.org/curated/en/854661472715924111/pdf/106283-PPAR-P118585-PUBLIC-ppar-Ghana-0816.pdf | 10. Lessons 10.1 Among the lessons derived from this review are\. Â· To provide the public with relevant and reliable statistics, the national statistical office needs a responsive governing body to give strategic direction. Of particular importance is the presence of directors who represent the interest of data users â€“ researchers, development partners, academicians, students and policy makers. Ghana once had such a guiding hand; it was called the National Advisory Council for Producers and Users of Statistics. With the help of this project and its successor, an active Board is now at work at GSS. Gradually, capacity at GSS is being built. In addition, a governing body like NACPUS is expected to be established, once the Statistics Bill, which has been dormant for four years, is approved by parliament. Â· In supporting corporate or institutional reform agenda, it is essential to ensure orderly, efficient and effective implementation to minimize the impact on staff. It requires meticulous design, thorough consultations, adequate funding and the supervision of specialists. In particular, by failing to include the funding for redeployment and retrenchment, the project held up the completion of corporate reforms for years. Â· It helps to ensure that all the technical assistance services are in place before the project is presented to the Board. This was not the case with this project. After it became effective in February, 2011, GSS was unable to get an expert to advise on the World Bank's procurement simply because it did not know how to use the World Bank's procurement to hire that expert. To address this issue, the World Bank has offered the use of Project Preparation Facility, which can be drawn on before the project becomes effective. But the World Bank Unit of the Ministry of Finance in Ghana noted that the PPF is seldom, if ever, used in the country. The reason, according to Ghanaian officials familiar with the PPF, getting approval for the PPF is as complex and time consuming as getting the underlying project through the Board. Â· Despite the large role that the World Bank has played in mobilizing international support for statistical development, the capacity of the World Bank team to deliver results in this area should not be taken for granted. Under this statistical capacity development project, much was made of the limitations of counterpart agencies in Ghana, based on multiple needs assessments sponsored by the World Bank. Even though the World Bank team appeared to be well qualified and to possess the right skill mix, project results were modest. As discussed throughout this report, the quality of project design, preparation, implementation and supervision all fell short of the norms for Bank operations. Â· The check-list approach to monitoring and evaluation, as applied in this project, does not work. The results framework relied exclusively on administrative data (disbursements) and outputs (reports) of various activities to indicate the extent of progress made. No interim variables were chosen or developed to track progress.
P118593 | WBG Support for Fiscal Sustainability and Public Financial Management | Middle East and North Africa | West Bank and Gaza |  | FCS | Equitable Growth, Finance and Institutions | Governance | SPF | DPF | 2011 | 2011 | 2012 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/747701474574838201/text/000020051-20140625081541.txt | http://documents.worldbank.org/curated/en/747701474574838201/pdf/000020051-20140625081541.pdf | Coordinated Bank support, with clear objectives, reasonably ambitious actions and conditions, and good donor collaboration can generate results even in difficult and challenging situations.By focusing on the same key policy areas through the series of three quick disbursing DPGs, the Bank strengthened the likelihood that the results would be delivered and increased the chances of sustaining the results.
P118597 | CN Integrated Economic Development of Small Towns | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | IPF | 2012 | 2019 | 2020 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/678201582041595811/text/China-CN-Integrated-Eco-Dev-of-Small-Towns.txt | http://documents.worldbank.org/curated/en/678201582041595811/pdf/China-CN-Integrated-Eco-Dev-of-Small-Towns.pdf | Following lessons are adapted from ICR (pages 36 and 37). Avoid PDOs that are layered, broad andhard-to-measure. Since project success is measured against its intended PDOs, unattainable PDOs set a project up forfailure - even if all investments are completed in time and of good quality. The project experience shows that publicinfrastructure and services require an adequate number of years to show measurable economic impacts. To show measurable impact bythe end of the implementation period, the PDO for this project would need to have been formulated in more intermediateterms. In countries with central and provincial government structures, it is important to securecentral governments commitment and support in designing and implementing multi-province operations. The decision ofthe National Development Reform Commission to withdraw from the coordination of provincial level activities early on in the life ofthis project life and the cancellation of the matching national program adversely impacted project performance in terms ofimplementation and cross learning. Avoid setting up project implementation units (PIUs) at very lowlevels of government without sufficient higher-level monitoring and control. In this project, most town-level PIUs provedto be too weak in authority, severely understaffed, and limited in technical capacity and project management experience to beeffective implementors of a World Bank project.
P118610 | Project Preparation Technical Assitance Facility Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Transport | IDA | IPF | 2010 | 2018 | 2018 | ICRR | >=50 million & <100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/342191529512481218/text/Vietnam-VN-Project-Preparation-TA-Facility.txt | http://documents.worldbank.org/curated/en/342191529512481218/pdf/Vietnam-VN-Project-Preparation-TA-Facility.pdf | The ICR (p. 29-30)lists severallessons, adapted by IEG: A technical assistance/capacitydevelopment project requires detailed preparation andtimeto deliver results and measureableoutcomes.Even though a short preparation time can show strong commitment by both, the government and the Bank, itmight result in design shortcomings. This project was prepared and appraised within 10 months. However, there were severaldesign shortcomings such as a complicated institutional set-up, weak implementation capacity at the Ministry of Planning andInvestment (MPI) and decentralized agencies, and in the projects Results Framework. Allowing more time for projectpreparation might have helped to identify challenges linked to theseareas. Formulating and identifying outcome-oriented indicators to measure progress indeveloping capacity at different institutional levels is challenging. In this project, the Results Framework did notadequately measure the progress towards the achievement of the PDO.It waschallenging to define easily monitorableoutcome indicatorsto assess progress in strengthening capacity at variouslevels. Strong supervision is critical for implementing technical assistance/capacitydevelopment projects. Field-based task teams may facilitate implementation of TA projects, allowing for frequentcommunication and engagement. MTRs should be used effectively and external views may be beneficial in identifying opportunities andoptions for change and adjustments that may strengthen implementation and impact.
P118636 | Samoa Economic Crisis Recovery Support Credit | East Asia and Pacific | Samoa | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2011 | 2012 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Negligible | http://documents.worldbank.org/curated/en/560811474587297041/text/000020051-20140625054027.txt | http://documents.worldbank.org/curated/en/560811474587297041/pdf/000020051-20140625054027.pdf | The experience of this credit indicates that the tool of direct budget support can be effective in supporting recovery from natural disasters if the government has a rehabilitation agenda and is committed to it. The experience also shows that if these conditions are present the risks of program failure when supporting a government that has limited capacity are likely to be low.The experience of Samoa shows that the Bank can use the knowledge of other people and other organizations to design a program of support for recovery from natural disasters that is effective and timely.
P118647 | China: Anhui Shaying River Channel Improvement Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2011 | 2018 | 2019 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/748151538347830675/text/China-CN-Anhui-Shaying-River-Channel-Improv.txt | http://documents.worldbank.org/curated/en/748151538347830675/pdf/China-CN-Anhui-Shaying-River-Channel-Improv.pdf | The following two lessons are adapted from several general lessons/findings in the ICR: An inland watertransport (IWT) project is likely to be successful whenplanned in coordinationwith road/rail modes, national/locallevel policiesand upstream/downstream development. This IWT project benefited from policy and planning support andinvestments towards waterway transport as well assupport to competitiveness of water-based transport over rail or roadways bythe Government. The pre-conditions were set to provide adequate demand for the increase in IWT capacity, at the national level tosupport underdeveloped provinces with connectivity and increase in economic trade and at the provincial level to increase thenavigation capacity of specific river channels, which lead to further transfer of goods to other modes oftransport. A demand analysisis critically important forinland watertransport projects. This project benefited from upfront consultation and confirmation of projectactivities by usersof the Shaying river channel i.e. shipping companies, associations of logistic companies, manufacturers. During the project period,there was a significant increase in the number of water transport enterprises, port operators, and shipbuildingenterprises.
P118701 | Bangladesh - Employment Generation Program for the Poorest | South Asia | Bangladesh | IDA | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2011 | 2014 | 2016 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/537841468186528939/text/ICRR14790-P118701-Box393191B-PUBLIC.txt | http://documents.worldbank.org/curated/en/537841468186528939/pdf/ICRR14790-P118701-Box393191B-PUBLIC.pdf | Three lessons -- all presented in the ICR (pp. 34-35) -- are highlighted here. They are all well grounded in the evidence presented:1. The adoption of a Disbursement-Linked Indicator framework can be very effective in keeping the focus on output, outcomes, and results and ensuring continuity in the dialogue between the Government and the Bank. The DLI framework included all the relevant indicators (with the exception of the vulnerability measure to be collected through the impact evaluation). It forced a clear articulation of a complete results chain and the definition of a rich M&E framework. It also kept the dialogue going and focused on results.2. A diverse and complete set of evaluation mechanisms ensures proper documentation of results and can help overcome unexpected shortcomings. In addition to the M&E framework, the project had planned for independent evaluations, including an impact evaluation, spot checks, qualitative assessments, and external validations. When it became clear that the new M&E framework could not be put in place on time, spot checks allowed for positive feedback loops to identify areas in need of course correction. Moreover, different indicators could be collected with the most appropriate means (for example, the vulnerability measure through impact evaluation).3. Strong project design and proper stocktaking of existing experience allows for introduction of innovations and can ensure better inclusion of specific groups. This project's design focused on marginal, but significant improvement in an already promising government program under implementation. It introduced an innovative payment system. It introduced not only a quota, but also greater attention to working conditions favored by women to increase female participation. It also took notice of existing evaluations of the previous version of the program to introduce improvement.
P118708 | Bangladesh - Health Sector Development Program | South Asia | Bangladesh | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/114181528922648368/text/Bangladesh-BD-Health-Sector-Development-Program.txt | http://documents.worldbank.org/curated/en/114181528922648368/pdf/Bangladesh-BD-Health-Sector-Development-Program.pdf | Lessons drawn from the ICR (pp. 31-32) include:Managing pooled funds forhealthIt is observed that in large programs, with multiple pooling partners, effective coordination andconsultation mechanisms among the Bank, development partners (DPs), and government are essential to avoid fragmentation/duplicationof efforts, reduce transaction costs, and align project objectives to a countrys development needs.TheProjectenhanced coordination and consultation mechanisms among DPsby conducting joint missions and providingcoordinated technical assistance with different partners leading different themes. The establishement of the Local ConsultativeGroup on Health also improved coordination and harmonization of DPs support.DLIs and incentivestructuresEffectiveness of the disbursement-linked-indicator (DLI)approachis attenuatedwhenbudgetary incentives are only partly associated with the achievement of results.In this project, the governmentbudget for the HPNSDP was pre-financed by the Ministry of Finance at the beginning of each fiscal year, which reduced theeffectiveness of the incentive structure of a project with DLIs.
P118713 | Peru Third Programmatic Environmental Development Policy Loan | Latin America and Caribbean | Peru | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IBRD | DPF | 2011 | 2014 | 2017 | ICRR | >=50 million & <100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial |  |  | Five lessons are drawn from the ICR (pages 32-36), with some adaptation.One, strengthening environmentalgovernance by public institutions and mainstreaming environmental sustainability in private industry are long-term processes andneed considerable time to implement. The ENVDPL benefitted from the decision to structure the ENVDPL1 as a deferred drawdownoperation (DDO), which kept ENVDPL1 active for five years, well beyond the original one-year life of the operation. The longer timeperiod accorded the Bank the opportunity to systematically help strengthen the institutional capacity of the Government, enablingpublic agencies to meet the prior actions of the reform program.Two, building a reform program requiresextensive analytical work, including not just of the technical and the institutional but also the political economy dimensions ofthe reform effort. Perus Country Environmental Analysis (CEA) of 2007 served as the organizing analytical documentunderpinning the environmental management reform plan advanced by the ENVDPL. The CEA thoughtfully: examined the shortcomings ofthe national environmental management system in the country, and identified priorities that were consistent with thecountrys development agenda and could be linked to poverty reduction.Three, government ownership is essentialto the effective implementation of policy reforms. Political commitment was secured across the spectrum of agencies responsible forenvironmental management in the country, and at key levels of the organization in these public agencies. The top-line agenciesresponsible for implementing the reforms measures --- MEF, the newly created MINAM, PRODUCE, MEM, and MTC --- were individually andcollectively committed to the reform agenda.Four, framing poor air quality as detrimental to poverty reduction helpscatalyze action to address the air pollution problem. The negative effects of air pollution were demonstrated to be significantlyhigher on the poor and on the vulnerable in Peru --- women, the elderly, and children. Poor air quality stunted productivity andeducational performance, constraining the opportunities of the poor and the vulnerable for economic advancement. By highlightingthese findings, the Government succeeded in raising an awareness of the air pollution problem and in mobilizing a broad base ofstakeholders for the ENVDPL to address the problem.Five, measures to address MELs need to be constantly evaluated.The Government completed all the measures designed to completely identify MELs and to commit resources to remediate the high-risksites. Yet, mining-related social conflict has not decreased in Peru, where at least a fourth of the social conflicts in 2008-14were mining-related. The 2016 study Peru: Policy Options to Enhance Environmental Sustainability in the Mining Sectoridentified five issues: the fear of pollution; competition over land and water resources; cultural and social issues that are notadequately addressed, leading many communities to oppose mining activities; the asymmetry of power relations between industry andthe communities; and, the lack of confidence among communities that the Government can adequately protect the environment.
P118737 | Energy Efficiency Facility for Industrial Enterprises | Europe and Central Asia | Uzbekistan | Blend | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2010 | 2024 | 2025 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/750541525389739814/text/Uzbekistan-ENERGY-EFF-INDUST-ENTERPRISES.txt | http://documents.worldbank.org/curated/en/750541525389739814/pdf/Uzbekistan-ENERGY-EFF-INDUST-ENTERPRISES.pdf | The following lessons were derived from the ICR (ICR, pages 20-21):1. Policy support andgovernment commitment are critical for projects introducing innovative, transformational EE initiatives. In the reviewedProject, conducive Presidential and Government Decrees and resolutions, such as Government Decrees PP-2343, provided incentives andguidance for IEs to implement EE measures, creating demand and removing technical barriers for EE investment. This experiencedemonstrated that innovative EE investments, when combined with policy dialogue, technical assistance, and the development of legaland regulatory framework, can lead to transformative impact.2. Adequate monitoring of EE investment projects thatuse credit lines to banks and sub-lending to enterprises requires well-defined ME procedures and related significant capacitybuilding for banks and sub-borrowers. In the reviewed Project, PBs had incentives to monitor financial performance of thesub-projects but not energy savings, which was theProjects main outcome indicator. Missed opportunities included: (i)unclear ME responsibilities for all parties; (ii) lack of clear guidelines for PBs and IEs on measuring energy savings(including via pre- and post-investment energy audits); (iii) insufficient monitoring by the PCU of sub-project implementation,sub-project reporting quality, and energy audits; and (iv) inadequate capacity building on energy savings verification for the PCUand PBs. Apart from energy savingsME issues, tracking IEs co-financing and some other outcomes was alsoinsufficiently guided. Better ME procedures to measure and verify inputs and outcomes of EE investments would have enhancedProject efficiency and outcomes. 3. Customized capacity building for banks andsub-borrowers is critical for EE investment projects that use credit lines to banks and sub-lending to enterprises. In thereviewed Project, opportunities to maximize EE potential through capacity building was missed, such as (i) enhancing PBscapacity in marketing, pipeline development, safeguards reviewing, screening, and reporting; (ii) implementing targetedcapacity building for IEs; and (iii) conducting energy audits for selected companies to provide best practice examples to othermarket players. The Project would have benefited from allocating a portion of the loan for essential TA activities identifiedduring Project preparation.
P118779 | Pakistan: Tertiary Education Support Project | South Asia | Pakistan | Blend | Non-FCS | Human Development | Education | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=100 million | Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/572681529415603286/text/Pakistan-PK-Tertiary-Education-Support-Project.txt | http://documents.worldbank.org/curated/en/572681529415603286/pdf/Pakistan-PK-Tertiary-Education-Support-Project.pdf | The ICR (p. 29-30) provided a number of lessons, which IEG has synthesized and prioritized asfollows:Shifting the higher education sector to an accountability-oriented model will requirebetter monitoring and evaluation data. The prior operation began the process of focusing on accountability that wascontinuedwith thisprojectand a follow-on investment.The completion report suggested the importance ofallocating public recurrent and development grants based on observable and measurable outcomes, which implies a need forbetter monitoring and evaluation indicators than were utilized in this operation.Strongerpreparation may have facilitated better implementation, as issues not resolved were bottlenecks toimplementation. An updated capacity assessment of HEC was not conducted at entry - thus, capacity wasoverstated. Clarity was also lacking on how to operationalize the budgetary transfer of money from the Ministry of Finance tothe Secretariat. As a result,technical assistance and implementation were delayed. The Operational Manual wasprovided to the Bank a year after effectiveness.
P118783 | Vietnam Managing Natural Hazards Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IDA | IPF | 2013 | 2020 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/712681593464124942/text/Vietnam-VN-Managing-Natural-Hazards-Project.txt | http://documents.worldbank.org/curated/en/712681593464124942/pdf/Vietnam-VN-Managing-Natural-Hazards-Project.pdf | The ICR (p. 32-33) provided several lessons learned, of which the following are selected for their relevance for similar futureoperations: Long-term engagement for building resilience facilitates learning. This projectwas part of a multi-phased programmatic approach and built on activities initiated under the previous project, the NDRMP.Successful activities were scaled up under this project, allowing for learning and innovation. Introducing newapproaches such as an integrated river basin approach can be challenging and complex but will have long-termimpacts. This project introduced eight river basins plans which were supported by MARD and the Vietnam DisasterManagement Authority (VNDMA), resulting in this approach being continued to be supported by two new World Bank projects (theEmergency Reconstruction Project and the Dam Safety and RehabilitationProject). Bringing a System Integrator on board at an early stage is critical for hydrometprojects. In this project, the System Integrator was based in the country and was available for technical supportand system integration, allowing for the identification of technical, administrative, and capacity bottlenecks and providing theopportunity to address them in a timely manner. Increasing resilience through a three-ponged approach whichincludes investments in infrastructure, CBDRM, and early warning systems are complex and challenging. However, such an approach isinnovative and effective and has the potential to be scaled up. This projects design strengthened resiliencethrough improving weather forecasting and early warning systems, which complemented community-based disaster preparedness andsmall-scale infrastructure activities with investments in large high-priority infrastructure activities.
P118806 | Sri Lanka - Second Health Sector Development Project | South Asia | Sri Lanka | IDA | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/665021576857571288/text/Sri-Lanka-LK-Second-Health-Sector-Development.txt | http://documents.worldbank.org/curated/en/665021576857571288/pdf/Sri-Lanka-LK-Second-Health-Sector-Development.pdf | This ICR Review concurs with the followinglessonsfrom the ICR (p. 31): Verification is a crucial partof the use of DLIs as a disbursement mechanism. Verification of DLIs should be plannedthoroughly, and the verificationmethodology should be made robust and simple to allowfor straightforwarddisbursement of funds. Given that third-partyverification arrangements can be relatively costly, it is best to try to build in that role and capacity within thegovernments own institutional arrangements. While gender issues in the health sector areusually viewed fromthe lens of improving access to women,the experience of this project shows that mencan bethedisadvantaged group when it comes to NCD care utilization. Concerted effortscan berequired to improve accesstothe public health system for men. Measures such as extending the hours of outpatient clinics through the evening, setting up HLCsin work places, and increasing the number of mobile medical units with HLCs can help resolve thisissue.This ICR Review alsoconcurs with the lesson related to the use of DLI mechanisms notedby the borrower (ICR, p. 59): While DLIs can be an important positive factor in project implementation, it isimportant to match the pace of the DLI targets and release of funds with implementation progress on theground.Based on review of the ICR,ICR Review alsoconcludesthat: Strongly aligning aproject with acountryssector strategyreduces transactioncosts and the reporting burdenon the client government.However,a projectneeds tobedesignedcarefully to maintain clearfocus, boundaries, andscope,and to ensure thatit includesindicators and targetsmeasuring what specificallycanbe achieved with project support. Theuse of DLIs as disbursement mechanism incentivizesa project team tofocus particularly on reporting progress on DLIs andon the outcome and intermediate outcome indicatorsthat are in the results framework. While these indicators arecriticalfor progress reporting, it is importantnot to overlook the entire results chain, and toreporton plannedactivities and outputs.
P118814 | Lao Sixth Poverty Reduction Support | East Asia and Pacific | Lao People's Democratic Republic | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | DPF | 2010 | 2011 | 2014 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/662231474634349460/text/000180307-20141201111524.txt | http://documents.worldbank.org/curated/en/662231474634349460/pdf/000180307-20141201111524.pdf | IEG concurs with the lessons derived by the ICR, including the importance of:(1) Complementarity between policy and institutional dialogue through PRSO and existing investment and technical assistance projects is critical for the success of reforms.(2) Adapting to the political economy of reforms, identifying champions in government with a reasonably well-defined reform agenda and engaging with a broader range of actors, and selecting focused sector engagement were PRSO work has a clear comparative advantage.In addition to these lessons from the ICR, IEG notes the importance of selecting performance indicators, ex ante, which can be benchmarked and monitored.
P118826 | India: Bihar Integrated Social Protection Strengthening Project | South Asia | India | IBRD | Non-FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2014 | 2021 | 2022 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099135001192219089/text/India000IN00Bihar0Social0Protection.txt | http://documents.worldbank.org/curated/en/099135001192219089/pdf/India000IN00Bihar0Social0Protection.pdf | The ICR (p. 17 to 18) provided useful lessons learned: Remaining flexible and proactive is important foradjusting costing associated with exchange rate fluctuations. In this project, the Bank team reacted well to thefluctuations by restructuring the project and adjusting its costing. Projects that aim to strengtheninstitutional capacity in a low-capacity context require time to put in place necessary capacity across all tiers of government.In this project, capacity needed to be built in financial management, procurement, disbursements, safeguards, and HRresulting in implementation delays.
P118838 | Agricultural Productivity Assistance Project | Europe and Central Asia | Kyrgyz Republic | IDA | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2011 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/363651468949693157/text/ICRR-Disclosable-P118838-07-19-2016-1468949682008.txt | http://documents.worldbank.org/curated/en/363651468949693157/pdf/ICRR-Disclosable-P118838-07-19-2016-1468949682008.pdf | The ICR included five lessons. The following two are emphasized with some adaptation oflanguage: Aprojectsdesign needs to ensure that designed activitiesare consistentwitha borrowersimplementation capacity. This project experience showed thatthe keyreason fordelay in project implementation was that some of the project interventions were beyond the implementation capacity of thestakeholders. In particular, the lack of financial and technical capacity within Kyrgyz Hydromet led to protracted delays inreaching agreements and taking actions. This slowed the pace of project progress and forced an extension of the closingdate. Dissemination of information through a public awareness program is important foruptake of project activities and foradoption of new or improved agricultural technologies.In this case, inthe early stages of project implementation, CSF membership was not at expected levels as the PublicUnion of CSFs, the organization in charge of overseeing the functioning of CSFs, had weak outreach capacity. Once it hired socialmobilizers to disseminate the benefits of membership in all seven oblasts, the network of CSFs began to expand rapidly and theproject was able to bring a larger than expected number of beneficiaries into its fold. The following lessonis added by IEG: AResults Frameworkneeds to be amended early enoughto capturesignificantimplementation shifts. When there is unanticipated demand for certain activities, new ME indicatorsmay need to be introduced to capture a new set of impacts. In this project there was an unanticipated high demand for livestocksub-loans which turned out to be much larger than the planned loan sizes yet the benefits from these activities were not adequatelycaptured due to thelack of relevant indicators.
P118858 | Ghana Statistics Development Program | Western and Central Africa | Ghana | IDA | Non-FCS | Equitable Growth, Finance and Institutions | Poverty and Equity | IDA | IPF | 2012 | 2019 | 2020 | ICRR | >=25 million & <50 million | Satisfactory | Moderately Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/374301584737416364/text/Ghana-GH-Statistics-Development-Program-FY11.txt | http://documents.worldbank.org/curated/en/374301584737416364/pdf/Ghana-GH-Statistics-Development-Program-FY11.pdf | The following lessons are taken from the ICR, with some adaptation of language by IEG: Delays inproject approval can increase project costs. The potential for delays can be reduced by addressing risks up frontduringproject design. In the case of this project, thelengthy delay reduced resources available for the project.Collaboration between stakeholders raises the chances of project success. In the case of this project, close stakeholdercooperation was enhanced through the establishment of a steering committee and could serve as a model for other projects of thistype. The effective prioritizing and sequencing of key activities, including capacity development to upgrade staffskills, can result in strong ownership on the part of country counterparts. In the case of this project, this prioritizationmaximized the use of project resources.IEG adds the following lessons:Assessing project effectiveness can best be addressed through careful indicator design. In the case of this project, notincorporating an indicator to determine the extent to which the improved statistics were being used in policy and analysis limitedthe ability to assess project impact. Using international indices as outcome indicatorscan beof limitedusefulness. First, they often only become available with a lag and are therefore of little use in monitoring progress. Second, theyare not customized to the specific circumstances of the country or specific project. Using the Statistical Capacity Index in thecase of thisproject added little to the understanding of project achievements.
P118870 | Sri Lanka: Emergency Northern Recovery Project | South Asia | Sri Lanka | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2010 | 2014 | 2015 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/231821467998764808/text/ICRR14679-P118870-Box393183B-PUBLIC.txt | http://documents.worldbank.org/curated/en/231821467998764808/pdf/ICRR14679-P118870-Box393183B-PUBLIC.pdf | 1. A cash for work program implemented in a post-conflict or emergency situation provides an opportunity to deliver immediate relief while taking the opportunity to consult with the affected community to discern their priority economic and social needs. Community based infrastructure that is delivered in centralized or supply-side manner is less likely to be owned or sustainable managed by resettled communities. Consultation should be broad-based: it should allow for the meaningful participation of women and allocation of economic and social assets that are in line with their needs. The same lesson holds true to the most vulnerable (landless, disabled etc.) persons in a post-conflict assistance operation. World Bank projects should report on the differentiated assistance that was received by these different groups. 2. Reporting on the number of persons resettled in a a World Bank assisted resettlement program is insufficient; project reporting should include the quality of the resettlement process, the preferences and concerns of the displaced, issues pertaining to access and equity, restitution (housing and land) and the manner by which grievances were handled. The Northern Recovery project in Sri Lanka mainly reported on the number of persons that were resettled, without indicating where they were being resettled from, and the number and area of assets and land that were distributed or restored, without reporting on access or interim impacts (negative or positive). 3. A project that is designed to support social reintegration of a minority group in a post-conflict situation should develop interventions that directly address the drivers of the group's exclusion. In the case of Sri Lanka, the Northern Recovery Project would have had to address the cultural and linguistic barriers faced by the returning population.
P118904 | Learning, Equity and Accountability Program Support Project | East Asia and Pacific | Philippines | IBRD | Non-FCS | Human Development | Education | IBRD | IPF | 2014 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/404061575914666532/text/Philippines-Learning-Equity-and-Accountability-Prog.txt | http://documents.worldbank.org/curated/en/404061575914666532/pdf/Philippines-Learning-Equity-and-Accountability-Prog.pdf | IEG has synthesized the lessons presented in the ICR to the following:Using withinbudget financing to support improvements in the education system can also support improvements in countrysystems. This operation employed disbursement-linked indicators (DLIs) to finance a mix of activities, outputs, andoutcomes.The DLIs supported appropriate policies for improving early reading and numeracy. These policies have been adoptedand institutionalized.Appropriate design of DLIs is an important issue for TTLs.In the case of this project,aclear understanding of how country systems operated was lacking during preparation, resultingin limited flexibility for thegovernment, implementation delays,and the need to address during restructuring.The use of a verification process is animportant complementof DLIs.Follow-up support is critical component to teachertraining.One-off training is ineffective.For this reason, the Department of Education introduced a blendedapproach to teacher training that combined the original cascade training with school-level activities through School LearningAction Cells (SLACs). The new plan allowed smaller groups of teachers from each school to participate in division-level trainingand then return to their schools and deliver training to other teachers through the SLACs. This was envisioned as a method ofimproving teacher quality; however, teachers still reported a need for mentoring or follow-up support, which the literature showsis critical.Includingstudent learning in a project development objective isfeasible.The project used internationally recognized tools to measure reading and math improvement, since trackingimprovements is critical.The project demonstrated that it is possible to improve learning outcomes, and thus, feasible tohave an ambitious PDO (i.e. improved student learning).However,an evaluation with a control group is neededtoattributeobserved outcomesto project interventions. In addition, monitoring and evaluation must also clearlydefine and measure target groups.
P118916 | Indonesia Infrastructure Guarantee Fund Project | East Asia and Pacific | Indonesia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2013 | 2019 | 2020 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/209741571764343315/text/Indonesia-Indonesia-Infrastructure-Guarantee-Fund.txt | http://documents.worldbank.org/curated/en/209741571764343315/pdf/Indonesia-Indonesia-Infrastructure-Guarantee-Fund.pdf | Three lessons are drawn from this operation.Governmentsshould work to strengthen the institutionalcapacities of government contracting agencies and project sponsors to prepare, screen, and appraise PPP projects. Inthis project for Indonesia, it was not enough to strengthen the institutional capacity of the IIGF to advance the development andfinancing of infrastructure PPP projects in Indonesia. The project exposed gaps in the institutional capacities of governmentcontracting agencies, as well as project sponsors, to adhere to international standards for environmental and social safeguards forinfrastructure projects. The inability of the contracting agencies to meet the safeguards requirementsdefined in theoperations manual forced the IIGF to withdraw the application of twoprojects that would have otherwise qualified forBanksupport of IIGF guarantees.Governments will needto better define the roles ofvarious institutions in the PPP market tohelp build a more robust pipeline of infrastructure PPP projects. Inthis project for Indonesia, the government may want to start reviewing the mandate of, and the services offered by, the IIGF goingforward. The ICR (page 30) reports that the IIGFhasnot been allowed to issue guarantees to PPP projects that havealready been awarded to project developers. This not only limits the base from which the IIGF may consider projects eligiblefor guarantees, italso constraints the ability of some projectdevelopers to obtain risk products offered by theIIGF. The government may also want to start re-examining the role of the IIGF relative to state-owned enterprises andstate-sponsored infrastructure finance companies operating in Indonesia.The Bank will need tostrategically and systematicallyinvolve the otherBank Group institutionsto help country clients betterdeveloptheirinfrastructure PPP market. In this project for Indonesia, the IFC should be able to helpspursustained private sector interest, both domestic and foreign, in Indonesias infrastructure PPP program. ThePalpa Ring project would have required a guarantee of US$500 million, an amount which was well beyond the size of the Banksfinancing. The IIGF is reportedly exploring the participation of MIGA in the guarantee for this project. The Bankitself may want to consider acting as a co-guarantor, together with the IIGF, of infrastructure PPP projects; the arrangementshouldgive the Bank a greater role in helping identify, prepare and appraise projects at the outset of project developmentrather than at the end stage of guarantee appraisal, hence imparting the IIGF with greater knowledge and experience withinternational standards for infrastructure PPP projects.
P118925 | Afghanistan: Sustainable Development of Natural Resources Project II | South Asia | Afghanistan | IDA | FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2017 | 2018 | ICRR | >=25 million & <50 million | Unsatisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/692941523628294631/text/Afghanistan-Afghanistan-SDNRP-II.txt | http://documents.worldbank.org/curated/en/692941523628294631/pdf/Afghanistan-Afghanistan-SDNRP-II.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.(1) A strong portfolio of resource development projectsthrough smaller investmentscan be helpful to both the government and the investor. This would aid in enabling regulatory and contractcompliance.(2) Government ownership is important for ensuring success. The implementation of this projectwas undermined by the frequent changes in leadership in the ministry.(3) Long term engagement for sustainablereforms is likely to be be required in the extractive industry sector. While the Bank engagement has been facingsignificant challenges regarding projects in Afghanistan, the experience of this project showed that it is critical to maintainsome level of engagement and then rapidly scale up investment when the political economy environment becomes moreconducive.(4) The project design should address issues related to absorptive capacity, particularly in weakenvironments. The decision to cancel some parts of the grant was mainly on account of the low absorptive capacity in thecountry context.(5) Strong donor coordination is required at the outset of project preparation to avoid duplication.This is particularly so in the case of resource rich but fragile countries where there is likely to be significantdonor-funded activities.
P118931 | Philippines Development Policy Loan to Foster More Inclusive Growth | East Asia and Pacific | Philippines | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2011 | 2012 | 2018 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/345331509719524414/text/Philippines-PH-Development-Policy-Loan.txt | http://documents.worldbank.org/curated/en/345331509719524414/pdf/Philippines-PH-Development-Policy-Loan.pdf | The ICR distills the following main lessons: A programmatic multi-year DPL can provide an effectiveplatform to support reforms and institutional development. Complementary knowledge and technical assistance, as well asclose coordination among different teams and partners are vital for results. ME frameworks need to take into accountdata gathering constraints. When supportingenhanced fiscal management, acareful balance needs to bestruckbetween the risks and criticality of supporting legislative reforms, and between revenue and expenditure in budgetmanagement reforms.IEG concurs with these lessons, which are grounded in the experience of this operation. Inparticular, given the complex political economy in the Philippines,they underscore the importance of broad consultation andconsensus building thatneeds toinvolve the legislature from the outset in the discussion ofcritical policyreforms, when these depend on legislative endorsement.
P118974 | MAURITANIA - Skills Development Support Project | Western and Central Africa | Mauritania | IDA | Non-FCS | Human Development | Education | IDA | IPF | 2011 | 2018 | 2019 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/850871544649345062/text/Mauritania-MR-Skills-Dev-Support-Project-FY11.txt | http://documents.worldbank.org/curated/en/850871544649345062/pdf/Mauritania-MR-Skills-Dev-Support-Project-FY11.pdf | Lessons drawnby the ICR (Lessons, page 33): A competitive fundingmechanism can effectively promote demand-driven skills development and training. In the case of this project, thecompetitive selection process for providers of short-term training courses helped to fill current gaps in the labor marketidentified by small industries and TVET providers themselves. The involvement of the private sector in theupstream identification of training needs can increase the relevance of training provided and thus insertion rates forgraduates. In the case of this project, outreach efforts were directed to small industries to ensure their inputinto training programs and form partnerships to facilitate eventual placement of graduates.
P118979 | Coastal Resources for Sustainable Development Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2012 | 2019 | 2020 | ICRR | >=50 million & <100 million | Highly Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/359301571924282654/text/Vietnam-VN-Coastal-Resources-for-Sustainable-Dev.txt | http://documents.worldbank.org/curated/en/359301571924282654/pdf/Vietnam-VN-Coastal-Resources-for-Sustainable-Dev.pdf | The ICR highlights four lessons which are of relevance for similar projects:1. Integrated spatial planning hasproven to be an effective tool for improving planning of coastal areas. This was achieved in the projectthrough inclusion,consultation, participation, and information-sharing between related sectors, as has the decentralization of roles andresponsibilities from the central to the provincial levels.2. Introduction of the GAP (Good Aquaculture Practices) zonescan lead to cooperation among small farmers. In this project small farmers undertook collective action to improve biosecurityinfrastructure, environmental monitoring, disease risk management, and outbreak containment. Through use of appropriate technologythey demonstrated clear benefits in reducing shrimp disease risks and improving survival rates and also increased yields and farmprofitability.3. Co-management in near shore areas along provincial coastlines resulted in increased fishermensincomes and more sustainable fisheries. This process included mass information and awareness campaigns, local participation andtraining, strategic public sector support in preparing and implementing Co-management Plans (CMPs), infrastructure upgrading, andmonitoring, control, and surveillance (MCS) strengthening together with the promotion of alternative livelihoods can result inincreased incomes and more sustainable production from coastal capturefisheries.4. In principle, shifting fishers toalternative forms of employment can reduce pressures on fisheries. However, experience from this project indicatesthatincluding a sub-component in this regardadds complexity to the project and suggests that a longer timehorizon may be needed in order to achieve results at scale. It was thus recommended that alternative livelihood initiatives shouldinstead be integrated in broader local government socio-economic development plans and supported through separateprograms.In addition IEG draws the following lesson:5. The project illustrates how the Banks mobilization ofexternal specializedtechnical assistance -- both for aquaculture and near-shore coastal fisheries --during both preparationimplementation, in this case from the FAO Cooperative Program, can contribute positively to its successful outcome,especially considering that this was the first Bank operation for the fisheries sector in the country. This is an example of goodpractice.
P119039 | India Low-Income Housing Finance | South Asia | India | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2013 | 2019 | 2020 | ICRR | >=100 million | Satisfactory | Satisfactory | Satisfactory | Satisfactory | Modest | http://documents.worldbank.org/curated/en/107651580140655017/text/India-IN-Low-Income-Housing-Finance.txt | http://documents.worldbank.org/curated/en/107651580140655017/pdf/India-IN-Low-Income-Housing-Finance.pdf | The ICR draws the following main lessons from the experience of implementing this project, with some adaptation oflanguage.(1) TheBank should encourage innovation and take calculated risks in order to create new marketssuch as housing finance for informal and low-income households. The approach of this project was untested in India andother low-income markets and the Bank assumed a calculated risk in approving the project as a pilot for providing housing financefor informal and low-income households.2) Addressing demand side constraints is necessary but needs to becomplemented with supply-side reforms forlow-income housing benefits. This projects interventions targetedmainly the demand side constraints ofimproving access to housing finance. These need to be complemented with supply-sidereforms (such as access to water, sanitation and electricity), for sustained improvements in housing for the low-incomepopulation.(3) The Bank should adopt the Environmental and Social Due Diligence (SEDD) framework as aninstitutional framework to ensure efficient and sustainable safeguards in housing finance projects. The experience of thisproject demonstrated that setting the SEDD framework as an institutional framework between the NHB and the PLIs, combinedwith sample-based loan-level monitoring can be an efficient and sustainable way to ensure compliance with environmental and socialsafeguards.
P119043 | India: Scaling Up Sustainable and Responsible Microfinance | South Asia | India | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IBRD | IPF | 2010 | 2016 | 2017 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/839161474489824970/text/ICRR-Disclosable-P119043-09-21-2016-1474489817329.txt | http://documents.worldbank.org/curated/en/839161474489824970/pdf/ICRR-Disclosable-P119043-09-21-2016-1474489817329.pdf | The ICR identified a long list of ten lessons, but the majority of them are either findings or recommendations, exceptthefollowing two, with which IEG concurs:(i) Ownership by the borrower andits implementing andsupporting agencies is cardinal foragood projects performance:The support of the Government and theRBI after the crisis, and the role playedby the RBI in developingregulations to foster responsible finance, largelycontributed to the depth of achieved reforms.SIDBI, the implementation agency, played also an important roleinfacilitating the uptake of reforms and for making the project-supported initiatives sustainable over time.(ii)A lenders forum can be a useful tool to spearheard needed reforms in the countrys financial sector:The lenders forum was used to bring microfinance stakeholders together in order to share responsibilities towardeffective approachin frontier lending. However, to establish common standards for lending, a more normalinstitutional structure is needed in order to help develop codes for lending,assess performance and monitor actualimplementation, and thisrequires a strong political commitment.IEG identified an additional lesson asfollows:(iii) A weak ME design can significantly affectthe projects implementation andperformance: Throughoutthe project design and implementation,the Banks team did not succeed to have aclear and appropriate results framework. Thisshortcoming has affected theME arrangements and implementation, andhas strained both the assessment of the project, and even thedialogue between the Bank and the client as regards to theproject evaluation.
P119047 | Financial Sector Rapid Response Project | South Asia | Afghanistan | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2012 | 2020 | 2021 | ICRR | >=10 million & <25 million | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/311341614703894397/text/Afghanistan-Financial-Sector-Rapid-Response-Project.txt | http://documents.worldbank.org/curated/en/311341614703894397/pdf/Afghanistan-Financial-Sector-Rapid-Response-Project.pdf | Three lessons are drawn from the ICR (pages 20-21), with some adaptation.The developmentoutcomes of project interventions are likely at risk without proactive steps to ensure their post-project operationalsustainability. In this project, the card and mobile payment switch at the AfghanistanPayments System remainsunderutilized. The Automated Transfer System is half-operational. And the Collateral Registry has not been adequatelymaintained. The lesson is that measures for strengthening operational sustainabilityinclude: (a) cost recovery schemes;(b) options to shift responsibility over operational costs to government budgets; and (c) legal covenants mandating national ratherthan donorresponsibility over operations. Incentives for banks to participatein anAutomated Payment Systeminclude: (a) afee structure that incentivizesthe timely submission of payment transactions; (b) collateralizedliquidity support to mitigate liquidity risk; and (c) settlement guarantee mechanisms.The complexity ofprojects needs careful consideration in fragile and conflict-affectedsettings. In this project, the creationof a new modern national payment system tested not only the political commitment of the government and the institutional andtechnical capacity of the central bank but also the business judgment of banks and financial services providers and the operationalability of technology suppliers and technical consultants to bid for projects and deliver on contracts. More extensiveplanning and stakeholder consultation at the design stage, including for contingencies in a wide range of adverse conditions, wouldhave helped the government and the Bank prepare for a rough project implementation. However, scaling down the scope and scaleof the project to what could be reasonably achieved in a fragile and conflict-affected setting would have been a betteralternative. In this project, the central bank was loaded with too manymandates compared with its staff and financialcapacity. The lesson is that reducing the scope and scale of a project to what can be reasonably achieved in an fragile andconflict-affectedsetting is the best strategy.The inability to contract for, and to obtainthe delivery of, quality consulting services can derail the implementation of technical assistance-intensive projectactivities. In this project, the contracting for consultant services proved to be difficult, delaying the deliveryof technical assistance to key institutions and derailing the initiation and completion of several project activities.According to the ICR (page 20),problems withthe procurement and delivery of consulting services werenot unique tothis project but areprevalent across Afghanistan owing to the difficult security situation in the country. The lessonis that at project design, consideration needs tobe given to permittingconsultants to use technology (audio and videoconferences, remote communications, rather than in-person appearances) to deliver technical services, encouraging consultants, whowould otherwise be deterred by difficult travel and living arrangements, to bid for projects. Another lesson, duringimplementation, was that more extensive use of the hands-on extended implementation support mechanism, in whichthe Bankdeploys a dedicated procurement specialist to provide close support to implementing agencies throughout the procurement process,can be a successful option.
P119051 | Support to IAVI-Sendai Vector | Other | World |  |  | Human Development | Health, Nutrition & Population | RETF | IPF | 2010 | 2016 | 2017 | ICRR | Less than 10 million | Highly Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | High | http://documents.worldbank.org/curated/en/686941483050133672/text/1483050132795-0000A8056-ICRR-Disclosable-P119051-12-29-2016-1483050128374.txt | http://documents.worldbank.org/curated/en/686941483050133672/pdf/1483050132795-0000A8056-ICRR-Disclosable-P119051-12-29-2016-1483050128374.pdf | The ICR (pp. 16-19) offers several in-depth and insightful lessons, including:As the Bank launches the PandemicEmergency Financing Facility, there are important lessons to be learned from its earlier experience in financing vaccine,antiviral, and antibiotics research. As that experience is relatively limited, in this case the mature and comprehensivetechnical expertise of the grantee (IAVI) was key.Openness and flexibility help manage events in an environment that isalmost always unpredictable. In this case, close collaboration and communication helped the team to deal with situationsinvolving identification of new sites for clinical trials and emergence of unanticipated results from a similar immunizationapproach as clinical trials were being initiated.
P119063 | Ghana Greater Accra Metropolitan Area Sanitation and Water Project | Western and Central Africa | Ghana | IDA |  | Sustainable Development | Water | IDA | IPF | 2013 | 2026 | 2021 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/998061595252778758/text/Ghana-GH-GAMA-Sanitation-and-Water-Project.txt | http://documents.worldbank.org/curated/en/998061595252778758/pdf/Ghana-GH-GAMA-Sanitation-and-Water-Project.pdf | The ICR (para 104) lists several relevant lessons and recommendations including: Effective design andimplementation of a strategy for improvement in sanitation and water supply requires an integrated approach and coordinationbetween the key agencies involved. The establishment of a dedicated central government Ministry of Sanitation and WaterResources (MSWR) with a dedicated unit for LIUCs was a key factor in turning around implementation progress under the project byhelping provide direction, coordination and resources. Local governments have a key role toplay in strengthening environmental sanitation and water supply services and mechanisms need to be provided for ensuring provisionof the required technical assistance and advisory support. In the case of the project, the use of the CL4D services from the Bankproved to be effective in overcoming obstacles to implementation of some of the key components of the sanitation program,particularly household toilets. The employment of dedicated Environmental Health Officers (EHOs) in the MMAs was an importantcontributor to supporting project implementation. Affordability concerns can precludethe poorer households from participation. Despite levels of subsidies of up to 70 percent provided by the MMAs, the pooresthouseholds were often not able to participate. Appropriate funding mechanisms need to be established for providingadequate levels of targeted subsidies and direct contributions as warranted in the specific circumstances.
P119071 | Hubei Xiangyang Urban Transport | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | IBRD | IPF | 2012 | 2020 | 2020 | ICRR | >=50 million & <100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/602721593210625379/text/China-CN-Hubei-Xiangyang-Urban-Transport.txt | http://documents.worldbank.org/curated/en/602721593210625379/pdf/China-CN-Hubei-Xiangyang-Urban-Transport.pdf | Based on lessons noted in the ICR the following stand out as being broadly relevant to other similar projects - with someadjustments in their presentation.Land acquisition and resettlement are complex actions thatrequire good advance work during project preparation and appraisal. The main reason forresettlement delays in this project was the lack of coordination between the PMO (which was responsible for road construction), theXiangcheng District Government (which was responsible for land acquisition), and the Xiangcheng Urban Investment Company (which waswas responsible for the construction of resettlement housing). This was overlooked during the initial stages and caused majordelays, as did the fact that this project was only one of the many tasks for these institutions, and their work for the project wasnot planned and coordinated and also not synchronized with the projects timeline. The lesson is that closecoordination among the different authorities responsible for land acquisition and resettlement is critical for the projectssuccess and needs to be envisaged and planned in the PAD.The requirements needed to apply newmethods of results measurement must to be understood and fully incorporated in the ME framework. The project used arelatively new way of measuring transport impact by including accessibility as an indicator in the Results Framework. This couldadd to the project by allowing a different understanding of transport issues. In this project there was insufficent understandingof the required baseline and a relevant definition of accessibility. There was also insufficient capacity to have available thedetailed geographic travel information to allow accessibility to be calculated, in anything other than a simplistic way; either atappraisal or completion. The lesson is that where best efforts are made to initiate new techniques, these must be understood andcompletely thought through to be used even on a trial basis. If on a trial basis, then it should be identified as such, andprobably not form part of the main Results Framework.
P119077 | URBAN WATER SUPPLY AND WASTEWATER | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Sustainable Development | Water | IDA | IPF | 2011 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/346791607117671782/text/Vietnam-VN-Urban-Water-Supply-and-Wastewater.txt | http://documents.worldbank.org/curated/en/346791607117671782/pdf/Vietnam-VN-Urban-Water-Supply-and-Wastewater.pdf | Inexperienced implementing entities may require periodic, customized, technical assistance to build theircapacity to achieveproject objectives. In this project, constructingwastewater systems was delayed because ofthe introduction of new processes for which the implementation entities were not prepared, such as the preparationofsanitation strategy plans before implementingthe environment sanitation sub-projects. In addition to the capacity buildingcomponents of the project itself, additionaltechnical assistance efforts wereincluded in consulting packages to addresscapacity gapsof implementing agencies, particularly those unfamiliar with World Bank processes. Informationand educational campaigns may influence behavioral change in households to address theirreluctance to connecttowastewater systems.In this project, the outcome indicator called for increasing the number of householdsconnected to the wastewater system. Households who used septic tanks or public drains and who did not appear to be negativelyaffected by wastewater discharge were disinclined to connect to the system without the incentives that other households received.The project financed household connections to the wastewater systemsand technical engineering solutions but didnotdevise educational campaigns or behavior change strategies to increase the level of householdconnections. Engaging beneficiaries may improve the data productivity and utilization of a projectsME system.In this project, the quality of beneficiary information under theME system was inadequate.The implementing agencies could not monitor performance of the utilities and outcome of the project interventions using beneficiaryinformation. Data disaggregated by relevant factors. could not be collected. Engaging beneficiaries through periodic customersurveys could strengthen the usefulness of anME system, refinebeneficiary selection for outcomeattribution,facilitate decision making, and bring transparency in sector service delivery.
P119085 | IN National Ganga River Basin Project | South Asia | India | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2011 | 2022 | 2023 | ICRR | >=100 million | Satisfactory | Moderately Unsatisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/099062923174522092/text/P119085060f5a10740b628078e07720803b.txt | http://documents.worldbank.org/curated/en/099062923174522092/pdf/P119085060f5a10740b628078e07720803b.pdf | (Reference ICR paras. 107 to 112).The ICR lists a number of lessons derived from the Project experience whichhave relevance for similar projects carried out in comparable environments. From these, IEG derives the followinglessons:1. A mismatch between the ambition of the Project and the absorptive capacity of the client canbedetrimental to implementation. The Project was initially conceivedas the first project in the long-termprogram for rejuvenation of the Ganga. However, in response to the GoIs wishes, the Projects ambition wassubstantiallyincreased, and the result was that the expandedProject was oversized in relation to the absorptivecapacity of the client. A lesson learned is that a Series of Projects/Multiphase Programmatic Approach could be better suited tothe absorptive capacity of the client and to help ensure improved implementation with satisfactory results.2.Support of higher-level political champions may facilitate building momentum for change, but achieving development outcomesrequires an appropriate administrative architecture and operational/field level champions. In the case of the Project,project implementation in the earlier years was adversely affected by the limited capacity and mandate of the nodal ministryinitially assigned the responsibility for project oversight. Switching of the nodal ministryresponsible to one adequatelyequipped and empowered to meet the needs of the Project was a critical step in improving project implementation.3.Creation and strengthening of new institutions takes timeand a steady and iterative increase in staffing, mandate,authority, and experience from learning-by-doing. There were prolonged delays in implementation in the earlier years ofproject implementation. But with progressive increases in staffing, authority, and experience, the implementing agencies (NMCG andmost of the SPMGs) were able to function effectively in the later years of project implementation. Project design needs to takeinto account adequately the time and resources required for the institutions to become effective and the associated implicationsfor implementation.4. The HAM-PPP model, jointly developed by the World Bank and IFC, is an important contractualinnovation for the wastewater sector by helping tackle the challenge of adequate OM operations and contributing to enhancedoperational sustainability. The experience under the Project indicates that the model worksand is scalable andreplicable. It has the potential to be used in other parts of India and countries with comparable environments.
P119090 | Hospital Waste Management Support Project | East Asia and Pacific | Viet Nam | IBRD | Non-FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2011 | 2020 | 2021 | ICRR | >=100 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/207021599676395146/text/Vietnam-Hospital-Waste-Management-Support.txt | http://documents.worldbank.org/curated/en/207021599676395146/pdf/Vietnam-Hospital-Waste-Management-Support.pdf | The following lessons werederived from the lessons presented in the ICR.Aligning project investment planswith provincial plans, preparing them up-front, and having them reviewed by multiple provincial stakeholders increases provincialownership. This project based its investments on the provincial plans for facility investment and then appliedadditional filters to ensure the efficiency and equity of the subset of project facilities. The project also highlighted theeffectiveness of using the provincial project management units under the provincial Departments of Health for projectcoordination.Coordination between the Ministry of Health, environmental agencies, and provinces enhancescollaboration andimplementation efficiency. Public environmental agencies, consulted during design and construction,supervised, monitored and inspected treatment systems as a condition to issue permits for waste discharge; and they advisedprovincial peoples committees in plan approval and promulgation for collecting, transporting and handling hazardous wasteand coordinating with all actors and stakeholders on plan implementation.Targeting the more visible problems andengaging people living close to the hospitals right from the outset are effective approaches for informing and involving thepublic, and for achieving results. The project invested in 40 health care waste management systems that wereincluded in the Prime Ministers blacklist of seriously polluted institutions (mentioned in Section 4 under Policy andinstitutional environment strengthening). These hospitals met the national environmental standards and were removedfrom the blacklist. Trained hospital staff had improved capacities to reach out to the communities. Early engagement ofsurrounding populations from the projects outset incited their involvement in monitoring the implementation and operationsof the systems; and surveys of their opinions provided timely feedback to hospitals on the performance of thesesystems.Results-based financing takes time for concerned agencies and staff to understand and implement,especially in a highly decentralized context. Lack of experience and skills in results-based financing at the outsetwas an important reason for the implementation delays during the early years of the project. In retrospect, more intensive,up-front capacity building for project management, through training and recruitment of qualified staff and the careful design ofinstitutional arrangements, may have alleviated implementation issues and delays.
P119140 | 4th Northwest Mountainous & Forested Areas Development Project (PNO4) | Middle East and North Africa | Tunisia | IBRD | Non-FCS | Sustainable Development | Agriculture and Food | IBRD | IPF | 2011 | 2017 | 2018 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/868291530232911418/text/Tunisia-TN-4th-NW-Mount-Forest-Area-Dev-PNO4.txt | http://documents.worldbank.org/curated/en/868291530232911418/pdf/Tunisia-TN-4th-NW-Mount-Forest-Area-Dev-PNO4.pdf | The ICR presented four lessons. Theyhad some shortcomings because they wereeither not based on evidence in theICR or were recommendations rather than lessons. The following three potential lessons summarized below are stimulated by thelessons presented in the ICR.1. Mitigating and preventing the degradation of natural resourcescombined with investments in livelihood improvements stimulates community interest in improved natural resourcemanagement. Thislesson did not come out clearly from the ICRbecause the ICRdid not detail howtheCommunity Development Plans (PDCs) were developed by communities, how investments were prioritized, and most importantlywhat was the linkage established between livelihood improvement, economic activities and natural resources preservation andmanagement. Without this more detailed information on arrangements and processes adopted by thePDCsand the provisionofincentives for the PDCsto improve natural resource management, the lesson is not likely to bereplicated.2. A project aimed at improving livelihoods needs to have technical support to developappropriate flexible financing products and instruments to link smallholder farmers to credit resources. The projectfailed to link smallholder farmers tofinancing institutions due tothe political instability in country at the time ofimplementation, but also because of a lack of appropriate financing instruments that were affordable and accessible forsmallholders. The ICR suggested that if technical assistance had been provided under the project to advance development ofappropriate financing instruments for smallholder farmersthe outcomes would have been better. However, there was no evidencein the ICR on which to base this lesson and, consequently,this is more a recommendation than alesson.3. Community-driven development projects can contribute to decentralization bypromoting participatory development initiatives. Lessons from the PNO4 on defining priorities in a participatory mannerand allocating budgetsto these prioritieshave been utilized already in many countries. The ICR suggesteda lessonthat promoting decentralization reforms, such as the establishment of innovative funding mechanismsusing communal investmentfunds (with various funding windows ranging from social objectives,infrastructure development,to economic empowerment),were proven to be useful in this project as also already evidencedin some countries in Africa.
P119214 | Iraq Fiscal Sustainability Development Policy Loan | Middle East and North Africa | Iraq | IBRD | FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IBRD | DPF | 2010 | 2011 | 2012 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/930781474509773220/text/000020051-20140625184427.txt | http://documents.worldbank.org/curated/en/930781474509773220/pdf/000020051-20140625184427.pdf | The experience demonstrates that policy operations can work well in a high risk environment when governments are motivated by fiscal stress, but that the sustainability of achievements is uncertain if the fiscal stress is removed. It also shows the importance of a mutually reinforcing package of properly sequenced analytical work, technical assistance, policy lending, and assistance from other donors.
P119307 | Cash Transfer Project | Middle East and North Africa | West Bank and Gaza |  | FCS | Human Development | Social Protection & Jobs | SPF | IPF | 2011 | 2018 | 2019 | ICRR | >=10 million & <25 million | Satisfactory | Satisfactory | Highly Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/950641560110250637/text/West-Bank-and-Gaza-West-Bank-and-Gaza-Cash-Transfer-Project.txt | http://documents.worldbank.org/curated/en/950641560110250637/pdf/West-Bank-and-Gaza-West-Bank-and-Gaza-Cash-Transfer-Project.pdf | IEG highlights the following lessons, selected from the many presented in the ICR. The ICR emphasized theimportance of collaboration and coordination among partners in the provision of social assistance, as well as the importance ofstrong partnership with the client. The ICR also highlighted the positive role played by sustained funding and technical support incontributing to the achievement of project objectives, as well as the value of an effective MIS system in providing a robust basisfor reliable data analysis and sound project recommendations. Finally, the ICR observed that cash transfer should be an instrumentof last resort for those who need it the most (the extreme poor) to cover basic needs, and that governments should carefullyconsider the costs associated with maintaining cash assistance programs in the long run, as donor assistance may not be providedfor extended periods of time.IEG places particular emphasis on the ICRs lesson thatdrawsattention to the importance of a communication strategy when designing CTPs and the need to clarify procedures and responsibilitiesfor officials, provide training and training materials on complaints handling, and develop systems that ensure all complaints arecaptured and can be addressed. This lesson resonates with IEGs 2016 paper - Introducing a Framework for Evaluating ServiceDelivery in Sector Evaluations - in which the need for communication and feedback loops in service delivery is considered tobe critical to solution-focused, adaptive implementation.
P119308 | AGRICULTURE SECTOR SUPPORT PROJECT | Western and Central Africa | Cote d'Ivoire | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2014 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/713081554142030771/text/Cote-dIvoire-CI-Agriculture-Sector-Support-Project.txt | http://documents.worldbank.org/curated/en/713081554142030771/pdf/Cote-dIvoire-CI-Agriculture-Sector-Support-Project.pdf | A few lessons, adapted from the ICR are below:Longer term governance goals areoften lost in the context of project implementation infragile and/or post-conflict situations, whereby focusing on short tomedium term objectives of building infrastructure and capacities appear toproduce immediate results - The projectwas successful in building the productive infrastructure and assets but fell short in enhancing institutional organization,decision making, and strategic stakeholder alliances / IPOs.It is important to choose anappropriate financing instrument to achieve the goal of institutional transformation - for example would theuse ofProgram-for-Results (PforR)financing be more effective than Investment Project financing (IPF) for the stated goal -The two IPOs that secured accreditation (INTERCOTON and AIPH) from the Ministry of Agriculture and Rural Development (MINADER) hadthe advantage to be institutionally advanced compared to the other value chains. To have a full impact, specific institutionalchanges needs to be conceived and imbedded as part as country reform programs with a longer-term horizon, and hence a PfoR type offinancing instrument may be moreappropriate.It is important to have clear delegation from theGovernment for institutional strengthening of the inter-professional organizations or IPOs - Stronginvolvement of the Government in development operations limits the ability of IPOs to flourish and also limitstheagricultural sectors efforts towards private sector led growth. This lesson seems to be relevant to the country context as perthe task team.Asole focus solely on achievements that can be easily measured is likely toignore monitoring of the extent to which the project is achieving its development outcomes -When implementing aproject, the final development outcomes to be achieved should always be kept in mind as well as the process to achieve the requiredchanges.
P119308 | AGRICULTURE SECTOR SUPPORT PROJECT | Western and Central Africa | Cote d'Ivoire | IDA | FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2014 | 2018 | 2023 | PPAR | >=25 million & <50 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099306303292311596/text/SECBOS07377729088095ef0a5be24a0e30d.txt | http://documents.worldbank.org/curated/en/099306303292311596/pdf/SECBOS07377729088095ef0a5be24a0e30d.pdf | 3. Lessons 3.1 Project relevance and efficacy are enhanced by aligning projects with national strategies, building on existing institutional mechanisms and stakeholder consensus, and supporting ongoing activities. The PSAC adequately built on past and contemporary agricultural strategies, policies, and projects in CÃ´te dâ€™Ivoire. Its financial leverage enabled the scaling up and reinforcement of ongoing activities and working modes of the public, private, and cooperative institutions operating within the sector. This alignment ensured that the PSAC addressed relevant challenges on productivity, market access, and sectoral governance and realized a substantial impact despite its short time span. Comparatively limited achievements on improving governance underlined the importance of widespread buy-in and consensus across all stakeholders on the extent of institutional reforms during project appraisal. 3.2 Project efficiency and sustainability are enhanced by ensuring continuity in coordination and management staffing from design through implementation to postproject internalization. Limited involvement of PCU staff during PSAC design implied a transfer in ownership at the projectâ€™s start and consequent implementation delays. Conversely, the governmentâ€™s involvement during PSAC implementation was more limited than foreseen, with regard to both senior leadership in the steering committee and technical focal points across departments. After closure, the PCU was completely dissolved instead of integrated within government structures. Ultimately, this led to weak capitalization on achievements after project closure. 3.3 Projects with short time frames need to set realistic goals on institutional development and governance improvement, while adapting to institutional and political risks, to be effective. The PSAC underestimated the complexity of, and the time required for, enhancing sectoral organizations and governance. Professionalizing cooperatives and IPOs into sustainable structures, while cementing good governance principles within the sector, is known to be a long-term process requiring elaborate support programs. Moreover, project implementation showed that institutional development critically depends on contextual factors, such as broad government buy-in and commitment to reform, and the governmentâ€™s human and financial resource capacity. 27 The project duration needs to be correspondingly adapted and its objectives calibrated to realistically achievable goals along an institutional development pathway. 3.4 Effective institutional development requires elaborate methodologies and monitoring frameworks, instead of merely end goals and flexible ad hoc approaches. The PSACâ€™s methodology for enhancing sectoral organizations and governance was only approximately specified and was frequently implemented through ad hoc approaches for selected stakeholders, whereas the monitoring framework lacked indicators on cooperative and governance achievement. Consequently, institutional development achievements were limited and, to the extent they were achieved, poorly quantified. Effective institutional development and governance improvement require in- depth prior assessments, detailed and systematic methods for institutional reinforcement across all stakeholders, and a comprehensive monitoring framework with process-based outcome indicators. This requires sound capacity and expertise on the part of the World Bank team and the government and development partners, for example by involving institutional specialists. 3.5 Reinforcing the role of IPOs and producer cooperatives in agricultural value chains requires fulfillment of key prerequisites. Strengthening IPOs into accredited, recognized, and professionalized development partners can be a commendable approach on its own, but its utility could be questioned if other conditions remain unfulfilled. The experience of this project showed that buy-in from both the state and the private sector on a well-defined and well-balanced demarcation of roles and powers is needed to avoid a dynamic of competition, adversity, and conflict. It was also apparent from this project that a solid and loyal base of professionalized cooperatives is required to ensure true representativity. It also leads to a more equitable power distribution throughout the value chain, which is further promoted by total transparency between different actor groups. Strengthening producer cooperatives is equally contingent on a set of conditionalities, including well-defined strategies and procedures, an explicit choice on the cooperative type to be supported, and adequate certification and compensation modalities. 3.6 A diverse set of productivity enhancement interventions can support overcoming challenges of rural poverty, lack of competitiveness, demographic pressure, and land scarcity. The PSAC made significant strides in improving agricultural productivity, through increasing access to improved planting material, and providing technologies for enhanced labor productivity. Productivity enhancement provided opportunities in keeping up agricultural production with demographic growth, despite limited opportunities for agricultural land expansion. Importantly, to guide which productivity innovations are deployed and where, profound ex ante knowledge of the production base is essential, especially for perennial crops. 28 3.7 Sustainability of project achievements can be compromised if contingencies among development pathways are not recognized. The long-term goal of increasing producer incomes is typically conditional on simultaneous advances in multiple development pathways, such as increased productivity, improved market access, and strengthened governance. In the case of the PSAC specifically, further improving value chain governance will be critical to preserve progress made on productivity and market access. 3.8 A pilot project is only truly useful if capitalized on by the government. In view of limited financial resources and the fragile postcrisis context, this project appropriately applied an integrated intervention package in confined pilot areas to identify promising activities for progressive expansion. However, during design and implementation, it failed to develop strategies and mechanisms to achieve this expansion after project closure. In parallel, the government did not establish the support structuresâ€”adapted to its actual human and financial resource capacityâ€”required for expansion after closure. As a result, rather than expanding project successes beyond the pilot areas after project closure, certain achievements on increasing productivity and market access were reduced or lost. 3.9 Co-financing provides critical leverage and ownership; however, sustained effects require co-management and arrangements for postproject continuation. The PSAC combined financial resources from a range of public and private partners to multiply its impact. Although co-financing can empower partners by enhancing their capacity and project ownership, this is a complex process involving distribution of powers and frequent negotiations on operations and budget allocations. The time required to achieve an equitable co-management dynamic often exceeds the short duration of a project. Moreover, the PSAC demonstrated that abrupt termination of co- financing at project closure without follow-up arrangements can damage trust relationships with implementing partners and significantly compromise the sustainability of project achievements. 1Agricultural output per hectare and individual crop yields remain well below those of regional peers. Moreover, there is variation across the agroecological zones within the country: the southern forest zone generally has higher productivity than the northern savannah zone. Cash crops are also more concentrated in the former; cocoa, rubber, and oil palm form the basis of the forest zoneâ€™s diversified production mix, whereas cotton and cashew are the driving cash crops in the savannah zone (World Bank 2013, 2021a). 2An interprofessional organization (IPO) is an agricultural value chain organization composed of agribusiness companies and farmers associations that aims to develop the industry while 29 ensuring a fair distribution of value addition along the chain. IPOs also implement development programs with their own funding from voluntary member contributions (World Bank 2013). An agricultural council is an institution established by the government to play a regulatory role within the sector (World Bank 2013). As the Agriculture Sector Support Project (PSAC) explicitly aimed for project ownership by the private sector, the project was implemented by IPOs in the oil palm, rubber, and cotton sectors (by, respectively, the Oil Palm Interprofessional Association [AIPH], the Association of Natural Rubber Professionals of CÃ´te dâ€™Ivoire [APROMAC], and the Cotton Interprofessional Organization [INTERCOTON]). In the cashew and cocoa sectors, however, the PSAC was implemented by the sector councils (the Cotton and Cashew Council [CCA] and the Coffee and Cocoa Council [CCC], respectively), as IPOs did not exist within these sectors at project design. Project implementation was further supported by the National Rural Support Agency, the National Agricultural Research Center, and the Interprofessional Fund for Agricultural Research and Advisory Servicesâ€”all three parastatal structures that play a key role in agricultural research and extension in CÃ´te dâ€™Ivoire. 3 The ordinance No. 2011-473 on agricultural IPOs is an ordinance issued by the government in December 2011 (CÃ´te dâ€™Ivoire 2011). It sets out the definitions, principles, and rules governing agricultural IPOs and specifies their missions, the internal modalities of representation, and the framework of collaboration with the institutions representing the government. It also specifies the criteria based on which an IPO is officially recognized and accredited. 4A total of 67.6 billion francs was disbursed by project closure: 26.8 billion francs by the International Development Association, 17.8 billion francs by the French Development Agency, 17.2 billion francs by IPOs and councils, 4.2 billion francs by beneficiaries, and 1.9 billion francs by the treasury (CÃ´te dâ€™Ivoire MINADER 2018). 5For example, in the rubber sector, although farmers had to cover 40â€“50 percent of improved seedling costs under traditional subsidy schemes, the PSAC reduced this to 5 percent, according to Project Performance Assessment Report interviewees. 6Although several respondents reported on dispersion of activities, indicating that the three pathways may have been implemented in isolation at times or in specific places. 7The criteria for official recognition and accreditation of IPOs are specified in the 2011 ordinance on IPOs (see endnote 3; CÃ´te dâ€™Ivoire 2011). The Association of Natural Rubber Professionals of CÃ´te dâ€™Ivoire was accredited in February 2020. The cashew IPO was accredited in October 2022. 8The websites of the Network of Farmers Organizations and Agricultural Producers of West Africa (https://roppa-afrique.org) and Inter-rÃ©seaux (https://inter-reseaux.org/en)â€”the organizations that have been following the evolution of farmer organizations in the subregion for yearsâ€”show a multitude of examples. 9The lack of success of traditional approaches has also been demonstrated in the last decades by a vast evidence base from Inter-rÃ©seaux, the International Fund for Agricultural Development, the Food and Agriculture Organization of the United Nations, and other institutions and was further confirmed by the interviews conducted for the Project Performance Assessment Report. 30 10As an example, postharvest losses for cereal grains in CÃ´te dâ€™Ivoire are estimated at 11â€“ 18 percent (APHLIS 2021). 11The Gender Innovation Lab also conducted a detailed study on the impacts of productivity interventions in the rubber sector (Donald, Goldstein, and Rouanet 2022). 12Although the National Agricultural Research Center distributed planting material for a total area of 3,936 hectares in 2015â€“16, this figure increased to 6,705 hectares in 2016â€“17 because of the increase in coated seed production capacity (National Agricultural Research Center data). 13Similar concerns on insufficient production base knowledgeâ€”with associated price and processing capacity risksâ€”were also raised for the rubber sector. 14For example, for the roads rehabilitated by the PSAC (1,740 kilometers in total), only 5 percent received (or will receive) maintenance by the Road Management Agency (AGEROUTE) every year between 2019 and 2024. 15 See endnote 7. 16Although it should be acknowledged that a significant number of training sessions allowed for specific improvements of certain problems. 17 See endnote 9. 18For example, the final implementation report notes that for the rubber sector, the expectations of the directors of the cooperative societies mainly concern the purchase price of rubber from producers, which is too low to finance operations and services to be provided to members. In fact, this is a problem common to all sectors. 19Transparency issues, and the differentiation between producers and agro-industries and exporters in particular, are a recurring and widely recognized problem of IPOs in CÃ´te dâ€™Ivoire and the subregion. 20The cashew factory in Yamoussoukro could play such a role if its cost structure is made completely transparent and widely disseminated within the IPO. 21 For example, the final implementation report states that according to field surveys, more than 70 percent of producers lack the financial means to employ a laborer to maintain their rubber fields, whereas less than 40 percent of producers implement the knowledge gained from their training because of a lack of means. 22This contingency is also demonstrated by the political and institutional limitations for operationalizing the national strategy for road maintenance and rehabilitation (see paragraph 2.30). 31
P119328 | COTE D'IVOIRE - Emergency Basic Education Support Project - GPEF Grant | Western and Central Africa | Cote d'Ivoire | IDA | FCS | Human Development | Education | RETF | IPF | 2012 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/420781560447178668/text/Cote-dIvoire-CI-Emerg-Basic-Edu-Supp-Proj-BESP.txt | http://documents.worldbank.org/curated/en/420781560447178668/pdf/Cote-dIvoire-CI-Emerg-Basic-Edu-Supp-Proj-BESP.pdf | The ICR identifieda set of insightfullessons that include reference to the value ofan auditofpre-service teacher training for effective reform assuming the audit covers all stages of the process of teacherdevelopment from recruitment through training and certification; the efficiencies that can be achieved through decentralized(regional) teacher training; and how,in the case of an emergency project, it is important that project design has activitiesthat areready to go. The ICR suggestedthe projectwas partially successful in this regard,inthat it identified and pursued the most urgent priorities, though it did not anticipate, for example, that the school feedingprogram would run into difficulty.The projectwas also overly ambitious in expecting the realization of a consolidateddata system under an emergency project (although progress was made in upgrading data collection and reporting for the educationsector).And finally,the ICR finds that the community approach used bythe projectwas cost-effectiveinbuilding local schools and may have a positive impact on social cohesion (lowered construction costs while also engaging thecommunity, andimproved capacity ofschool-based management committeesthat put the training provided by theprojectto practical use).In addition, IEG identifies the followinglessons:Realism is always important, but particularly so in a post-conflict situation where expectationsmay be high and where stability may be dependent on demonstrating coherence and early results, serving, forexample,tosupport the legitimacy of government. In this instance, theproject was unrealistic in its ambitiongiven the context and the short implementation period in question. Ultimately, certain core activities were dropped, and theproject ran over its projected three-year cycle by 23 months.A lack of urgency and proactivity inaddressing issues arising in project managementcan haveundesirableknock on effects. In this instance known issueswith theproject implementation unitwere left unchanged until relevant personnel ran out of contract. Thisresultedin weak monitoring for much of the project.Once the picture became clearer with new personnel insitu,alate restructuring was effected to enable completion of project activities. That said,executing change solate in the process is less than ideal.
P119355 | Decentralized Service Delivery Program II | Western and Central Africa | Sierra Leone | IDA | FCS | Human Development | Social Protection & Jobs | IDA | IPF | 2012 | 2018 | 2019 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/632771557239364310/text/Sierra-Leone-SL-Decentralized-Service-Delivery-Prog-2.txt | http://documents.worldbank.org/curated/en/632771557239364310/pdf/Sierra-Leone-SL-Decentralized-Service-Delivery-Prog-2.pdf | The ICR (p. 31-32) provided useful lessons learned, adapted here byIEG: Developing data-sharing mechanisms through an integrated Management Information System(MIS) across different government agencies, Local Council (LCs), and service providers to better understand, promote, and manageresources and local services is critical. In this project, gathering and disseminating datato informdecision making was challenging between the different levels such as line ministries, decentralization units, LCs, and WardCommittees. The ME system lacked a shared standardized platform with parameters that provided alerts when information was notdelivered in a timely manner. Coordination and knowledge exchange between LCs are critical for building capacityin all entities. In this project, LCs benefitted from LC officers rotating from one LC to another. Moreintensive and formal fostering of peer-to-peer learning, mentoring between officers, and exchange visits of best-performingofficers/managers between LCs would be useful to ensure capacity building in all LCs. A decentralized governmentframework can reduce social tensions in post-conflict countries with deep geographic and ethno-political divisions. InSierra Leone, the decentralization process introduced services closer to beneficiaries, increased citizen engagement and ownershipoflocal agendas, and mitigated tensions between ethnic groups, fosteringcooperation among these groups.
P119357 | China Energy Efficiency Promotion in Industry | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Energy & Extractives | GEF | IPF | 2011 | 2016 | 2017 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/318261497975478825/text/ICRR-Disclosable-P119357-06-20-2017-1497975470344.txt | http://documents.worldbank.org/curated/en/318261497975478825/pdf/ICRR-Disclosable-P119357-06-20-2017-1497975470344.pdf | Technical Assistance programs that include in depth policy studies need strongGovernment commitment beyond the support of a singular champion. In this project momentum was lostduring the period that the primary supporter was transferred to another department. Training programs should bedesigned to provide sufficient time to allow participants to absorb the presented material. In this project, trainingprogram participants thought that five days was too short a time to allow for full absorption of the large volume of materialpresented.
P119380 | GEF - Africa - 2nd phase fish. (GBissau) | Western and Central Africa | Western and Central Africa |  |  | Sustainable Development | Environment, Natural Resources & the Blue Economy | IDA | IPF | 2011 | 2018 | 2019 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/826271532532404451/text/Western-Africa-Africa-2nd-phase-fish-GEF-GBissau.txt | http://documents.worldbank.org/curated/en/826271532532404451/pdf/Western-Africa-Africa-2nd-phase-fish-GEF-GBissau.pdf | The ICR provided comprehensive lessons. The most important follow with some modification oflanguage:Partnering with relevant regional organizations helps better coordination and projectimplementation and hence leads to better project results impacting regions as a whole. The Sub-Regional FisheriesCommission (CSRP) played an important role through facilitating dialogue between participating fisheries ministries under theRegional Steering Committee (RSC) and enhancing data transparency across the sub-region through the dashboard. CSRP was also in agood position to guide the government on particularly procurement and ME, and facilitate collaboration with other countries inareas of mutual interest, such as stock assessments and surveillance, as it had the experience from the first set of WARFPprojects. .Reforming the fisheries sector to generate sustainable benefits requires an incrementalapproach and long -term commitment. As demonstrated by this project, APL/Series of operations type of instrument may bebeneficial. Reforms involving changing behavior to control resource use and reduce illegal actions in a context of limitedgovernment budgets and capacities requires considerable allocations of time and capacity building actions, particularly in initialphase. Second phase projects can focus around countries priority investments with emphasis on further strengtheninginstitutions to ensure that fisheries management functions are sustainable, and engaging communities in fisheriesmanagement.IEG developed the following lesson:To achieve an objective such increased valueaddition from local fisheries sector, many constraints need to be addressed and it is not realistic to include such an objectivefor projects dealing mainly with institutional capacity development. The gaps in Guinea Bissau were small/artisanal fisheriesindustry in the country was lacking and funds needed to be mobilized from the private sector to create a local industry; also locallanding and marketing infrastructure, particularly a functioning port was missing. These activities were beyond the scope of theproject. Therefore, the project activities were weakly linked to this objective, yet the PDO was not revised during the course ofimplementation.
P119432 | Lesotho Smallholder Agriculture Development Project | Eastern and Southern Africa | Lesotho | IDA | Non-FCS | Sustainable Development | Agriculture and Food | IDA | IPF | 2012 | 2020 | 2021 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/645881622156470237/text/Lesotho-LS-Smallholder-Agriculture-Dev-Project.txt | http://documents.worldbank.org/curated/en/645881622156470237/pdf/Lesotho-LS-Smallholder-Agriculture-Dev-Project.pdf | The ICR (p.28-29) included the following lessons learned, which were adapted by IEG: When a project aimsto promote commercial agriculture, a mix of activities including investments and institutional support is critical. Thisproject was able to change the mindset of smallholder agricultural producers but the ICR did not provide any evidence to back upthose claims.. Assessing critical conditions during project preparation is important for ensuring the achievementof intended outcomes. In this project, the importance of farmers having incentives to work together in groups was notsufficiently identified during project preparation. As a result, AIP sub-projects were unsustainable and performedpoorly. The provision of financial capital needs to be combined with building resilience of agribusinesses toclimate shocks. While this project did not address harsh weather andclimatic events in its project design, it wassufficiently flexible to introduce climate-smart agriculture practices and activities during project implementation resulting inlong-term climate resilience by project beneficiaries.
P119471 | PNG Road Maintenance and Rehabilitation Project II | East Asia and Pacific | Papua New Guinea | Blend | FCS | Infrastructure | Transport | IDA | IPF | 2011 | 2023 | 2024 | ICRR | >=100 million | Moderately Satisfactory | Moderately Unsatisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/099053024213014633/text/P11947112d82520891b0951d263d77dd5a7.txt | http://documents.worldbank.org/curated/en/099053024213014633/pdf/P11947112d82520891b0951d263d77dd5a7.pdf | This review has drawn three lessons based on the information in the ICR.Systematic data collection on roadconnectivity and building capacity for the implementation of Roads Assets Management System (RAMS) is critical in providing asufficient evidence base of the achievement of desired outcomes. The project highlighted the value of systematic datacollection on road connectivity outcomes to guide future investments and policy reforms. Data collection throughout projectimplementation was insufficient. Initially planned socio-economic surveys were not conducted, missing a crucial chance tounderstand the projects impact on various populations and to refine the ME design. Utilizing additional data sourcescould have enriched the evidence base, offering clearer insights into the specific needs of diverse beneficiary groups, such aswomen, children, the disabled, and the elderly. Building capacity for the implementation of RAMS could provide a sufficientevidence base to assess the development impact of road rehabilitation projects especially so in an FCVcontext.In an FCV context, regular technical assistance in financial management, procurement, and safeguards canprevent lengthy project implementation delays. The projects experience reaffirms the necessity of ongoing capacitybuilding in fiduciary and safeguards areas in an FCV context, beyond delivering sporadic training sessions and issuingcommunication when faced with non-compliance. Encountered delays due to procurement issues and capacity gaps highlight the need forconsistent and strategic support for addressing implementation challenges and achieving project objectives effectively and forbuilding long-term capacity as envisaged in the World Bank Environmental and Social Framework, and World Bank guidelines forprocurement and financial management.Insufficient preparation of civil works designs and employers projectmanager (EPM) bidding documents at appraisal can adversely affect project implementation and cause significant delays in an FCVcontext. The preparation of the civil works designs and EPM bidding documents were deferred to the implementation stage,which resulted in no support from the EPM at the initial phases of the project implementation and resulted in a two-year delay. Inan FCV context, project preparation should take into account high-capacity risks. As the ICR (p.24) notes, additional preparationsupport and longer lead times for engineering studies and work designs could improve the effective and efficient implementation ofroad projects in FCV countries. Such support may include initiating the procurement process of an EPM and preparing civil works andbidding documents under an ongoing project and including flexible terms in EPM contracts to extend EPM support to other projectsduring their preparation phase.
P119654 | GEF Guangdong Green Freight Demonstration Project | East Asia and Pacific | China | IBRD | Non-FCS | Infrastructure | Transport | GEF | IPF | 2011 | 2016 | 2018 | ICRR | Less than 10 million | Moderately Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/158691507667920347/text/ICRR-Disclosable-P119654-10-10-2017-1507667913822.txt | http://documents.worldbank.org/curated/en/158691507667920347/pdf/ICRR-Disclosable-P119654-10-10-2017-1507667913822.pdf | The lessons proposed by the ICR are:Project Development Objective indicators should be clear, measurable andflexible: the indicators should be flexible and enable the adaptation to changes in circumstances especially indemonstration projects as such. In addition, all the data necessary for measuring the indicators should be available and valuesproperly assessed.Strong government leadership is important for successful implementation of projects:The project was considered to be of high priority by the provincial government and sufficient time was spent communicating betweenthe line departments for smooth coordinationThe design of a demonstration project should be flexible andinclude a strong outreach component: It is important in the case of demonstration projects, that extensive outreach activities areembedded within the project design. In the case of this project, since the project activities were not rigidly defined atappraisal, it offered flexibility to adopt a phased approach and, add new activities to further enhance the projectdesign.Careful consideration need to be given to local context such that even though all the technologiesimplemented during the project were verified by the US EPA and some of them had proven to be energy efficient in the Guangzhoudemonstration pilot project, some of the technologies proved to be less energy efficient in the context of the Guangdong.
P119662 | Burkina Faso - Bagre Growth Pole Project | Western and Central Africa | Burkina Faso | IDA | FCS | Equitable Growth, Finance and Institutions | Finance, Competitiveness and Innovation | IDA | IPF | 2011 | 2021 | 2023 | ICRR | >=100 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/099145008122229242/text/P1196620f533550850a5d003b256142f6fe.txt | http://documents.worldbank.org/curated/en/099145008122229242/pdf/P1196620f533550850a5d003b256142f6fe.pdf | Three lessons are drawn from the ICR (pages 35-37) with some adaptation. Inlow-capacity environments,design should be simple and include a realistic set of components and activities implementable by the Project Coordination Unit.The scope of the Project was complex and included several activities such as irrigation canal construction, electric powerinfrastructure, roads, investment promotion and capacity building, and agriculture productivity. As a result,there waslimited progress during Project implementation. This wasevident from the fact that only 28 percent of the funds weredisbursed more than four yearsafter Project effectiveness. In addition,low implementation capacity andsignificantshortcomings in the technical aspects of irrigation networksfurther exacerbated the situation. Forprojects that involve construction of irrigation canals, it is crucial to allocate sufficientpreparation time to ensure thatthe design of the irrigation canalsis based onmore recent or updateddiagnostics and technical/topographicstudies.In the case of this Project, the design of the irrigation canalswas based on outdatedtechnical/topographic studies, resulting in significant cost overruns during implementation. Thereby,affecting theimplementation ofactivitiescrucial for access to markets and electricity to achieve private sector investments inagriculture. For World Bank projects that focus on achieving private sector-led groupcollaborationwiththeIFC teams, it is crucial to build the capacity of investment promotion agencies in the country in order toattractand retain investors. In the case of this Project, the weakcoordination between the implementing agency and the investmentpromotion agency was strengthenedafter theProject team collaborated with IFC, which helped in building the capacity ofthe investment promotion agency. A matching grant scheme should clearly identify the needs of the beneficiaries atthe time of the project design, especially in countries that lack funding from financial institutions to firms. As part of theAdditional Financing, a parallel cash transfers program was implemented without a requirement for an own contribution frombeneficiaries. This is because during implementation the Project team found that the original requirement for an own contributionof 20 percent under the matching grants program was unrealistic for many SMEs.
P119690 | PUBLIC EMPLOYMENT FOR SUSTAINABLE AGRICULTURE AND WATER MANAGEMENT PROJECT | Europe and Central Asia | Tajikistan | IDA | Non-FCS | Sustainable Development | Water | RETF | IPF | 2010 | 2012 | 2014 | ICRR | Less than 10 million | Satisfactory | Moderately Satisfactory | Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/654651474577843419/text/000180307-20141201034326.txt | http://documents.worldbank.org/curated/en/654651474577843419/pdf/000180307-20141201034326.pdf | For emergency-type projects designed to primarily deliver quick turn around results, a one year implementation period may be appropriate, but this arrangement often does not allow for adequate lead time for proper preparatory social, technical, administrative and M&E activities. In public works programs supporting agricultural work rehabilitation or construction, a one year project is challenged by the need to split implementation across cropping seasons and by the inability to monitor and report on results after a full off-season period, thus limiting the ability of the client to learn how to improve aspects of the approach. It is possible to overcome social barriers and include women in project activities that are typically viewed as geared more towards men Women can benefit from public works projects by applying a few simple additional incentive measures including by allocating smaller-scale works with lower lifting and throwing requirements to women, arranging for women to be assigned to work sites that are close to their homes and in certain societal contexts, by assigning separate work fronts and locations.
P119694 | PA Metro Water and Sanitation Improvement Project | Latin America and Caribbean | Panama | IBRD | Non-FCS | Sustainable Development | Water | IBRD | IPF | 2010 | 2017 | 2018 | ICRR | >=10 million & <25 million | Unsatisfactory | Moderately Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/836141530307002857/text/Panama-PA-Metro-Water-and-Sanitation-Improvemen.txt | http://documents.worldbank.org/curated/en/836141530307002857/pdf/Panama-PA-Metro-Water-and-Sanitation-Improvemen.pdf | The ICR listed four lessons from the project ofwhich three were regarded by IEG aspotentially relevant to otherBank-assisted projects.The threelessons in the ICRare re-arranged and presentedbelow with someeditingto emphasize their applicability beyond this project.1. High risk, transformationalengagements with new clients require a willingness totake major steps to ensure the efficiency of existingimplementing institutionsover a significant period of time. This projecttook aconservative, pilot project approach to strengthening an existing institution for project implementation assumingthatthe existing institution would mature and that a follow-up operation would be able toharness the existingimplementing institution for a future more ambitious project. However, in this case IDAANs existing institutional weaknesswere chronic and not correctedwhich limited the effectiveness of the currentproject, negatively affecting the will ofthe GoP and the World Bank Country Management Unit (CMU) to support a follow-up projectand ultimately, threatening thesustainability of this projects outcome.2. The establishment of PIU to work withtheinstitution responsible for the overall implementation of the project will not work unless clear lines of responsibilityand accountability are established among the two. In this project, thePIUs lack ofautonomy from IDAAN resulted in limited implementation and significant delays. IDAANs structural weaknessesessentially became project weaknesses which the PIU could not resolve.3. PBCs enable low capacityutilities to test innovative methods to transform the way of doingbusiness. For utilities that are fully occupied maintaining the status quo,the performance based contracts (PBC) model offers a solution to test and lay the groundwork for new methods of doing business. Inthe case of IDAAN, the PBC offered a method to not only rapidly improve service continuity in Colon but also shift the focus withinthe Colon Business Unit from infrastructure development to service enhancement. The PBC provided the Colon Unit with a concreteexample of service-focused operation as well as the tools necessary (including key network data and a sectorization strategy) toleapfrog into this way of doing business.IEGs reviewof the project situationsuggests thefollowing additional lesson: Timely and close monitoring and supervision of the project and honest reportingto Bank management on the projects performance would pre-empt issues facing a project as they arise.This is an oft repeated lessonbut one that is particularly relevantfor this project given the successive over-rating oftheprojects performance by a series of Bank supervision missions.
P119736 | Enhancing Agricultural Productivity Project | Eastern and Southern Africa | Kenya | Blend | Non-FCS | Sustainable Development | Agriculture and Food | RETF | IPF | 2010 | 2012 | 2015 | ICRR | >=25 million & <50 million | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Moderately Unsatisfactory | Substantial | http://documents.worldbank.org/curated/en/698041474942417513/text/000180307-20150108101148.txt | http://documents.worldbank.org/curated/en/698041474942417513/pdf/000180307-20150108101148.pdf | The following lessons are taken from the ICR with some adaptation of language:In-country systems, such as input distribution, agricultural credit, and assistance in crop diversification, need to be able to support emergency interventions adequately. Although the Bank has developed special procedures that allow quick preparation and disbursements for emergency projects, this project was constrained by delays in disbursements, procurement, and other procedures and processes in the country. More attention to appraising capacity, and supporting capacity building, increases the chances of success.Fiduciary management capacity of the implementing agencies at both the national and lower levels needs to be adequate. In this case, fiduciary management at the national and district levels was not strong enough. There is need to provide adequately for capacity building of national and district level staff and to encourage computerization and simplification of record-keeping.Inclusion of some critical post-harvest interventions could improve project outcomes. Whenever production-enhancing technologies are promoted, it is advisable to also support other off-farm activities such as storage and marketing.Incorporation of cross-sectoral and international experience, especially in input voucher schemes, is likely to reduce implementation difficulties. For example, support for more than one season, in line with common practice in other countries, could be considered, as could location-specific input packages and voucher pricing.
P119737 | Electricity Sector Development Project | Eastern and Southern Africa | Uganda | IDA | Non-FCS | Infrastructure | Energy & Extractives | IDA | IPF | 2011 | 2019 | 2021 | ICRR | >=50 million & <100 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Substantial | http://documents.worldbank.org/curated/en/923801624992466959/text/Uganda-UG-Electricity-Sector-Development-Proj.txt | http://documents.worldbank.org/curated/en/923801624992466959/pdf/Uganda-UG-Electricity-Sector-Development-Proj.pdf | IEG derives the following lessons, based on the ICR:1. In estimating the benefits of increased access underelectric power projects, estimates of the number ofproject beneficiaries should include both primary as wellassecondary beneficiaries, and a clear methodology should be provided in regard to estimation of the beneficiaries. Inthe case of the project, there was no clear methodology during project design to estimate the number of secondary beneficiaries.This led the ICR team to make assumptions that may not have been fully consistent with those used in the appraisalanalysis.2. Projects that include social electrification aspects should also include design and implementation ofappropriate social economic assessments to assess the benefits of the adopted initiatives in improving the well-being andlivelihoods of the direct beneficiaries. In the case of the project, the lack of such surveysand assessments prevented anassessment of the impact of the project interventions as perceived by the targeted beneficiaries.3. Appointment of keyproject implementation staff in the PMUs, supported by specialized consultants as appropriate, should be ensuredat earlystages of project preparation, including through project preparation advances where possible. The project was adversely affected bysignificant capacity related constraints, including delays in appointment of key managerial and technical staff, and specializedconsultants in the project PMUs which resulted in substantial delays in the earlier parts of projectimplementation.4.. Social safeguard activities, particularly for Category A projects as in the case of thisproject, require substantial lead times for preparation. This includes mechanisms for compensation of Project AffectedPersons (PAPs) and land title mutation. In the case of the project, resettlement related issuesweredetermined to be themain reason which delayed the schedule for activation of the Kawanda-Masaka transmission line by nearly threeyears.5.In the case of the project, effectiveness was significantly delayed in part by the need for Parliamentaryapprovals. In such cases, preparation of the necessary documents and internalapprovals by the GoU agenciesconcernedneed tobe assessed at an early stage, and required actions on the part of the Government counterparts beappropriately structured as conditions of appraisal or negotiations.
P119781 | MA-Solid Waste Sector DPL2 | Middle East and North Africa | Morocco | IBRD | Non-FCS | Infrastructure | Urban, Resilience and Land | IBRD | DPF | 2011 | 2012 | 2014 | ICRR | >=100 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory |  | http://documents.worldbank.org/curated/en/561341474628273003/text/000020051-20140625220252.txt | http://documents.worldbank.org/curated/en/561341474628273003/pdf/000020051-20140625220252.pdf | The following lessons are taken from the ICR with some adaptation of language:(i) Sector-wise DPLs can be feasible and successful. While the Bank has used extensively DPLs to support structural reforms mainly to strengthen the management of public resources, this operation illustrates that this kind of lending can be used effectively to promote change is line ministries involved in the supply of public goods.(ii) Ownership by the government is key to making progress in a new and difficult area of reforms, especially when using DPL operations. Sustained coordination among state entities is central to producing results. When the Government is in the driverâ€™s seat, the Bank can easily integrate in its country strategy government-initiated reforms and donors can support a transformative reform agenda.(iii) Launching an operation aimed at delivering services to citizens at central and regional levels can lead the government to scale up coordination and lay the foundations for improved financial management for local governments, and better handling of the relationship with private sector service providers. (iv) Sustainability in any sector requires strong investment in building internal technical capacity. Performance of this operation relied on the training program in new areas initiated by the Government, and supported by the donor community.
P119805 | EG - Sanitation | Middle East and North Africa | Egypt, Arab Republic of | IBRD | Non-FCS | Sustainable Development | Water | RETF | IPF | 2010 | 2016 | 2017 | ICRR | Less than 10 million | Unsatisfactory | Unsatisfactory | Unsatisfactory | Unsatisfactory | Modest | http://documents.worldbank.org/curated/en/481161493305200745/text/ICRR-Disclosable-P119805-04-27-2017-1493305193204.txt | http://documents.worldbank.org/curated/en/481161493305200745/pdf/ICRR-Disclosable-P119805-04-27-2017-1493305193204.pdf | This Review finds the following lessons: Infrastructure projects may result in more positive outcomes ifsub-projects are given sufficient time to finish the works that have already started. The ISSIP 1 experience demonstratedthat had the project been given an extension, the works that started under Phase 2 as well as the capacity development activitiesthat were still ongoing, could have been finished. The Banks decision to close the project based on an overall portfolioreview did not consider the fact that many bottlenecks were resolved and the project started to disburse rapidly during the lastyear. Although the unfinished works were left to be completed through government funding, the availability of this funding was notcertain. Linked with the earlier lesson, follow on projects need to be designed afterthe earlier project design is tested sufficiently, so that its lessons can bebrought into the next Project. Beforecompleting ISSIP I, ISSIP II project came into effect with similar design bottlenecks. Thus, two problematic projects were createdback to back without any opportunity for improvement.The ICR provided comprehensive lessons. Themost important follow with some modification of language: Complex project design jeopardizesproject outcomes. ISSIP 1 addressed rural sanitation as both a means to improved water quality and an objective in its ownright. Additionally, the project design included multiple innovations, and required high levels of coordination across governmentagencies and funding from multiple stakeholders. Institutional arrangements were weak involving two institutions without clearsplit of responsibility and ownership arrangements. A borrower unfamiliar with World Bank procedures working in a challengingsector is unlikely to be able to effectively carry out such a complex project. A simpler project design, and better institutionalarrangements adapted to the prevailing context would have had a greater likelihood ofsuccess. Technical assistance and policy reform are critical for sustainability ofinfrastructure projects and require stable funding. ISSIP 1 provides additional evidence that infrastructure cannot beleveraged effectively outside of a supportive policy framework and institutional environment. Although the PAD identified criticalcapacity and policy constraints, funding issues and delays in launching Components 2 and 3 pushed TA to the final years of theproject. Given the long time frame required for policy reform and capacity building, this TA would have been significantly moreeffective if it began well before construction started. Had the TA been funded through the IBRD loan or a global trust fund, thisdelay may have been avoided. Citizen engagement is a necessary step that needs to beintegrated in infrastructure projects. By engaging with communities earlier in the project, several problems could havebeen avoided, including the delays in land acquisition, villages blocking construction, and unwillingness to pay connection fees.Difficulties in identifying ownership, negotiating land prices, and navigating clearances from multiple ministries resulted in longdelays in land acquisition. Addressing land acquisition prior to effectiveness could have reduced the risk of implementationdelays. Until the JSDF-funded consultant began work, there was minimal outreach to communities impacted by the project. Morecommunity consultation could have helped build greater support for the project, which was initially opposed by somevillages. Effective procurement requires an understanding of contractor capacity, aswell as sufficient contract supervision. Many of the contractors eligible to bid on the sub-projects lacked the financialresources and technical ability to effectively carry out the complex technologies specified in the bidding documents. This resultedin multiple rounds of bidding, major cost overruns, and delays in beginning construction. Moreover, awarding two or three contractsto the same small contractors constrained their financial capacity to complete the respective contracts, which resulted insignificant delay in completion of their contracts. Prequalification introduced to exclude low-capacity contractors for Phase IIschemes resulted in bid prices significantly higher than the cost estimate, leading to rebidding, which significantly delayed theprocurement process. Also poor or lack of contract supervision during Phase I of the project, also caused delays as well as poorquality works in some cases.
P119815 | CF-Health System Support Project | Western and Central Africa | Central African Republic | IDA | FCS | Human Development | Health, Nutrition & Population | IDA | IPF | 2012 | 2019 | 2021 | ICRR | >=25 million & <50 million | Moderately Satisfactory | Satisfactory | Satisfactory | Satisfactory | Substantial | http://documents.worldbank.org/curated/en/899911624280323235/text/Central-African-Republic-CF-Health-System-Support-Project-FY12.txt | http://documents.worldbank.org/curated/en/899911624280323235/pdf/Central-African-Republic-CF-Health-System-Support-Project-FY12.pdf | The ICR (p0. 34-35) offered several useful lessons, including the following adapted by IEG: Contracting with NGOsto deliver servicescan facilitate achievement of results in fragility, conflict and violence (FCV) settings. In this case,the NGO contracting model used in the health sector allowedfor provision ofa flexible, well-prioritized package ofservices even in an FCV situation. NGOs had the independence to deliver services in a deteriorating security context and were ableto forge alliances and agreements with local leaders and adapt to specific local conditions in ways that would not have beenpossible for government employees. Investment in monitoring and evaluation can lead to sound data and analysis andstrengthen national health information systems. In this case, the reinforcement of the ME and health information systems, aswell asthe strengthening routine data collection and management (annual statistical reports and data produced by PBF), led togood quality data for tracking results. It also reinforced confidenceamong stakeholders and was used as a tool foraccountability. Also, contracting independent experts and an impartial agency to undertakevarious data analyses andpublications ensured high-quality and reliable data and knowledge management. Different mechanisms of health financingneed to be integrated with tangible investment from domestic resources. In this case, although the project was adequately costed,the governments declaration ofa policy of free health care for mothers and childrenin 2018 did not consider astreamlined and integrated PBF. Hence, a free care services approach created potentially contrary incentives for healthproviders. Partnerships and solid national leadership are essential ingredients of success.In this case, someinstitutional stability at the ministerial level, decision-maker level, and the anchor of the PBF technical unit contributed to theadoption of results-based approaches by the government and other stakeholders. Pragmatic adaptation in PBF designand implementation is essential.Proactive adjustments to the program to address changing contexts and needscontributed to ensuring appropriate and context-specific support to target populations. In this case, adaptation ofthePBFdesign to the requirements of the different health zones provided resources to deliver free services to the poorestpopulations.
P119825 | Mongolia Multi-Sectoral Technical Assistance Project | East Asia and Pacific | Mongolia | IBRD | Non-FCS | Equitable Growth, Finance and Institutions | Macroeconomics, Trade and Investment | IDA | IPF | 2010 | 2017 | 2018 | ICRR | >=10 million & <25 million | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Moderately Satisfactory | Modest | http://documents.worldbank.org/curated/en/626151529334287644/text/ICRR0021216-REVISED-PUBLIC-P119825.txt | http://documents.worldbank.org/curated/en/626151529334287644/pdf/ICRR0021216-REVISED-PUBLIC-P119825.pdf | Lessons are drawn from the ICR:There should be a balance between the demands of the reformand related capacity building. Designers, both in government and the Bank, should consider the environment, weighingthe capacity building requiredwith the challenges that the reform poses - are the two compatible over the time horizon of theproject. In the case of Mongolia, the project closed with severalreforms still underway, especially in the fiscal andfinancial sectors. Some of the reforms were quite complex, stretchingthe capacity of implementing agencies, andrequiring more time for completion than had been anticipated.The results framework should beas explicit at possible. There is a needto ensure that indicators are as specific as possible, and thatorganizational responsibilities are defined. Indicators should be within the control of the project, measurable, and quantitativewhere possible to allow determination of attribution of a particular project.PMT should beconsidered in anenvironment of chronic poverty or where systemic shocks are prevalent.The choice of targetingmechanism is crucial in countries where the needs are great relative to funding, or where budget pressure can besignificant. Mongolia experienced a significant improvement in social welfare targeting with theintroduction of PMT, generating significant efficiency gains and safety net program savings. This underscores the experiencein other countries that have adopted PMT, either on its own or with complementary targetingmechanisms.Another lesson drawn by IEG:Similar fiscal and/orfinancial reforms can be relevant whether in crisis or non-crisis situations. When external circumstances change,the borrower and the Bank should assess how muchconditions have changed, and whether, or how much,key outputs andoutcomes need to change. The fiscal and financial reforms introduced under the project had been designed during the globalfinancial crisis of 2009-2010, and were heavily weighted towards activitiesthat were meant to address the immediate effectsof the crisis on budget management. However, once the crisis was over, focus shifted to longer term challenges ofsustainability and resilience in the key subject areas-fiscal, social, and financial. Still, the results chain was largely maintained (short-term measures were likely also to strengthen the economy in the longer term), andstrategieswere adjusted only whennecessary, including redefining someactivities and indicators in a longer-termperspective.